Dev 318c

r.02/22/95

STATE OF WISCONSIN

DEPARTMENT OF TRANSPORTATION

BUREAU OF AERONAUTICS

MODIFICATION OF CONSTRUCTION STANDARDS

MODIFICATION NO.:  1 	PROJECT NO.:3-55-    -24

AIRPORT:  Dane County Regional Airport                     	CONTRACT NO.:  1

PROJECT DESCRIPTION:  Construct PCC rwy 3/21

REQUEST FOR MODIFICATION OF CONSTRUCTION STANDARDS:  This request for modification of construction standards to accommodate unique local conditions is as follows:

A.	List of standards requiring modification and a discussion of why the standard cannot be met:

The WI Bureau of Aeronautics' position is that the Fuel Cost Adjustment clause isn't a true escalator clause as defined in FAA Order 5100.38A, 821.c, because both parties to the contract have the same risk factor, that is to say, the contract price that the contractor receives can go either "up" or "down".

The FCA clause was originally utilized during the 1970's oil embargoes. At the request of the Wisconsin Road Builder's Association, it was re-introduced in 1990 by WisDOT Division of Highways to protect the contractor and owner against the fluctuating fuel cost due to the Persian Gulf Crisis. Currently, WisDOT Bureau of Highway Construction (formly Division of Highways) limits the use the FCA clause to grading projects over 100,000 C.Y.  The Bureau of Aeronautics proposes to follow the same policy on the Dane County Reigional Airport AIP 24 project since it has 1.5 million C.Y. of grading.

The FCA clause provides a mechanism for changing the contract price when the Current Fuel Index (CFI) to base Fuel Index (BFI) ratio falls outside the 0.85 and 1.15 limits.

The CFI is adjusted by the Department of Transportation each month.  The CFI is the price of No. 2 fuel oil, as reported in U.S. Oil Week, using the first issue dated that month.  The CFI is the average of prices quoted for Green Bay, Madison, Milwaukee and Minneapolis.

The BFI is adjusted every October.  It is calculated by using CFI values averaged over the past year.

Unusual specific circumstances for Dane County Regional Airport AIP 24 project are as follows:

• This project has an estimated cost of $21,000,000.00.  Of which, $ 2,500,000.00 is for the 1.5 million cubic yards of grading.  Grading accounts for 40 % of the construction time, and may extend into the next construction season.  Fuel is a major component of a grading contractors expense and fluctuating fuel cost can add a higher factor of risk.

• Two construction seasons are need to finish this project, so bidders are going to be adding extra fuel costs into the contract to ensure that they are covered unless there is a FCA.

• The Dane County Regional Airport project will be Let March 1997.  Currently, fuel prices are climbing and may not accordingly reflect the price of fuel during the construction season.

• Contractors bidding on State administered projects expect our contracts to be the same as the Bureau of Highway Construction.

The above can be resolved by using a FCA.  With fluctuating fuel cost and length of project contractors will put together reasonable bids if they know that they will be reimbursed if fuel costs go up.

B.	A description of the proposed modification:

We are requesting the use of the Fuel Cost Adjustment clause on the Dane County Regional Airport AIP 24 project.

C.	A discussion of how proposed modification will provide an economical and feasible alternative to the FAA standard:

•	The Bureau can re-coup money when fuel prices decrease.

•	Bidders would perceive less risk resulting in better bid prices for the owner.

•	The Middle East has been and remains unstable.

•	Home heating fuel prices can drive diesel fuel costs.  Refineries produce more gasoline during the summer and more home heating fuel in the winter.  If the winter is long and cold, shortages and high prices for diesel fuel can occur.  If the winter is short and warm, diesel fuel prices can go down, resulting in savings to the projects utilizing the FCA clause.

D.	A discussion of how proposed modification was successfully used under similar conditions:

The Federal Highway Administration re-authorized the use of the Fuel Cost Adjustment clause in 1990 (see exhibit A).

FCA methods are used by other states (see exhibit B).

ASSURANCE STATEMENT:

This is to assure that the proposed modification of construction standards will provide a product that will meet or exceed FAA standards for acceptance and that the finished product will perform for its intended design life based on historical data:

ENGINEER

Name of Firm

by:                                                    Title                      Date

BUREAU OF AERONAUTICS

Date

C. M. Gelderman, P.E.

Specifications Development Chief

Date

Keith F. Richardson, P.E., Chief

Airport Engineering Section

APPROVAL:

FEDERAL AVIATION ADMINISTRATION

Approved by:                                            Title                        Date

Note:  A copy of this approval will be attached to either the "SPONSOR CERTIFICATION FOR PROJECT PLANS AND SPECIFICATIONS" or "SPONSOR CERTIFICATION FOR CONSTRUCTION PROJECT FINAL ACCEPTANCE" as appropriate.

AIP#

Contract #