## TaskList
DRAFT 9/22/2016 | [7 empty] | Resurfac-ing | Recondi-tioning | Pavement Replace-ment | Reconstruction |  | Expansion |  | Bridge Rehabili-tation | Bridge Replacement |  |  |  | Effort Needed (hrs) |  |  | Architect |  |  |  |  | Civil Engineer |  |  |  |  | Construction Manager |  |  |  |  | Electrical Engineer |  |  |  |  | Environmental Engineer |  |  |  |  | Geotechnical Engineer |  |  |  |  | GIS Professional |  |  |  |  | Landscape Architect |  |  |  |  | Mechanical Engineer |  |  |  |  | Planner |  |  |  |  | Structural Engineer |  |  |  |  | Surveyor |  |  |  |  | Traffic Engineer |  |  |  |  | CADD Technician |  |  | Civil Engineering Technician |  |  | Field Technician |  |  | GIS Technician |  |  | Mechanical Engineering Technician |  |  | Envrionmental Specialist | Admin Assistant | Exec Assistant | Marketing Assist | Marketing Manager | Marketing Director | Graphic Designer | Historian/ Archaeologist |  | Scientist | Hydrogeologist | Real Estate Agent |  | Licensed Asbestos Inspector | Asbestos Management Planner | Asbestos Project Designer | Asbestos Supervisor | Asbestos Worker | Geospatial Specialist | Region Communications Manager | Region Railroad Coordinator (RRC) | Equal Rights Officer | Geospatial Specialist
Outline | Activity Group | Activity Name | Activity Code | Activity Task | Activity Task Description | Guidance | Ohio Task | RESURF | RECOND | PVRPLA | RECST | BRNEW | RECSTE | BRNEW | BRRHB | BRELIM | BRRPLE | BRRPL | Units | Low | Medium | High | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Project | Project Manager | Dept Manager | Principal | Instrument Person | Technician | Crew Chief | Project Surveyor/ Survey coordinator | Dept Manager | Entry | Project | Project Manager | Dept Manager | Principal | Entry | Mid | Senior | Entry | Mid | Senior | Entry | Mid | Senior | Entry | Mid | Senior | Entry | Mid | Senior | [7 empty] | Project | Senior |  |  | Senior | Advanced | [9 empty] | Entry | Senior | Advanced | Manager | CO Railroad Coordinator
1 | Project Management
1.1 |  | Scope, Schedule and Change Management (8/24/16)
1.1.1 |  |  | 886 | Develop Project Scope (7/28/16)
1.1.1.1 |  |  |  | 886 | Includes activities directly related to scope development
1.1.1.2 |  |  |  | 886.1 | Develop and review project concept definition |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 4 | 12 | [7 empty] | 1-4-12
1.1.1.3 |  |  |  | 886.2 | Define purpose and need |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 4 | 12 | [7 empty] | 1-4-12
1.1.1.4 |  |  |  | 886.3 | Define study area and logical termini |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 4 | 12 | [7 empty] | 1-4-12
1.1.1.5 |  |  |  | 886.4 | Conduct field review |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 16 | [5 empty] | 1-4-8 |  | 1-4-8
1.1.1.6 |  |  |  | 886.5 | Identify and define design deficiencies |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 4 | 12 | 24 | [7 empty] | 4-12-24
1.1.1.7 |  |  |  | 886.6 | Identify design issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 8 | 16 | 36 | [5 empty] | 4-8-10 |  | 4-8-26
1.1.1.8 |  |  |  | 886.7 | Identify geotechnical issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 24 | [7 empty] | 1-4-12 | [19 empty] | 1-4-12
1.1.1.9 |  |  |  | 886.8 | Identify utility issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 4 | 12 | [7 empty] | 1-4-12
1.1.1.10 |  |  |  | 886.9 | Identify railroad issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 4 | 12 | [7 empty] | 1-4-12
1.1.1.11 |  |  |  | 886.1 | Identify environmental issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 16 | [7 empty] | 1-4-12
1.1.1.12 |  |  |  | 886.11 | Identify storm water/drainage issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 24 | [7 empty] | 2-8-24
1.1.1.13 |  |  |  | 886.12 | Identify traffic issues (capacity-safety/crash) |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 4 | 12 | 24 | [7 empty] | 2-6-12 | [54 empty] | 2-6-12
1.1.1.14 |  |  |  | 886.13 | Identify real estate issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 16 | [7 empty] | 2-8-16
1.1.1.15 |  |  |  | 886.14 | Identify airport issues |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 16 | [7 empty] | 2-8-16
1.1.1.16 |  |  |  | 886.15 | Determine street lighting and traffic signal needs |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 4 | 8 | 24 | [7 empty] | 4-8-24
1.1.1.17 |  |  |  | 886.16 | Determine ITS needs for project |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 4 | 12 | 24 | [7 empty] | 4-12-24
1.1.1.18 |  |  |  | 886.17 | Determine structure needs |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 24 | [7 empty] | 1-4-12 | [44 empty] | 1-4-12
1.1.1.19 |  |  |  | 886.18 | Determine complete streets needs for project (bike-pedestrian-transit) |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 16 | [7 empty] | 2-4-8 | [39 empty] | 0-4-8
1.1.1.20 |  |  |  | 886.19 | Determine public involvement needs (PIM-Hearings) |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 4 | 12 | [7 empty] | 1-4-12
1.1.1.21 |  |  |  | 886.2 | Determine aesthetic needs (landscaping-streetscaping-CSS) |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 0 | 0 | 0 | [7 empty] | 0-0-0
1.1.1.22 |  |  |  | 886.21 | Determine construction traffic control needs (staged or detour) |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 24 | [7 empty] | 2-8-24
1.1.1.23 |  |  |  | 886.22 | Determine local particiaptation |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 8 | 24 | [7 empty] | 2-8-24
1.1.2 |  |  | 887 | Manage Project Scope and Schedule (8/24/16)
1.1.2.1 |  |  |  | 887 | Includes processes for establishing the policies, procedures, and documentation needed to plan, develop, manage, execute, and control the project schedule and scope.
1.1.2.2 |  |  |  | 887.1 | Create project schedule |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 2 | 6 | 12 | [7 empty] | 2-6-12
1.1.2.3 |  |  |  | 887.2 | Update and Track project progress/percent complete |  |  | x | x | x | x | x | x | x | x | x | x | x | monthly | 1 | 2 | 4 | [7 empty] | 1-2-4
1.1.2.4 |  |  |  | 887.3 | Prepare/attend scope and schedule meetings / conference calls |  |  | x | x | x | x | x | x | x | x | x | x | x | monthly | 1 | 2 | 4 | [6 empty] | 1-2-4
1.1.2.5 |  |  |  | 887.4 | 30% Plan review meeting |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40 | [6 empty] | 4-15-20 | 4-15-20
1.1.2.6 |  |  |  | 887.5 | 60% Plan review meeting |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40 | [6 empty] | 4-15-20 | 4-15-20
1.1.2.7 |  |  |  | 887.6 | 90% Plan review meeting |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40 | [6 empty] | 4-15-20 | 4-15-20
1.1.2.8 |  |  |  | 887.7 | Develop and maintain financial plan | [5 empty] | x | x | x | x |  |  |  |  | project | 8 | 16 | 24 | [7 empty] | 8-16-24
1.1.3 |  |  | 884 | Manage Change (7/28/16)
1.1.3.1 |  |  |  | 884 | Includes processes for identifying, monitoring, and controlling change on a project.
1.1.3.2 |  |  |  | 884.1 | Change management process and plan |  |  | X | X | X | X | X | X | X | X | X | X | X | Project | 24 | 120 | 200 | [5 empty] | 4-8-12 | 4-8-12 | 16-92-152 | 0-8-16 | 0-4-8
1.1.3.3 |  |  |  | 884.2 | Program Re-balance |  |  | X | X | X | X | X | X | X | X | X | X | X | RE-BALANCE | 8 | 24 | 40 | [6 empty] | 0-4-8 | 8-18-28 | 0-2-4
1.1.3.4 |  |  |  | 884.3 | Coordinate construction timing with other projects & completion restrictions |  |  | X | X | X | X | X | X | X | X | X | X | X | CHANGE | 4 | 10 | 40 | [7 empty] | 4-10-40
1.1.3.5 |  |  |  | 884.4 | Monitor funding resources (local-state-federal) |  |  | X | X | X | X | X | X | X | X | X | X | X | CHANGE | 2 | 16 | 30 | [47 empty] | 2-16-30
1.1.3.6 |  |  |  | 884.5 | Analyze and review contractor change order and claims request |  |  | X | X | X | X | X | X | X | X | X | X | X | CHANGE | 4 | 8 | 35 | [6 empty] | 0-4-9 | 4-4-24 | 0-0-2
1.2 |  | Budget, Cost, Procurement andResource Management (9/1/16)
1.2.1 |  |  | 888 | Manage Project Delivery
1.2.1.1 |  |  |  | 888 | Includes management of project engineering delivery costs.
1.2.1.2 |  |  |  | 888.1 | Develop and manage project human resources | [13 empty] | Hours/project | 10 | 40 | 80 | [7 empty] | 10-36-70 | 0-4-10
1.2.1.3 |  |  |  | 888.2 | Develop initial project delivery cost estimate | [13 empty] | Hours/project | 8 | 12 | 16 | [7 empty] | 8-12-16
1.2.1.4 |  |  |  | 888.3 | Review and develop revised and final project delivery cost estimate | [13 empty] | Hours/project | 3 | 10 | 20 | [7 empty] | 3-10-20
1.2.2 |  |  | 883 | Manage Consultant Selection (7/28/16)
1.2.2.1 |  |  |  | 883 | Involves the process of selecting a consultant based on federal and state requirements (ex. QBS). Includes time to document all selection activities.
1.2.2.2 |  |  |  | 883.1 | Prepare solicitation package |  |  | x | x | x | x | x | x | x | x | x | x | x | package | 16 | 24 | 40 | [7 empty] | 16-24-40 | [73 empty] | .5-.5-1
1.2.2.3 |  |  |  | 883.2 | Review solicitation package |  |  | x | x | x | x | x | x | x | x | x | x | x | package | 2 | 2 | 4 | [5 empty] | .5-.5-1 | .5-.5-1 | .5-.5-1 | [73 empty] | .5-.5-1
1.2.2.4 |  |  |  | 883.3 | Review NOIs |  |  | x | x | x | x | x | x | x | x | x | x | x | per NOI per person | 0.5 | 0.5 | 1 | [7 empty] | 16-20-30
1.2.2.5 |  |  |  | 883.4 | Conduct and evaluate consultant interviews |  |  | x | x | x | x | x | x | x | x | x | x | x | per interview per person |  |  | 5 | [7 empty] | 0-0-20 | 0-0-5
1.2.2.6 |  |  |  | 883.5 | Make final selection |  |  | x | x | x | x | x | x | x | x | x | x | x | package/ person | 2 | 4 | 6 | [7 empty] | 1-2-3 | 1-2-3
1.2.2.7 |  |  |  | 883.6 | Review final selection |  |  | x | x | x | x | x | x | x | x | x | x | x | package | 2.5 | 2.5 | 4.5 | [5 empty] | .5-.5-1 |  | .5-.5-1 | .5-.5-1 | .5-.5-.5 | [71 empty] | .5-.5-1
1.2.2.8 |  |  |  | 883.7 | Prepare/attend consultant scoping meeting |  |  | x | x | x | x | x | x | x | x | x | x | x | person | 2 | 6 | 8 | [7 empty] | 2-6-8
1.2.2.9 |  |  |  | 883.8 | Negotiate contract |  |  | x | x | x | x | x | x | x | x | x | x | x | contract | 16 | 30 | 60 | [7 empty] | 16-30-60
1.2.2.10 |  |  |  | 883.9 | Prepare and review consultant contract documents |  |  | x | x | x | x | x | x | x | x | x | x | x | contract | 6 | 10 | 16 | [7 empty] | 1-2-3 | [73 empty] | 2-4-5
1.2.3 |  |  | 773 | Manage Consultant Contract (9/1/16)
1.2.3.1 |  |  |  | 773 | Includes activities to determine and manage the scope of the consultant contract(s), negotiation, consultant management oversight, and consultant contract administration oversight. |  |  | x | x | x | x | x | x | x | x | x | x | x
1.2.3.2 |  |  |  | 773.1 | Prepare consultant invoice and supporting documents |  |  | X | X | X | X | X | X | X | X | X | X | X | invoice | 4 | 6 | 12 | [7 empty] | 3-5-8 | 0-0-2 | [72 empty] | 1-1-2
1.2.3.3 |  |  |  | 773.2 | Review consultant invoices |  |  | X | X | X | X | X | X | X | X | X | X | X | invoice | 1 | 3 | 5 | [7 empty] | 0.5-1.5-2.5 | [73 empty] | 0.5-1.5-2.5
1.2.3.4 |  |  |  | 773.3 | Review and negotiate contract amendments |  |  | X | X | X | X | X | X | X | X | X | X | X | amendment | 2 | 8 | 16 | [7 empty] | 2-8-12 | 0-0-4
1.2.3.5 |  |  |  | 773.4 | Review errors and omissions/disputes |  |  | X | X | X | X | X | X | X | X | X | X | X | issue | 2 | 4 | 12 | [7 empty] | 2-4-8 | 0-0-4
1.2.3.6 |  |  |  | 773.5 | Setting up CARS roles - Region administrator |  |  | X | X | X | X | X | X | X | X | X | X | X | contract | 1 | 1 | 1 | [81 empty] | 1-1-1
1.2.3.7 |  |  |  | 773.6 | Evaluate performance of contract |  |  | X | X | X | X | X | X | X | X | X | X | X | contract | 1 | 2 | 3 | [7 empty] | 1-2-3
1.2.4 |  |  | 889 | Manage Project Non-Delivery Cost (7/12/16)
1.2.4.1 |  |  |  | 889 | Includes management of payments made to contractor(s) for the construction project.
1.2.4.2 |  |  |  | 889.1 | Manage and review construction project cost estimate |  |  | X | X | X | X | X | X | X | X | X | X | X | Hours per estimate | 10 | 20 | 40 | [5 empty] | 2-6-10 | 4-8-22 | 4-6-8
1.2.4.3 |  |  |  | 889.2 | Manage and review R/W costs |  |  | X | X | X | X | X | X | X | X | X | X | X | Hours per parcel | 4 | 10 | 24 | [6 empty] | 2-6-14 | 2-4-10
1.2.4.4 |  |  |  | 889.3 | Mange and review Utility costs |  |  | X | X | X | X | X | X | X | X | X | X | X | Hours per utility company | 4 | 10 | 24 | [6 empty] | 2-6-14 | 2-4-10
1.2.4.5 |  |  |  | 889.4 | Mange and review "supplied by WisDOT" costs (signals, cabinets, etc.) |  |  | X | X | X | X | X | X | X | X | X | X | X | Hours per location | 4 | 10 | 24 | [6 empty] | 2-6-14 | 2-4-10
1.2.5 |  |  | 892 | Manage Procurement of Goods and/or Services
1.2.5.1 |  |  |  | 892 | Includes activities related to purchase and acquisition of other goods & non-engineering services needed for a project.
1.2.5.2 |  |  |  | 892.1 | Purchasing
1.2.5.2.1 |  |  |  | 892.1.1 | Develop and manage simplified bid | http://dotnet/purchasing/guidelines.htm |  | x | x | x | x | x | x | x | x | x | x | x | per quote | 8 | 10 | 12 | [6 empty] | 8-10-12
1.2.5.2.2 |  |  |  | 892.1.2 | Develop and manage RFB/RFI | http://dotnet/purchasing/guidelines.htm |  | x | x | x | x | x | x | x | x | x | x | x | per purchase item | 24 | 40 | 80 | [6 empty] | 24-40-80
1.2.5.2.3 |  |  |  | 892.1.3 | Develop and manage RFP | http://dotnet/purchasing/guidelines.htm |  | x | x | x | x | x | x | x | x | x | x | x | per purchase item | 24 | 40 | 80 | [6 empty] | 24-40-80
1.2.5.2.4 |  |  |  | 892.1.4 | Develop and manage Sole Source purchase | http://dotnet/purchasing/guidelines.htm |  | x | x | x | x | x | x | x | x | x | x | x | per purchase item | 8 | 10 | 12 | [6 empty] | 8-10-12
1.2.5.3 |  |  |  | 892.2 | Coordinate "supply by WisDOT" orders |  |  | x | x | x | x | x | x | x | x | x | x | x | per project | 8 | 10 | 12 | [6 empty] | 8-10-12
1.2.5.4 |  |  |  | 892.3 | Pay invoices for purchased items |  |  | x | x | x | x | x | x | x | x | x | x | x | per invoice | 8 | 8 | 8 | [6 empty] | 8-8-8
1.3 |  | Quality and Risk Management (8/24/16)
1.3.1 |  |  | 890 | Manage Project Quality (8/24/16)
1.3.1.1 |  |  |  | 890 | Includes activities directly related to managing and monitoring quality outcomes.
1.3.1.2 |  |  |  | 890.1 | Prepare/attend oversight meetings |  |  | x | x | x | x | x | x | x | x | x | x | x | per project | 2 | 4 | 8 | [7 empty] | 2-4-8
1.3.1.3 |  |  |  | 890.2 | Review project documentation/reports/plans and documents
1.3.1.3.1 |  |  |  | 890.2.1 | Review 30% project plan |  |  | x | x | x | x | x | x | x | x | x | x | x | Project | 76 | 144 | 212 | [6 empty] | 60/112/164 | 16/32/48
1.3.1.3.2 |  |  |  | 890.2.2 | Review 60% project plan |  |  | x | x | x | x | x | x | x | x | x | x | x | Project | 144 | 212 | 280 | [6 empty] | 112/164/216 | 32/48/64
1.3.1.3.3 |  |  |  | 890.2.3 | Review 90% project plan |  |  | x | x | x | x | x | x | x | x | x | x | x | Project | 212 | 280 | 348 | [6 empty] | 164/216/268 | 48/64/80
1.3.1.3.2 |  |  |  | 890.2.4 | Review special provisions and supporting documents |  |  | x | x | x | x | x | x | x | x | x | x | x | Project | 46 | 92 | 160 | [6 empty] | 16/32/48 | 30/60/112
1.3.1.4 |  |  |  | 890.3 | Specialty - Technical construction expert | [5 empty] | x | x | x | x |  | x | x | x | Project | * | * | *
1.3.1.5 |  |  |  | 890.4 | Specialty - Value engineering | [5 empty] | x | x | x | x |  | x | x | x | Project | * | * | *
1.3.2 |  |  | 894 | Manage Project Risks (8/24/16)
1.3.2.1 |  |  |  | 894 | Includes activities related to risk planning, identification, analysis, and response/control.
1.3.2.2 |  |  |  | 894.1 | Develop and define risk register |  |  | x | x | x | x | x | x | x | x | x | x | x | Per Project Per Person | 2 | 4 | 8 | [7 empty] | 2-4-8
1.3.2.3 |  |  |  | 894.2 | Evaluate risk |  |  | x | x | x | x | x | x | x | x | x | x | x | Per Project Per Person | 2 | 4 | 8 | [7 empty] | 2-4-8
1.3.2.4 |  |  |  | 894.3 | Prepare risk management plan |  |  | x | x | x | x | x | x | x | x | x | x | x | Per Project Per Person | 2 | 4 | 8 | [7 empty] | 2-4-8
1.3.2.5 |  |  |  | 894.4 | Manage risk |  |  | x | x | x | x | x | x | x | x | x | x | x | Month | 1 | 2 | 3 | [7 empty] | 1-2-3
1.4 |  | Communication and Stakeholder Management (7/12/16)
1.4.1 |  |  | 743 | Manage Project Stakeholders (7/12/16)
1.4.1.1 |  |  |  | 743 | Includes engagement of both internal and external stakeholders in project information activities such as public involvement meetings, hearings, operational planning, scoping, local officials meetings, neighborhood, open house, community, property owner, or other contacts and response to inquiries. Includes preparation, planning, invites, logs, attendance, summary, certification for all pre-meetings, actual meeting, and post meeting review.
1.4.1.2 |  |  |  | 743.1 | Respond to inquiries (public, government, media) |  |  | x | x | x | x | x | x | x | x | x | x | x | Monthly | 1 | 4 | 8 | [6 empty] | 0-0-2 | 2-4-6
1.4.1.3 |  |  |  | 743.2 | Develop public involvement plan |  |  | x | x | x | x | x | x | x | x | x | x | x | Project | 4 | 16 | 40 | [6 empty] | 1-8-8 | 3-8-32
1.4.1.4 |  |  |  | 743.3 | Prepare and maintain public involvement log/comment database |  |  | x | x | x | x | x | x | x | x | x | x | x | Monthly | 1 | 2 | 4 | [6 empty] | 0-1-2 | 1-1-2
1.4.1.5 |  |  |  | 743.4 | Notify property owners |  |  | x | x | x | x | x | x | x | x | x | x | x | Project | 3 | 5 | 9 | [6 empty] | 1-2-4 | [24 empty] | 1-2-4 | [49 empty] | 1-1-1
1.4.1.6 |  |  |  | 743.5 | Pre-meeting (PIM PAC TAC)
1.4.1.6.1 |  |  |  | 743.5.1 | Develop and maintain contact mailing list (email/address) |  |  | x | x | x | x | x | x | x | x | x | x | x | Project | 4 | 12 | 24 | [6 empty] | 1-8-16 | 1-1-3 | [23 empty] | 1-2-4 | [49 empty] | 1-1-1
1.4.1.6.2 |  |  |  | 743.5.2 | Plan pre-meeting and meeting arrangements |  |  | x | x | x | x | x | x | x | x | x | x | x | Meeting | 2 | 2 | 2 | [6 empty] | 1-1-1 | [74 empty] | 1-1-1
1.4.1.6.3 |  |  |  | 743.5.3 | Prepare/print/mail/email meeting invites |  |  | x | x | x | x | x | x | x | x | x | x | x | Meeting | 4 | 6 | 8 | [6 empty] | 2-3-4 | 1-1-1 | [73 empty] | 1-2-3
1.4.1.6.4 |  |  |  | 743.5.4 | Prepare news release |  |  | x | x | x | x | x | x | x | x | x | x | x | Meeting | 2 | 2 | 2 | [6 empty] | 1-1-1 | [74 empty] | 1-1-1
1.4.1.6.5 |  |  |  | 743.5.5 | Prepare/Review/Revise meeting materials (handouts, exhibits, presentation) PIM, PAC, TAC |  |  | x | x | x | x | x | x | x | x | x | x | x | Meeting | 32 | 50 | 80 | [5 empty] | 4-6-12 | 16-20-32 | 4-16-24 | [58 empty] | 6-6-10 | [14 empty] | 2-2-2
1.4.1.6.6 |  |  |  | 743.5.6 | Attend PIM, PAC, TAC |  |  | x | x | x | x | x | x | x | x | x | x | x | Meeting | 4 | 8 | 15 | [5 empty] | 0-0-5 | 0-4-5 | 4-4-5
1.4.1.6.7 |  |  |  | 743.5.7 | Prepare/Review PIM, PAC, TAC meeting minutes or summary |  |  | x | x | x | x | x | x | x | x | x | x | x | Meeting | 2 | 4 | 6 | [5 empty] | 0-0-2 | 1-3-3 | 1-1-1
1.4.1.7 |  |  |  | 743.6 | General Project Meeting
1.4.1.7.1 |  |  |  | 743.6.1 | Prepare for, attend, and summarize meeting |  |  | x | x | x | x | x | x | x | x | x | x | x | Meeting | 5 | 8 | 10 | [5 empty] | 0-0-2 | 1-4-4 | 4-4-4
1.4.2 |  |  | 893 | Manage Project Communications (7/12/16)
1.4.2.1 |  |  |  | 893 | Includes development and implementation of communications plans and tools based on stakeholder information needs and project requirements. |  |  | X | X | X | X | X | X | X | X | X | X | X
1.4.2.2 |  |  |  | 893.1 | Develop/Prepare materials, update and manage project website |  |  | X | X | X | X | X | X | X |  | X | X | X | Hours per exhibit | 2 | 2 | 4 | [5 empty] | 1-0-0 | 1-1-2 | 0-1-2
1.4.2.3 |  |  |  | 893.2 | Develop project pamphlet/brochure/newsletter |  |  | X | X | X | X | X | X | X |  | X | X | X | Hours per exhibit | 2 | 4 | 8 | [5 empty] | 1-1-1 | 1-2-4 | 0-0-2 | [73 empty] | 0-1-1
1.4.2.4 |  |  |  | 893.3 | Manage news media releases and social media |  |  | X | X | X | X | X | X | X |  | X | X | X | Hours per response | 1 | 1 | 3 | [5 empty] | 0-0-1 | 1-1-1 | 0-0-1
1.4.2.5 |  |  |  | 893.4 | Regional communication manager coordination |  |  | X | X | X | X | X | X | X | X | X | X | X | Hours per interaction | 1 | 1 | 3 | [5 empty] | 0-0-1 | 1-1-1 | 0-0-1
1.4.3 |  |  | 266 | Coordinate Local Public Agency (LPA)
1.4.3.1 |  |  |  | 266 | Includes activities related to Local Public Agency coordination.
1.4.3.2 |  |  |  | 266.1 | Develop SMA |  |  | X | X | X | X | X | X | X | X | X | X | X | MUNICIPALITY | 4 | 40 | 500
1.4.3.3 |  |  |  | 266.2 | LPA coordination |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 6 | 20 | 160
2 | Preliminary and Final Design
2.1 |  | Pavement and Soils Design
2.1.1 |  |  | 208 | Design Soils & Earthwork (9/1/16)
|  |  |  | Design Soils & Earthwork |  |  |  | X | X | X | X | X | X | X | X | X | X | X | LF | 75 | 100 | 150
2.1.1.1 |  |  |  | 208 | Includes design activities related to earthwork and soils engineering.
2.1.1.2 |  |  |  | 208.1 | Roadway
2.1.1.2.1 |  |  |  | 208.1.1 | Review available geotechnical and design information |  |  | X | X | X | X | X | X | X | X | X | X | X | Project | 4 | 8 | 12 | [26 empty] | 4/8/10 | 0/0/2
2.1.1.2.2 |  |  |  | 208.1.2 | Develop subsurface exploration program |  |  | X | X | X | X | X | X | X | X | X | X | X | Project | 4 | 8 | 12 | [26 empty] | 4/8/10 | 0/0/2
2.1.1.2.3 |  |  |  | 208.1.3 | Complete subsurface investigation |  |  | X | X | X | X | X | X | X | X | X | X | X | 1 Mile Urban or 2.5 Mile Rural | 12 | 20 | 30 | [69 empty] | 6/10/15 |  |  | 6/10/15
2.1.1.2.4 |  |  |  | 208.1.4 | Additional Resources for Subsurface Investigation |  |  | X | X | X | X | X | X | X | X | X | X | X | 1 Mile Urban or 2.5 Mile Rural | 4 | 25 | 40 | [26 empty] | 0/5/5 | 0/0/5 | [41 empty] | 2/10/15 |  |  | 2/10/15
2.1.1.2.5 |  |  |  | 208.1.5 | Perform laboratory testing and evaluate results |  |  | X | X | X | X | X | X | X | X | X | X | X | 1 Mile Urban or 2.5 Mile Rural | 4 | 8 | 13 | [26 empty] | 1/2/3 | [42 empty] | 3/6/10
2.1.1.2.6 |  |  |  | 208.1.6 | Complete analysis and develop soils report |  |  | X | X | X | X | X | X | X | X | X | X | X | 1 Mile Urban or 2.5 Mile Rural | 12 | 16 | 20 | [26 empty] | 8/10/12 | 4/6/8
2.1.1.3 |  |  |  | 208.2 | Structures
2.1.1.3.1 |  |  |  | 208.2.1 | Review available geotechnical and design information | [8 empty] | X | X | X | X | X | Structure | 2 | 4 | 8 | [26 empty] | 2/4/6 | 0/0/2
2.1.1.3.2 |  |  |  | 208.2.2 | Develop subsurface exploration program | [8 empty] | X | X |  | X | X | Structure | 2 | 4 | 6 | [26 empty] | 2/4/4 | 0/0/2
2.1.1.3.3 |  |  |  | 208.2.3 | Complete subsurface investigation | [8 empty] | X | X |  | X | X | Structure | 30 | 40 | 120 | [69 empty] | 15/20/60 |  |  | 15/20/60
2.1.1.3.4 |  |  |  | 208.2.4 | Additional Resources for Subsurface Investigation | [8 empty] | X | X |  | X | X | Structure | 4 | 40 | 120 | [26 empty] | 0/4/8 | 0/0/8 | 0/0/4 | [40 empty] | 2/18/50 |  |  | 2/18/50
2.1.1.3.5 |  |  |  | 208.2.5 | Perform laboratory testing and evaluate results | [8 empty] | X | X |  | X | X | Structure | 5 | 12 | 20 | [26 empty] | 2/4/5 | 1/2/3 | 0/1/2 | [40 empty] | 2/5/10
2.1.1.3.6 |  |  |  | 208.2.6 | Complete analysis and develop soils report | [8 empty] | X | X |  | X | X | Structure | 20 | 40 | 60 | [26 empty] | 10/15/20 | 10/20/30 | 0/5/10
2.1.1.4 |  |  |  | 208.3 | Miscellaneous
2.1.1.4.1 |  |  |  | 208.3.1 | Review available geotechnical and design information |  |  |  |  | X | X | X | X | X |  | X | X | X | Feature | 4 | 8 | 24 | [26 empty] | 4/8/20 | 0/0/4
2.1.1.4.2 |  |  |  | 208.3.2 | Develop subsurface exploration program |  |  |  |  | X | X | X | X | X |  | X | X | X | Feature | 4 | 8 | 16 | [26 empty] | 4/8/12 | 0/0/4
2.1.1.4.3 |  |  |  | 208.3.3 | Complete subsurface investigation |  |  |  |  | X | X | X | X | X |  | X | X | X | Feature | 20 | 40 | 120 | [69 empty] | 10/20/60 |  |  | 10/20/60
2.1.1.4.4 |  |  |  | 208.3.4 | Additional Resources for Subsurface Investigation |  |  |  |  | X | X | X | X | X |  | X | X | X | Feature | 0 | 20 | 80 | [26 empty] | 0/4/15 | 0/0/5 | [41 empty] | 0/8/30 |  |  | 0/8/30
2.1.1.4.5 |  |  |  | 208.3.5 | Perform laboratory testing and evaluate results |  |  |  |  | X | X | X | X | X |  | X | X | X | Feature | 10 | 20 | 40 | [26 empty] | 2/4/6 | 0/2/4 | 0/2/4 | [40 empty] | 8/8/8 | 0/4/18
2.1.1.4.6 |  |  |  | 208.3.6 | Complete analysis and develop soils report |  |  |  |  | X | X | X | X | X |  | X | X | X | Feature | 10 | 20 | 45 | [26 empty] | 5/5/10 | 5/10/20 | 0/5/15
2.1.1.5 |  |  |  | 208.4 | Identify possible waste, borrow, and aggregate sources
2.1.1.6 |  |  |  | 208.5 | Analyze select material in subgrade
2.1.1.7 |  |  |  | 208.6 | Specialty - Subsurface exploration drilling and field operations/testing services
2.1.1.8 |  |  |  | 208.7 | Specialty - Geotechnical engineering
2.1.2 |  |  | 277 | Design Pavement Structure (6/21/16)
2.1.2.1 |  |  |  | 277 | Includes roadway site investigation; pavement design; and pavement design report. |  |  | X | X | X | X | X | X | X | X |  | X | X
2.1.2.2 |  |  |  | 277.1 | Conduct site investigation |  |  | X | X | X | X | X | X | X | X |  | X | X | project | 5 | 8 | 12 | [5 empty] | 0-0-0 | 4-6-8 | 0-0-0 | [64 empty] | 1-2-4
2.1.2.3 |  |  |  | 277.2 | Develop Preliminary Pavement Design Recommendation |  |  | X | X | X | X | X | X | X | X |  | X | X | project | 5 | 11 | 19 | [5 empty] | 0-0-0 | 4-8-14 | 0-1-1 | [64 empty] | 1-2-4
2.1.2.4 |  |  |  | 277.3 | Review information |  |  | X | X | X | X | X | X | X | X |  | X | X | project | 7 | 11 | 14 | [5 empty] | 0-0-0 | 5-10-10 | 0-0-0 | [64 empty] | 2-1-4
2.1.2.5 |  |  |  | 277.4 | Perform pavement structural calculations/evaluations |  |  | X | X | X | X | X | X | X | X |  | X | X | project | 6 | 12 | 42 | [5 empty] | 0-0-0 | 6-12-42 | 0-0-0 | [64 empty] | 0-0-0
2.1.2.6 |  |  |  | 277.5 | Perform LCCA calculations/evaluations |  |  | X | X | X | X | X | X | X | X |  | X | X | project | 0 | 12 | 20 | [5 empty] | 0-3-4 | 0-9-16 | 0-0-0 | [64 empty] | 0-0-0
2.1.2.7 |  |  |  | 277.6 | Prepare Draft and Final pavement design report |  |  | X | X | X | X | X | X | X | X |  | X | X | project | 9 | 18 | 37 | [5 empty] | 0-0-0 | 6-12-30 | 1-2-3 | [64 empty] | 2-4-4
2.1.2.8 |  |  |  | 277.7 | Specialty - FWD and GPR data collection and/or analysis | [5 empty] | X |  | X | [5 empty] | mile | 2 | 3 | 4
2.2 |  | Engineering and Plan Development (9/12/16)
2.2.1 |  |  | 268 | Develop and Manage Access Control (7/17/16)
2.2.1.1 |  |  |  | 268 | Determine development/access issues that need to be addressed on the project. | FDM Chapter 7
2.2.1.2 |  |  |  | 268.1 | Determine land development and access |  |  | x | x | x | x | x | x | x | x | x | x | x | mile | 2 | 4 | 8 | [5 empty] | 1-1-2 | 0-1-2 | [24 empty] | 0-1-2 | [37 empty] | 1-1-2
2.2.1.3 |  |  |  | 268.2 | Analyze access locations |  |  | x | x | x | x | x | x | x | x | x | x | x | mile | 4 | 8 | 16 | [6 empty] | 2-4-8 | 1-2-4 | [61 empty] | 1-2-4
2.2.1.4 |  |  |  | 268.3 | Identify access management recommendations (moving-removing-consolidation) |  |  | x | x | x | x | x | x | x | x | x | x | x | parcel | 2 | 16 | 40 | [6 empty] | 1-6-16 | 1-2-8 | [61 empty] | 0-6-12 | [11 empty] | 0-2-4
2.2.1.5 |  |  |  | 268.4 | Develop service road/emergency access feasibility |  |  | x | x | x | x | x | x | x | x | x | x | x | each | 8 | 40 | 80 | [5 empty] | 1-4-8 | 4-20-40 | 1-8-16 | [58 empty] | 0-4-8 |  |  | 2-4-8
2.2.1.6 |  |  |  | 268.5 | Develop multi-modal overpass/underpass justification |  |  | x | x | x | x | x | x | x | x | x | x | x | each | 16 | 80 | 160 | [5 empty] | 2-8-16 | 8-40-80 | 2-16-40 | 1-4-8 | [57 empty] | 1-4-8 |  |  | 2-8-8
2.2.1.7 |  |  |  | 268.6 | Specialty - Reasonable access studies
2.2.2 |  |  | 778 | Design Drainage (8/17/16)
2.2.2.1 |  |  |  | 778 | Includes activities related to existing and preliminary drainage structures/systems, existing drainage areas, and flow rates. | FDM Chapter 13; FDM 10-25/30/35/40. WisDOT Drainage SharePoint
2.2.2.2 |  |  |  | 778.1 | Identify existing drainage structures/systems, drainage patterns | FDM 13-5 |  | x | x | x | x | x | x | x | x | x | x | x | outfall | 2 | 4 | 6
2.2.2.3 |  |  |  | 778.2 | Identify existing land use, land cover, soil types, imperviousness (CN, C) | FDM 13-10 |  | x | x | x | x | x | x | x | x | x | x | x | acre | 1 | 2 | 4
2.2.2.4 |  |  |  | 778.3 | Establish existing drainage areas, time of concentration (tc) flow paths, flow rates | FDM 13-10 |  | x | x | x | x | x | x | x | x | x | x | x | outfall | 3 | 5 | 8
2.2.2.5 |  |  |  | 778.4 | Identify existing deficiencies/concerns |  |  | x | x | x | x | x | x | x | x | x | x | x | outfall | 1 | 3 | 6
2.2.2.6 |  |  |  | 778.5 | Prepare Existing Condition Drainage Area Exhibits |  |  | x | x | x | x | x | x | x | x | x | x | x | sheet | 4 | 6 | 8
2.2.2.7 |  |  |  | 778.6 | Establish and evaluate proposed drainage flow path/time of concentration/peak discharge | FDM 13-10 |  | x | x | x | x | x | x | x | x | x | x | x | outfall | 2 | 6 | 10
2.2.2.8 |  |  |  | 778.7 | Design storm sewer system, size pipes, and inlet spacing | FDM 13-25 |  | x | x | x | x | x | x | x | x | x | x | x | station | 2 | 4 | 8
2.2.2.9 |  |  |  | 778.8 | Design temporary drainage for staged construction |  |  | x | x | x | x | x | x | x | x | x | x | x | station | 1 | 2 | 3
2.2.2.10 |  |  |  | 778.9 | Analyze hydraulics and design culvert pipes | FDM 13-15 |  | x | x | x | x | x | x | x | x | x | x | x | each | 2 | 4 | 6
2.2.2.11 |  |  |  | 778.1 | Analyze hydraulics and design ditches | FDM 13-30 |  | x | x | x | x | x | x | x | x | x | x | x | mile
2.2.2.12 |  |  |  | 778.11 | Perform hydraulic analysis for navigable/floodzone bridges/culverts | FDM 13-20 |  | x | x | x | x | x | x | x | x | x | x | x | each
2.2.2.13 |  |  |  | 778.12 | Design channel relocation |  |  |  |  | x | x | x | x | x |  | x | x | x | mile
2.2.2.14 |  |  |  | 778.13 | Perform water quality calculations | FDM 10-25, 10-30 |  |  | x | x | x | x | x | x |  | x | x | x | outfall
2.2.2.15 |  |  |  | 778.14 | Design detention pond(s) and outlet control structure(s) | FDM 10-35 |  |  |  | x | x |  | x | [5 empty] | each
2.2.2.16 |  |  |  | 778.15 | Water Quality/Stormwater Control Measure Design | FDM 10-35 |  | x | x | x | x | x | x | x | x | x | x | x | each
2.2.2.17 |  |  |  | 778.16 | Stormwater-Drainage-Water Quality (WQ) Spreadsheets | FDM 10-25/30/35, 13-1-10 |  | x | x | x | x | x | x | x | x | x | x | x | outfall
2.2.2.18 |  |  |  | 778.17 | Prepare Proposed Drainage Area Exhibits |  |  | x | x | x | x | x | x | x | x | x | x | x | sheet
2.2.2.19 |  |  |  | 778.18 | Complete Stormwater Report | FDM 10-25 |  | x | x | x | x | x | x | x | x | x | x | x | outfall
2.2.2.20 |  |  |  | 778.19 | Complete Hydraulic Report | FDM 13-20 |  | x | x | x | x | x | x | x | x | x | x | x | each structure
2.2.3 |  |  | 768 | Design Erosion Control and Landscaping (7/15/16)
2.2.3.1 |  |  |  | 768 | Design erosion control and landscaping plan
2.2.3.2 |  |  |  | 768.1 | Analyze existing erosion control conditions | FDM 10-5, 10-10 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 16 | 32 | 48 | [5 empty] | 6-12-18 | 8-16-24 | 2-4-6
2.2.3.3 |  |  |  | 768.2 | Determine temporary erosion control features | FDM 10-5, 10-10 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 32 | 64 | 96 | [5 empty] | 16-32-48 | 12-24-36 | 4-8-12
2.2.3.4 |  |  |  | 768.3 | Determine permanent erosion control features | FDM 10-5, 10-10 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 32 | 64 | 96 | [5 empty] | 16-32-48 | 12-24-36 | 4-8-12
2.2.3.5 |  |  |  | 768.4 | Erosion control plan preparation | FDM 10-5, 10-15 |  | x | x | x | x | x | x | x | x | x | x | x | sheet | 8 | 16 | 32 | [6 empty] | 2-4-8 | 1-2-4 | [58 empty] | 5-10-20
2.2.3.6 |  |  |  | 768.5 | Review & define landscaping parameters | None |  |  |  | x | x | x | x | x |  |  |  |  | mile | 40 | 200 | 400 | [6 empty] | 3-12-24 | 1-8-16 | [27 empty] | 20-100-200 | 16-80-160
2.2.3.7 |  |  |  | 768.6 | Landscaping plan preparation | None |  |  |  | x | x | x | x | x |  |  |  |  | sheet | 8 | 20 | 40 | [6 empty] | 2-5-10 | 1-3-6 | [58 empty] | 5-12-24
2.2.4 |  |  | 776 | Design Geometrics and Details (9/12/16)
2.2.4.1 |  |  |  | 776 | Includes existing horizontal alignment; existing vertical profile; preliminary horizontal alignment; preliminary vertical profile; and preliminary intersection/interchange design and reports associated with these
2.2.4.2 |  |  |  | 776.1 | Determine and document design criteria |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 20 | 40 | [5 empty] | 2-6-15 | 4-10-20 | 2-4-5
2.2.4.3 |  |  |  | 776.2 | Analyze existing geometrics |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 6 | 12 | 30 | [5 empty] | 4-8-12 | 1-2-4 | 1-2-2 | [61 empty] | 4-8-12
2.2.4.4 |  |  |  | 776.3 | Develop preliminary horizontal alignments |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 2 | 6 | 12 | [5 empty] | 2-6-12 | 1-4-9 | 1-2-3
2.2.4.5 |  |  |  | 776.4 | Develop preliminary vertical alignments |  |  |  | X | X | X | X | X | X | X | X | X | X | mile | 8 | 24 | 48 | [5 empty] | 3-12-24 | 2-6-10 | 1-1-1 | [62 empty] | 1-7-13
2.2.4.6 |  |  |  | 776.5 | Develop preliminary intersection design |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 80 | 100 | [5 empty] | 12-24-30 | 10-22-26 | 2-3-4 | [53 empty] | 4-8-12 | 2-3-4 | [7 empty] | 10-20-24
2.2.4.7 |  |  |  | 776.6 | Develop preliminary interchange design | [5 empty] | X | X | X | X |  |  |  |  | each | 200 | 400 | 600
2.2.4.8 |  |  |  | 776.7 | Analyze and document geometric alternatives |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 80 | 120 | [5 empty] | 10-25-35 | 8-12-16 | 2-3-4 | [61 empty] | 10-20-35 | 10-20-30
2.2.4.9 |  |  |  | 776.8 | Finalize preliminary geometrics |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 100 | 200 | 400
2.2.4.10 |  |  |  | 776.9 | Create basic templates |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 8 | 24 | 40
2.2.4.11 |  |  |  | 776.1 | Develop preliminary surface models | [13 empty] | each
2.2.4.11.1 |  |  |  | 776.10.1 | Roadway |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 40 | 80 | 120
2.2.4.11.2 |  |  |  | 776.10.2 | Intersection |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 80 | 160 | 240
2.2.4.11.3 |  |  |  | 776.10.3 | Interchange |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 200 | 320 | 480
2.2.4.11.4 |  |  |  | 776.10.4 | Roundabout |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 100 | 180 | 280
2.2.4.11.5 |  |  |  | 776.10.5 | Construction staging |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 20 | 40 | 60
2.2.4.11.6 |  |  |  | 776.10.6 | Miscellaneous |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 20 | 40 | 60
2.2.4.12 |  |  |  | 776.11 | Perform airway/railway/highway clearance analysis |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 40 | 80 | [5 empty] | 6-10-20 | 5-8-10 | 1-2-4 | [61 empty] | 4-12-26 | 4-8-20
2.2.4.13 |  |  |  | 776.12 | Determine need for design exception |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 20 | 40 | [5 empty] | 3-6-14 | 4-6-8 | 1-2-4 | [61 empty] | 2-6-14
2.2.4.14 |  |  |  | 776.13 | Design aesthetic & Community Sensitive Design Features |  |  |  |  | X | X | X | X | X |  |  | X | X | project | 100 | 250 | 400 | 20-60-120 | 30-60-80 | 5-15-20 |  |  |  | 20-60-80 | 4-8-10 | 1-2-4 | [27 empty] | 18-41-76 | 2-4-10
2.2.4.15 |  |  |  | 776.14 | Beamguard calculations and geometrics |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 8 | 16 | 40 | [5 empty] | 2-4-12 | 1-2-8 | 1-2-3 | [61 empty] | 2-5-10 | 2-3-8
2.2.4.16 |  |  |  | 776.15 | Develop preliminary roadside design elements |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 40 | 80 | 160
2.2.4.17 |  |  |  | 776.16 | Update intersection geometrics and details |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 60 | 120 | 200
2.2.4.18 |  |  |  | 776.17 | Update interchange geometrics and details |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 300 | 500 | 800
2.2.4.19 |  |  |  | 776.18 | Develop final horizontal alignments (mainline and side road) |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 16 | 36 | 72
2.2.4.20 |  |  |  | 776.19 | Develop final vertical alignments (mainline, side road, and driveway) |  |  |  | X | X | X | X | X | X | X | X | X | X | mile | 24 | 54 | 96
2.2.4.21 |  |  |  | 776.2 | Develop final intersection design |  |  | X | X | X | X | X | X | X |  |  |  |  | each | 80 | 120 | 160
2.2.4.22 |  |  |  | 776.21 | Develop final interchange design | [5 empty] | X | X | X | X |  |  |  |  | each | 400 | 600 | 800
2.2.4.23 |  |  |  | 776.22 | Finalize geometrics |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 600 | 800 | 1000
2.2.4.24 |  |  |  | 776.23 | Refine and finalize surface models |  |  | X | X | X | X | X | X | X |  |  |  |  | project | 200 | 400 | 800
2.2.4.25 |  |  |  | 776.24 | Design Documentation
2.2.4.25.1 |  |  |  | 776.24.1 | Prepare and review interchange access justification report (IAJR) | FDM 7-45 |  |  |  |  | x |  | x | [5 empty] | Each report | 280 | 480 | 700 | [5 empty] | 64-112-152 | 80-140-200 | 24-48-72 | 4-8-16 | 2-4-8 | [21 empty] | 4-8-12 | [19 empty] | 4-8-16 | [13 empty] | 10-16-24 | 24-32-42 |  |  | 16-24-36 | 32-48-80 | [10 empty] | 16-32-42
2.2.4.25.2 |  |  |  | 776.24.2 | Develop and document Encroachment Report | FDM 12-1-20 |  | x | x | x | x | x | x | x | x | x | x | x | Each report | 16 | 32 | 60 | [5 empty] | 8-16-30 | 2-5-8 | 1-1-2 | [60 empty] | 4-8-16 | [12 empty] | 1-2-4
2.2.4.25.3 |  |  |  | 776.24.3 | Develop and document Roadside Hazards Report | FDM 11-45-3 |  | x | x | x | x | x | x | x | x | x | x | x | Each report | 6 | 16 | 40 | [5 empty] | 3-8-20 | 2-6-16 | 1-2-4
2.2.4.25.4 |  |  |  | 776.24.4 | Develop and document Design Study Report | FDM 3-15-25.4 |  | x | x | x | x | x | x | x | x | x | x | x | Each report | 60 | 80 | 120 | [5 empty] | 24-32-48 | 12-16-30 | 2-4-8 | [43 empty] | 2-4-6 | [18 empty] | 16-16-16 | [10 empty] | 4-8-12
2.2.4.25.5 |  |  |  | 776.24.5 | Prepare addendum to the Design Study Report | FDM 3-15-25.4 |  | x | x | x | x | x | x | x | x | x | x | x | Each Addendum | 16 | 24 | 40 | [5 empty] | 6-8-14 | 6-8-16 | 1-2-4 | [62 empty] | 2-4-4 | [10 empty] | 1-2-2
2.2.4.25.6 |  |  |  | 776.24.6 | Develop and prepare Design Exceptions Report | FDM 11-1 |  | x | x | x | x | x | x | x | x | x | x | x | Each exception | 32 | N/A | 80 | [5 empty] | 10-n/a-24 | 12-n/a-32 | 1-n/a-3 | [43 empty] | 2-n/a-5 | [18 empty] | 5-n/a-10 | [10 empty] | 2-n/a-6
2.2.4.25.7 |  |  |  | 776.24.7 | Develop and prepare Programmatic Exceptions to Standards Report | FDM 11-40-4 |  | x | x | x | [8 empty] | Each exception | 16 | N/A | 32 | [5 empty] | 8-n/a-16 | 4-n/a-8 | 1-n/a-2 | [62 empty] | 2-n/a-4 | [10 empty] | 1-n/a-2
2.2.4.25.8 |  |  |  | 776.24.8 | Perform Value Engineering evaluation | FDM 1-15 |  | x | x | x | x | x | x | x | x | x | x | x | Per VE evaluation | 280 | 400 | 600 | [6 empty] | 48-72-108 | 60-92-160 | 8-10-16 | 4-8-16 |  | 24-32-40 | [9 empty] | 24-32-40 |  |  |  |  | 16-16-16 |  |  |  |  | 12-16-24 | [19 empty] | 24-32-40 | [14 empty] | 12-18-32 | 24-36-48 | [13 empty] | 24-36-60
2.2.4.25.9 |  |  |  | 776.24.9 | Prepare Technical memorandum for design related issues | None |  | x | x | x | x | x | x | x | x | x | x | x | Each memo | 8 | 20 | 40 | [6 empty] | 4-8-20 | 2-4-8 | [62 empty] | 1-4-6 | [10 empty] | 1-4-6
2.2.4.26 |  |  |  | 776.25 | Plan Preparation
2.2.4.26.1 |  |  |  | 776.25.1 | Title sheet |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 14 | 16 | 24 | [6 empty] | 6-8-8 | 4-4-8 | [58 empty] | 4-4-8
2.2.4.26.2 |  |  |  | 776.25.2 | General notes |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 14 | 16 | 24 | [6 empty] | 6-8-10 | 4-4-6 | [58 empty] | 4-4-8
2.2.4.26.3 |  |  |  | 776.25.3 | Project Overview |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 16 | 24 | 40 | [6 empty] | 7-10-20 | 3-6-8 | [58 empty] | 6-8-12
2.2.4.26.4 |  |  |  | 776.25.4 | Typical sections |  |  | X | X | X | X | X | X | X | X | X | X | X | Each section | 14 | 16 | 20 | [6 empty] | 7-8-12 | 3-4-4 | [58 empty] | 4-4-4
2.2.4.26.5 |  |  |  | 776.25.5 | Construction details |  |  | X | X | X | X | X | X | X | X | X | X | X | Each detail | 6 | 32 | 48 | [6 empty] | 2-14-20 | 0-4-8 | [58 empty] | 4-14-20
2.2.4.26.6 |  |  |  | 776.25.6 | Building and site clearance details | [5 empty] | X | X | X | X |  |  |  |  | sheet | 16 | 32 | 40 | [6 empty] | 7-14-18 | 2-4-4 | [58 empty] | 7-14-18
2.2.4.26.7 |  |  |  | 776.25.7 | Jointing details |  |  |  |  | X | X | X | X | X | X | X | X | X | Each detail | 6 | 10 | 16 | [6 empty] | 3-4-6 | 1-1-2 | [58 empty] | 2-5-8
2.2.4.26.8 |  |  |  | 776.25.8 | Driveway details |  |  | X | X | X | X | X | X | X | X | X | X | X | Each detail | 6 | 10 | 20 | [6 empty] | 3-4-8 | 1-1-2 | [58 empty] | 2-5-10
2.2.4.26.9 |  |  |  | 776.25.9 | Curb ramp details |  |  | X | X | X | X | X | X | X | X | X | X | X | Each detail | 0 | 6 | 20 | [6 empty] | 0-2-6 | 0-1-2 | [58 empty] | 0-2-12
2.2.4.26.10 |  |  |  | 776.25.10 | Plan / paving details |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 28 | 40 | 52 | [6 empty] | 10-16-14 | 4-4-6 | 0-0-4 | [57 empty] | 14-20-28
2.2.4.26.11 |  |  |  | 776.25.11 | Intersection details |  |  | X | X | X | X | X | X | X | X | X | X | X | each intersection | 40 | 60 | 80 | [6 empty] | 22-36-32 | 4-6-8 | 0-0-4 | [57 empty] | 14-18-36
2.2.4.26.12 |  |  |  | 776.25.12 | Interchange details | [5 empty] | X | X | X | X |  |  |  |  | sheet | 40 | 60 | 80 | [6 empty] | 22-36-32 | 4-6-8 | 0-0-4 | [57 empty] | 14-18-36
2.2.4.26.13 |  |  |  | 776.25.13 | Storm Sewer and Utilities details |  |  |  | X | X | X | X | X | X |  |  |  |  | sheet | 42 | 64 | 100 | [6 empty] | 22-32-44 | 4-6-12 | 0-0-4 | [57 empty] | 16-26-30
2.2.4.26.14 |  |  |  | 776.25.14 | Alignment diagram |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 24 | 36 | 52 | [6 empty] | 8-14-26 | 2-2-6 | [58 empty] | 14-20-20
2.2.4.26.15 |  |  |  | 776.25.15 | Superelevation table |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 24 | 36 | 44 | [6 empty] | 8-20-24 | 2-2-4 | [58 empty] | 10-14-16
2.2.4.26.16 |  |  |  | 776.25.16 | Plan and profile sheets |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 40 | 60 | 86 | [6 empty] | 16-24-32 | 4-4-6 | [58 empty] | 20-32-44
2.2.4.26.17 |  |  |  | 776.25.17 | Plan and profile - mainline |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 40 | 60 | 86 | [6 empty] | 16-24-32 | 4-4-6 | 0-0-4 | [57 empty] | 20-32-44
2.2.4.26.18 |  |  |  | 776.25.18 | Plan and profile - crossroads |  |  | X | X | X | X | X | X | X | X | X | X | X | sheet | 40 | 60 | 86 | [6 empty] | 16-24-32 | 4-4-6 | 0-0-4 | [57 empty] | 20-32-44
2.2.4.26.19 |  |  |  | 776.25.19 | Plan and profile - ramps | [5 empty] | X | X | X | X |  |  |  |  | sheet | 40 | 60 | 80 | [6 empty] | 16-24-32 | 4-4-6 | 0-0-4 | [57 empty] | 20-32-11
2.2.4.26.20 |  |  |  | 776.25.20 | Cross sections |  |  | X | X | X | X | X | X | X |  |  |  |  | sheet | 2 | 4 | 6 | [6 empty] | 1-1-2 | 0-1-1 | [58 empty] | 1-2-3
2.2.4.27 |  |  |  | 776.26 | Specialty - Roundabout design | [5 empty] | X | X | X | X
2.2.5 |  |  | 786 | Develop Quantities and Estimates (7/17/16)
2.2.5.1 |  |  |  | 786 | Includes developing miscellaneous quantities and preparing estimate materials
2.2.5.2 |  |  |  | 786.1 | Calculate/estimate quantities | FDM 15-1-30, 19-5-5.7 |  | x | x | x | x | x | x | x | x | x | x | x | project | 68 | 114 | 152 | [5 empty] | 32-54-70 | 8-12-16 | 2-4-8 | [60 empty] | 16-26-30 | 8-14-18 | 2-4-10
2.2.5.3 |  |  |  | 786.2 | Calculate Earthwork and Develop Summary Tables | FDM 11-5-10, 15-1-30 |  | x | x | x | x | x | x | x | x | x | x | x | project | 24 | 36 | 48 | [5 empty] | 4-6-8 | 8-12-16 | 2-3-4 | [60 empty] | 0-0-0 | 8-12-16 | 2-3-4
2.2.5.4 |  |  |  | 786.3 | Prepare Estimate Documentation Report/Determine unit prices | FDM 19-5-5 |  | x | x | x | x | x | x | x | x | x | x | x | project | 24 | 40 | 80 | [5 empty] | 0-0-0 | 16-26-52 | 4-8-16 | [60 empty] | 0-0-0 | 0-1-3 | 3-4-8 | [10 empty] | 1-1-1
2.2.5.5 |  |  |  | 786.4 | Prepare non-delivery cost (Estimator/Trns.port PES estimate) | FDM 19-5-10 |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 12 | 20 | [5 empty] | 4-6-10 | 1-2-3 | 1-1-1 | [60 empty] | 0-0-0 | 2-3-6 | 0-0-0
2.2.6 |  |  | 856 | Develop PSE Documents (7/15/16)
2.2.6.1 |  |  |  | 856.1 | Develop special provisions |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 20 | 40 | 80 | [6 empty] | 19-39-59 | [62 empty] | 0-0-20 | [11 empty] | 1-1-4
2.2.6.2 |  |  |  | 856.2 | Develop construction time chart |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 8 | 20 | 40 | [6 empty] | 7-19-10 | 1-1-5 | [62 empty] | 0-0-25
2.2.6.3 |  |  |  | 856.3 | Develop certificate of right of way |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 2 | 3 | [6 empty] | 1-2-0 | [63 empty] | 0-0-2 | [20 empty] | 0-0-1
2.2.6.4 |  |  |  | 856.4 | Develop Utility status report |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 2 | 3 | [6 empty] | 1-2-1 | [63 empty] | 0-0-2
2.2.6.5 |  |  |  | 856.5 | Develop Certification of Railroad Coordination |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 1 | [6 empty] | 1-1-1
2.2.6.6 |  |  |  | 856.6 | Develop Governors Bond - DT25 |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 1 | [6 empty] | 1-1-0 | [63 empty] | 0-0-1
2.2.6.7 |  |  |  | 856.7 | Develop highway work proposal |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 2 | [6 empty] | 1-1-0 | [63 empty] | 0-0-2
2.2.6.8 |  |  |  | 856.8 | Develop plan letter |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 8 | 16 | 24 | [6 empty] | 7-15-5 | 1-1-1 | [62 empty] | 0-0-18
2.2.6.9 |  |  |  | 856.9 | Develop news release form |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 2 | 2 | [6 empty] | 2-2-2
2.2.6.10 |  |  |  | 856.1 | Develop notes to construction engineer |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 2 | 4 | [6 empty] | 1-2-1 | [63 empty] | 0-0-3
2.2.6.11 |  |  |  | 856.11 | Develop Region Specific PS&E Documents |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 4 | 8 | [6 empty] | 2-4-2 | [63 empty] | 0-0-6
2.2.6.12 |  |  |  | 856.12 | AutoCAD Civil 3D Project Data Submittal |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 4 | 8 | 16 | [70 empty] | 4-8-16
2.2.6.13 |  |  |  | 856.13 | Project Archive |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 4 | 8 | [70 empty] | 2-4-8
2.2.6.14 |  |  |  | 856.14 | Contractor Data Packet |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 8 | 24 | 40 | [70 empty] | 8-24-40
2.2.6.15 |  |  |  | 856.15 | Create Standard Detail Spreadsheet |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 1 | 1 | 1 | [70 empty] | 1-1-1
2.2.6.16 |  |  |  | 856.16 | Prepare e-plan submittal |  |  | x | x | x | x | x | x | x | x | x | x | x | PS&E package | 2 | 4 | 8 | [70 empty] | 2-4-8
2.3 |  | Data, Survey, and Mapping (9/7/16)
2.3.1 |  |  | 610 | Acquire Aerial Imagery (7/8/16)
2.3.1.2 |  |  |  | 610.1 | Develop flight plans and target document | FDM 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 0.6 | 0.7 | 0.9 | [98 empty] | .6/.7/.9 | [5 empty] | .6/.7/.9
2.3.1.3 |  |  |  | 610.2 | Capture aerial imagery | FDM 9-45-5.1, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 0.6 | 0.7 | 0.9 | [98 empty] | .6/.7/.9 | [5 empty] | .6/.7/.9
2.3.1.4 |  |  |  | 610.3 | Image processing - film; develop; QA/QC | FDM 9-45-5, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 0.2 | 0.4 | 0.6 | [98 empty] | .2/.4/.6 | [5 empty] | .2/.4/.6
2.3.1.5 |  |  |  | 610.4 | Image processing - digital; initial processing; QA/QC | FDM 9-45-5 |  | x | x | x | x | x | x | x | x | x | x | x | project | 4 | 8 | 10 | [98 empty] | 4/8/10 | [5 empty] | 4/8/10
2.3.2 |  |  | 668 | Scan Aerial Images (7/28/16)
2.3.2.1 |  |  |  | 668.1 | Convert film imagery to digital with high resolution scanners | FDM 9-45-5.1, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 0.12 | 0.18 | 0.24 | [98 empty] | .12/.18/.24 | [5 empty] | .12/.18/.24
2.3.3 |  |  | 237 | Perform Analytical Triangulation (7/28/16)
2.3.3.1 |  |  |  | 237.1 | Analytical Control | FDM 9-45-10, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 0.4 | 2 | 8 | [98 empty] | .4/2/8 | [5 empty] | .4/2/8
2.3.3.2 |  |  |  | 237.2 | Softcopy Analytical Triangulation | FDM 9-45-10, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 3 | 6 | 10 | [98 empty] | 3/6/10 | [5 empty] | 3/6/10 | Question for Jan
2.3.4 |  |  | 232 | Develop Digital Terrain Model (DTM) (7/28/16)
2.3.4.1 |  |  |  | 232.1 | Create digital terrain model for Civil3D (DTM) | FDM 9-45-10.1, 9-45-15
2.3.4.1.1 |  |  |  | 232.1.1 | No R/W | FDM 9-45-10.1, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 12 | 20 | 48 | [98 empty] | 12/20/48 | [5 empty] | 12/20/48 | Question for Jan
2.3.4.1.2 |  |  |  | 232.1.2 | With R/W | FDM 9-45-10.1, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 24 | 40 | 96 | [98 empty] | 24/40/96 | [5 empty] | 24/40/96 | Question for Jan
2.3.5 |  |  | 236 | Develop Planimetric Mapping (7/28/16)
2.3.5.1 |  |  |  | 236.1 | Create base planimetric mapping | FDM 9-45-10.2, 9-45-10.3, 9-45-15
2.3.5.1.1 |  |  |  | 236.1.1 | No R/W | FDM 9-45-10.2, 9-45-10.3, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 6 | 10 | 24 | [98 empty] | 6/10/24 |  |  |  |  | 3/5/12 | 3/5/12 | Question for Jan
2.3.5.1.2 |  |  |  | 236.1.2 | With R/W | FDM 9-45-10.2, 9-45-10.3, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 12 | 20 | 48 | [98 empty] | 12/20/48 |  |  |  |  | 6/10/24 | 6/10/24 | Question for Jan
2.3.6 |  |  | 665 | Edit Mapping and Digital Terrain Model (7/28/16)
2.3.6.1 |  |  |  | 665.1 | Edit planimetric mapping | FDM 9-45-10, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 0.5 | 1 | 2 | [98 empty] | .5/1/2 | [6 empty] | .5/1/2
2.3.6.2 |  |  |  | 665.2 | Edit digital terrain model (DTM) | FDM 9-45-10, 9-45-15 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 1 | 2 | 4 | [98 empty] | 1/2/4 | [6 empty] | 1/2/4
2.3.7 |  |  | 669 | Develop Digital Orthophotos (7/28/16)
2.3.7.1 |  |  |  | 669.1 | Develop digital orthophotos | FDM 9-45-10.5 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 0.3 | 0.4 | 0.5 | [98 empty] | .3/.4/.5 | [5 empty] | .3/.4/.5
2.3.7.2 |  |  |  | 669.2 | Develop digital georeferenced imagery | FDM 9-45-5.3 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 0.4 | 0.5 | 0.6 | [98 empty] | .4/.5/.6 | [5 empty] | .4/.5/.6
2.3.8 |  |  | 373 | Acquire Aerial LiDAR (8/3/16)
2.3.8.1 |  |  |  | 373.1 | Develop flight plans and target document | FDM 9-45-20.2 |  | x | x | x | x | x | x | x | x | x | x | x | project | 4 | 8 | 16 | [104 empty] | 3.8/7.7/15.4 | 0.2/0.3/0.6
2.3.8.2 |  |  |  | 373.2 | Collect aerial LiDAR data | FDM 9-45-20.1.1 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 1 | 1 | 1 | [104 empty] | 1/1/1
2.3.9 |  |  | 374 | Process Aerial LiDAR (8/3/16)
2.3.9.1 |  |  |  | 374.1 | Data preparation and registration; QA/QC | FDM 9-45-20.1.1 |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 1 | 1.75 | 2.5 | [104 empty] | 0.9/1.65/2.4 | 0.1/0.1/0.1
2.3.9.2 |  |  |  | 374.2 | Process data and create deliverables; QA/QC | FDM 9-45-20.5 |  | x | x | x | x | x | x | x | x | x | x | x | centerline mile | 5 | 8 | 10 | [103 empty] | 3/5/6 | 1.8/2.7/3.6 | 0.2/0.3/0.4
2.3.10 |  |  | 375 | Acquire Static LIDAR (7/7/16)
2.3.10.1 |  |  |  | 375.1 | Develop scan positions and target document | FDM 9-45-20.2.1, 9-45-25 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 3 | 4 | 5 | [98 empty] | 3/4/5 | [5 empty] | 3/4/5
2.3.10.2 |  |  |  | 375.2 | Collect scan data and images | FDM 9-45-20.1.3, 9-45-25 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 20 | 25 | 30 | [98 empty] | 20/25/30 | [5 empty] | 20/25/30
2.3.11 |  |  | 376 | Process Static LIDAR (7/7/16)
2.3.11.1 |  |  |  | 376.1 | Data preparation and registration; QA/QC | FDM 9-45-20.2.1 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 10 | 12 | 15 | [98 empty] | 10/12/15 | [5 empty] | 10/12/15
2.3.11.2 |  |  |  | 376.2 | Process data and create deliverables; QA/QC | FDM 9-45-20.5 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 50 | 85 | 110 | [98 empty] | 50/85/110 | [5 empty] | 50/85/110
2.3.12 |  |  | 377 | Acquire Mobile LiDAR (8/3/16)
2.3.12.1 |  |  |  | 377.1 | Develop drive paths and target document | FDM 9-45-20.2 |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 16 | 24 | [104 empty] | 6/13/20 | 2/3/4
2.3.12.2 |  |  |  | 377.2 | Collect scan data and images | FDM 9-45-20.1.2 |  | x | x | x | x | x | x | x | x | x | x | x | centerline mile | 1 | 2 | 3 | [103 empty] | 0.5/1.5/2.5 |  | 0.5/0.5/0.5
2.3.13 |  |  | 378 | Process Mobile LiDAR (8/3/16)
2.3.13.1 |  |  |  | 378.1 | Data preparation and registration; QA/QC | FDM 9-45-20.1.2 |  | x | x | x | x | x | x | x | x | x | x | x | centerline mile | 3 | 4.5 | 6 | [104 empty] | 2.9/4.3/5.8 | 0.1/0.2/0.2
2.3.13.2 |  |  |  | 378.2 | Process data and create deliverables; QA/QC | FDM 9-45-20.5 |  | x | x | x | x | x | x | x | x | x | x | x | centerline mile | 10 | 12 | 15 | [103 empty] | 3.6/4.5/6.4 | 6/7/8 | 0.4/0.5/0.6
2.3.14 |  |  | 379 | Merge LiDAR Data (7/28/16)
2.3.14.1 |  |  |  | 379.1 | Develop boundary between data types; delete unneeded data | None |  | x | x | x | x | x | x | x | x | x | x | x | mile | 1 | 3 | 4 | [98 empty] | 1/3/4 | [5 empty] | 1/3/4
2.3.14.2 |  |  |  | 379.2 | Create deliverables; QA/QC | FDM 9-45-20.5 |  | x | x | x | x | x | x | x | x | x | x | x | mile | 1 | 3 | 4 | [98 empty] | 1/3/4 | [5 empty] | 1/3/4
2.3.15 |  |  | 382 | Setup Survey Project (8/24/16)
2.3.15.1 |  |  |  | 382.1 | Fill out "Greenie" request form |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 1 | 5 | 10 | [58 empty] | 1-5-10
2.3.15.2 |  |  |  | 382.2 | For aerial photography flights |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 12 | 16 | [58 empty] | 8-12-16
2.3.15.3 |  |  |  | 382.3 | For aerial LiDAR |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 12 | 16 | [58 empty] | 8-12-16
2.3.15.4 |  |  |  | 382.4 | For mobile LiDAR |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 16 | 24 | [58 empty] | 8-16-24
2.3.15.5 |  |  |  | 382.5 | For static LiDAR |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 4 | 8 | 12 | [58 empty] | 4-8-12
2.3.16 |  |  | 381 | Place and Survey Targeting (8/3/16)
2.3.16.1 |  |  |  | 381.1 | Targeting for aerial photography and aerial LiDAR |  |  | x | x | x | x | x | x | x | x | x | x | x | flight line mile | 7 | 15 | 25 | [56 empty] | 0/7/10 | 7/7/10 | 0/1/5
2.3.16.2 |  |  |  | 381.2 | Targeting for static LiDAR |  |  | x | x | x | x | x | x | x | x | x | x | x | acre | 8 | 10 | 12 | [57 empty] | 8/8/8 | 0/2/4
2.3.16.3 |  |  |  | 381.3 | Targeting for mobile LiDAR |  |  | x | x | x | x | x | x | x | x | x | x | x | centerline mile | 30 | 35 | 40 | [56 empty] | 14/16/16 | 14/15/16 | 2/5/8
2.3.17 |  |  | 666 | Establish Project Control (7/15/16)
2.3.17.1 |  |  |  | 666 | Includes activities related to establishing project control.
2.3.17.2 |  |  |  | 666.1 | Set horizontal and vertical control for GPS or other conventional methods | FDM 9-25-5
2.3.17.2.1 |  |  |  | 666.1.1 | Set project control | FDM 9-25-10 |  | X | X | X | X | X | X | X | X | X | X | X | POINT | 0.25 | N/A | 0.5 | [56 empty] | .25/NA/.5
2.3.17.2.2 |  |  |  | 666.1.2 | Set project benchmarks | FDM 9-25-10 |  | X | X | X | X | X | X | X | X | X | X | X | POINT | 0.25 | N/A | 0.5 | [56 empty] | .25/NA/.5
2.3.17.2.3 |  |  |  | 666.1.3 | Create control tie sheets | DT2262 |  | X | X | X | X | X | X | X | X | X | X | X | EACH | 1 | 1 | 1 | [65 empty] | 1/1/1
2.3.17.2.4 |  |  |  | 666.1.4 | Set project reference points |  |  | X | X | X | X | X | X | X | X | X | X | X | STATION | 0.5 | 0.5 | 0.5 | [56 empty] | .5/.5/.5
2.3.17.2.5 |  |  |  | 666.1.5 | GPS observation | FDM 9-45, FDM 9-20, |  | X | X | X | X | X | X | X | X | X | X | X | POINT | 0.25 | 0.5 | 1 | [57 empty] | .25/.5/1
2.3.17.2.6 |  |  |  | 666.1.6 | Total station observations (closed traverse) | FDM 9-35 |  | X | X | X | X | X | X | X | X | X | X | X | MILE | 0.5X2 | 0.5X2 | 1X2 | [56 empty] | .5/.5/1 | .5/.5/1
2.3.17.2.7 |  |  |  | 666.1.7 | Perform leveling (closed traverse) | FDM 9-40 |  | X | X | X | X | X | X | X | X | X | X | X | MILE | 2X2 | 4X2 | 5X2 | [56 empty] | 2/4/5 | 2/4/5
2.3.17.3 |  |  |  | 666.2 | Replace Height Modernization geodetic survey control
2.3.17.3.1 |  |  |  | 666.2.1 | Perform geodetic survey control station reconnaissance | None |  | X | X | X | X | X | X | X | X | X | X | X | EACH | 2 | 3 | 4 | [57 empty] | 2 / 3 / 4
2.3.17.3.2 |  |  |  | 666.2.2 | Install geodetic survey control station | FDM 9-25-10.1 |  | X | X | X | X | X | X | X | X | X | X | X | EACH | 2 | 4 | 6 | [56 empty] | 1 / 2 / 3 |  | 1 / 2 / 3
2.3.17.3.3 |  |  |  | 666.2.3 | Develop a geodetic survey control station description | “Input Formats and Specifications of the National Geodetic Survey Data Base," Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998. |  | X | X | X | X | X | X | X | X | X | X | X | EACH | 1 | 2 | 3 | [56 empty] | 1 / 2 / 3
2.3.17.3.4 |  |  |  | 666.2.4 | Perform Second Order, Class 1 geodetic leveling (double-run) | "Standards and Specifications for Geodetic Control Networks," September 1984, Federal Geodetic Control Committee (FGCC), Reprinted 1993. 6.3.6.2 "Geodetic Leveling", NOAA Manual NOS NGS3, NOAA, National Geodetic Survey, August 1981; "Interim FGCS Specifications and Procedures to Incorporate Electronic Digital/Bar-Code Leveling Systems", FGCS (Ver. 4.0 7/15/94); "VFPROC--Vertical Control Field Data Processing System", NOAA, C&GS, National Geodetic Survey, Version 3.00, December 1992; "Input Formats and Specifications for the National Geodetic Survey Data Base", Volume II, Vertical Control Data, Federal Geodetic Data Committee, September 1994, Reprinted November 1998; “NGS PROPOSAL for An Addendum to Current FGCS Specifications and Procedures to Incorporate Electronic Digital/Bar-Code Leveling Systems”, National Geodetic Survey, February 2001; “Input Formats and Specifications of the National Geodetic Survey Data Base", Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998. |  | X | X | X | X | X | X | X | X | X | X | X | KILOMETER | 3 | 5 | 7 | [56 empty] | 2 / 4 / 6 | 1 / 1 / 1
2.3.17.3.5 |  |  |  | 666.2.5 | Perform static GPS observations to National Geodetic Survey (NGS) standards | "Standards and Specifications for Geodetic Control Networks," September 1984, Federal Geodetic Control Committee (FGCC), Reprinted 1993; “Input Formats and Specifications of the National Geodetic Survey Data Base," Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998; “Guidelines for Establishing GPS-Derived Orthometric Heights (Standards: 2cm and 5 cm),” Draft, Version 1.4, National Geodetic Survey, October 2005; “Guidelines for Establishing GPS-Derived Ellipsoid Heights (Standards: 2cm and 5 cm),” NOAA Technical Memorandum NOS NGS-58, National Geodetic Survey, November 1997. |  | X | X | X | X | X | X | X | X | X | X | X | EACH STATION | 10 | 20 | 30 | [56 empty] | 6 / 12 / 18 | 2 / 4 / 6 | 2 / 4 / 6
2.3.17.3.6 |  |  |  | 666.2.6 | Perform data post-processing, analysis, adjustment for acceptance and inclusion into the National Spatial Reference System (NSRS) | "Standards and Specifications for Geodetic Control Networks," September 1984, Federal Geodetic Control Committee (FGCC), Reprinted 1993; “Input Formats and Specifications of the National Geodetic Survey Data Base," Volume I, Horizontal Control Data, Federal Geodetic Data Committee, September 1994, Revised and Reprinted November 1998 |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 10 | 15 | 20 | [57 empty] | 3.33 / 5 / 6.67 | 5 / 7.5 / 10 | 1.67 / 2.5 / 3.33
2.3.17.4 |  |  |  | 666.3 | Specialty - Wisconsin height modernization program
2.3.17.5 |  |  |  | 666.4 | Specialty - Geodetic services
2.3.18 |  |  | 723 | Conduct and Process Existing Field Survey (6/15/16)
2.3.18.1 |  |  |  | 723 | Survey of existing surface, utilities, stormsewer; process data; and create existing surface model. | FDM Chapter 9
2.3.18.2 |  |  |  | 723.1 | Review plans and as-builts | FDM 9 & 12 |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 4 | 6 | [57 empty] | 2 2 2 |  | 0 2 4
2.3.18.3 |  |  |  | 723.2 | Measure existing centerline | FDM 9 |  | X | X | X | X | X | X | X | X | X | X | X | MILE | 2 | 4 | 6 | [56 empty] | 2 3 5 |  | 0 1 1
2.3.18.4 |  |  |  | 723.3 | Measure existing monumentation | FDM 9.25 |  |  |  |  | X |  | X | X |  | X |  |  | MILE | 4 | 5 | 6 | [56 empty] | 3 4 5 |  | 1 1 1
2.3.18.6 |  |  |  | 723.4 | Existing surface and topographic survey | FDM 9.65 |  |  | X | X | X | X | X | X | X | X | X | X | MILE | 10 | 16 | 20 | [56 empty] | 6 10 15 |  | 4 6 5
2.3.18.7 |  |  |  | 723.5 | Structure field survey | FDM 9.60 | [8 empty] | X | X | X | X | .1 MILE | 8 | 10 | 20 | [56 empty] | 4 5 10 |  | 4 5 10
2.3.18.8 |  |  |  | 723.6 | Call diggers hotline | FDM Chapter 9 |  |  | X | X | X | X | X | X | X | X | X | X | MILE | 1 | 2 | 2 | [57 empty] | 1 2 2
2.3.18.9 |  |  |  | 723.7 | Dip manholes and water valves | FDM Chapter 9 |  |  |  | X | X | X | X | [5 empty] | EACH | 1 | 2 | 2 | [56 empty] | 1 1 1 |  | 0 1 1
2.3.18.10 |  |  |  | 723.8 | Stake marking limits | FDM Chapter 9 |  |  | X | X | X | X |  |  |  | X | X | X | TRIP | 4 | 5 | 6 | [58 empty] | 4 5 6
2.3.18.11 |  |  |  | 723.9 | Photographs | FDM Chapter 9 |  |  | X | X | X |  |  |  | X | X | X | X | PROJECT | 2 | 4 | 8 | [56 empty] | 2 4 8
2.3.18.12 |  |  |  | 723.1 | Meet with utility locator in field | FDM Chapter 9 |  |  |  |  | X | X | [6 empty] | TRIP | 4 | 5 | 6 | [57 empty] | 4 5 6
2.3.18.14 |  |  |  | 723.11 | Review 1077 utility facility map | FDM Chapter 9 |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 4 | 8 | [57 empty] | 2 4 8
2.3.18.16 |  |  |  | 723.12 | Field survey exisitng utilities | FDM Chapter 9 |  |  | X | X | X | X | X | X | X | X | X | X | MILE | 4 | 6 | 10 | [56 empty] | 2 3 5 |  | 2 3 5
2.3.18.17 |  |  |  | 723.13 | Perform storm sewer structure evaluations (size-depth-invert) | FDM Chapter 9 |  |  |  | X | X | X | X | X |  |  |  |  | EACH | 1 | 2 | 2 | [57 empty] | 1 2 2
2.3.18.18 |  |  |  | 723.14 | Process survey data and create existing surface | FDM Chapter 9 |  |  | X | X | X | X | X | X | X | X | X | X | .1 MILE | 2 | 3 | 4 | [57 empty] | 2 3 4
2.3.18.19 |  |  |  | 723.15 | Field notes |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 5 | 6 | [56 empty] | 2 5 6
2.3.18.20 |  |  |  | 723.16 | Measure/map exisitng drainage features | FDM Chapter 9 |  | X | X | X | X | X | X | X | X | X | X | X | .1 MILE | 1 | 2 | 3 | [58 empty] | 1 2 3
2.3.18.21 |  |  |  | 723.17 | Traffic control for survey | [13 empty] | DAY (8 HOURS) | 1 | 2 | 4 | [56 empty] | 1 2 4
2.3.18.22 |  |  |  | 723.18 | Create deliverables in Civil 3D | FDM Chapter 9 |  | X | X | X | X | X | X | X | X | X | X | X | MILE | 6 | 8 | 10 | [57 empty] | 6 8 10
2.3.18.23 |  |  |  | 723.19 | Reduce field notes | FDM Chapter 9 |  | X | X | X | X | X | X | X | X | X | X | X | MILE | 2 | 3 | 4 | [56 empty] | 2 3 4
2.3.18.24 |  |  |  | 723.2 | Level 1500 feet upstream and downstream from structure | FDM 9.60 |  | MOSTLY | USE | GPS |  |  |  | X | X | X | X | X | 0.1 mi | 2 | 6 | 8 | [56 empty] | 1 3 4 |  | 1 3 4
2.3.18.25 |  |  |  | 723.21 | Measure structure clearances | FDM 9.60 | [7 empty] | X | X | X | X | X | STRUCTURE | 4 | 6 | 10 | [56 empty] | 2 3 5 |  | 2 3 5
2.3.18.26 |  |  |  | 723.22 | Measure water and high water elevations | FDM 9.60 | [7 empty] | X | X | X | X | X | PROJECT | 2 | 3 | 4 | [56 empty] | 1 1 2 |  | 1 2 2
2.3.18.27 |  |  |  | 723.23 | Create stream cross sections | FDM 9.60 | [7 empty] | X | X | X | X | X | PROJECT | 4 | 6 | 8 | [56 empty] | 2 3 4 |  | 2 3 4
2.3.18.28 |  |  |  | 723.24 | Railroad Profile Survey
2.3.19 |  |  | 726 | Survey Existing and Proposed Right-of-Way (7/18/16)
2.3.19.1 |  |  |  | 726 | Develop existing and proposed right-of-way; temporary staking, and permanent property pins. |  |  |  | X | X | X | X | X | X | X | X | X | X
2.3.19.2 |  |  |  | 726.1 | Measure existing right of way and property monumentation | FDM 12-1-5 |  |  | X | X | X | X | X | X | X | X | X | X | hrs/person/1/4 mile | 8 | 12 | 20 | [56 empty] | 3/5/7 | 3/5/7 | 1/1/4 | 1/1/2
2.3.19.3 |  |  |  | 726.2 | Measure evidence of occupation | FDM 12-1-5 |  |  | X | X | X | X | X | X | X | X | X | X | hrs/person/1/4 mile | 3 | 9 | 16 | [56 empty] | 1/4/4 | 1/4/4 | 1/1/4 | 0/0/4
2.3.19.4 |  |  |  | 726.3 | Measure government corners and ties | FDM 12-1-5, FDM 9-5-1 |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 1 | 3 | 8 | [56 empty] | 1/1/2 | 0/1/2 | 0/1/2 | 0/0/2
2.3.19.5 |  |  |  | 726.4 | Re-establish missing government corners and ties | FDM 12-1-5, FDM 9-5-1, FDM 9-25, A-E 7.08 |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 4 | 8 | 16 | [56 empty] | 1/3/5 | 1/3/5 | 2/2/6
2.3.19.6 |  |  |  | 726.5 | Produce tie sheets for government corners | FDM 12-1-5, FDM 9-5-1, A-E 7.08 |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 2 | 3 | 4 | [56 empty] | 1/1/2 |  | 1/2/2
2.3.19.7 |  |  |  | 726.6 | Research public records | FDM 12-1-5, A-E 7.03 |  |  | X | X | X | X | X | X | X | X | X | X | hours / mile | 2 | 4 | 6 | [58 empty] | 1/2/3 | 1/2/3
2.3.19.8 |  |  |  | 726.7 | Review legal documents | FDM 12-1-5, A-E 7.03 |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 0.5 | 1 | 2 | [58 empty] | 0.5/1/1 | 0/0/1
2.3.19.9 |  |  |  | 726.8 | Review plans and as-builts | FDM 12-1-5, A-E 7.03 |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 0.5 | 2 | 4 | [57 empty] | 0.5/0/0 | 0/2/2 | 0/0/2
2.3.19.10 |  |  |  | 726.9 | Review title work | FDM 12-1-10, Real Estate Program Manual |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 0.5 | 2 | 4 | [58 empty] | 0.5/1/1 | 0/1/3
2.3.19.11 |  |  |  | 726.1 | Field locate section corners, block corners, iron pins | FDM 12-1-5, FDM 9-1, 9-5, 9-10 |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 0.25 | 0.5 | 3 | [56 empty] | 0.25/0.5/1 |  | 0/0/1 | 0/0/1
2.3.19.12 |  |  |  | 726.11 | Survey property corners | FDM 12-1-5, FDM 9-1, 9-5, 9-10 |  |  | X | X | X | X | X | X | X | X | X | X | hours / corner | 0.25 | 0.5 | 2 | [56 empty] | 0.25/0.25/0.5 | 0/0.25/0.5 | 0/0/0.5 | 0/0/0.5
2.3.19.13 |  |  |  | 726.12 | Survey section corners | FDM 12-1-5, FDM 9-1, 9-5, 9-10 |  |  | X | X | X | X | X | X | X | X | X | X | hours / corner | 1 | 3 | 8 | [56 empty] | 1/1/2 | 0/1/2 | 0/1/2 | 0/0/2
2.3.19.14 |  |  |  | 726.13 | Appraisal staking | FDM 9-75 |  |  | X | X | X | X | X | X | X | X | X | X | hours / point | 0.25 | 0.5 | 1 | [56 empty] | 0.25/0.25/0.25 | 0/0.25/0.25 | 0/0/0.25 | 0/0/0.25
2.3.20 |  |  | 897 | Place Monumentation (7/18/16)
2.3.20.1 |  |  |  | 897 | Includes tasks to identify, recover, and preserve a landmark, monument or corner. |  |  |  | X | X | X | X | X | X | X | X | X | X
2.3.20.2 |  |  |  | 897.1 | Set right of way pins | FDM 9-5, FDM 9-25, A-E 7.07 |  |  | X | X | X | X | X | X | X | X | X | X | hours / point | 1.25 | 2 | 4 | [56 empty] | .5/1/2 | 0.25/0.5/1 | 0.5/0.5/1
2.3.20.3 |  |  |  | 897.2 | Place type 1, 2,3, 4 monument | FDM 9-5, FDM 9-25, A-E 7.07 |  |  | X | X | X | X | X | X | X | X | X | X | hours / point | 1.25 | 2 | 6.5 | [56 empty] | .5/1/2 | 0.25/0.5/2 | 0.5/0.5/2
2.3.20.4 |  |  |  | 897.3 | Recover monumentation | FDM 9-5, FDM 9-25, A-E 7.07 |  |  | X | X | X | X | X | X | X | X | X | X | hours each | 0.25 | 1 | 4 | [56 empty] | 0.25/0.5/1 | 0/0.5/1 | 0/0/2
2.3.21 |  |  | 745 | Develop Transportation Project Plat (TPP) (9/7/16)
2.3.21.1 |  |  |  | 745 | ncludes activities related to providing design information to TPP plat section; identifying existing TPP lines, easements, alignments and access control; section corners; determining property ownership and property lines; conducting field review; developing preliminary plat; identifying proposed TPP lines, easements, alignments and parcels; and completing final plat and relocation order. This includes any drafting and revisions. | FDM Chapter 12 and A-E 7 |  |  | X | X | X | X | X | X |  | X | X | X
2.3.21.2 |  |  |  | 745.1 | Railroad right of way | FDM 12-15-1.6.2 |  |  | X | X | X | X | X | X |  | X | X | X | project | 1 | 2 | 4 | [58 empty] | 1/1/2 | 0/1/2
2.3.21.3 |  |  |  | 745.2 | Develop property exhibits | REPM (CH2 ?) |  |  | X | X | X | X | X | X |  | X | X | X | parcel | 1 | 2 | 3 | [58 empty] | .5/1/1 | [7 empty] | .5/1/2
2.3.21.4 |  |  |  | 745.3 | Develop schedule of lands | FDM 12-10-1.2.21 |  |  | X | X | X | X | X | X |  | X | X | X | parcel | 1 | 2 | 3 | [58 empty] | .5/.5/.5 | [7 empty] | .5/1.5/2.5
2.3.21.5 |  |  |  | 745.4 | Legal descriptions | FDM 12-10-20 |  |  | X | X | X | X | X | X |  | X | X | X | parcel | 1 | 1 | 2 | [56 empty] | .5/.5/1 |  | .5/.5/1
2.3.21.5.1 |  |  |  | 745.4.1 | Closure reports | FDM 12-10a1.6 |  |  | X | X | X | X | X | X |  | X | X | X | sheet | 1 | N/A | 2 | [58 empty] | .5/na/1 | [7 empty] | .5/na/1
2.3.21.6 |  |  |  | 745.5 | Record TPP |  |  |  | X | X | X | X | X | X |  | X | X | X | sheet | 1 | 2 | 2 | [58 empty] | .5/1/1 | [7 empty] | .5/1/1
2.3.21.7 |  |  |  | 745.6 | Design information to TPP section | FDM 12-5 |  |  | X | X | X | X | X | X |  | X | X | X | PLSS Qtr Section | 1 | 1 | 1 | [58 empty] | 1/1/1
2.3.21.8 |  |  |  | 745.7 | Section corners | FDM 12-10-1.2.13 |  |  | X | X | X | X | X | X |  | X | X | X | PLSS Qtr Section | 1 | 4 | 8 | [58 empty] | .5/1/2 | [7 empty] | .5/3/6
2.3.21.9 |  |  |  | 745.8 | Review title searches and updates | FDM 12-1-10 |  |  | X | X | X | X | X | X |  | X | X | X | parcel | 1 | 2 | 4 | [58 empty] | .5/1/3 | [7 empty] | .5/1/1
2.3.21.10 |  |  |  | 745.9 | Existing R/W lines, easements, alignments, and access control | FDM 12-1-10 & 12-1-5 |  |  | X | X | X | X | X | X |  | X | X | X | PLSS Qtr Section | 10 | 20 | 30 | [58 empty] | 4/8/10 | [7 empty] | 6/12/20
2.3.21.11 |  |  |  | 745.1 | Field review-property owner walkthrough | REPM Chatper 2 |  |  | X | X | X | X | X | X |  | X | X | X | parcel | 3 | 10 | 20 | [92 empty] | 3/10/20
2.3.21.12 |  |  |  | 745.11 | Preliminary TPP (Layout and Annotation) | FDM 12-10 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 2 | 4 | 6 | [58 empty] | .5/1/2 | [7 empty] | .5/3/4
2.3.21.13 |  |  |  | 745.12 | Determine/label compensable utilities and utility easements | FDM 12-10-1.2.26 |  |  | X | X | X | X | X | X |  | X | X | X | PLSS Qtr Section | 10 | 15 | 20 | [58 empty] | 6/10/15 | [7 empty] | 4/5/5
2.3.21.14 |  |  |  | 745.13 | Utility legal descriptions (may be included in legal descriptions and closure calculations) | Move to Utility Section??? Or 12-10-1.2.26 |  |  | X | X | X | X | X | X |  | X | X | X | PLSS Qtr Section | 2 | 4 | 10
2.3.21.15 |  |  |  | 745.14 | Proposed R/W lines, easements, alignments, parcels, etc. | FDM 12-5-1 |  |  | X | X | X | X | X | X |  | X | X | X | Each | 1 | 2 | 4 | [58 empty] | .5/1/2 | [7 empty] | .5/1/2
2.3.21.16 |  |  |  | 745.15 | Final plat to technical services section | ?? WisDOT function |  |  | X | X | X | X | X | X |  | X | X | X | PLSS Qtr Section | 5 | 10 | 20
2.3.21.17 |  |  |  | 745.16 | Final TPP relocation order | FDM 12-10-1.2.4 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 1 | 2 | 2 | [58 empty] | .5/1/1 | [7 empty] | .5/1/1
2.3.21.18 |  |  |  | 746.17 | TPP drafting (Title sheet) | FDM 12-10-1.3 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 1 | 1 | 2 | [58 empty] | .5/.5 | 0.5 | [6 empty] | .5/.5/1.5
2.3.21.19 |  |  |  | 747.18 | Sheet revisions/ amendments | FDM 12-10-15 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 0.5 | 1 | 2 | [58 empty] | .5/1/2
2.3.21.19 |  |  |  | 745.18 | Traditional plats | FDM 12-15
2.3.21.19.1 |  |  |  | 745.18.1 | Existing R/W lines, easements, alignments, and access control | FDM 12-1-10 & 12-1-5 |  |  | X | X | X | X | X | X |  | X | X | X | PLSS Qtr Section | 10 | 20 | 30 | [58 empty] | 4,8,10 | [7 empty] | 6,12,20
2.3.21.19.2 |  |  |  | 745.18.2 | Proposed R/W lines, easements, alignments, parcels, etc. | FDM 12-5-1 |  |  | X | X | X | X | X | X |  | X | X | X | Each | 1 | 2 | 4 | [58 empty] | .5,1,2 | [7 empty] | .5,1,2
2.3.21.19.3 |  |  |  | 745.18.3 | Title sheet | FDM 12-15-1.1 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 8 | 8 | 8 | [58 empty] | 4,4,4 | [7 empty] | 4.4.4
2.3.21.19.4 |  |  |  | 745.18.4 | Overview sheet | FDM 12-15-1.3 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 8 | 12 | 16 | [58 empty] | 4,6,8 | [7 empty] | 4,6,8
2.3.21.19.5 |  |  |  | 745.18.5 | Schedule of lands and interests | FDM 12-15-1.2 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 4 | 8 | 8 | [58 empty] | 2,3,4 | [7 empty] | 2,3,4
2.3.21.19.6 |  |  |  | 745.18.6 | Detail sheets | FDM 12-15-1.4 |  |  | X | X | X | X | X | X |  | X | X | X | Sheet | 12 | 18 | 24 | [58 empty] | 6,9,12 | [7 empty] | 6,9,12
2.3.21.19.7 |  |  |  | 745.18.7 | Legal descriptions | FDM 12-15-20 |  |  | X | X | X | X | X | X |  | X | X | X | Each | 0.5 | 1 | 2 | [58 empty] | 0.5,1,2
2.3.21.19.8 |  |  |  | 745.18.8 | Relocation order and revision | FDM 12-15-1, 12-15-15 |  |  | X | X | X | X | X | X |  | X | X | X | Each | 0.5 | 0.5 | 1 | [58 empty] | 0.5,0.5,1
2.4 |  | Environmental and Cultural Impact (8/4/16)
2.4.1 |  |  | 762 | Analyze Socio-Economic and Physical Environment Impacts (8/4/16)
2.4.1.1 |  |  |  | 762 | Analyze air, noice, agricultural, and environmental justice impacts.
2.4.1.2 |  |  |  | 762.1 | Conduct air quality analyses | 22
2.4.1.2.1 |  |  |  | 762.1.1 | Overview of conformity and disucssion of MSATs | 22 | [12 empty] | Project | 16 | 36 | 48* | [20 empty] | 12-28-36 |  | 4-8-12
2.4.1.2.2 |  |  |  | 762.1.2 | Review/compare carbon monoxide | 22 | [12 empty] | Project | 40 | [22 empty] | 20 | 12 | 8
2.4.1.2.3 |  |  |  | 762.1.3 | Run air quality model | 22 | [12 empty] | Project | 96* | [22 empty] | 56 | 24 | 16
2.4.1.3 |  |  |  | 762.2 | Conduct farmland studies | FDM 21-25-35; FDM 24-10-15; NRCS form AD-1006 or CPA-106 |  |  |  |  | X | X | X | X |  | X | X |  | Project |  | 16 | [21 empty] | 12 |  | 4
2.4.1.3.1 |  |  |  | 762.2.1 | Conduct farmland studies with low to moderate impacts | FDM 21-25-30; FDM 24-10-15; Ag Impact Notice |  |  |  |  | X | X | X | X |  | X | X |  | Owner | 2 | 6 | 8 | [20 empty] | 1-4-6 |  | 1-2-2
2.4.1.3.2 |  |  |  | 762.2.2 | Conduct farmland studies with high impacts | FDM 21-25-30; FDM 24-10-15; Ag Impact Notice |  |  |  |  | X | X | X | X |  | X | X |  | Owner |  |  | 10 | [20 empty] | 0-0-6 |  | 0-0-4
2.4.1.4 |  |  |  | 762.3 | Review economic factors (general, business, agriculture) | 25-5-10; 25-5-18; 25-5-20 |  | X | X | X | X | X | X | X | X | X | X | X | Buisness | 1 | 2 | 4 | [20 empty] | 1-2-3 |  | 0-0-1
2.4.1.5 |  |  |  | 762.4 | Review community and residential issues | 25-5-5; 25-5-30; 25-10-5
2.4.1.5.1 |  |  |  | 762.4.1 | Evaluate right of way impacts | [5 empty] | X | X | X | X |  | X | X |  | Owner | 1 | 2 | 4 | [20 empty] | 1-1-2 |  | 0-1-2
2.4.1.5.2 |  |  |  | 762.4.2 | Evaluate relocation impacts | 25-5-30 |  |  |  |  | X | X | X | X |  | X | X |  | Relocation | 20 | 24 | 32 | [20 empty] | 16-18-24 |  | 4-6-8
2.4.1.5.3 |  |  |  | 762.4.3 | Collect/obtain socio-economic data | 25-10-1 |  |  |  | X | X | X | X | X |  | X | X | X | Project | 8 | 20 | 40 | [20 empty] | 6-16-32 |  | 2-4-8
2.4.1.5.4 |  |  |  | 762.4.4 | Collect/obtain population data | 25-10-5 |  | X | X | X | X | X | X | X | X | X | X | X | Project | 2 | 4 | 6 | [20 empty] | 2-4-6
2.4.1.5.5 |  |  |  | 762.4.5 | Evaluate impacts to environmental justice and Title VI populations | 20-10-35; 20-5-35; 25-5-5 |  | X | X | X | X | X | X | X | X | X | X | X | Affected resident or business | 1 | 4 | 10 | [21 empty] | 1-3-8 | 0-1-2
2.4.1.5.6 |  |  |  | 762.4.6 | Evaluate transportation, access, and alternate mode impacts | 25-5-2 |  | X | X | X | X | X | X | X | X | X | X | X | Project | 2 | 8 | 16 | [21 empty] | 2-6-12 | 0-2-4
2.4.1.5.7 |  |  |  | 762.4.7 | Obtain land use plans | 25-5-15 |  |  |  |  | X | X | X | X |  | X | X |  | Project | 2 | 4 | 6 | [20 empty] | 1-3-4 |  | 1-1-2
2.4.1.5.8 |  |  |  | 762.4.8 | Complete indirect and cumulative effects pre-screening worksheets | 25-5-17; Pre-Screening Worksheets | [6 empty] | X | X |  | X |  |  | Project | 8 | 12 | 20 | [21 empty] | 6-10-16 | 2-2-4
2.4.1.5.9 |  |  |  | 762.4.9 | Conduct indirect effects analysis | 25-5-17; Indirect and Cumulative Effect Analysis for Project-Induced Land Development: Technical Reference Guidance Document; WisDOT Guidance for Conducting an Indirect Effects Analysis | [6 empty] | X | X |  | X |  |  | Project |  | 96 | 176 | [21 empty] | 0-72-120 | 0-24-56
2.4.1.5.10 |  |  |  | 762.4.10 | Conduct cumulative effects analysis | 25-5-17; Indirect and Cumulative Effect Analysis for Project-Induced Land Development: Technical Reference Guidance Document; WisDOT Guidance for Conducting a Cumulative Effects Analysis | [6 empty] | X | X |  | X |  |  | Project |  | 60 | 120 | [21 empty] | 0-48-96 | 0-12-24
2.4.1.5.11 |  |  |  | 762.4.11 | Evaluate aesthetic impacts | 27-10 |  | X | X | X | X | X | X | X | X | X | X | X | Project |  | 4 | 40 | [20 empty] | 0-4-32 |  | 0-0-8
2.4.1.5.12 |  |  |  | 762.4.12 | Evaluate construction noise impacts | 23-40 |  | X | X | X | X | X | X | X | X | X | X | X | Project | 2 | 4 | 12 | [20 empty] | 2-3-8 |  | 0-1-4
2.4.1.6 |  |  |  | 762.5 | Perform noise analysis | 23
2.4.1.6.1 |  |  |  | 762.5.1 | Perform field review/measurement for sound quality impact | 23-20-5 |  |  |  |  | X |  | X | X |  |  |  |  | Sampling Site | 8 | 6 | 4 | [20 empty] | 6-4-3 |  | 2-2-1
2.4.1.6.2 |  |  |  | 762.5.2 | Set up existing conditions model | 23-20-10; 23-25-10 |  |  |  |  | X |  | X | X |  |  |  |  | Model | 8 | 16 | 24 | [20 empty] | 8-16-24
2.4.1.6.3 |  |  |  | 762.5.3 | Set up future no-build model | 23-20-10; 23-25-10 |  |  |  |  | X |  | X | X |  |  |  |  | Model | 4 | 8 | 16 | [20 empty] | 4-8-16
2.4.1.6.4 |  |  |  | 762.5.4 | Set up build model | 23-20-10; 23-25-10 |  |  |  |  | X |  | X | X |  |  |  |  | Model | 8 | 16 | 24 | [20 empty] | 8-14-20 |  | 0-2-4
2.4.1.6.5 |  |  |  | 762.5.5 | Create sound quality report | 23-45 |  |  |  |  | X |  | X | X |  |  |  |  | Receptor | 3 | [22 empty] | 2 |  | 1
2.4.1.6.6 |  |  |  | 762.5.6 | Identify impacted receptors (owners and occupants) | 23-30 |  |  |  |  | X |  | X | X |  |  |  |  | Receptor | 1 | [22 empty] | 1
2.4.1.6.7 |  |  |  | 762.5.7 | Perform noise wall analysis | 23-30-1; 23-30-2; 23-25-5; 23-36-6; 23-35-7, 23-25-10, 23-25-15; 23-35-20 |  |  |  |  | X |  | X | X |  |  |  |  | Project | 24 | 36 | 50 | [20 empty] | 16-24-32 | 6-8-12 | 2-4-6
2.4.1.6.8 |  |  |  | 762.5.8 | Conduct Public Involvement Meeting for Noise Abatement Measures | 23-35-20 |  |  |  |  | X |  | X | X |  |  |  |  | Meeting | 52 | 72 | 96 | [20 empty] | 24-32-40 | 16-24-32 | 12-16-24
2.4.1.6.9 |  |  |  | 762.5.9 | Prepare, mail and tabulate Noise Wall Voting Ballot | 23-35-20 |  |  |  |  | X |  | X | X |  |  |  |  | Ballot | 2 | 4 | [21 empty] | 2-4-0
2.4.1.6.10 |  |  |  | 762.5.10 | Follow-up/request unreturned ballots | 23-35-20 |  |  |  |  | X |  | X | X |  |  |  |  | Ballot | 2 | [22 empty] | 1 |  | 1
2.4.1.6.11 |  |  |  | 762.5.11 | Document Noise Analysis, Voting, and Barrier Selection Process | 23-35-20 |  |  |  |  | X |  | X | X |  |  |  |  | Project | 8 | 12 | 16 | [20 empty] | 6-10-12 |  | 2-2-4
2.4.1.6.12 |  |  |  | 762.5.12 | Coordinate Results with WisDOT | 23-35-20 |  |  |  |  | X |  | X | X |  |  |  |  | Project | 4 | [24 empty] | 4
2.4.2 |  |  | 763 | Analyze Archaeological and Historical Impact and Tribal Consultation (7/27/16)
2.4.2.1 |  |  |  | 763 | Archaeological and historical impact analysis | FDM Ch 26
2.4.2.2 |  |  |  | 763.1 | Identify Consulting Parties/Notify | FDM 26-5-2 |  | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 16 | 24 | [6 empty] | 1-2-4 | [68 empty] | 3-5-6 | [5 empty] | 4-9-14
2.4.2.3 |  |  |  | 763.2 | Does the project have the potential to affect historic properties (screening list) | FDM 26-5-1 |  | X | X | X |  |  |  |  | X |  |  | X | project | 4 | X | 24 | [80 empty] | 1-X-4 | [6 empty] | 2-X-18 | 1-X-2
2.4.2.4 |  |  |  | 763.3 | Determine Area of Potential Effect | FDM 26-5-3 |  | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 22 | [6 empty] | 2-4-10 | [73 empty] | 0-2-6 | [6 empty] | 0-2-6
2.4.2.5 |  |  |  | 763.4 | Conduct archaeological and historical surveys (Identification Step) | FDM 26-5-4
2.4.2.5.1 |  |  |  | 763.4.1 | Conduct archaeological surveys | FDN 26-5-4 |  | X | X | X | X | X | X | X | X | X | X | X | acre | 1.5 | 4 | 10 | [75 empty] | 0.25-0.5-1 | [11 empty] | 1-3-8 | 0.25-0.5-1
2.4.2.5.2 |  |  |  | 763.4.2 | Conduct historical surveys | FDM 26-5-4 |  | X | X | X | X | X | X | X | X | X | X | X | mile | 25 | 50 | 110 | [75 empty] | 2-4-15 | [11 empty] | 20-40-80 | 3-6-15
2.4.2.6 |  |  |  | 763.5 | Determine if Eligible Properties are present (evaluation) | FDM 26-5-5
2.4.2.6.1 |  |  |  | 763.5.1 | DOE - archaeology | FDM 26-5-5 |  |  | X | X | X | X | X | X | X | X | X | X | per cubic meter excavated | 40 | 100 | 240 | [75 empty] | 5-10-15 | [11 empty] | 30-78-200 | 5-12-25
2.4.2.6.2 |  |  |  | 763.5.2 | DOE - history | FDM 26-5-5 |  |  | X | X | X | X | X | X | X | X | X | X | per potentially eligible property | 65 | 145 | 250 | [75 empty] | 5-10-20 | [11 empty] | 50-120-200 | 10-15-30
2.4.2.7 |  |  |  | 763.6 | Determine if there is an effect (if NRHP listed/eligible property present) | FDM 26-5-6 | [12 empty] | per eligible property | 6 | X | 40 | [6 empty] | 2-X-6 | [80 empty] | 4-X-34
2.4.2.8 |  |  |  | 763.7 | Complete/submit Section 106 Review Form |  |  |  | X | X | X | X | X | X | X | X | X | X | per project | 16 | X | 32 | [6 empty] | 6-X-10 | [73 empty] | 4-X-12 | [6 empty] | 6-X-10
2.4.2.9 |  |  |  | 763.8 | Assess Effects (if NRHP listed or eligible properties are affected) | FDM 26-5-7
2.4.2.9.1 |  |  |  | 763.8.1 | Prepare Determination of No Adverse Effect (DNAE) or Conditional No Adverse Affect (CNAE) | FDM 26-5-7 |  |  | X | X | X | X | X | X | X | X | X | X | per project | 25 | 90 | 144 | [6 empty] | 2-8-12 | [68 empty] | 1-5-10 |  |  |  |  | 10-20-30 | [6 empty] | 10-50-80 | 2-7-12
2.4.2.9.2 |  |  |  | 763.8.2 | Resolution of Adverse Effects | FDM 26-5-8
2.4.2.9.2.1 |  |  |  | 763.8.2.1 | Prepare Finding of Adverse Affect (FAE aka DforC, now through e106) | FDM 26-5-8 |  |  | X | X | X | X | X | X | X | X | X | X | per project | 25 | 90 | 144 | [6 empty] | 2-8-12 | [68 empty] | 1-5-10 |  |  |  |  | 10-20-30 | [6 empty] | 10-50-80 | 2-7-12
2.4.2.9.2.2 |  |  |  | 763.8.2.2 | Develop and Evaluate Measures to Avoid, Minimize, or Mitigate Adverse Effects to Historic Properties. Prepare MOA. Obtain agreement on stipulations of MOA. Obtain signatures on MOA. | FDM 26-5-8 |  |  | X | X | X | X | X | X | X | X | X | X | per project | 50 | 120 | 300 | [6 empty] | 12-35-100 | [73 empty] | 6-20-60 | [6 empty] | 30-60-120 | 2-5-20
2.4.2.10 |  |  |  | 763.9 | Implementation of commitments or stipulations | FDM 26-5-9 |  | X | X | X | X | X | X | X | X | X | X | X | per project | 10 | 60 | 600 | [6 empty] | 2-10-100 | [73 empty] | 4-20-100 | [6 empty] | 4-25-350 | 0-5-50
2.4.2.11 |  |  |  | 763.1 | State Burial Site Law (Wisconsin 157.70) | FDM 26-25-1
2.4.2.11.1 |  |  |  | 763.10.1 | determine whether the boundary of the cemetery or other type of burial site extends into the project's APE | FDM 26-25-1.2 |  | X | X | X | X | X | X | X | X | X | X | X | per burial site | 8 | 16 | 40 | [6 empty] | 1-2-6 | [80 empty] | 7-14-34
2.4.2.11.2 |  |  |  | 763.10.2 | petition for permission to work within the boundaries of the site | FDM 26-25-1.3 |  | X | X | X | X | X | X | X | X | X | X | X | per project | 4 | 4 | 4 | [6 empty] | 1 | [73 empty] | 3
2.4.2.12 |  |  |  | 763.11 | prepare Section 4(f) determination | FDM 26-35-5.1.3 |  |  | X |  | X | X | X | X |  |  | X | X | per 4(f) property with use | 10 | 40 | 120 | [6 empty] | 6-30-95 | [73 empty] | 4-10-25
2.4.3 |  |  | 765 | Analyze Hazardous Materials Site Impact (7/29/16)
2.4.3.1 |  |  |  | 765 | Investigation of potentially contaminated sites. Includes Phase 1-3 investigation, Phase 4 remediation, and asbestos inspection and abatement | FDM 21-35 (potentially exempt projects 21-35-1.5)
2.4.3.2 |  |  |  | 765.1 | Perform Phase 1 hazardous materials assessment | 21-35-5 |  |  |  |  | x | x | x | x | x |  | x | x |  | 71 | 175 | 400
2.4.3.2.1 |  |  |  | 765.1.1 | Data Collection and Review | 21-35-5.3 (1) | [12 empty] | hours, per project | 16 | 70 | 150 | [80 empty] | 16/70/150 Entry level
2.4.3.2.2 |  |  |  | 765.1.2 | Field reconnaisance | 21-35-5.3 (2) | [12 empty] | hours, per project | 10 | 30 | 50 | [80 empty] | 10/30/50 Entry level
2.4.3.2.3 |  |  |  | 765.1.3 | Data evaluation and review, prepare conclusions and recommendations; Prepare site summaries and draft/final hazardous materials report | 21-35-5.3 (3) | [12 empty] | hours, per project | 45 | 75 | 200 | [80 empty] | 40/70/195 entry level, mid level review | 3-3-3 | [8 empty] | 2-2-2
2.4.3.3 |  |  |  | 765.2 | Perform additonal hazardous materials assessment | [5 empty] | x | x | x | x | x |  | x | x
2.4.3.3.1 |  |  |  | 765.2.1 | Perform field investigation and phase 2 report | 21-35-10 | [12 empty] | hours, per site | 70 | 100 | 150 | [22 empty] | 2-2-2 | [52 empty] | 1, 3, 5 |  |  |  |  | 65-95-135 | 3-3-3
2.4.3.3.2 |  |  |  | 765.2.2 | Perform Phase 2.5 investigation, develop materials handling plan and special provisions | 21-35-12 |  |  |  |  | x | x | x | x | x |  | x | x | hours, per project | 30 | 150 | 300 | [22 empty] | 2-5-10 | [43 empty] | 5-7-10 | [8 empty] | 1-5-15 |  |  |  |  | 18-12-240 | 3-3-3 | [8 empty] | 2-10-20
2.4.3.3.2.1 |  |  |  | 765.2.2.1 | Prepare phase 2.5 report | 21-35-12.5 | [12 empty] | Included in above number
2.4.3.3.2.2 |  |  |  | 765.2.2.2 | Obtain DNR concurrence on materials handling plan | 21-35 attachment 12.1 | [12 empty] | Included in above number
2.4.3.3.3 |  |  |  | 765.2.3 | Perform Phase 3 investigation, Determinefull nature and extent of contamination and prepare remediation plan | 21-35-15 |  |  |  |  | x | x | x | x | x |  | x | x | hours, per site | 65 | 300 | 520 to 1000 or more | [22 empty] | 5-10-40 | [43 empty] | 5-10-30 | [8 empty] | 3-15-30 | [5 empty] | 5-5-5 | [8 empty] | 40, 250, 400 to 800
2.4.3.3.3.1 |  |  |  | 765.2.3.1 | Perform field investigation | 21-35-15.4 (3) | [12 empty] | Included in above number
2.4.3.3.3.2 |  |  |  | 765.2.3.2 | Develop remediation plan | 21-35-15.5 | [12 empty] | Included in above number
2.4.3.3.3.3 |  |  |  | 765.2.3.3 | Obtain DNR Concurrence on Remediation Plan | 21-35-15.8 | [12 empty] | Included in above number
2.4.3.3.3.4 |  |  |  | 765.2.3.4 | Prepare Phase 3 report | [13 empty] | Included in above number
2.4.3.3.5 |  |  |  | 765.2.4 | Perform Phase 4 Hazardous Materials Remediation and Materials Management | 21-35-20 |  |  |  |  | x | x | x | x | x | x | x | x | Hours, per site | 100 to 300 | 600 | 1000 or more | [22 empty] | 5-10-50 | [43 empty] | 5-25-50 | [8 empty] | 10-20-40 |  |  |  |  | 70 to 200, 500,700 | 5-5-5 (accounting and report production) | [8 empty] | 10-50-150
2.4.3.3.5.1 |  |  |  | 765.2.4.1 | Prepare phase 4 report, site closure package | 21-35-20.5 |  |  |  |  | x | x | x | x | x |  | x | x | Included in above number
2.4.3.4 |  |  |  | 765.3 | Conduct asbestos inspection | 21-35-45 |  |  |  |  | x | x | x | x | x | x | x | x | per structure | 15 | 35 | 100 | [22 empty] | 2-2-2 | [24 empty] | 1.5-1.5-1.5 | [27 empty] | 1-1-1 | [5 empty] | 2-2-2 | [11 empty] | 10-30-95 | [10 empty] | 0.5 - .5 .-.5
2.4.3.5 |  |  |  | 765.4 | Conduct asbestos abatement | [9 empty] | x | x | x | x | Per structure | 50 | 150 | 200 | [22 empty] | 2-2-2 | [24 empty] | 2-2-2 | [32 empty] | 10-30-55 | 3-3-3 | [12 empty] | 5-15-20 | 5-15-20 | 30-90-120 | 30-90-120 | [6 empty] | 1-1-1
2.4.3.5.1 |  |  |  | 765.4.1 | Prepare abatement plan | [111 empty] | x | x
2.4.3.5.2 |  |  |  | 765.4.2 | Prepare notification of Demolition | [113 empty] | x
2.4.3.5.3 |  |  |  | 765.4.3 | conduct abatement | [113 empty] | x | x
2.4.3.5.4 |  |  |  | 765.4.4 | prepare and submit abatement report and disposal documentation
2.4.4 |  |  | 766 | Analyze Natural Environment Impact (7/27/16)
2.4.4.1 |  |  |  | 766 | Analyze impact to natural environment (wetlands, streams, lakes, upland), coordinate with resource agencies, and develop permits and mitigation measures.
2.4.4.2 |  |  |  | 766.1 | Evaluate impact on wetlands | Wetlands - C1
2.4.4.2.1 |  |  |  | 766.1.1 | Determine presence and delineate exisiting wetlands | FDM 21-25-20 and 24-5-10,21-30-1 |  | X | X | X | X | X | X | X | X | X | X | X | mile | 8 | 20 | 40 | [6 empty] | 2-5-10 | [68 empty] | 1-2-5 |  |  |  |  | 5-13-25
2.4.4.2.2 |  |  |  | 766.1.2 | Determine and Quantify wetland and waterway impacts | FDM 21-30-1 |  | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 8 | 40 | [6 empty] | 0-3-15 | [68 empty] | 0-1-5 |  |  |  |  | 0-4-20
2.4.4.2.3 |  |  |  | 766.1.3 | Prepare wetland finding if needed | FDM 21-30-1; Factor Sheet C1 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 24 | 24 | [6 empty] | 0-12-12 | [73 empty] | 0-12-12
2.4.4.2.4 |  |  |  | 766.1.4 | Develop 401/404 permit application | 21-30-1.1 and 21-30-1.2 |  | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 56 | 96 | [6 empty] | 0-20-30 | [68 empty] | 0-6-16 |  |  |  |  | 0-30-50
2.4.4.3 |  |  |  | 766.2 | Evaluate impacts to rivers, streams and floodplains | Rivers, Streams, and Floodplains - C2
2.4.4.3.1 |  |  |  | 766.2.1 | Inventory resources, document impacts and mitigation | FDM 24-5-5, Factor Sheet C2 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 16 | 24 | [6 empty] | 1-2-4 | [68 empty] | 1-2-4 |  |  |  |  | 2-12-16
2.4.4.3.2 |  |  |  | 766.2.2 | Obtain permits/approvals as applicable: USACE - Section 10 (with 404 permit), Section 408 USCG Section 9 | FDM 21-25-25 |  | X | X | X | X | X | X | X | X | X | X | X | project | 0 | 24 | 40 | [6 empty] | 0-8-16 | [68 empty] | 0-2-4 |  |  |  |  | 0-14-20
2.4.4.4 |  |  |  | 766.3 | Evaluate impacts to lakes and other open water | Lakes or other Open Water - C3
2.4.4.4.1 |  |  |  | 766.3.1 | Inventory resources, document impacts and mitigation | FDM 24-5-5, Factor Sheet C3 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 24 | [6 empty] | 1-2-4 | [68 empty] | 1-2-4 |  |  |  |  | 2-4-16
2.4.4.5 |  |  |  | 766.4 | Evaluate impacts to groundwater wells and springs | Groundwater, Wells and Springs - C4
2.4.4.5.1 |  |  |  | 766.4.1 | Inventory resources (locate wells and springs), document impacts and mitigation | FDM 24-5-5, Factor Sheet C4 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 24 | [6 empty] | 1-2-4 | [68 empty] | 1-2-4 |  |  |  |  | 2-4-16
2.4.4.6 |  |  |  | 766.5 | Evaluate impacts to upland habitat | Upland Wildlife and Habitat - C5
2.4.4.6.1 |  |  |  | 766.5.1 | Inventory resources (habitat and wildlife), document impacts | FDM 24-10 and 24-15, Factor Sheet C5 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 24 | [6 empty] | 1-2-4 | [68 empty] | 1-2-4 |  |  |  |  | 2-4-16
2.4.4.7 |  |  |  | 766.6 | Evaluate impact to coastal zones | Coastal Zones - C6
2.4.4.7.1 |  |  |  | 766.6.1 | Identify if project is in Coastal Zone, coordinate with Coastal Management Program, obtain coastal zone consistency determination | FDM 5-10-35.2; 20-30-1.4, Factor Sheet C6 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 8 | 24 | [6 empty] | .5-2-4 | [68 empty] | .5-2-4 |  |  |  |  | 1-4-16
2.4.4.8 |  |  |  | 766.7 | Evaluate impacts to Threatened and Endangered Species | Threatened and Endangered Species - C7
2.4.4.8.1 |  |  |  | 766.7.1 | Determine if any species are present in project area (IPaC/official species list for federally listed species, NHI review for state listed species) | FDM 20-25-1, Factor Sheet C7 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 6 | [8 empty] | 6 | [73 empty] | 6
2.4.4.8.2 |  |  |  | 766.7.2 | Survey for species/habitat | FDM 20-25-1 |  | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 50 | 100 | [75 empty] | 4-10-15 |  |  |  |  | 16-40-85
2.4.4.8.3 |  |  |  | 766.7.3 | Evaluate impacts and make effect determinations for species/critical habitat | FDM 20-25-1 |  | X | X | X | X | X | X | X | X | X | X | X | listed species | 1 | 5 | 20 | [6 empty] | .5-2-5 | [73 empty] | .5-3-15
2.4.4.8.4 |  |  |  | 766.7.4 | Agency Consultation | FDM 20-25-1
2.4.4.8.4.1 |  |  |  | 766.7.4.1 | Federally Listed Species (Section 7 Consultation): United States Fish and Wildlife Service (USFWS) | FDM 20-25-1 |  | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 6 | 150 | [6 empty] | 1-2-40 | [73 empty] | 1-4-110
2.4.4.8.4.2 |  |  |  | 766.7.4.2 | State Listed Species: Wisconsin Department of Natural Resources (WDNR) | FDM 20-25-1 |  | X | X | X | X | X | X | X | X | X | X | X | project | 1 | 8 | 70 | [6 empty] | .5-3-20 | [73 empty] | .5-5-50
2.4.4.8.5 |  |  |  | 766.7.5 | Relocations (mussels, rare plants, host plants, etc.) | FDM 20-25-1 |  | X | X | X | X | X | X | X | X | X | X | X | project | 24 | 50 | 150 | [80 empty] | 24-50-150
2.4.4.9 |  |  |  | 766.8 | Analyze Drainage and Stormwater Impacts | Stormwater - D5
2.4.4.9.1 |  |  |  | 766.8.1 | Determine and document project's effect on drainage/stormwater | FDM 10, Factor Sheet D5 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 16 | 32 | [6 empty] | 3-14-28 | [73 empty] | 1-2-4
2.4.4.10 |  |  |  | 766.9 | Section 4(f) – This section covers parks/refuges only. Historical 4(f) is covered under 763.11 | Section 4(f) and 6(f) or Other Unique Areas - B8
2.4.4.10.1 |  |  |  | 766.9.1 | Determine if Section 4(f) properties are present | FDM 21-25-1, Factor Sheet B8 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 16 | 24 | 40 | [6 empty] | 2-3-6 | [68 empty] | 4-6-8 |  |  |  |  | 10-15-26
2.4.4.10.2 |  |  |  | 766.9.2 | Determine if there is a "use" of the 4(f) property | FDM 21-25-1, Factor Sheet B8 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 24 | 40 | [6 empty] | 8-9-12 | [68 empty] | 4-5-8 |  |  |  |  | 8-10-20
2.4.4.10.3 |  |  |  | 766.9.3 | Prepare Section 4(f) Evaluation | FDM 21-25-1, Factor Sheet B8 guidance |  | X | X | X | X | X | X | X | X | X | X | X | property | 40 | 60 | 160 | [6 empty] | 35-55-120 | [73 empty] | 5-5-40
2.4.4.11 |  |  |  | 766.1 | Section 6(f) and other grant funded properties | Section 4(f) and 6(f) or Other Unique Areas - B8
2.4.4.11.1 |  |  |  | 766.10.1 | Identify if any properties have special funding associated with them | FDM 21-25-5, Factor Sheet B8 guidance |  | X | X | X | X | X | X | X | X | X | X | X | project | 16 | 24 | 32 | [6 empty] | 4-6-8 | [69 empty] | 4-6-8 |  |  |  | 8-12-16
2.4.4.11.2 |  |  |  | 766.10.2 | Identify replacement property, if required; prepare Section 6(f) conversion request | FDM 21-25-5, Factor Sheet B8 guidance |  | X | X | X | X | X | X | X | X | X | X | X | property | 70 | 110 | 190 | [6 empty] | 10-20-40 | [69 empty] | 10-20-40 |  |  |  | 40-50-70 | [10 empty] | 10-20-40
2.4.4.12 |  |  |  | 766.11 | Specialty - Storm water management
2.4.4.13 |  |  |  | 766.12 | Specialty - Biological services
2.4.5 |  |  | 769 | Environmental Documentation and Agency Coordination (7/26/16)
2.4.5.1 |  |  |  | 769 | Prepare and review environmental document
2.4.5.2 |  |  |  | 769.1 | Initial Agency and Tribal Coordination
2.4.5.2.1 |  |  |  | 769.1.1 | WDNR - General Coordination & Assessment | FDM 5-10-1 |  | X | X | X | X | X | X | X | X | X | X | X | 1 Letter | 10 | 16 | 24 | [21 empty] | 8/12/18 | 2/4/4 | 0/0/2
2.4.5.2.2 |  |  |  | 769.1.2 | USFWS | FDM 5-5-10 |  | X | X | X | X | X | X | X | X | X | X | X | 1 Letter | 3 | 5 | 8 | [20 empty] | 1/2/3 | 1/2/3 | 1/1/2
2.4.5.2.3 |  |  |  | 769.1.3 | Bureau of Indian Affairs - Native American Tribes | FDM 5-15-10 and Environmental Webpage |  | X | X | X | X | X | X | X | X | X | X | X | Letter Batch | 16 | 16 | 24 | [20 empty] | 6/6/10 | 6/6/10 | 3/3/3 | 1/1/1
2.4.5.2.4 |  |  |  | 769.1.4 | BOA | FDM 5-10-25 |  |  |  |  | X | X | X | X |  | X |  |  | 1 Letter | 10 | 24 | 24 | [20 empty] | 4/9/9 | 4/9/9 | 2/4/4 | 0/2/2
2.4.5.2.5 |  |  |  | 769.1.5 | FAA | [5 empty] | X | X | X | X |  | X |  |  | 1 Letter
2.4.5.2.6 |  |  |  | 769.1.6 | County Drainage Board | FDM 5-15-1 |  | X | X | X | X | X | X | X | X | X | X | X | 1 Letter | 2 | 8 | 8 | [22 empty] | 2/8/8
2.4.5.2.7 |  |  |  | 769.1.7 | USACE | FDM 5-5-20 |  | X | X | X | X | X | X | X | X | X | X | X | 1 Letter | 8 | 12 | 16 | [20 empty] | 3/5/5 | 3/5/5 | 2/2/4 | 0/0/2
2.4.5.2.8 |  |  |  | 769.1.8 | US EPA | 2015 Red Book |  |  |  |  | X | X | X | X |  |  |  |  | 1 Letter | 16 | 16 | 16 | [21 empty] | 8/8/8 | 6/6/6 | 2/2/2
2.4.5.2.9 |  |  |  | 769.1.9 | Local Agency Coordination | FDM 3-10-1 |  | X | X | X | X | X | X | X | X | X | X | X | 1 Letter per agency | 6 | 8 | 10 | [21 empty] | 4/6/8 | 2/2/2
2.4.5.2.10 |  |  |  | 769.1.10 | Add'l Coord. ( NPS, NRCS, USGS) |  |  | X | X | X | X | X | X | X | X | X | X | X | 1 Letter | 8 | 12 | 16 | [21 empty] | 6/10/10 | 2/2/4 | 0/0/2
2.4.5.3 |  |  |  | 769.2 | Determine document type | FDM 21-5 |  | X | X | X | X | X | X | X | X | X | X | X |  | 8 | 8 | 8 | [22 empty] | 6 | 2
2.4.5.4 |  |  |  | 769.3 | Prepare draft project initiation letter, submit to REC | FDM 21-10-1 23 USC 139(e) |  |  |  | X |  |  | X | X | X |  |  |  | 1 Letter | 10 | 10 | 10 | [21 empty] | 5/5/5 | 4/4/4 | 1/1/1
2.4.5.5 |  |  |  | 769.4 | Categorical Exclusion Checklist |  |  | X | X | X | [5 empty] | X | X | X | Each | 54 | 54 | 54 | [20 empty] | 18 | 18 | 14 | 4
2.4.5.6 |  |  |  | 769.5 | Programmatic Categorical Exclusion |  |  | X | X | X |  |  |  |  | X | X | X | X | Each | 60 | 60 | 60 | [20 empty] | 20 | 20 | 16 | 4
2.4.5.7 |  |  |  | 769.6 | Environmental Report
2.4.5.7.1 |  |  |  | 769.6.1 | Environmental Report Basic Sheets |  |  |  |  | X | X | X | X | X |  | X | X | X | LS | 70 | 100 | 130 | [20 empty] | 25/40/50 | 25/40/45 | 15/20/25 | 5/5/10
2.4.5.7.2 |  |  |  | 769.6.2 | Environmental Report Factor Sheets |  |  |  |  | X | X | X | X | X |  | X | X | X | Each | 8 | 16 | 20 | [20 empty] | 5/10/14 |  | 2/5/5 | 1/1/1
2.4.5.7.3 |  |  |  | 769.6.3 | Environmental Report Appendices |  |  |  |  | x | X | X | X | X |  | X | X | X | LS | 12 | 18 | 24 | [20 empty] | 10/16/20 |  | 2/2/4
2.4.5.8 |  |  |  | 769.7 | Environmental Assessment
2.4.5.8.1 |  |  |  | 769.7.1 | Environmental Assessment Basic Sheets | [5 empty] | X | X | X | X |  |  |  |  | LS | 95 | 135 | 180 | [20 empty] | 30/50/75 | 35/50/75 | 20/25/30 | 10/10/10
2.4.5.8.2 |  |  |  | 769.7.2 | Environmental Assessment Factor Sheets | [5 empty] | X | X | X | X |  |  |  |  | Factor Sheet | 8 | 16 | 20 | [20 empty] | 3/5/7 | 2/5/7 | 2/5/5 | 1/1/1
2.4.5.8.3 |  |  |  | 769.7.3 | Environmental Assessment Appendices | [5 empty] | X | X | X | X |  |  |  |  | LS | 12 | 18 | 24 | [20 empty] | 5/8/10 | 5/8/10 | 2/2/4
2.4.5.8.4 |  |  |  | 769.7.4 | Environmental Assessment NOA, Dist, and Comment Period | [5 empty] | X | X | X | X |  |  |  |  | Each | 32 | 46 | 58 | [20 empty] | 10/15/20 | 10/15/20 | 10/12/14 | 2/4/4
2.4.5.8.5 |  |  |  | 769.7.5 | Environmental Assessment Public Hearing | [5 empty] | X | X | X | X |  |  |  |  | Each | 120 | 180 | 270 | [20 empty] | 35/60/100 | 35/60/100 | 30/40/50 | 20/20/20
2.4.5.8.6 |  |  |  | 769.7.6 | Environmental Assessment Addendum A | [5 empty] | X | X | X | X |  |  |  |  | Each | 16 | 28 | 36 | [20 empty] | 6/12/18 |  | 8/14/14 | 2/2/4
2.4.5.8.7 |  |  |  | 769.7.7 | FONSI | [5 empty] | X | X | X | X |  |  |  |  | Each | 8 | 8 | 8 | [20 empty] | 2 |  | 4 | 2
2.4.5.8.8 |  |  |  | 769.7.8 | Agency Meeting | [5 empty] | X | X | X | X |  |  |  |  | Each | 45 | 65 | 100 | [20 empty] | 10/15/20 | 15/25/35 | 15/20/35 | 5/5/10
2.4.5.9 |  |  |  | 769.8 | Environmental Impact Statement
2.4.5.9.1 |  |  |  | 769.8.1 | Prepare draft notice of intent to prepare an EIS | [5 empty] | X |  | X | [5 empty] | Each | 10 | 10 | 10 | [22 empty] | 6 | 4
2.4.5.9.2 |  |  |  | 769.8.2 | Identify lead, participating, and cooperating agencies | FDM 21-10-5 |  |  |  |  | X |  | X | [5 empty] | Each | 12 | 12 | 18 | [22 empty] | 8/8/14 | 4/4/4
2.4.5.9.3 |  |  |  | 769.8.3 | Prepare Draft Coordination plan | * none of these documents can be finalized without input. FDM 21-10-13 |  |  |  |  | X |  | X | [5 empty] | Each | 40 | 80 | 110 | [21 empty] | 30/60/90 | 8/16/16 | 2/4/4
2.4.5.9.4 |  |  |  | 769.8.4 | Update Coordination plan | * none of these documents can be finalized without input. FDM 21-10-13 |  |  |  |  | X |  | X | [5 empty] | Each | 24 | 32 | 40 | [20 empty] | 12/18/24 | 6/8/10 | 6/6/6
2.4.5.9.5 |  |  |  | 769.8.5 | Prepare Draft Impact Assessment Methodology(IAM) | [5 empty] | X |  | X | [5 empty] | Each | 80 | 120 | 160 | [21 empty] | 60/80/110 | 15/30/40 | 5/10/10
2.4.5.9.6 |  |  |  | 769.8.6 | Agency Meeting | FDM 21-10-15 |  |  |  |  | X |  | X | [5 empty] | Each | 65 | 100 | 140 | [20 empty] | 10/20/40 | 30/40/50 | 20/30/40 | 5/10/10
2.4.5.9.7 |  |  |  | 769.8.7 | Prepare DEIS
2.4.5.9.7.1 |  |  |  | 769.8.7.1 | Purpose and Need | [5 empty] | X |  | X | [5 empty] | Each | 100 | 160 | 220 | [20 empty] | 30/50/70 | 40/60/70 | 20/30/50 | 10/20/30
2.4.5.9.7.2 |  |  |  | 769.8.7.2 | Alternatives | [5 empty] | X |  | X | [5 empty] | Each | 240 | 360 | 480 | [20 empty] | 80/120/160 | 90/130/170 | 50/80/110 | 20/30/40
2.4.5.9.7.3 |  |  |  | 769.8.7.3 | Affected Environment | [5 empty] | X |  | X | [5 empty] | Each | 200 | 300 | 400 | [20 empty] | 100/160/220 | 60/80/120 | 20/40/40 | 20/20/20
2.4.5.9.7.4 |  |  |  | 769.8.7.4 | Environmental Consequences | [5 empty] | X |  | X | [5 empty] | Each | 500 | 750 | 1000 | [20 empty] | 200/300/335 | 160/240/335 | 100/150/250 | 40/60/80
2.4.5.9.7.5 |  |  |  | 769.8.7.5 | Cover Sheet, TOC, List of Preparers, Dist List, References, Acronyms, Index, Exhibit List | [5 empty] | X |  | X | [5 empty] | Each | 150 | 175 | 200 | [20 empty] | 80/80/80 | 50/65/80 | 10/20/30 | 10/10/10
2.4.5.9.7.6 |  |  |  | 769.8.7.6 | DEIS Appendices | [5 empty] | X |  | X | [5 empty] | Each | 60 | 90 | 120 | [21 empty] | 30/45/55 | 20/35/45 | 10/10/10
2.4.5.9.7.7 |  |  |  | 769.8.7.7 | Executive Summary | [5 empty] | X |  | X | [5 empty] | LS | 100 | 100 | 100 | [20 empty] | 40 | 40 | 15 | 5
2.4.5.9.7.8 |  |  |  | 769.8.7.8 | Comment Review Meetings During DEIS Prep | [5 empty] | X |  | X | [5 empty] | LS | 40 | 75 | 110 | [20 empty] | 15/20/35 | 10/25/35 | 10/20/25 | 5/10/15
2.4.5.9.8 |  |  |  | 769.8.8 | DEIS Release and Comment Period
2.4.5.9.8.1 |  |  |  | 769.8.8.1 | Prepare and publish Notice of Availability | [5 empty] | X |  | X | [5 empty] | Each | 28 | 28 | 28 | [21 empty] | 20 | 6 | 2
2.4.5.9.8.2 |  |  |  | 769.8.8.2 | Print and Distribute DEIS to Agencies and Individuals | [5 empty] | X |  | X | [5 empty] | Each | 100 | 140 | 180 | [20 empty] | 40/50/65 | 40/50/65 | 18/38/48 | 2/2/2
2.4.5.9.8.3 |  |  |  | 769.8.8.3 | Prepare Web-ready Document | [5 empty] | X |  | X | [5 empty] | Each | 24 | 32 | 40 | [20 empty] | 10/14/17 | 10/14/17 | 3/3/5 | 1/1/1
2.4.5.9.8.4 |  |  |  | 769.8.8.4 | Conduct Hearing | [5 empty] | X |  | X | [5 empty] | Each | 140 | 260 | 360 | [20 empty] | 40/70/85 | 40/70/85 | 50/60/70 | 5/5/5
2.4.5.9.8.5 |  |  |  | 769.8.8.5 | Collect and Categorize Comments | [5 empty] | X |  | X | [5 empty] | Each | 16 | 32 | 48 | [20 empty] | 10/20/30 | 3/8/12 | 3/4/6
2.4.5.9.8.6 |  |  |  | 769.8.8.6 | Prepare Hearing Certification for FHWA | [5 empty] | X |  | X | [5 empty] | Each | 24 | 36 | 48 | [21 empty] | 17/24/30 | 5/10/16 | 2/2/2
2.4.5.9.9 |  |  |  | 769.8.9 | Prepare FEIS and ROD
2.4.5.9.9.1 |  |  |  | 769.8.9.1 | Respond to comments and make EIS revisions | FDM 21-15-1.2.5 |  |  |  |  | X |  | X | [5 empty] | Each | 100 | 400 | 700 | [20 empty] | 30/200/300 | 20/110/260 | 40/60/100 | 10/30/40
2.4.5.9.9.2 |  |  |  | 769.8.9.2 | Document environmental commitments | http://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/environment/formsandtools.aspx |  |  |  |  | X |  | X | [5 empty] | Each | 40 | 60 | 80 | [21 empty] | 20/40/60 | 18/18/18 | 2/2/2
2.4.5.9.9.3 |  |  |  | 769.8.9.3 | Prepare Record of Decision (ROD) | [5 empty] | X |  | X | [5 empty] | Each | 100 | 160 | 200 | [20 empty] | 30/50/60 | 30/50/60 | 36/54/72 | 4/6/8
2.4.5.9.10 |  |  |  | 769.8.10 | FEIS Release and Comment Period
2.4.5.9.10.1 |  |  |  | 769.8.10.1 | Prepare and publish Notice of Availability | [5 empty] | X |  | X | [5 empty] | Each | 24 | 24 | 24 | [20 empty] | 16 |  | 6 | 2
2.4.5.9.10.2 |  |  |  | 769.8.10.2 | Print and Distribute FEIS to Agencies and Individuals | [5 empty] | X |  | X | [5 empty] | Each | 80 | 120 | 180 | [20 empty] | 60/95/150 |  | 20/25/30
2.4.5.9.10.3 |  |  |  | 769.8.10.3 | Prepare Web-ready Document | [5 empty] | X |  | X | [5 empty] | Each | 24 | 32 | 40 | [20 empty] | 20/28/36 |  | 4/4/4
2.4.5.9.10.4 |  |  |  | 769.8.10.4 | Collect and Categorize Comments | [5 empty] | X |  | X | [5 empty] | Each | NA | NA | NA
2.4.5.9.10.5 |  |  |  | 769.8.10.5 | Prepare Statute of Limitations Notice | [5 empty] | X |  | X | [5 empty] | Each | 8 | 8 | 8 | [22 empty] | 7 | 1
2.4.5.9.10 |  |  |  | 769.9 | Prepare administrative record | [5 empty] | X |  | X | [5 empty] | 100 Records | 12 | 20 | 36 | [20 empty] | 11/19/34 |  | 1/1/2
2.4.5.9.11 |  |  |  | 769.1 | Carry out environmental commitments | [5 empty] | X |  | X
2.4.5.9.12 |  |  |  | 769.11 | Prepare DRR or other Amended Environmental Documentation | [5 empty] | X |  | X | [5 empty] | Each | 60 | 120 | 200 | [21 empty] | 40/85/150 | 16/30/44 | 4/5/6
2.4.5.9.13 |  |  |  | 769.12 | Revise environmental document | [5 empty] | X | X | X | X
2.5 |  | Structures (9/13/16)
2.5.1 |  |  | 647 | Develop Structure Survey Report (9/13/16)
2.5.1.1 |  |  |  | 647 | Includes development of the Structure Survey Report.
2.5.1.2 |  |  |  | 647.1 | Conduct structures site review |  |  | X | X | X | X | X | X | X | X | X | X | X | structure | 4 | 6 | 8
2.5.1.3 |  |  |  | 647.2 | Prepare structure survey report |  |  | X | X | X | X | X | X | X | X | X | X | X | structure | 16 | 24 | 40
2.5.2 |  |  | 651 | Structure Fabrication - Review and Oversight (WisDOT only)
2.5.2.1 |  |  |  | 651 | Scoping task
2.5.2.2 |  |  |  | 651.1 | Specialty - Shop inspection structural steel
2.5.3 |  |  | 653 | Structure - Liaison Activities (WisDOT only)
2.5.4 |  |  | 656 | Design Structure (9/13/16)
2.5.4.1 |  |  |  | 656.1 | Preliminary design
2.5.4.1.1 |  |  |  | 656.1.1 | Box Culvert (cast in place concrete)
2.5.4.1.1.1 |  |  |  | 656.1.1.1 | Single Cell
2.5.4.1.1.1.1 |  |  |  | 656.1.1.1.1 | BOS | [13 empty] | structure | 14 | 19 | 24
2.5.4.1.1.1.2 |  |  |  | 656.1.1.1.2 | Consultant | [13 empty] | structure | 60 | 65 | 70
2.5.4.1.1.2 |  |  |  | 656.1.1.2 | Two Cell
2.5.4.1.1.2.1 |  |  |  | 656.1.1.2.1 | BOS | [13 empty] | structure | 18 | 23 | 26
2.5.4.1.1.2.2 |  |  |  | 656.1.1.2.2 | Consultant | [13 empty] | structure | 64 | 69 | 74
2.5.4.1.2 |  |  |  | 656.1.2 | Prestressed concrete slabs and boxes | [13 empty] | structure | * | * | *
2.5.4.1.3 |  |  |  | 656.1.3 | Prestressed concrete girders
2.5.4.1.3.1 |  |  |  | 656.1.3.1 | Single span | [13 empty] | structure | 40 | 60 | 80
2.5.4.1.3.2 |  |  |  | 656.1.3.2 | Additional Span(s) | [13 empty] | span | 8 | 24 | 40
2.5.4.1.4 |  |  |  | 656.1.4 | Concrete slab
2.5.4.1.4.1 |  |  |  | 656.1.4.1 | Single span | [13 empty] | structure | 40 | 60 | 80
2.5.4.1.4.2 |  |  |  | 656.1.4.2 | Additional Span(s) | [13 empty] | span | 8 | 16 | 24
2.5.4.1.5 |  |  |  | 656.1.5 | Steel plate girders
2.5.4.1.5.1 |  |  |  | 656.1.5.1 | Single span | [13 empty] | structure | 64 | 84 | 104
2.5.4.1.5.2 |  |  |  | 656.1.5.2 | Additional Span(s) | [13 empty] | span | 8 | 28 | 48
2.5.4.1.6 |  |  |  | 656.1.6 | Retaining wall
2.5.4.1.6.1 |  |  |  | 656.1.6.1 | Cast in place concrete | [13 empty] | structure | 48 | 80 | 100
2.5.4.1.6.2 |  |  |  | 656.1.6.2 | Modular block (no MSE) | [13 empty] | structure | 40 | 52 | 64
2.5.4.1.6.3 |  |  |  | 656.1.6.3 | MSE | [13 empty] | structure | 40 | 64 | 80
2.5.4.1.6.4 |  |  |  | 656.1.6.4 | Wire face with tip-up precast panel | [13 empty] | structure | * | * | *
2.5.4.1.6.5 |  |  |  | 656.1.6.5 | Post and panel, Soldier pile | [13 empty] | structure | 48 | 72 | 88
2.5.4.1.6.6 |  |  |  | 656.1.6.6 | Sheet pile | [13 empty] | structure | * | * | *
2.5.4.1.7 |  |  |  | 656.1.7 | Sign bridge | [13 empty] | structure | * | * | *
2.5.4.1.8 |  |  |  | 656.1.8 | Noise wall | [13 empty] | structure | * | * | *
2.5.4.1.9 |  |  |  | 656.1.9 | Rigid frame | [13 empty] | sheet | * | * | *
2.5.4.1.10 |  |  |  | 656.1.10 | Rehabilitation
2.5.4.1.10.1 |  |  |  | 656.1.10.1 | Box culvert single cell extension
2.5.4.1.10.1.1 |  |  |  | 656.1.10.1.1 | BOS | [13 empty] | structure | 14 | 19 | 24
2.5.4.1.10.1.2 |  |  |  | 656.1.10.1.2 | Consultant | [13 empty] | structure | 60 | 65 | 70
2.5.4.1.10.2 |  |  |  | 656.1.10.2 | Box culvert multi cell extension
2.5.4.1.10.2.1 |  |  |  | 656.1.10.2.1 | BOS | [13 empty] | structure | 18 | 23 | 26
2.5.4.1.10.2.2 |  |  |  | 656.1.10.2.2 | Consultant | [13 empty] | structure | 64 | 69 | 74
2.5.4.1.10.3 |  |  |  | 656.1.10.3 | Deck overlay | [13 empty] | structure | 16 | 24 | 32
2.5.4.1.10.4 |  |  |  | 656.1.10.4 | Deck replacement (w/o widening) | [13 empty] | structure | * | * | *
2.5.4.1.10.5 |  |  |  | 656.1.10.5 | Widening (w/deck replacement) | [13 empty] | structure | * | * | *
2.5.4.1.10.6 |  |  |  | 656.1.10.6 | Widening (w/ or w/o deck replacement) | [13 empty] | structure | * | * | *
2.5.4.1.10.7 |  |  |  | 656.1.10.7 | Superstructure replacement | [13 empty] | structure | * | * | *
2.5.4.1.11 |  |  |  | 656.1.11 | Structure alternative development | [13 empty] | structure alternative | 20 | 26 | 32
2.5.4.2 |  |  |  | 656.2 | Final design
2.5.4.2.1 |  |  |  | 656.2.1 | Box Culvert (cast in place concrete)
2.5.4.2.1.1 |  |  |  | 656.2.1.1 | Single Cell
2.5.4.2.1.1.1 |  |  |  | 656.2.1.1.1 | BOS | [13 empty] | structure | 42 | 57 | 72
2.5.4.2.1.1.2 |  |  |  | 656.2.1.1.2 | Consultant | [13 empty] | structure | 80 | 85 | 90
2.5.4.2.1.2 |  |  |  | 656.2.1.2 | Two Cell
2.5.4.2.1.2.1 |  |  |  | 656.2.1.2.1 | BOS | [13 empty] | structure | 56 | 68 | 80
2.5.4.2.1.2.2 |  |  |  | 656.2.1.2.2 | Consultant | [13 empty] | structure | 88 | 93 | 98
2.5.4.2.2 |  |  |  | 656.2.2 | Prestressed concrete slabs and boxes | [13 empty] | structure | * | * | *
2.5.4.2.3 |  |  |  | 656.2.3 | Prestressed concrete girders
2.5.4.2.3.1 |  |  |  | 656.2.3.1 | Single span | [13 empty] | structure | 160 | 200 | 240
2.5.4.2.3.2 |  |  |  | 656.2.3.2 | Additional Span(s) | [13 empty] | span | 40 | 80 | 120
2.5.4.2.4 |  |  |  | 656.2.4 | Concrete slab
2.5.4.2.4.1 |  |  |  | 656.2.4.1 | Single span | [13 empty] | structure | 120 | 160 | 200
2.5.4.2.4.2 |  |  |  | 656.2.4.2 | Additional Span(s) | [13 empty] | span | 32 | 64 | 96
2.5.4.2.5 |  |  |  | 656.2.5 | Steel plate girders
2.5.4.2.5.1 |  |  |  | 656.2.5.1 | Single span | [13 empty] | structure | 224 | 272 | 320
2.5.4.2.5.2 |  |  |  | 656.2.5.2 | Additional Span(s) | [13 empty] | span | 48 | 120 | 160
2.5.4.2.6 |  |  |  | 656.2.6 | Retaining wall
2.5.4.2.6.1 |  |  |  | 656.2.6.1 | Cast in place concrete | [13 empty] | structure | 40 | 60 | 80
2.5.4.2.6.2 |  |  |  | 656.2.6.2 | Modular block (no MSE) | [13 empty] | structure | 16 | 20 | 24
2.5.4.2.6.3 |  |  |  | 656.2.6.3 | MSE | [13 empty] | structure | 16 | 24 | 32
2.5.4.2.6.4 |  |  |  | 656.2.6.4 | Wire face with tip-up precast panel | [13 empty] | structure | * | * | *
2.5.4.2.6.5 |  |  |  | 656.2.6.5 | Post and panel, Soldier pile | [13 empty] | structure | 20 | 28 | 36
2.5.4.2.6.6 |  |  |  | 656.2.6.6 | Sheet pile | [13 empty] | structure | * | * | *
2.5.4.2.7 |  |  |  | 656.2.7 | Sign bridge | [13 empty] | structure | * | * | *
2.5.4.2.8 |  |  |  | 656.2.8 | Noise wall | [13 empty] | structure | * | * | *
2.5.4.2.9 |  |  |  | 656.2.9 | Rigid frame | [13 empty] | sheet | * | * | *
2.5.4.2.10 |  |  |  | 656.2.10 | Rehabilitation
2.5.4.2.10.1 |  |  |  | 656.2.10.1 | Box culvert single cell extension
2.5.4.2.10.1.1 |  |  |  | 656.2.10.1.1 | BOS | [13 empty] | structure | 42 | 57 | 72
2.5.4.2.10.1.2 |  |  |  | 656.2.10.1.2 | Consultant | [13 empty] | structure | 80 | 85 | 90
2.5.4.2.10.2 |  |  |  | 656.2.10.2 | Box culvert multi cell extension
2.5.4.2.10.2.1 |  |  |  | 565.2.10.2.1 | BOS | [13 empty] | structure | 56 | 68 | 80
2.5.4.2.10.2.2 |  |  |  | 565.2.10.2.2 | Consultant | [13 empty] | structure | 88 | 93 | 98
2.5.4.2.10.3 |  |  |  | 656.2.10.3 | Deck overlay | [13 empty] | structure | 48 | 64 | 96
2.5.4.2.10.4 |  |  |  | 656.2.10.4 | Deck replacement (w/o widening) | [13 empty] | structure | * | * | *
2.5.4.2.10.5 |  |  |  | 656.2.10.5 | Widening (w/deck replacement) | [13 empty] | structure | * | * | *
2.5.4.2.10.6 |  |  |  | 656.2.10.6 | Widening (w/ or w/o deck replacement) | [13 empty] | structure | * | * | *
2.5.4.2.10.7 |  |  |  | 656.2.10.7 | Superstructure replacement | [13 empty] | structure | * | * | *
2.5.4.2.11 |  |  |  | 656.2.11 | ESubmit | [13 empty] | structure | 4 | 4 | 4
2.5.5 |  |  | 657 | Draft Structure Plan (9/13/16)
2.5.5.1 |  |  |  | 657.1 | Box Culvert (cast in place concrete) | [13 empty] | sheet | 4 | 6 | 8
2.5.5.2 |  |  |  | 657.2 | Prestressed concrete slabs and boxes | [13 empty] | sheet | * | * | *
2.5.5.3 |  |  |  | 657.3 | Prestressed concrete girders | [13 empty] | sheet | 9 | 12 | 18
2.5.5.4 |  |  |  | 657.4 | Concrete slab | [13 empty] | sheet | 10 | 13 | 19
2.5.5.5 |  |  |  | 657.5 | Steel plate girders | [13 empty] | sheet | 10 | 15 | 21
2.5.5.6 |  |  |  | 657.6 | Retaining wall
2.5.5.6.1 |  |  |  | 657.6.1 | Cast in place concrete | [13 empty] | sheet | 10 | 11 | 12
2.5.5.6.2 |  |  |  | 657.6.2 | Modular block (no MSE) | [13 empty] | sheet | 8 | 8 | 8
2.5.5.6.3 |  |  |  | 657.6.3 | MSE | [13 empty] | sheet | 8 | 8 | 8
2.5.5.6.4 |  |  |  | 657.6.4 | Wire face with tip-up precast panel | [13 empty] | sheet | 8 | 8 | 8
2.5.5.6.5 |  |  |  | 657.6.5 | Post and panel, Soldier pile | [13 empty] | sheet | 8 | 8 | 8
2.5.5.6.6 |  |  |  | 657.6.6 | Sheet pile | [13 empty] | sheet | 8 | 8 | 8
2.5.5.7 |  |  |  | 657.7 | Sign bridge | [13 empty] | sheet | * | * | *
2.5.5.8 |  |  |  | 657.8 | Noise wall | [13 empty] | sheet | * | * | *
2.5.5.9 |  |  |  | 658.9 | Rigid frame | [13 empty] | sheet | * | * | *
2.5.5.10 |  |  |  | 657.1 | Rehabilitation
2.5.5.10.1 |  |  |  | 657.10.1 | Box culvert extension | [13 empty] | sheet | 4 | 6 | 8
2.5.5.10.2 |  |  |  | 657.10.2 | Deck overlay | [13 empty] | structure | 20 | 60 | 100
2.5.5.10.3 |  |  |  | 657.10.3 | Deck replacement (w/o widening) | [13 empty] | sheet | * | * | *
2.5.5.10.4 |  |  |  | 657.10.4 | Widening (w/deck replacement) | [13 empty] | sheet | * | * | *
2.5.5.10.5 |  |  |  | 657.10.5 | Widening (w/ or w/o deck replacement) | [13 empty] | sheet | * | * | *
2.5.5.10.6 |  |  |  | 657.10.6 | Superstructure replacement | [13 empty] | sheet | * | * | *
2.5.6 |  |  | 658 | Design Structure Hydrology and Hydraulics (9/13/16)
2.5.6.1 |  |  |  | 658 | Includes design activities related to hydrology and hydraulics on project.
2.5.6.2 |  |  |  | 658.1 | Hydrology Computations & Documentation | [13 empty] | structure | 8 | 12 | 20
2.5.6.3 |  |  |  | 658.2 | Hydraulics Computations, Modeling & Report | [13 empty] | structure | 28 | 36 | 60
2.5.6.4 |  |  |  | 658.3 | Scour Computations & Evaluation | [13 empty] | structure | 2 | 4 | 8
2.5.6.5 |  |  |  | 658.4 | H&H for Temporary Structures | [13 empty] | structure | 6 | 6 | 6
2.5.7 |  |  | 659 | Review In-House Structure Plan (WisDOT only)
2.5.8 |  |  | 779 | Review Consultant Structure Plan (WisDOT only)
2.5.8.1 |  |  |  | 779 | Includes review of final structure plan from consultant
2.5.8.2 |  |  |  | 779.1 | Specialty - Complex structural analysis
2.6 |  | Traffic Operations (9/15/16)
2.6.1 |  |  | 313 | Analyze Traffic Data/ Forecast (8/26/16)
2.6.1.1 |  |  |  | 313 | Conduct analysis of traffic data and forecasting/projections.
2.6.1.2 |  |  |  | 313.1 | Review local land use and transportation plans |  |  |  | X | X | X |  | X | X |  |  |  |  | plan | 1 | 4 | 8 | [45 empty] | 1-4-6 | 0-0-2
2.6.1.3 |  |  |  | 313.2 | Process crash data-analyze crash trends (per road segment) |  |  | X | X | X | X | X | X | X | X | X | X | X | segment | 1 | 40 | 80 | [60 empty] | 1-30-60 | 0-10-20
2.6.1.4 |  |  |  | 313.3 | Process crash data-analyze crash trends (per intersections) |  |  | X | X | X | X | X | X | X | X | X | X | X | intersection | 1 | 40 | 80 | [60 empty] | 1-30-60 | 0-10-20
2.6.1.5 |  |  |  | 313.4 | Certified traffic for preferred alternative | [13 empty] | forecast
2.6.1.6 |  |  |  | 313.5 | Transportation demand modeling ( Microscopic) |  |  |  |  | X | X |  | X | [5 empty] | alternative | 4 | 40 | 160 | [60 empty] | 2-20-80 | 2-20-80
2.6.1.7 |  |  |  | 313.6 | Transportation demand modeling (Macroscopic) |  |  |  |  | X | X |  | X | [5 empty] | alternative | 8 | 24 | 80 | [45 empty] | 4-12-40 | 4-12-40 | [13 empty] | 4-12-40 | 4-12-40
2.6.1.8 |  |  |  | 313.7 | Conduct road safety audit | [5 empty] | X |  | X | [5 empty] | project | 100 | 290 | 480 | [60 empty] | 40-135-230 | 40-135-230 | 20-20-20
2.6.1.9 |  |  |  | 313.8 | Traffic projection and traffic forecast |  |  |  |  | X | X | X | X | X |  |  |  |  | project | 1 | 6 | 12 | [45 empty] | 1-4-8 | 0-2-4
2.6.1.10 |  |  |  | 313.9 | Determine time of day peak characteristics (peak hour factors) |  |  |  |  | X | X |  | X | [5 empty] | intersection | 2 | 2 | 2 | [45 empty] | 2-2-2 | [14 empty] | 2-2-2
2.6.1.11 |  |  |  | 313.1 | Determine directional composition of traffic flow (directional distribution) |  |  |  |  | X | X |  | X | [5 empty] | alternative | 2 | 2 | 2 | [45 empty] | 2-2-2 | [14 empty] | 2-2-2
2.6.1.12 |  |  |  | 313.11 | Develop and document Intersection Control Evaluation (ICE) report |  |  |  |  | X | X | X | X | X |  |  |  |  | intersection | 8 | 32 | 48 | [60 empty] | 6-20-32 | 2-8-8 | 0-4-8
2.6.2 |  |  | 347 | Collect Traffic Field Data (8/25/16)
2.6.2.1 |  |  |  | 347 | Conduct and review traffic counts and other traffic data collection
2.6.2.2 |  |  |  | 347.1 | Complete directional counts on roadways and ramps (ADT Counts) | FDM 3-10-10 |  | X | X | X | X | X | X | X | X | X | X | X | setup | 3 | 4 | 8 | [60 empty] | 3-4-4* | [11 empty] | 0-0-4
2.6.2.3 |  |  |  | 347.2 | Complete vehicle classification counts | FDM 3-10-10 |  | X | X | X | X | X | X | X | X | X | X | X | setup | 4 | 6 | 12 | [60 empty] | 4-6-6* | [11 empty] | 0-0-6
2.6.2.4 |  |  |  | 347.3 | Complete speed data collection | TGM 13-5-1, Wisconsin Statewide Speed Management Guidelines |  |  |  |  | X |  | X | [5 empty] | setup | 4 | 6 | 12 | [60 empty] | 4-6-6* | [11 empty] | 0-0-6
2.6.2.5 |  |  |  | 347.4 | Turning movement counts at intersections
2.6.2.5.1 |  |  |  | 347.4.1 | Automated turning movement counts at intersections | TSDM Chapter 2, Section 2 |  | X | X | X | X |  | X | [5 empty] | intersection | 3 | 4 | 8 | [60 empty] | 3-4-4* | [10 empty] | 3-4-4* | 0-0-4
2.6.2.5.2 |  |  |  | 347.4.2 | Manual turning movement counts at intersections | TSDM Chapter 2, Section 2 |  | X | X | X | X |  | X | [5 empty] | hour per intersection | 2 | 3 | 4 | [60 empty] | 2-3-2* | [10 empty] | 2-3-2* | 0-0-2
2.6.2.6 | MOVE TO 313??? |  |  | 347.5 | Control and continuous counts |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 2 | 6 | 12 | [60 empty] | 2-4-8 | 0-2-4
2.6.2.7 |  |  |  | 347.6 | Complete field signal timing data study |  |  | X | X | X | X |  | X | [5 empty] | timing plan per intersection | 2 | 3 | 4 | [60 empty] | 2-3-4* | [11 empty] | 2-3-4*
2.6.2.8 |  |  |  | 347.7 | Complete traffic gap study | [5 empty] | X |  | X | [5 empty] | hour per location | 2 | 3 | 4 | [60 empty] | 2-3-4* | [11 empty] | 2-3-4*
2.6.2.9 |  |  |  | 347.8 | Complete traffic delay study | [5 empty] | X |  | X | [5 empty] | hour per approach | 2 |  | 4 | [60 empty] | 2-x-4* | [11 empty] | 2-x-4*
2.6.2.10 |  |  |  | 347.9 | Collect queue data | [5 empty] | X |  | X | [5 empty] | hour per approach | 2 |  | 3 | [60 empty] | 2-x-3* | [11 empty] | 2-x-3*
2.6.2.11 |  |  |  | 347.1 | Collect lane utilization data | [5 empty] | X |  | X | [5 empty] | hour per location | 2 |  | 3 | [60 empty] | 2-x-3* | [11 empty] | 2-x-3*
2.6.2.12 |  |  |  | 347.11 | Collect occupancy data | [5 empty] | X |  | X | [5 empty] | hour per location | 2 |  | 3 | [60 empty] | 2-x-3* | [11 empty] | 2-x-3*
2.6.2.13 |  |  |  | 347.12 | Complete travel time study | [5 empty] | X | X | X | X | [5 empty] | * | * | *
2.6.2.14 |  |  |  | 347.13 | Complete origin-destination study | FDM 3-10-10 |  |  |  |  | X | X | X | X | [5 empty] | * | * | *
2.6.3 |  |  | 785 | Design Traffic Signal and Details (8/26/16)
2.6.3.1 |  |  |  | 785 | Prepare or review signal plans.
2.6.3.2 |  |  |  | 785.1 | Prepare, submit, review signal warrant | TSDM - Chapter 2 |  | X | X | X | X |  | X | [5 empty] | Intersection | 2 | 4 | 10 | [60 empty] | 1-3-8 | 1-1-2
2.6.3.3 |  |  |  | 785.2 | Traffic analysis
2.6.3.3.1 |  |  |  | 785.2.1 | Analyze and determine signal phasing | TSDM Chapter 7 |  | X | X | X | X |  | X | [5 empty] | Intersection | 2 | 4 | 6 | [61 empty] | 1-3-4 | 1-1-2
2.6.3.3.2 |  |  |  | 785.2.2 | Analyze and determine intersection timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 |  | X | X | X | X |  | X | [5 empty] | Intersection | 2 | 3 | 5 | [61 empty] | 3-4-6 | 1-1-2
2.6.3.3.3 |  |  |  | 785.2.3 | Analyze and determine coordination timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 |  | X | X | X | X |  | X | [5 empty] | Timing Plan Per intersection | 6 | 8 | 10 | [62 empty] | 4-6-8 | 2-2-2
2.6.3.4 |  |  |  | 785.3 | Traffic signal plan details
2.6.3.4.1 |  |  |  | 785.3.1 | Develop signal equipment layout | TSDM - Chapter 3/MUTCD |  | X | X | X | X |  | X | [5 empty] | Intersection | 8 | 10 | 16 | [61 empty] | 3-4-5 | 1-1-4 |  |  |  | 4-5-7
2.6.3.4.2 |  |  |  | 785.3.2 | Develop cable routing | TSDM - Chapter 9 |  | X | X | X | X |  | X | [5 empty] | Intersection | 4 | 5 | 8 | [61 empty] | 2-3-4 | 1-1-2 |  |  |  | 1-1-2
2.6.3.4.3 |  |  |  | 785.3.3 | Develop sequence of operations | TSDM - 7.1.5 & 7.1.6 |  | X | X | X | X |  | X | [5 empty] | Intersection | 4 | 6 | 10 | [61 empty] | 2-4-6 | 1-1-2 |  |  |  | 1-1-2
2.6.3.5 |  |  |  | 785.4 | Develop quantities and estimate | FDM 19.5.1 |  | X | X | X | X |  | X | [5 empty] | Intersection | 16 | 24 | 32 | [60 empty] | 10-8-4 | 4-8-16 | 0-4-6 |  |  |  | 2-4-6
2.6.3.6 |  |  |  | 785.5 | Develop PSE special provisions | FDM 19.15 |  | X | X | X | X |  | X | [5 empty] | Intersection | 6 | 9 | 16 | [60 empty] | 4-4-4 | 4-8-12 | 1-2-4
2.6.3.7 |  |  |  | 785.6 | Determine existing signal inventory and complete signal removal plan |  |  | X | X | X | X |  | X | [5 empty] | Intersection | 5 | 6 | 10 | [60 empty] | 4-5-7 | 1-1-2 | 0-0-1
2.6.3.8 |  |  |  | 785.7 | Complete traffic signal communication design |  |  | X | X | X | X |  | X | [5 empty] | Signal System | 12 | 24 | 48 | [61 empty] | 8-15-25 | 2-5-10 | 0-0-5 |  |  | 2-4-8
2.6.3.9 |  |  |  | 785.8 | Develop railroad preemption plans |  |  | X | X | X | X |  | X | [5 empty] | Signal | 5 | 10 | 20 | [61 empty] | 4-8-15 | 2-2-5
2.6.3.10 |  |  |  | 785.9 | Temporary signals
2.6.3.10.1 |  |  |  | 785.9.1 | Develop signal equipment layout | TSDM - Chapter 3/MUTCD |  | X | X | X | X | X | X | X | X | X | X | X | Signal | 4 | 8 | 12 | [61 empty] | 2-4-8 | 1-1-2 |  |  |  | 4-6-8
2.6.3.10.2 |  |  |  | 785.9.2 | Develop sequence of operations | TSDM - 7.1.5 & 7.1.6 |  | X | X | X | X | X | X | X | X | X | X | X | Signal | 3 | 5 | 8 | [61 empty] | 2-4-6 | 1-1-2
2.6.3.10.3 |  |  |  | 785.9.3 | Analyze and determine intersection timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 |  | X | X | X | X | X | X | X | X | X | X | X | Intersection | 2 | 3 | 5 | [61 empty] | 3-4-6 | 1-1-2
2.6.3.10.4 |  |  |  | 785.9.4 | Analyze and determine coordination timing data | TGM 4.2.5/MUTCD/FDM 11.5.3 |  | X | X | X | X | X | X | X | X | X | X | X | Timing Plan Per intersection | 6 | 8 | 10 | [62 empty] | 4-6-8 | 2-2-2
2.6.4 |  |  | 788 | Develop Traffic Control and Staging (8/26/16)
2.6.4.1 |  |  |  | 788 | Traffic Control and Construction Staging
2.6.4.2 |  |  |  | 788.1 | Develop/Coordinate/Review Transportation Management Plan (Type 1, 2, 3, 4) for all statuses.
2.6.4.2.1 |  |  |  | 788.1.1 | Identify work restrictions (special events-holidays) |  |  | X | X | X | X | X | X | X | X | X | X | X | occurance | 4 | 6 | 16 | [5 empty] | 4-6-12 | 0-0-4
2.6.4.2.2 |  |  |  | 788.1.2 | Work hour restrictions-lane closure evaluation |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 6 | 16 | [5 empty] | 4-6-12 | 0-0-4
2.6.4.2.3 |  |  |  | 788.1.3 | Work zone capacity traffic analysis (LOS-delay-queue) |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 12 | 40 | [5 empty] | 4-8-30 | 0-4-10
2.6.4.2.4 |  |  |  | 788.1.4 | Detour route evaluations (vertical clearance-travel time-improvements needed; surface and shoulder condition-corridor; and intersection capacity) |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 12 | 40 | [5 empty] | 4-8-30 | 0-4-10
2.6.4.2.5 |  |  |  | 788.1.5 | Temporary pedestrian accomodations |  |  | X | X | X | X | X | X | X | X | X | X | X | intersection | 4 | 8 | 16 | [5 empty] | 4-6-12 | 0-2-4
2.6.4.2.6 |  |  |  | 788.1.6 | OSOW accomodations (clear lane width determination) |  |  | X | X | X | X | X | X | X | X | X | X | X | location | 8 | 24 | 48 | [5 empty] | 8-16-24 | 0-8-8 | 0-0-8
2.6.4.2.7 |  |  |  | 788.1.6 | Alternate route evaluations (vertical clearance-travel time-improvements needed; surface and shoulder condition-corridor; and intersection capacity) |  |  | X | X | X | X | X | X | X | X | X | X | X | route-mile | 16 | 40 | 80 | [5 empty] | 12-30-50 | 4-10-20 | 0-0-10
2.6.4.2.8 |  |  |  | 788.1.8 | Temporary transit accomodations |  |  | X | X | X | X | X | X | X | X | X | X | X | bus stop | 4 | 8 | 16 | [5 empty] | 4-8-12 | 0-0-4
2.6.4.2.9 |  |  |  | 788.1.9 | Temporary ITS |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 0 | 4 | 16 | [60 empty] | 0-4-12 | 0-0-4
2.6.4.3 |  |  |  | 788.2 | Develop incident management plan |  |  | X | X | X | X | X | X | X | X | X | X | X | plan | 16 | 24 | 40 | [60 empty] | 8-12-20 | 8-12-20
2.6.4.4 |  |  |  | 788.3 | Detour plan and signing |  |  | X | X | X | X | X | X | X | X | X | X | X | per detour | 8 | 16 | 24 | [5 empty] | 4-8-12 | 4-8-12
2.6.4.5 |  |  |  | 788.4 | Traffic control plan |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 40 | 60 | 120 | [5 empty] | 20-30-60 | 20-30-40 | 0-0-20
2.6.4.6 |  |  |  | 788.5 | Traffic control staging plans |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 20 | 40 | 120 | [5 empty] | 10-20-60 | 10-20-50 | 0-0-10
2.6.4.7 |  |  |  | 788.6 | Pedestrian/bike/snowmobile detour |  |  | X | X | X | X | X | X | X | X | X | X | X | /detour /direction | 8 | 8 | 12 | [5 empty] | 8-6-8 | 0-2-4
2.6.5 |  |  | 819 | Design Signing and Pavement Marking (9/15/16)
2.6.5.1 |  |  |  | 819 | Includes tasks related to signing information, recommendations, plans and/or review for design (SPO); and field work on improvement projects (review of existing sign locations and conformance to current standards and guidelines.) Includes review of current policies and guidelines to make sure that signing and pavement marking meets current standards.
2.6.5.2 |  |  |  | 819.1 | Prepare Type 1 and/or Type 2 guide sign alternatives | MUTCD (multiple chapters) & TGM Chapter 2 |  |  |  |  | x |  | x | [5 empty] | interchange | 25 | 60 | 100 | [7 empty] | 2-4-8 | [53 empty] | 18-44-72 |  |  |  |  | 5-12-20
2.6.5.3 |  |  |  | 819.2 | Develop plan sign plans
2.6.5.3.1 |  |  |  | 819.2.1 | Inventory eixsting signs | FDM Chapters 11 & 15 |  | x | x | x | x | x | x | x | x | x | x | x | project | 5 | 10 | 12 | [60 empty] | 4-8-10 | 1-2-2
2.6.5.3.2 |  |  |  | 819.2.2 | Develop sign removal plans | FDM Chapters 11 & 15 |  | x | x | x | x | x | x | x | x | x | x | x | project | 3 | 6 | 8 | [60 empty] | 2-4-6 | 1-2-2
2.6.5.3.3 |  |  |  | 819.2.3 | Develop permanent sign plans | TGM Chpater 2 and MUTCD Part 2 |  | x | x | x | x | x | x | x | x | x | x | x | project | 22 | 44 | 60 | [60 empty] | 18-36-48 | 4-8-12
2.6.5.3.4 |  |  |  | 819.2.4 | Develop signing plates (DOT task only) | Guide Sign Design Manual & MUTCD Part 2 |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 16 | 24 | [61 empty] | 1-2-3 | [5 empty] | 7-14-21
2.6.5.4 |  |  |  | 819.3 | Develop pavement marking plan details | FDM Chapters 11 & 15, TGM Chapter 3, WisMUTCD (multiple parts) |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 30 | 40 | [60 empty] | 5-22-28 | 3-8-12
2.6.6 |  |  | 830 | Design Street Lighting (6/6/16)
2.6.6.1 |  |  |  | 830.1 | Improvement Project Operational Improvement - Lighting Plan & Inspection |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 16 | 60 | 120
2.6.6.2 |  |  |  | 830.2 | Determine potential locations for lighting |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 16 | 80 | 150
2.6.6.3 |  |  |  | 830.3 | Complete Lighting Investigation Report |  |  | x | x | x | x | x | x | x | x | x | x | x | report | 12 | 40 | 80
2.6.6.4 |  |  |  | 830.4 | Complete lighting permit forms (preliminary and final) |  |  | x | x | x | x | x | x | x | x | x | x | x | permit | 16 | 32 | 80
2.6.6.5 |  |  |  | 830.5 | Determine existing lighting inventory and complete lighting removal plan |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 16 | 40 | 120
2.6.6.6 |  |  |  | 830.6 | Complete street lighting layout and equiptment design |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 40 | 200 | 1000
2.6.6.7 |  |  |  | 830.7 | Complete street lighting electrical design |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 40 | 200 | 1000
2.6.6.8 |  |  |  | 830.8 | Temporary lighting |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 40 | 100 | 500
2.6.7 |  |  | 832 | Design ITS (8/26/16)
2.6.7.1 |  |  |  | 832.1 | Design Traffic/Vehicle Detection Components – Interchange |  |  | X | X | X | X | X | X | X | X | X | X | X | interchange | 60 | 80 | 100 | [16 empty] | X | [44 empty] | 30-50-60 | 20-20-20 |  |  | 10-10-20
2.6.7.2 |  |  |  | 832.2 | Design Traffic/Volume Detection Components – Mainline |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 60 | 80 | [16 empty] | X | [44 empty] | 20-40-40 | 10-10-20 |  |  | 10-10-20
2.6.7.3 |  |  |  | 832.3 | Design Traffic/Volume Detection Components – Bluetooth |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 20 | 30 | 40 | [16 empty] | X | [44 empty] | 12-12-20 | 4-10-10 |  |  | 4-8-10
2.6.7.4 |  |  |  | 832.4 | Design CCTV Camera Components |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 40 | 60 | 80 | [16 empty] | X | [44 empty] | 20-40-40 | 10-10-20 |  |  | 10-10-20
2.6.7.5 |  |  |  | 832.5 | Design Dynamic Message Sign – Roadside |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 60 | 80 | 100 | [16 empty] | X | [44 empty] | 30-50-60 | 20-20-20 |  |  | 10-10-20
2.6.7.6 |  |  |  | 832.6 | Design Dynamic Message Sign – Overhead |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 80 | 160 | 240 | [16 empty] | X | [44 empty] | 40-80-160 | 20-60-60 |  |  | 20-20-20
2.6.7.7 |  |  |  | 832.7 | Design Fiber Regeneration Hut |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 100 | 150 | 200 | [16 empty] | X | [44 empty] | 60-80-80 | 20-50-100 |  |  | 20-20-20
2.6.7.8 |  |  |  | 832.8 | Design Fiber Optic Communications |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 20 | 50 | 80 | [61 empty] | 16-32-50 | 0-10-20 |  |  | 4-8-10
2.7 |  | Real Estate, Railroad and Utilities (8/18/16)
2.7.1 |  |  | 247 | Manage Real Estate Relocation
2.7.1.1 |  |  |  | 247 | Includes activities related to acquisition stage relocation plan and relocation assistance.
2.7.1.2 |  |  |  | 247.1 | Conceptual Plan - Relocation (environmental document)
2.7.1.2.1 |  |  |  | 247.1.1 | Residential | [5 empty] | X | X | X | X |  | X | X | X | relocation | 4 | 8 | 16 | [91 empty] | 4-8-16
2.7.1.2.2 |  |  |  | 247.1.2 | Non-Residential | [5 empty] | X | X | X | X |  | X | X | X | relocation | 12 | 24 | 28 | [91 empty] | 12-24-28
2.7.1.3 |  |  |  | 247.2 | Relocation Plan (at acquisition stage)
2.7.1.3.1 |  |  |  | 247.2.1 | Residential | [5 empty] | X | X | X | X |  | X | X | X | relocation | 38 | 74 | 114 | [91 empty] | 38-74-114
2.7.1.3.2 |  |  |  | 247.2.2 | Non-Residential | [5 empty] | X | X | X | X |  | X | X | X | relocation | 47 | 70 | 108 | [91 empty] | 47-70-108
2.7.1.4 |  |  |  | 247.3 | Relocation Assistance to Displaced Person
2.7.1.4.1 |  |  |  | 247.3.1 | MOVE ONLY with No Displaced Persons | [13 empty] | relocation | 20-40 | [93 empty] | 20-40
2.7.1.4.2 |  |  |  | 247.3.2 | Residential | [13 empty] | relocation | 86 | 147 | 289 | [91 empty] | 86-147-289
2.7.1.4.3 |  |  |  | 247.3.3 | Non-Residential | [13 empty] | relocation | 92 | 156 | 429 | [91 empty] | 92-156-429
2.7.1.5 |  |  |  | 247.4 | Demolition/razing contracts
2.7.2 |  |  | 254 | Develop Real Estate Appraisal
2.7.2.1 |  |  |  | 254 | Includes activities related to real estate appraisal preparation and appraisal review.
2.7.2.2 |  |  |  | 254.1 | Prepare and review real estate appraisal | [13 empty] | parcel | 40 | 68 | 96 | [91 empty] | 40-68-95
2.7.2.3 |  |  |  | 254.2 | Specialty - Real estate appraisal services right of way projects | [5 empty] | X | X | X | X |  | X | X | X | parcel | 40 | 68 | 96 | [91 empty] | 40-68-96
2.7.2.4 |  |  |  | 254.3 | Specialty - Real estate appraisal review services | [5 empty] | X | X | X | X |  | X | X | X | parcel | 8 | 12 | 16 | [91 empty] | 8-12-16
2.7.2.5 |  |  |  | 254.4 | Specialty - Eminent domain real estate services | [5 empty] | X | X | X | X |  | X | X | X | parcel | 40 | 68 | 96 | [91 empty] | 40-68-96
2.7.3 |  |  | 253 | Nominal Parcel Acquisition (less than $10k) (6/28/16)
2.7.3.1 |  |  |  | 253 | Purchase of nominal parcel acquisition
2.7.3.2 |  |  |  | 253.1 | Purchase of nominal parcel acquisition with appraisal | [5 empty] | X | X | X | X |  | X | X | X | parcel | 24 | [93 empty] | 24
2.7.3.3 |  |  |  | 253.2 | Purchase of nominal parcel acquisition without appraisal | [5 empty] | X | X | X | X |  | X | X | X | parcel | 16 | [93 empty] | 16
2.7.4 |  |  | 256 | Parcel Acquisition (greater than $10k) (6/17/16)
2.7.4.1 |  |  |  | 256 | Includes negotiation of real estate agreement (except nominal parcel).
2.7.4.2 |  |  |  | 256.1 | Purchase of parcel | [5 empty] | X | X | X | X |  | X | X | X | parcel | 24 | 28 | 32 | [91 empty] | 24-28-32
2.7.5 |  |  | 265 | Litigate Real Estate (6/17/16)
2.7.5.1 |  |  |  | 265 | Includes activities related to Real Estate litigation. | [14 empty] | * | * | *
2.7.6 |  |  | 746 | Coordinate Utilities (8/18/16)
2.7.6.1 |  |  |  | 746 | Includes Prepare and maintain TUMS or DT 1079 form, SMA Review, Plan/attend/document utility meetings, Create Utility Coordination Task List and/or review utility coordination contract, PMP, 1077 Process, Field survey and compare to system maps, Review base and preliminary right of way plats and establish utility projects in FIIPS, DSR Review, Identify potential utility conflicts, 1078 Project Plan Process, 1078 Compensable Process, Plan Changes, Reviews of utility work plans, Create or review utility special provisions, Execute utility agreements, Work plan approval and start work notice process, Permitting process, PS&E Review, Post PS&E activities, Construction support, and Utility invoicing.
2.7.6.2 |  |  |  | 746.1 | Prepare and maintain TUMS or DT1079 form |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 4 | 8 | 16 | [68 empty] | X | X
2.7.6.3 |  |  |  | 746.2 | SMA Review |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 2 | 4 | [6 empty] | X | X | [62 empty] | X
2.7.6.4 |  |  |  | 746.3 | Plan/attend/document utility meetings |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 10 | 35 | 60+ | [5 empty] | X | X | X | [61 empty] | X | X
2.7.6.5 |  |  |  | 746.4 | Create Utility Coordination Task List and/or review utility coordination contract |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 2 | 3 | [6 empty] | X | X | [62 empty] | X
2.7.6.6 |  |  |  | 746.5 | PMP |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 2 | 3 | [6 empty] | X | X | [62 empty] | X
2.7.6.7 |  |  |  | 746.6 | 1077 Process |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 8 | 10 | 15 | [68 empty] | X | X
2.7.6.8 |  |  |  | 746.7 | Field survey and compare data to system maps |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 3 | 5 | [68 empty] | X | X
2.7.6.9 |  |  |  | 746.8 | Review base and preliminary right of way plats and establish utility projects in FIIPS |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 5 | 10 | 15 | [6 empty] | X | X | [50 empty] | X | [11 empty] | X
2.7.6.10 |  |  |  | 746.9 | DSR Review |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 2 | 3 | [6 empty] | X | X | [62 empty] | X
2.7.6.11 |  |  |  | 746.1 | Identify potential utility conflicts |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 10 | 32+ | [5 empty] | X | X | [62 empty] | X | X
2.7.6.12 |  |  |  | 746.11 | 1078 Project Plan Process |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 10 | 13 | 18 | [68 empty] | X | X
2.7.6.13 |  |  |  | 746.12 | 1078 Compensable Process |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 3 | 5 | 8+ | [6 empty] | X | X | [50 empty] | X | [11 empty] | X
2.7.6.14 |  |  |  | 746.13 | Plan changes |  |  | X | X | X | X | X | X | X | X | X | X | X | PLAN CHANGE | 9 | 17 | 40+ | [5 empty] | X | X | [62 empty] | X | X
2.7.6.15 |  |  |  | 746.14 | Reviews of utility work plans |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 8 | 24 | 40+ | [5 empty] | X | X | [62 empty] | X | X
2.7.6.16 |  |  |  | 746.15 | Create or review utility special provisions |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 6 | 15+ | [5 empty] | X | X | [62 empty] | X | X
2.7.6.17 |  |  |  | 746.16 | Execute utility agreements |  |  | X | X | X | X | X | X | X | X | X | X | X | UTILITY NUMBER | 1 | 3 | 5 | [6 empty] | X | X | [62 empty] | X
2.7.6.18 |  |  |  | 746.17 | Work plan approval and start work notice process |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 5 | 7 | [68 empty] | X | X
2.7.6.19 |  |  |  | 746.18 | Permitting Process |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 5 | 10 | 20+ | [5 empty] | X | X | [62 empty] | X | X
2.7.6.20 |  |  |  | 746.19 | PS&E Review |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 3 | 5 | [5 empty] | X | X | [62 empty] | X | X
2.7.6.21 |  |  |  | 746.2 | Post PS&E activities |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 2 | 3 | 4 | [5 empty] | X | X | [62 empty] | X | X
2.7.6.22 |  |  |  | 746.21 | Construction support |  |  | X | X | X | X | X | X | X | X | X | X | X | PROJECT | 1 | 3 | 6 | [5 empty] | X | X | X | [61 empty] | X | X
2.7.6.23 |  |  |  | 746.22 | Utility invoicing |  |  | X | X | X | X | X | X | X | X | X | X | X | UTILITY NUMBER | 0 | 2 | 3 | [5 empty] | X | X | [62 empty] | X | X
2.7.7 |  |  | 847 | Coordinate Railroad
2.7.7.1 |  |  |  | 847 | Includes activities related to project submittal, railroad coordination meeting, signatures from local agencies, signed agreement (WisDOT and Governor), and OCR hearings (pre-conference, proposed and final decision).
2.7.7.2 |  |  |  | 847.1 | Complete railroad safety training or notification to enter railroad right of way |  |  | X | X | X | X | X | X | X | X | X | X | X | person | 0.5 | 0.75 | 1
2.7.7.3 |  |  |  | 847.2 | Railroad project submittal package
2.7.7.3.1 |  |  |  | 847.2.1 | For grade separated crossing |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 15 | 15 | 15 | [6 empty] | 7-7-7 | [93 empty] | 2-2-2 | [5 empty] | 6-6-6
2.7.7.3.2 |  |  |  | 847.2.2 | For at grade crossing |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 15 | 40 | 62 | [6 empty] | 7-17-25 | [93 empty] | 6-15-25 | [5 empty] | 2-8-12
2.7.7.4 |  |  |  | 847.3 | Complete OCR process
2.7.7.4.1 |  |  |  | 847.3.1 | For grade separated crossing |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 8 | 104 | [6 empty] | 0-0-20 | 0-0-20 | [92 empty] | 2-2-4 | [5 empty] | 6-6-60
2.7.7.4.2 |  |  |  | 847.3.2 | For at grade crossing |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 56 | 140 | [6 empty] | 0-20-40 | 0-12-20 | [92 empty] | 2-12-40 | [5 empty] | 6-12-40
2.7.7.5 |  |  |  | 847.4 | Coordinate traffic signal peemption plans |  |  | X | X | X | X | X | X | X |  |  |  |  | project | 21 | 40 | 80 | [6 empty] | 15-30-41 | [93 empty] | 6-10-40
2.7.7.6 |  |  |  | 847.5 | Acquire railroad real estate |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 6 | 15 | 102 | [6 empty] | 0-3-40 | 0-0-10 | [83 empty] | 4-4-12 | [8 empty] | 4-6-20 | [5 empty] | 0-2-20
3 | Construction Management
3.1 |  | Post-PSE through Letting (6/21/16)
3.1.1 |  |  | 790 | Manage Post-PSE Though Let (6/21/16)
3.1.1.1 |  |  |  | 790 | Includes activities related to post-PS&E corrections and development of addenda.
3.1.1.2 |  |  |  | 790.2 | Prepare addendum development form and addendum form |  |  | x | x | x | x | x | x | x | x | x | x | x | addenda | 12 | 20 | 32
3.1.1.3 |  |  |  | 790.1 | Respond to contractor inquires prior to let |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 2
3.1.1.4 |  |  |  | 790.3 | Respond to BPD requests (engineer's estimate justification, etc.) |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 8 | 10 | 12
3.1.1.5 |  |  |  | 790.4 | Pre-letting meeting
3.1.1.6 |  |  |  | 790.5 | Manage letting
3.2 |  | Post-Let Pre-Construction Project Management (7/12/16)
3.2.1 |  |  | 791 | Manage Construction Start (7/12/16)
3.2.1.1 |  |  |  | 791 | Includes coordination, preparation for meetings and reviews (pre-construction, utility, public and business meetings, workshops, erosion control implementation plan)
3.2.1.2.2 |  |  |  | 791.1 | Develop contruction outreach meetings |  |  | x | x | x | x | x | x | x | x | x | x | x | meeting | 8 | 8 | 8
3.2.1.5 |  |  |  | 791.2 | Set up field office and materials testing arrangements (coordinate computer application set up) |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 16 | 24 | 40
3.2.1.7 |  |  |  | 791.3 | Set up of lane closure system (STOC coordination) |  |  | x | x | x | x | x | x | x | x | x | x | x | project | 2 | 4 | 8
3.3 |  | Construction Contract Administration (8/1/16)
3.3.1 |  |  | 271 | Perform Construction Surveying (7/5/16) | [15 empty] | 64 | 238 | 392
3.3.1.1 |  |  |  | 271 | Construction Surveying - includes construction staking, quantity measurement, as-built development, and digital file storage for archive.
3.3.1.2 |  |  |  | 271.1 | Initial preparation/checking |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 20 | 30 | 40 | [56 empty] | 10-15-20 | 10-15-20
3.3.1.3 |  |  |  | 271.2 | Perform construction staking |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 15 | 80 | 140 | [56 empty] | 5-30-50 | 10-50-90
3.3.1.4 |  |  |  | 271.3 | Survey quantity measurements/computation |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 25 | 100 | 160 | [56 empty] | 10-40-60 | 15-60-100
3.3.1.5 |  |  |  | 271.4 | Develop as built |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 0 | 20 | 40 | [56 empty] | 0-10-20 | 0-10-20
3.3.1.6 |  |  |  | 271.5 | Digital file storage for archive |  |  | X | X | X | X | X | X | X | X | X | X | X | mile | 4 | 8 | 12 | [57 empty] | 8-10-12
3.3.2 |  |  | 826 | Complete Construction Finals (7/12/16) | [15 empty] | 106 | 262 | 396
3.3.2.1 |  |  |  | 826 | Final documentation and checking of all project records including contractor payments, and evaluations
3.3.2.2 |  |  |  | 826.1 | Check all entries and source documents |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 60 | 80 | [5 empty] | x | x
3.3.2.3 |  |  |  | 826.2 | Explanation of Variation |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 10 | 20 | 32 | [6 empty] | x | x
3.3.2.4 |  |  |  | 826.3 | Close out items in FM |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 6 | 12 | 16 | [6 empty] | x | x
3.3.2.5 |  |  |  | 826.4 | FIT entries |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 4 | 8 | [6 empty] | x
3.3.2.6 |  |  |  | 826.5 | Prepare As-Built Plans |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 28 | 40 | [5 empty] | x | x
3.3.2.7 |  |  |  | 826.6 | Settle Quantity Discrepancies |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 16 | 24 | 40 | [6 empty] | x | x
3.3.2.8 |  |  |  | 826.7 | Complete Evaluations (DQI, Contractor Performance) |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 8 | 24 | 40 | [7 empty] | x
3.3.2.9 |  |  |  | 826.8 | CQI Walkthrough |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 16 | [7 empty] | x
3.3.2.10 |  |  |  | 826.9 | Prepare/organize accounting finals for submittal |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 6 | 14 | 28 | [5 empty] | x | x
3.3.2.11 |  |  |  | 826.1 | DT 1310 Certification of Materials used on Highway Projects |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 4 | 8 | 16 | [6 empty] | x | x
3.3.2.12 |  |  |  | 826.11 | Update finals after Department review |  |  | X | X | X | X | X | X | X | X | X | X | X | project | 20 | 60 | 80 | [6 empty] | x | x
3.3.3 |  |  | 852 | Evaluate Construction Material (8/1/16)
3.3.3.1 |  |  |  | 852 | Tasks involved with the evaluation of construction materials, including quality control, material records, plant review, etc. |  |  | x | x | x | x | x | x | x | x | x | x | x
3.3.3.2 |  |  |  | 852.1 | Evaluate Structure Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Each Structure | 12 | 24 | 40 | [10 empty] | 4/10/16 | 0.3/0.8/0.8 | 0.2/0.2/0.2 | [59 empty] | 7.5/13/23
3.3.3.3 |  |  |  | 852.2 | Evaluate Concrete Pavement Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Paving Days | 4 | 8 | 12 | [10 empty] | 1/2/4 | 0.8/1.5/2 | 0.2/0.5/1 | [59 empty] | 2/4/5
3.3.3.4 |  |  |  | 852.3 | Evaluate Ancillary Concrete Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Placement Days | 2 | 4 | 8 | [10 empty] | 1/1/1 | 0.5/0.5/0.5 | 0 | [59 empty] | .5/2.5/6.5
3.3.3.5 |  |  |  | 852.4 | Evaluate HMA Pavement Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Paving Days | 4 | 8 | 12 | [10 empty] | 1/2/4 | 0.8/1.5/2 | 0.2/0.5/1 | [59 empty] | 2/4/5
3.3.3.6 |  |  |  | 852.5 | Evaluate Aggregate/Base Course Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Placement Days | 4 | 6 | 8 | [10 empty] | 1/1/1 | 0.8/1.5/1.5 | 0.2/0.5/.5 | [59 empty] | 2/3/5
3.3.3.7 |  |  |  | 852.6 | Evaluate Electrical/ITS Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Project | 24 | 40 | 80 | [10 empty] | 10/30/60 | 1/2/4 | 0 | [59 empty] | 13/8/16
3.3.3.8 |  |  |  | 852.7 | Evaluate Pipe Culverts & Storm Sewer Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Project | 8 | 12 | 16 | [10 empty] | 2/4/6 | 1/2/3 | 0 | [59 empty] | 5/6/7
3.3.3.9 |  |  |  | 852.8 | Evaluate MSE/Noise Walll Materials | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Project | 60 | 140 | 260 | [10 empty] | 20/80/120 | 0.3/0.8/0.8 | 0.2/0.2/0.2 | [59 empty] | 39.5/59/139
3.3.3.10 |  |  |  | 852.9 | Review Misc. Project Material Submittals | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Project | 40 | 64 | 160 | [10 empty] | 16/31/100 | 1/2/6 | 0/1/2 | [59 empty] | 23/30/52
3.3.3.11 |  |  |  | 852.1 | Material Finals | CMM/Specials/E-guide |  | x | x | x | x | x | x | x | x | x | x | x | Project | 120 | 180 | 300 | [10 empty] | 59/89/149 | 0.8/0.8/0.8 | 0.2/0.2/0.2 | [59 empty] | 60/90/150
3.3.4 |  |  | 853 | Evaluate Work Operations (7/12/16)
3.3.4.1 |  |  |  | 853 | Includes activities involving the evaluation of work operations and contractor performance.
3.3.4.2 |  |  |  | 853.1 | Inspect work operations |  |  | X | X | X | X | X | X | X | X | X | X | X | hr/day/person | 8 | 10 | 12
3.3.4.3 |  |  |  | 853.2 | General construction engineering |  |  | X | X | X | X | X | X | X | X | X | X | X | hr/day/person | 1 | 4 | 6
3.3.4.4 |  |  |  | 853.3 | General field inspection |  |  | X | X | X | X | X | X | X | X | X | X | X | hr/day/person | 1 | 2 | 4
3.3.4.5 |  |  |  | 853.4 | Respond to contractor RFI's |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 4 | 20 | 40
3.3.4.6 |  |  |  | 853.5 | Prepare DIN's |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 5 | 10
3.3.4.7 |  |  |  | 853.6 | Review contractor proposed CRI's |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 10 | 25 | 40
3.3.5 |  |  | 881 | Manage Construction Contract Accounting (6/21/16)
3.3.5.1 |  |  |  | 881 | Tasks involved with updating FieldManager and other project records |  |  | X | X | X | X | X | X | X | X | X | X | X
3.3.5.2 |  |  |  | 881.1 | FM/FIT initial contract info entry |  |  | X | X | X | X | X | X | X | X | X | X | X | project ID | 8 | 8 | 10 | [6 empty] | 6-6-8 | 2-2-2
3.3.5.3 |  |  |  | 881.2 | Quantity measurement/computation |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [5 empty] | 4-8-10
3.3.5.4 |  |  |  | 881.3 | Ticket entry into pantry sheets |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 2 | 4 | 5 | [5 empty] | 1-3-4 | 1-1-1
3.3.5.5 |  |  |  | 881.4 | Quantity checking and entry into FM |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [5 empty] | 2-4-5 | 2-4-5
3.3.5.6 |  |  |  | 881.5 | FM/FIT steps to create estimate (diary consolidation) |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [6 empty] | 4-8-10
3.3.5.7 |  |  |  | 881.6 | Print estimate/diaries to binder |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 2 | 2 | 2 | [6 empty] | 2-2-2
3.3.5.8 |  |  |  | 881.7 | Cost Tracking Updates |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 1 | 1 | 2 | [6 empty] | 1-1-2
3.3.5.9 |  |  |  | 881.8 | Research quantity discrepancies (plan vs. measured) |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 1 | 4 | 5 | [6 empty] | 1-4-5
3.3.5.10 |  |  |  | 881.9 | Other project records (Erosion control reports, Traffic Control reports) |  |  | X | X | X | X | X | X | X | X | X | X | X | week | 4 | 8 | 10 | [5 empty] | 3-7-9 | 1-1-1
3.3.5.11 |  |  |  | 881.1 | Contract Modifications
3.3.5.11.1 |  |  |  | 881.10.1 | Engineer ROM |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 2 | [6 empty] | x | x
3.3.5.11.2 |  |  |  | 881.10.2 | CM Negotiation |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 4 | 8 | 15 | [7 empty] | x
3.3.5.11.3 |  |  |  | 881.10.3 | WAF |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 2 | [6 empty] | x | x
3.3.5.11.4 |  |  |  | 881.10.4 | AJR |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 3 | [6 empty] | x | x
3.3.5.11.5 |  |  |  | 881.10.5 | Write/review/process CM |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 3 | [6 empty] | x | x
3.3.5.11.6 |  |  |  | 881.10.6 | Filing of all CM source documentation |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 2 | [6 empty] | x
3.3.5.11.7 |  |  |  | 881.10.7 | Claims |  |  | X | X | X | X | X | X | X | X | X | X | X | each | 1 | 1 | 1 | [7 empty] | x
3.3.6 |  |  | 885 | Enforce Labor Provisions (6/21/16)
3.3.6.1 |  |  |  | 885 | Includes activities to ensure contract requirements are met.
3.3.6.2 |  |  |  | 885.1 | Sublet approval (DT 1925) | [5 empty] | X | X | X | X | X | X | X | X | Project | 2 | 2-4 | 4 | [101 empty] | 2-2/4-4
3.3.6.3 |  |  |  | 885.2 | Precon preparation and attendance | [5 empty] | X | X | X | X | X | X | X | X | Project | 2 | 2-4 | 4 | [101 empty] | 2-2/4-4
3.3.6.4 |  |  |  | 885.3 | Assist contractor with worker classification and reporting (CRCS) | [5 empty] | X | X | X | X | X | X | X | X | Project | 2 | 4 | 6 | [101 empty] | 2-4-6
3.3.6.5 |  |  |  | 885.4 | Wage interviews | [5 empty] | X | X | X | X | X | X | X | X | Project | 2 | 4 | 8 | [6 empty] | 1-2-4 | [94 empty] | 1-2-4
3.3.6.6 |  |  |  | 885.5 | Weekly payroll review | [5 empty] | X | X | X | X | X | X | X | X | Week | 2 | 3 | 6 | [101 empty] | 2-3-6
3.3.6.7 |  |  |  | 885.6 | Payroll clear date process and payroll audits | [5 empty] | X | X | X | X | X | X | X | X | Project | 4 | 8 | 16 | [101 empty] | 4-8-16
4 | Program Management
4.1 |  | Policy Development and Program Controls
4.1.1 |  |  | 855 | Program and Policy Development
4.1.1.1 |  |  |  | 855.1 | Develop transportation program and policy
4.1.1.2 |  |  |  | 855.2 | Manual development and updates (FDM, CMM, etc.)
4.1.1.3 |  |  |  | 855.3 | Standards and specification development and updates (Std Spec, STSP, Region SPV)
4.1.1.4 |  |  |  | 855.4 | Process reviews and process improvements
4.1.1.5 |  |  |  | 855.5 | Prepare STIP and TIP
4.1.2 |  |  | 863 | Program Controls
4.1.2.1 |  |  |  | 863 | Includes tasks involving budget and cost management, schedule management, issue management, and project and document management.
4.1.2.2 |  |  |  | 863.1 | Performance measurement management
4.1.2.3 |  |  |  | 863.2 | Report development and updates
4.1.2.4 |  |  |  | 863.3 | Report processing and review (Production, Health, Scheduling, Finals, etc.)
4.1.2.5 |  |  |  | 863.4 | Update project tracking applications (ex FIIPS, FOS, PeopleSoft)
4.1.2.6 |  |  |  | 863.5 | Project audits (LAB)
4.1.2.7 |  |  |  | 863.6 | Document management
4.2 |  | Systems Planning
4.2.1 |  |  | 211 | Statewide System Plans
4.2.2 |  |  | 214 | Corridor Study (Major Highway)
4.2.3 |  |  | 249 | Corridor Study (Other Highway)
4.2.4 |  |  | 250 | 84.25 Access Control Project New/Update
4.2.5 |  |  | 251 | 84.295 Statutory Expressway/Freeway
4.2.6 |  |  | 252 | Conceptual Land Division Review Activities
4.2.7 |  |  | 257 | Formal Land Division Review Activities
4.2.8 |  |  | 263 | Land Division TIA Review
4.2.8.1 |  |  |  | 263.1 | Determine land divisions
4.2.9 |  |  | 269 | Functional Class Routine Activities
4.2.10 |  |  | 280 | Census Review - (Urban Boundary Change)
4.2.11 |  |  | 281 | Jurisdictional Transfers on Non-State Roads
4.2.12 |  |  | 282 | Jurisdictional Transfers per STH Change Statute 84.02(3)
4.2.13 |  |  | 283 | Jurisdictional not Associated with any Relocation Project 84.02(8)
4.2.14 |  |  | 284 | Comprehensive Plan Involvement
4.2.15 |  |  | 285 | MPO and RPC Planning Liaison Activities
4.2.16 |  |  | 286 | Miscellaneous Land Use Studies
4.2.17 |  |  | 287 | Corridor Planning (Non-statutory Access Management Plans)
4.2.18 |  |  | 288 | Non-Highway Special Studies
4.2.19 |  |  | 289 | Public Transit Coordination and Outreach
4.2.20 |  |  | 296 | Park and Ride Lot and Commuter Center Management & Coordination
4.2.21 |  |  | 297 | Bike and Pedestrian Coordination and Outreach
4.2.22 |  |  | 299 | Coordination of Rail and Harbor Activities
4.2.23 |  |  | 300 | State Highway Program Development
4.2.24 |  |  | 314 | STN Activities
4.2.25 |  |  | 340 | Program Level Scoping
4.2.26 |  |  | 348 | Local Program Management and Implementation
4.2.27 |  |  | 349 | State Program Management and Implementation
4.2.28 |  |  | 687 | Rideshare Coordination and Outreach
4.3 |  | Systems Operations
4.3.1 |  |  | 227 | Roadside Facilities
4.3.2 |  |  | 228 | Bridge Maintenance
4.3.3 |  |  | 231 | Accident Damage Administration
4.3.4 |  |  | 275 | Inspect Structure
4.3.4.1 |  |  |  | 275 | Scoping task
4.3.4.2 |  |  |  | 275.1 | Specialty - Underwater dive bridge inspection
4.3.4.3 |  |  |  | 275.2 | Specialty - Bridge sign and signal inspection
4.3.4.4 |  |  |  | 275.3 | Specialty - Bridge deck survey structure inspection
4.3.4.5 |  |  |  | 275.4 | Specialty - Structure nondestructive evaluations and structure inspection
4.3.4.6 |  |  |  | 275.5 | Specialty - In plant QV inspection at prestress plants
4.3.4.7 |  |  |  | 275.6 | Specialty - Quality verification of precast concrete and metal drainage ...
4.3.5 |  |  | 322 | Inventory or Data Gathering
4.3.6 |  |  | 332 | Outdoor Advertising
4.3.7 |  |  | 333 | Adopt-A-Highway
4.3.8 |  |  | 334 | Utility Permits
4.3.9 |  |  | 335 | Driveway and Street Connection Permits
4.3.10 |  |  | 338 | Work on Right-of-Way Permits
4.3.11 |  |  | 520 | Crash Investigation
4.3.12 |  |  | 648 | Automation, Policy, and Standards Development
4.3.13 |  |  | 649 | Bridge Management and Asset Management
4.3.14 |  |  | 650 | Bridge Load Rating
4.3.15 |  |  | 652 | Bridge OSOW Permits Analysis and Review
4.3.16 |  |  | 684 | Sign & Miscellaneous Permits
4.3.17 |  |  | 685 | Diggers Hotline Administration
4.3.18 |  |  | 686 | Ancillary Structure Inspection
4.3.18.1 |  |  |  | 686 | Scoping task
4.3.18.2 |  |  |  | 686.1 | Specialty - Sign, signal and ancillary structure inspection
4.3.19 |  |  | 688 | Bridge Maintenance & Operations-Operational Bridges
4.3.20 |  |  | 689 | Bridge Maintenance & Operations-Ferry
4.3.21 |  |  | 690 | Bridge Maintenance and Operations - Ancillary Structures
4.3.22 |  |  | 691 | Roadway Maintenance-Pavement & Shoulder
4.3.23 |  |  | 692 | Roadway Maintenance-Culverts
4.3.24 |  |  | 693 | County Budget Development & Oversight
4.3.25 |  |  | 694 | Winter Maintenance Field Monitoring
4.3.26 |  |  | 695 | Winter Chemical Oversight
4.3.27 |  |  | 696 | Roadside Maintenance-Encroachments
4.3.28 |  |  | 697 | Roadside Maintenance-Drainage & Slopes
4.3.29 |  |  | 698 | Roadside Maintenance-Vegetation Management
4.3.30 |  |  | 738 | Lighting Design (non-improvement work)
4.3.31 |  |  | 739 | Contacts & Response to Inquiries
4.3.32 |  |  | 800 | COMPASS
4.3.33 |  |  | 801 | Improvement Project Operational Involvement-Roadway Maintenance
4.3.34 |  |  | 802 | Improvement Project Operational Involvement-Bridge Maintenance
4.3.35 |  |  | 804 | Traffic Engineering Studies
4.3.36 |  |  | 805 | Traffic Regulations & Declarations
4.3.37 |  |  | 806 | Electrical Facility Locates
4.3.38 |  |  | 807 | Improvement Project Operational Involvement-Traffic General
4.3.39 |  |  | 808 | Traffic Signal/Beacon-Design & Review (non-improvement work)
4.3.40 |  |  | 809 | Traffic Signal/Beacon Operational Review-Engineering
4.3.41 |  |  | 810 | Traffic Signal/Beacon Maintenance & Installation
4.3.42 |  |  | 811 | Signal/Lighting Inventory Data Management
4.3.43 |  |  | 812 | Improvement Project Operational Involvement-Traffic Signal/Beacon
4.3.44 |  |  | 813 | Sign Program Management
4.3.45 |  |  | 814 | Sign Plan Design (non-improvement work)
4.3.46 |  |  | 815 | Sign Inventory Data Management
4.3.47 |  |  | 817 | Sign Installation Review & Oversight
4.3.48 |  |  | 818 | Engineering Evaluation of Sign Needs/Requests
4.3.49 |  |  | 820 | Pavement Marking Program Management
4.3.50 |  |  | 821 | Pavement Marking Plan Design (non-improvement work)
4.3.51 |  |  | 822 | Pavement Marking Inventory Data Management
4.3.52 |  |  | 828 | Lighting Equipment Installation & Maintenance
4.3.53 |  |  | 829 | Lighting Permits
4.3.54 |  |  | 835 | ITS Activities
4.3.55 |  |  | 838 | Incident Response
4.3.56 |  |  | 867 | Traffic Signal System Program Delivery (admin of "stand-alone" only)
4.3.57 |  |  | 868 | Implements of Husbandry
4.4 |  | Technical Services
4.4.1 |  |  | 239 | Materials Research
4.4.1.1 |  |  |  | 239 | Scoping task
4.4.1.2 |  |  |  | 239.1 | Specialty - WisDOT qualified labs inspection
4.4.2 |  |  | 259 | R/E Technical User Groups
4.4.3 |  |  | 260 | Property Management
4.4.4 |  |  | 262 | Surplus Land Sales
4.4.5 |  |  | 991 | Tribal Meetings
4.4.6 |  |  | 992 | Tribal Relations
4.4.7 |  |  | 990 | Office of Business Opportunity and Equity Compliance
4.4.7.1 |  |  |  | 990 | Scoping task
4.4.7.2 |  |  |  | 990.1 | Specialty - Loan mobilization program
4.4.7.3 |  |  |  | 990.2 | Specialty - Outreach and marketing
4.4.7.4 |  |  |  | 990.3 | Specialty - Technical assistance
4.4.7.5 |  |  |  | 990.4 | Specialty - Legal assistance
5 | General
5.1 |  | General
5.1.1 |  |  | 101 | Work time
5.1.2 |  |  | 104 | Supervision
5.1.3 |  |  | 121 | Training
5.1.4 |  |  | 122 | Meetings and conventions
5.1.5 |  |  | 123 | Travel time
5.1.6 |  |  | 129 | Approved Professional Development Time
5.1.7 |  |  | 132 | Vacation - In Lieu of Sick Leave
5.1.8 |  |  | 133 | Legal Holiday - In Lieu of Sick Leave
5.1.9 |  |  | 134 | Personal Holiday - In Lieu of Sick Leave
5.1.10 |  |  | 135 | Vacation - FMLA | For use with Family Medical Leave Act (FMLA) time off
5.1.11 |  |  | 136 | Legal Holiday - FMLA | For use with Family Medical Leave Act (FMLA) time off
5.1.12 |  |  | 137 | Personal Holiday - FMLA | For use with Family Medical Leave Act (FMLA) time off
5.1.13 |  |  | 138 | Sick - FMLA | For use with Family Medical Leave Act (FMLA) time off
5.1.14 |  |  | 139 | Termination/Sabbatical - FMLA | For use with Family Medical Leave Act (FMLA) time off
5.1.15 |  |  | 140 | Absence without Pay - FMLA | For use with Family Medical Leave Act (FMLA) time off
5.1.16 |  |  | 141 | Comp Time Taken - FMLA | For use with Family Medical Leave Act (FMLA) time off
5.1.17 |  |  | 150 | Vacation Without Pay (Crafts) | For Crafts employees only
5.1.18 |  |  | 151 | Vacation
5.1.19 |  |  | 153 | Legal Holiday
5.1.20 |  |  | 154 | Jury Duty
5.1.21 |  |  | 155 | Military Leave - Annual Training
5.1.22 |  |  | 157 | Personal Holiday
5.1.23 |  |  | 161 | Sick - Employee Illness
5.1.24 |  |  | 163 | Sick - Family Illness
5.1.25 |  |  | 165 | Sick - Death in Family
5.1.26 |  |  | 167 | Exam and Interview Time
5.1.27 |  |  | 169 | Termination/Sabbatical
5.1.28 |  |  | 174 | Sick - Employee/Family Medical Appt
5.1.29 |  |  | 181 | Compensatory Time Taken
5.1.30 |  |  | 151 | Vacation
5.1.31 |  |  | 153 | Legal Holiday
5.1.32 |  |  | 154 | Jury Duty
5.1.33 |  |  | 155 | Military Leave - Annual Training
5.1.34 |  |  | 157 | Personal Holiday
5.1.35 |  |  | 163 | Sick - Family Illness
5.1.36 |  |  | 165 | Sick - Death in Family
5.1.37 |  |  | 167 | Exam and Interview Time
5.1.38 |  |  | 169 | Termination/Sabbatical
5.1.39 |  |  | 174 | Sick - Employee/Family Medical Appt
5.1.40 |  |  | 181 | Compensatory Time Taken
Note on U356: MitchPatoka: EX 2 person crew
Note on DV1: MitchPatoka: Includes LIDAR and Photogrammetry