#### US 53 Haugen Interchange

#### Barron County

##### April 2012

Project schedule:

May 2012: Start construction

November 2012: Winter shutdown

Spring 2013: Resume construction

November 2013: Construction

complete

For additional information about the project, contact:

WisDOT Northwest Region

Superior Office:

1701 N. 4th Street

Superior, WI 54880

Phone: (715) 392-7925

Brendan Dirkes

Project Manager

(715) 395-3026

brendan.dirkes@dot.wi.gov

Devin Harings

Project Engineer

(715) 579-4974

devin.harings@dot.wi.gov

Chris Ouellette

Communication Manager

(715) 833-9814

chris.ouellette@dot.wi.gov

Mission statement:

To provide leadership in the development and operation of a safe and efficient transportation system.

The Wisconsin Department of Transportation (WisDOT) is conducting a public involvement meeting to present project plans for the intersection improvement plans at US 53 and County V in Barron County this summer.

The meeting will be on Tuesday, April 17 at the Haugen Town Hall in Haugen. The meeting will be an informal, open house format.

You may stop in anytime between 5:30-7:30 p.m. to review the schedule, and ask questions of WisDOT staff regarding the project. All persons having an interest in the project are encouraged to attend.

Project Plans

- County V will underpass US 53

- Vehicles will merge onto US 53 via ramps

- All side-road crossing maneuvers will be eliminated

Traffic impact

US 53 will be reduced to one lane in each direction and bi-directional at times on either north or southbound US 53. County V west of US 53 will be detoured

County V east of US 53 will remain open at all times

Construction Schedule (Subject to change)

2012

- Construct temporary cross-overs and widenings

- Move all of US 53 traffic to NB lanes.

- Complete US 53 SB pavement, SB bridge, half of the retaining wall, and most of 19th Street North.

- Restore traffic to pre-construction conditions.

2013

- Move all of US 53 traffic to SB lanes.

- Complete US NB pavement, NB bridge, retaining wall, ramps, loops, and County V.

- Tie in 19th Street North.

- Open ramps, loops, and new County V to traffic.

- Remove cross-overs, 27th Ave West, US 53/County SS Intersection.

- Complete construction.

Wisconsin Department of Transportation – Dedicated people creating transportation solutions through innovation and exceptional service.