## Sheet1
Wisconsin Department of Transportation
Statewide Utility Conflict Analysis Report For Period: 1/1/2023 through 12/31/2023
Statewide Report Sorted by Contract, Project, and Report Number
03/04/2024
Contract ID | Federal Project Number | Construction Project ID | Description | Region | County | Route | Project Engineer | Project Engineer Office | Region Utility Coordinator | Conflict Report No | Report Completion Date | Project Type | Improvement Concept | Highway Contractor or Sub Affected #1 | Utility Company #1 | Facility Type #1 | Utility Location #1 | Highway Contractor or Sub Affected #2 | Utility Company #2 | Facility Type #2 | Utility Location #2 | Highway Contractor or Sub Affected #3 | Utility Company #3 | Facility Type #3 | Utility Location #3 | Date Utility Issue Discovered | Date Utility Issue Resolved | Digger Hotline Request Locating Issue | Utility Conflict Affects Controlling Item of Work | Existing Utility Facilities Shown Incorrectly In Project Plan | Conflict w/ Project Plan Not Identified | Not In Compliance w/ Work Plan/Permit | Project Plan Change | Other | Other Reason | Highway Contractor or Sub Used Alternate Means and Methods | Designed Around Utility Facility | Protected Utility Facility | Relocated Utility Facility | Discontinued Use of Utility Facility | Other | Other Resolution | Utility Conflict Impact On Contractor Schedule or Operations | Other Reason | Estimated Hours Spent by WisDOT / LPA / Consultant on Utility Issue | Other Reason | Estimated Hours Highway Contractor or Sub Was Affected | Other Reason | Impact to Contract Time and Cost | Other Reason | Attachments | Additional Pertinent Detail
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 62 | 10/27/2023 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | We Energies | Electricity | Underground | [8 empty] | 03/22/2023 | 03/22/2023 | No | Yes | [13 empty] | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | conflicting line was at the back of curb cuts for roadway excavation. The engineer and contractor agreed to move the subgrade cut in by two feet to alleviate the conflict.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 63 | 10/27/2023 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | We Energies | Gas/Petroleum | Underground |  | AT&T | Communication Line | Underground |  |  |  |  | 03/15/2023 | 04/04/2023 | No | No | [13 empty] | Contractor stopped work until utility delay was resolved |  | 16 to 24 hours |  | 16 to 24 hours |  | Non-Excusable Non-Compensable Delay |  |  | We Gas main and ATT Fiber concrete ductbank were in conflict with 60" storm sewer pipe. Both utilities were relocated to allow storm to be installed per plan.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 64 | 10/27/2023 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | AT&T | Communication Line | Underground | [8 empty] | 03/22/2023 | 03/29/2023 | No | No | [13 empty] | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | ATT line in conflict with 52nd Ave subgrade. Line was relocated.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 65 | 10/27/2023 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Charter Communications | Communication Line | Underground | [8 empty] | 03/29/2023 | 04/04/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Comm line is subgrade was relocated.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 66 | 10/27/2023 | 302 | RECONSTRUCTION, EXPANSION | ZIGNEGO COMPANY, INC. | We Energies | Electricity | Overhead |  | Spectrum | Communication Line | Overhead |  |  |  |  | 03/29/2023 | 04/19/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Utility pole guy wire anchors were in conflict with permanent concrete sidewalk construction.
20201208015 | wisc 2021031, 032, 033 | 1310-10-71 | 75th St, C Kenosha/V Pleasant Prair; 74th Ave To 43rd Ave | SE | Kenosha | STH 050 | Tom.Schmidt | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 67 | 10/27/2023 | 302 | RECONSTRUCTION, EXPANSION | MUSSON BROS., INC. | Midwest Fiber Networks LLC | Communication Line | Underground | ZIGNEGO COMPANY, INC. | [7 empty] | 06/07/2023 | 06/28/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Underground cable depth coming off of utility pole riser was not installed deep enough to allow for sidewalk subgrade excavation and permanent concrete sidewalk construction.
20210511016 | wisc 2021307 | 1146-75-72 | Sth 76-New London; Cth Jj - Lily Of The Valley Dr | NE | Outagamie | STH 015 | BenL.Thompson | JT ENGINEERING, INC. | Garrett.Vickman | 1 | 05/31/2023 | 302 | RECONSTRUCTION, EXPANSION | MASHUDA CONTRACTORS, INC. | We Energies | Electricity | Overhead | MICHELS ROAD & STONE, INC. |  | Other | [5 empty] | 05/17/2023 | 05/31/2023 | No | No |  |  |  |  | Yes | Overhead Light Facility at the CTH JJ/STH 15 could have been removed prior to the project. The overhead connection and light pole need to be removed for building the proposed WB lanes of STH 15. |  |  |  |  | Yes |  |  | Other | Conflict was identified ahead of contractor beginning work in this area | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Issue Overhead electrical wire from overhead power line runs to single pole with light at the CTH JJ/STH 15 intersection. Overhead wire and light need to be removed. BLT contracted WE energies on 5/17 to have facility removed prior to early June. 5/23 - WE looking at conflict on CTH JJ. 5/31 - WE notified BLT that pole and light at CTH JJ have been removed. This conflict is resolved
20210511016 | wisc 2021307 | 1146-75-72 | Sth 76-New London; Cth Jj - Lily Of The Valley Dr | NE | Outagamie | STH 015 | BenL.Thompson | JT ENGINEERING, INC. | Garrett.Vickman | 2 | 06/20/2023 | 302 | RECONSTRUCTION, EXPANSION | MICHELS ROAD & STONE, INC. | Spectrum | Communication Line | Overhead | MASHUDA CONTRACTORS, INC. | [7 empty] | 05/16/2023 | 06/20/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Other | Overhead line can remain in place until new underground line is installed under driveway with no effect to contractors work | 16 to 24 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Issue OH conflict was discovered at nursing home driveway. Spectrum OH line is 11' above proposed driveway grade. Vince from Spectrum was notified on 5/16. 5/18 Vince stopped out to look at facility, he will be on boarding a contractor to relocate line underground through the driveway. Vince asked that the department expedite the permit approval process as the overhead facility is at risk of being hit by traffic using the driveway. I passed this information to Jesse at the department. 5/30/2023 - I left a message for Vince at Spectrum as I have not seen a permit request or heard anything about when this wire will be installed underground. 5/31/2023 - I contacted Garrett at the department to see if he had any contacts for Spectrum since Vince took a new position. I am afraid that the overhead line at the driveway will be hit and damaged soon and want to make sure the ball is still rolling on this issue. Jeff (Spectrum) called and informed me that they dropped the ball on submitting the permit, but it will sent to the department today and they will be issuing a NTP to the contractor to get this work done ASAP. 6/6/2023 - Garbage truck brushed up against overhead line in this location. I contacted Jeff (Spectrum) and he informed me that they are still waiting on one signature to get the NTP issued for this work. I contacted Jesse and he said he signed it yesterday and will get it out ASAP. 6/8/2023 - KS contractor for Spectrum called they are installing underground facility today and should have the overhead switched over by Wednesday next week. 6/19 Stopped at the nursing home driveway after I saw workers looking at the underground cable installed, Foreman said they would be cutting the service over to the new line tonight and wrecking out the overhead line at the same time. 6/20 OH line was removed overnight. Conflict is resolved.
20210511016 | wisc 2021307 | 1146-75-72 | Sth 76-New London; Cth Jj - Lily Of The Valley Dr | NE | Outagamie | STH 015 | BenL.Thompson | JT ENGINEERING, INC. | Garrett.Vickman | 3 | 09/15/2023 | 302 | RECONSTRUCTION, EXPANSION | MICHELS ROAD & STONE, INC. | Spectrum | Communication Line | Overhead |  | AT&T | Communication Line | Overhead |  |  |  |  | 05/18/2023 | 09/15/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Other | Overhead lines can stay in place with low clearance until they are raised to adequate height without effecting contractors work | 16 to 24 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Conflict Overhead crossing of AT&T and Spectrum lines found to be only 13' above proposed grade at Bennett Court intersection. Vince from Spectrum was notified 5/18 and will secure a contractor to raise west end of overhead line at pole. Kyle (AT&T) was notified 5/18 based on how low spectrum is I don't think that AT&T can get high enough on the west end to get clearance over the sideroad like spectrum can. AT&T is securing a contractor to potentially add an independent pole at Bennett to get clearance. 7/12 - Chris (Michels) informed me that he spoke with Kyle Weber (AT&T) and the relocation is 3+ weeks out due to materials. Once materials are in the work order will go to emergency. 7/28 - WisDOT approved permit for relocation 7/31 - Bennett is up to finished red top grade and binder will be paved this afternoon. Bennett Nursery spade truck brushed the line without a tree in the spade on the way in this afternoon prior to binder being placed. I spoke with driver and owner that the line is in the works to get buried, but is a few weeks out by the sounds of it. 8/2 - BLT called Kyle (AT&T) this work has been released for construction. He estimates 2 weeks to complete. I notified Kyle that the line is conflicting with Bennett Nursery spade track without the asphalt on so I would not be surprised if the line is damaged after the asphalt is paved at Bennett. 8/16 - BLT contacted Kyle (AT&T) and informed him that traffic switch is happening week of 8/21 and it will be more difficult to complete the relocation. I also informed Kyle that the spade truck is now backing out onto 15 underneath the line to avoid damage to the line. After the traffic switch the spade truck will not be able to do this. Kyle informed me that the project has a completion date of 8/31 and would likely not be completed prior to traffic switch. 8/23 - Holtger Brothers will be on site tomorrow working on Bennett undgerground crossing tomorrow and Friday 8/24 - Holger boring under Bennett today. 9/15 - AT&T conflict at Bennett has been resolved
20210511016 | wisc 2021307 | 1146-75-72 | Sth 76-New London; Cth Jj - Lily Of The Valley Dr | NE | Outagamie | STH 015 | BenL.Thompson | JT ENGINEERING, INC. | Garrett.Vickman | 4 | 06/21/2023 | 302 | RECONSTRUCTION, EXPANSION | WEST-LAND RESTORATION, INC. | AT&T | Communication Line | Overhead | [8 empty] | 05/30/2023 | 06/21/2023 | No | No |  |  |  |  | Yes | Contractor damaged facility when landscaping | [5 empty] | Yes | New Guy Wire needs to be installed to replace the damaged guy and anchor | Other | Contractor damaged anchor. New anchor was installed and did not effect contractors work | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Issue 5/30/2023 BLT was notified that guy wire and anchor for AT&T overhead line was hit near Lily of the Valley. BLT contacted Kyle (AT&T). Kyle will put this work on his schedule to have the guy and anchor replaced. 6/21 New anchor was installed. Issue resolved
20210511016 | wisc 2021307 | 1146-75-72 | Sth 76-New London; Cth Jj - Lily Of The Valley Dr | NE | Outagamie | STH 015 | BenL.Thompson | JT ENGINEERING, INC. | Garrett.Vickman | 5 | 06/21/2023 | 302 | RECONSTRUCTION, EXPANSION | MASHUDA CONTRACTORS, INC. | We Energies | Electricity | Overhead | [8 empty] | 06/01/2023 | 06/21/2023 | No | No |  |  |  |  | Yes | Guy Wires need to be lowered due to location in backslope of ditch |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Conflict 6/1/2023 - Discovered conflict with Guy wires and Back slope of ditch for poles along North Rd. BLT contacted Mike (WE) and Mike said he would address these next week 6/21 BLT contracted Mike to check in on schedule to install new anchors. Crews on site today to install new anchors. Conflict resolved.
20210511016 | wisc 2021307 | 1146-75-72 | Sth 76-New London; Cth Jj - Lily Of The Valley Dr | NE | Outagamie | STH 015 | BenL.Thompson | JT ENGINEERING, INC. | Garrett.Vickman | 6 | 08/18/2023 | 302 | RECONSTRUCTION, EXPANSION | MASHUDA CONTRACTORS, INC. | Hortonville Area Schools | Communication Line | Underground | [8 empty] | 06/19/2023 |  | No | No |  | Yes | [10 empty] | Fiber Vault will have an extension added to bring the vault up to match the proposed grade | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Issue 6/19 Mashuda notified BLT of fiber vault for Hortonville Fiber not matching the proposed grading near the CTH JJ obliteration 6/20 BLT contacted Hortonville Schools and met Matt out on site to look at conflict. Matt will be scheduling work to add extension to vault to be completed as soon as possible. 8/10 I called Matt and asked him about vault and he informed me that it was raised. I stopped out on site and found the vault in the same state as it was in June. I informed Matt it was not raised. 8/11 Matt called and informed me that the wrong vault was raised and asked if I could meet TAK on site to show them the location of the vault to raise. I showed TAK the location and he will be informing me prior to work on the vault. 8/17 TAK called and they will be raising the vault tomorrow 8/18 TAK raised vault today, conflict has been resolved
20210511016 | wisc 2021307 | 1146-75-72 | Sth 76-New London; Cth Jj - Lily Of The Valley Dr | NE | Outagamie | STH 015 | BenL.Thompson | JT ENGINEERING, INC. | Garrett.Vickman | 7 | 07/27/2023 | 302 | RECONSTRUCTION, EXPANSION | NORTHEAST ASPHALT, INC | We Energies | Gas/Petroleum | [9 empty] | 07/26/2023 | 07/27/2023 | No | No |  | Yes | [5 empty] | Yes | [7 empty] | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Unresolved Utility Issue 7/26 - Discovered conflict with WE Energies gas valve and tracer wire. BLT contacted Cody (WE) and was put into touch with Adam (Field Contact). 7/27 - Valve and tracer wire were adjusted approximately 5". Paving of trail will be shifted slightly north to avoid having side by side valves in the middle of the trail avoiding potential issues with future settlement around the valves. Conflict has been resolved
20210914024 | wisc 2021441, 442 | 2270-04-70 | Sth 57-Vil Brown Deer & City Mequon; Teutonia Avenue To Mequon Road | SE | Milwaukee | STH 100 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 17 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | ZIGNEGO COMPANY, INC. | AT&T Wisconsin | Communication Line |  | TRIERWEILER CONSTRUCTION & SUPPLY COMPAN | [7 empty] | 05/09/2023 | 06/26/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | During sidewalk grading contractor identified that AT&T facilities were high compared to sidewalk finish elevation. Communication lines were potholed to determine depth and look to be within excavation depth to subgrade sidewalk and adjust slopes to meet ADA compliance.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 2 |  | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 04/12/2023 | 04/25/2023 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | James Peterson conducted ULO's on various ditch cut locations for utilities on the project to ensure they were clear of grading operations. One ULO identified a shallow cable as it approached the pedestal at station 183+25 LT that was recently installed. Cable was supposed to be 5 ft deep, however was only approximately 3 feet deep.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 3 | 05/24/2023 | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 04/12/2023 | 04/24/2023 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Contractor was grading for ditches and hit the newly installed Frontier cable at station 146+50 LT. The depth of the cable was approximately 3.5 feet deep, yet the permit called for the cable to be 6 feet deep in this location. Frontier was notified and project staff met with their contractor on Friday April 14. It was determined that the hit of the cable occurred at a splice location, and the splice was not dug down to the appropriate depth. Tracing the cable, it dived down to 6 feet within 10 feet for both side of the area hit. Crew was onsite on Monday April 24 to lower cable down and completed the work that day too.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 4 | 05/02/2023 | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | Charter Communications | Communication Line | Underground | [8 empty] | 04/04/2023 | 04/25/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 16 to 24 hours |  | Non-Excusable Non-Compensable Delay |  |  | While performing voluntary ULOs on existing utilities along STH 69, James Peterson identified a conflict with the existing Charter facility located along the west side of STH 69 between Richard St and Gehin Rd. According to the utilities SPV, this facility was identified, but noted to not be in conflict. When it was exposed, the cable was found to only be down 16" deep in an area with 2 feet of cut. JPS has not started grading in the area once the cable was identified, but did start grading just north. On April 11 David Moldenhauer stopped out, and asked staff for a current plan set. I responded that day with a link to the let plan set. Cross Country cable did end up coming out around 19th of April and placed a new cable on top of the ground so that JPS may resume grading. On April 25, Cross Country arrived back onsite to set a new pedestal and bury the new cable.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 5 |  | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 05/11/2023 |  | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Less than 01 hour |  |  |  |  | A conduit conflict was identified with Frontiers facility at 136+60 LT. Conduit should be installed 5-6 ft deep, however it is only approximately 2.5 ft deep and there is a ditch cut through there for 3 ft in depth. Frontier notified immediately, and coordinated for a crew to be onsite on Monday May 15. Crew arrived on the 15th to lower their facitility to find that electrical is on top of them, so electrical will have to move too. Crew able to lower most of their facility but leave the crossing area until they know what the electrical is going to do.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 6 |  | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | Alliant Energy | Electricity | Underground | [8 empty] | 05/15/2023 |  | No | No |  |  | Yes | [6 empty] | Yes | [12 empty] | While Frontier was onsite to lower their facility out of the way for the ditch cut at 136+60 LT, they discovered that electric is on top of their facility. I contacted Bruce Murray from Alliant and he responded that he will have their contractor onsite later today or tomorrow to start relocating.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 7 |  | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | Frontier Communications | Communication Line | Underground |  | Alliant Energy | Electricity | Underground |  |  |  |  | 05/12/2023 |  | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 01 to 04 hours |  |  |  |  | When grading for ditch on CTH A west, Peterson identified that Frontier and Alliant facilities were not deep enough for the ditch cuts on the new CTH A west road. Basically the cable will be on the surface once the ditch cut is complete. Frontier and Alliant were notifed the day the issue was discovered. Frontier will have their contractor address on Monday when they are onsite. Monday May 15 United Electric on site adjusting the facility to be out of conflict. Bruce Murray from Allliant will have their contractor adjust their portion later today or tomorrow he said.
20220208052 | wisc 2022004 | 1693-05-72 | New Glarus - Verona; Cth D To Valley Road | SW | Dane | STH 069 | Kim.Ballweg | AYRES ASSOCIATES INC (MDSN) | Richard.Olson | 8 |  | 303 | RECONSTRUCTION, PRESERVATION | JAMES PETERSON SONS, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 06/07/2023 |  | Yes | No | [9 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  | Digger&apos;s Hotline |  |  | While excavating ditching along the north side of the new CTH A west connection, a dozer cut both a phone and fiber optic cable that has not been marked by utility locating companies. Peterson moved to begin constructing the ditch for 69 just north of CTH A and noticed that the cable there for frontier was right at their finished elevation. Chris said they will not finishing cutting the ditch there too, for they are afraid that the weight of their equipment will damage the cable. Frontier onsite that evening, 06/07, to repair the fiber optic line. Waiting for United to return on site to lower the cable along STH 69.
20220412029 | n/a |  |  | NW |  | IH 094 | Chad.Beyer | GREMMER & ASSOCIATES, INC. |  | 1 |  |  |  | HOFFMAN CONSTRUCTION COMPANY | CenturyLink | Communication Line | [9 empty] | 10/19/2023 | 10/23/2023 | No | No | [5 empty] | Communication line at 90+19 'TRE', 36.5' LT was hit, but was found to be dead. | [7 empty] | Contractor stopped work at current location and moved to another location
20220614006 | wisc 2022422 | 1310-04-70 | 75th St, Village Of Paddock Lake; 256th Ave To 236th Ave | SE | Kenosha | STH 050 | Ryan.Cournoyer | GRAEF (MILW) | Michael.Birschbach | 2 |  | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | We Energies | Gas/Petroleum | [9 empty] | 03/28/2023 |  | No | Yes | Yes |  | Yes | [6 empty] | Yes |  |  | Oakes staked out proposed inlets and worked with Meade to have gas line "bubbled" around structure. Mark out included a buffer distance for storm sewer work. | Other | No impact to schedule - Meade moved lines around proposed inlets before storm sewer crew in area.
20220614006 | wisc 2022422 | 1310-04-70 | 75th St, Village Of Paddock Lake; 256th Ave To 236th Ave | SE | Kenosha | STH 050 | Ryan.Cournoyer | GRAEF (MILW) | Michael.Birschbach | 3 |  | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | We Energies | Electricity | [9 empty] | 03/28/2023 |  | No | Yes |  |  | Yes | [6 empty] | Yes | [12 empty] | Wood light pole at 1031+50, 35' RT with overhead electric was to be moved per permit, but WE Energies became confused with Village of Paddock Lake's decision to not have street lighting. Decision made after design was completed. WE Energies to remove and replace pole to new station 1031+60, 39' RT and 9.5' deep.
20220614006 | wisc 2022422 | 1310-04-70 | 75th St, Village Of Paddock Lake; 256th Ave To 236th Ave | SE | Kenosha | STH 050 | Ryan.Cournoyer | GRAEF (MILW) | Michael.Birschbach | 4 | 05/23/2023 | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | Frontier Communications | Communication Line | [9 empty] | 05/18/2023 | 05/23/2023 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 16 to 24 hours |  | Non-Excusable Non-Compensable Delay
20220614006 | wisc 2022422 | 1310-04-70 | 75th St, Village Of Paddock Lake; 256th Ave To 236th Ave | SE | Kenosha | STH 050 | Ryan.Cournoyer | GRAEF (MILW) | Michael.Birschbach | 5 |  | 303 | RECONSTRUCTION, PRESERVATION | A.W. OAKES & SON, INC. | AT&T | Communication Line | [9 empty] | 05/18/2023 | 06/08/2023 | No | No |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 16 to 24 hours |  | Non-Excusable Non-Compensable Delay |  |  | Holtger Bros. will move the line in conjunction with A.W. Oakes constructing the new ditch line. Holtger has coordinated with A.W. Oakes.
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 1 | 05/02/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 04/17/2023 | 05/02/2023 | No | Yes | [5 empty] | The line was installed too shallow, so it is in conflict with our ditch cut. Lowered in place. | [7 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Other |  |  | The work was at Smiley lane intersection, gas crossing on West and East sides in ditch cut, utility was not deep enough. WE Gas lowered the facility 1.5 to 2 feet. Rock Road was able to keep grading at a different location and just come back to grade this ditch later.
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 2 | 08/03/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Spectrum | Communication Line | Overhead | [8 empty] | 07/17/2023 | 08/03/2023 | No | Yes | [5 empty] | New overhead line sagging between utility poles, it is in the way of grading bulldozer work. | [6 empty] | Old line that was to be removed. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | The line location was Sta. 616 to 622 LT
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 3 | 08/09/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Spectrum | Communication Line | [9 empty] | 07/17/2023 | 08/09/2023 | No | Yes | [5 empty] | Pedestal and overhead line needed to be wrecked out and was not completed when new work was cut over. | [6 empty] | Facility was removed so contractor could continue grading. Spectrum delay of removing their dead facility also delayed WE Energies electric from removing their pole in the grading limits. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | The line was at Sta. 636+45 LT
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 4 | 08/09/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Spectrum | Communication Line | Underground | [8 empty] | 07/17/2023 | 08/09/2023 | No | Yes | [5 empty] | The facility was at too high of an elevation and was in conflict with our grading at Sta. 612+50 to 613+50 RT. This was a line that crossed the roadway under groung. | [6 empty] | Lowered facility in place so we could grade above it. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 5 | 10/31/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Spectrum | Communication Line | Underground | [8 empty] | 08/31/2023 | 10/31/2023 | No | Yes | [5 empty] | Line was in ditch cut. Needed to be lowered. | [6 empty] | Lowered line in place so we could perform ditch cut. Badger Basement driveway 594+50 LT | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 6 | 08/15/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 07/14/2023 | 08/15/2023 | No | Yes | [5 empty] | Handhole at Hackbarth is located inside the roadway shoulder. Need to move outside of roadway. | [7 empty] | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  |  |  |  | Near Sta. 4+00 HA LT
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 7 | 08/15/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 07/14/2023 | 08/15/2023 | No | Yes | [5 empty] | Existing pedestal in the roadway and needs to be moved out of the roadway. | [7 empty] | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  |  |  |  | The pedestal was removed and the communication line was spliced and buried in place. We filled over it.
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 8 | 08/08/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 08/01/2023 | 08/08/2023 | No | Yes | [5 empty] | The utility was underground, then up a pole to overhead at Hackbarth SW intersection corner. The subsoils was weathered bedrock, so I assume when the utility was relocated, they did not go below the bedrock to get good cover. We had ditch and backslope excavation in this area, resulting in a line hit. | [6 empty] | The utility lowered the line in its current location, excavated into the weathered bedrock to lower the repaired line. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | I believe this was a 50 pair phone line.
20220913003 | wisc 2022528 | 3575-03-71 | Fort Atkinson - Whitewater; Cth M - Buckingham Road | SW | Jefferson | USH 012 | Chad.Raschein | CGC, INC. | Richard.Olson | 9 | 07/11/2023 | 303 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Baldwin Broadband LLC | Communication Line | Underground | [8 empty] | 05/23/2023 | 07/11/2023 | No | Yes | [5 empty] | This line is Wisconsin Independent Network, LLC. It was not an option in the drop down arrow list "Utility Co. Name/ Municipal Utility 1" above. The line was noted as possible conflict in the Specials, we also had a bid item to locate the facility (pothole). | [6 empty] | The utility arrived on site as Rock Road scheduled to expose the entire line where in conflict and lower in place. Rock Road foreman worked with the contractor to give them cut elevations as they exposed the line and lowered it. | Contractor delayed start of work |  | 04 to 08 hours |  | Less than 01 hour |  |  |  |  | Fiber line that was in our subgrade cut for roadway core. The line was lowered as much as possible to below subgrade cut, very hard bedrock 1-2 feet below our subgrade, was the limit to lower the line.
20220913011 | wisc 2022512 | 2340-10-70 | Washington Ave, Town Dover; Sth 36 To Sb Ush 45 | SE | Racine | STH 020 | Willard.Bailey | KAPUR & ASSOCIATES, INC. | Michael.Birschbach | 1 |  | 303 | RESURF (OVERLAY >= 4 IN) |  | We Energies | Electricity | Overhead |  | AT&T | Communication Line | Overhead |  |  |  |  | 05/15/2023 | 05/24/2023 | No | No |  |  | Yes | [8 empty] | Yes | WE Energies will re-anchor guy. Grading complete in area so ther will be no conflict AT& T pulled guy anchor and will look into reinstalling anchor after project completion | Other |  | Other |  | Other |  | Other |  |  | Guy wires on WE Energies pole 22-8783 are in new ditch slope. Musson graded the slope which exposed about 1 foot of the guy anchor. James Nelson from WE Energies was contacted, a representative visited and determined the guy anchor will need to be re-anchored. No impact to the project. Guy wire from WE Energies pole 19-50767 is in conflict with backslope of the new ditch. James Nelson from WE Energies was contacted and stated this was an AT&T guy wire. Mike Vanboven from AT&T was contacted and he sent out a representative. This guy anchor was removed and the wire was wrapped around pole. AT&T will revisit after the project is completed and determine if the guy wire needs to be reinstalled. No impact to the project
20220913012 | wisc 2022513 | 3330-07-70 | Green Bay Rd - City Of Kenosha; Sth 50 To Cth S | SE | Kenosha | STH 031 | Kevin.Klipstein | WSP USA INC | Michael.Birschbach | 1 | 03/17/2023 | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | MP SYSTEMS, INC. | We Energies | Electricity | Overhead | [8 empty] | 03/08/2023 | 03/17/2023 | No | No |  | Yes | [5 empty] | Yes | [5 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | In the SE corner of 67th Street and STH 31, temporary wood pole 4, if installed per plan, would sit 3 feet below primary overhead electrical power and 7 feet above the neutral overhead power line. After consulting with James Nelson and Logan Peterson from WE Energies, we learned that the top of the wood pole could not be within 3 feet horizontally or vertically of the neutral power line. In order to maintain at least 17 feet of clearance for the lowest point of the temporary traffic signal head over live traffic, the lowest the temporary wood pole could be set at is 29 ft. The temporary traffic signal plan had to be revised to minimize the impact of the overhead electrical facility impact in the SE corner of 67th Street and STH 31. The revised plan, which was approved by John Bruggeman, has the contractor add a wood pole in the median between wood poles 4 and 5. Signal heads 5 and 15 will be mounted on this new pole. Wood pole 4 will be installed per plan and have signals 1 and 14 mounted on it. Since we will now not have any signal heads hanging from span between the new pole in the median and wood pole 4, MP System can lower the span wire between the median pole and wood pole 4. This will lower the height of wood pole 4 beneath the Neutral overhead electrical line by over the 3 feet required by WE Energies and out of conflict with WE Energies.
20220913014 | wisc 2022515 | 4080-06-71 | Kewaskum-Eden; Milwaukee River Bridge | NE | Fond Du Lac | USH 045 | Christopher.Wacek | WSP USA INC | Garrett.Vickman | 1 | 02/01/2024 | 201 | BRIDGE REPLACEMENT, PRESERVATION | RELYCO PLUS, LLC | Frontier Communications | Communication Line | Underground | SHEET PILING SERVICES LLC | Frontier Communications | Communication Line | Underground |  |  |  |  | 07/31/2023 | 08/15/2023 | No | Yes | [13 empty] | Contractor stopped work until utility delay was resolved |  | Other | These issues were discovered on 7/31/2023, resolution to all issues was determined on 8/4/2023, all issues were resolved on 8/15/2023; as multiple issues were discovered on the same date, the time spent to resolve these 2 specific issues was estimated at 24 to 32 hours; see Part 9 of this report for additional details. | Other | Contractor could not perform any work in the area of these 2 issues, from the discovery of the issues on 7/31/2023, until after the issues were resolved on 8/15/2023; at total of 11 working days were impacted; see Part 9 of this report for additional details. | Excusable - Non-Compensable Delay |  |  | See attached, 40800671_Utility Conflict Timeline Summary_Frontier.pdf, for details regarding the progression of the beginning of the utility conflicts and the subsequent efforts to resolve the conflicts. As facility was temporarily relocated to allow for construction to resume, the final relocation of the facility to the new permanent location was performed on 11/10/2023.
20220913014 | wisc 2022515 | 4080-06-71 | Kewaskum-Eden; Milwaukee River Bridge | NE | Fond Du Lac | USH 045 | Christopher.Wacek | WSP USA INC | Garrett.Vickman | 1 | 02/01/2024 | 201 | BRIDGE REPLACEMENT, PRESERVATION | SHEET PILING SERVICES LLC | AT&T | Communication Line | Underground | RELYCO PLUS, LLC | [7 empty] | 07/31/2023 | 08/07/2023 | No | Yes | [13 empty] | Contractor stopped work until utility delay was resolved |  | Other | The issue was discovered on 7/31/2023, resolution to the issue was determined on 8/2/2023, and the issue was resolved on 8/7/2023; as multiple issues were discovered on the same date, the time spent to resolve this specific issue was estimated at 24 to 26 hours; see Part 9 of this report for additional details. | Other | Contractor could not perform any work in the area of this issue, from the discovery of all the issues on 7/31/2023, until after this issue was resolved on 8/7/2023; at total of 5 working days were impacted by this specific issue; see Part 9 of this report for additional details. | Excusable - Compensable Delay |  |  | See attached, 40800671_Utility Conflict Timeline Summary_AT&T.pdf, for details regarding the progression of the beginning of the utility conflicts and the subsequent efforts to resolve the conflicts. As facility was temporarily relocated to allow for construction to resume, the final relocation of the facility to the new permanent location was performed on 10/5/2023.
20220913014 | wisc 2022515 | 4080-06-71 | Kewaskum-Eden; Milwaukee River Bridge | NE | Fond Du Lac | USH 045 | Christopher.Wacek | WSP USA INC | Garrett.Vickman | 1 | 02/01/2024 | 201 | BRIDGE REPLACEMENT, PRESERVATION | RELYCO PLUS, LLC | Charter Communications | Communication Line | Underground | SHEET PILING SERVICES LLC | [7 empty] | 08/01/2023 | 08/09/2023 | No | No | [12 empty] | Facility was determined to not been installed per the plan/permit for the utility, however it had been installed outside of the project limits and not in conflict with construction for the project. | Contractor delayed start of work |  | Other | The issue was discovered on 8/1/2023, resolution to the issue was determined and resolved on 8/9/2023; as multiple issues were discovered on the same date, the time spent to resolve this specific issue was estimated at 24 to 28 hours; see Part 9 of this report for additional details. | Other | Contractor could not perform any work in the area of this issue, from the discovery of all the issues on 7/31/2023, until after this issue was resolved on 8/9/2023; at total of 8 working days were impacted; see Part 9 of this report for additional details. | Excusable - Non-Compensable Delay |  |  | See attached, 40800671_Utility Conflict Timeline Summary_Charter-Spectrum.pdf, for details regarding the progression of the beginning of the utility conflicts and the subsequent efforts to resolve the conflicts.
20221011007 | N/A | 6100-08-60 | Fairwater-Brandon; Wcl-Sth 49 | NE | Fond Du Lac | STH 044 | Cayleigh.Shermo | GREMMER & ASSOCIATES, INC. | Garrett.Vickman | 1 | 08/28/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | HIGHWAY LANDSCAPERS, INC. | Alliant Energy | Electricity | Underground | [8 empty] | 08/22/2023 | 08/22/2023 | No | Yes |  | Yes | [10 empty] | Alliant repaired electrical utility that was hit and Highway Landscapers installed riprap over the utility. Alliant will permanently relocate the facility. | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Utility was 10" below existing grade. Location of conflict: Sta 100+83 LT.
20221108049 | wisc 2023052 | 9513-00-70 | Cth K - Cth B; Cth K To N Flowage Lake Road | NC | Vilas | CTH S | Jim.Peck | KAPUR & ASSOCIATES, INC. | Michael.Caban | 1 | 07/19/2023 | 201 | RECONSTRUCTION, PRESERVATION | EARTH, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 05/24/2023 | 07/19/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | Other | Resolution took ~7 weeks from first contact with Frontier to relocation. | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Pedestal at STA 269 LT was not identified as a conflict during design. The pedestal had to be raised and moved away from the new roadway.
20221108049 | wisc 2023052 | 9513-00-70 | Cth K - Cth B; Cth K To N Flowage Lake Road | NC | Vilas | CTH S | Jim.Peck | KAPUR & ASSOCIATES, INC. | Michael.Caban | 1 | 07/17/2023 | 201 | RECONSTRUCTION, PRESERVATION | EARTH, INC. | Frontier Communications | Communication Line | Underground | [8 empty] | 05/24/2023 | 07/17/2023 | No | No |  | Yes |  |  |  |  | Yes | [6 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Telephone cable STA 41 East Flowage Road inside of new roadway cut. Roadway contractor excavated and lowered cable during grading work.
20221213012 | N/A | 5992-10-04 | V Shorewood Hills, Lake Mendota Dr; Multi-Use Trail, B-13-0692 | SW | Dane | LOC STR | Tyler.Hassett | STRAND ASSOCIATES, INC. | Richard.Olson | 1 |  | 201 | BRIDGE REPLACEMENT, PRESERVATION | ZENITH TECH., INC. - WAUKESHA | Village of Shorewood Hills | Water | [9 empty] | 09/06/2023 |  | No | Yes | [13 empty] | Other | Contractor was not charged working days on 9/25, 9/26, 9/27, 9/28. See Additional Pertinent Detail for more information. | Other | See Additional Pertinent Detail for more information. | Other | See Additional Pertinent Detail for more information. | Excusable - Non-Compensable Delay |  |  | 9/6/23 Contractor hit and broke existing Village of Shorewood hills Water Main at Pier 1. Village of Shorewood Hills contractor repaired the break on the same day. No loss in work production. 9/7/23 Contractor submitted RFI No. 5 regarding Village of Shorewood Hills water main conflicts at Pier 2. 9/11/23 Designer provided markups in response to RFI No. 5 for a box out of the Village of Shorewood Hills water main at Pier 2. Village and Contractor agreed to perform the box out under time and materials and would be later added to the contract through a change order. 9/11/23 Project staff submitted RFI No. 6 regarding Village of Shorewood Hills water main conflicts at the West Abutment and East Abutment. 9/13/23 Project staff, Village of Shorewood Hills, and the contractor met on site to discuss how to proceed with the conflicts at the West and East Abutments with the Village of Shorewood Hills water main. The Village will lower the existing watermain at the west and east abutment with the assistance of the contractor. 9/19/23 Village of Shorewood Hills with the assistance of the contractor cut the existing water main at the west abutment to allow the contractor to continue structure excavation. No loss in work production. 9/25/23 - 9/28/23 Village of Shorewood Hills contractor on site to relocate water main at the west abutment. No working days were charged to the contractor as the Village of Shorewood Hills water main relocation did not allow the contractor to work on the controlling item of work (west abutment construction). 10/2/23 - 10/4/23 Village of Shorewood Hills contractor on site to relocate water main at the east abutment. No loss in work production.
20221213020 | wisc 2023101, 104 | 1146-75-76 | Sth 76-New London; Cth T-Wi Central Rr | NE | Outagamie | STH 015 | Marc.Roesler | WISDOT | Garrett.Vickman | 1 | 12/18/2023 |  | RECONSTRUCTION, EXPANSION | MCC, INC. | We Energies | Electricity |  |  | AT&T | Communication Line |  |  | Spectrum | Communication Line |  | 07/07/2023 | 10/04/2023 | No | No | [13 empty] | Contractor delayed start of work |  | 08 to 16 hours |  | Other | Issue didn't directly affect / delay contractor working time. Required modifying operations, planning, coordination, etc. | Other | No measurable impact to contract time or cost |  | 7/7/23 Contacted Spectrum about potential conflicts and to get relocation schedule. Existing pole line south of Old 15 had communication lines not relocated. Special provisions stated no anticipated conflicts. Work completed 10/4/23. No project delays but required coordination / effort by project staff to get this work completed without delays. 7/7/23 Contacted AT&T about potential conflicts and to get relocation schedule. Existing pole line south of Old 15 had communication lines not relocated. Special provisions stated work to be completed prior to construction. Work completed 10/4/23. No project delays but required coordination / effort by project staff to get this work completed without delays. Both utilities were located on WE Energies poles. Contractor pulled poles themselves the day after utilities were relocated to avoid delays.
20221213020 | wisc 2023101, 104 | 1146-75-76 | Sth 76-New London; Cth T-Wi Central Rr | NE | Outagamie | STH 015 | Marc.Roesler | WISDOT | Garrett.Vickman | 2 | 12/18/2023 |  | RECONSTRUCTION, EXPANSION |  | We Energies | Electricity | [9 empty] | 07/07/2023 | 08/08/2023 | No | No | [13 empty] | Contractor delayed start of work |  | 01 to 04 hours |  | Other | No Delays | Other | No measurable contract time or cost impact |  | 7/7/23 Notified WE Energies about three power poles near the intersection of Old 15 and Givens Rd that were relocated once already but are still in conflict with grading operations. Coordinated new pole locations with WE engineers. WE applied for new DOT permit and completed relocation work on 8/8/23 with no project delays.
20221213020 | wisc 2023101, 104 | 1146-75-76 | Sth 76-New London; Cth T-Wi Central Rr | NE | Outagamie | STH 015 | Marc.Roesler | WISDOT | Garrett.Vickman | 3 | 12/18/2023 |  | RECONSTRUCTION, EXPANSION | MCC, INC. | Spectrum | Communication Line | Underground | [8 empty] | 11/08/2023 | 11/13/2023 | No | No | [13 empty] | Other | None | Less than 01 hour |  | Less than 01 hour |  | Other | No measurable contract delay or cost |  | Business located adjacent to the project stopped on site to notify staff that their internet was not working. MCC was grading in this area at the time. A review of the area didn't identify any utility hits. Two days later a spectrum tec identified the service was hit by MCC while grading. The drop pole for the service was relocated out of the grading are prior to construction, but the underground service was left within the grading limits. Spectrum replaced the service, no project delays, no project costs.
20221213029 | wisc 2023113 | 1590-12-73 | Rhinelander - Monico; Ush 8 And Ush 45 South Intersection | NC | Oneida | USH 008 | Matthew.Spindler | REI ENGINEERING INC. | Michael.Caban | 1 | 06/29/2023 | 303 | PAVT REPLACEMENT | MUSSON BROS., INC. | Frontier Communications of WI LLC | Communication Line | Underground | [8 empty] | 06/28/2023 | 06/29/2023 | No | Yes |  |  |  |  | Yes | Utility issues was identified in the plans. Utilities were not relocated prior to the start of the project. | [5 empty] | Yes | On 6/29/23, it was determined that this utility line will be relocated and replaced in the upcoming months. However, until that time, it was determined that the pedestal will be removed, the line wrapped, and buried below the subgrade of the roadway. When the line is relocated, the existing line will be abandoned. | Contractor stopped work at current location and moved to another location |  | Other | As of 6/28/23, I estimate that this will take several days to be resolved. | Other | As of 6/28/23, I estimate that this will impact the contract several days. Not being able to work in the area will limit their production and completion of operations. Operations will need to continue through this area within a couple working days to progress the contract. | Non-Excusable Non-Compensable Delay |  |  | Pedestal is located near Sta. 440+25 RT, USH 8. The pedestals are approximately 8 feet within grading for the new intersection alignment and are approximately 3 feet vertically above the subgrade elevation. According to the special provisions, this facility was to be relocated prior to construction. This possible conflict was discussed during the preconstruction meeting and staff was informed that Frontier confirmed they are clear on this project.
20221213029 | wisc 2023113 | 1590-12-73 | Rhinelander - Monico; Ush 8 And Ush 45 South Intersection | NC | Oneida | USH 008 | Matthew.Spindler | REI ENGINEERING INC. | Michael.Caban | 2 | 06/29/2023 | 303 | PAVT REPLACEMENT | MUSSON BROS., INC. | Frontier Communications of WI LLC | Communication Line | Underground | [8 empty] | 06/29/2023 | 06/29/2023 | No | Yes |  |  |  |  | Yes | The utilities were marked. The contractor believes the line was 2-4 feet off the mark. 6/29/23 - At 2:30 pm, it was determined that the line found in the field was an abandoned line at a shallower depth in the vicinity of the fiber. | [5 empty] | Yes | As of 2:30 pm, it was determined that the line encountered in the field was an abandoned telephone line, not an active fiber. The line was struck during the marsh excavation which made it hard to see the line. It was determined that there were no outages in the area and a representative from the utility company was on site to determine the line was an abandoned line. Frontier sent a representative on 7/3/23 to verify the line was abandoned and the active line was not damaged. | Contractor stopped work at current location and moved to another location |  | Other | 6/29/23 - As of 11:30 am, the time to resolve the issue is unknown. 6/29/23 - As of 2:30 pm, the issue was resolved. | Other | 6/29/23 - As of 11:30 am, the time affected is unknown. 6/29/23 - As of 2:30 pm, the issue was resolved. | Non-Excusable Non-Compensable Delay |  |  | The contractor was performing marsh excavation near Sta. 439+00 RT in the SE quadrant of USH 8 and USH 45, South Intersection. The contractor potholed for the utility line and was not able to find the utility at the marked location. It was assumed that the utility was below their excavation depth. During excavation, a line was struck. This line was approximately 2-4 feet off the marking. It is unsure if the line is an abandoned line or an active line but the contractor feels confident that the line is the active line.
20221213029 | wisc 2023113 | 1590-12-73 | Rhinelander - Monico; Ush 8 And Ush 45 South Intersection | NC | Oneida | USH 008 | Matthew.Spindler | REI ENGINEERING INC. | Michael.Caban | 3 | 07/12/2023 | 303 | PAVT REPLACEMENT | MUSSON BROS., INC. | Frontier Communications of WI LLC | Communication Line | Underground | [8 empty] | 07/10/2023 | 07/12/2023 | No | Yes |  |  |  |  | Yes | Relocated cables were not installed deep enough. Found approximately 1-foot above finished grade. |  |  |  | Yes |  | Yes | 7/10/23 - Frontier representative on site at 10:30, stated that lines will need to be buried deeper. | Contractor stopped work at current location and moved to another location |  | Other | 7/10/23 - As of 10:30, it is anticipated for the cables to be repaired by the end of the day Wednesday, July 12th. | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | 7/10/23 - At 8:30, Musson struck a line near Sta. 1417+50 RT/Sta. 436+75 RT in the SE quad of the intersection of USH 8 and USH 45, South Intersection. Musson performed potholing operations in the area and found the cables. Between pothole locations, the cable raised elevation approximately 3-feet. The cables were found to be approximately 1-foot above the finished grade of the new alignment. A Frontier representative came to the site and verified that they 2 cables were damaged. As of 10:30, the Frontier representative believed that it may take until Wednesday to repair the lines if crews can be sent to the area.
20221213029 | wisc 2023113 | 1590-12-73 | Rhinelander - Monico; Ush 8 And Ush 45 South Intersection | NC | Oneida | USH 008 | Matthew.Spindler | REI ENGINEERING INC. | Michael.Caban | 4 | 07/12/2023 | 303 | PAVT REPLACEMENT | MUSSON BROS., INC. | Frontier Communications of WI LLC | Communication Line | Underground | [8 empty] | 07/11/2023 | 07/12/2023 | No | Yes | Yes |  |  |  | Yes | 7/11/23 - Frontier fiber line was not identified in the plan at this location. |  |  |  | Yes |  | Yes | 7/11/23 - Telecom called Frontier and they came to site to repair the line within a few hours. | Contractor stopped work at current location and moved to another location |  | 16 to 24 hours |  | 16 to 24 hours |  | Non-Excusable Non-Compensable Delay |  |  | 7/11/23 - Telecom was subcontracted out by Frontier to repair Utility Conflict 3. Telecom needed to lower the telephone lines that were struck on 7/10/23 to get them below finished grade and at an appropriate depth. During excavation, Telecom struck a Frontier fiber line. From what I heard through members on site, no markings were staked for this line as it was believed to be at a different location, well away from this away. This line was believe to be abandoned. Frontier arrived mid-day to begin splicing the line.
20221213029 | wisc 2023113 | 1590-12-73 | Rhinelander - Monico; Ush 8 And Ush 45 South Intersection | NC | Oneida | USH 008 | Matthew.Spindler | REI ENGINEERING INC. | Michael.Caban | 5 | 07/14/2023 | 303 | PAVT REPLACEMENT | MUSSON BROS., INC. | Spectrum | Communication Line | Overhead | NORTHEAST ASPHALT, INC | [7 empty] | 06/28/2023 | 07/14/2023 | No | Yes |  | Yes |  |  |  | 6/28/23 - The contractor requested a timeline of when the remaining pole was going to be removed. 6/29/23 - The contractor informed WisDOT that the pole had street lighting on the pole and also found a Spectrum line on the pole that was not identified to be conflict in the specials. 6/29/23 - Received an email from Harold |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location | 6/28/23 - The contractor requested a timeline of when the remaining pole was going to be removed. 6/29/23 - The contractor informed WisDOT that the pole had street lighting on the pole and also found a Spectrum line on the pole that was not identified to be conflict in the specials. 6/29/23 - Received an email from Harold | 01 to 04 hours |  | Other | Wires on the pole were in the way for work operations. The contractor maneuvered around the wire but would of been ideal if the conflict was removed. | Non-Excusable Non-Compensable Delay |  |  | The plans indicate to remove the lighting pole near Sta. 432 RT. WPS came out to the site and removed the lighting. It was found that a Spectrum line was also on the pole. WPS removed their pole tags and equipment and left the pole as is. 6/28/23 - The contractor requested a timeline of when the remaining pole was going to be removed. 6/29/23 - The contractor informed WisDOT that the pole had street lighting on the pole and also found a Spectrum line on the pole that was not identified to be conflict in the specials. 6/29/23 - Received an email from Harold Moore (Charter) that a job has been placed to have the pole removed. 7/11/23 - Musson requested from Harold when this pole will be removed as the pole will now be holding up grading/paving operations.
20221213029 | wisc 2023113 | 1590-12-73 | Rhinelander - Monico; Ush 8 And Ush 45 South Intersection | NC | Oneida | USH 008 | Matthew.Spindler | REI ENGINEERING INC. | Michael.Caban | 6 | 07/14/2023 | 303 | PAVT REPLACEMENT | GORDON J. GRUBE CONSTR. CO., INC. | Frontier Communications of WI LLC | Communication Line | Underground | MUSSON BROS., INC. | [7 empty] | 07/14/2023 | 07/14/2023 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Plans indicate a communications line to be under the west apron of B-43-64. The special provisions did not indicate the line to be in conflict with work operations. On 7/14/23, bridge crew located the line approximately three feet below water elevation. While this may have cleared the excavation of the apron and undercut of breaker run, it did account for the cofferdam installation. Grube contacted Frontier once discovered. Frontier sent a crew to the site to relocate the line in the morning of 7/14/23.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 1 | 10/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | ATC Management, Inc. | Electricity | Overhead | [8 empty] | 03/03/2023 | 10/26/2023 | No | No | [5 empty] | These work operations were not included in project coordination. | [11 empty] | Less than 01 hour |  |  |  |  | There is ATC transmission line reconstruction work within the project limits. There was no mention of this work during the design coordination but work is currently being done within the project limits that includes a crossing of STH 21 and will need coordination with the construction project.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 10 | 04/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Bug Tussel Wireless, LLC | Communication Line | Underground | [8 empty] | 04/13/2023 | 04/26/2023 | No | No |  | Yes | Yes | [7 empty] | Yes |  |  |  |  | Less than 01 hour |  | Less than 01 hour |  |  |  |  | STA 238+25 LT - Conduit and handhole in conflict with proposed grading - Conduit and handhole removed utilities on 4/26/23 (work completed by subcontractor KES) - Interduct still in the ground. STA 238+25 RT - Conduit in conflict with proposed grading - Conduit removed utility on 4/26/23 (work completed by subcontractor KES) - Interduct still in the ground. STA 345+00 - 353+50 LT - Conflict identified with proposed grading - Handhole and fiber removed by KES on 4/26/23 - Handhole at 11th Rd and fiber from interduct going100 ft north on 11th Rd, also removed fiber from interduct from handhole at 11th Rd going west along the north and south side of STH 21 STA 353+00 - 372+25 RT - Conflict identified with proposed grading - Fiber and handhole (STA 375+25 RT) removed by KES on 4/26/23 - Interduct still in the ground.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 11 | 05/22/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground |  | Adams-Columbia Electric Cooperative | Electricity | Underground |  |  |  |  | 04/27/2023 | 05/02/2023 | No | No |  |  | Yes | [6 empty] | Yes | Yes | [11 empty] | BRIGHTSPEED, STA 564+00 - 548+20 LT - Mashuda hit a phone line that was no buried deep enough. The line was located 1.5 feet above the proposed ditch grade. - Scott Heinzelman of Brightspeed indicated that the hit was not Mashuda's responsibility, the utility was to have been buried deeper than the proposed ditch as indicated in the permit and the plan. - Brightspeed abandoned line and cut service over to another line on 4/27/23. ADAMS COLUMBIA ELECTRIC, STA 548+28 LT - Guy wire in conflict with proposed grading - ACEC to move wire prior to grading - Move was completed on 5/2/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 12 | 05/01/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground |  | Adams-Columbia Electric Cooperative | Electricity | Underground |  |  |  |  | 04/10/2023 | 05/01/2023 | No | No |  | Yes | Yes | [6 empty] | Yes | [5 empty] | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | BRIGHTSPEED, STA 6+5+00 - 567+00 LT - Mashuda discovered phone line is not deep enough to accommodate proposed grading. - Brightspeed lowered the phone line on 4/28/23 BRIGHTSPEED, STA 563+50 RT - Mashuda discovered communication line not deep enough to accommodate proposed grading - Brightspeed lowered the communication line on 5/1/23 ADAMS COLUMBIA ELECTRIC, STA 564+00 LT - Mashuda discovered power line not deep enough to accommodate proposed grading - ACEC lowered the power line on 5/1/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 13 | 04/27/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground | [8 empty] | 04/26/2023 | 04/27/2023 | No | No |  | Yes | [7 empty] | Yes | [5 empty] | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | STA 589+00 - 594+00 LT - Phone line in conflict with proposed grading - Brightspeed lowered line on 4-27-23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 14 | 04/27/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 04/25/2023 | 04/27/2023 | No | No |  | Yes | Yes | [6 empty] | Yes | [12 empty] | STA 614+50 - 616+00 RT - Mashuda identified that a low pressure gas main was within 4 inches of the proposed subgrade and a service was within 6 inches of the proposed subgrade. - We Energies lowered both the main and the drop service on
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 15 | 04/25/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground | [8 empty] | 04/25/2023 | 04/25/2023 | Yes | No | [9 empty] | Yes | [5 empty] | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | STA 657+60 LT - Mashuda struck a 50 pair phone line that had not been marked by Diggers - Brightspeed was on site within 2 hours and repaired the phone line
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 16 | 04/21/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Spectrum | Communication Line | Underground | [8 empty] | 04/21/2023 | 04/21/2023 | No | No | [9 empty] | Yes | [5 empty] | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | STA 658+90 RT - Mashuda struck a coax line next to a culvert. Potholing had been completed by Mashuda on both end of the culvert to determine the depth of the line. However, in the middle of the driveway, the line came up significantly because of a rock. - Line was repaired by Spectrum on 4/21/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 17 | 05/22/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Spectrum | Communication Line | Underground | [8 empty] | 04/10/2023 | 05/15/2023 | No | No |  | Yes | [7 empty] | Yes | [12 empty] | STA 662+00 LT - Mashuda struck an underground Spectrum communication line on 4/20/23 - Spectrum temporarily ran an above ground line to continue service to the affected resident - Brian Stephens told Mashuda on 4/20/23 that he had put a work order in for the line to be restored underground but it would be a minimum of two weeks to a month for the line to be repaired. - The line was successfully repaired on 5/15/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 18 | 04/21/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground | [8 empty] | 04/03/2023 | 04/21/2023 | No | No |  | Yes | [7 empty] | Yes | [12 empty] | STA 669+50 LT - Brightspeed had a pedestal in conflict with the proposed ditch grading - Pedestal move completed on 4/21/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 19 | 10/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Spectrum | Communication Line | Underground | [8 empty] | 05/08/2023 | 08/02/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location | [8 empty] | SPECTRUM - Mashuda contacted Spectrum about a communication line in conflict with the proposed work - Paul Grove (Spectrum) indicated he would review the conflict. - Duane (Mashuda) contacted Paul Grove in regards to an update on the progress for the line in conflict. Paul indicated that Spectrum was waiting for a permit approval from the Department. - WisDOT utility received the permit on 6-2-23 - Duane called Paul in regards to the permits previously requested. He left messages, but no reply. - Duane met with Paul Groves (6/12/23) to plan line replacement the week of 6/12/23 - Duane contacted Paul Groves (6/28/23) and stated that his contractor would be able to begin work on the lines on July 13th Performed the relocation then had to wait for splicing
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 2 | 04/24/2023 | 303 | PAVT REPLACEMENT |  | Adams-Columbia Electric Cooperative | Electricity | [9 empty] | 04/07/2023 | 04/24/2023 | No | No | [22 empty] | STA 285+02, 50' LT Adams-Columbia Electric - Power pole is located on the old R/W line. Pole will be in the proposed back slope, resulting in an additional 2ft of the pole exposed after the proposed grading. - Underground line fed from power pole in conflict with ditch bottom - ACEC will review proposed cut and lower pole and line. - Anticipated date of completion is April 20, 2023. - Pole and underground line both lowered. Completed work on April 24, 2023.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 20 | 05/22/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Adams-Columbia Electric Cooperative | Electricity | Underground | [8 empty] | 05/12/2023 | 05/31/2023 | No | No |  | Yes | [8 empty] | Yes |  |  |  |  | 01 to 04 hours | [6 empty] | ADAMS-COLUMBIA ELECTRIC STA 352+70 - 354+00 RT - Conflict identified with proposed apron endwall elevation. Duane (Mashuda) met with ACEC on 5/15/23 to discuss conflict - ACEC de-energized line in conflict so Mashuda could complete their work
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 21 | 05/22/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Adams-Columbia Electric Cooperative | Electricity | Underground | [8 empty] | 05/09/2023 | 05/09/2023 | No | No | [22 empty] | ADAMS-COLUMBIA ELECTRIC STA 458+00 LT - Mashuda struck a power line while installing a culvert. The power line was potholed and located by Mashuda on either side of the driveway, showing that the line was 1.5 feet below the grade of the new pipe. Mashuda began to excavate material above the power line and discovered the line quickly changed grade beneath the driveway. See notes from DWR below: While backhoe began grading for driveway culvert pipe at 458+06 LT, buried asphalt was found several feet under existing driveway elevation. Backhoe began pulling asphalt out of the way of pipe subgrade, which resulted and asphalt catching unseen power line and breaking. Mashuda had potholed for the marked electrical line on each side of the driveway. The up station end of culvert had +/- 4' of cover. The down station end had less, but still below pipe subgrade. The power line was hit in middle of driveway. Line jumped in elevation at that location and was almost even with pipe subgrade. Mashuda foreman was notified and they called Adams-Columbia Electric. Crew moved to opposite side of road to work on Cottonville Ct. culvert. ACEC arrived on site within half hour. Repairs were completed around 1pm.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 22 | 05/22/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Adams-Columbia Electric Cooperative | Electricity | Underground | [8 empty] | 05/18/2023 | 05/19/2023 | No | No |  | Yes | [8 empty] | Yes | [11 empty] | ADAMS-COLUMBIA ELECTRIC STA 486+00 LT - Mashuda identified a conflict with the existing electric and proposed apron endwall. - Mashuda informed ACEC of the conflict, ACEC de-energized the line to allow Mashuda to complete the construction on 5/18/23. - The line was replaced on 5/19/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 23 | 05/22/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground | [8 empty] | 05/17/2023 | 05/17/2023 | No | No |  | Yes | [7 empty] | Yes | [5 empty] | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | BRIGHTSPEED STA 533+00 RT - Mashuda identified two communication lines in conflict with the culvert pipe endwall. - Mashuda completed the lowering of the communication line with Brightspeed oversight. Mashuda took 2 hours to lower the line. STA 533+00 LT - Mashuda identified two communication lines in conflict with the culvert pipe endwall. - Mashuda completed the lowering of the communication line with Brightspeed oversight. Mashuda took 2 hours to lower the line.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 24 | 05/31/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Adams-Columbia Electric Cooperative | Electricity | Underground |  | Union Telephone Company | Communication Line | Underground |  |  |  |  | 05/24/2023 | 05/31/2023 | No | No | [15 empty] | 01 to 04 hours | [6 empty] | STA 212+25 LT (9th Ave) Adams Columbia Electric - 5/24/23 Duane (Mashuda) met with Duane Moore (ACEC) to discuss power line conflict. Duane Moore contacted Union Telephone (the utility the power was supplying), it was mutually decided to abandon the power to Union Telephone on 5/31/23 Union Telephone - 5/24/23 Duane (Mashuda) met with Darrel Wessels (Union Tel) to discuss two conflicts at STA 212+25 LT. They met again on 5/25/23 and it was decided to lower one utility and abandon the second. Both will occur on 5/31/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 25 | 06/12/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Adams-Columbia Electric Cooperative | Electricity | Underground |  | Brightspeed of Wisconsin, LLC | Communication Line | Underground |  |  |  |  | 05/25/2023 | 06/12/2023 | No | No | [15 empty] | 01 to 04 hours | [6 empty] | STA 459+80 - 461+50 LT/RT -- Lunch Creek Box Culvert Adams-Columbia Electric - Duane (Mashuda) contact Duane Moore (ACEC) with utility conflict at culvert replacement on 5/25/23. - Power is planned to de-energize on 6/2/23 and a crew will be back on site to assist with the wire when it will be pulled back on 6/5/23 - MJ Electric started boring a new power line and had difficulty installing (6-8-23). The plan on tentative completion on 6-12-23. Brightspeed - Duane (Mashuda) met with Scott (Brightspeed) on 5/25/23 - A line is possibly in conflict with the diversion channel. Scott indicated he would be on site during the diversion channel work and would work with Mashuda to eliminate any conflicts or delays. - Bright speed started boring but ran into difficulty with the installation. The plan of tentative completion on 6-12-23.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 26 | 10/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Spectrum | Communication Line | Underground | [8 empty] | 05/31/2023 | 06/26/2023 | No | No | [22 empty] | STA 220+75 - 221+50 RT SPECTRUM - On 5/31/23, Duane (Mashuda) contacted Paul Grove (Spectrum) that a line was in conflict with a backslope. Paul indicated that the line would be moved. Duane expressed the importance of moving this line quickly since grading operations will happen at that location within the next week. - Duane met with Paul Groves (6/12/23) to discuss sending a Spectrum crew to dig up and move the cable behind the silt fence the week of 6/12/23. He will re-bore cable after grading is complete. The final relocation for this segment may be part of a overall relocation for the line from 220+00-235+00 RT side after the project. As of end of October crews had not completed the relocation of the line from 240-230+00, but the area listed above at 221+00 was relocated so the proposed back slope could be completed.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 27 | 08/02/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Spectrum | Communication Line | Underground |  | Union Telephone Company | Communication Line | Underground |  |  |  |  | 06/08/2023 | 08/02/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | STA 10+00 RT/LT SPECTRUM: - Duane with Mashuda contacted spectrum to move a box at 10+00 RT. He left messages, no reply. (6-8-23, 6-9-23) - Duane met with Paul Groves (6/12/23) and decided that Spectrum was going to try and get the box (10+00 RT) moved the week of 6/12/23. - Duane with Mashuda called to request that a utility needs to be lowered at 10+00 LT (6-8-23) - Duane met with Paul Groves (6/12/23) and decided that Spectrum would try and lower the utility (10+00 LT) the week of 6/12/23. - Duane contacted Paul Groves (6/21/23) and informed him that if there were any penalties charged to Mashuda for late work, that they would be charged to Spectrum along with any mobilizations. - Duane contacted Paul Groves (6/26/23) asking when Spectrum would be getting on site, and they did not know when they would get there. - Duane called Paul Groves (6/28/23) and stated that his contractor would be able to begin work July 13th. UNION TELEPHONE: - Duane contacted Darrel Wessel with Union Telephone (6-8-23). They met 6-9-23 to discuss and confirm moving ped and hand hole work at 10+00 LT to the week of 6-12-23. - Completed 6/14/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 28 | 06/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Village Of Coloma | Water | Underground |  | Alliant Energy | Electricity | Underground |  | Spectrum | Communication Line | Underground | 06/09/2023 | 06/26/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | STA 18+00 LT VILLAGE OF COLOMA: - Duane with Mashuda contacted the Village of Coloma (6-9-23) in regard to a water valve box that needs to be lowered. The Village plans to lower the box the week of 6-12-23. - Duane met with Bud from the Village (6/12/23). Bud plans on cutting off the water valve stand pipe by digging around the water valve and water line. Bud plans to install insulation over the water line because it has minimal cover. The village plans this work to be performed the week of 6/12/23. - Duane contacted Bud (6/26/23) to ask off the water line was insulated. Bud stated that he was going to hand dig around the shut off pipe and insulate that only. Bud cut off the stand pipe below ditch grade. ALLIANT ENERGY: - Duane contacted Alliant Energy (6-9-23) to notify them that their wire will only have about a foot of cover after grading operations. Alliant Energy plans to inspect the week of 6-12-23. - Duane talked with Alliant (6/12/23) to plan that the line will be lowered on 6/14/23. SPECTRUM - Mashuda hit a coex line in the intersection. There were no markings, Spectrum came to temporary repair 6/15/23. - Spectrum Utility Investigator (Leonard Cheruiyot from PRG) came on-site to inspect coex damages. Leonard documented no markings and Duane gave him Diggers number (2023231208).
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 29 | 08/02/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Spectrum | Communication Line | Underground | [8 empty] | 05/15/2023 | 08/02/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | STA 9+00 RT - Cole called Spectrum (6/15/23) stating there was a conflict with a communication line - Duane with Mashuda called Paul Groves (Spectrum). Paul said that there was no line in that area (STA 9+00 RT) - Duane had Cole contact Paul Groves to tell him that it was a live utility wire and it needed to be moved. - Duane contacted Paul Groves (6/21/23) and informed him that if there were any penalties charged to Mashuda for late work, that they would be charged to Spectrum along with any mobilizations. - Duane contacted Paul Groves (6/26/23) asking when Spectrum would be getting on site, and they did not know when they would get there. - Duane called Paul Groves (6/28/23) and stated that his contractor would be able to begin work July 13th.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 3 | 04/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Bug Tussel Wireless, LLC |  |  |  | Adams-Columbia Electric Cooperative | Electricity | Underground |  | Brightspeed of Wisconsin, LLC | Communication Line | Underground | 04/07/2023 | 04/21/2023 | No | No | [22 empty] | STA 372+25 RT, CTH II/STH 21 Intersection Adams-Columbia Electric - Power box at STA 372+28, 62' RT - Box and underground line located within grading limits - Anticipated resolution: ACEC will eliminate power box and relocated underground line outside of grading limits, near right of way. Work to be done end of week of April 17, 2023. - Power box moved to right of way, work completed on April 21, 2023 Brightspeed - Pedestal located at 372+25, 48' RT, located within grading limits - Brightspeed completed the pedestal move on 4/12/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 30 | 10/26/2023 | 303 | PAVT REPLACEMENT | HIGHWAY LANDSCAPERS, INC. | Spectrum | Communication Line | Other | [8 empty] | 09/19/2023 | 09/20/2023 | No | No | [5 empty] | This was a underground communication line that had been laid on top of the ground. Spectrum had run a temporary line on top of the ground while they are waiting to install their new line along the south side of the hill cut. That line was in conflict with Mashuda earlier in the year and Spectrum had laid a temporary line in the woods, grass in the interim. As Highway was mowing their seeded areas they went around a handhole that had cable coils up on it but between that handhole and the woods to the south where they laid the fiber line on the ground is was in grown grass and the 3 point mower caught it. Crews were there that night to make repairs. Spectrum Inspector was onsite and asked the PL questions in regards to who was working there. MJD asked to meet him onsite but the investigator said he was from Dodgeville and would not come back up there to meet. When all contract work was completed the installation/relocation of that temporary line was still not completed. In previous meetings earlier in fall Paul Grove stated that they would be there this October to install a new line. When all contract work was completed on 10/26/23 they still had not been there to complete that work. Lath was installed in the hill-cut backslope to show them were the special seed was located so they could replace in kind if they disturbed the project restoration. | [6 empty] | Spectrum/Charter crews the evening of 9/19 spliced and repaired the cable, left it still on top of the ground but added some stakes and markers along it. | Contractor stopped work at current location and moved to another location |  | 08 to 16 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 4 | 07/26/2023 | 303 | PAVT REPLACEMENT |  | Adams-Columbia Electric Cooperative | Electricity | Underground |  | Brightspeed of Wisconsin, LLC | Communication Line | Underground |  |  |  |  | 04/07/2023 | 07/12/2023 | No | No | [22 empty] | STA 383+00 - 385+00 LT Adams-Columbia Electric - Underground power line marked near location of box culvert bypass channel. ACEC will review depth of line to confirm it is deep enough for bypass channel. - ACEC checked depths of power and indicated to Mashuda that the line is 9 to 10 feet deep and would not be an issue. - ACEC de-energized the power line during the construction of box culvert for added safety. The box culvert was successfully constructed without effecting the power line and the line was re-energized. - Work at the box culvert was complete on July 26, 2023 Brightspeed - Fiber optic line located within bypass channel. Brightspeed indicated at the April 14 utility meeting on site that there was adequate clearance at that location and a relocation would not be necessary.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 5 | 05/01/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground |  | Adams-Columbia Electric Cooperative | Electricity |  |  | Marquette-Adams Communications LLC | Communication Line | Underground | 04/04/2023 | 05/01/2023 | No | No |  | Yes | Yes |  |  |  |  | Yes |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 01 to 04 hours |  |  |  |  | STA 588+00 RT/LT - CTH Y Intersection with STH 21 (SW Quadrant) Designed culvert was extended 20 additional feet to prevent relocation of power pole, pedestals, and hand hole that would have been in conflict with the required cut at the design location. Brightspeed (STA 588+00 RT) - There is an undergound fiber line and pedestal in conflict with the proposed grading, so the culvert pipe was extended by project staff to eliminate the conflict. - Brightspeed plans to be on site during culvert installation. They will have a generator power their cabinet across the road to continue service. If a cut over is necessary at that time, Brightspeed will complete the work during construction. Adams-Columbia Electric (STA 588+00 RT) - Very little cover over underground power line (~0.5 feet) - Back slope cut at the power pole will result in an additional 2.7 feet of the pole exposed - ACEC indicated they would be on site when grading and pipe work takes place at the location. They will hold and lower the pole and lower the underground wire. - Provided pole holding and lowering during culvert installation on May 1, 2023. Marquette Adams Telephone Cooperative STA 588+00 RT: - Locate flags indicate there is was close grading work to a line. - Mashuda will work on potential conflict. MATC will be on site during operations to assist if necessary. STA 588+00 LT: - Fiber line only 6-inches below the proposed ditch line. - Mashuda determined the communication line needed to be lowered. Marquette Adams Telephone was on site within 2 hours of being made aware of the conflict and the line was successfully lowered. - Completed on April 27, 2023. Culvert pipe at CTH Y installed on May 1 with no conflict.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 6 | 04/21/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground | [8 empty] | 04/07/2023 |  | No | No |  | Yes | [7 empty] | Yes | [12 empty] | STA 660+91, 38' LT Brightspeed - Pedestal is located within the proposed backslope - Brightspeed plans to move the pedestal out of the grading limits - Completed move on 4/21/23
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 7 | 04/21/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground | [8 empty] | 04/07/2023 | 04/21/2023 | No | No | [22 empty] | STA 412+00 RT Brightspeed - Mashuda noticed that the line was very shallow, only 6inches below subgrade - Brightspeed indicated that they would review the location and lower the line if necessary - Brightspeed indicated the location would not be lowered and informed Mashuda on 4/21/23 that if there was damage to the line, Brightspeed would take full responsibility and obligation to repair the line.
20221213030 | wisc 2023114, 123 | 6170-00-70 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 9 | 10/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Union Telephone Company | Communication Line | Underground |  | We Energies | Gas/Petroleum | Underground |  |  |  |  | 04/28/2023 | 06/09/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  |  |  |  | STA 239+00 LT UNION TELE: - Mashuda contacted Darrel Wessels and discussed moving a pedestal and wire in conflict with proposed grading. - Union removed pedestal - Mashuda and Union crossed off lines that had been marked but were abandoned. WE ENERGIES: -Duane with Mashuda contacted Matt Dumke (6-9-23) in regard to a gas marker that needed to be removed on the East side of CTH B because it is in the way of the shoulder. Matt said they will take a look and follow up with Duane.
20221213030 | wisc 2023114, 123 | 6170-00-74 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 1 | 10/26/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Union Telephone Company | Communication Line | Underground |  | Spectrum | Communication Line | Underground |  |  |  |  | 04/03/2023 | 04/26/2023 | No | No | [22 empty] | STA 219+00 - 239+00 LT/RT (STH 21 Hill Cut) Union Telephone - Underground line marked by locator. Cut over had been completed two weeks prior and line was abandoned. Spectrum - Live line within hill cut grading - Special Provisions indicated line was supposed to be moved to near right of way before construction began - Construction began on March 27, 2023 - Cut over is scheduled to occur on April 26, 2023 between 12am and 6am. - Mashuda confirmed cut over completed on April 27 with Spectrum and could resume work in that location. - On 4/27/23 Mashuda struck the newly installed communication line. The newly installed line was still within the proposed grading limits. - A temporary line was run above ground to re-establish service to the affected customers. Upon completion of contract work, 10/26/23 Spectrum still had to install a new line in the hill cut to replace the temporary laid on the ground. This will be completed now outside of the project contract work.
20221213030 | wisc 2023114, 123 | 6170-00-74 | Coloma - Wautoma; Madison Street To Sth 22 | NC | Waushara | STH 021 | Mike.Dombeck | GREMMER & ASSOCIATES, INC. | Michael.Caban | 8 | 05/11/2023 | 303 | PAVT REPLACEMENT | MASHUDA CONTRACTORS, INC. | Adams-Columbia Electric Cooperative | Communication Line | Underground | [8 empty] | 04/27/2023 | 05/11/2023 | No | No | [22 empty] | STA 227+00 - 231+00 LT - Mashuda discovered power line is within grading backslope cut. - Scheduled to move line on 5/10/23 - Move completed on 5/11/23 STA 239+00 LT - Conflict with an underground line and electrical box - Mashuda and ACEC met on site on 4/27, 5/2, and 5/4 to discuss solution - ACEC scheduled to move line and box on 5/10/23 - Move completed on 5/11/23
20221213031 | wisc 2023115 | 9040-03-71 | Rhinelander - Eagle River; Ush 8 To Stevens Street | NC | Oneida | STH 017 | Adam.Holquist | WISDOT | Michael.Caban | 1 | 07/18/2023 | 303 | PAVT REPLACEMENT | VAN ERT ELECTRIC COMPANY, INC. | Wisconsin Public Service Corporation | Electricity | [9 empty] | 04/11/2023 | 04/21/2023 | No | Yes | [12 empty] | WPS moved overhead neutral and 3-phase electric up to allow work within safe range (10-foot minimum, per OSHA regulations) for temporary traffic signal, temporary signal pole, and control wire and span wire installations in CTH P and STH 17 intersection. This was done by adding temporary pole in NE quadrant of CTH P and STH 17. Per SDD09G01-04b, a minimum height to the bottom of the temporary signal head is 17-feet, with the top of heads and span wire being approximately 20-feet in height. Project staff relocated (2) project work poles to better work with this overhead electric conflict (to allow better constructability for the contractor), but ultimately without WPS’s lifting of their transmission lines, OSHA 10-foot minimum clearances would not have been met. NSIGHT fiber Line was also lifted with this process by WPS (not required but better constructability for contractor). Note: this issue was discovered prior to start work notice being granted to contractor. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Other | Did not effect contract time |  | WPS moved overhead neutral and 3-phase electric up to allow work within safe range (10-foot minimum, per OSHA regulations) for temporary traffic signal, temporary signal pole, and control wire and span wire installations in CTH P and STH 17 intersection. This was done by adding temporary pole in NE quadrant of CTH P and STH 17. Per SDD09G01-04b, a minimum height to the bottom of the temporary signal head is 17-feet, with the top of heads and span wire being approximately 20-feet in height. Project staff relocated (2) project work poles to better work with this overhead electric conflict (to allow better constructability for the contractor), but ultimately without WPS’s lifting of their transmission lines, OSHA 10-foot minimum clearances would not have been met. NSIGHT fiber Line was also lifted with this process by WPS (not required but better constructability for contractor). Note: this issue was discovered prior to start work notice being granted to contractor.
20221213031 | wisc 2023115 | 9040-03-71 | Rhinelander - Eagle River; Ush 8 To Stevens Street | NC | Oneida | STH 017 | Adam.Holquist | WISDOT | Michael.Caban | 2 | 07/18/2023 | 303 | PAVT REPLACEMENT |  | Spectrum | [10 empty] | 06/06/2023 | 06/08/2023 | No | No |  | Yes | [9 empty] | Yes | Utility company excavated and lifted existing fiber vault to match proposed pedestrian sidewalk landing area on NW quadrant of STH 17 and Eisenhower. This vault is located in the 5-foot ADA landing area for concrete pedestrian ramp and was NOT show in the plan set. Crews set sidewalk forms to allow Spectrum to have grades for raising and then re-set forms after excavation/lifting was complete. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Other | Did not effect contract time
20230110004 | wisc 2023138 |  |  | SW |  | STH 073 | Rebecca.Frank | ONEIDA ENGINEERING SOLUTIONS, LLC (OES) |  | 1 |  | 303 |  | MCGUIRE INC | Alliant Energy | Gas/Petroleum | Underground | [8 empty] | 07/10/2023 |  | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 16 to 24 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay
20230110005 | wisc 2023139 | 5017-00-70 | V Of Norwalk - T Of Ridgeville; Moore Creek Bridge B-41-0319 | SW | Monroe | CTH U | Colin.Olson | WSP USA INC | Richard.Olson | 1 |  | 201 | BRIDGE REPLACEMENT, PRESERVATION | PHEIFER BROTHERS CONSTRUCTION CO., INC. | Norwalk Municipal Water Utility | Water | Underground | GERKE EXCAVATING INC | [7 empty] | 06/19/2023 | 06/29/2023 | No | Yes |  |  | Yes | [8 empty] | Yes | Utility was left in place. Substructure was adjusted to accommodate utility - Wing 1 was shortened with approval of the designer and BOS. | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  | Yes
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 1 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 04/24/2023 | 05/06/2023 | No | Yes | [5 empty] | AT&T representative Ryan Denewellis confirmed no anticipated conflicts during the design process. | [7 empty] | Contractor productivity rate was affected |  | 08 to 16 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 10 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/11/2023 | 06/02/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 11 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/09/2023 | 05/22/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 12 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/18/2023 | 05/25/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 13 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/19/2023 | 05/26/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 14 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 04/26/2023 | 07/27/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 15 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 04/26/2023 | 07/27/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 16 to 24 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 16 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/11/2023 | 05/22/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 17 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/23/2023 | 05/24/2023 | No | Yes | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 08 to 16 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 18 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/19/2023 | 05/16/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 08 to 16 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 19 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 06/05/2023 | 06/12/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 2 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/09/2023 | 05/11/2023 | No | Yes | [5 empty] | AT&T representative Ryan Denewellis confirmed no anticipated conflicts during the design process. | [7 empty] | Contractor productivity rate was affected |  | 08 to 16 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 20 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/24/2023 | 05/26/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 08 to 16 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 21 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 06/13/2023 | 06/21/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 22 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 06/08/2023 | 06/16/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 23 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 06/22/2023 | 06/23/2023 | No | Yes | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 08 to 16 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 24 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Alliant Energy | Gas/Petroleum | Underground | [8 empty] | 06/29/2023 | 06/30/2023 | No | Yes | [13 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 08 to 16 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 25 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 07/10/2023 | 07/10/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | 08 to 16 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 26 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | City of Janesville | Water | Underground | [8 empty] | 07/14/2023 | 07/14/2023 | No | Yes | [13 empty] | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  |  | City watermain was much higher than the plan anticipated. Solution was to raise the storm sewer run to get over the watermain beginning from the previous structure.
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 27 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | City of Janesville | Water | Underground | [8 empty] | 07/14/2023 | 07/18/2023 | No | Yes | [13 empty] | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay |  |  | Existing watermain was much lower than it was supposed to be based on plan elevations. Could not raise storm sewer because it would have conflicted with AT&T duct. Could not lower storm sewer because it would involve redesign of multiple inlets in the system to achieve positive drainage. Solution was to install a watermain offset to get storm sewer through. See CCO #6 for more details.
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 3 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 04/26/2023 | 05/06/2023 | No | Yes | [5 empty] | AT&T representative Ryan Denewellis confirmed no anticipated conflicts during the design process. | [7 empty] | Contractor productivity rate was affected |  | 08 to 16 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 4 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/26/2023 | 06/07/2023 | No | Yes | [5 empty] | AT&T representative Ryan Denewellis confirmed no anticipated conflicts during the design process. | [7 empty] | Contractor productivity rate was affected |  | 08 to 16 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 5 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Alliant Energy | Electricity | Underground | [8 empty] | 06/02/2023 | 06/02/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 08 to 16 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 6 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 06/05/2023 | 06/07/2023 |  | Yes | [5 empty] | AT&T representative Ryan Denewellis confirmed no anticipated conflicts during the design process. | [7 empty] | Contractor stopped work and demobilized from project |  | 08 to 16 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 7 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | Alliant Energy | Electricity | Underground | [8 empty] | 06/19/2023 | 06/19/2023 | No | Yes | [13 empty] | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 8 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground |  |  | Communication Line | [5 empty] | 05/08/2023 | 05/10/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110009 | wisc 2023143 | 5990-01-41 | C Of Janesville, East Milwaukee Str; Atwood Avenue To Main Street | SW | Rock | LOC STR | Colten.Tuescher | R.H. BATTERMAN & CO., INC. | Richard.Olson | 9 |  | 201 | RECONSTRUCTION, PRESERVATION | ROCK ROAD COMPANIES, INC. | AT&T | Communication Line | Underground | [8 empty] | 05/10/2023 | 06/07/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 04 to 08 hours |  | 16 to 24 hours |  | Excusable - Non-Compensable Delay
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 1 | 04/13/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | We Energies | Electricity | [9 empty] | 04/04/2023 | 04/13/2023 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Other | Contractor was able to mobilize to a different location within the general work area. Currently this has not caused a delay, but may depending on how long it takes to resolve. | Excusable - Compensable Delay |  | Yes | Unresolved Utility Issue. At STA ~ 607+00, 20’ LT the plan and cross section call for us to cut a new ditch (approximately 6’ deep cut) for the installation of the new Honey Creek Roadway alignment. At this location an existing utility pole and guy wire are currently at the new ditch line location. Dylan Gates notified of issue.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 10 | 07/14/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | Charter Communications | Communication Line | [9 empty] | 06/12/2023 | 07/14/2023 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  |  | Charter/Spectrum utility line in conflict with new Hwy O roadway alignment. Conflict was missed by Charter/Spectrum during design. Existing fiber line runs down an existing pole then to a box just south of the fire station driveway, west toward the fire station, then north toward the communication tower. The existing pole and box are both in conflict with the new roadway location. Charter/Spectrum redesigned to remove the pole and box and bore in a new line.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 11 | 08/16/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | We Energies | Electricity |  |  | AT&T | Communication Line | [5 empty] | 08/03/2023 | 08/16/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay |  |  | Existing guy wires for utility pole 22-12462 are located in an area of grade with a 3 foot cut. The guy wires are for AT&T and WE Electric on a WE pole. WE Electric confirmed that the pole was buried an extra 3 feet deep per their plan/permit but the guys were not buried to the extra depth.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 12 | 09/01/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | Charter Communications | Communication Line | [9 empty] | 08/10/2023 | 09/01/2023 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | Other | Contractor moved to new location, resumed work after conflict was resolved. | Excusable - Compensable Delay |  |  | Charter/Spectrum line on the NE corner of the Hwy L intersection was called to be lowered per the approved work plan. Deluca-Tobin contracted by Charter/Spectrum to complete work, however they claim that they never had a copy of the new work plan which showed the utility lowering in place. Deluca-Tobin mobilized their crew and lowered the line per the original work plan.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 2 | 05/19/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | We Energies | Electricity | [9 empty] | 04/24/2023 | 05/19/2023 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Electrical crossing at STA ~ 297+00, 21' LT was potholed. Contracted took GPS shot on electrical line and found it to be only 13" below proposed subgrade cut. WE Energies verified that the cable was installed too shallow per their requirements/clearances. WE to relocate the cable lower.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 3 | 05/31/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | We Energies | Electricity | [9 empty] | 05/03/2023 | 05/31/2023 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Excusable - Non-Compensable Delay |  |  | Electrical pole guy wire at STA 187+89 LT extended into the new roadway shoulder. Conflict was not identified in initial permit. WE Energies removed existing guy wire and installed a guy pole on the opposite side of the roadway.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 4 | 07/21/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | AT&T | Communication Line | [9 empty] | 05/30/2023 | 07/21/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | On Honey Creek Rd in the left ditch between STA 602+00 and ~ 603+50 there is an existing F.O. line that is not shown on our cross sections. The line is located at 23’ LT and is buried approximately 1 foot below the existing grade. A ditch is to be cut in this area so the line was lowered in place.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 5 | 06/19/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | We Energies | Electricity | [9 empty] | 05/25/2023 | 06/19/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor delayed start of work |  | 04 to 08 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | At new cross culvert STA 71+01 there is an electrical line that crosses the road at STA ~ 69+90 and then follows the ditch line to the north. The contractor potholed the location and found it at elevation 810.39. There is a new culvert at this location with a pipe invert of 809.80. I verified with the locators that this is a WE Electric line. WE Electric to relocate line before storm sewer work in this area begins.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 6 | 07/06/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | AT&T | Communication Line | [9 empty] | 05/30/2023 | 07/06/2023 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor delayed start of work |  | 04 to 08 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay |  |  | AT&T installed a Guy wire off of a WE Energies Electric Pole at STA 252+89, 49' RT. The pole is behind the back of the curb but the guy wire is within the proposed roadway location. AT&T did not show this guy wire on their proposed work plan. AT&T to redesign/relocate guy to remove from roadway. AT&T removed existing guy wire and reinstalled on a pole approximately 100 feet north.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 7 | 08/11/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | We Energies | Electricity | [9 empty] | 05/31/2023 | 08/11/2023 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  |  |  | Excusable - Non-Compensable Delay |  |  | At STA 240+67 RT utility pole guy wire is in conflict with the new roadway cross section shoulder. WE Electric to redesign to relocate guy out of roadway shoulder point. They also mobilized to "hold" poles during Marsh Excavation as they were not installed to extra depth in order to incorporate adjacent Marsh Excavation.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 8 | 07/27/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | TDS Telecom | Communication Line | [9 empty] | 06/01/2023 | 07/27/2023 | No | Yes |  |  |  |  | Yes | Marsh Excavation was added late in design and the designer did not notify the utility companies of the change. Existing utility in marsh excavation cut. |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  |  | Contractor mobilized to site immediately and spliced in a "house line" to bypass the marsh excavation area. Then, once marsh excavation was complete, they coordinated with Musson to install a new buried line in the subgrade.
20230110012 | wisc 2023146 | 1300-09-70 | Northwest Highway (Sth 83); Sth 20 To Ih 43 | SE | Racine | STH 083 | Matthew.Helland | COLLINS ENGINEERS, INC. | Michael.Birschbach | 9 | 07/14/2023 | 303 | SHORT TERM OVERLAY (MILL AND OVERLAY) | MUSSON BROS., INC. | AT&T | Communication Line | [9 empty] | 06/01/2023 | 07/14/2023 | No | Yes |  |  |  |  | Yes | Marsh Excavation was added late in design and the designer did not notify the utility companies of the change. Existing utility in marsh excavation cut. |  |  |  | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay |  |  | AT&T plans to relocate existing fiber line on WE Electric overhead lines. Lines relocated the week of 7/3 and splicing completed on 7/14.
20230110015 | wisc 2023148 | 3325-06-71 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | JW SCHULTZ CONSTRUCTION CO, INC | We Energies | Gas/Petroleum | Underground | [8 empty] | 05/05/2023 | 05/10/2023 | No | Yes |  |  |  |  | Yes | Tracer Wire Post was in the sidewalk footprint and needed to be moved |  |  |  | Yes |  |  |  | Other | In the way of Sidewalk, not at the point of pouring sidewalk at this location so no delay to schedule. | Less than 01 hour |  | Less than 01 hour |  | Other | No Impact
20230110015 | wisc 2023148 | 3325-06-71 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | JW SCHULTZ CONSTRUCTION CO, INC | Alliant Energy | Electricity | Underground | [8 empty] | 05/18/2023 | 05/30/2023 | No | Yes |  |  |  |  | Yes | Hand pullbox was in the sidewalk footprint and needed to be moved |  |  |  | Yes |  |  |  | Other | Handbox was in the way of Sidewalk, Forced contractor to return at a later date. | Other |  | 08 to 16 hours |  | Other | 6.Multiple day delay 8. No Impact
20230110015 | wisc 2023148 | 3325-06-71 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | OUTDOOR LIGHTING CONST CO INC | Alliant Energy | Electricity | Underground | [8 empty] | 06/05/2023 | 06/05/2023 | No | Yes | [7 empty] | Yes | [5 empty] | Other | RRFB base was adjusted to avoid utilities on the East side of the roadway. | Less than 01 hour |  | Less than 01 hour |  | Other | no impact
20230110015 | wisc 2023148 | 3325-06-72 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | ROCK ROAD COMPANIES, INC. | Williams Bay Municipal Water Utility | Water | Underground | [8 empty] | 04/17/2023 | 04/17/2023 | No | Yes |  |  |  |  | Yes | Watermain Break | [5 empty] | Yes | Used Village supplied patch/repair bracket. | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | 01 to 04 hours |  | Excusable - Compensable Delay
20230110015 | wisc 2023148 | 3325-06-72 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | ROCK ROAD COMPANIES, INC. | Williams Bay Municipal Water Utility | Water | Underground | [8 empty] | 04/12/2023 | 04/13/2023 | No | Yes |  |  |  |  | Yes | Watermain Break | [5 empty] | Yes | Used Village supplied patch/repair bracket. | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | 01 to 04 hours |  | Excusable - Compensable Delay
20230110015 | wisc 2023148 | 3325-06-72 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | ROCK ROAD COMPANIES, INC. | Williams Bay Municipal Water Utility | Water | Underground | [8 empty] | 04/07/2023 | 04/07/2023 | No | Yes |  |  |  |  | Yes | Watermain Break | [5 empty] | Yes | Used Village supplied patch/repair bracket. | Contractor stopped work until utility delay was resolved |  | 04 to 08 hours |  | 04 to 08 hours |  | Excusable - Compensable Delay
20230110015 | wisc 2023148 | 3325-06-72 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | ROCK ROAD COMPANIES, INC. | Williams Bay Municipal Water Utility | Water | Underground | [8 empty] | 03/24/2023 | 03/24/2023 | No | Yes |  |  |  |  | Yes | Watermain Break | [5 empty] | Yes | Used Village supplied patch/repair bracket. | Contractor stopped work until utility delay was resolved |  | 04 to 08 hours |  | 04 to 08 hours |  | Excusable - Compensable Delay
20230110015 | wisc 2023148 | 3325-06-72 | Walworth - Elkhorn; Geneva St To Glenwood Dr | SE | Walworth | STH 067 | Jacob.Olp | WISDOT | Michael.Birschbach | 1 | 06/16/2023 | 303 | RESURF (OVERLAY >= 4 IN) | ROCK ROAD COMPANIES, INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 04/13/2023 | 04/13/2023 | No | Yes |  |  |  |  | Yes | Gas Line Break | [5 empty] | Yes | WE Energies came on site and repaired the damaged pipe. | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | 01 to 04 hours |  | Excusable - Compensable Delay
20230110017 | wisc 2023150 | 3755-02-70 | Cth D; Heritage Rd To 753 Ft W Of State St | SE | Racine | CTH D | Justin.Niemec | JNI ENGINEERING, LLC | Michael.Birschbach | 1 | 06/05/2023 | 201 | RECONSTRUCTION, PRESERVATION |  | TDS Metrocom LLC | Communication Line | Underground | [8 empty] | 03/20/2023 | 05/15/2023 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Contractor delayed start of work |  | Other | 200 + plus hours monitoring Utility Relocation that were scheduled to be complete prior to construction | Other | Delayed Start of Construction by 7 weeks. | Excusable - Compensable Delay |  |  | C.) TDS – a. TDS has relocated fiber in Stage 1 as of May 15th, Copper splicing will continue during the week of May 15th. They are scheduled to stay ahead of all construction operations. b. Relocations in stage 2 will be complete prior to construction starting on Phase 2. The Department understands this is a excusable compensable delay per specification 108.10.3.5 non-completion of utilities. Based on a planned start of April 3rd, 2023 and significant delays to the start of grading the department will be extending the project completion date to October 29th, 2023.
20230110019 | wisc 2023152 | 4323-08-72 | Maple Grove - North County Line; Taus Road To Mancal Road | NE | Manitowoc | CTH W | Tyler.Owens | I & S GROUP, INC. | Garrett.Vickman | 1 | 10/06/2023 | 201 | PAVT REPLACEMENT | GORDON J. GRUBE CONSTR. CO., INC. | Spectrum | Communication Line | Underground | [8 empty] | 07/21/2023 | 07/21/2023 | No | No | [5 empty] | Utility was relocated for the final/end condition, but spacial needs during construction were not accounted for when determining the new location of the utility. | Yes | [6 empty] | Other | Contractor had restricted space and tight working conditions leading to restraints with various work items. | Less than 01 hour |  | Less than 01 hour |  | Other | No impact to project timeline.
20230110019 | wisc 2023152 | 4323-08-72 | Maple Grove - North County Line; Taus Road To Mancal Road | NE | Manitowoc | CTH W | Tyler.Owens | I & S GROUP, INC. | Garrett.Vickman | 2 | 10/06/2023 | 201 | PAVT REPLACEMENT |  | Wisconsin Public Service Corporation | Electricity | Overhead | [8 empty] | 08/31/2023 | 08/31/2023 | No | No | [5 empty] | Truck driver hit overhead line with bucket raised. Lines were clearly visible and identified with traffic cones by Northeast Asphalt prior to beginning the paving operation. | [6 empty] | As a result of being hit, the overhead line snapped. The paving operation was haulted while the crew investigated the problem and notified the proper contacts. The line was determined to be a ground and not hazardous to the continuation of work or the safety of individuals in the area, so the crew then resumed the operation. Wisconsin Public Service arrived on site later in the day to repair the line. | Contractor productivity rate was affected |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay
20230110023 | wisc 2023160, 161 | 6230-14-71 | Shiocton - Seymour; Park Avenue - French Road | NE | Outagamie | STH 054 | Brian.Heiden | WISDOT | Garrett.Vickman | 1 | 06/26/2023 | 303 | RESURF (OVERLAY >= 4 IN) | RELYCO PLUS, LLC | Spectrum | Communication Line | Underground | [8 empty] | 06/06/2023 | 06/09/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Other | No direct impact to contract time or cost. Contractor had work elsewhere that they planned to go to prior to exposing utility conflict. |  | 6/6/2023 - Relyco Plus was working on the culvert replacement at STA 835+75 and came across the existing underground fiber optic line running parallel to the roadway along the south shoulder of WIS 54. This line was in direct conflict with the proposed culvert pipe. Brian Heiden (project leader) checked with the design utility coordinator to see if this facility was included in the DT1078 plan that was sent to the utilities. I received word that the utilities were indeed made aware of the proposed culvert invert 2 feet lower than the existing and it was Spectrum's responsibility to include what work was needed in their work plan to get their facility out of the way. 6/7/2023 - Relyco Plus went to work on a different job for the day. They had planned on this prior to the finding of the facility in conflict. Bill Parmeter (Spectrum) was notified by Shane Peters (Relyco) and Bill has TAK set up to for early the next day to begin working to bypass this line. 6/8/2023 - Relyco Plus not onsite today. TAK/Spectrum onsite to work on installing bypass fiber lines to abandon the in conflict line. 6/9/2023 - Project staff were notified around noon today that TAK finished the bypass/abandonment of the in conflict facility. 6/12/2023 - Relyco Plus was back onsite Monday to continue culvert replacement work at this location as the facility is no longer operational.
20230110023 | wisc 2023160, 161 | 6230-14-71 | Shiocton - Seymour; Park Avenue - French Road | NE | Outagamie | STH 054 | Brian.Heiden | WISDOT | Garrett.Vickman | 2 | 06/26/2023 | 303 | RESURF (OVERLAY >= 4 IN) | RELYCO PLUS, LLC | Spectrum | Communication Line | Underground | [8 empty] | 05/30/2023 | 05/30/2023 | No | No |  |  |  |  | Yes | Contractor stated facility did not have any locate marks identifying it was there. |  |  |  | Yes |  |  |  | Other | Contractor continued work at this location and worked around facility. | Less than 01 hour |  | Less than 01 hour |  | Other | No impact to contract time or cost. |  | At approximately 2:00 pm, Relyco Plus hit an unmarked utility at STA 582+82 RT that ended up being a Spectrum Fiber line. Crew backhoe ripped right thru the line. Spectrum on site at approximately 5:15 pm to begin repair and splice the line back together. Project staff heard the splice was completed and facility back operational at about 8-9pm later that night.
20230110023 | wisc 2023160, 161 | 6230-14-71 | Shiocton - Seymour; Park Avenue - French Road | NE | Outagamie | STH 054 | Brian.Heiden | WISDOT | Garrett.Vickman | 3 | 08/08/2023 | 303 | RESURF (OVERLAY >= 4 IN) | RELYCO PLUS, LLC | Spectrum | Communication Line | Underground | [8 empty] | 05/10/2023 | 06/14/2023 | No | No |  |  |  |  | Yes | Utility did not complete their work by the deadline stated in the work plan. | Yes | [6 empty] | Other |  | 08 to 16 hours |  | 01 to 04 hours |  | Other | No impact to contract time and cost, but it did cause project staff to constantly check back up and push Spectrum to get workers to site and continue their work. |  | Week of 5/10/2023: Bill Parmenter (Spectrum) stated their crews have 2 borings and associated splices west of STA 720+00 to make prior to contract culvert work. Week of 5/17/2023: Bill Parmenter (Spectrum) stated their contractor (TAK Communications) is trying to complete the remaining bores in the wet areas along WIS 54 this week. Week of 5/24/2023: Spectrum gave project staff James Brown (TAK) phone number and stated how wet it was. Adam Gaugh explained to Bill that we are going to be installing pipes that may be in conflict during the week of 5/29/23. Spectrum said their contractor is still trying to complete the remaining bores along WIS 54. The switch over to new fiber line is scheduled for the night of Friday June 2. Adam Gaugh has been in contact with Bill Parameter (Spectrum) and they are aware this work is now leaking into holding up Relyco’s culvert replacement operation. Adam said he is working with Relyco and they are thinking maybe they can get in and work around the existing fiber line. Adam Gaugh called James Brown from TAK on the following days – During the week of 5/22/23 – He stated that they would finish up their conduit during the week of 5/22/23 and Spectrum had a scheduled outing on Friday 6/2/23 to complete the cross over. Week of 5/31/2023: Spectrum said their contractor is still trying to complete the remaining bores along WIS 54. Adam Gaugh called James Brown from TAK on the following days - 5/31/2023 – Stated he couldn’t get his sub to call him back. 6/1/2023 – Stated sub would be on site to install fiber in conduit on 6/4/2023. Brian Heiden reached out to Becky Reese (Utility Coordination Engineer) to see if she has the ability to somehow get the contractor onsite to get their work completed. On 6/1/2023, at 4:40 pm, Becky sent out a Trans 220 Violation Letter to Spectrum's representative Bill Parmenter as the approved work plan stated they would have work completed by mid-April and it is now June. This letter is stored in project records. Week of 6/7/2023: According to Bill Parmenter, as of 6/6 Spectrum’s subcontractor is going to be completed with fiber pulling by the end of the day on 6/7. Will then make the splices end of this week and an emergency test and transfer over to new facility week of 6/12. Week of 6/14/2023: According to Bill Parmenter, Spectrum has completed fiber install and splices along WIS 54. Facility is switched to new lines.
20230214005 | n/a | 3575-02-73 | C Fort Atkinson, Whitewater Avenue; Madison Avenue To Cth M | SW | Jefferson | USH 012 | Tammy.Buss | WISDOT | Richard.Olson | 1 |  | 303 | RESURF(OVLAY>= 2.5 IN AND < 4 IN) | JW SCHULTZ CONSTRUCTION CO, INC | City of Fort Atkinson | Electricity | Underground | [8 empty] | 07/18/2023 | 07/19/2023 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor productivity rate was affected |  | 04 to 08 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay |  |  | Existing traffic signal conduit was detoriating. In addition to this the conduit was placed just below the existing brick pavement allowing for no cover during removals. To provide adequate room for the stone and lowered sidewalk, the cables also needed to be lowered.
20230214006 | wisc 2023220 |  |  | SW |  | STH 023 | Jamie.Brandt | TEAM ENGINEERING, INC. |  | 1 | 06/23/2023 |  |  | A-1 EXCAVATING LLC | Alliant Energy | Electricity |  |  | Spectrum | Communication Line | [5 empty] | 06/08/2023 | 06/22/2023 |  | Yes | [5 empty] | Alliant is not able to move poles on STH 23 but due to conflicts with Spectrum needing power at 12+00 (SW quadrant) until new cabinet placed at 110+00 Rt. Poles can’t be removed or transferred. | [7 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | Other | A-1 worked around Spectrums cable until relocations were completed. | Other |  |  | Special Provisions state Spectrums work will take 50 working days after Alliant completes underground duct work on Parcel 5, after Parcel 5 contract work is completed. Work on Parcel 5 was completed 5/17/23, so 17working days have passed. Frontier relocations will take 30working days and will start after the contract work on Parcel 5 is completed.
20230214022 | wisc 2023227 | 2722-07-72 | C New Berlin Moorland Road; W Beloit Road To W National Ave | SE | Waukesha | CTH O | Chaz.Krueger | LAKESIDE ENGINEERS, LLC | Michael.Birschbach | 1 |  | 201 | PAVT REPLACEMENT | A.W. OAKES & SON, INC. | We Energies | Gas/Petroleum | Underground | [8 empty] | 07/06/2023 | 07/07/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | 04 to 08 hours |  | Non-Excusable Non-Compensable Delay |  |  | Shallow gas main crossing CTH O identified at STA 82+50 during roadway excavation on 7/6/23 at 3 pm. WE-Gas contractor NPL already on site completing relocation work along National Avenue. WE-Gas directs NPL to lower the the approximately 8 ft of main in conflict with roadway excavation to resolve the conflict. NPL completes the lowering by the end of shift on 7/7/23.
20230214025 | n/a | 3700-11-70 | Signal Install & Signal Replacement; Various Signalized Intersections | SE | Kenosha | VAR HWY | Kyle.Reinke | WISDOT | Michael.Birschbach | 1 | 08/16/2023 | 303 | STH - TRAFFIC OPS-TRAFFIC SIGNALS | HIGHWAY LIGHT & LANDSCAPE, INC. | Midwest Fiber Networks LLC | Communication Line | Underground |  | Charter Communications | Communication Line | Underground |  | We Energies | Gas/Petroleum | Underground | 08/01/2023 | 08/02/2023 | No | No | [12 empty] | Department resolution Issue: In the weekly meeting Highway brought up a utility conflict for the special two 3” conduit at 165/H on the East side see PDF. I ask Pete if we could just keep the existing one 3” conduit run because there is multiple utilities crossing North and south. I looked at moving the bore run to the East but then there is an old gas line and then a new gas line and then a storm sewer run. Pete said this option would be OK as long as Highway can route the signal cables, half way each way from the cabinet then the cables in that crossing would be minimal. 165/H Boring conflict with utilities at bore run PB7-PB10-PB11 Solution: We are going to use the existing one 3” conduit an eliminate this special bore run as there is no good way to bore in this location with all of the utilities: Pete the head electrician said this option would be OK as long as Highway can route the signal cables, half way each way from the cabinet then the cables in that crossing would be minimal. Multiple Fiber lines in the way no way to tell exact companies they are listed as estimate . | Other | None | Other | Department took a day to issue a formal response to contractor . | Other | Caught during temporary signal placement and did not affect contract work. | Other | None
20230214025 | n/a | 3700-11-70 | Signal Install & Signal Replacement; Various Signalized Intersections | SE | Kenosha | VAR HWY | Kyle.Reinke | WISDOT | Michael.Birschbach | 2 |  | 303 | STH - TRAFFIC OPS-TRAFFIC SIGNALS | HIGHWAY LIGHT & LANDSCAPE, INC. | We Energies | Other | Underground |  | We Energies | Gas/Petroleum | Underground |  | Spectrum | Communication Line | Overhead | 08/08/2023 | 08/29/2023 | No | Yes | [5 empty] | SB 12 165/H: Light Pole: It was determined that SB12 conflicts with an old inactive gas line, WE Power Street lightning, and a fiber optic line. Department is verifying with utilities unit to determine the status of old gas line. Denise (WisDOT Utility Coordinator) sent a response. The response included a email chain regarding light pole. Southeast corner SB12, is close to existing light, should be ok if pole is supported during excavation. If too close we can shift the pole as well. The work plan for new gas line includes statement confirming gas line was in the way of SB12. Project engineer discussed moving the light pole With James Nelson. Planned on moving Tuesday 8/14 if crew lined up but due to Monday's rain event there were no crews available and was told later in the week pole would be removed. The pole was removed in the afternoon and taken off site by We Electric on (8/17). More issues occurred today see Highway Light at 165 comments on 8/23. Highway Light & Landscape: began placing SB 12 form and ran into more issues with the finding an additional wiring for removed light pole with no locates marked. While the department staff contacted WE Energies (WE Electric) James Nelson multiple times to no response, then tried WE Electric utilities coordinator sent to voicemail, then gave Mike Birschbach (WisDOT Utilities Supervisor) a call he got a hold of someone and said the best way to deal with it was to call the emergency hotline. (10-11 am) Project Engineer called the emergency hotline was talked to multiple people finally got sent to John Anderson he was able to get an answer after that they can move the lines. and put back. 11 am called John Anderson back to see if they could send someone out on site to verify if the new line found was discontinued and deenergized. The WE Electric employee arrived and verified the new found line was discontinued and Highway could remove the other line temporarily. So drilling began around lunch time after the After the pole line was dug out. It was going smoothly until the 8-10 feet deep mark and then a mysterious object and keep digging to no movement and the next option is the place the base on old gas line. Gas Line We Gas returned call and scheduled gas line for Thursday if locates occurs. Tuesday WE gas rep Chris Degraves called and complained about moving the gas line. He was complaining that the discontinued gas line should be responsibility of Highway light for removal and wanted highway to excavate. Region Utility Supervisor was brought in the loop and told that We energies was responsible for gas line. We energies clarified there issues is they want Highway to excavate and then they would cut the gas line. They confirmed locate occurred and removals was 8/17 to 11 am. The crew showed up on site and potholed the gas line to verify the depth of 6'. The gas company could not place a trench box to remove said gas line due to Street Lighting. Further conversation occurred between WisDOT Utilities and WE Energies Gas. It was determined that 6' is below the 5' 3" form depth and with Highway Light approval to leave has line in place as long as We Energies Gas has a rep on site during drilling. Reached out to Chris Degraves at WE Gas and began the process of scheduling removing discontinued gas line for which was confirmed for Friday 8/25. The gas line was removed | [6 empty] | The gas line was cut out of the way , While the light pole was removed and taken off site. Old street light wire was removed and the new street lighting was set to the side to avoid damage | Contractor stopped work at current location and moved to another location |  | Other | Need to see the light pole if was movable. | Other | Took Multiple weeks to resolve. Time was extended on interim completion date. | Excusable - Compensable Delay
20230214025 | n/a | 3700-11-70 | Signal Install & Signal Replacement; Various Signalized Intersections | SE | Kenosha | VAR HWY | Kyle.Reinke | WISDOT | Michael.Birschbach | 3 |  | 303 | STH - TRAFFIC OPS-TRAFFIC SIGNALS | HIGHWAY LIGHT & LANDSCAPE, INC. | AT&T Wisconsin | Communication Line | Underground |  | We Energies | Gas/Petroleum | Underground |  |  |  |  | 08/10/2023 | 08/28/2023 | No | Yes | [5 empty] | SB 10 Utility Line open the AT&T Fiber Optic Line had issues of not finding the wire but found a pipe. Also waited for a refresh on locates at the for SB 10 and talked with the high pressure gas line guy on spacing. Between the department and Highway Light and Landscaping | [7 empty] | Other | Contractor waited to call the High Pressure Gas Contact and delayed there work on this SB11 | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | The location of SB 10 was shifted towards the intersection and South based on the Location AT&T lines . IF the plan would had better location for the high pressure gas the Monotube arm would of been shorter.
20230214025 | n/a | 3700-11-70 | Signal Install & Signal Replacement; Various Signalized Intersections | SE | Kenosha | VAR HWY | Kyle.Reinke | WISDOT | Michael.Birschbach | 4 |  | 303 | STH - TRAFFIC OPS-TRAFFIC SIGNALS | HIGHWAY LIGHT & LANDSCAPE, INC. | Wisconsin Department of Transportation | Other | Overhead | [8 empty] | 08/07/2023 | 08/17/2023 | No | No | [13 empty] | Contractor productivity rate was affected |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | : Street lighting conduit is affecting the SB 13 monotube location. The monotube will be shifted north to avoid the conduit.
20230214026 | wisc 2023230 | 3831-07-72 | C Kenosha Washington Road; Intersection With 39th Ave | SE | Kenosha | LOC STR | Zach.Pilichowski | HNTB | Michael.Birschbach | 1 | 10/27/2023 | 201 | MISCELLANEOUS |  | Kenosha Water Utility | Water | Underground | [8 empty] | 06/01/2023 | 07/17/2023 | No | Yes | [5 empty] | The Kenosha Water Utility (KWU) was perofrming work at the intersection and the work was not completed as scheduled. The work was not identifed in the special provisions. | [6 empty] | The KWU work was scheduled to be completed prior to the start of construction. Work began on the temporary signals starting on 6/12/23 and traffic control was installed. On 6/22/23 the Contractor was ready to make the switch from the existing signals to the temporary signals. This work was not able to be completed due to the KWU still performing work at the intersection. Work was delayed until the water utility was clear on 7/17/23. | Contractor stopped work until utility delay was resolved | [5 empty] | Excusable - Non-Compensable Delay |  |  | Due to the Kenosha Water Utility (KWU) watermain relay project at Washington Road and 39th Avenue not being completed as scheduled, the following Change Orders were executed: Change Order #02: Time extension for Kenosha Water Utility conflict - No Cost Change Order #03: Expedited work schedule to accelerate Stage One completion.- $15,700.00 Change Order #07: Remove Outside EB Lane Closure.- $667.00 Total Cost of the executed change orders due to the KWU work delaying the project: $16,367.00
20230214026 | wisc 2023230 | 3831-07-72 | C Kenosha Washington Road; Intersection With 39th Ave | SE | Kenosha | LOC STR | Zach.Pilichowski | HNTB | Michael.Birschbach | 2 | 10/27/2023 | 201 | MISCELLANEOUS | D K CONTRACTORS, INC | Kenosha Water Utility | Water | Underground | [8 empty] | 07/25/2023 | 07/25/2023 | No | Yes | [5 empty] | The Kenosha Water Utility (KWU) performed work in the intersection of Washington Rd and 39th Avenue prior to the beginning of the project start. KWU installed a water lateral at approximate STA 103+75. This water lateral was installed at an elevation that conflicts with the storm sewer pipe between Inlet 4 and Inlet 7. The water lateral will need to be lowered to install the storm sewer. | [6 empty] | Ian Bagley from Kenosha Water Utility gave his approval to have the storm sewer contractor (DK Contractor’s) excavate around the line to provide enough slack to lower the lateral below the storm sewer. This will result in 4” of separation between the lateral and the storm sewer, with insulation in-between. This work was done by the contractor under Force Account. | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  |  | The following change order was executed due to this conflict. Change Order #10: Kenosha Water Utility Conflict with Storm Sewer - $4,703.70.
20230214026 | wisc 2023230 | 3831-07-72 | C Kenosha Washington Road; Intersection With 39th Ave | SE | Kenosha | LOC STR | Zach.Pilichowski | HNTB | Michael.Birschbach | 3 |  | 201 | MISCELLANEOUS | D K CONTRACTORS, INC | AT&T | Communication Line | Underground | [8 empty] | 07/25/2023 | 08/03/2023 | No | Yes | [5 empty] | During storm sewer installation the contractor exposed a utility line. The line is an AT&T Wisconsin communications line that conflicts with Inlet 4 and the pipe run from Inlet 3 to Inlet 4. Dale Kannegiesser (AT&T Contractor) stated that because the line is copper and not a fiber line, they will need to excavate 10-feet on either side of the trench for every 1-foot of lateral distance the line needs to be relocated. The line will need to be moved approx. 3-feet to the west to not conflict with Inlet 4. This will require removing 12' of the adjacent pavement in the WB inside lane. It will take AT&T Wisconsin 2-3 days to relocate the line after the pavement has been removed. | [7 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | The ultility line was potholed by the contractor to determine the extent of the conflict. To expedite the completion of the relocate the project’s contractor will sawcut and remove the pavement that is needed to make the relocate. The AT&T contractor relocated the utility. The contractor did not give the utility and the project engineer the required 14 calendar day notice that the site was ready for the utility relocate. The following change order was executed due to the utility conflict. Change Order #11: AT&T Utility Conflict with Storm Sewer. Cost- $1,133.74
20230214031 | wisc 2023242 | 4685-29-60 | Appleton, Sth 441; Ush 10-North Junction Ih 41 | NE | Outagamie | STH 441 | Evan.Tursky | GRAEF (MILW) | Garrett.Vickman | 1 | 11/20/2023 | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | VINTON CONSTRUCTION COMPANY | We Energies | Gas/Petroleum | Underground | TNT PROFESSIONAL LAND SURVEYORS, INC. |  |  |  | HIGHWAY LANDSCAPERS, INC. |  |  |  | 08/03/2023 | 08/09/2023 | No | No | [13 empty] | Contractor delayed start of work |  | 04 to 08 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Upon completion of the utility locates, it was determined that the proposed Sign Structure S-44-309 @ STA 562+06 NB RT along the STH 441 NB auxiliary lane to the CTH OO off-ramp will be in conflict with a WE Energies high-pressure gas main that runs East-West below STH 441 at ~STA 562+15 +/-. It was determined that the proposed northern-most drilled shaft foundation will be directly in conflict or in close proximity to the utility as located. A representative from We Energies was on site and stated that the approximate depth of the gas main at this location is ~12 to 16-FT. He also mentioned that the structure should be relocated to a minimum of 25-FT away in order to provide a safe horizontal clearance between the structure and the utility. Project staff submitted RFI006 to the designer regarding this utility conflict - in response Strand stated that when the utility survey was completed at this particular location that there was unfortunately not a gas main located here. Ultimately, it was determined by the department that Sign Structure S-44-309 will be moved 37-FT to the North in order to gain the 25-FT clearance in between as requested by WE Energies - See Revised Plan Sheet 360 showing the updated location. Also note that the MGS guardrail will need to be extended 37-FT to the North to account for the new location along with revised gravel and paved shoulders respectively.
20230214031 | wisc 2023242 | 4685-29-60 | Appleton, Sth 441; Ush 10-North Junction Ih 41 | NE | Outagamie | STH 441 | Evan.Tursky | GRAEF (MILW) | Garrett.Vickman | 2 | 01/10/2024 | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | VINTON CONSTRUCTION COMPANY | Wisconsin Department of Transportation | Electricity | Other | LUNDA CONSTRUCTION COMPANY |  |  |  | BODART ELECTRIC SERVICE, INC. |  |  |  | 08/24/2023 | 09/13/2023 | No | Yes | [12 empty] | Utility was disconnected to complete structure joint replacement then reconnected | Contractor stopped work at current location and moved to another location |  | 16 to 24 hours |  | 08 to 16 hours |  | Excusable - Compensable Delay |  |  | It was determined that the conduit/wiring for the WisDOT Navigational Lighting for the existing structure B-44-126 on STH 441 over the Fox River was located within the median concrete parapet wall (running North-South) on the northbound side. The existing navigational lighting which was NOT originally addressed per plan was in conflict with the proposed structure B-44-126 modular expansion joint replacements at both Hinge #1 (STA 554+96 NB) and Hinge #2 (STA 559+22 NB). A navigational lighting repair (disconnect and reconnect) was necessary to be completed in conjunction with the proposed modular expansion joint replacement work in order to minimize additional costs and/or schedule delays related to the additional work. A large amount of utility coordination was required between project staff and various representatives from the WisDOT NER Electric Unit, U.S. Coast Guard and the prime contractor/subcontractor to acceptably complete the repair as directed.
20230214031 | wisc 2023242 | 4685-29-60 | Appleton, Sth 441; Ush 10-North Junction Ih 41 | NE | Outagamie | STH 441 | Evan.Tursky | GRAEF (MILW) | Garrett.Vickman | 3 | 01/10/2024 | 303 | PATCH/RUT FILL/REPAIR & GRIND/SLAB REPLC | VINTON CONSTRUCTION COMPANY | We Energies | Electricity | Underground | BODART ELECTRIC SERVICE, INC. | [7 empty] | 07/05/2023 | 07/05/2023 | No | No | [12 empty] | Utility was initially damaged then repaired by contractor | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Bodart Electric hit and damaged the existing street lighting conduit/wiring at STA 87+79 EB, 17' LT on CTH CE EB (College Avenue) while plowing in the proposed 1" conduit rigid nonmetallic schedule 40 between proposed pull box 3 and pull box 2 to connect the previously installed loop detectors 61 and 62 respectively. It was determined that the street lighting was fed by WE Energies and maintained by the City of Appleton Public Works. Project staff made note that the existing utilities were originally located prior to the start of construction but the markings had not been refreshed now that grading work had begun. According to representatives from Bodart Electric they had a Diggers Hotline Ticket Number that supposedly cleared 6/29/2023. No further investigation took place as Bodart Electric repaired the conduit/wiring themselves then notified the City of Appleton to verify that it was acceptably repaired.
20230214032 | wisc 2023233 | 4987-02-78 | C Green Bay, Chantel Street; Beaver Dam Creek Bridge | NE | Brown | LOC STR | Keith.Nikolay | COLEMAN ENGINEERING COMPANY-IRNMTN | Garrett.Vickman | 1 |  | 201 | BRIDGE REPLACEMENT, PRESERVATION | PHEIFER BROTHERS CONSTRUCTION CO., INC. | Brown County Technology Services | Communication Line | Underground | [8 empty] | 06/13/2023 | 06/21/2023 | No | Yes |  |  | Yes | [6 empty] | Yes |  |  |  | Other | No impact to project schedule. | 04 to 08 hours |  | Less than 01 hour |  | Other |  |  | The existing utility was located under the bridge west wingwalls, which were scheduled to be removed. It was unknown how far below the wingwalls the utility was located and there was some concern this utility could be compromised when the wingwalls were removed. When the contractor was ready to remove the west wingwalls, it was discovered there was no footing and the precast wingwall panels were just sitting on top of the existing ground. The contractor did not need to excavate to remove the west wingwalls so ultimately, there was no conflict.
20230214036 | n/a | 6370-01-77 | Sth 13 - Stratford; Sth 13 To Stainless Avenue | NC | Marathon | STH 153 | Dave.Katzner | MSA PROFESSIONAL SERVICES, INC. | Michael.Caban | 1 | 05/09/2023 | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | Frontier Communications | Communication Line | [9 empty] | 04/03/2023 | 05/09/2023 | No | No |  | Yes | [7 empty] | Yes |  |  |  | Contractor productivity rate was affected |  | 01 to 04 hours |  | 04 to 08 hours |  |  |  |  | Engineer discussed probable conflict with Utility on 4/3/23. Contractor confirmed utility is in conflict 5/1/23. There was some confusion by the contractor whether they could work around the existing line and on 5/2/23 the contractor confirmed the line will need to be adjusted in order for plan work to be performed. Utility on site 5/8/23 to review adjusting line so contractor could complete work. Utility crew left with out making adjustment. 5/9/23 Utility crew on site set 2 new handholes. Handholes were placed out side work area and temporary line installed laid above ground south of work area. At 3PM the existing line was able to be removed and contractor began work on south endwall. Engineer estimated the contractor lost 2 days since they were unable to work on the south side during slow periods of working on the north endwall.
20230214040 | n/a | 9303-03-72 | Upson - Montreal River; West Mill Street To Mi State Line | NC | Iron | STH 122 | Garth.Stengard | COLEMAN ENGINEERING COMPANY-IRNMTN | Michael.Caban | 1 | 08/08/2023 | 303 | PAVT REPLACEMENT | JAMES PETERSON SONS, INC. | Brightspeed of Wisconsin, LLC | Communication Line | Underground | [8 empty] | 08/08/2023 | 08/08/2023 | Yes | No | [13 empty] | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay
20230214046 | wisc 2023256 |  |  | NW |  | LOC STR | Isaac.Hiner | KRECH OJARD AND ASSOCIATES |  | 1 | 08/04/2023 | 201 |  |  | Eau Claire Energy Cooperative | Electricity | [9 empty] | 08/02/2023 | 08/04/2023 | No | Yes | [13 empty] | Contractor stopped work until utility delay was resolved |  | 16 to 24 hours |  | 04 to 08 hours |  | Excusable - Non-Compensable Delay |  |  | Utitily pole described as being moved was still in conflict. See Email Chain Attachment
20230214049 | wisc 2023249 | 8060-00-70 | Somerset - St Croix Falls; Cth C To Laser Drive | NW | St Croix | STH 035 | Andrew.Huntley | CORRE INC. |  | 2 | 02/19/2024 | 303 | PAVT REPLACEMENT | A-1 EXCAVATING LLC | Xcel Energy | Electricity | [9 empty] | 04/17/2023 | 04/18/2023 | No | No | [5 empty] | Power poles were supposed to be relocated prior to work beginning. | [7 empty] | Contractor stopped work at current location and moved to another location |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Resolved
20230214049 | wisc 2023249 | 8060-00-70 | Somerset - St Croix Falls; Cth C To Laser Drive | NW | St Croix | STH 035 | Andrew.Huntley | CORRE INC. |  | 3 | 02/19/2024 | 303 | PAVT REPLACEMENT |  | Northwest Comm | Communication Line | Underground | [8 empty] | 05/23/2023 | 05/23/2023 | No | No | [13 empty] | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | Resolved
20230214049 | wisc 2023249 | 8060-00-72 | Somerset - St Croix Falls; Cth C To Laser Drive | NW | St Croix | STH 035 | Andrew.Huntley | CORRE INC. |  | 1 | 02/19/2024 | 303 | MISCELLANEOUS | A-1 EXCAVATING LLC | Northwest Comm | Communication Line | Underground | [8 empty] | 05/16/2023 | 05/16/2023 | Yes | Yes | [5 empty] | DOT allowed the Utility company to leave all existing/old 24" steel casing in the grade. Diggers did not mark dead facilities. | [6 empty] | Contractor called facility owner and asked if the facility was live or dead. Utility said dead so the Contractor removed the facility themselves. | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | Less than 01 hour |  | Digger&apos;s Hotline |  |  | Resolved
20230314008 | wisc 2023274 | 5989-00-31 | Town Of Beloit, Park Avenue; Cranston Road To E Inman Parkway | SW | Rock | LOC STR | Brian.Boelter | SHORT ELLIOTT HENDRICKSON INC. | Richard.Olson | 1 |  | 201 | RECOND (INTERSECTION/WIDEN/SHOULDER) | ROCK ROAD COMPANIES, INC. | AT&T Wisconsin | Communication Line | [9 empty] | 05/15/2023 | 07/27/2023 | No | Yes | [13 empty] | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Other | Two additional working days needed for contractor to return to the area and grade ditch and path where the conflict was located. | Non-Excusable Non-Compensable Delay |  |  | AT&T noted the conflict during Precon meeting and that the communication cabinet needed to be moved to new location. AT&T had a lack of workforce for the splicing of communication lines which caused longer delay.
20230314008 | wisc 2023274 | 5989-00-31 | Town Of Beloit, Park Avenue; Cranston Road To E Inman Parkway | SW | Rock | LOC STR | Brian.Boelter | SHORT ELLIOTT HENDRICKSON INC. | Richard.Olson | 2 |  | 201 | RECOND (INTERSECTION/WIDEN/SHOULDER) | ROCK ROAD COMPANIES, INC. | Unite Private Networks | Communication Line | Underground | [8 empty] | 09/08/2023 | 09/15/2023 | No | No | [13 empty] | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 01 to 04 hours |  | Non-Excusable Non-Compensable Delay |  |  | Elevation of fiber optic line was in conflict with proposed storm culvert pipe. Fiber line was lowered in the ground in order to place culvert pipe as planned. Pipe placed over lowered fiber line.
20230314008 | wisc 2023274 | 5989-00-31 | Town Of Beloit, Park Avenue; Cranston Road To E Inman Parkway | SW | Rock | LOC STR | Brian.Boelter | SHORT ELLIOTT HENDRICKSON INC. | Richard.Olson | 3 |  | 201 | RECOND (INTERSECTION/WIDEN/SHOULDER) | ROCK ROAD COMPANIES, INC. | AT&T Wisconsin | Communication Line | Underground | [8 empty] | 09/07/2023 | 09/07/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Compensable Delay |  |  | Inlet structure was lowered 6" in order to fit proposed storm pipe below the fiber duct package that was in conflict. Contractor had already placed the inlet and endwall when the conflict was discovered, so crew had to repeat work in order to lower the structure and endwall. Additional ditch grading was also needed outside of the project limits in order to make water flow off site.
20230314008 | wisc 2023274 | 5989-00-31 | Town Of Beloit, Park Avenue; Cranston Road To E Inman Parkway | SW | Rock | LOC STR | Brian.Boelter | SHORT ELLIOTT HENDRICKSON INC. | Richard.Olson | 4 |  | 201 | RECOND (INTERSECTION/WIDEN/SHOULDER) | ROCK ROAD COMPANIES, INC. | AT&T Wisconsin | Communication Line | Underground | [8 empty] | 09/15/2023 | 09/21/2023 | No | Yes | [12 empty] | Manhole adjustments were needed to match new pavement elevation. AT&T wanted to reconstruct chimney of manholes and not just adjust castings. The time for reconstruction of each manhole chimney caused the delay. | Contractor stopped work until utility delay was resolved |  | Less than 01 hour |  | 16 to 24 hours |  | Excusable - Compensable Delay |  |  | The delay in the manhole adjustments caused delay in paving operations. This also pushed the completion date of the contract past the initial deadline. Additional days needed to be added to contract as compensation.
20230314009 | wisc 2023276 | 6992-00-75 | Village Of Windsor, Windsor Road; Yahara River Bridge, B-13-0890 | SW | Dane | LOC STR | Emily.Jackson | JT ENGINEERING, INC. | Richard.Olson | 1 | 10/18/2023 | 201 | BRIDGE REPLACEMENT, PRESERVATION | SHEET PILING SERVICES LLC | TDS Metrocom LLC | Communication Line | [9 empty] | 06/07/2023 | 06/26/2023 | No | Yes |  |  | Yes |  |  |  | Yes |  |  | Yes | [7 empty] | Other | 40 Hours. Issue affected one work week. |  |  |  | One phone call and one email sent on 6/5/23 from Emily Harrison (Jackson) to TDS plan contact without response. Email sent on 6/8/23 from Richard Olson (WisDOT Utility Coordinator) to TDS plan contact without response. Joe McNeeley (TDS), Village of Deforest, and Eric Halverson with Vierbecher on site to discuss TDS conflict on 6/12/23. On 6/12/23 Joe Mcneeley says they will drill new line on Thursday (6/15/23) but will not be able to switch the line over until the following Wed-Friday (6/21-23/23). Line was successfully moved 6/22/23.
20230314015 | wisc 2023284 | 2565-02-71 | C Glendale, N Green Bay Ave; Intersection With Cth Pp | SE | Milwaukee | STH 057 | Brian.Dressler | DAAR ENGINEERING, INC | Michael.Birschbach | 1 | 10/25/2023 | 303 | MISCELLANEOUS | LALONDE CONTRACTORS INCORPORATED | We Energies | Electricity | Underground | [8 empty] | 05/01/2023 | 05/05/2023 | No | Yes | [12 empty] | Utility Company de-energized facility and then installed a new facility after the work in the area was completed. | Contractor delayed start of work |  | 04 to 08 hours |  | Other | Delayed Work 3 Days for We Energies to De Energize underground and move light pole | Excusable - Non-Compensable Delay |  |  | Underground Facilities in the roadway cut for the WB Good Hope Road RT Turn Lane
20230314015 | wisc 2023284 | 2565-02-71 | C Glendale, N Green Bay Ave; Intersection With Cth Pp | SE | Milwaukee | STH 057 | Brian.Dressler | DAAR ENGINEERING, INC | Michael.Birschbach | 2 | 10/25/2023 | 303 | MISCELLANEOUS | DOLSON, INC. | City of Glendale | Water | Underground | [8 empty] | 05/11/2023 | 05/11/2023 | No | Yes | [13 empty] | Contractor productivity rate was affected |  | 01 to 04 hours |  | 04 to 08 hours |  | Excusable - Compensable Delay |  |  | The new storm sewer structure in the WB Good Hope Road RT Turn Lane was at the same location as existing WM. It wasn't known that there would be a conflict until excavating for the storm sewer and finding the WM at the same depth as the Storm Sewer Structure. Storm Sewer modifications were made to avoid the WM and maintain drainage.
20230314015 | wisc 2023284 | 2565-02-71 | C Glendale, N Green Bay Ave; Intersection With Cth Pp | SE | Milwaukee | STH 057 | Brian.Dressler | DAAR ENGINEERING, INC | Michael.Birschbach | 3 | 10/25/2023 | 303 | MISCELLANEOUS | DOLSON, INC. | City of Glendale | Water | Underground | [8 empty] | 05/16/2023 | 05/16/2023 | No | No | [13 empty] | Other | Made Storm Sewer Modifications prior to the date of installation | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | The new storm sewer structure in the EB Good Hope Road RT Turn Lane was at the same location as existing WM. Storm Sewer modifications were made to avoid the WM and maintain drainage.
20230314015 | wisc 2023284 | 2565-02-71 | C Glendale, N Green Bay Ave; Intersection With Cth Pp | SE | Milwaukee | STH 057 | Brian.Dressler | DAAR ENGINEERING, INC | Michael.Birschbach | 4 | 10/25/2023 | 303 | MISCELLANEOUS | LALONDE CONTRACTORS INCORPORATED | AT&T | Communication Line | Underground | [8 empty] | 05/15/2023 | 05/19/2023 | No | Yes | [13 empty] | Other | Contractor continued work around the utility | 01 to 04 hours |  | Less than 01 hour |  | Excusable - Non-Compensable Delay |  |  | The underground facility was damaged during concrete pavement removal because the utility was directly below the concrete pavement. AT&T was notified and they came out and lowered the facility and then fixed the damaged facility.
20230314018 | N/A | 2967-17-70 | C Milwaukee, Appleton Avenue; Bridge Over Menomonee River | SE | Milwaukee | STH 175 | Jeff.Reedy | LAKESIDE ENGINEERS, LLC | Michael.Birschbach | 1 | 12/06/2023 | 303 | BRIDGE REHABILITATION | ARBOR GREEN, INC. | Milwaukee Metropolitan Sewerage District | Sewer (Storm or Sanitary) | [9 empty] | 10/05/2023 | 10/14/2023 | No | No | [13 empty] | Other | Conflict identified early. Additional effort for investigation and redesign by construction oversight team. | 04 to 08 hours |  | Less than 01 hour
20230314028 | wisc 2023291 | 6744-02-70 | V Westfield, Main Street; Westfield Creek Bridge B-39-0081 | NC | Marquette | LOC STR | Garrett.Lysne | POINT OF BEGINNING, INC. | Michael.Caban | 1 | 06/02/2023 | 201 | BRIDGE REPLACEMENT, PRESERVATION |  | Frontier Communications | Communication Line | Underground | [8 empty] | 05/30/2023 | 05/31/2023 | No | No |  |  | Yes |  |  |  | Yes | Yes |  |  |  | Yes | Utility contact was informed and they sent a private locator out to provide depths and a more accurate location. The contractor determined based on the depths that it should not be an issue. | Other | The contractor had concerns about the depth for installing their sheeting for the cofferdam. | Less than 01 hour |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  | Yes | See plan sheet mark up of where the location of the frontier line should have been relocated to based on their work plan vs. the location it was located too.
20230509010 | wisc 2023362 | 2200-20-70 | C Brookfield, Bluemound Rd; Ih 94 To East County Line | SE | Waukesha | USH 018 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 1 | 07/31/2023 | 303 | RESURF (OVERLAY >= 4 IN) | OUTDOOR LIGHTING CONST CO INC | We Energies | Electricity | Overhead |  | Spectrum | Communication Line | Overhead |  |  |  |  | 07/14/2023 | 07/31/2023 | No | No |  | Yes | [5 empty] | Yes |  |  |  |  | 124th Street intersection with Bluemound Rd. Conflict with temporary signal span wires - re-design to eliminate need for temporary signals. See WAF 003 | Other |  | 01 to 04 hours |  | Less than 01 hour
20230509010 | wisc 2023362 | 2200-20-70 | C Brookfield, Bluemound Rd; Ih 94 To East County Line | SE | Waukesha | USH 018 | Paul.Watry | BLOOM COMPANIES, LLC | Michael.Birschbach | 2 | 07/31/2023 | 303 | RESURF (OVERLAY >= 4 IN) | OUTDOOR LIGHTING CONST CO INC | City of Brookfield | Sewer (Storm or Sanitary) | Underground | [8 empty] | 07/14/2023 | 07/31/2023 | No | No |  | Yes | [5 empty] | Yes |  |  |  |  | Underwood Crossing SE corner - field inlet shown in plan but not pipe connection. Planned mono tube base spread footing in conflict with storm pipe. Footing redesigned to avoid pipe | Other | identified prior to work | 01 to 04 hours |  | Less than 01 hour
20230509014 | wisc 2023364 | 2450-00-73 | T Genesee, Genesee Rd; Saylesville Creek To Rockwood Trail | SE | Waukesha | STH 059 | Matthew.Smith | WISDOT | Michael.Birschbach | 1 | 08/04/2023 |  | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) |  | We Energies | Gas/Petroleum | [9 empty] | 07/31/2023 | 08/04/2023 | No | Yes | [13 empty] | Other | ULO verified location and adjustments were made to avoid the 16" gas main and keep a clearance of at | Other | Bright Stream was not relocated as the plan had called out. They were contacted and they sent field personal to verify and come up with a field solution. | Other |  | Other |  |  | 16" gas main was identified in the plan to locate to verify location. Soil was unstable in the trench area of the main and would pose a clearance issue for SB 3 (mono tube ). So the signal was moved 6" to gain enough clearance and placed a rock shield and slurry in place.
20230509014 | wisc 2023364 | 2450-00-73 | T Genesee, Genesee Rd; Saylesville Creek To Rockwood Trail | SE | Waukesha | STH 059 | Matthew.Smith | WISDOT | Michael.Birschbach | 2 |  | 303 | RESURF(OVLAY>= 4 IN DOESNT INC PROFILE) | ROCK ROAD COMPANIES, INC. | Brightspeed of Western Wisconsin, LLC | Communication Line | [9 empty] | 10/02/2023 | 10/05/2023 | No | Yes | [12 empty] | Utility had placed new cable without hooking it up. Utility sent a crew to hook up new facility and disconnect existing cable. | Contractor stopped work at current location and moved to another location |  | Less than 01 hour |  | Less than 01 hour |  | Other | Line was located in advance and the contractor was able to work around area until the line was cut over.
20230509018 | wisc 2023368, 369, 370 | 9560-06-71 | Pembine - Michigan State Line; S Jct Ush 141-N Jct Ush 141 | NE | Marinette | USH 141 | Ryan.Erkkila | COLEMAN ENGINEERING COMPANY-IRNMTN | Garrett.Vickman | 1 | 10/05/2023 | 303 | RESURF (OVERLAY < 2.5 IN) |  |  | Communication Line | Underground | [8 empty] | 10/05/2023 | 10/05/2023 | No | No |  |  |  |  | Yes | There was no conflict but I was asked to fill this out given it was a near miss. The plan shows the utility but the painted out locates were off horizontally resulting in a near miss with the excavator. | [5 empty] | Yes | There was no conflict it was just a near miss given the locate paint was improperly placed. The contractor did not hit but came in close contact with buried communication lines while excavating. They just worked carefully around the area and that was the end of it. | Other | Near miss. The plan shows the utility but the painted out locates were off horizontally resulting in a near miss with the excavator. | Other | Zero time. There was no conflict but I was asked to fill this out given it was a near miss. | Other | Zero time. There was no conflict but I was asked to fill this out given it was a near miss. | Non-Excusable Non-Compensable Delay |  |  | Posts 1 and 2 of the guardrail replaced near station 1250+75Lt required excavation work to take place given boulders and such that wouldn't allow them to be driven to proper depths. The contractor had the utilities located in the area prior to starting the excavation. When digging down for the obstructions they exposed some communication conduit that was miss marked by the locator. The contractor did not hit or disturb the utility during this process. They worked around it backfilling and later driving their posts with no conflict or issue.
20230711003 | n/a | 1330-22-70 | Sth 83 - Hartford To Chenequa; Sth 167 To Monroe Avenue | SE | Washington | STH 083 | Travis.Brush | KL ENGINEERING, INC | Michael.Birschbach | 1 |  | 303 | RESURF (OVERLAY >= 4 IN) | GORDON J. GRUBE CONSTR. CO., INC. | Frontier Communications | Communication Line | [9 empty] | 09/25/2023 | 09/26/2023 | Yes | No | [15 empty] | 16 to 24 hours | Issue was resolved by 9am on 9/26, which did not end up delaying contractor as they didn't work due to rain. | Less than 01 hour |  | Digger&apos;s Hotline |  |  | Issue ended up being the USIC locator had marked out the old fiber. The contractor who installed new fiber came to the site at 8am on 9/26/23 to show where new handhole is located and showed that the line is well outside of the footprint of our project and at the appropriate depth needed.
20230711006 | n/a | 6518-06-71 | Shiocton - Bear Creek; Sth 54 - Ncl | NC | Outagamie | STH 076 | Mick.Magalski | MCMAHON | Garrett.Vickman | 1 | 09/21/2023 | 303 | PARTIAL DEPTH CIR WITH > 2.5 IN CAP | MICHELS ROAD & STONE, INC. | Frontier Communications | Communication Line | Underground | MITCH & SONS EXCAVATION/UTILITY | [7 empty] | 09/11/2023 | 09/14/2023 | Yes | No | [15 empty] | Less than 01 hour |  | Less than 01 hour |  | Digger&apos;s Hotline |  | Yes | Phone line was in conflict but not located. The utility was cut through while installing a culvert on 9/11/23 and later cut through while excavating near the culvert on 9/14/23. In both cases, there were no delay to the work. Diggers Hotline ticket #20233421580.
20230808002 | wisc 2023576, 577 | 5090-05-60 | Reedsburg - Baraboo; W Mulberry St To E V Limits | SW | Sauk | STH 033 | Tadd.Owens | CORRE INC. | Richard.Olson | 5 |  | 303 | PAVT REPLACEMENT | A-1 EXCAVATING LLC | Village of West Baraboo | Sewer (Storm or Sanitary) | Underground | [8 empty] | 12/12/2023 |  | No | Yes | [5 empty] | Conflict shown in the plans but was not addressed in the contract documents | [6 empty] | Assumed at this time that we will have to design around the conflict | Other |  | Other | Unknown at this time but this will entail a considerable amount of time for any redesign | Other |  | Excusable - Non-Compensable Delay
20230808002 | wisc 2023576, 577 | 5090-05-71 | C Baraboo, Eighth Street; W City Limit To Lincoln Avenue | SW | Sauk | STH 033 | Tadd.Owens | CORRE INC. | Richard.Olson | 1 |  | 303 | PAVT REPLACEMENT | MERKEL COMPANY INC | Alliant Energy | Electricity | Overhead |  | Spectrum | Communication Line | Overhead |  | Brightspeed of Central Wisconsin, LLC | Communication Line | Overhead | 09/06/2023 |  | No | No |  | Yes | [6 empty] | Yes | Yes | Yes | Yes | All three utilities are aware of the conflicts. They are currently re-designing to remove the conflicts. If the desired offset can not be achieved, there are some instances with the facility may be protected with a guard / shield. In at least one of the locations, the existing line is to be removed in the original work plan so this will eliminate the conflict as long as this work is done prior to the active construction. The conflict with the overhead lines and the new light poles occurs in the Village of West Baraboo from Mulberry Street to the east end of the Village Limits and in the City of Baraboo from the western city limits to Draper Street and from Camp Street to Lincoln Avenue on the eastern portion of the project. | Other | There is no impact at this time. Trying to resolve the conflict to prevent a delay to the work when we install the new light poles for the project in 2024. | 16 to 24 hours |  |  |  | Non-Excusable Non-Compensable Delay |  |  | The conflict with the overhead lines and the new light poles occurs in the Village of West Baraboo from Mulberry Street to the east end of the Village Limits and in the City of Baraboo from the west city limits to Draper Street on the west end of the project and from Camp Street to Lincoln Avenue on the eastern portion of the project. I have been working since 9/6/23 to identify conflicts with the light poles that were not previously identified. I have been working with the various utilities since 9/11/23 to resolve the conflicts with the overhead lines. The conflicts are not technically conflicts at this point but they will be next year. We are trying to get out in front of this work as to avoid any delay to the project schedule in 2024
20230808002 | wisc 2023576, 577 | 5090-05-71 | C Baraboo, Eighth Street; W City Limit To Lincoln Avenue | SW | Sauk | STH 033 | Tadd.Owens | CORRE INC. | Richard.Olson | 2 |  | 303 | PAVT REPLACEMENT | A-1 EXCAVATING LLC | Brightspeed of North Central Wisconsin, LLC | Communication Line | [9 empty] | 09/06/2023 |  | No | No |  | Yes | [7 empty] | Yes |  |  |  | Other | This was an additional conflict that was identified. There is not impact to the schedule at this time but will impact the schedule in 2024 | 16 to 24 hours |  | Other |  | Non-Excusable Non-Compensable Delay |  |  | The manhole covers for the communication vaults in the area of the new ramps on the north side of STH 33 in the City of Baraboo have to relocated outside of the ramp areas. It is not possible to properly construct the curb ramps or to install the warning fields for the ramps with the manhole covers in their current locations.
20230808002 | wisc 2023576, 577 | 5090-05-71 | C Baraboo, Eighth Street; W City Limit To Lincoln Avenue | SW | Sauk | STH 033 | Tadd.Owens | CORRE INC. | Richard.Olson | 3 |  | 303 | PAVT REPLACEMENT | A-1 EXCAVATING LLC | Brightspeed of North Central Wisconsin, LLC | Communication Line |  |  |  | Communication Line | [5 empty] | 10/03/2023 | 10/18/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | Other |  | Other |  | Non-Excusable Non-Compensable Delay |  |  | There are utilities crossing Lincoln Ave on the north leg that were not identified in the plans. The plans indicated the pack of conduit that runs from vault to vault under the sidewalk on the north side of the roadway. However, we discovered a 900 pair telephone line and an unknown conduit that were both within the BAD of the existing roadway. Both of these utilities need to be lowered approximately 2'. We also need to identify what is in the unknown conduit in this area. It is assumed that this is work pertaining to Brightspeed. They have called in a locate and will work on lowering these lines next Monday. They will also be trying to determine what the unknown conduit / line is and whose it is. This is not a conflict at this time but will be a conflict if this is not resolved by the time that the contractor performs the grading in this area. This did indeed end up being a conflict and delayed the progress of the grading through this area. Brightspeed took a week and a half longer than expected to resolve this conflict and A-1 actually performed a portion of the work for the utility due to the fact that the subcontractor did not have the proper equipment or material to perform the work that was required to eliminate the conflict.
20230808002 | wisc 2023576, 577 | 5090-05-71 | C Baraboo, Eighth Street; W City Limit To Lincoln Avenue | SW | Sauk | STH 033 | Tadd.Owens | CORRE INC. | Richard.Olson | 4 | 10/05/2023 | 303 | PAVT REPLACEMENT | A-1 EXCAVATING LLC | Alliant Energy | Gas/Petroleum | Underground | [8 empty] | 10/05/2023 | 10/05/2023 | No | Yes |  | Yes | [7 empty] | Yes |  |  |  | Contractor stopped work until utility delay was resolved |  | 01 to 04 hours |  | 01 to 04 hours |  | Excusable - Non-Compensable Delay |  |  | A-1 encountered a live gas main in the way of the storm sewer work. This conflict was with the run of pipe between manhole 15.0 and inlet 15.16. Alliant notified at 3:00 p.m. Alliant moved their sub down to this location to lower the gas main. Took 1 hour 45 minutes to lower gas. A-1 was on hold during this time as they would have been in the way of the utility if they has tried to continue to work on the other runs of storm sewer in this intersection.
DB6526-00-71 | wisc 2022699 | 6526-00-71 | T. Grand Chute, College Ave; Ih41 - Bluemound Drive | NE | Outagamie | STH 125 | Bryan.Schaller | ALFRED BENESCH & COMPANY | Garrett.Vickman | 1 | 11/30/2023 | 303 | BRIDGE REPLACEMENT, PRESERVATION | PHEIFER BROTHERS CONSTRUCTION CO., INC. | ANR Pipeline | Gas/Petroleum | Underground | VINTON CONSTRUCTION COMPANY | [7 empty] | 08/02/2023 | 09/14/2023 | No | Yes | [13 empty] | Contractor delayed start of work |  | 16 to 24 hours |  | Other | 7 Calendar days | Excusable - Compensable Delay | Adding 7 calendar days to the allowable lane user impact, and additional costs to the contract for modified removals. See CCO #3 |  | TC Energy/MM Services/Badger Daylighting were on site on 8/2/2023 and exposed the ANR Gas pipeline at the center pier and both east and west abutments of existing structure B-44-10. At all three locations where the pipeline crosses the structure elements, the pipe is cased in metal and the footings were cast around the pipeline. The as-built plan shows a footing depth at all three locations of 2’, however it was confirmed that the footings were poured deeper and fully encase the pipeline. It does not appear that there was any kind of foam or cork wrap utilized between the pipeline and the concrete in the footings, and any gap present is minimal. The top of pipe, top of footing, and stream bed were all surveyed at the center pier. The stream bed is approximately 3’ above the top of the footing, and the top of the footing is approximately 1’ to 1.2’ above the top of the pipe. A survey shot was not obtainable on the bottom of the footing. Water depth was approximately 1’. The utility is in conflict with removal operations and the contractor believes this modifies the plan requirements for structure removal. 8/23/23 update: The design-builder and WisDOT have agreed to alternate removal methods for the rigid frame structure. This results in additional costs to the Department and additional lane user impacts to the traveling public. See CCO #3. 9/13/23 update: B-44-10 existing box culvert structure removals and demolition are complete. Additional conflicts were discovered with piling operations regarding the existing wing footings from 1953 that were cast monolithically with the footings for the main rigid frame structure. Additional effort for removals was necessary by the Design-Builder, added costs also captured in CCO #3. Pile driving operations are planned to be complete by the end of the day today. 9/14/23 update: Utility conflict resolved. Additional time added to project: 9 additional traffic impact days, one additional calendar day added to completion date. Additional project costs: $242386.56
DB6526-00-71 | wisc 2022699 | 6526-00-71 | T. Grand Chute, College Ave; Ih41 - Bluemound Drive | NE | Outagamie | STH 125 | Bryan.Schaller | ALFRED BENESCH & COMPANY | Garrett.Vickman | 2 | 11/30/2023 | 303 | BRIDGE REPLACEMENT, PRESERVATION | PHEIFER BROTHERS CONSTRUCTION CO., INC. | AT&T | Communication Line | Underground | VINTON CONSTRUCTION COMPANY | [7 empty] | 08/18/2023 | 08/25/2023 | No | No | [13 empty] | Other | No impact. | 01 to 04 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay | No impact to cost or time. |  | 8/18/23 notes: • AT&T leases a duct located along the south side of STH 125 to CCSI Network. Teleport (TCG) leases a duct from AT&T • AT&T completed all of their relocation work (including splicing) last Thursday (8/10/23). • CCSI Network still has live fiber located within the existing conduit along the STH 125 outside shoulder (labeled as Telephone lines owned by AT&T Wisconsin in the plans). • Dale anticipates it taking 2 days to get their new innerduct placed in AT&T’s new duct, new fiber pulled thru and spliced. Dale is hoping their contractor DeLuca can get out their sometime next week to place the innerduct and pull the fiber over. Dale said it may be 8/28/23 or 8/29/23 until they can complete their work. • Brad told Dale the contractor will be performing dewatering operations next week, starting on 8/21/23, which will require some heavy machinery along the south side of STH 125. Dale said this should not be a problem. • Brad told Dale the contractor will be starting structure removals on 8/28/23 and AT&T’s existing duct package along the south side of STH 125 is in direct conflict with these removal operations. • Brad told Dale liquidated damages for the project are $55,000 per day. 8/23/23 update: Innerduct was installed in the new line yesterday (8/22/23). The cutover is planned for Friday 8/25/23 at midnight, which will eliminate the utility conflict. The agreement date for all relocations with AT&T was 8/25/23, and AT&T is in violation of their agreement. Trans220 Violation letter is recommended. 8/25/23 update: Trans220 Violation letter sent. 8/28/23 Update: Received confirmation that the utility has been relocated and is no longer in conflict. Contractor did not experience any delay or financial loss because of conflict.
DB6526-00-71 | wisc 2022699 | 6526-00-71 | T. Grand Chute, College Ave; Ih41 - Bluemound Drive | NE | Outagamie | STH 125 | Bryan.Schaller | ALFRED BENESCH & COMPANY | Garrett.Vickman | 3 | 11/30/2023 | 303 | BRIDGE REPLACEMENT, PRESERVATION | PHEIFER BROTHERS CONSTRUCTION CO., INC. | TDS Metrocom LLC | Communication Line | Underground | VINTON CONSTRUCTION COMPANY | [7 empty] | 10/11/2023 | 10/12/2023 | No | No | [13 empty] | Contractor stopped work at current location and moved to another location |  | 04 to 08 hours |  | Less than 01 hour |  | Non-Excusable Non-Compensable Delay |  |  | TDS vault located on the EB outside shoulder, E of the new structure was found to be in conflict with proposed shoulder widening. TDS was contacted by Brad Becker (CBS Squared, Design-Build Utility Coordinator) on 10/11 at approximately 2:00 PM. Representatives from TDS met project staff on site at 7:00 AM on 10/12, and proceeded to relocate the vault approximately 10 ft south of the existing location. New location is in ditch foreslope. Vinton was able to continue work in other project locations and conflict did not delay operations.
Total Number of Contracts with Utility Conflict Reports: 48
Total Number of Contracts Excluding PBM, LFA, LCS, Test, and Utility Contracts: 912
-