## LPA Schedule Tool
LPA Project Design Schedule Tool |  |  |  |  | 2026-07-15
Sponsor |  |  |  | Environment Complexity Checklist | Yes
County |  |  |  | Roadway/ Structure Widening
Roadway/ Structure ID |  |  |  | Project to Impact Public Land
Project Limits |  |  |  | Historical Property in Limits
Project Length |  |  |  | Archeological Site in Limits
AADT Traffic Count/ Count Year |  |  |  | Project to Impact Floodplain
Program Cycle (Start/ End Year) |  |  |  | Hazardous Material Open Site
Project Type | Bridge Replacement |  | 12 | Endangered Species Mitigation
Fed funding in Design | Yes |  | 6 | Wetland or Waterway Impacts
Real Estate | Permanent Interest (PLE, HE, Fee, & Existing ROW) |  | 15 | Public Concerns with Project
Curb Ramps | Yes |  |  | Other Project Concerns
Railroad | Near or in Project (w/in 1000ft) |  | 12
Utility Timeline | Bridge Replacement |  | 2
Environmental Complexity | Low |  | 4
Minimum Project Timeline | 43 | Months |  | SMA to LET
Design Timeframe | 34 | Months |  | Design Contract Authorized - PS&E
Recommended Schedule | Deadline |  | Start
SMA & Authorization Approved | 2023-07-01 |  | 2023-06-01
Consultant Selection (DT1515) | 2023-10-01 |  | 2023-09-01
Design Contract Authorized | 2024-01-01 |  | 2023-07-01 | User Instructions
Environmental Document Signed | 2025-05-01 |  | 2025-01-01 | Manual Entry for Blue Cells
Design Study Report Signed | 2025-07-01 |  | 2024-07-01 | Check Box in Gray Cells
Plat Recorded/ Real Estate Start | 2025-08-01 |  | 2024-05-01 | Select from List for Orange Cells
PSE | 2026-11-01 |  | 2025-08-01
Recommended Letting | 2027-02-01 |  | 2026-11-01
Construction Year | 2027 |  | 2027-05-01
Formulas:
Yes = EDATE([Start, row below],-3)
Start = EDATE([Yes],-1)
Start = EDATE([Yes],-D10)

## Data
Data
Utility Timeline
| Preliminary engineering |  |  |  | Design Contract Included
Project Type |  | Months | Program | Months |  | Months | Environmental Complexity | Months |  | Real Estate | Months | Railroad | Months | Construction Year | Base
Bridge Rehabilitation |  | 2 | STP 205 Bridge | 2 | No | 0 | Low | 4 |  | None | 0 | None within 1000 ft | 0 | 2025 | 2025-05-01
Bridge Replacement | 12 | 2 | STP 206 Local | 2 | Yes | 6 | Medium | 6 |  | Temporary Interests Only (TLE) | 12 | Near or in Project (w/in 1000ft) | 12 | 2026 | 2026-05-01
Resurfacing | 12 | 2 | STP 206 Rural | 2 |  |  | High | 9 |  | Permanent Interest (PLE, HE, Fee, & Existing ROW) | 15 | Signal or Crossing Work | 24 | 2027 | 2027-05-01
Pavement Replacement | 12 | 2 | STP 206 Urban | 4 |  |  | Extreme | 12 |  | Tribal Land Interest | 24 | Highway over railroad | 36 | 2028 | 2028-05-01
Recondition | 12 | 4 | STP 206 Urban in MPO | 6 | [5 empty] | Relocation | 24 | Highway under the railroad | 48 | 2029 | 2029-05-01
Reconstruction | 12 | 5 | HSIP/ HRRR | 2 | [9 empty] | 2030 | 2030-05-01
Expansion | 12 | 6 | TAP | 3 |  |  | Roadway/ Structure Widening | FALSE | 0 |  |  |  |  | 2031 | 2031-05-01
Major Project | 12 | 9 | TEA | 3 |  |  | Project to Impact Public Land | FALSE | 0 |  |  |  |  | 2032 | 2032-05-01
Signal/ Signage | 12 | 2 | CMAQ | 3 |  |  | Historical Property in Limits | FALSE | 0 |  |  |  |  | 2033 | 2033-05-01
Trail/ Pedestrian | 12 | 3 |  |  |  |  | Archeological Site in Limits | FALSE | 0 |  |  |  |  | 2034 | 2034-05-01
Other | 12 | 3 |  |  |  |  | Project to Impact Floodplain | FALSE | 0 |  |  |  |  | 2035 | 2035-05-01
[7 empty] | Hazardous Material Open Site | FALSE | 0
Preferred PSE | [6 empty] | Endangered Species Mitigation | FALSE | 0
May | [6 empty] | Wetland or Waterway Impacts | FALSE | 0 |  |  | Curb Ramps
August | [6 empty] | Public Concerns with Project | FALSE | 0 |  |  | Yes
November | [6 empty] | Other Project Concerns | FALSE | 0 |  |  | No
February
[7 empty] | Complexity Scale | Low | 0
Note on K4: GROOM, PAULA L: Must be greater that 3 months.
Note on K12: GROOM, PAULA L: This can include parks, trails, schools, DNR easements, and more.
Note on H18: GROOM, PAULA L: This can include parks, trails, schools, DNR easements, and more.