## DT1997
PROGRESS SCHEDULE | [13 empty] | Wisconsin Department of Transportation
DT1997 4/2019
[11 empty] | Page |  | of
Project ID |  |  |  | Name of Road |  |  | County |  | Hwy. No. |  |  | Contractor
Contract Time |  |  | or Completion Date of |  | Estimated Start Date |  |  | Estimated Completion Date |  | Prepared By |  |  |  | Date
Working Days
Calendar Days
1. The contractor shall submit a copy of the progress schedule to the Region's Project Manager prior to beginning work and 14 days prior to the preconstruction conference. At any time the work falls behind schedule, the Contractor shall submit a revised schedule, if requested by the Engineer.
2. Bar graphs shall be drawn chronologically in the sequence the work will be performed to depict the progress schedule. Identify the controlling items of work.
Month
Week of
Estimated No. of Working Days per |  |  |  | Month
Week
Work Items or Operations |  | Quantity & Units |  | Est. Daily Production | BAR GRAPH LEGEND
[6 empty] | Controlling Item |  |  | Non-Controlling Item
Proposed
Actual
Proposed
Actual
Proposed
Actual
Proposed
Actual
Proposed
Actual
Proposed
Actual
Proposed
Actual
Proposed
Actual
Proposed
Actual
Proposed
Actual

## Instructions
INSTRUCTIONS
DT1997
1 | General. A comprehensive progress schedule can be a valuable asset to the contractor as well as to the engineer in identifying, at an early date, a rate of progress which will not result in completion within the contract time. In working day contracts, the progress schedule is also necessary to determine the controlling item for which to charge working days. Therefore, the contractor shall prepare the progress schedule so that it will accurately reflect the sequence of operations and realistic production rates for the various items of work.
2 | Controlling Item. The controlling item is one which must be partially or wholly completed to permit progress essential for the completion of the work within the contract time. The contractor shall identify, by using the legend shown on the front of the form, which item is controlling at any time. The controlling item may be a bid item or a portion of bid item (such as at a particular location), or it may be an operation, such as painting or clean-up. An item may be controlling for a period, then be noncontrolling for a time, then again become controlling.
3 | Estimated Working Days Per Month. This will vary depending on the type of work and the time of the year.
4 | Estimated Daily Production. The value entered in this column should be the daily rate of production proposed by the contractor during each period that the item is controlling.