## Sheet1
Schedule to Meet PS&E
IMPORTANT: To maintain the automatic date calculations fill in only the highlighted areas.
| Scheduled to be completed | Explanation | # of Days* | Variable* | Formula
Construction PS&E Date | 2025-08-01 | enter this date
28 days prior to PS&E | 2025-07-04 | required per FDM |  |  | 28 days subtracted from PS&E date
pER/DSR approval |  | enter this date
Right of Way Plat approval |  | enter this date
Relocation Order approval |  | enter this date
File Relocation Order |  | enter this date
Remaining nominals will be appraised by | 2025-03-28 |  | 14 | days for appraisal approvals | "days for appraisal approvals" subtracted from all appraisals approved by
All appraisals approved by | 2025-04-11 | "X" number of days for appraisal approvals; need to schedule 6-8 weeks if state/fed money in real estate |  |  | 1 day subtracted from last offer made
Last offer made | 2025-04-12 | Offer made the day after "all appraisals approved by" |  |  | 60 days subtracted from "end of 60 day period"
End of 60 day period | 2025-06-11 | 60 days for property owners to obtain their appraisal | 1 | days for negotiation (must be at least 1 day) | JO mailed out then subtracted "days for negotiation"
Jurisdictional Offer mailed out | 2025-06-12 | "X" number of days after the 60 day period for negotiations |  |  | 20 days subtracted from JO expires
Jurisdictional Offer (JO) expires | 2025-07-02 | 20 days after JO is mailed | 1 | days to cut check | 29 days subtracted from PS&E date then subtracted "days to cut check"
Award and check mailed to owner | 2025-07-03 | "X" number of days to cut check |  |  | 29 days subtracted from PS&E date
Award sent in for recording | 2025-07-03 | can be done same day as check is delivered/mailed |  |  | 29 days subtracted from PS&E date
Local forwards all R/W documentation and LPA Cert | 2025-07-04 | 1 day to forward paperwork to MC |  |  | 28 days subtracted from PS&E date
MC recommends Cert 1 to WisDOT | 2025-07-29 | 24 days for MC to review paperwork |  |  | 3 days subtracted from PS&E date
WisDOT Certifies R/W | 2025-07-31 | 3 days for DOT to certify R/W |  |  | 1 day subtracted from PS&E date
*Number of days can be changed according to the circumstances of each individual municipality and project.
Formulas:
Scheduled to be completed = [Scheduled to be completed, row above]-28
Scheduled to be completed = [Scheduled to be completed, row below]-E14