## Schedule
Task | Scheduled Dates |  | Actual | Additional Days | Comments
Real Estate Project Start Date | 2022-10-01 | 26 months before PS&E |  | 0 |  | modules in learn center
Conceptual Stage Reocation Plan | 2022-10-01 |  |  | 0
Real Estate/Utility Coordination |  |  |  | 0
Encumbrance Cost Estimate/PCA Completed | 2022-10-08 | 30 days before prelim plat |  | 0
Preliminary Plat submitted to RE | 2022-11-07 | 21 days before scoping completion |  | 0
Appraisal & Acquisition Scoping Completed | 2022-11-28 | 21 days before contract started |  | 0
Contracts started | 2022-12-19 | 56 days before contract complete |  | 0
Setup Project in READS | 2023-01-30 | 7 days before DSR Approval |  | 0
DSR Approved | 2023-02-06 | 14 days before plat recording |  | 0
Consultant (acq, relo, appraisal) Contracts Completed / Internal staff assigned | 2023-02-13 | 21 days before start up meeting |  | 0
Plat Recorded | 2023-02-20 | 14 days before start up meeting |  | 0
Start Up Meeting | 2023-03-06 | 42 days before sales study submitted |  | 0
Sales Study Submitted for review | 2023-04-17 | 40 days before Sales study Approval |  | 0
Acquisition Stage Relocation Plan | 2023-05-21 | 90 days after plat recorded |  | 0
Staking | 2023-05-20 | 21 days before NPPR submitted |  | 0
Sales Study Approved | 2023-05-27 | 14 days before NPPR submitted |  | 0
NPPR submitted for review | 2023-06-10 | 21 days before NPPR approved |  | 0
NPPR Approved | 2023-07-01 | 21 days before nominal offers out |  | 0
Nominal offers out | 2023-07-22 | 30 days before flipping |  | 0
Flip remaining nominals | 2023-08-21 | 45 days before appraisal submission |  | 0
Appraisal submitted for review | 2023-10-05 | 60 days before apraisal approval |  | 0
Contract Amendment |  |  |  |  | enter additional days as needed
Appraisal approved | 2023-12-04 | 14 days before offer date |  | 0
Offer/relocation packet to owner | 2023-12-18 | 90 days before JO date |  | 0
Owner's appraisal due (if applicable) | 2024-02-16 | 60 days after appraisal delivered |  | 0
Finalize agreed negotiations | 2024-03-03 | 14 days before JO date |  | 0
Last date to JO | 2024-03-17 | 45 days before Target date |  | 0
Order Checks | 2024-03-23 | 21 days before paying owner |  | 0
JO expiration date | 2024-04-06 | 20 days after JO |  | 0
Owner Paid | 2024-04-13 | 7 days before recording |  | 0
Signed Conveyance Recorded | 2024-04-20 | 7 days after Owner paid |  | 0
Award recorded | 2024-04-20 | 14 days after JO Expiration |  | 0
Relocations vacated | 2024-06-04 | must be vacated before razing contract awarded |  | 0
Razing (begin contract docs, contact BPD, Advertise, bid opening, Contract award, Demo) | 2024-06-04 | begin 6 months before PS&E |  | 0
Target Acquisition Date/Utility date | 2024-05-01 | 7 mths before PS&E |  | 0
Documents submitted for Review (LPA) | 2024-11-03 | 28 days before PS&E |  | 0
Relocation Assistance & Advisory Services |  | relocation assistance and advisory services are on going through the acquisition process and until up to 2 years after vacate date.
PS&E | 2024-12-01 |  | 2024-12-01 | 0
Ad
Let date
# days | 780
#months | 26
Formulas:
Scheduled Dates = [Scheduled Dates, row above]
Scheduled Dates = [Scheduled Dates, row below]-30
Additional Days = IF([Actual]="",0,DAYS([Actual],[Scheduled Dates]))
Actual = SUM([Scheduled Dates],E2:E37)
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (factors include: complex parcels, relocations, appraisals, 15+ parcels)
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: compared to Preferred Schedule