## Agenda
LOCAL PROGRAM REAL ESTATE START-UP MEETING AGENDA
Project ID
Project Title/Limits
LPA Sponsor & County
Date
Introductions
ROLE | NAME | AFFILIATION | PHONE / EMAIL
LPREPM | Angie Kneip | WisDOT | 608-245-2623 // angela.kneip@dot.wi.gov
LPREPM Assistance | Kathy Bruflat | WisDOT | 715-836-3908 // kathryn.bruflat@dot.wi.gov
LPPM
Local Sponsor (LPA)
Designer
Appraiser
Review Appraiser
Acquisition Agent
Relocation Agent
Utility Coordinator
Funds in Real Estate (check all that apply):
Local | State* | Federal*
*Additional WisDOT oversight is required
Project Need (explain):
Project & Parcels Details (include a total number then as needed, list the specific parcels or expain):
ITEM |  | TOTAL COUNT | PARCEL LIST / EXPLANATION
Real Estate Parcels
Appraisals (starting out)
Nominal Waivers (starting out)
Utility Land Interests and/or Rights
Choose One: | Follow REPM Chapter 3.1.1.2 (acquire as part of real estate; as a party of interest)
Follow Wisconsin's Guide to Utility Coordination (WGUC) Chapter 17
*ACS must document and match the above decision
Condominium Parcels
Government Owned Parcels
Railroad Parcels
Bike/Ped Parcels
*The above includes recreational trails, bicycle ways, bicycle lanes, or pedestrian ways. NOT sidewalk. Reference Wis. Stat. 32.025
Relocations
> -- Residences
> -- Businesses
> -- Signs
> -- Fences
> -- Other
Hazmat Concerns
Uneconomic Remnants
Sensitive / Priority Parcels
TLE Timeframe (starts the effective date of the sales-study/appraisal and runs until the end of construction):
Check this box if there are NO TLEs on the project.
Construction start date
Construction end date
TLE end date
Project Minimum Offer Amount (provide a dollar amount)
Encroachments
Check this box if there are NO encroachments or if an encroachment report is NOT needed.
ITEM |  | TOTAL COUNT | PARCEL LIST / EXPLANATION
Encroachments to be removed
Encroachments allowed to remain
Revocable Occupancy Permits to be used |  |  | Yes No
Schedule (indicate when each item has been completed or when it will be completed by):
PROJECT SCHEDULE |  | DATE | NOTES / COMMENTS
Environmental Document Approved
DSR Approved
ACS Approved
Final Plat & Relocation Order Approved
> -- Recorded / Filed
PS&E Date
AD Date
Letting Date
DRAFT REAL ESTATE SCHEDULE |  | DATE | NOTES / COMMENTS
Introduction Letters & Brochures Sent |  |  | 15 days minimum recommended
R/W Staking |  |  | 30 " "
Waiver Offers Sent |  |  | 30 " "
Waivers Flipped to Appraisal |  |  | 60 " "
Appraisals Submitted for Review/Approval |  |  | 30 " "
Appraisal Offer Sent |  |  | 60 (required by statute) " "
Last Day to JO |  |  | 30 (20 required by statute) " "
Real Estate Clear Date |  |  | 15 " "
WisDOT Cert Audits (prior to clearance) |  |  | 15 " "
Link to Scheduling Spreadsheet
Responsibilities (indicate who is responsible for completing each real estate item):
REAL ESTATE ITEM |  | REQUIRED ROLE | SPECIFIC PERSONELLE
Cost Estimate |  | LPA
Sales Study Review & Approval |  | Review Appraiser
NPPR Review & Approval |  | LPA
Waiver of Appraisal Review & Approvals |  | LPA
Appraisal Preparations |  | Appraiser
Appraisal Review & Approvals |  | Review Appraiser
OPR Review & Approvals |  | Review Appraiser
Administrative Revision Approvals |  | LPA
Reminder: Admin revisions must be completed for all changes to an offering amount. Any change made to the offering amount must be followed up with a new offer letter to the owner(s) which must state that it replaces and recinds any prior offers.
STCE Final Review & Approvals |  | LPA / Engineer
Payment Requests Submitted To |  | LPA
Local Cert of ROW Review & Approval |  | LPA
State ROW Cert Prep, Review & Approval |  | Designer
LPREPM
Title Searcch Updates
Acquisition of Utility Land Interests/Rights
Local Sponsor meetings for approvals held every (time period)
Time for Local Sponsor to process & cut a check
If committees/councils are involved in Local Sponsor approvals, is there a resolution that could be passed to allow the approving individual to approve increases up to a certain %
Process Notes for Negotiations/Documents for Certification of ROW:
~Signature line clauses should be added to conveyance documents for all entities (see REPM 3.5.4 to 3.5.17)
~Documents to be signed by the proper individual with their title listed
~Payments are to be made to the entity on the title
~Local Sponsor must confirm payments are being made to the correct entity
~WisDOT RE forms are to be used in READS. READS must be used in it's full capacity
~Partial Release of Mortgages should be obtained on all parcels with Fee acquisition (including existing ROW).
~Negotiation diaries must include detailed dialog with property owner(s)
~Negotiation diaries are to be signed. /s/ with typed name is acceptable
~Statement to Construction Engineers (STCEs) must be signed by the owner(s), negotiator, & Local Sponsor
~STCEs must note "NONE" if no commitments were made
~Risk Assessments must be completed anytime a party of interest will not be cleared (see LP RE Manual)
~See LP RE Manual for items needed in READS
~Certificate of ROW (RE1899) is to be prepared by the designer, and identify encroachments and Haz Mat
~Certificate of ROW (RE1899) must be forward to the LPREPM by the designer
~Supporting documents are to be in READS (see LP RE Manual)
Monthly Status Updates (submitted by when each month):
Questions??

## Data for Formulas & Rules
Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Contact | Affiliation | Phone / Email | Checkbox Data
LPREPMs |  |  | LPPM |  |  | Local Sponsor / PM |  |  | Designer |  |  | Appraiser |  |  | Review Appraiser |  |  | Acquisition Agent |  |  | Relocation Agent |  |  | Utility Coordinator |  |  | FALSE | Follow REPM Chapter 3.1.1.2 (acquire as part of real estate; as a party of interest)
Angie Kneip | WisDOT | 608-245-2623 // angela.kneip@dot.wi.gov | [24 empty] | FALSE | Follow Wisconsin's Guide to Utility Coordination (WGUC) Chapter 17
Joua Dorner | WisDOT | 920-492-5997 // joua.dorner@dot.wi.gov | [24 empty] | FALSE | Check this box if there are NO TLEs on the project.
Maggie Hegeman | WisDOT | 262 548-5914 // margaret.hegeman@dot.wi.gov | [24 empty] | FALSE | Check this box if there are NO encroachments or if an encroachment report is NOT needed.
Sara Jewell | WisDOT | 715-365-5799 // sara.jewell@dot.wi.gov
LPREPM Assistance
Kathy Bruflat | WisDOT | 715-836-3908 // kathryn.bruflat@dot.wi.gov
Cindy Michalski | WisDOT (consultant) | 715-450-4462 // cmichalski@correinc.com
N/A | -- | --
Drop Down List for Roles
Title Searcch Updates
Designer
Acquisition Agent
Acquisition of Utility Land Interests/Rights
Utility Coordinator
Acquisition Agent