## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20160712 | 20160712004 | 4 | Earthwork | Couple of questions in regards to the above referenced project. 1. Alignment FR Station 35+50. Earthwork data table (plan sht. 1012) does not indicate any cut for station 35+50. X section for 35+50 FR line (plan sht. 1270) indicates that there is cut. Please clarify. 2. The main sources of borrow on this project are the two main sedimentation basins and the Fitchrona Road Alignment. At this point in time, we have no information on the soils in the sed basins. The plans show that borings were done, but no borehole logs were included with the geotechnical reports supplied on the HCCI site for the specific borings listed below. Specifically, we would like to request copies of the borelogs for PB3-1 (Pond D), IT1, IT2, PB2-2 (Pond A) since these areas are the main sources of fill for this project. | 1. There will be a plan correction that will increase the common excavation by approximately 1,150 CY on Fitchrona Road at Station 35+50 in the next addendum put out for this proposal. 2. Additional soil boring information at the drainage basins was add to the HCCI site for this proposal. The soil boring information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1206-07-74/12060774%20geotech/ | Mike Coleman | 1 | 2016-06-15 09:09 | 2016-06-16 13:29
20160712 | 20160712004 | 4 | Earthwork - MSE Wall Backfill | Looked at special provisions for MSE Wall backfill. Usual specs. The note on plan sht. 58 says that we can use on-site material for MSE Wall Bfill, if visually approved by the engineer. If the engineer visually approves on-site material to be utilized as MSE Wall Backfill, is the testing required (per the special provisions) for the MSE Wall backfill still applicable to the onsite material? Please clarify. | Note 4 on sheet 58 states â€œUse of on-site material is acceptable as retaining wall backfill.â€ The note does not indicate on site material can be used as MSE Backfill if visually approved by the engineer. Please note the difference in the materials and the areas in which those materials are used as indicated on sheet 58. Retaining wall backfill includes the area in front at the foot of the retaining wall and behind the MSE backfill as shown on the detail. MSE backfill testing will be in accordance with the special provisions. | Mike Coleman | 3 | 2016-06-15 10:22 | 2016-06-16 13:34
20160712 | 20160712001 | 1 | Possible Common Excavation Adjustment | For the construction of the new USH 10 EB bridge over USH 41, it seems a portion of the common excavation has already been removed for the construction of that structure and not represented on the cross sections. Stations FEN 144+50 and 145+00, along with FNW 1331+00 and 1331+50. Therefore, it is still included in the station to station listing. Shouldn't the common excavation number be reduced to reflect this material being already removed? | An addendum will be issued to resolve this. | Mike Coleman | 1 | 2016-06-15 10:28 | 2016-06-22 07:56
20160712 | 20160712017 | 17 | Working off of deck with a crane. | While it speaks about allowing a crane to work off of the old bridge as long as it is sitting over a pier, can a crane be used on the new deck for removing the forming once cured? The crane would have to be able to work across the whole length of the bridge. | It was not our design intent for a crane to be used on the new bridge deck. It was our intent that deck form removal would be completed in accordance with the standard spec. | Mike Coleman | 1 | 2016-06-16 11:58 | 2016-06-16 14:58
20160712 | 20160712018 | 18 | In Stream Disturbance Restrictions | Currently the special provisions indicate an in stream disturbance start date of October 1st. Is this restriction for pier/abutment construction only? or will the superstructure falsework removal be included with this restriction? | As stated in the provision, There shall be no instream disturbance of Little Wolf River as a result of construction activity under or for this contract, from October 1 to May 15 both dates inclusive, in order to avoid adverse impacts upon the spawning of trout. â€¦meaning all construction must be out of the water by October 1. There should be no insteam work after that date. The Little Wolf River is a high quality trout steam. The DNR granted this project an extension for instream work through September, but not beyond. | Scott lawry | 1 | 2016-06-16 13:54 | 2016-06-24 14:22
20160712 | 20160712001 | 1 | Temporary Precast Concrete Barrier | Item 2420 SPV 0090.200 Maintain Concrete Barrier Temporary precast Left In Place indicates and moving, if necessary, would be paid under respective standard bid items of delivered and installed. Will this be change order items if needed in the field or will an addendum be issued to add the items and estimated quantities? | An addendum addressing this issue is being prepared to add the bid items. All barrier that is left in place has no plans for moving during 1517-07-77 construction. That barrier will be moved by a future contract 1517-07-80. | Mike Coleman | 2 | 2016-06-17 11:13 | 2016-06-20 08:41
20160712 | 20160712003 | 3 | Design Files | Will you provide the existing and proposed contours/surface files for the new weight facility site? If so, please include line work for edge of pavement, etc. | Here is the link for the posted files. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1070-00-72/ | Scott lawry | 1 | 2016-06-20 10:43 | 2016-06-24 13:45
20160712 | 20160712003 | 3 | Earthwork Summary | 1. In the plans and specials it states that site earthwork is designed to balance, including excess grading material being wasted on-site in the berm as designed. 2. It appears that the 'berm' is included in the earthwork station to station listing. But in the earthwork summary the table shows waste in addition to the what will be wasted in the 'berm'. So therefore the site doesn't balance as stated. 3. Is the prime contractor to locate an off site waste source or will the DOT make additional accommodations (bigger berm or another berm location) for the waste on site? | 1. Correct, the plan provided dimensions and contours of the proposed berm are intended to provide sufficient space to waste all excess SWEF site grading material on-site. 2. After reviewing the earthwork data sheets, a summation error was identified. There will be an addendum provided for this proposal to revise the dimensions of the proposed berm, revise associated earthwork data sheets, and revise the earthwork miscellaneous quantity table. The earthwork computations shown in the plan utilize the standard accepted Average End Area method, which does not calculate to a balanced earthwork site, but alternative earthwork computation methods, such as a surface model to surface model comparison performed in AutoCAD Civil 3D do calculate to a balanced earthwork site. 3. No, the prime contractor will not need to locate an off-site waste source, an addendum will be provided to revise the plan dimensions of the proposed berm for the on-site waste material. | Mike Coleman | 2 | 2016-06-20 10:51 | 2016-06-22 11:37
20160712 | 20160712001 | 1 | Constructability Review | Was there a constructability Review completed on this project that can be shared? | This is posted now at : http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx | Scott lawry | 3 | 2016-06-23 17:11 | 2016-06-24 14:29
20160712 | 20160712001 | 1 | Piling quantities for B-70-61 | The piling quantity for P21 seems to be wrong. The pile length on Pg 4 of 109 states 45' and there are 52 piles and this should equate to 2340 lf. Plan quantity states 1992 lf??? | The correct piling quantity at B-70-61 pier 21 is 2,352 LF accounting for uplift piles which are embedded 1â€™-0â€ into the footing. The corrected quantity will be included in addendum 2. | Mike Coleman | 4 | 2016-06-24 11:31 | 2016-06-27 08:38
20160712 | 20160712003 | 3 | WIM system | For optimal tracking and WIM system performance the mainline WIM should be installed at station 1179+06 for our configuration. Is this be acceptable? | Alternative locations for the mainline WIM are acceptable, but electrical service is planned to be provided near station 1141+00. The presence of existing large wetland areas on the south-side of IH 90 and the feasible route to provide electrical service along the IH 90 corridor are limiting factors in locating the mainline WIM. Also the General Notes indicate one possible WIM system is detailed and that other WIM system configurations will be considered. | Mike Coleman | 3 | 2016-06-24 15:21 | 2016-07-05 07:38
20160712 | 20160712003 | 3 | WIM System | The proposal calls for the Automated USDOT reader (AUR) to be located on the mainline so that all trucks are screened. The plans show it on the weigh station ramp. Is it acceptable for the AUR to be located on the mainline? | Alternative locations for the AUR are acceptable. | Mike Coleman | 4 | 2016-06-24 15:23 | 2016-07-05 07:39
20160712 | 20160712003 | 3 | WIM System | The optimal distance for camera performance with our configuration is 18' from the center of the lane. Sheet 96 of the plans shows the camera pole at 22' from the center of the lane and 4' from the guardrail. How close to the guardrail can the pole be located? | The design notes within SDD 14B42 Midwest Guardrail System (MGS) Guardrail provides the various minimum working widths depending on the type of MGS installations. | Mike Coleman | 5 | 2016-06-24 15:25 | 2016-07-05 07:39
20160712 | 20160712003 | 3 | WIM System | For our configuration and optimal system performance various loops would be located at different places. Is this acceptable? | Alternative locations for loops are acceptable. | Mike Coleman | 6 | 2016-06-24 15:25 | 2016-07-05 07:40
20160712 | 20160712003 | 3 | WIM system | For optimal tracking and system performance the Changeable message signs should be installed at station 1194+25 for our configuration. Will this be acceptable? | Alternative locations for Changeable Message Signs are acceptable. | Mike Coleman | 7 | 2016-06-24 15:26 | 2016-07-05 07:40
20160712 | 20160712003 | 3 | WIM System | For optimal tracking and system performance the WIM in the station entrance ramp and sensors on IH90 EB will need to be installed at station 1204+76. Will this be acceptable? | Alternative locations for the entrance ramp WIM and sensors are acceptable. | Mike Coleman | 8 | 2016-06-24 15:27 | 2016-07-05 07:41
20160712 | 20160712003 | 3 | WIM System | Is it acceptable for the ramp WIM to verify trucks and sort them with the LCS downstream? | Alternative truck verifying and sorting methods are acceptable. | Mike Coleman | 9 | 2016-06-24 15:29 | 2016-07-05 07:42
20160712 | 20160712003 | 3 | WIM System | If the system can accurately track vehicles from the mainline WIM to the ramp can the second overview camera shown on page 91 of the plans be eliminated as is standard with our configuration? | The 2nd overview camera is required. | Mike Coleman | 10 | 2016-06-24 15:29 | 2016-07-05 07:43
20160712 | 20160712003 | 3 | WIM system | Based on our experience in other States and previous discussions with State Patrol all data needed to check license plate and USDOT number reads against is contained in the PRISM targeted file. Is only downloading the PRISM targeted file for the Local Credential Repository as described in section 5.1.10 of the Weigh-In-Motion system special provisions acceptable? | Only downloading the PRISM targeted file is acceptable. | Mike Coleman | 11 | 2016-06-24 15:30 | 2016-07-05 07:44
20160712 | 20160712003 | 3 | WIM system | Should a cell modem be provided for the WIM and static scale systems in the weigh station for remote support and for data collection? | Cell modem is not currently required | Mike Coleman | 12 | 2016-06-24 15:31 | 2016-07-05 07:45
20160712 | 20160712003 | 3 | Virtual Weigh Station | On sheet 96 of the plans it shows high speed internet being run to the STH16 VWS cabinet. Is this a single mode fiber cable being provided by the State or utility provider or should a cell modem be provided for connectivity? | Contractor is responsible for the internet connection and modem/router. It may be wired or wireless. | Mike Coleman | 13 | 2016-06-24 15:32 | 2016-07-05 12:14
20160712 | 20160712003 | 3 | Static Scale | In section B.6.1 of the static scale system special provisions it calls for a max load cell cable length of 10'. Will a length of 22' be allowed as this has no impact on the scale performance? | Yes | Mike Coleman | 14 | 2016-06-24 15:33 | 2016-07-05 07:47
20160712 | 20160712003 | 3 | Static Scale | For past projects a PE stamp has not been required for a manufacturers scale drawing. Will it be required for this project? | Yes | Mike Coleman | 15 | 2016-06-24 15:33 | 2016-07-05 07:47
20160712 | 20160712003 | 3 | WIM system warranty | Will the lane closure for the weigh station mainline WIM system maintenance, due every 6 months, need to be done during off-peak traffic periods? | Yes | Mike Coleman | 16 | 2016-06-24 15:35 | 2016-07-05 07:46
20160712 | 20160712003 | 3 | WIM system Warranty | Will the lane closure for the STH16 VWS, due every 6 months, need to be done during off-peak traffic periods? | No | Mike Coleman | 17 | 2016-06-24 15:35 | 2016-07-05 07:46
20160712 | 20160712005 | 5 | Quantities | The quantities in the miscellaneous quantities table for Removing Asphaltic Surface Milling and the total quantity for this item don't match. Which is correct? | An addendum was issued on June 30 to correct this. | Mike Coleman | 1 | 2016-06-27 15:24 | 2016-07-01 11:28
20160712 | 20160712012 | 12 | Shoulders and Tack | 1) Does the shaping shoulders item need to be completed the same day as paving operations? 2) Is tack for base patches paid under the tack item or incidental to the base patching item? | 1) No. But if contractors operations, create a 2-inch or more drop off at the edge of pavement the contractor shall eliminate the drop-off within 48 hours per standard specifications 305.3.3.3 using either Base Aggregate Dense ¾ or Shaping Shoulder. This is not anticipated except for grading operations for beam guard. 2) It is incidental to the base patch item. (Per Standard Specification 390.5 (3), â€¦Base Patching Asphalt includes providing asphaltic material. Tack Coat is an Asphaltic Material.) | Mike Coleman | 1 | 2016-06-28 19:21 | 2016-06-29 10:46
20160712 | 20160712017 | 17 | Causeway Utility Conflict | it appears that there is a utility conflict with the current location of the causeway. Details depict that the causeway needs to be east of the watermain and it extends out into the river past the Eastern R/W line. This puts the causeway directly under the newly relocated power lines. By field estimatations there is less than 25ft of clear room between the watermain and the power lines. With OSHA Minimum Clear Distances, there is no room for working on/near the causeway. Can the causeway location/details be modified to allow its effective use? | The utility company will de-energize the aerial lines located above the temporary causeway. An addendum to the utilities article of the special provisions will be issued, which will provide further information. | Mike Coleman | 2 | 2016-06-28 22:21 | 2016-06-30 09:43
20160712 | 20160712003 | 3 | Weigh Station Mainline WIM | Currently the specifications require that the mainline WIM on IH90 be installed in one 24 hour lane closure. For our WIM scales we need a total of 96 hours of lane closure. This could be done in one continuous 24 hour lane closure and then a second 72 hour continuous lane closure at a later date if this is preferred. Is this acceptable? | This approach is acceptable as long as times are approved by the engineer during construction, efforts are made to minimize travel delay, and lane closures avoid times (weekend, holidays, and/or special events) of higher traffic volumes. An addendum is being prepared to allow this approach. | Mike Coleman | 18 | 2016-06-29 09:27 | 2016-07-05 07:35
20160712 | 20160712017 | 17 | Construction Staking - Structure | There is currently not a bid item for construction staking for the structure. Is the Department planning on performing the construction staking for the structure? | Upon review, the bid item for construction staking structure layout will be included through an addendum. | Mike Coleman | 3 | 2016-06-29 15:26 | 2016-06-30 09:44
20160712 | 20160712004 | 4 | Excavation Special / Excavation,Hauling and Disposal of of Contaminated Soil | Reviewing the above referenced special Provisions, my interpretation is as follows; If contaminated soils are encountered, and testing reveals that the contamination level exceeds certain parameters, then the material has to go to a landfill and the WDOT will pay it as Excavation,Hauling, and Disposal of Contaminated Soil. If that same material is tested, and the test results are low enough, then the material is to be utilized as fill onsite (location determined by WDOT & WDNR) and the WDOT will pay that volume as Excavation Special. Is this interpretation correct? Please clarify | The interpretation is correct. | Mike Coleman | 4 | 2016-06-29 15:30 | 2016-06-30 14:03
20160712 | 20160712002 | 2 | Earthwork Data | There are no Earthwork Data sheets as a part of Section 9 in the plan set. These are the sheets that show the cut and fill by station. Please provide the customary information that is normally part of the plan set. Graders use this data to determine hauls. | Earthwork data sheets will be provided in an upcoming addendum. | Mike Coleman | 1 | 2016-06-30 11:27 | 2016-07-05 11:04
20160712 | 20160712001 | 1 | Item 204.9165.S quantity | It appears 440 sf of the 873 sf is associated with Structure B-70-61 as shown on sheet 313. We have been unable to locate the remaining quantity of 433 sf in the plans. could you assist us in locating the remaining 433 sf? | Bid item 204.9165.S should be a total quantity of 440 SF. The quantity will be revised in future Addendum No. 2. | Mike Coleman | 5 | 2016-07-01 08:48 | 2016-07-01 09:52
20160712 | 20160712001 | 1 | Temporary Barrier Block Left In Place | The project contains two left in place items...Maintain Left in Place Block and Temp Barrier Left In Place. My understanding of the Maintain Item is the contractor is responsible only for block previously left in place by another contract. The Temp Barrier Left In Place item usually means block we bring to the site and leave in place after our contract is done. The quantity of the Left in Place item and the Maintain item were originally the same and now is slightly different due to the addition of 2800 LF of delivered and installed by Addendum 1. The question I have is do we really have to bring approx 30000 lf of block or are we only actually bringing an additional 2800 lf of block to the site? If it is the latter I feel this should be the new quantity of Left in Place block to not artificially inflate the bid. | The Maintain (SPV.0090.200) is the left in place from previous project. The Concrete Left if place is the 07-77 contractor leaving what they place for the next contract. The 27,310 shown in Addendum #1 sheet 148 should be removed from Concrete Left In Place SPV.0090.201 as that is cover under item SPV.0090.200. This will be reissued as part of Addendum #2. | Mike Coleman | 6 | 2016-07-01 09:44 | 2016-07-01 10:29
20160712 | 20160712001 | 1 | Midway Road Early Fill | In review of the Earthwork Summary and cross sections for Midway Road Early Fill, it appears most of the available fill in the plans has been included in previous projects. Meaning the 103,006 CY is not available for this project. | The comment in the question above is correct and the 103,006 CY may not be available for this project. The department will remove this and correct the earthwork table in the plans and also address some other potential waste sites in an Addendum. | Scott lawry | 7 | 2016-07-01 15:06 | 2016-07-06 12:53
20160712 | 20160712001 | 1 | Temporary shoring - Structure B-70-405 | Plan sheets 499, 500 and 501 indicate shoring at Piers 4, 11 and 13 yet the Quantities sheet indicates piers 3, 7 and 8. We assume the Quantities sheet is in error, correct? Also, it appears the Cofferdam item is only for Pier 6, is that correct? | The quantities sheet should reflect the temp shoring at piers 4, 11 and 13. The cofferdam is only for pier 6. | Scott lawry | 8 | 2016-07-05 15:59 | 2016-07-06 15:50
20160712 | 20160712004 | 4 | Earthwork | Wondering if you could provide the Earthwork quantities by stage on the earthwork summary?? | There are essentially two stages for the project, Stage 1 and Stage 2. In accordance with the contract documents, Stage 1 entails completing Nesbitt Road, the west portion of Williamsburg Way (roundabout), Anton Drive, Pond D and a portion of Pond A. Stage 2 entails completing the remainder of the project. The earthwork is provided by the various individual roadways and ponds, therefore the earthwork is essentially provided by stage. No additional earthwork information by stage will be provided. | Scott lawry | 5 | 2016-07-05 17:04 | 2016-07-06 13:12
20160712 | 20160712016 | 16 | Asphalt Detail | The curb detail on sheet 6 for the asphalt being placed in side the box culvert shows a 6" vertical face. I am not aware of any equipment that does this. What is the Department trying to accomplish with this design? Also the 9' height restriction presents a challenge to find a paver that fits inside the box. | Asphalt detail 6-inch vertical face: Answer â€“ There is not a strong engineering reason to require a 6-inch vertical and will be removed via addenda Paving the box floor: Answer â€“ A similar box culvert for pedestrians was installed near the Chula Vista Resort under STH 13 in 2009. The installation was a similar precast box culvert with a 9-foot vertical dimension. After the box was completed it was found that the precast box units did not align smoothly along the floor and an asphalt paved surface was installed to provide a smooth floor. The floor was successfully paved by machine after other alternatives were considered. | Scott lawry | 1 | 2016-07-05 17:31 | 2016-07-06 13:33
20160712 | 20160712006 | 6 | Salt Shed | When will the County have the site ready for the Salt Shed to be erected. I do not see specific dates for the start and completion of the salt shed. | Contact Sauk County two (2) weeks prior to beginning work on the footings and foundations so that they can complete the required excavation work. Refer to the Information to Bidders, Coordination with other Work of these special provisions for Sauk County contact information. This will be addressed with addendum #4. | Scott lawry | 1 | 2016-07-06 10:38 | 2016-07-07 08:11
20160712 | 20160712001 | 1 | Removing Existing Rubble | During the excavation of the soil nailing/temp shoring of the 79 Project we encountered some large rubble in the slope of the EB roadway that needed to be broken up and hauled away. 1.)There appeared to be more rubble beyond our excavation limits extending under the existing EB 10 traffic lane, will you add quantity for this area also? 2.)How will the cubic yards of rubble be measured? Take the whole excavated area including minor amounts of dirt? Pieces bigger than 1 cubic yard? Truck loads based on ___ cubic yards per load? Can you clarify this please? Thanks | 1.)This area will be added to Addendum #3 to page 147 to the â€œRemoving Existing Concrete Rubble Tableâ€. 2.)The pay item pays for all materials within the concrete rubble area to a depth as directed by the engineer. Truck loads will be measured to determine CYs per load and no price adjustments will be made for rubble pieces larger than 1 CY. | Scott lawry | 9 | 2016-07-06 11:17 | 2016-07-07 08:22
20160712 | 20160712006 | 6 | Rout/Seal | On past projects on this same stretch of highway there has always been a rout/seal bid item for the PCCP/Bituminous Shoulder longitudinal joint. Has the department overlooked this item on this project or is it purposely being left off this time? | A rout and seal item will be added to the contract as part of addendum #4. | Scott lawry | 2 | 2016-07-06 12:02 | 2016-07-07 08:12
20160712 | 20160712002 | 2 | Line items; 0800,0810,0820,0830 Preparation and coating of top flanges | In regards to preparation and coating of the top flanges. The interim completion dates for B-13-91/B-13-93 and B-13-92 and B-13-94 are May 26,2017 and May 25,2018. This poses a low temperature problem for the application of the zinc rich primers as this work would need to be performed in @ February to meet this deadline. Has this been considered? Is there an alternate primer that is not currently on the WISDOT approved list being considered for use? | The product information for the approved zinc-rich primers are summarized below: Manufacturer Product Lowest Listed Lowest Listed Lowest Listed Ambient Drying Low Temp Application Temp Temp ( °F) Curing ( °F) ( °F) Carboline Carbozinc 859 35 --- 35 International Paint Interzinc 52 41 23 32 (When using this alternative curing agent it should be noted that the VOC will increase to 360g/l) PPG Industries Amercoat 68HS 32 --- 50 Sherwin-Williams Zinc Clad III HS 35 --- 35 The average temperatures by week last year are summarized below: Week Mean High Temp ( °F) Mean Ave Temp ( °F) Mean Low Temp ( °F) Feb 7 2016 37 15 5 Feb 14 2016 45 27 11 Feb 21 2016 44 35 30 Feb 28 2016 45 28 14 March 6 2016 61 48 40 March 13 2016 49 44 37 March 20 2016 47 37 27 March 27 2016 48 42 30 The anticipated schedule assumes starting bridge work in mid-March, and therefore the preparation and coating of top flanges would occur in late March. With the information presented above, it is reasonable to assume that the temperatures would be high enough in March to allow for the preparation and coating of top flanges to be done in the acceptable temperature ranges required on the product information sheets. | Scott lawry | 2 | 2016-07-06 12:59 | 2016-07-07 10:56
20160712 | 20160712001 | 1 | Soils Report | Are soils reports available for this proposal? | The files have been saved to the ftp server at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20160712001/soils-reports/ As well as a link has been added to the NE Preliminary Plans page http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx the link will be posted in the next Q/A posting. | Scott lawry | 10 | 2016-07-06 13:52 | 2016-07-07 08:04
20160712 | 20160712003 | 3 | Weigh Station Mainline WIM | Currently the specifications require the Weigh Station Mainline WIM use load cells. Would quartz piezo WIM sensors for this location be acceptable as an alternative in order to minimize the maintenance cost and inconvenience to the traveling public if the following conditions are met: -The other WIM locations, (weigh station ramp and STH16 Virtual Weigh Station) will still require a load cell WIM per the specifications -The specified accuracy requirements for the mainline WIM will not change and must be met by the quartz piezo WIM -No other operational and functionality requirements from the specifications will be allowed with this change -Bidders should include quantity 4 spare 2 meter quartz piezo WIM sensors as a part of the WIM system warranty to meet the life cycle expectancy of the load cell WIM | Quartz piezo WIM sensors would be acceptable for the mainline WIM location. Providing four additional quartz piezo WIM sensors would be acceptable. All accuracy requirements as specified must be met. | Scott lawry | 19 | 2016-07-06 14:08 | 2016-07-07 15:04
20160712 | 20160712003 | 3 | Earthwork Table EBS Backfilled with Breaker Run | Within the Earthwork Table shown on sheet 308, Note 3 states â€œEBS excavation to be backfilled with Breaker Runâ€. How is the Breaker Run being paid? Is this incidental to the 205.0100 Excavation Common Item? | The bid item 311.0110 Breaker Run should be used to backfill any encountered EBS excavation. An addendum will be prepared to add this bid item to the project. | Scott lawry | 20 | 2016-07-06 14:11 | 2016-07-07 14:23
20160712 | 20160712001 | 1 | Pier Shaft Construction Joints | For pier shafts are greater than 25 feet in height and do not show a construction joint, will a construction joint be allowed and would the splice bars, which could amount to over 100,000 lbs, be paid for under the appropriate bid items? | There is one pier shaft that is shown taller than 25â€™ without a construction joint. The height of that pier is 28â€™-1 ¾â€. A construction joint would be allowed, but the bar projection will not exceed the limit that is shown in the Bridge Manual Standard for when to detail bar laps in the plans Splice bars would not be paid for if added at the contractorâ€™s option. | Scott lawry | 11 | 2016-07-06 16:08 | 2016-07-07 08:41
20160712 | 20160712001 | 1 | Follow up to Question 11 - Shaft Construction Joints | We agree the shaft construction joints are shown as optional and the bill of bars on structures B-61, 405 and 406 are detailed showing the shaft verticals with the splices at the 25' construction joints. Structure B-70-401 bill of bars has the shaft verticals listed as full height of the pier shaft. if the construction joint is utilized, these verticals would need to be field cut and additional splice bars utilized. would this be considered extra work and the contractor compensated via contract mod if the construction joint is utilized? | If a construction joint is utilized, the contractor still should be able to utilize the bar steel as detailed per the plans. They should not need to cut down the bars dimensioned in the plan and lap on new steel as the bars should not have an extension out of the top of the construction joint of more than 20â€™ (which is the Bridge Manual defined limit for requiring lapped bars â€“ and this was discussed/agreed upon at the Bridge Technical Committee in the past). If the contractor decides to cut down the bars and lap on new steel, the department would not deem this as compensable additional work. | Scott lawry | 12 | 2016-07-07 11:24 | 2016-07-07 14:13
20160712 | 20160712001 | 1 | Lane Closures | In the miscellaneous quantities you have all the drums, signs, lights and III's for left in place but you missed the arrowboards left in place from the other project. Is there an addendum coming out for the left in place arrowboards and days for them? Missing a lot of lane closures that need to be performed that the other companies will not have in their quote as it really does not show them. I see issues with change orders coming for closures. | The comment is correct and two arrow boards will need to remain in place and be managed under this contract, a addendum will be issued tomorrow to add items for that work. | Scott lawry | 13 | 2016-07-07 13:36 | 2016-07-07 17:30
20160712 | 20160712001 | 1 | Earthwork | The addendums for the 1517-07-77 project in next weekâ€™s letting did not include any plans or details related the fill site currently being utilized along Northbound I-41, Ehlers Road, and North of Jacobsen road. Will this site be available for the 1517-07-77 contract as a fill site and if so, what is a rough quantity of fill this site can accept? | The 1517-07-79 contractor is currently using this site. The department has a very rough estimate of 20K to 30K CY of material that can go into this area after the current project is complete but will require further investigation to confirm and may also require a culvert pipe extension or other preparatory work to make further use of the site. | Scott lawry | 14 | 2016-07-11 10:35 | 2016-07-11 10:37
20160712 | 20160712004 | 4 | Earthwork | Is there a earthwork data summary in excel format that can be made available? | A earthwork data summary sheet has been added to the preliminary plan portion of the HCCI site at the following location: http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx and directly at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1206-07-74/ | Scott lawry | 6 | 2016-07-11 11:42 | 2016-07-11 13:46