## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20160809 | 20160809002 | 2 | Noise Wall testing | For the small amount of noise walls required for this project, will the testing requirements be waived? | Testing requirements for Noise Reduction Coefficient (NRC) & Salt Scaling Resistance scaling for the noise barrier will be waived. | Scott lawry | 1 | 2016-07-19 15:03 | 2016-07-19 15:14
20160809 | 20160809002 | 2 | Timeframe to complete Project | Based on the non-work requirement during peak hours for this project it appears that there is roughly 7 hours per day allowed to work. This includes the Installation and removal of the Maintenance of Traffic Items. With the average night time lows in September being 55 degrees, there is a concern that the resin for the high friction will not be cure and ready for traffic. There are some products that setup faster than others but in general at 55 degrees you are looking for at least 4 to 5 hours of cure which does not leave enough time to install and remove the MOT and also perform the installation of the high friction. Since this location is a hard curve provided extra time to ensure full cure is achieved is critical. In order to attempt 7 hours working restrictions for the installation of the HFTS, the night time temperatures need to be at least 75F. Please review. Also, please note the 55F is about the lowest temperature that manufactures will allow for the installation of the HFST. | There is adequate time in the specifications to complete all of the work necessary to open northbound and southbound IH 94/IH 43 to traffic prior to 12:01 AM October 16, 2016. | Scott lawry | 2 | 2016-07-27 13:30 | 2016-07-27 13:32
20160809 | 20160809002 | 2 | Work Schedule | Can the state please provide the anticipated work schedule for the daily work items and also the overall working schedule. Please confirm the anticipated nightly temperature and time required to cure the HFST. Please confirm that no time allowances will be granted for nightly lane closure or contract completion dates in the event that it is not possible to complete the HFST due to weather and temperature. | Anticipated work schedule for the daily work items and the overall working schedule can be found at http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx. The document is for information only and not a bidding document. The contractor is required to develop their bid to meet the contractual obligations that are defined in the plans and proposal. â€¢ Contractor can use various resources to anticipate nightly temperature â€¢ Time required to cure the HFST is shown in the proposal â€¢ Lane closure restrictions and contract completion dates are shown in the proposal. | Scott lawry | 3 | 2016-08-02 16:24 | 2016-08-02 17:46
20160809 | 20160809007 | 7 | Item 305.0502.S, Shaping Roadway | What is the intent of using the 305.0502.S Shaping Roadway item? | The intent of this item was to have a method of payment to the contractor for blading, shaping, compacting, etc the existing base aggregate onsite for the new roadway. | Mike Coleman | 1 | 2016-08-05 12:06 | 2016-08-05 12:08