## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20160913 | 20160913007 | 7 | CAD Files | A request has been made to get the CAD files for this project to aid in bid preparation. | The files have been provided and can be found in the following location: http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Mike Coleman | 1 | 2016-08-22 07:10 | 2016-08-22 15:07
20160913 | 20160913008 | 8 | Soils Report, Structure Reports, and Rock Probes | Can industry get a copy of the soils report, structure reports, and rock probes? | The geotechnical reports for the mainline and structures, along with the rock probes can be found at the following location. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20160913008/ | Mike Coleman | 1 | 2016-08-31 07:54 | 2016-08-31 07:57
20160913 | 20160913007 | 7 | Time Chart | A request has been made for a copy of the time chart. | The time chart can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20160913007/ | Mike Coleman | 2 | 2016-08-31 08:01 | 2016-08-31 08:02
20160913 | 20160913004 | 4 | MSE Wall Reinforcement Lengths | It appears the minimum reinforced length in the external stability table does not account for the height of the abutment fill sitting on top of the MSE wall. Please provide the minimum reinforced length accounting for the abutment, and confirm the friction angle of 26 degrees for the retained and foundation fills. Thank you. | Based on the fill surcharge loading of 6 feet above the wall height, the minimum reinforcement lengths below were determined to be the following: Wall R-40-604 Total Wall Height = 15.65 feet Exposed Wall Height = 14.15 feet Min Reinforcement Length = 17.2 feet Wall R-40-605 Total Wall Height = 13.5 feet Exposed Wall Height = 12.0 feet Min Reinforcement Length = 14.5 feet This information will be revised and updated on sheets 503 and 508 as part of Addendum #3 of the advertised plan set. The friction angle of 26 degrees for the retained and foundation fills is confirmed. | Mike Coleman | 1 | 2016-09-01 10:32 | 2016-09-08 14:46
20160913 | 20160913004 | 4 | High Performance Dowel Bars for Concrete Pavement | Is it necessary to use high performance dowel bars on this project? We usually only see them used on the interstate projects. | No they are not necessary. Addendum #01 was issued on August 29 to remove the high performance bar language. | Mike Coleman | 2 | 2016-09-01 14:06 | 2016-09-01 14:08
20160913 | 20160913004 | 4 | Preformed Thermoplastic Pavement Marking | WisDOT is phasing out Preformed Thermoplastic Pavement Marking. Do you still want to use this for this project? | The Preformed Thermoplastic Pavement Marking items will remain in the plan. Please bid accordingly. No addenda will be issued. | Mike Coleman | 3 | 2016-09-01 14:13 | 2016-09-01 14:14
20160913 | 20160913004 | 4 | Metalizing ends of girders | Do we metalize the 4 feet at each girder prior to painting? Is this for every girder on the structure or just the ends of the bridge? | Metalizing occurs only on the outer 4' of each end of each girder. It further protects the portion of the girders that are embedded in the concrete abutments. | Mike Coleman | 4 | 2016-09-01 14:18 | 2016-09-01 14:19
20160913 | 20160913004 | 4 | Storm Sewer Pipe | Why are you only specifying concrete storm sewer pipe. Shouldn't this be changed to include HDPE and HDPP? | Addendum #02 was issued on September 1 to add the options of HDPE and HDPP. | Mike Coleman | 5 | 2016-09-01 14:21 | 2016-09-01 14:22
20160913 | 20160913007 | 7 | Preformed Thermoplastic Pavement Marking | WisDOT is phasing out Preformed Thermoplastic Pavement Marking. Do you still want to use this for this project? | The Preformed Thermoplastic Pavement Marking items will remain in the plan. Please bid accordingly. | Mike Coleman | 3 | 2016-09-06 07:16 | 2016-09-06 07:17
20160913 | 20160913008 | 8 | Retaining Walls R-66-37 & R-66-38 | With regard to Retaining Walls R-66-37 and R-66-38, the plans call for a 30â€ footing for W18x35 posts and a 36â€ footing for W21x50 & W24x68 posts. The plans also call for the posts to be set on a 1â€H:12â€V batter. As these posts will be drilled from the â€œtopâ€, average pile length is on the order of 25 ft, which means there is 25â€ of horizontal difference in the pile location from top of pile to bottom of pile. As such, the pile will be located outside the diameter of the concrete footing. How does DOT plan on addressing this constructability issue? | An addendum is being prepared to change the batter from 1"H:12"V to 1/4"H:12"V | Mike Coleman | 2 | 2016-09-07 07:35 | 2016-09-07 14:10
20160913 | 20160913007 | 7 | Milling | Construction detail for intersections on sheet 25 calls for milling of existing pavement on side roads. However, under the typical sections (sheet 15, 16 & 17) it states just removing asphaltic surface and not removing asphaltic surface milling. Are the side roads to specifically be milled or just removed? | Sheet 25 has an error in the legend. The note should call out â€œRemoving Asphaltic Surfaceâ€ and not milling. Using the Removing Asphaltic Surface item will allow the contractor to either remove with an excavator or by milling. Due to the timing an addenda will not be updated for a construction detail note. The typical section and quantities are correct. | Scott lawry | 4 | 2016-09-07 12:41 | 2016-09-08 16:18
20160913 | 20160913007 | 7 | Hazardous Material Tipping Fee | Does the DOT pay for the tipping fee for Excavation, Hauling, and Disposal of Petroleum Contaminated Soil (Item 205.0501.S) | No additional payment will be made for tipping fees associated with the disposal of contaminated soil. | Mike Coleman | 5 | 2016-09-07 13:56 | 2016-09-07 13:57
20160913 | 20160913004 | 4 | MSE wall Backfill | There is a bid item for Granular backfill which appears to be paying for the quantity of MSE wall backfill. This differs from what the special provisions tell us. The wall detail also shows limits of granular backfill which basically represents the MSE wall backfill. Is the MSE wall backfill being paid by the CY under bid item 209.0100 Backfill granular? | The Granular backfill quantity represents what was calculated for the MSE Wall Backfill for each of the walls. Per the special provisions, the granular backfill for the MSE walls is included in the pay item for Wall Concrete Panel Mechanically Stabilized Earth LRFD/QMP. An addendum will be issued to remove the bid items. | Mike Coleman | 6 | 2016-09-08 10:11 | 2016-09-08 13:12
20160913 | 20160913002 | 2 | Base Aggregate Dense | The 1.25" item contains 5583 ton of undistributed shoulder strengthening for the length of the project. Is this the quantity of base to be used in the Prep of Foundation for Asphaltic Shoulder Item? | The undistributed amount is for use in areas where there is not a total reconstruction or other shoulder widening noted, but where additional material is needed to pave a 24â€™ width with the outer 1â€™ on each side serving as a paved shoulder. | Scott lawry | 1 | 2016-09-08 17:05 | 2016-09-09 08:46
20160913 | 20160913002 | 2 | Prep of Foundation Asphaltic Shoulders | This item needs to be constructed after milling. Is 24-48 hours enough time to perform the excavation, installation and prep work required? What determines suitable material for reuse? | This requirement is necessary to limit the amount of time the road is under traffic in a milled state because of the concern about the pavement holding up after 3 ½â€ of material is removed. The contractor should developed their method of operations to meet those requirements. The engineer will determine whether or not the material is suitable for use based on visual inspection of the material. | Scott lawry | 2 | 2016-09-08 17:19 | 2016-09-09 08:51
20160913 | 20160913008 | 8 | Controlled Low Strength Matrial | For both retaining walls R-66-37 and 38, pages 548 and 555 respectively, in the general notes it says "see special provisions for description of controlled low strength material". Cannot find anything in the specials that provides specs on the material. | Addendum Number 4 is being issued to provide specs on the material to be used. | Mike Coleman | 3 | 2016-09-09 16:33 | 2016-09-12 10:17
20160913 | 20160913004 | 4 | Bridge construction in winter 2016 | Can bridge construction start this winter? | No. Construction cannot be performed over the winter. According to the utility special provision, AT&T will not have their utilities moved prior to March 1, 2017. Therefore we do not anticipate work starting prior to March 1, 2017. | Mike Coleman | 7 | 2016-09-12 11:31 | 2016-09-12 11:32