## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20161108 | 20161108001 | 1 | Excess Marsh | On Plan sheet number 27, there is a note in the Marsh Excavation Detail that says "Marsh disposal shall not be placed in the median". Are you referring to any open space between the NB and SB lanes on IH39 or in the just the 2:1 slopes on the LT side of NB lanes? | There shall be no marsh disposal in any open space anywhere in the median. Marsh disposal outside of the 2:1 on the median side of the NB interferes with the SB reconstruct. There is a lot of median grading on both NB and SB sides in the final project 1007-11-74 and we donâ€™t want any risk of marsh being placed where it could impact that project. | Mike Coleman | 1 | 2016-10-11 15:32 | 2016-10-12 08:43
20161108 | 20161108001 | 1 | Select Crushed & Select Borrow in EBS/Marsh Fills | It appears Select Borrow was not expanded. Select Borrow is usually measured in its Original Position. How are you measuring it on this project, final position or original position? If its original then Select Borrow needs to be expanded. Traditionally the marsh backfill is expanded 1.5 times to account for waste, it appears this wasn't done on this project. Is this accurate or should the Select Crushed be expanded more than 1.9 ton/cy? | 1. The payment for the item of Select Borrow will be paid in its final position. There will be an addendum that will include language in the special provisions that will clarify this. 2. Select Crushed is intended to backfill marsh excavation areas only to an elevation of 1 ft above the water line, where water is encountered, as noted on page 27. Since water levels fluctuate throughout the year, the actual quantity of material may be more or less than indicated in the plan based on weather conditions. | Mike Coleman | 2 | 2016-10-12 13:39 | 2016-10-19 07:40
20161108 | 20161108001 | 1 | Select Crushed vs Breaker Run | Is there a significant reason why the plan specifies Select Crushed vs Breaker Run? If the Department uses Breaker Run vs Select Crushed there would be a significant cost savings to the project. On this project, Breaker Run is being used under the Box Culvert (more than likely this Breaker Run will be placed in the water), therefor Breaker Run should be acceptable to be used in Marsh Fills and Subgrade Improvement Areas (the 16 inches under the base course). | After additional internal WisDOT review, the following update applies to the answer for this question. WisDOT will be issuing an addendum for this project which will fully address the changes. The addendum will remove the Select Crushed item specification requirement where it is currently used for backfilling marsh excavation areas, and replace it with Select Borrow. Select Crushed material will still be required in the subgrade treatment beneath the pavement structure. The Select Borrow specification will be updated to the following as a part of the addendum: Select Borrow, Item 208.1100. Conform to the requirements of standard spec 208 and as hereinafter provided. Materials Furnish and use material that consists of granular material meeting the following requirements: Maximum particle size of 12 inches when measured from any face. The material passing the No. 4 sieve shall have a maximum of 15% by weight passing the No. 200 sieve. As a contractorâ€™s option, the department will allow the use of select crushed material for select borrow. The material shall conform to the requirements of standard spec 312, and will be measured and paid for as Select Borrow. Measurement Replace standard spec 208.4 with the following: The department will measure select borrow by the cubic yard acceptably completed in its final location using the method of average end areas, with no correction for curvature or settlement, except as follows: 1. The engineer and contractor mutually agree to an alternative volume calculation method; 2. The method of average end areas is not feasible. If it is not possible to compute volumes of select borrow by the method of average end areas due to erratic location of isolated deposits, the department may compute the volumes by alternative methods involving three-dimensional measurements. The department will not measure select borrow material beyond the limits of the required slopes as shown on the plans. | Mike Coleman | 3 | 2016-10-14 08:48 | 2016-10-19 07:54
20161108 | 20161108001 | 1 | Sand in lieu (or as an alternate) of Select Crushed for Marsh Backfill | Sources of Select Crushed are limited in proximity to this project while sand (sand stone) is readily available. Can sand be used to backfill the Marsh Excavation in lieu of using Select Crushed? Or can there at least be an alternate to use sand as backfill in the Marsh areas? | After additional internal WisDOT review, the following update applies to the answer for this question. WisDOT will be issuing an addendum for this project which will fully address the changes. The addendum will remove the Select Crushed item specification requirement where it is currently used for backfilling marsh excavation areas, and replace it with Select Borrow. Select Crushed material will still be required in the subgrade treatment beneath the pavement structure. The Select Borrow specification will be updated to the following as a part of the addendum: Select Borrow, Item 208.1100. Conform to the requirements of standard spec 208 and as hereinafter provided. Materials Furnish and use material that consists of granular material meeting the following requirements: Maximum particle size of 12 inches when measured from any face. The material passing the No. 4 sieve shall have a maximum of 15% by weight passing the No. 200 sieve. As a contractorâ€™s option, the department will allow the use of select crushed material for select borrow. The material shall conform to the requirements of standard spec 312, and will be measured and paid for as Select Borrow. Measurement Replace standard spec 208.4 with the following: The department will measure select borrow by the cubic yard acceptably completed in its final location using the method of average end areas, with no correction for curvature or settlement, except as follows: 1. The engineer and contractor mutually agree to an alternative volume calculation method; 2. The method of average end areas is not feasible. If it is not possible to compute volumes of select borrow by the method of average end areas due to erratic location of isolated deposits, the department may compute the volumes by alternative methods involving three-dimensional measurements. The department will not measure select borrow material beyond the limits of the required slopes as shown on the plans. | Mike Coleman | 4 | 2016-10-18 08:40 | 2016-10-19 07:55
20161108 | 20161108001 | 1 | Typical Existing Sections | Can Typical Existing Sections be supplied for Sta. 1659+00 - Sta. 1772+02 | This is the same existing typical section as Sta. 1830+08'NB' to Sta. 1926+30'NB'. An upcoming addendum will correct this. | Mike Coleman | 5 | 2016-10-20 11:07 | 2016-10-20 14:33
20161108 | 20161108001 | 1 | Stage 2 Traffic Switch | Under the Special Provisions, Section 3 - Prosecution and Progress/Contractor Coordination, it states that Stage 2 may begin on or after April 24, 2017. If the contractor for Project 1007-11-75 can coordinate the Stage 2 traffic switch with Project 1005-10-71/72 prior to the April 24, 2017 date, would this be allowed. | Yes, but the date to make this switch earlier would need to be approved by WisDOT. Approval of an earlier switch date would still be dependent upon having proper conditions and temperatures to install all traffic control, including striping, as well as a reasonable expectation that winter maintenance (plowing) would be finished for the season. | Mike Coleman | 6 | 2016-10-24 14:26 | 2016-10-26 08:24
20161108 | 20161108001 | 1 | Asbestos Inspection Reports | Can we get a copy of the asbestos inspection reports for Structures B-13-169 and B-13-172? | The asbestos inspections reports can be found at the following location (copy/paste into your browser): ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1007-10-01/ | Mike Coleman | 7 | 2016-10-26 12:58 | 2016-10-26 13:21
20161108 | 20161108001 | 1 | Select Borrow in Marsh | Will the addendum state that select borrow will be used in marsh as backfill from bottom of marsh to subgrade, or will select crushed still be utilized to one foot above the water? It would seem that settlement of the pavement would be an issue if select borrow is used in the water. Past projects where this was done were multiple year projects, where the pavement on this project will be placed within a month of the grading operations. Please clarify. | No. The addendum requires Select Borrow to 2 feet above the water line if water is encountered. Any material meeting the specification for Embankment can be used from 2 feet above the water line to the subgrade. | Scott lawry | 8 | 2016-10-29 09:32 | 2016-10-31 13:55
20161108 | 20161108001 | 1 | B-13-711 Abutment Footing Embedment Into Rock | Sheets 716, 717, 719, & 720 have a note that says to embed footing a minimum of 6" into bedrock, however the rock elevation shown is 6-9' higher than the bottom of footing elevation. Will excavation only be required to achieve 6" embedment for the abutment footings? | The contractor should excavate to the elevations shown in the plan at a minimum, and also provide a 6â€ embedment into the rock. This is shown with the dashed line in the â€œSection Thru Bodyâ€ detail. They may also extend the footing depth as needed as shown in the â€œBedrock Variability Detailâ€. The berm elevation shown on the North abutment sheet is incorrect. It is correct on the front sheet. It should be 930.58, not 926.11. | Scott lawry | 9 | 2016-10-31 08:25 | 2016-10-31 12:39
20161108 | 20161108001 | 1 | Rumble Strips | When looking through the plan, noticed there is no milling new rumble strips into the new concrete or asphalt shoulders. Is this something that was missed? Also did not see an item in the bid for them either? | It is correct that there are no rumble strips next year. In 2018, the new NB side will be used for counter-directional traffic while the SB lanes are reconstructed, so if they were put in next year, the rumble strips would need to be filled after winter of 2017 (in spring of 2018) prior to that traffic switch. So the decision was made to not install those until the end of 2018 (when the SB lanes are fully reconstructed in the same stretch) when traffic will be finished moving around. So that next contract will mill in all of them, both NB and SB. | Scott lawry | 10 | 2016-10-31 10:08 | 2016-10-31 10:09
20161108 | 20161108001 | 1 | Concrete Pavement Aggregate | We are looking to bid the concrete paving aggregate and also the HPC ready mix for structures. The new language in the special provisions specifies a lightweight particle testing interval of 10K cubic yards of concrete produced. In the past, the Department went off the approved agg source listing. My concern is what happens if a test happens to fall out of the lightweight particle spec? there is no language in the spec to address this. We have no control over the specific gravity of material being extracted from the earth for concrete aggregate, so Iâ€™m sure you understand our concern. Will there be a penalty structure, or would this be handled similar to rapid chloride permeability testing, where mix adjustments are required when a test falls out? | The department would expect to handle a nonconforming material with this special as the department wants it handled in all cases. If the department confirms that the material is out of specification and has not been incorporated into the work it would not be allowed. The department should not allow nonconforming material to be incorporated into our projects. In the past the department has reserved the right to test material from an approved source if we had concerns it was no longer within specification and if the material did not meet our specification we could remove the source form the approved list at any time. The department expects that when we have tested and approved a source that the material would continue to remain within specification throughout the project. If there is a failing test we will go through the process of retesting and verifying the material is nonconforming. A contractor will have an opportunity to adjust material and process control to bring material back within specification. One failing test will not permanently disqualify a source. | Scott lawry | 11 | 2016-11-07 09:23 | 2016-11-07 09:36
20161108 | 20161108002 | 2 | Pavement Markng | Bid item 1620 - 646.0881.s Pavement marking grooved wet reflective tape 4" - 92,548 LF seems way overstated. For stationing 975+00SB - 1131+48 SB you have a total of 28,428LF. Almost double the roadway length. Same stationing going NB you have 33,110LF. Will this be addressed with an addendum? Stationing that look overstated - 864+50SB - 975+00SB (9,183') 975+00SB - 1131+48SB (28,428') 864+50NB - 975+00NB (14,570) 975+00NB - 1131+48NB (33,110') | Correct. The pavement marking quantities for items 646.0881.S and 646.0883.S have been over-estimated. An addendum will be prepared to address this question providing the updated quantity distribution. | Mike Coleman | 1 | 2016-10-24 16:46 | 2016-10-26 13:42
20161108 | 20161108002 | 2 | Removing HMA Pavement Longitudinal Joint Milling | Is placement and removal of the temporary longitudinal joint required at the joint between the driving lane and the 10' shoulder and at the joint between the median lane and the median shoulder? Must temporary joints (in all locations) be placed and removed for both binder and surface course? If yes, it seems that the quantity may be understated for this item. Thank You. | Bid item SPV.0090.03 and 460.4110.S were originally intended to include joint milling/reheating only at the upper layer and at longitudinal joints between lanes. These will be updated via addendum. To provide contractor flexibility in using shoulder closures, the quantity of joint milling will be increased to include the longitudinal joints between lanes and shoulders. This will allow inclusion of the safety edge and subsequent milling if the contractor choses to open the shoulders. The prior assumption was that the shoulders would remain closed or that lane and adjacent shoulder would be paved in the same night. The construction detail on plan sheet 25 will be updated with an addendum currently under development. The current detail depicts the previous practice of milling the joint on upper and lower layers. This detail will be revised to show milling and heating only on the upper layer longitudinal joints. The joint heating quantity will be updated to include all upper layer longitudinal joints. | Scott lawry | 2 | 2016-10-27 12:45 | 2016-10-31 09:55
20161108 | 20161108002 | 2 | 390.0203 Base Patching Asphaltic vs SPV 0180 Concrete Pavement SHES Repair | If I understand correctly Base Patching Asphaltic is to be used only on shoulders and Concrete Pavement Repair is to be used on traffic lanes. In the staging on page 7 of spec's stages 1b and 1c refer to Base patching the median lane, center lane, and outside lane. Should that read Concrete Pavement Repair for those lanes or are we doing some Asphaltic Base Patching on driving lanes? | It would be more clear to state: Stage 1b: Construct median lane, center lane, median shoulder and concrete barrier wall rehabilitation. Stage 1c: Construct outside lane, slope grading and crash wall. The text is meant to state construction is in those areas, but not necessarily all of the exact bid item work that will occur. The miscellaneous quantities and construction details provide the quantity distribution. Base patching is not intended within traffic lanes. | Scott lawry | 3 | 2016-11-01 11:20 | 2016-11-02 11:37
20161108 | 20161108002 | 2 | SPV.0180.01 Cable Barrier Mow Strip, Asphalt | Will the Cable Barrier Posts be driven through the Asphalt Mow Strip or will the posts be installed prior to placement of the Asphalt Mow Strip? | The approved products list for cable barrier in Columbia County lists two systems that both use a footing and sleeve for the barrier post. Therefore the posts should not be driven. It is expected that drilling footings into previously placed asphaltic surface would cause damage to the surface as well as heave the asphalt with the drilling operation. The asphalt surface is intended to be placed after the footings are placed, but prior to placement of posts and cable. | Scott lawry | 4 | 2016-11-01 13:40 | 2016-11-02 11:36
20161108 | 20161108002 | 2 | Shaping shoulders item 305.0500 | I understand the shaping shoulders along the areas of asphalt base patching. Why is there need for shaping shoulders along medians from 825+00 - 985+00 SB and 825+00 - 925+00 NB ? Trying to figure when this shaping would need to be done! | The shaping shoulder bid item provides for two situations. First, it is used to address areas of asphalt base patching where the shoulder is disturbed and requires shaping upon completion of base patching. It is also provided on the median side of the two lane roadways to pull base up next to the lower layer of paving â€“ this is to provide stability and security when traffic is placed on the median lane lower layer for outside lane paving. The median shoulder in the two lane section of IH 90/94 is generally 6â€™ wide which puts traffic close to the edge of pavement during the outside lane paving operation. | Scott lawry | 5 | 2016-11-04 11:25 | 2016-11-04 12:32
20161108 | 20161108002 | 2 | Lane Closures Charts | It appears that the chart on page 9 of specs. and the 1st chart on page 10. of specs are for same time periods and road segments. If so which one is correct? | The chart on the bottom of page 9 is for the northbound roadway. The chart on the top of page 10 is for the southbound roadway. Lane closures are different for northbound and southbound. | Scott lawry | 6 | 2016-11-04 16:05 | 2016-11-04 16:15
20161108 | 20161108003 | 3 | Parapets | Will slip forming of the bridge parapets be allowed? | No, slip forming of parapets is not allowed per standard spec 502.3.1. | Scott lawry | 1 | 2016-11-03 13:18 | 2016-11-03 15:03
20161108 | 20161108005 | 5 | Municpal Specifications for Sewer and Water Construction | There is reference to the Standard Specifications for Sewer and Water Construction in Wisconsin, latest edition, which is fine but the individual special provisions reference Section 33 30 00 of the 2016 City of Columbus technical Standards for Sewer and Water Main Construction. These can not be found in the special provisions and researching on the City's website one finds no reference to these, how does one get a copy of these 2016 City of Columbus Technical Standards? | A COPY OF THE 2016 CITY OF COLUMBUS TECHNICAL STANDARDS CAN BE FOUND AT ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161108005/. IT IS IN PROGRESS OF BEING AVAILABLE FOR DOWNLOAD FROM THE CITY OF COLUMBUS WEBSITE. | Scott lawry | 1 | 2016-10-14 07:02 | 2016-10-21 15:55
20161108 | 20161108005 | 5 | Hughes Street Lift Station | Researching the work involved for the Hughes Street Lift Station , there seems to be considerable information missing. The special provisions refer to the 2016 technical Standards which are not is the specifications and per plans and specifications. The plan while showing the general layout gives no specifics about the pumps, prefabricated enclosure, control panel, scada etc.. Where does one find all this information? | THE INFORMATION MISSING FROM THE PROJECT PLANS AND SPECIFICATIONS IS AVAILABLE IN THE 2016 CITY OF COLUMBUS TECHNICAL STANDARDS. THE FILE CAN BE FOUND AT ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161108005/ | Scott lawry | 2 | 2016-10-14 07:10 | 2016-10-21 15:57
20161108 | 20161108005 | 5 | Soil Boring | Is there Soil borings on this | The soil borings performed for this project design can be located at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161108005/ WisDOT SW Region completed a Soils Report (dated 6-9-14) which includes the soil boring logs. GEI Consultants completed soil borings (dated 12-19-14) for the City of Columbus (Ruekert-Mielke) for the purpose of their sanitary sewer and water main design. | Scott lawry | 3 | 2016-10-18 13:04 | 2016-10-21 16:01
20161108 | 20161108005 | 5 | Asphalt Quantities | Looking at the miscellaneous quantities and bid quantity, the HMA Pavement 4 MT quantity does not include stage 2 subtotal. Will this be corrected in an addendum? | Yes, this will be corrected in an addendum. | Mike Coleman | 4 | 2016-10-27 14:50 | 2016-10-28 10:15
20161108 | 20161108005 | 5 | Bidders List | Where can we get a bidders list for this project? | The contractor's list of plan holders and the contractor's list of approved/eligible bidders are updated/posed 5 times, starting 10 days before the letting. Friday, Monday, Wednesday, Friday, Monday The contractor's list of plan holders and the contractor's list of approved/eligible bidders can be found on the department's HCCI site at the following location for the November 8, 2016 letting (copy/paste into your browser): http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2016/20161108.aspx | Mike Coleman | 5 | 2016-10-27 15:45 | 2016-10-27 16:26
20161108 | 20161108010 | 10 | Stream Bed Medium & Temporary diversion/erosion control | 1. For the stream bed medium item, is the granular backfill part of the item grade 1 or grade 2. In the plan it says grade 2 but in the specials it says grade 1? 2. Is there a detail for the temp diversion / erosion control for the Marathon Co culvert replacement? The plan set contains one for the Portage Co replacement but not the other. If there is no detail what is the thought for a temp diversion for the Marathon Co replacement? | 1. The stream bed medium item will require grade 1 granular backfill. An addendum will not be required/issued as the discrepancy is addressed via 105.4. 2. The Marathon County culvert pipe does not carry an active stream. | Mike Coleman | 1 | 2016-10-27 11:01 | 2016-10-27 11:03
20161108 | 20161108010 | 10 | Asphalt Mix Type | The ESAL's on the plan are 13,000,000 and 17,000,000. Is the MT mix with PG 58-28 S the correct mix type? | 3MT 58-28 S for lower layers, and 4MT58-28S for upper layers are the correct mix types for the project. | Scott lawry | 2 | 2016-11-03 16:23 | 2016-11-04 16:01
20161108 | 20161108010 | 10 | Stream Bed Material | Does the Stream Bed Medium material and 12â€ to 24â€ stones need to be placed continually through the pipes, or is it only needed on the flat aprons of the endwalls? | Per the note on the bottom left of Page 8 of the plans, the Stream Bed Medium shall be placed continually throughout the pipes, the median inlet structure, and the masonry endwall aprons. It should be 8â€ thick through one of the pipes and 12â€ thick through the other. The 12â€ to 24â€ stones are part of the Stream Bed Medium item and are also to be placed inside the pipes. | Scott lawry | 3 | 2016-11-04 16:02 | 2016-11-04 16:03
20161108 | 20161108011 | 11 | Temporary Marking Quantity | In looking at the pavement markings, it appears the temporary marking quantity is higher (double) than what is needed. By putting Same Day Epoxy on the surface in stage 2B as shown in the plans, you would eliminate the need for the temporary marking outlined in stage 2B in the plans. In addition, both the plans and the proposal define pre-stage 1F, stage 1B, and stage 2B as getting temporary and/or SDE placed in the southbound lane after it is milled (1B) and paved (2B) but do not have any included for the northbound lane after it is milled (1A) and paved (2A). What are you going to do to delineate the markings that are removed in the northbound lane after milling and once again after paving? Your timely clarification and, if deemed appropriate, an addendum would be appreciated. Thank you. | 1. In looking at the pavement markings, it appears the temporary marking quantity is higher (double) than what is needed. By putting Same Day Epoxy on the surface in stage 2B as shown in the plans, you would eliminate the need for the temporary marking outlined in stage 2B in the plans--The department will submit an addenda to correct the temporary pavement marking quantity that was described in the first question. 2. In addition, both the plans and the proposal define pre-stage 1F, stage 1B, and stage 2B as getting temporary and/or SDE placed in the southbound lane after it is milled (1B) and paved (2B) but do not have any included for the northbound lane after it is milled (1A) and paved (2A). What are you going to do to delineate the markings that are removed in the northbound lane after milling and once again after paving?--Per Article 4 of the Special Provisions, â€œRoadway elevations between adjacent lanes must be even when opening lanes to traffic at the end of each work day.â€ Article 4 also states, â€œThe contractor may choose to begin with the construction operations taking place on either the NB or SB lane. The stages below describe the construction operations beginning on the NB lane.â€ The intent of the plan is that the contractor must work on segments of the project as stated in the special provisions. If you mill the NB lane from South End to say 2 miles, the SB lane would also need to be milled from the South End to say 2 miles the same day and pavement marking installed to meet the criteria shown in the special provisions so that both lanes can be opened to traffic overnight. That is why pavement marking is only shown for the SB lanes. The only delineation will be the centerline pavement marking on the milled surface. The plan also shows a quantity of Epoxy Pavement Marking 4-Inch to restore the centerline Same Day Epoxy that will get removed during the centerline rumble strip process. | Scott lawry | 1 | 2016-10-26 14:12 | 2016-11-01 16:32
20161108 | 20161108014 | 14 | Aggregate Gradation Question | Special Provision for item SPC.0180.02 Seal Coat Special on page 22 of 23 states the gradation range on the No. 30 Sieve to be 0% passing. Should this say 0% passing?? | It should read be 0-5%. An addenda will be developed to address the issue. | Scott lawry | 1 | 2016-10-18 07:38 | 2016-10-21 15:44
20161108 | 20161108015 | 15 | 305.0110 - 3/4" Base | Is the plan quantity correct for this item? Seems rather high for a 8.65 mile mill and overlay job. Barely coming up with a quarter of the 29,300 tons that the plan states. | After reviewing the quantity for 305.0110 and the calculations that were made, it was realized that some errors existed. These errors were corrected and an addendum has been developed to adjust the plan quantity. | Scott lawry | 1 | 2016-11-02 14:13 | 2016-11-03 12:53
20161108 | 20161108015 | 15 | Traffic Control | The specials read: "Daylight Hours on weekdays" Please verify if Saturday work is allowed as needed, or do we have to be done on Friday? Thank You | WisDOT interprets this to mean paving will be allowed to occur on Saturdays that do not fall within the â€œHoliday Work Restrictionsâ€ listed in Section 5 of the Special Provisions. | Scott lawry | 2 | 2016-11-03 16:23 | 2016-11-04 08:09
20161108 | 20161108016 | 16 | Earthwork Listing | Is it possible for DOT to supply the Earthwork listing by each stage and / or show the staged match lines on the cross sections? | An addendum will be issued adding staged match lines on the cross sections. | Mike Coleman | 1 | 2016-10-10 12:02 | 2016-10-13 10:39
20161108 | 20161108016 | 16 | Culvert Pipe and Storm Sewer Pipe Materials | Effective with the December 2015 lettings, polypropylene and polyethylene pipe have been approved on WisDOT projects under sections 608 and 520 of the Standard Spec. Furthermore, according to paragraph 17.5 under section 13-1-1 of the FDM. The objective of specifying new materials is to take advantage of advances in materials technology. When new materials are approved for use as alternatives to traditional materials, the competitive bidding process is enhanced. Allowing contractors to bid on the basis of total installed cost for several materials should result in the lowest total cost for the storm sewer system. Therefore, it is desirable to allow all materials that meet engineering requirements for the project. Based on the above criteria, we request that the Culvert Pipe Reinforced Concrete Class III items should be changed to Culvert Pipe Class III-B-size items. Also, the Storm Sewer Reinforced Concrete items should be changed to Storm Sewer Class III-B-size items. | An addendum will be issued to change the bid items. | Mike Coleman | 2 | 2016-10-12 13:40 | 2016-10-13 10:40
20161108 | 20161108016 | 16 | Ramp Construction at I-94 | For ramps A, B & C there is work that abuts the existing traffic lanes on I-94. Based on the cross sections starting on sheet 425 it appears that the existing 10' shoulder is being removed and the new pavement will go up to the fog line where the ramps meet I-94. We understand that the work in this area will occur during a lane closure and will likely get filled back in flush prior to the lane closure coming down. However what is the plan for the paving operation? The lower layer is 4 inches once this is completed there will be a 6 inch drop-off along I-94. After the second lift is completed there will still be a 2.5 inch drop-off along I-94. | As per the FDM 11-50, unless there is a 3:1 or flatter taper, the dropoff off will need to be eliminated (paved) in less than three continuous days and nights. | Mike Coleman | 3 | 2016-10-27 10:26 | 2016-10-27 15:33
20161108 | 20161108016 | 16 | HMA | Is the pavement to be completed through the upper layer for each stage or will the upper layer be completed at the end of the project? What areas is the IRI ride expected to apply to? Is there a way to show the limits of the permanent asphalt pavement for each stage and what will be considered temporary pavement; specifically at the ramp intersections and roundabout areas? The typical sections for the ramps show a 4% paved shoulder or to match the drive lane slope when it is greater than 4%. This can be done when the ramp is closed, however it does not work where we are required to pave the ramps 1/2 at a time to keep them open to traffic. The paved shoulders on the existing ramps match the slope of the drive lane the entire length. We would suggest making the shoulders the same slope as the drive lane for future maintenance and constructability. | 1. There will be areas that should not have the upper layer paved until later in the project. 2. STH 128 NB, STH 128 SB. The quantity for these would be 2110. The estimate quantity also includes ramps and side roads, but those should not have been included and will be address with an addenda. 3. There will be revised sheets as part of a future addenda. 4. The department agrees. | Scott lawry | 4 | 2016-10-27 11:56 | 2016-11-01 16:20
20161108 | 20161108016 | 16 | Ramp C 270+15 to 275+15 | On ramp C from 270+15C to 275+15C the typical section shows just 2.5 inches of asphaltic pavement over an "asphaltic base course." It shows this area under the quantities for Removing Asphaltic Surface. Just confirming the plan is to remove the asphalt to the base and then just put down 2.5 inches of HMA for the ramp area between the deceleration lane construction and the roundabout construction? | The intent is to remove 2.5 inches of existing asphalt and replace it with 2.5 inches of HMA. There should be more than 2.5 inches of existing asphalt. The department does not intend to remove all of the asphalt off and only replaced it with 2.5 inches. | Scott lawry | 5 | 2016-10-27 14:36 | 2016-10-31 10:52
20161108 | 20161108016 | 16 | Bore Pipe on Ramp D | On Page 526 it shows bored 36" pipe. Should there be a separate item for this or is it supposed to be included in the 36" RCP price? | This issue will be addressed via Addenda. | Scott lawry | 6 | 2016-10-31 12:14 | 2016-10-31 13:54
20161108 | 20161108016 | 16 | DTM in conjunction with the earthwork stage lines | Would the department be willing to supply the DTM at the same time they supply the stage matchlines? | The surface files can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161108016/ | Scott lawry | 7 | 2016-11-01 11:06 | 2016-11-03 16:00
20161108 | 20161108016 | 16 | Soil Borings | Are soil borings available for this project? | The soil boring information can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20161108016/ | Scott lawry | 8 | 2016-11-03 14:03 | 2016-11-03 15:54
20161108 | 20161108017 | 17 | Prosecution & Progress | Special Provisions Page 6/55. Lane Closure Restrictions. ...The maximum temporary single lane closure shall not exceed 4 miles. Only one lane closure in each direction of STH 29 will be allowed at a time.... Special Provisions Page 3/55. ...The contract time for completion is based on an expedited work schedule and may require extraordinary forces and equipment... Difficult to complete all this in a single 4 mile lane closure. The project is 15.7 miles long with different restrictions on each side of STH 27. We really need to have multiple closures in each direction so more than a single operation can be going at the same time. | Work zones will be held to 4 miles in length. We will issue an addendum that allows up to two separate work zones in one direction but 2 miles must be maintained between those work zones. An addendum will be issued. | Mike Coleman | 1 | 2016-10-12 08:20 | 2016-10-13 10:33
20161108 | 20161108017 | 17 | Traffic Control | Special Provisions 9/55. ... During lane closures access work zone from closed lane. Construction traffic from the work zone must run out of the closed lane unless otherwise approved... Not sure how this works when you have concrete patches excavated or when you have a tack truck ahead of the paving train? Delivery trucks need to merge out of the closed lane into traffic to allow the operations to proceed. | Entering and exiting from a closed lane should occur when work operations allow. There is language that indicates coordination with the engineer can occur when this is not feasible. All trucks entering and exiting live traffic must be done in a safe manner. | Mike Coleman | 2 | 2016-10-12 08:26 | 2016-10-13 10:34
20161108 | 20161108017 | 17 | SMA Pavement | Plan calls for a 4 (12.5 mm) aggregate size. Will the department allow a 5 (9.5 mm) aggregate size? Plan and bid item call for SMA 3.0% Va regression special. Please check on this. Not aware that SMA was under the regression special. | The Department is proposing 12.5mm aggregate size. No change in mix size is planned at this time and it should be bid as shown. The 3.0% Va regression does not apply to SMA. An addendum will be issued to correct this. | Mike Coleman | 3 | 2016-10-12 08:33 | 2016-10-13 10:36
20161108 | 20161108017 | 17 | Asphalt Overlay on Ramps | Typical sections show the ramps with hot mix asphalt overlays will have variable slope. I agree this is how the ramps were originally constructed however it is not possible to pave with hot mix asphalt in this manner and keep the ramp open to traffic. Please confirm the asphalt overlays will be like they have been in the past with the slopes the same and in the same direction? | Changes in cross slope or super elevation are not anticipated. The overlay on the ramps will follow existing cross slopes. | Mike Coleman | 4 | 2016-10-22 10:58 | 2016-10-26 08:26
20161108 | 20161108017 | 17 | STH 29 Mainline Butt Joint and Transition Detail | Detail shows 2" depth for the butt joint. Past experience with SMA over concrete pavement, see IH 94 West of Menomonie, the SMA is not holding up. Other projects where the butt joint depth is greater allowing dense graded hot mix to be left when milling surface butt joint is completed, the SMA pavement has worked out much better. Is it possible to increase the depth of the butt joint to at least 3"? | Yes, this can be increased to 3â€ on the mainline butt joint detail with SMA over concrete. A revised detail will be issued in an addendum. | Mike Coleman | 5 | 2016-10-22 11:05 | 2016-10-26 08:52
20161108 | 20161108017 | 17 | Prosecution & Progress / Staged Construction | Page 4/55. Stage 1 calls for filling outside rumble strips with hot mix asphalt, place temporary wedge joint. In misc qty's there is only 574 tons for the "wedge joint" under asphaltic surface patching, which includes filling rumble strips. It appears that this is not enough quantity to fill rumble strips let alone this temporary wedge joint. Shouldn't typical section for temporary wedge joint on existing outside driveling lane shoulder sheet 26 of the plans show flushing out the hot mix at the edge of existing concrete and continuing across the rumble strip? Would it make more sense to put this quantity as Asphaltic Surface Temporary and keep the asphaltic surface patching item for the patching material used in the prep of foundation for asphalt paving item? | We are not anticipating a temporary wedge joint along the entire project. The quantity reflects the assumption for filling in all rumble strips and addressing spot areas of differential settlement in each direction. The areas will be determined in cooperation with the engineer as noted on the construction detail. | Mike Coleman | 6 | 2016-10-22 11:17 | 2016-10-26 08:53
20161108 | 20161108017 | 17 | Removing Raised pavement markers and filling void? | In the special provisions, it states that Epoxy can be used to fill the voids. Would the DOT really want just Epoxy in the voids, or would it want a filler with the Epoxy? | The material to fill the void can be an epoxy based patch material or HMA pavement specified. The contractor can select the properties of the material(s) and the method for patching. | Mike Coleman | 7 | 2016-10-24 14:14 | 2016-10-27 11:08
20161108 | 20161108018 | 18 | Concrete Sawcutting | Of the 9785 Lf of Concrete Sawing it appears that up to 9000 Lf of that is for removal of lanes, islands, curbs, etc. Would this portion of the sawing be on the joints or in the pavement itself? Thank you. | The exact location for the sawing quantity detailed for â€œcurb and gutter replacementâ€ and â€œturn lane and island repairâ€ will be dependent on the contractorâ€™s staging plan. The design team assumed the curb & gutter would be sawn at the flag of the existing curbâ€¦on a joint. The same is true for the median side longitudinal cuts required for turn lane and island repair. Other saw cuts for pavement repair/replacement will be determined by the field engineer and may be a combination of joint and pavement sawing. The department recommends the sawing contractor discuss with the prime contractor to see how staging is intended. | Scott lawry | 1 | 2016-11-03 12:52 | 2016-11-04 08:02
20161108 | 20161108020 | 20 | Roads Past Crack Sealing Stage | We have concerns on SPV. 0125.03 (Boon Blvd. - ECL) & SPV.0125.08 (USH12 from CTH D â€“ E. Jct. CTH M). There is evident sign of block cracking and rutting fatigue in the drive lanes. We feel that crack sealing would not provide the best return on the dollars for this section of roadway. We would recommend that a scrub seal be performed on this section of roadway to achieve the most return on investment and also minimize future deterioration due to the block cracking and wheel rutting. Also, our experience with large amounts of crack sealant in wheel paths, as required on this roadway creates safety and friction issues for traveling public, specifically motorcycles. | The department is comfortable with the plan and provisions for this project. | Scott lawry | 1 | 2016-10-31 13:11 | 2016-11-02 13:10
20161108 | 20161108020 | 20 | Project length | We are looking for confirmation on the end point on IH94 for the crack sealing project. The sign for black river was found, but could you confirm the end point. Does Perry Creek refer to the cranberry facility. Can we confirm that the mileage is 4.55 miles minus structures. | Perry Creek crosses IH 94 about 1200-ft south of mile marker 120 at the beam guard location. The mileage of 4.55 miles is correct. | Scott lawry | 2 | 2016-11-02 13:15 | 2016-11-02 13:16
20161108 | 20161108021 | 21 | Post Foundation - Reinforcing Steel | Is it a WI DOT requirement to have vertical reinforcing steel rods in the concrete post foundation? | The post foundation needs to follow manufacturerâ€™s recommendation and P.E. stamped approved design. There are 2 general notes on SDD 14 B 52-1a. Provide a Wisconsin Professional Engineers stamped analysis that the line posts and cable barrier end terminal footing are designed for the soil conditions present. The Wisconsin P.E. stamp analysis is to include, but is not limited to: design impact loads, foundation design methodology used, factors of safety, soil type, soil conditions, and temperature ranges. Design line post footings so that the line post footings move less than 1 inch when line post is impacted by a TL-3 small car. | Scott lawry | 1 | 2016-11-02 17:01 | 2016-11-04 08:53
20161108 | 20161108021 | 21 | Cable Barrier Manufacturers on Approved Product List | All 5 cable barrier manufacturers are shown to be approved statewide but in the county listing only two are shown for each county. This project encompasses three counties. Only one manufacturer is shown in the three counties included in this project. Is this project exclusive to that one manufacturer or is this a competitive bid for as many as 5 manufacturers? | Below are the approved products by county. Contractor has choice to use any of the suppliers listed in each county on this project. All for suppliers can be used. If contractor chooses to use 1 manufacturer or all 4, that is up to them. Juneau--Safence, Brifen Sauk--Safence, Cass Columbia--Safence, Nucor/Marion | Scott lawry | 2 | 2016-11-02 17:18 | 2016-11-04 08:06
20161108 | 20161108021 | 21 | Excavation and Base Course | There is no excavation item and new base course is shown under the repairs and replacements. Should it be assumed there will be no excavation and the base course will only be used in low areas? Please explain why there is no excavation. |  |  | 4 | 2016-11-07 12:45
20161108 | 20161108022 | 22 | Bearing Pad Replacement, Allowable Closure duration for STH 80 | In the traffic portion of the special provisions there are a maximum of 4-15 minute full closures of STH 80 allowed for the bearing pad replacement. During this time the structure will need to be jacked, the bearings/sole plates cut out and ground smooth, bearing pads installed, and the bridge lowered. At piers 1 and 3 there are 13 of these bearings to be worked on in this timeframe. The 15 minute closure seems very unrealistic and highly unlikely for the amount of work to be performed here. Would a full night closure of STH 80 be considered? | The 4-15 minute closures are for the jacking process only. Once raised, the bridge will be opened to traffic while bearing replacement takes place. | Scott lawry | 1 | 2016-10-31 12:39 | 2016-11-02 08:21
20161108 | 20161108023 | 23 | Railroad Flagging | Is there any information available on the rates that will be charged by the railroad for flagging and monitoring of the track during the boring? Will the DOT be reimbursing for half of the flagging charges? | The railroad contact listed in Article 7 of the Special Provisions should be contacted for specifics on railroad flagging charges. There will be no reimbursement of the flagging costs so the Contractor needs to bid the work accordingly. | Scott lawry | 1 | 2016-10-31 07:08 | 2016-10-31 11:23
20161108 | 20161108023 | 23 | Pipe and boring information | Page 24â€“Please confirm that installation of carrier pipe may be done using wood blocking or factory fabricated spacers. We would prefer wood as it gives us easier adjustment within the casing. RCP pipe comes in 8â€™ lengths so three spacers per pipe is a bit much. Page 24-The casing pipe (if required) will need to be 60â€ minimum (OD of 36â€ RCP is 51â€ + 2â€ all around = 55â€, ID of 60â€ casing is 58â€). E-80 Loading for 60â€ casing calls for a wall thickness of 0.750 when pipe is bare and 0.688 if coated (see attached chart). Spec mentions 9/16â€ or 0.562 wall which would be insufficient per railroad requirements. My experience is to install 0.750 wall or greater. My question is can I go ahead and price out this project for 0.750 wall and no coating? We find that the coating gets scratched up pretty good during the installation anyway. | 1. Page 24â€“The specification under B. Materials, allows for wood blocking or factory fabricated spacers. 2. Page 24-The specification states the minimum thickness for the casing pipe shall be 9/16 inches and be according to E-80 loading. | Scott lawry | 2 | 2016-11-02 11:45 | 2016-11-02 11:46
20161108 | 20161108023 | 23 | Pipe and Boring | Page 25-Spec calls for boring and Jacking at a minimum of 30â€™ from centerline of track. The bid quantity in the proposal is 85LF. How much casing do you want installed? Will some be laid in the boring and receiving pit? Will the casing pipe laid in the pits be paid at the same price? What if the general decides to open cut without casing? My cost for 60â€ steel casing pipe will in the neighborhood of $400.00LF and I need some clarification on this item. In addition we have other costs, such as mobilizationâ€¦..do I divide that cost by 60LF installed or 85LF? Do you have a geo tech report in the location of the Jack & Bore? Have you heard of slick boring and would you consider it in lieu of a 60â€ casing? Slick boring is best described as auger boring a steel casing slightly greater than the OD of the RCP. Once installed to line and grade we would push it out with the RCP. The casing gets pushed out fully and is cut off in generally 20â€™ lengths. | Page 25 -The specification states to "Locate boring and jacking pits at a minimum of 30 feet from the centerline of track". Therefore a minimum of 60 of boring and jacking is required but due to construction means and methods additional bid quantity up to a total of 85 LF is provided. The boring and jacking contractor shall coordinate means and methods with the general contractor and submit their bid accordingly. There is no Geo Tech Report in the location of the Jack & Bore The boring and jacking shall be bid in accordance with the project plans and special provisions. | Scott lawry | 3 | 2016-11-02 11:50 | 2016-11-02 11:53
20161108 | 20161108023 | 23 | Storm Sewer - Class IIIB | Per the village of Woodman they would approve the use of CLASS IIIB Storm Sewer in-lieu of Class III. Regarding the Class IV Specified would WisDOT also consider using Class IIIB Storm Sewer? Based on proposed cover heights it appears they are in acceptable range for Class IIIB. | The storm sewer should be bid based on the items currently in the plan and proposal. The contractor shall prepare their bid accordingly. | Scott lawry | 4 | 2016-11-03 09:11 | 2016-11-04 16:16
20161108 | 20161108024 | 24 | Temporary Markings | I am curious as to why there is a set price for the temporary paint markings on this project. We have not seen that before and, with the number of trips required to do this work, the set price may or may not cover the cost to do this. Thank you for your time. | This was an error and will be corrected via addenda to remove the fixed price. | Scott lawry | 1 | 2016-11-01 15:03 | 2016-11-01 16:25
20161108 | 20161108025 | 25 | Pavement Marking | 1. There is no bid item for the 4 â€œYieldâ€ pavement marking words around the roundabout, is this correct? 2. There is a conflict between the plans and quantities for bike symbol marking. The quantities call for 12, but the plans only show 6. | 1. That is correct, the item is missing from the quantities. 2. That is correct, there should only be 6 bike symbols, not 12. A future addendum will be processed to address these. | Mike Coleman | 1 | 2016-10-18 07:04 | 2016-10-18 07:09
20161108 | 20161108025 | 25 | Added Addendum | I do not see where the additional item 647.0356 has been added to the revised EBS File. I have downloaded it twice and it is not after 647.0336. | Please checked the file downloaded was the EBLib file. The item 647.0356 is located at the bottom of the list of items, not in numerical order. | Scott lawry | 2 | 2016-11-04 14:03 | 2016-11-04 14:38
20161108 | 20161108027 | 27 | Asphalt Mix Type | The designer has LT mix designed. The last time this was paved I think it was E10. With the Flambeau River Paper Mill being there and the trucks turning movements, wouldn't a MT or HT be designed. | We have reviewed the pavement design information and will adjust the asphalt mix type to an MT. An addendum will be issued to resolve this. | Mike Coleman | 1 | 2016-10-19 17:12 | 2016-10-20 11:07
20161108 | 20161108027 | 27 | Paper-making equipment | Is there any information on what type of "Paper-making equipment" is of concern? What is the make & model of the equipment, the location of the equipment in relation to the construction work, and if there are any vibration specifications for the equipment found in the manual. Any help obtaining this info would be much appreciated. Depending on the specs on the equipment there may be a significantly different scope of work than what would be considered typical for vibration monitoring. | Questions related to Flambeau River Papers facilities or equipment can be directed to mill maintenance supervisor Bill Hilgart (office 715-762-5393 or cell 715-493-3725). | Mike Coleman | 2 | 2016-10-26 08:20 | 2016-10-26 08:21
20161108 | 20161108027 | 27 | Geotechnical Report | Can we get a copy of the full Geotechnical Report? | A copy of the Geotechnical Report will be posted to the HCCI site. A copy of the Geotechnical Report can also be emailed upon request. Please contact Mike Grage at 715-365-5705 or michael.grage@dot.wi.gov | Scott lawry | 3 | 2016-10-28 14:25 | 2016-10-31 10:57
20161108 | 20161108027 | 27 | River Access/Pier Access as it relates to Contaminated Sediment and Water | Article 10 on page 11 of the special provisions, it appears the 404 permit was issued based on the contractor utilizing barges to access the pier construction and set beams. No additional work platforms in the river were included in the permit When reviewing article 60 beginning on page 87, it appears the designer, COE and DNR have ruled out the use of any type of causeway in lieu of barges due to the contaminated materials and the volume of material that would be generated by using a causeway. Has it been verified that there is enough water to float to access the piers and set beams. If not, dredging may be required also increasing the volume of contaminated materials and making containment of the contaminated water nearly impossible. Is it therefore, a requirement of this project to utilize barges only to construct this project in light of the contaminates soils/water issue? | The intent of the special provisions was not to rule out any construction methods or require a contractor to use barges only. Contractors will have to determine what they feel is the best construction method and do the necessary coordination. The depth of water was reviewed and anticipated to be enough for barges without dredging, but that should be verified by the contractor, and the use of a causeway was not ruled out and would be up to the contractor to have this method properly permitted | Scott lawry | 4 | 2016-11-01 14:13 | 2016-11-02 11:31
20161108 | 20161108027 | 27 | Material Availability | The Special Railing Pedestrian Steel item calls for 2" x 1 1/2" x 3/16" steel tubing and in speaking with multiple steel suppliers, this size is not available. Please confirm that 2" x 1 1/2" x 1/8" steel tubing is an acceptable alternative. | This material has been used on previous projects without issue and appears to still be available. We do not intend to accept a thinner material as an acceptable alternative. | Scott lawry | 5 | 2016-11-02 13:07 | 2016-11-02 14:42
20161108 | 20161108027 | 27 | Follow up to question 4 - River | Upon receiving the response to question 4, we verified the water depths and determined the water depths inadequate to float barges to construct the east pier without dredging or utilizing a causeway. If dredging is utilized, will item 1660 - SPV.0195 Special 01. Excavate, Haul and disposal of contaminated sediment and dewatering of contaminated sediment be utilized to handle the dredged material? If a causeway is utilized, will the causeway material be treated as contaminated sediment since it will mix with the river sediment when removed? If so, would item 1660 also be utilized to handle the removal of the causeway materials? | The item of â€œExcavation, Hauling, and Disposal of Contaminated Sediment and Dewatering of Contaminated Sediment, Item SPV.0195.01â€ is intended to be used for the removal of the existing bridge abutments and piers and placement of the proposed abutment, piers and riprap. Any contaminated sediment disturbed through other contractor operations, such as dredging or causeway construction/removal, is the responsibility of the contractor and handling and disposal of this sediment should be coordinated appropriately with WDNR and the US Army Corps of Engineers. An emergency addenda will be coming shortly to clarify this issue within the special provisions. | Scott lawry | 6 | 2016-11-04 14:50 | 2016-11-07 13:08
20161108 | 20161108028 | 28 | Bridges to be cleaned / painted | Cover of proposal & plans shows (4) four bridges (B-37-179, 180, 181, 182) but bid sheet shows only Bridges (B-37-179, 180, 181). Which is correct (3 or 4 bridges)? | The documents appear correct. There bridges have the following general work types as shown in further detail on the structure plan sheets: â€¢ B-37-179 o Painting and Reseal Slope Paving â€¢ B-37-180 o Painting and Reseal Slope Paving â€¢ B-37-181 o Painting and Reseal Slope Paving â€¢ B-37-182 o Reseal Slope Paving Only The text string â€œB-37-182â€ does not appear in the bid form since there are no items associated with B-37-182 that have a supplemental description. The only item associated with B-37-182 is the reseal slope paving which does not include the bridge number text. | Mike Coleman | 1 | 2016-10-27 13:20 | 2016-10-27 16:06
20161108 | 20161108029 | 29 | Crash rated temp sign support detail | Do you have a WZ cert # or a MASH cert # for this design? It is not in the proposal or plans. There are usually torque and weight minimums/maximums. | The department will be obtaining the necessary certifications. The detail on page 12 will be revised via addenda to address the sign is to be Mounted on the temporary sign support as depicted on the detail drawing. | Scott lawry | 1 | 2016-10-07 16:22 | 2016-10-25 17:51
20161108 | 20161108029 | 29 | RS-1 or RS-2 Tack | Page 2 of the plan set states that wherever Asphaltic Concrete Pavement abuts PCC that RS-1 or RS-2 shall be used. My question is can a CSS-1H be used since we are only talking about the vertical faces that abut the concrete and the quantity will be less than 20 gallons? Also, if that is not an option can a CRS-2 be used? | Materials listed under Standard Specification 455.2.5 and CRS-1 and CRS-2 are also allowed. | Scott lawry | 2 | 2016-10-31 15:44 | 2016-11-02 12:54
20161108 | 20161108029 | 29 | Joints and Joint repair for Structures B-69-15 and 16 | On sheets 237and 245, the plan view shows joint repair only at the east abutment on both structures. Sheets 238/239 and 243/244 appear to indicate joint repair at both abutments. Since Expansion Joints are bid as a Lump Sum, could you please clarify if there is joint repair at one or both abutments on these structures. | Both Joints at both structures are to be repaired. The note on page 237 and 245 is followed by â€œ- TYP.â€ Indicating that it is a dimension for both joints. | Scott lawry | 3 | 2016-11-01 12:21 | 2016-11-07 09:54
20161108 | 20161108029 | 29 | Asphalt Binder | Is 58-28S the correct binder for HMA Pavement 4HT on this project or should it be 58-28H? |  |  | 4 | 2016-11-01 15:22
20161108 | 20161108030 | 30 | Retaining Wall Excavation | R-66-37 & 38, a note has been added stating no disturbance behind back of wall beyond 5'. If shoring is required for construction, can the tie backs or soil nails extend beyond 5' or is that considered disturbance? | The intent is that the existing ground surface not be disturbed beyond 5' behind the wall. Soil nails or other tie back methods that do not disturb the existing ground surface and remain within the right of way is acceptable. | Mike Coleman | 1 | 2016-10-05 15:11 | 2016-10-06 07:40
20161108 | 20161108030 | 30 | R-66-36 | Can you provide a dimension along this wall from the front face (or back) to the right of way? | The dimensions requested for R-66-36 are shown on sheet 543 of the plan. | Mike Coleman | 2 | 2016-10-25 21:51 | 2016-10-26 10:13
20161108 | 20161108030 | 30 | Sign Bridge Design Question | Should the sign bridges be designed with AASHTO 2001 or 2013 standards. | Use the AASHTO 2013 standards. Signs should be centered over the lanes as noted. Dimensions provided for bidding purposes only in a document posted at the following location (copy/paste into web browser): ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/3360-09-72/ | Mike Coleman | 3 | 2016-10-26 14:58 | 2016-10-26 15:02
20161108 | 20161108030 | 30 | Pavement Removal | Why is removing pavement shown for stations 1464+00 to 1473+00 in the removing pavement chart on page 288? | The 1600 SY of Removing Pavement shown on sheet 288 is not correct. This area is accounted for and will be paid as Removing Asphaltic Surface Milling and correct via addendum. | Scott lawry | 4 | 2016-10-28 10:20 | 2016-10-31 11:21
20161108 | 20161108030 | 30 | Line item 2790 SPV.0060 Sp09 Grooved Preformed Thermoplastic Yield Line 18 inch has 4 each | Shouldn't this item be paid by the linear foot instead of each? | The item SPV.0060.09 Grooved Preformed Thermoplastic Yield Line 18 inch will be paid by each unit, acceptably placed according to the detail shown in the plan and at the locations listed in the miscellaneous quantities. | Scott lawry | 5 | 2016-11-03 08:49 | 2016-11-03 15:49