## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170110 | 20170110001 | 1 | Storm Sewer Bid Items | Is there a reason storm sewer pipe Class III was used vs. storm sewer pipe Class III-A or Class III-B? The culvert bid items are specified as Class III-A, but the storm sewer pipe is not. Would the DOT permit the use of Class III-A or Class III-B storm sewer pipes? | An addendum will be developed to deal with this issue. | Scott Lawry | 1 | 2016-12-16 13:49 | 2016-12-21 08:14
20170110 | 20170110004 | 4 | Error in bid quantities - structure | Estimate of quantities on the bridge plans appear to be what was used to generate the schedule of prices. The abutment quantities calculate out to significantly less then the estimate of quantities schedule. Also the abutment piling in the estimate of quantities suggest that pile length is 75'. 7 ea @ 75' = 525'<in estimate of quantities/schedule of prices. Abutment notes say 7 pile @ 70 ft. Please verify quantities. | An addendum will be developed to address the quantity discrepancies. | Scott Lawry | 1 | 2016-12-19 14:33 | 2016-12-21 10:41
20170110 | 20170110005 | 5 | Storm Sewer Bid Items | Is there a reason storm sewer pipe Class III was used vs. storm sewer pipe Class III-A or Class III-B? Would the DOT permit the use of Class III-A or Class III-B storm sewer pipes? | The City of Janesville requires the use of Reinforced Concrete Pipe in accordance with their specification, so Class III-A and Class III-B bid items would not be acceptable. | Scott Lawry | 1 | 2016-12-16 13:52 | 2016-12-20 14:52
20170110 | 20170110006 | 6 | Storm Sewer Backfill Requirements | Are there borings that can be referenced for this project to see if the onsite material is suitable for the new 2017 storm sewer bedding requirements? | The soils report is posted at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170110006/ | Scott Lawry | 1 | 2017-01-04 15:35 | 2017-01-06 12:18
20170110 | 20170110007 | 7 | Pipe Grates for Apron Endwalls | On page 8 of the plan, on the erosion control sheet, there is a Remark in the "Storm Sewer System 1" table stating "Pipe Grate Required". On page 20 in the "Storm Structures" section of the miscellaneous quantities are a total of 4 Apron Endwalls for Culvert Pipe - 24 inch. There is no note requiring Pipe Grates. Will Pipe Grates be required for the 1 - 15" AEW and the 4 - 24" AEW or only the 15" AEW as the plan implies? Also, is the Pipe Grate to be considered incidental to the Apron Endwall, or will a bid item be added? | The Designer is working on an Addendum to address this issue | Scott Lawry | 1 | 2017-01-03 10:17 | 2017-01-04 12:40
20170110 | 20170110007 | 7 | Concrete pavement approach slab | I do not see a detail for the concrete pavement approach slab. I am assuming that the structural approach slab and the associated footing will be paid under the bar steel and concrete masonry bridges items? I am also assuming that the concrete pavement approach slab is intended to follow the standard detail for reinforcement? Please provide a detail for the concrete pavement approach slab for this project. Thank you. | The proposal includes bid item 415.0410, Concrete Pavement Approach Slab, at 166 SY. This item includes all necessary materials necessary to complete the work. An addendum will be developed to add the standard detail for this item as well as several others. | Scott Lawry | 2 | 2017-01-06 11:54 | 2017-01-06 13:41
20170110 | 20170110007 | 7 | 12 1/2" Concrete Pavement | Regarding the 12 1/2"â€ Concrete pavement item (the sidewalk), Will this pavement require reinforcement? Will the walk be tied to the back of curb? No detail is noted about this unique situation. Section 415 refers to dowels but specifically section 415.3.5 states â€œReinforce the concrete if and as the plans specifyâ€. | The Concrete Pavement 12 1/2", Item #415.0125 shall be Dowelled. The Curb & Gutter, 18â€ Type D, Item #601.0407 shall be tied to all adjacent Concrete Pavements including all Approach Slabs. | Scott Lawry | 3 | 2017-01-09 11:47 | 2017-01-09 11:49
20170110 | 20170110008 | 8 | Soils Borings | Are there any soil borings available for the project? | The soils report can be found at the folder below ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170110008/ | Scott Lawry | 1 | 2016-12-15 08:40 | 2016-12-15 12:52
20170110 | 20170110008 | 8 | Salvaging existing materials to be used as base | In past DOT projects we were allowed to salvage existing base (concrete, asphalt, base aggregate & curb) to be processed to a useable form for new base. We have also been allowed to pulverize the existing asphalt and base and use it as base material. Will this be allowed on this project? | Please bid according to Section 305 Dense Graded Base of the 2017 Edition of the Standard Specifications for Highway and Structure Construction. | Scott Lawry | 2 | 2017-01-04 09:06 | 2017-01-04 09:08
20170110 | 20170110008 | 8 | U.S. Army Corp of Engineers Section 404 Permit | Is a copy of the U.S. Army Corp of Engineers Section 404 Permit available for this project? | A copy of the file has been posted at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170110008/ and on the NE preliminary plans page. | Scott Lawry | 3 | 2017-01-04 13:11 | 2017-01-04 14:22
20170110 | 20170110008 | 8 | Railroad Insurance | In the project documents the subject project identifies Railroad insurance. I know that there is an old railroad through the project limits which is now a bike path. Do we really need railroad insurance? | See Article 9 on Page 19 of the Special Provisions. Railroad protective liability insurance coverage or Commercial General Liability certificate of insurance, with the stipulations in this article, needs to be provided. | Scott Lawry | 4 | 2017-01-04 14:00 | 2017-01-04 14:01
20170110 | 20170110008 | 8 | Existing Retaining Wall | On Sheet 20 of the plans for the Retaining Wall. In the Retaining Wall Notes it references an existing retaining wall built on the Northeast Quadrant of Pioneer Road and Hickory Street. Do you know the manufacturer of the existing wall? | The existing wall is a VERSA-LOK wall that was manufactured by Willow Creek Concrete Products, Inc. | Scott Lawry | 5 | 2017-01-06 10:22 | 2017-01-06 10:25
20170110 | 20170110008 | 8 | Traffic Control | -With the addendum does this require that all four legs of the intersection need to be maintained to local traffic? -Will local cross traffic be allowed on Military Rd. and CTH VV at the intersection? | Answer: At times all four legs at various locations will be maintained to two-way local traffic depending on the location and what is written in the Special Provisions. Answer: Two way local traffic along Military Road (including through the intersection of Pioneer Road) shall be maintained at all times except for the 60 day closure along Military from 450â€™NBâ€™+00 to 457â€™NBâ€™+84. During the closure on Military Road, two way local traffic shall be accommodated along Pioneer Road (including through the intersection of Military Road). Two way local traffic shall also be maintained along Military Road from the southwest project limits to Pioneer Road at all times. | Scott Lawry | 6 | 2017-01-06 10:31 | 2017-01-06 10:31
20170110 | 20170110011 | 11 | Infrasence infrared deck scan | Does the department have the Infrasence infrared deck scan report available? | Contractors can request a copy of the report by contacting Dan Erva at 715-365-5776 | Scott Lawry | 1 | 2017-01-03 10:37 | 2017-01-03 10:37
20170110 | 20170110011 | 11 | Staging | The plans do not show traffic control/staging details for B-58-93. Will details be provided? | No special traffic control details are needed at this structure so the contractor should use the standard detail drawings for their traffic control at this structure. | Scott Lawry | 2 | 2017-01-03 15:52 | 2017-01-05 08:46
20170110 | 20170110011 | 11 | 28 day Cure Period/Working Day Assessment | During the required 28-day curing period after deck patching that is needed for the polymer overlay placement, will the contractor be assessed working days? Or, will the curing time be considered a contract-identified, non-working day during the construction season, which is excluded from working day assesment? | The contractor will be assessed working days. | Scott Lawry | 3 | 2017-01-03 15:59 | 2017-01-05 08:41
20170110 | 20170110011 | 11 | Item 0290 - Cement Slurry Mixture | Ready Mix suppliers and not willing to haul the specified mix design for the item 0290 - Cement Slurry Mixture, as it's close relation to a bentonite seal, which would cause damage to their mixers. Will the Department allow alternates such as a grout mix and polyurethane, which have been proven methods to accomplish the same type of work? | The Cement Slurry Mixture is intended to be a mud jacking material for raising the concrete shoulders. SPV.0035.01 is directly tied to the item SPV.0060.01, 0035.01 provides the material (cubic yard) and 0060.01 provides for the placing at specific locations (each). Typically the material is mixed on site as needed, and we would not entertain an alternate material without proof of meeting the intent of the original material, and a formal mix design. | Scott Lawry | 4 | 2017-01-09 07:31 | 2017-01-09 11:46
20170110 | 20170110012 | 12 | Missing Station to Station Listing | The plan is missing the station to station listing for stage 2/4 STH 54 (from station 1243+00 - 1252+00). Is this available? | The information is available for the earthwork data sheets and an addendum will be sent out to add the table to this plan. No changes to the earthwork summary shown in the miscellaneous quantities are anticipated. | Scott Lawry | 1 | 2016-12-15 16:08 | 2016-12-20 14:54
20170110 | 20170110012 | 12 | Pipe Bid Items | Based on cover heights, ADT, and diameter range, Class III-A or Class III-B culverts should have been specified in lieu of corrugated metal per updated FDM. Furthermore, the project is in a county with soils known to be highly corrosive. http://wisconsindot.gov/rdwy/fdm/fd-13-01-015att.pdf#fd13-1a15.1 Would the DOT allow the use of Class III-A or Class III-B culverts? Based on same cover heights, ADT, and diameter range, Class III-A or Class III-B storm sewers should have been specified. Would the DOT allow the use of Class III-A or Class III-B storm sewers? | An addendum will be issued to address the locations where alternative pipe products would be acceptable. | Scott Lawry | 2 | 2016-12-16 14:17 | 2016-12-23 12:28
20170110 | 20170110012 | 12 | Depth of the existing aspahlt. | Is there a boring log available for this project? | Borings logs and information prepared for the design of these projects can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170110012/ One file includes pavement cores and borings completed along the existing STH 54 alignment. Depth of the existing asphalt and base thickness are included in this information. The second report contains boring logs and marsh probe depths for the proposed alignment located in areas that are off-alignment from the existing roadway. | Scott Lawry | 3 | 2016-12-16 16:54 | 2016-12-23 13:36
20170110 | 20170110012 | 12 | Select Borrow | Is there any reason why the undistributed select borrow quantity could be eliminated. We see Note # 9 in the earthwork summary, but if the cross sections and marsh quantities are correct per the plan why such a unaccounted for, undistributed quantity. | Based on geotechnical investigation, marsh hand probes were conducted in various locations to determine marsh depth and were based only on resistance to probe advancement. Field staff completing the probes indicated depths could be deeper or shallower than estimated, and indicated the depths could vary away from the exploration location. The undistributed quantities are included to account for these variations. The project team will be reevaluating the undistributed quantity and including necessary revision in a forthcoming addendum. | Scott Lawry | 4 | 2016-12-20 10:28 | 2016-12-22 14:28
20170110 | 20170110012 | 12 | grading | How are all the off station existing road going to be handled? Will it be paid Obliterate Old Road? | To further clarify the response below: All road removal areas for projects 6950-03-73 and 6950-03-75, other than School Lane, will not be paid as Obliterating Old Road. On project 6950-03-73, the existing STH 54 roadway will be remaining as a town road between Lonesome Road and Old STH 54. Modifications of the existing roadway at these intersections fall within the grading limits of the proposed roadway and is address through the earthwork grading. On project 6950-03-75, the cross sections and grading have been extended to remove the old roadbed and include this material in the earthwork (Sheets 177, 189, & 197). The only area of obliterating old roadway falls along a section of School Lane. | Scott Lawry | 5 | 2017-01-09 08:23 | 2017-01-09 10:28
20170110 | 20170110012 | 12 | grading | So we can assume all the existing asphalt and dirt can be used in the fills? | Contractor should use materials obtain within the project limits and from other bid items in the fills to the extent practical as noted under Standard Specification 208.2.2. | Scott Lawry | 6 | 2017-01-09 10:35 | 2017-01-09 12:01
20170110 | 20170110013 | 13 | Common Excavation | 1.) The quantity for common excavation for the west crossover is 380 CY. The typical calls for 8â€ Base Ag 1 /4â€ and then 6â€ of HMA. The HMA surface would need to be flush with the existing concrete roadway. So, would we need to cut out the 14â€ plus an additional 6â€ because the median grade is higher with the curb and gutter in there? Just rough numbers with a 20â€™ wide median would be 340 CY. 2.) How is the removal of the west crossover being paid? The east crossover is getting removed and paid under removing asphaltic surface. Is the west crossover removal being paid under the common ex bid item? Is the common ex quantity correct? | 1.) Yes, you would need to cut the 14â€ for the base aggregate and HMA plus the additional 6â€ depth behind the curb and gutter. 2.) The west crossover removal will be paid under removing asphaltic surface. | Scott Lawry | 1 | 2017-01-03 10:30 | 2017-01-03 10:31
20170110 | 20170110013 | 13 | Borrow and Concrete Approach Slabs | 3.) Once the HMA is removed on the west crossover, the grade will be 6â€ lower than the pavement across that section. The plans call for 6â€ of salvaged topsoil to be placed but that would only get you flush with the adjacent pavement. Would borrow be needed to raise the grade of the median so the grade is flush with the top of the curb and gutter? 4.) On the USH 12 approach slab replacement, can you confirm that this needs to be done under traffic, half at a time? | 3.) You are correct. Borrow will be needed to get the median grade flush with the top of the curb and gutter. An addendum will be developed to address this issue 4.) Yes, approach slab replacements will be done half at a time utilizing single lane closures. | Scott Lawry | 2 | 2017-01-03 10:32 | 2017-01-03 10:33
20170110 | 20170110013 | 13 | Bearing Maintenance B-27-45, Item SPV.0060.03 | Article 23 in the special provisions C.1 States to completely remove the anchor bolts in the abutments. Is the intent to remove the existing anchor bolts in the abutments? Item C.1 also states " As given in the plans, use new anchor bolts to reinstall masonry plates after cleaning and painting." This appears not to be addressed in the plans, please advise. | The intent of the plan set is to remove and replace the bearing under girder 1 at the east abutment, and to remove/clean/paint/replace the existing bearings at all other girder bearing locations at the east and west abutments. The quantities table in the plans dictate that the existing bearing at the east abutment under girder 1 is to be removed and replaced with a new expansion bearing via the use of the bid item â€œ506.6000 Bearing Assemblies Expansion B-27-45â€. The quantities table in the plans dictate that the other bearings undertake maintenance via the bid item â€œSPV.0060 Bearing Maintenance B-27-45â€. There are no plan details showing the removal, cleaning, and painting of the existing bearings that are to be reused. However, on plan sheet 5 of the structure plan set, there are notes in the â€œMasonry Plate Dâ€ detail that show the location of new anchor bolts to be used in the existing bearings as compared to the location of the existing anchor bolt holes. For the existing bearings that will be reused, the contractors have the option of either burning of the existing anchor (per the â€œExpansion Bearing Removalâ€ detail in the lower left corner of page 5 of the structure plan set) or fully removing them per C.1 of SPV.0060. | Scott Lawry | 3 | 2017-01-06 10:57 | 2017-01-06 13:37
20170110 | 20170110013 | 13 | Temporary Precast Concrete Barrier, Delivered | Is the quantity for the delivered quantity overstated? Based on staging, wouldn't the barrier brought out for stage 1 then be utilized in stage 2 resulting in the quantity for delivered going from 2,450 LF to 1,225 LF? | Per standard spec 603.3.2.2 delivery is paid any time the barrier is to be loaded on a truck, transported to another work site on the project, and unloaded. In our determination of quantities, we assumed that the barrier would need to be loaded and reset for each stage of work to maintain one lane of traffic at all times. | Scott Lawry | 4 | 2017-01-06 11:27 | 2017-01-09 10:11
20170110 | 20170110014 | 14 | HMA | The project is requiring an LT mix. There are two active limestone quarries on the project that use CTH Q as their primary haul road leading to IH 94. The first quarry is on 640th Ave (Sta. 227+75) and the second in located directly on the project with the entrance to the quarry at station 201+00. With CTH Q -> I-94 being the primary haul route to both of these locations would a MT mix with a stiffer binder such as 58-34H or 58-34V be better for this section? | There will be a change the pavement design for the segment of CTH Q from 630th to the north end of the project. The revised design for this section will be 4.5â€ HMA [2â€ upper layer 4MT 58-34H, 2.5â€ lower layer 3MT 58-28H] over 6â€ pulverized and re-laid pavement. A formal addenda will be issued for this change. | Scott Lawry | 1 | 2016-12-21 08:04 | 2016-12-22 14:31
20170110 | 20170110014 | 14 | Select Crushed bid item quantity | What is the intended use of the Select Crushed bid item quantity? | An addendum will be developed to address this issue. | Scott Lawry | 2 | 2017-01-03 14:40 | 2017-01-04 09:09
20170110 | 20170110015 | 15 | LT Mix | The project has LT mix specified. From STH 37 to the West there is a considerable amount of truck traffic down to the Red Flint driveway. Along with the local businesses, Short Street is a designated truck route for the City of Eau Claire. Due to the traffic in this area it may be better to look at a MT mix. It may also be beneficial to look at the asphalt binder in the surface and use a 58-34H instead of the 58-34S. | The designer and the City is comfortable with the project as designed. | Scott Lawry | 1 | 2016-12-20 10:13 | 2016-12-23 12:30