## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170214 | 20170214001 | 1 | Expansion joints on bridge # B-41-84 | Are both the North & South expansion joints being replaced on this bridge. Drawings do not show North expansion joint Highlighted. South expansion joint says (both Joints). | Both joints are being replaced. Please see page 77 of the plans, or page 3 of 4 of B-41-84 structure plans. This page provides details for the expansion device and clearly shows quantities for both the north and south abutments. | Scott Lawry | 1 | 2017-02-13 14:40 | 2017-02-13 16:26
20170214 | 20170214003 | 3 | pouring piers | Can the pier footings be poured under water? | Yes, the pier footings can be poured under water. The plans call out â€˜combined footing/sealâ€™ for the pier footing (pages 10-13 of structure plan). | Scott Lawry | 1 | 2017-02-09 14:42 | 2017-02-10 13:49
20170214 | 20170214003 | 3 | Pier footing elevations | The plans show the bottom of footing 4 ft below refusal according to the borings. If the sheeting for the cofferdams cannot be driven to the bottom of planned footing depth will the Dept. allow the elevation of the bottom of the footing to be raised? | The piers are to be supported on sound material with a factored bearing resistance of 10 tons per square foot. If this is encountered higher than shown on the plans, raising the footing depth would be considered. If it is encountered lower than plan, the footing will be made thicker. However, it is not expected that sheet piling will work at this site. Some other cofferdam method will probably be required. The pier footings are designed as combined footing/seals. The footings can be poured under water. Once the footings are in place, the pier shaft pour will need to be dewatered. | Scott Lawry | 2 | 2017-02-10 13:24 | 2017-02-10 14:23
20170214 | 20170214003 | 3 | Pier Footings Elevations | The plans show the bottom of footing appx. 4ft below refusal, according to the borings. If the cofferdam sheeting cannot be driven to the bottom of footing elevation shown in the plans will the Dept. allow the bottom of footing elevation to be raised? | The piers are to be supported on sound material with a factored bearing resistance of 10 tons per square foot. If this is encountered higher than shown on the plans, raising the footing depth would be considered. If it is encountered lower than plan, the footing will be made thicker. However, it is not expected that sheet piling will work at this site. Some other cofferdam method will probably be required. The pier footings are designed as combined footing/seals. The footings can be poured under water. Once the footings are in place, the pier shaft pour will need to be dewatered. | Scott Lawry | 3 | 2017-02-10 13:28 | 2017-02-10 14:23
20170214 | 20170214007 | 7 | Painting sheet piling | Please confirm that the sheet piles need to be painted front and back as called out in the general notes on sheet 1 of the retaining wall plan. | The sheeting piling should be painted as stated in the plans. The painting limits of the piling will be as per standard specification 550.3.11.3.(1) Paint steel piles that are exposed in the completed work from the top of the pile to 4 feet or more below the streambed or ground line. Ensure that painted areas are fully cured before driving. | Scott Lawry | 1 | 2017-01-24 13:20 | 2017-01-24 13:26
20170214 | 20170214007 | 7 | Sheet Piling | Q1â€”Sheet piling connectionâ€”There is a detail on page 58 of the plans that shows Section A-A. It states â€œShear connection between piling steel sheet permanent panels (Typ.). Connection to develop sheeting shear capacityâ€. What is this detail trying to tell the contractor/supplier? Q2â€”Will flaggers be allowed during the installation of the sheet piling? There is not enough room to stage a crane on the shoulder of the road after the existing wall is removed to allow for two lanes of traffic during the installation. | A1â€”the detail is intended to convey that the piling are connected to act as a single wall. Most sheet pile sections are manufactured to interlock or connect to adjacent piles, that connection should be sufficient. A2â€”How the contractor utilizes that space to construct the wall is part of the means and method to construct the project and if it varies from the plan it should be proposed to the engineer for their approval prior to beginning work. It would be acceptable to reduce the width of the traffic lanes at the location of the site and use flaggers to monitor the traffic during this operation, however the traffic control layout in the plans would need to be restored for nighttime hours (7 PM â€“ 7 AM). Addendum #1 was issued on February 9th to allow the reduction of the lanes for nighttime hours to two-11' lanes. | Scott Lawry | 2 | 2017-02-10 15:58 | 2017-02-10 16:06
20170214 | 20170214009 | 9 | Bridge Railing Modification - Cleaning Railing Posts | In the special provisions article 22 for Bridge Railing Modification it states that payment is full compensation for preparing and cleaning the railing posts; etc. What is being required for preparing and cleaning railing posts? Is each post need to be cleaned or is it engineers discretion? | At bends in the rail (see Structure P-51-705 Railing Plan sheet 8 of 10), there are new aluminum channels that must be welded to the existing aluminum posts. These are the areas that would require cleaning, so that there is no dirt contamination mixing in/compromising the weld. Other areas on the railing have mechanical connection, so those will not need cleaning unless there is some buildup of dirt on the posts that would interfere with the connection. It will be the engineerâ€™s discretion as to the extent of cleaning at each weld location, but cleaning of the entire post is not required. | Scott Lawry | 1 | 2017-02-08 10:18 | 2017-02-10 13:48
20170214 | 20170214011 | 11 | Sealing | Does the outside face of the parapets or the outside fascia beam get sealed in this project. | Apply protective surface treatment to the entire top surface of the bridge deck; curb, including vertical the face; median and sidewalk surfaces; and the inside faces and tops of concrete parapets. | Scott Lawry | 5 | 2017-02-06 13:27 | 2017-02-07 11:33
20170214 | 20170214011 | 11 | Bridge List and Locations | In the bidding documents there are 3 places that show what bridges are to be sealed. All three of the sheets have different data for the total number of bridges, with the location maps being the least amount, they vary from 80 some locations all the way through 117 locations. what is the correct amount of locations | As shown in the work restrictions in the plan there are 112 individual locations/ bridges in this project. The lift bridges (B-15-0023 & B-15-0100) in this contract have a handful of sub structure numbers associated with them and although there are multiple bridge numbers show in the plan the are still one location. Traffic restrictions and protective surface treatment plan sheets are correct. Issues with the location maps will be addressed via addendum. | Scott Lawry | 4 | 2017-02-02 15:18 | 2017-02-07 11:31
20170214 | 20170214011 | 11 | Start Date | Is there a actual start date for this project or a date the dot would prefer the contractor to start? | Provide the time frame for construction of the project within the 2017 construction season to the engineer in writing within a month after executing the contract but at least 14 calendar days before the preconstruction conference. Assure that the time frame is consistent with the contract completion time. Upon approval, the engineer will issue the notice to proceed within ten calendar days before the beginning of the approved time frame. Due to the nature of the work the engineer is very unlikely approve any schedule that shows any work outside of the months of June, July, and August. | Scott Lawry | 9 | 2017-02-07 08:59 | 2017-02-07 13:51
20170214 | 20170214011 | 11 | Sealer on Parapets | It appears that some of the parapets have a concrete protective coating on them, in which the penetrating sealer serves no purpose. Was the square footage for those structures calculated with or without the parapet in the yardage? | Apply protective surface treatment to the entire top surface of the bridge deck; curb, including vertical face; median and sidewalk surfaces; and the inside faces and tops of concrete parapets. Quantities for protective surface treatment reseal, (Item 502.3215.S) account for the entire top surface of the bridge deck; curb, including vertical face; median and sidewalk surfaces; and the inside faces and tops of concrete parapets for all structures in the plan. | Scott Lawry | 1 | 2017-02-02 14:45 | 2017-02-07 11:28
20170214 | 20170214011 | 11 | Cleaning Process | On the past projects, what was the cleaning methods that were used. High pressure washing, low pressure high volume, or simply just dry cleaning and then blowing the surface of with air? | Ensure that the concrete is clean. Air blast immediately before applying the protective surface treatment to remove all dust or loose particles. Collect and properly dispose of all roadway debris that cannot be moved off of structure and onto roadway shoulder with air blasting. Do not throw roadway debris over the side of the structure. | Scott Lawry | 8 | 2017-02-07 08:48 | 2017-02-07 13:51
20170214 | 20170214011 | 11 | Completion time | The completion time in the bidding documents state that only 25 working days will be allowed. There are over 100 bridges that need to be cleaned and then treated. Is the working days in the bid accurate? | Yes. Production rates used to determine contract time for completion (number of working days) are based on past Northeast Region Wide Deck Sealing Projects. | Scott Lawry | 2 | 2017-02-02 15:04 | 2017-02-07 11:29
20170214 | 20170214011 | 11 | Liquidated Damages | What are the Liquidated Damages for not completing the project within the 25 working days? | The liquidated damages are determined based upon the value of the contract per 108.11 Liquidated Damages. | Scott Lawry | 6 | 2017-02-07 08:41 | 2017-02-07 13:50
20170214 | 20170214011 | 11 | Inspection Process | What will the inspection process be for this project as far as the level of cleanliness prior to the protective sealer is applied? | Per section 105 control of work the engineer decides all questions regarding: 1. Interpretation of the contract. 2. The quantity, quality, and acceptability of materials furnished and work performed. 3. Rate of progress of the work. 4. Payment, contract administration, and the acceptable fulfillment of the contract. 5. Disputes. 6. Mutual rights under the contract. | Scott Lawry | 7 | 2017-02-07 08:43 | 2017-02-07 13:50
20170214 | 20170214011 | 11 | Cleaning | Will mobile traffic operations be allowed for the pre-cleaning of the structures to be sealed? | Perform this work according to the requirements of standard spec 643, and as shown on the plans or as approved by the engineer, except as hereinafter modified. Submit to engineer for approval a detailed traffic control plan for any changes to the proposed traffic control detail as shown on the plans. Submit this plan ten days prior to the preconstruction conference. Obtain prior approval from the engineer for the location of egress and ingress for construction vehicles to prosecute the work. Conduct operations in such a manner that causes the least interference and inconvenience to the free flow of vehicles on the roadways. | Scott Lawry | 10 | 2017-02-07 10:41 | 2017-02-07 13:52
20170214 | 20170214011 | 11 | Cleaning prior to sealing. | Will the contractor be responsible for the removal all accumulated debris from the structure prior to sealing, or will the department of transportation have all winter salts,sand, and anti skid removed before the contractor begins the job. | The contractor will be responsible for the removal of all accumulated debris from the structure prior to sealing. | Scott Lawry | 3 | 2017-02-02 15:09 | 2017-02-07 11:30
20170214 | 20170214013 | 13 | Asbestos Report | Is the asbestos report available for the project? | The file has been posted: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170214013/ | Scott Lawry | 3 | 2017-02-03 09:32 | 2017-02-03 12:07
20170214 | 20170214013 | 13 | Intermediate Concrete Diaphragms | Sheet 19 of 33 of the structure plans for B-38-21 indicate that the existing intermediate concrete diaphragms are to remain in place. Historically, due to the minimal amounts of rebar holding these diaphragms to the beams and the amount of corrosion present, the ability to salvage the diaphragms during redecking operations has been unsuccessful. Once the deck has been removed, the girders rebound and load is shifted causing these types of diaphragms to drop out or become dislodges. As a result on previous redeck projects the Department has added bid items for replacement diaphragms. Should there be a bid item to replace the intermediate concrete diaphragms on this project. | The diaphragms of the existing bridge support the Fishing Platform on the downstream side of the bridge. If the diaphragms are removed, the Fishing Platform will not be supported, and will collapse. The exterior beam will also probably be damaged. There are holes in the outside beams where the support reinforcement for the fishing platforms extend thru. This support reinforcement is embedded in the concrete diaphragms. It is clearly noted on the plans that the diaphragms are to remain in place. Keeping the diaphragms in place is noted on the plans because we understand this is not the normal way re-decks are done. The contractor will need to use special methods to insure that the diaphragms remain in place, otherwise the Fishing Platform they supports will fail. | Scott Lawry | 1 | 2017-01-19 15:33 | 2017-01-20 09:11
20170214 | 20170214013 | 13 | 2" Concrete Topping | The plans indicate a 2" concrete Topping over the double T beams on the fishing path. How will this 2" topping be paid and what material/mix should be used? A 1.5" stone concrete mix doesn't seem appropriate. What type of cure will be required on the topping? Will there be a construction joint allowed in the topping and curb? | Answer: The 2â€ Topping is included in the bid item â€˜Concrete Masonry Bridgesâ€™ under the superstructure quantities. It should be the same mix as used for the Superstructure. Answer: The design team is comfortable with using the 1.5â€ stone concrete mix in this application. The overlay is a minimum of 2â€, and will be covered with a polymer overlay for the final surface. Answer: The cure for the white topping should be the same as what is done on the abutment wings. Answer: A construction joint will not be allowed between the curb and the topping. | Scott Lawry | 2 | 2017-01-31 08:17 | 2017-02-03 09:28
20170214 | 20170214013 | 13 | Railing | We are wondering about the plate detail on page 148 of the drawings. Plan base plate detail shows 4- 5/8â€ holes in the plate but # 9 in the legend calls for only 2- anchors. We are thinking that the 4- holes are for spanning the old railing that was cut off and indeed only 2- are required per post ? | There are only 2 anchor bolts required for each post. There are 4 holes provided in the base plate at each post because there are several locations where the new post location will conflict with the existing post sleeves that are to be filled with grout. The additional holes will allow the anchor bolts to be shifted so that they avoid the existing post sleeves. As noted in Note #9, the 2 unused holes in the anchor plate will be filled with non-staining gray non-bituminous joint sealer. This was done so that field drilled holes in the anchor plates would not be required. | Scott Lawry | 4 | 2017-02-06 15:47 | 2017-02-06 15:47
20170214 | 20170214015 | 15 | Preboring | On sheet 1 of 12, page 43,in the Foundation Data section it states "shafts shall be cased and have a diameter of at least 18-inches. After piles have been firmly seated, fill the shaft with cement grout". Are the shafts used to prebore going to be permanent or will the contractor be able to remove once the piles are grouted into the rock? | The casing can be removed following grouting. | Scott Lawry | 1 | 2017-02-06 09:26 | 2017-02-06 13:17
20170214 | 20170214016 | 16 | Lane Closures | Could you take a look at the lane closure restrictions on the HWY 29 roadway? The charts are difficult to read in the special provisions but from what I can tell, we can only work on the section by Abbotsford from noon to 5pm on Sundays in the West Bound lane. Does *** mean there are no restrictions? | There is an error in the STH 29 tables. The times reflected on those tables indicate peak hour concerns. An addendum will be issued to update the tables and clear up any concerns. | Scott Lawry | 2 | 2017-01-18 08:22 | 2017-01-18 08:23
20170214 | 20170214016 | 16 | Adjusting Inlet Covers | I believe the inlets in the Misc Quantities for adjusting inlet covers are Median Grate Inlets. Typically, when these need to be adjusted, whether it be 6" or 24", they are under the item Reconstruct Inlet. These inlets do not have covers that can be adjusted with rings but the entire structure needs to be reconstructed with rebar embedded and concrete poured to achieve the proper flow elevations and the lids are recessed in. Could the adjust inlet item be eliminated and the quantity added to Reconstruct Inlets? | We will be eliminating the Adjusting Inlet item and adding the quantity to the Reconstructing Inlet item via addendum. | Scott Lawry | 1 | 2017-01-13 14:26 | 2017-01-18 09:25
20170214 | 20170214016 | 16 | Cable systems | On a November 2016 project (20161108021)the High Tension Cable installations spanned several counties. Because the project encompassed more than 1 county the department allowed any of the approved systems for the counties for the project to be used. This allowed each manufacturer to quote the complete project quantity and provided for fair competition on the bid. I am requesting that the same consideration be made on the project so that ALL manufacturers can have a fair opportunity to bid the complete job. | The project should be bid as specified in the plan and special provisions, the contractor should be installing an approved system for the county in question from the approved products list. | Scott Lawry | 5 | 2017-02-09 09:13 | 2017-02-10 16:24
20170214 | 20170214016 | 16 | Lane Closures | On the lane closure schedule for STH 35, it is divided by east bound and west bound. This road is a north bound/south bound road. Is east bound, south bound and west bound, north bound? Thanks | This issue will resolved by addendum #1. | Scott Lawry | 3 | 2017-01-27 10:03 | 2017-01-30 08:06
20170214 | 20170214016 | 16 | Chippewa County Rail on WI 29 | The plans show 3 stretches totaling 6128' with 6 anchors. The misc quantities show one solid stretch for 6619' and 2 anchors, continuing the rail through the Seymour Cray overpass bridges. How will this rail be constructed? | This area will be constructed with 3 stretches of cable barrier, totaling 6128' with 6 anchors, as the plan shows. An addendum will be issued to update the miscellaneous quantities. | Scott Lawry | 4 | 2017-01-30 07:12 | 2017-01-30 12:39
20170214 | 20170214018 | 18 | Tempoary Bridge Elevations | At Structure 226 there is approx. 1.58â€™ from top of profile to Q5 water el. and at Structure 227 there is approx. 2.75â€™ from top of profile to Q5 water el. Neither clearance provides enough depth for a bridge superstructure to be above the Q5 water elevation as required in State Spec. Section 526.3.2(2) for the span length required. Would the state consider raising the profile of the temporary road to accommodate Q5 water elevation? Would the additional aggregate base required for the profile raise be paid for with the existing bid item? | An addendum will be developed to address these issues. | Scott Lawry | 1 | 2017-02-06 10:07 | 2017-02-07 11:34
20170214 | 20170214022 | 22 | Temporary Shoring for Stage Construction | Should there be an item for temporary shoring due to the staged construction? | It is felt that the item of temporary shoring is not needed for this project. | Scott Lawry | 1 | 2017-01-17 15:29 | 2017-01-19 10:49