## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170314 | 20170314001 | 1 | Rest Area Borrow | Will the DOT allow contractors to obtain embankment material from the rest area? | No assumptions should be made about availability of embankment material. The quantities and locations of quantities shown in the plans, or specifically stated in the special provisions, are the quantities of various materials WisDOT considers available for that project. Any requests for obtaining additional materials within the right of way (whether inside or outside the project limits) will only be considered after the contract is awarded. If a request is received after the contract is awarded, WisDOT will consider those requests on a case by case basis. | Scott Lawry | 1 | 2017-03-08 16:09 | 2017-03-13 16:08
20170314 | 20170314002 | 2 | Estimate of Quantities Item#503.0155 | On Proposal No 2 of the March 14, 2017 WisDOT letting: On the summary sheet for the letting, under estimate of Principal items: It lists Prestressed Girders, 5,883 LF 54-inch. Under the estimate of quantities sheet, it lists only item#503.0155 Prestressed Girder Type I 54W-inch with a quantity of 2,583 LF. Could you please confirm the type of prestressed girder and the LF for this proposal? Thank you. Christine Hamil County Materials Corporation | The advertisement for the March letting incorrectly lists the quantity of item 503.0155 at 5883 LF. The plan quantity of 2,583 LF is consistent and correct within the plan set, Estimate of Quantities, structure plans as well as the proposal and the Bid Express website. | Scott Lawry | 1 | 2017-02-10 07:54 | 2017-02-13 09:39
20170314 | 20170314002 | 2 | Earthwork | Are the earthwork quantities in the plan accurate? There appears to be a discrepancy between the earthwork data table and the earthwork summary table in the miscellaneous quantities sheets. | The quantities in the earthwork summary table in the miscellaneous quantities sheets is correct. The earthwork data table is incorrect. This will be corrected, along with some lighting plan modifications, in an addendum that should be issued next week. | Scott Lawry | 2 | 2017-02-10 14:21 | 2017-02-10 14:21
20170314 | 20170314002 | 2 | Surface, and Alignment files | Are the existing/proposed surface files, and alignment files available? If so please provide. Files in preliminary plans page should not be used for bidding purposes. | The files can be found at: http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1007-11-81 | Scott Lawry | 3 | 2017-02-13 10:54 | 2017-02-17 13:58
20170314 | 20170314002 | 2 | Colored Concrete | How will the coloring for the colored concrete for the truck aprons and OSOW off tracking areas be paid? | Bid item 405.0100 Coloring Concrete WisDOT Red will be added to the contract with an upcoming addendum. | Scott Lawry | 4 | 2017-02-14 13:54 | 2017-02-14 13:55
20170314 | 20170314002 | 2 | Asphalt Quantities | Is the asphalt quantity for the median areas represented in the plan, and is it accurate? | No. A line item will be added to the MQ table to clarify and correct the quantity in an upcoming addendum. | Scott Lawry | 5 | 2017-02-16 09:54 | 2017-02-16 09:54
20170314 | 20170314002 | 2 | Retaining Wall Specs | Previous staged-construction MSE walls along the IH39 project have utilized temporary wire wall designs with welded wire facing units, geogrid reinforcements, and a geotextile face-wrap that eliminated the fine metallic screen specified in SPV.0165.851. Please confirm this precedent will be acceptable for use on this project. Thank you. | The wall systems approved for temporary MSE Wall applications do, in fact, eliminate the fine metallic screening as mentioned in the question above. This is acceptable as it is a temporary application. | Scott Lawry | 6 | 2017-02-16 12:51 | 2017-02-21 12:20
20170314 | 20170314002 | 2 | Revised Earthwork | It appears that even after add #1 the earthwork tables for 1007-10-86 do not match the summary. Add #1 also never addressed the discrepancies between the tables and the summary for 1007-11-81. | An addendum will be issued early next week to address the discrepancies. | Scott Lawry | 7 | 2017-02-27 08:10 | 2017-03-03 12:52
20170314 | 20170314002 | 2 | MSE Wall | Is there a patterned form liner to be used to cast the concrete panel MSE panels for the retaining walls on this project? | There are no form liners to be used for the MSE panels. | Scott Lawry | 8 | 2017-03-01 08:41 | 2017-03-01 08:41
20170314 | 20170314002 | 2 | Concrete Pavement and Pipe Extensions | Q1: Is the quantity for 9-inch concrete pavement in stage 5B for the NB exit ramp (found in concrete pavements schedule in the MQ 11081 pg. 159) correct? Q2: Is there an error in the temporary pipe extension detail (in plan 10-86 pg. 30) in the pipe arch/size shown? This size does not exist as an arch. | A1: No. The quantity shown is 1689 SY. The quantity was inadvertently computed as SF. The correct quantity is 188 SY. A2: Yes, the detail will be updated to reflect the correct pipe size. The changes will be made and an addendum will be submitted | Scott Lawry | 9 | 2017-03-01 16:09 | 2017-03-01 16:11
20170314 | 20170314002 | 2 | MSE Wall Bearing Pressures | The allowable bearing pressures are exceeded in a few locations along the MSE walls. Are the bearing resistances shown just for the station point indicated or the entire section of wall with similar geometry, ie does the 4100 psf resistance apply to Sta 06+60 to 1+90 where the geometry is consistent or just Sta 1+90? How does the department plan to handle locations where the bearing resistance is exceeded? Thank you. | In regards to questions about values presented in the â€œWall External & Overall Stability Evaluationâ€ table for R-13-285 (Sheet 634): All wall values provided in this plan table only pertain to the stations indicted in the table. The values reported in the â€œWall External & Overall Stability Evaluationâ€ table in the plan for Station 1+90.0 reflect the lowest CDR value (1.4) for the weakest soil layer, which is located at a depth of 13.5â€™ â€“ 16.5â€™ below the MSE wall base. Based upon the soil information provided by B-1, the Factored Bearing Resistance at the base of the MSE wall at Wall Station 1+90.0 is 8,000 psf, with a CDR of 1.5. | Scott Lawry | 10 | 2017-03-08 11:45 | 2017-03-09 10:36
20170314 | 20170314002 | 2 | WisDot Site North of East Church Road | Will the WisDot site north of East Church Road be available to all contractors to mine for the CTY Hwy 'N' project? If so, what are the requirements? | No assumptions should be made about availability of rock material. The quantities and locations of quantities shown in the plans, or specifically stated in the special provisions, are the quantities of various materials WisDOT considers available for that project. Any requests for obtaining additional materials within the right of way (whether inside or outside the project limits) will only be considered after the contract is awarded. If a request is received after the contract is awarded, WisDOT will consider those requests on a case by case basis. | Scott Lawry | 11 | 2017-03-08 16:25 | 2017-03-13 09:22
20170314 | 20170314002 | 2 | Permanent steel sheet piling | Would cold-formed sheeting be acceptable for the 7,880 SF permanent steel sheet piling item on job #2? For example an SKZ 20 section. | Cold-formed sheeting could be used. The piling still needs to meet ASTM A328 and have the require strength and Section Modulus that is called out on the plans. | Scott Lawry | 12 | 2017-03-13 10:44 | 2017-03-13 10:45
20170314 | 20170314003 | 3 | Culvert and Storm Sewer | Will contractors be allowed to use Class IIIA or Class IIIB pipe for culvert pipe and storm sewer pipe? (competitive specifications) | An addendum is being developed to address the pipe materials that will be allowed on the project. | Scott Lawry | 1 | 2017-02-15 19:44 | 2017-02-22 11:26
20170314 | 20170314005 | 5 | Haul Road and Waste Material | 1. Would the City allow for a particular street to be used as a haul road? 2. Does the department or the City aware of anyone interested in excess fill? | 1. The haul roads should be limited to those that are designated truck routes within the City. The contractor should submit the request to use a haul road per standard specification 107.2, which will then be administered per standard specification 618. 2. WisDOT does not coordinate dump sites of excess material. It is up to the contractor to determine where to dispose of excess material. The City has however indicated that Hawthorn & Stone Development Inc. may be interested in excess material. 608-807-1413 | Scott Lawry | 1 | 2017-02-22 14:40 | 2017-02-22 14:49
20170314 | 20170314005 | 5 | Soil Boring Logs | Are soil boring logs available? | The file has been posted: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314005/ and http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx | Scott Lawry | 2 | 2017-02-23 10:54 | 2017-03-01 16:07
20170314 | 20170314005 | 5 | Remove Abandoned Steam Tunnels | Who will test to determine if asbestos is present? Does this item include the abatement of asbestos or will it be completed by others prior to the removal of the steam tunnels? | As per item SPV.0090.07. A Description : and A.3 coordination, the environmental consultant hired by WisDOT (TRC Environmental) will determine if the material is asbestos containing, and determine how it needs to properly handled and disposed of. As specified under E. Payment : Payment is full compensation for providing all labor, equipment and materials for all steam tunnel removal and associated steam tunnel abandonment and/or removal; for all excavating, for sheeting and shoring; for dewatering; for saw cutting; for sealing sections of abandoned steam tunnels; for proper disposal of removed items (including salvage if applicable). | Scott Lawry | 3 | 2017-03-09 12:15 | 2017-03-13 10:26
20170314 | 20170314006 | 6 | Storm Sewer | Due to the low ADT, will contractors be permitted to utilize competitive bid items for storm sewer? (Class IIIA or Class IIIB) | No, contractors will not be permitted to use alternative materials because many do not have the adequate cover under the subgrade based on the FDM guidance. The owner wants the bid items in the plan for Storm Sewer Pipe Reinforced Concrete to be used. | Scott Lawry | 1 | 2017-02-15 20:34 | 2017-02-17 14:43
20170314 | 20170314006 | 6 | Tack | How will the contractor be compensated for Tack on this project? | An addenda will be issued to address the tack coat. | Scott Lawry | 2 | 2017-03-06 08:37 | 2017-03-07 16:40
20170314 | 20170314006 | 6 | Soil Borings | Are there any soil borings/geotechnical data available for this Project? | The file can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314006/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx | Scott Lawry | 3 | 2017-03-06 13:04 | 2017-03-09 12:01
20170314 | 20170314006 | 6 | Storm Sewer Tables | Can the excel files for storm sewer tables in the miscellaneous quantities be provided to bidders? | We will not be supplying the excel files at this time. | Scott Lawry | 4 | 2017-03-07 13:51 | 2017-03-08 13:04
20170314 | 20170314006 | 6 | Railing Pedestrian Steel - Item SPV.0090.01 | Will epoxy anchors be allowed to attach the railing to the walk, or, will we need to use the anchorage detail as shown in the plan? | No, use the anchorage detail shown in the plan. | Scott Lawry | 5 | 2017-03-08 08:51 | 2017-03-08 13:05
20170314 | 20170314006 | 6 | RR Bridge Abutment Loadings | Per bid documents, temporary shoring is required under/along the RR Bridge to install water and storm sewer. Can loadings be provided in order to do a preliminary design for the shoring? | Loadings for the shoring will depend on the heights needed for the shoring, which is dependent upon the contractorâ€™s means and methods. | Scott Lawry | 6 | 2017-03-08 11:57 | 2017-03-09 09:16
20170314 | 20170314006 | 6 | Temporary Shoring Quantity | Per Sheet 127 of the plans, under Temporary Shoring, there is 180 lineal feet of shoring (Sta.38+10 to 39+90). Can the department confirm the length of the shoring wall required? | The length of shoring will be determined by the contractorâ€™s means and methods, to construct the infrastructure as shown on the plan. The quantity was estimated using the lengths shown from station to station. | Scott Lawry | 7 | 2017-03-08 12:01 | 2017-03-09 09:17
20170314 | 20170314006 | 6 | Temporary Shoring - Sheet 115 | On Sheet 115, under temporary shoring, there is 75 lf per the stationing. The square footage of 750 sf implies that the retained height is 10' which seems excessive when you review the cross section on Sheet 259, namely the depth of the storm sewer. Can the department check and confirm the lineal feet and square foot quantities? | The length of shoring will be determined by the contractorâ€™s means and methods, to construct the infrastructure as shown on the plan. The quantity was estimated using the lengths shown from station to station. | Scott Lawry | 8 | 2017-03-08 12:02 | 2017-03-09 09:18
20170314 | 20170314006 | 6 | Concrete Bridging Detail | Is this bridging detail required on all storm sewer pipe sizes, and all utility trench crossings including sewer, water, gas, electric, ect? | The bridging detail will be required for storm sewer pipes 18â€ and larger. The detail is intended for crossings of existing water main and sanitary sewer. | Scott Lawry | 9 | 2017-03-10 13:55 | 2017-03-10 15:56
20170314 | 20170314006 | 6 | Trench Backfill | Are all sewer, water and lateral trenches backfilled with granular or existing material? | Storm sewer backfill will follow the WisDOT standard specifications under section 608 for storm sewers. Sanitary sewer, water main, and lateral backfill will follow the granular backfill requirements stated in the special provision of â€œGeneral Requirements for Sanitary Sewer and Waterâ€. This special provision has the contact information to obtain the â€œVillage of Iron Ridgeâ€™s Standard Sewer and Water Specifications for WisDOT Let Projectsâ€. | Scott Lawry | 10 | 2017-03-10 13:56 | 2017-03-10 15:56
20170314 | 20170314006 | 6 | Concrete Pavement Jointing | The design of the concrete pavement has a very large number of width changes and is not condusive to providing a quality slipform product. As long as the plan Width are maintained, will the department consider making the pavement widths in the middle two lanes more uniform? | No, the lane widths were based on FDM requirements for bike accommodations. The construction engineering staff could work with the contractor once they submit their plan and specify their means and methods to provide a uniform width in certain sections. | Scott Lawry | 11 | 2017-03-11 20:29 | 2017-03-13 10:40
20170314 | 20170314006 | 6 | Schedule | Can the design schedule be provided? | The schedule requirements are indicated in the special provisions. The detailed schedule of work is to be determined by the contractor. | Scott Lawry | 12 | 2017-03-12 17:45 | 2017-03-13 10:32
20170314 | 20170314008 | 8 | Removing Asphaltic Surface Milling | Wondering if any consideration was given to milling 2" on entire job to minimize the potential for milling through the existing asphalt pavement? The HMA thickness would remain the same so Sta 10+85 - 107+65.96 would end up 1.5" higher than existing at centerline which would increase the overall thickness of the pavement structure. Also, is it the intention to pave the full 4.5" of HMA prior to milling in the reconstruction areas or will those areas only receive the 2.5" lower lift prior to milling? For ride quality it would be better to install the full 4.5" HMA then mill straight through those reconstruction sections. | #1 - No, the intent is not to raise the existing grade of the road due to the limited scope and environmental limitations of the project. Because of the lack of existing asphalt, the Departmentâ€™s intention is to mill and replace a greater depth for a new, thicker pavement structure. #2 â€“ No, the intent is not to pave the full 4.5â€ HMA and then mill through it. The intent is to mill the entire project to see if there are EBS areas that need to be addressed first. Then work on the EBS areas and pave the final upper layer last. | Scott Lawry | 1 | 2017-02-15 09:11 | 2017-02-17 14:46
20170314 | 20170314008 | 8 | Culvert Pipe | Based on ADT, will contractors be able to bid with alternate materials in lieu of the aluminum coated CMP? | No, based on our limited field data, the pipes donâ€™t appear to have adequate cover under the subgrade based on the FDM guidance for alternative materials. | Scott Lawry | 2 | 2017-02-15 20:57 | 2017-02-17 15:03
20170314 | 20170314010 | 10 | start notice | The instream disturbance dates are from September 15 to May 15. Why can't the Notice to Proceed be issued earlier than June 12, 2017? | The June 12th date minimizes the inconvenience to the motoring public by ensuring the roadway remains open until the end of the school year. | Scott Lawry | 2 | 2017-02-20 09:11 | 2017-02-20 14:50
20170314 | 20170314010 | 10 | Construction Staking - Structure Layout | Item is missing. Will this be added by addendum? | Yes, an addendum will be issued to add this item. | Scott Lawry | 3 | 2017-02-28 10:50 | 2017-03-02 10:54
20170314 | 20170314010 | 10 | Pile Points Quantity | Please confirm number of pile points. | It should be 23 pile points. | Scott Lawry | 4 | 2017-03-10 12:10 | 2017-03-10 14:28
20170314 | 20170314011 | 11 | SPV.0180.02. Porous Asphalt Pavement | 1)Under the Material Technical Spec is says "The aggregate shall be SMA 9.5 mm". Is it correct to assume that you want a 9.5 mm Porous Asphalt Pavement, not an SMA 9.5 mm mix? 2)Shouldn't the Dust to Binder Ratio have a range? Or is the mix requirement of 1.2 a maximum? 3)Please clarify what testing requirements under Section 455 are required under this special provision. Just the AC testing? | A1) Yes, a 9.5mm Porous Asphalt Pavement is required. The aggregate shall adhere to requirements for SMA 9.5mm in the Porous Asphalt pavement. A SMA mix shall not be used. A2) The Dust to Binder ratio mix requirement is 1.2 maximum. A3) Sampling and testing are required of the asphaltic materials according to 455.2.2 and 455.2.3. | Scott Lawry | 1 | 2017-03-01 09:21 | 2017-03-02 17:18
20170314 | 20170314012 | 12 | Earthwork Summary Table | In regards to the above referenced project: Plan sheets 348 Earthwork Summary Table indicates that the Ice Age Trail 208+62â€™ATâ€™ â€“ 216+97â€™ATâ€™ is in Stage 1 and has a rock excavation total of 4,359 CY. Per the Earthwork Data Sheet (plan sht. 607), this section of the Ice Age Trail is in Stage 2 and has a rock excavation total of 1,372 CY. Please clarify this discrepancy. Also, plan sht. 349 - Earthwork Summary Table Stage 3 lists Ice Age Trail 200+50â€™ATâ€™ â€“ 207+25â€™ATâ€™ with a rock excavation quantity of 663 CY. Per the Earthwork Data Sheet (plan sht. 616) Ice Age Trail 200+50â€™ATâ€™ â€“ 207+25â€™ATâ€™ does not list any rock excavation. Please clarify this discrepancy. Thank you for looking into this matter. | The rock excavation earthwork quantities are correctly shown in the Earthwork MQ table on page 348 and 349. The rock quantities were updated after PSE and the earthwork data table was not reprinted and updated in the plan. If an addendum is created for the project a revised earthwork data table will be included. | Scott Lawry | 1 | 2017-02-10 12:44 | 2017-02-17 15:11
20170314 | 20170314012 | 12 | CAD Files | Will CAD files for this project be available? Hopefully so and as soon as possible as quantifying the rock quantities will take quite a bit of time. Thank you. | The files have been posted at these locations: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314012/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx | Scott Lawry | 2 | 2017-02-16 09:55 | 2017-02-16 17:23
20170314 | 20170314012 | 12 | Stage 3 Country Grove Drive Earthwork Data sheets | Plan sht. 617 Earthwork Data Sheets Stage 3 lists Tanglewood Drive Earthwork Date twice. Per the Earthwork Summary Table (plan sht. 349) there should be Earthwork Data for Country Grove Drive. We believe that one of the Tanglewood Drive Data Tables should be the Data for Country Grove Drive. Please provide the Earthwork Data for Stage 3 Country Grove Drive 52+17 CM - 54+04 CM. | Country Grove earthwork table was omitted unintentionally. We are working on an addendum to add it. | Scott Lawry | 3 | 2017-02-22 10:20 | 2017-02-24 13:46
20170314 | 20170314012 | 12 | Asphalt Paving Details | On Plan sheet 21 the temporary wedges detail appears to be a monolythic pavement structure. Can this be paved with the lower layer or does the asphaltic surface temporary need to be paved on top of the HMA Lower with another pass? On plan sheet 23 the Asphaltic curb detail shows a 6'' x6'' curb. Would a Carlson curb be able to be used in lieu of this? | Monolithic temporary wedges are acceptable. A â€œCarlsonâ€ curb or sloped face asphalt curb is an acceptable substitute. | Scott Lawry | 4 | 2017-03-01 12:10 | 2017-03-07 15:22
20170314 | 20170314012 | 12 | B13-0848 Box Culvert Extension | The proposed box culvert extension at approximate station 151+00 LT shown on plan sheet 562 calls for a cast-in-place concrete structure. Is utilizing precast box culverts an acceptable alternate to complete this work. | Cast-in-place concrete is to be used for the structure. | Scott Lawry | 5 | 2017-03-06 15:46 | 2017-03-08 07:42
20170314 | 20170314012 | 12 | Soil Borings | Are the soil borings for this project available? If so, can you please make the available online. | The soiling borings can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314012/ | Scott Lawry | 6 | 2017-03-07 11:58 | 2017-03-07 16:24
20170314 | 20170314012 | 12 | Cast in Place Utility Structures | Per City of Madison Specifications, it states that all utility structures shall be Cast in Place (CIP). Are pre-cast structures going to be allowed on this project? If so, can the Department elaborate on which ones are to be CIP and which ones can be pre-cast? Be aware there is a significant up-charge in the cost of CIP vs. Pre-cast. | As per article 19. General Provisions for City of Madison Storm Sewer of the special provisions; all structures are to be bid as field poured. Precast structures may be used if the field conditions stated in the specifications are met and approval from the project leader is given. | Scott Lawry | 7 | 2017-03-08 08:04 | 2017-03-09 15:30
20170314 | 20170314012 | 12 | Earthwork Data Sheets (Excel Form) | Can the excel versions of the earthwork data sheets be made available prior to the letting? (Sheets 601 thru 620 of the planset) | The department feels that all the information needed is contained in the plans and will not supply excel earthwork data sheets at this time. | Scott Lawry | 8 | 2017-03-09 09:27 | 2017-03-09 11:32
20170314 | 20170314013 | 13 | Sawing Concrete Quantity | No sawing of the existing concrete is in the plan for sawing the concrete pavement between stages 3 and 4. Should sawing be added to the contract for this area? |  |  | 1 | 2017-03-03 16:00
20170314 | 20170314013 | 13 | On the Concrete Pavement over 300 feet does a concrete paver have to be used? | There are areas of concrete over 300 feet in length on the project. Does a concrete paver have to be used as required in the WisDOT Standard Specifications on pavements over 300 feet? | The contractor should bid according to the Standard Specifications. | Scott Lawry | 2 | 2017-03-10 15:30 | 2017-03-13 10:18
20170314 | 20170314014 | 14 | Surface files | Are any CAD or surface files below available for the project. 1. Existing Conditions Survey Surface CAD files (Format: LandXML, .Dwg or .DGN) 2. Existing Condition Survey Mapping CAD files (Format: LandXML, .Dwg or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .Dwg or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .Dwg or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .Dwg or .DGN) | The files can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314014/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx This project did not have a surface deliverable so the surfaces have not been refined enough to be used as a GPS grading surface. The contractor will likely need to refine them prior to use as a GPS grading surface. | Scott Lawry | 1 | 2017-02-13 16:46 | 2017-02-16 17:43
20170314 | 20170314014 | 14 | Soil Borings | Are there soil borings available for this project? | The file can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314014/ | Scott Lawry | 2 | 2017-03-07 16:27 | 2017-03-07 16:31
20170314 | 20170314014 | 14 | Shoulders | When I was looking through the Typical Sections for the on and off ramps it shows the full width of the of the ramp being all concrete. The 15â€™ driving lane with either 5â€™ or 6â€™ of concrete on both sides of the 15â€™ lane with no asphalt shoulders. When going through the cross section for these same 5 to 6â€™ areas it shows asphalt for these shoulder areas. Also on both sides of the bridge it shows the entire width to be concrete but on the cross sections it shows asphalt on the outer lanes. Can you please clarify if these areas are meant to be concrete or asphalt | Typical Section show full width concrete on the ramps, this is the intent. At the bridge concrete approach slab the entire width, including shoulders is to be concrete. The cross sections do show an asphalt shoulder at these locations. The quantities for concrete and aggregate base were calculated using the typical sections and the detail for the concrete approach slab. The quantities for earthwork was computed using the Datum (subgrade) which is the same for both asphalt and concrete shoulders. All the quantities should be correct based on the typical sections and concrete approach slab detail. The cross sections do show incorrectly an asphalt shoulder however no material computations (concrete, aggregate or asphalt) were done using the cross sections. | Scott Lawry | 3 | 2017-03-09 09:53 | 2017-03-09 09:54
20170314 | 20170314015 | 15 | Concrete | 1.) Stage 2 access road is 18' wide does not show a center line and or center steel. Should there be a center line with center steel figured in o the bid? 2.) The typical Milwaukee 31" curb detail has a 7" wide head by a 6" tall head. the detail for the integral 18" curb shows a 7" wide by 7"tall head. Is this correct or should the curbs all have the same head size ? If they are to be the same which size should we figure? 3) Would the department allow the 31" curb to be poured integral with the pavement? | A1) If the roadway is constructed as one pavement, a sawed centerline joint is required. If the roadway is constructed in two pavements, tie bars would be required. A2) The mainline median curb & gutter is the modified dimension of 7â€ wide and 7â€ tall curb head. An addendum has been prepared to address quantity error A3) Yes, on the mainline pavement only with a zero-clearance paver (due to trees, hydrants, etc behind the proposed curb). The access road shall remain constructed as shown in the typical section. Will remain paid for as 31â€ curb & gutter. | Scott Lawry | 1 | 2017-02-28 13:06 | 2017-03-02 10:57
20170314 | 20170314015 | 15 | Construction Staging | Is there a reason that SB traffic can not be placed onto the newly constructed NB lanes to facilitate constructability of Stages 3 & 4. Having a split work zone, as is shown in stages 3 & 4, will make it difficult or impossible to construct without regularly impeding SB traffic. | Due to the high number of properties on the west side of North 91st Street and the limited access (no side streets; few median openings), the City prepared the traffic control plans in such a manner to accommodate southbound traffic remaining in the southbound lanes and reducing the amount of motorists utilizing the grade to access their properties. Contractor will need to provide proper devices and methods to safeguard the traveling public through the work zone and provide vehicular access to all properties on the west side during construction of the southbound lanes. Any Cost Reduction Incentive should be submitted per standard specification 104.10 after contract execution. | Scott Lawry | 2 | 2017-03-07 10:46 | 2017-03-09 09:37
20170314 | 20170314015 | 15 | Item SPV.0090.02 Culvert Joint Repair | Referencing Section 58 of the Special Provisions, it states that we are responsible for repair widths up to 6". Referencing the "construction joint detail" on Sheet 5 of 7 in the plans (B-40-229), it shows 3" of width on either side of the construction joint. Under payment, however, it states that we are responsible for repairs 6" on either side of the construction joint. This is a 12" total repair width versus a 6" total repair width per LF of joint repair. Are we responsible for 12" wide repair or 6" wide repair per LF of joint? | The detail on page 5 of 7 of the structure plans correctly shows what we are looking for. The item should cover a 6" wide repair at the joint (3" on either side of the actual joint). | Scott Lawry | 3 | 2017-03-09 09:48 | 2017-03-13 10:11
20170314 | 20170314015 | 15 | Sawing Concrete | Should there be a quantity of Sawing Concrete along the stage line of Stages 3 and 4? | Based on City records and age of the roadway, we do not anticipate any tie bars in the existing pavement. Therefore, the removal of the pavement between the stages should not require sawing. | Scott Lawry | 4 | 2017-03-10 07:10 | 2017-03-10 09:27
20170314 | 20170314016 | 16 | Storm Sewer Pipe Items | Based on ADT, will contractors be permitted to bid based on competitive class III storm sewer bid items? (Class IIIA or Class IIIB) | The City of Greenfield has requested to use concrete pipe as per their standard for storm sewer. | Scott Lawry | 1 | 2017-02-15 21:26 | 2017-02-16 11:28
20170314 | 20170314016 | 16 | Storm Sewer Structure and PIpe Table | Will the WIDOT provide the Storm Structure and Pipe table as shown on pages 176-185 as an Excel file? | The file can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314016/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Scott Lawry | 2 | 2017-03-06 14:50 | 2017-03-09 13:45
20170314 | 20170314016 | 16 | Cover Plates Two Part Question | What is the minimum thickness for the steel cover plates required to protect the water main? It appears the plates will need to be left in place to build the typical pavement section, is this the intent of the special provisions? | A1) A minimum thickness of 1â€. A2) It is expected that the cover plates will NOT be left in place. The intent of the special provision is to protect the 24â€ and 54â€ water mains at vehicle crossings from the time existing pavement is removed until final pavement is placed - intersections, driveways and other locations where construction vehicles may cross the mains (example is access to the Drainage Swale on Lot 20). Milwaukee Water Works understands the need to construct the roadway facilities above the water mains. Plating during construction activities above the water mains is not needed if extreme caution is taken. Extreme caution may include but is not limited to: restricting the use of heavy equipment over the mains, restricting the use of vibratory compaction over the mains and installing traffic control devices over the mains for protection from construction traffic. | Scott Lawry | 3 | 2017-03-10 07:58 | 2017-03-10 14:12
20170314 | 20170314016 | 16 | Adjusting Manholes | On sheet 90 detail for adjusting manholes to grade. Note #3: Set covers to final surface grade prior to placement of lower HMA and ramp until final surface is placed. How are we getting paid for the removal of the asphalt ramp around the manhole? Didnâ€™t see it really spelled out as far as if it is incidental or which item is incidental? | This work is incidental to the adjusting Manhole Cover or Adjusting Inlet Cover items. | Scott Lawry | 4 | 2017-03-10 14:39 | 2017-03-10 14:44
20170314 | 20170314016 | 16 | Topsoil vs. Salvaged Topsoil | The plan calls for both topsoil and salvaged topsoil items but does not specify a location for either. Can you provide more clarity on where topsoil will be required and where salvaged topsoil will be required? | The miscellaneous quantities sheets list where there were be topsoil and salvaged topsoil broken down by the street name and stationing. This information can be found on Sheet 190. | Scott Lawry | 5 | 2017-03-13 11:51 | 2017-03-13 12:24
20170314 | 20170314016 | 16 | Storm Sewer backfill | Does all project Storm Sewer require Granular Backfill? | Yes, all State Let Storm Sewer requires it per Standard Specification. The City of Greenfield requirements do not apply. | Scott Lawry | 6 | 2017-03-13 12:25 | 2017-03-13 12:26
20170314 | 20170314017 | 17 | Pipe Bid Items | Based on ADT, will contractors be permitted to bid based on competitive bid items for culverts or storm sewer bid items? (Class IIIA or IIIB) | The section of roadway with concrete pipe that would qualify for the Class III A or B items is within jurisdictional transfer to City of Burlington limits. The City of Burlington has stated they require concrete pipe. | Scott Lawry | 1 | 2017-02-15 21:30 | 2017-02-22 11:26
20170314 | 20170314017 | 17 | CAD Files | We would like to request the following CAD files to assist with our planning and quantity verification processes. In addition to the below files any CAD information you may have with regards to the rock on the project would be very helpful. 1. Existing Conditions Survey Surface CAD files (Format: LandXML, .Dwg or .DGN) 2. Existing Condition Survey Mapping CAD files (Format: LandXML, .Dwg or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .Dwg or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .Dwg or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .Dwg or .DGN) | The files have been saved at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314017/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Scott Lawry | 2 | 2017-02-16 17:33 | 2017-02-16 17:33
20170314 | 20170314017 | 17 | Waste material | With this project there will be approximately 130,000 Cubic Yards of excess material from the common excavation work on this project. Does the department have any options for disposing of this material? Also, is there any soil boring/geotechnical reports available for this project? | WisDOT does not coordinate dump sites of excess material. It is up to the contractor to determine where to dispose of excess material. The soils report can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314017/ | Scott Lawry | 3 | 2017-02-22 10:47 | 2017-02-23 07:42
20170314 | 20170314017 | 17 | Rectangular Rapid Flashing Beacon (RRFB) System | While some of the spec language includes the ability to use the Carmanah systems (R920 or SC315), there are 3 areas where our product still differs. Would these be accepted as an approved equal? | This is acceptable as approved equal. | Scott Lawry | 4 | 2017-02-22 10:57 | 2017-02-22 10:59
20170314 | 20170314017 | 17 | Borrow | On sheet 212 of the plan, note 6 calls for EBS to be backfilled with â€œ208.0100 Borrowâ€. It then says â€œ30-inch Grade 2 Borrowâ€. Can you please clarify Grade 2 Borrow and/or what material does the designer want to backfill the EBS? | Grade 2 â€“ just refers to borrow fill depth in EBS areas of 30 inches. Item 208.0100 Borrow should be used for backfilling EBS areas at a depth of 30 inches. | Scott Lawry | 5 | 2017-02-24 14:55 | 2017-02-24 15:24
20170314 | 20170314017 | 17 | Overhead Sign Support (structure) 01. S-51-238 | We are wanting to quote the structures on the upcoming letting for the structure S-51-238 and we have been unable to locate any plans for this particular structure. If you could please point us in the right direction we would be most grateful. | The as-built plan for this project can be found at: The file has been added. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314017/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx For the requirements for S-51-238 please review standard specification 641 Sign Bridges and Overhead Sign Supports as well as the Detail Drawing on page 118 in the plans. | Scott Lawry | 6 | 2017-03-13 14:47 | 2017-03-13 14:53
20170314 | 20170314018 | 18 | Storm Sewer and Culvert Bid Items | Based on ADT, will contractors be permitted to bid based on competitive bid items for storm sewer and culverts? (Class IIIA or Class IIIB) | The department will be addressing this issue with an addendum. The storm sewer/culvert pipes will be investigated and modified where possible. | Scott Lawry | 1 | 2017-02-15 21:36 | 2017-02-20 11:03
20170314 | 20170314018 | 18 | Materials Specification | Can line #430 Asphaltic Base 315.0100 be changed to Asphaltic Surface Patching 465.0110 to allow for 19mm in place of 1" nominal as required by the 315 spec. | Item #430 Asphaltic Base (315.0100) will be changed to Asphaltic Base Widening (315.0200) and a special provision will be added to allow for 19mm aggregate. These changes will be addressed via addendum later today. | Scott Lawry | 2 | 2017-03-06 14:09 | 2017-03-09 09:40
20170314 | 20170314018 | 18 | Earthwork | Sheet 75 in the plan shows the common ex for the asphaltic base and excavation summary. The common appears to cover the 2' excavation for the patch. Is the additional 4' of the existing material be removed? If so, how is it being paid? Detail shows 6" of 1 1/4" material but the estimate of quantities do not show any. | Yes, the additional 4â€™ of existing material needs to be removed in order to add the 6â€ of new 1 ¼â€ base. This excavation along with the 2â€™ for the asphaltic base widening will be incidental to Asphaltic Base Widening bid item (315.0200). The quantity for this 1 ¼â€ base is missing and will be added via addendum later today. | Scott Lawry | 3 | 2017-03-06 14:14 | 2017-03-09 09:41
20170314 | 20170314018 | 18 | HMA | Line #440 Base Patching Asphaltic 390.0201 - There is 2000 ton listed as undistributed. What is the intention for the tonnage listed? Size of areas to be paved. Can the item be changed to the 465 spec, asphaltic surface patching? This would allow for smaller aggregate versus the 315 spec which requires 1" nominal. | The intent of this item is to repair or patch asphaltic pavement after milling operations. The locations where this is needed will be identified by the project engineer. Base Patching Asphaltic (390.0201) is the incorrect item and will be replaced by Asphaltic Surface Patching (465.0110) via addendum later today. | Scott Lawry | 4 | 2017-03-06 14:20 | 2017-03-09 09:41
20170314 | 20170314018 | 18 | HMA | Line #1940 - HMA PWL Test Strip - There is 1 each listed. Is this test strip for the lower layer only? | The current quantity shown (1 Each) is for the lower layer only. After further discussions with BTS it was decided to add PWL to the upper layer as well so the quantity will be adjusted to show 2 Each. This change along with Incentive Density PWL HMA Pavement (460.2005) will be included in an addendum later today. | Scott Lawry | 5 | 2017-03-06 14:28 | 2017-03-09 13:50
20170314 | 20170314018 | 18 | HMA | Sheet 7 shows 'Typical Finished Cross Section for Culvert Replacement' and sheet 8 shows 'Typical Finished Cross Section for Storm Sewer Laterals' - The detail shows depth and HMA type. Is this material accounted for in the miscellaneous quantities and if so, where? | No, this material is not currently shown in the miscellaneous quantity sheets. This will be addressed via addendum later today. | Scott Lawry | 6 | 2017-03-06 14:36 | 2017-03-09 09:42
20170314 | 20170314018 | 18 | HMA | Line #530 HMA Pavement 3 LT 58-28 S - Sheet 77 of the miscellaneous quantities under the Asphaltic Summary. Intersections CTH I (N), CTH I (S) and CTH K show a large amount on tons. Is this accurate? | Yes, Quantities for these three intersections include right-turn lanes. | Scott Lawry | 7 | 2017-03-06 14:40 | 2017-03-09 09:43
20170314 | 20170314018 | 18 | HMA | Sheet 10 shows detail for intersections. Verify HMA depth as the detail for B-B does not give a thickness, C-C does not give a thickness and A-A has a note that refers to a butt joint detail. That reference appears to show 5" but I would like that verified for all 3 locations. Other than A-A, B-B and C-C there is a cross hatched section for the rest of the intersection. Can you verify that depth. | The intent of these intersection details is to show typical shoulder and grading limits. Asphalt pavement thickness can be found on the Typical Sections. Most of these intersections will be paved 5â€ (3 ¼â€ lower, 1 ¾â€ upper). | Scott Lawry | 8 | 2017-03-06 14:55 | 2017-03-09 09:44
20170314 | 20170314018 | 18 | B-59-104 Concrete Surface Repair | In the general notes for B-59-104 it states that after cleaning parapets, any concrete surface repair required would be incidental to concrete masonry overlay. There is an item for concrete surface repair for this structure, so should the concrete surface repair on the parapets be considered part of this bid item or is it truly incidental to the concrete masonry overlay? | After â€œCleaning Parapetsâ€ if any areas are determined to require Concrete Surface Repair, those areas shall be repaired and completed to the satisfaction of the engineer prior to application of â€œProtective Surface Treatmentâ€. This work will be paid for under the Concrete Surface Repair item, 509.1500. The note on the plan for B-59-104 will be updated post let. | Scott Lawry | 9 | 2017-03-08 15:42 | 2017-03-09 15:32
20170314 | 20170314018 | 18 | Typical Finished Section | Sheet 6 shows the typical finished section for Sta 305+50-348+00. The cross sections show only excavating beyond 12' from the reference line to a 15" depth. This will be approx. 9" below the bottom of the existing pavement. Because constructability issues will require us to also excavate the 2' area below the asphalt base( 10'-12') to depth of 15", will this additional excavation and 1 1/14 BAD replacement be paid under the appropriate contract items? Common and 1 1/4" BAD? |  |  | 10 | 2017-03-13 15:28
20170314 | 20170314019 | 19 | Clearing and Grubbing | Will the department require all clearing and grubbing to be completed per the plan? | The plan includes clearing and grubbing for all areas where culvert lining operations may require clearing and grubbing. The contractors means and methods will dictate the final location and amount of clearing and grubbing that will be required. | Scott Lawry | 1 | 2017-03-10 13:09 | 2017-03-10 13:13
20170314 | 20170314022 | 22 | Davis Bacon Act Wages | The wages included in the contract state: Highway, Airport & Taxiway Construction Projects (does not include bridges over navigable waters; tunnels; buildings in highway rest areas; and railroad construction) This is a bridge project on a navigable water, does this mean Davis-Bacon does not apply and an hourly minimum wage of $10.20 is the MINIMUM rate an employee can be paid? | An addendum will be developed to add the necessary Davis-Bacon wages for Construction Type: Heavy. | Scott Lawry | 1 | 2017-02-23 09:52 | 2017-02-27 16:57
20170314 | 20170314028 | 28 | SPV.0180.03 Fog Seal | Section B.1 Asphalt Material for Fog Seal states to provide CRS-2P or HFRS-2P as a fog seal material. Using a Polymer modified oil as a fog can result in a reduction in friction on the surface causing a safety concern. Therefore, we request that CSS-1H and CQS-1H be added to section B.1 as other options to use as Fog Oil. | An addendum will be submitted soon. | Scott Lawry | 1 | 2017-03-01 16:42 | 2017-03-03 11:34
20170314 | 20170314029 | 29 | SPV.0180.03 Fog Seal | Section B.1 Asphalt Material for Fog Seal states to provide CRS-2P or HFRS-2P as a fog seal material. Using a Polymer modified oil as a fog can result in a reduction in friction on the surface causing a safety concern. Therefore, we request that CSS-1H and CQS-1H be added to section B.1 as other options to use as Fog Oil. | An addendum will be submitted soon. | Scott Lawry | 1 | 2017-03-01 16:44 | 2017-03-03 11:34
20170314 | 20170314030 | 30 | Soils Report | Please transmit the subsurface exploration reports referenced in the general notes of proposal #30 in the 3/14/17 letting. | The file has been saved: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314030/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nw.aspx | Scott Lawry | 1 | 2017-02-16 10:06 | 2017-02-16 17:35
20170314 | 20170314030 | 30 | HT Pavement Lift Thicknesses | On both RAB's, the HT pavement lift thickness is: Upper 2.5" 4HT 58-34V Lower 3.5" 3HT 58-34H Lower 4.0" 3HT 58-34H From our experience we see better results with thinner lifts. We feel something like the following would perform better: Upper 2.0" 4HT 58-34V Lower 2.5" 3HT 58-34H Lower 2.75" 3HT 58-34H Lower 2.75" 3HT 58-34H | WisDOT has relooked at the pavement depths, and is not planning on changing the depths at this time. | Scott Lawry | 2 | 2017-02-23 10:55 | 2017-03-02 17:15
20170314 | 20170314030 | 30 | Temp Ped Surface Asphalt | Path is shown as 5' wide. This is difficult if not impossible with a paver. 6' wide is somewhat doable but 8' wide is preferred. Either way you look at it 6' or 8', the aggregate base needs to be 9' wide to accommodate the paver. 5' wide will be hand work, functional but not the best. If it is understood what a 5' wide temporary asphalt path will look like that is fine, however if we look at the specification then the cost of the additional material to pave the path wider with a machine will be less than the cost to form up the temporary path for handwork. | The temporary pedestrian accommodations are based on WisDOT Standard Detail Drawing 15D-30C. The SDD calls for a 4â€™ minimum, 5â€™ desirable temporary pedestrian access. If there is adequate room to construct a larger access, and the contractor chooses to build a larger path for constructability purposes, that is acceptable, however, payment for the temporary access width will not exceed the dimensions as indicated in the plans. | Scott Lawry | 3 | 2017-02-23 11:00 | 2017-02-27 16:40
20170314 | 20170314030 | 30 | 1570-02-73 RAB | North leg of the RAB, the first +- 75 LF is specified as HT mix whereas the remainder of the leg is MT mix. This is supposed to be paved under the same stage. Doing it this way will cause an unnecessary joint. Could the entire leg be paved with HT mix? Or at least the surface course? | The north leg of the West RAB, Norway Street, is specified to have the upper layer as 4MT58-34H. The stationing for this mix is from 300+00 â€“ 302+90. 300+00 begins right at the edge of the circulating roadway. The north leg of the East RAB, USH 63, is specified to have an HT mix for the entire length. | Scott Lawry | 4 | 2017-02-23 11:41 | 2017-02-27 16:42
20170314 | 20170314030 | 30 | Prosser Ave | From +- 13+00 "PR" to +- 14+50 "PR", the plan calls for an HT mix. On either side of this section the plan calls for MT mix. It appears all this mix is to be paved in the same phase. This will create unnecessary joints. Would it be better to pave all of Prosser Ave with an HT mix? | The local roadways outside of the intersection/turning movements do not warrant the HT mix design. Prosser Avenue, outside of the intersection limits, will continue to have the MT mix design specified. | Scott Lawry | 5 | 2017-02-23 11:43 | 2017-02-27 16:43
20170314 | 20170314030 | 30 | RAB Night Paving | Special provisions call out paving the RAB's at night and allow a single closure for each RAB. Being conservative we feel it will take 2 nights to pave the RAB's and the legs. Can you change the special provisions to allow for additional nights of paving? | Only one night of roadway closing should be allowed for each roundabout, a total of 2 nights. The main goal of the nightly closure is to pave the top surface of the roundabout circulatory roadway in a single pass. It is permissible to pave the roundabout legs with flagging operations once US 8 is open. | Scott Lawry | 6 | 2017-02-23 11:45 | 2017-02-27 16:44
20170314 | 20170314030 | 30 | Asphalt Curb | There is a bid item for Asphalt Curb, 481 LF. Sheet 157 shows +-475 feet of this item with a note saying "Material for asphalt curb shall be paid for under Asphaltic Surface Temporary bid item". As you know the bid item for asphalt curb includes the material. Need clarification on how to bid this item. | The note on page 157 that states â€œAsphaltic Curb (PAID FOR UNDER â€œASPHALTIC SURFACE TEMPORARYâ€ BID ITEM)â€ is incorrect. There is quantity under the asphaltic curb bid item to cover the quantity, and the bid item will be paid for under 465.0310, Asphaltic Curb. | Scott Lawry | 7 | 2017-03-03 16:04 | 2017-03-07 15:19
20170314 | 20170314031 | 31 | Joint Repair | Can the steel plates used in joint repairs be cut, provided the joint is tight? As drawn, some panels weight close to 200#, and if we can use two smaller pieces of steel instead of one, it is much safer to handle in a confined space. In addition, if water is present in the box, will the Dept. permit mechanical fasteners in lieu of adhesive anchors when installing the steel plates? | The steel plates in the joint repair can be cut into 2 pieces if the joint is tight. The designer not have an issue using mechanical anchors if there is water present in the box at the time of installation. However, the mechanical anchors would only be used where there is water present. Areas above any water present in the box would still be adhesive anchors. | Scott Lawry | 1 | 2017-03-13 10:24 | 2017-03-13 10:51
20170314 | 20170314031 | 31 | Sheet Piling, Permanent Delivered and Installed | Will The Department permit the contractor to leave handling holes in the top of the permanently placed sheet piles? | The handling holes should not be left in place in top of the permanent placed sheet piles. They will need to be closed after installation. | Scott Lawry | 2 | 2017-03-13 10:54 | 2017-03-13 13:55
20170314 | 20170314034 | 34 | Deck Finishing equipment | Being that there is such a small quantity of concrete masonry overlay and ready-mix concrete is permitted, will a vibratory screed be allowed for the overlay? | A1) Ready mix concrete can't be used for the overlay placement, the use of that material is allowed for Item SPV.0035.01 Concrete Masonry Deck Patching. For the Concrete Masonry Overlay Decks item, read Section 501.3.5.1 in 2017 Wisconsin Standard Specifications. A2) No, Please read Section 509.3.2 in 2017 Wisconsin Standard Specifications. | Scott Lawry | 1 | 2017-03-06 11:13 | 2017-03-07 15:49
20170314 | 20170314034 | 34 | Concrete Overlay Material and Methods | Q1) Can ready mix concrete meeting the requirements of class E be allowed for the overlay placement? Q2) Can a truss screed be utilized for finishing of the overlay placement (air screed)? | A1) No, Please read Section 501.3.5.1 in 2017 Wisconsin Standard Specifications. A2) No, Please read Section 509.3.2 in 2017 Wisconsin Standard Specifications. | Scott Lawry | 2 | 2017-03-07 15:31 | 2017-03-07 15:38
20170314 | 20170314035 | 35 | Borrow quantity | For the -72 project, the Select borrow quantity seems to be the entire fill plus the expanded marsh backfill CY. That doesnâ€™t relate to what the plans say. Also, there is no quantity / table for the 1 foot select borrow lift for any part of this project. This is different from the -73 project where it seems to have the select borrow split up for the 1 foot lift along with a separate quantity for the fill. Can you clarify the select borrow for both projects? | For the -72 project, the select borrow was originally meant to be used for ALL of the fill, including Marsh Ex, regular fill, and the 12â€ lift. We are going to be changing the quantity of select borrow so that it is used for marsh fill and a 12â€ lift. The regular fill (above marsh, below 12â€ lift) can be used from the common excavation material, as there is going to be a large amount of common on the site. The quantity for select borrow was actually correct, but it not spelled out very well in the table â€“ there was extra quantity in Expanded Fill column on page 25 that accounted for the 1â€™ select borrow lift. An addenda is expected to be issued to correct this and clarify the select borrow. The -73 project numbers are correct. The fill quantity is separated out from the select borrow quantity. The fill needed should come from the otherwise excavated material, the select borrow is a separate quantity and should meet Grade 2 requirements | Scott Lawry | 1 | 2017-02-16 09:51 | 2017-02-16 09:52
20170314 | 20170314035 | 35 | 8865-00-72 Reheating Longitudinal Joints | It appears plan quantity for Reheating Longitudinal Joints includes quantity for mainline lower and upper layer as well as side roads. Past projects have only included mainline upper layer. With the mainline on this project being relatively short, is the item even necessary? | Reheating the longitudinal joint will be required, but only on the upper layer. An addenda will be issued to reduce the proposal quantity and revise the plan sheet. | Scott Lawry | 2 | 2017-02-23 11:47 | 2017-03-02 17:15
20170314 | 20170314035 | 35 | Mix Type Selection | 8865-00-73 shows an HT mix type whereas 8865-00-72 shows an MT mix type. Is the turning movements of this intersection any different than other intersections? If this were a regular mainline paving project they would not have segregated this intersection out as an HT mix and did the remainder of the project as an MT. Any chance to change 8865-00-73 to an MT mix? | Due to the turning movements at the intersection, the HT mix will be required for the 8865-00-73 project. | Scott Lawry | 3 | 2017-02-23 11:50 | 2017-03-02 17:16
20170314 | 20170314035 | 35 | Borrow | Q1: There is a large quantity of select borrow excavation that has to be grade 2 on this project and there is a large quantity of excess waste material on the project from common excavation. It appears from what I have seen on the project and from talking with neighbors that a large portion of the project excavation cut material will be a sand material. Is there a reason they are specing in the grade 2 select borrow? Is there a reason why the common excavation cut material that is sand can't be used for the select borrow fill areas? Q2: What are the rules/regulations for crushing base aggregate materials. I know when you borrow or waste materials on a property off of the project limits it requires an ECIP and then if everything works out with that it is approved to do. How about if you wanted to set up a crusher on someones property and crush materials off of their land. Is it the same rules or is there special circumstances/permitting for this? | A1: The reason we called for Select Borrow is because we wanted to ensure that the material backfilled be good material in the marshy areas. You are correct, the existing material is very sandy, and there is possibility that the material onsite will meet the Grade 2 specifications, if so, you will be able to use the cut material as the fill. There will be an addenda issued before the bid let that will clarify some of these numbers. A2: For waste and borrow materials, when you use a select site/private property the site is approved/cleared during the ECIP process. A commercial site already would have a stormwater permit, and DNR involvement for wetlands, so a commercial site does not have to be approved in an ECIP. Setting up a crusher on site that isnâ€™t already permitted for that purpose opens up a host of new questions â€“ especially if you are planning on using the material as something other than borrow. Processing or crushing materials off of the land would be considered a mining operation, and would require permitting over and above the ECIP, potentially including local, county and state agency permits. Prior to starting construction you will have to submit a â€œSource of Materialsâ€ document. This document identifies where you are getting your materials from. The materials must be from a WisDOT certified source, certification lasts from 3 to 5 years depending on the classification. Source locations for materials are not included in the ECIP because the source sites have already been through a permitting process with the local and state agencies. | Scott Lawry | 4 | 2017-02-27 16:29 | 2017-02-27 16:31
20170314 | 20170314035 | 35 | RCCP Class V 24" | Seems that the quantity for the Culvert Pipe Reinforced Concrete Class V 24" maybe incorrect. On page 26 of the plan it calls out 115 LF at station 448+60 while there is already a 113 LF in item 525.0124. Plan shows 525.0124 should be correct. | The culvert pipe located at 448+60 is called out as corrugated aluminum on the plan sheets. The pipe will be installed as aluminum and paid for as such. An addendum was just submitted to address the issue. | Scott Lawry | 5 | 2017-03-03 07:48 | 2017-03-09 13:33
20170314 | 20170314035 | 35 | Weight LImits | Question: There is a road ban/weight restriction that has been placed on STH 65 in Polk County. Is there special permission that can be granted to access the site to do test pits? It appears that several contractors have been on site doing test pit digging. | Answer: For access to the site, please contact Lance Burger, lance.burger@dot.wi.gov, or 715-392-7965, for an exception on the weight limit. | Scott Lawry | 6 | 2017-03-07 14:30 | 2017-03-07 14:31
20170314 | 20170314035 | 35 | Material Source | The Town of Alden has a gravel pit approx. 2 miles from the project. The Town of Alden says that they have agreed to sell materials out of there pit to the contractors bidding the DOT #35 project to be used on the project. They are planning to have a meeting to set the price of the material for the contractors this Thursday evening. I am under the understanding that the contractors are allowed to use this material and pay the township directly for this material. I just want to confirm that this is correct that we are able to purchase the material from the Town of Alden? | The Town of Alden would be a supplier of materials. Material purchasing can be from the source/supplier that you choose. Please keep in mind that different prevailing wages apply to different sources of materials. The materials supplied from any source shall meet the standards and specifications as shown in the standard specifications, additional special provisions, plans, special provisions and addenda included with the contract. | Scott Lawry | 7 | 2017-03-08 09:34 | 2017-03-08 09:43