## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170411 | 20170411003 | 3 | MSE Wall - Panel Size | Hello - Will the Department require the standard panel size for the MSE walls to measure 5'x5' similar to the other walls along IH39? Thank you. | There is no requirement for a specific panel size for the MSE walls. Bidder should estimate per the special provisions. The special provisions include loading and dimensional restrictions, including: â€œThe maximum height of a standard panel shall be 5 feet.â€ | Scott Lawry | 1 | 2017-04-04 08:08 | 2017-04-04 16:17
20170411 | 20170411003 | 3 | Emulsified Asphalt SPV.0180.01 | In the C. Construction section, it states to "Construct to a minimum depth of 6 inches." The E. Payment section states that this item is only for emulsified asphalt. Is the intent of the item to also place slope paving crushed aggregate, incidental to the Emulsified Asphalt? | The item â€œSPV.0180 Emulsified Asphalt Median Treatmentâ€ is to conform to standard spec 604.2 including 604.2(3) for slope paving crushed aggregate. As stated in 604.2(3) the crushed stone is to be furnished by this item. Payment for the bid items is full compensation for excavating and backfilling required for preparing the paving foundation; for disposing of surplus materials; for providing, handling, placing, and consolidating the crushed aggregate; and for providing, handling, heating, and applying asphaltic material binder. | Scott Lawry | 2 | 2017-04-05 10:14 | 2017-04-06 09:36
20170411 | 20170411003 | 3 | Timber Pile Removal | Can the department provide the estimated number of and the estimated lengths of the timber piles to be removed? | The existing timber piles in Pier 1 (the western pier) and Pier 3 (the eastern pier) were not considered in conflict. The designer estimated 23 of the 25 existing timber piles in Pier 2 (the center pier) to be in conflict. The approximate location of these existing timber piles are shown in the footing plan on the pier details (structure B-13-648â€™s sheet 10, plan sheet 149). The boring logs show the lengths of the 23 existing timber piles to be from 7.5-feet to 12-feet long with a total length of 239-feet. | Scott Lawry | 3 | 2017-04-05 10:16 | 2017-04-07 10:18
20170411 | 20170411004 | 4 | Bearing Maintenance for B-41-30, B-41-31 | These questions relate to the bid items SPV 00600.01 and SPV 00600.02, Bearing Maintenance on B-41-30,B-41-31 Q1: In Section A of the specials for this it describes work at the abutments and piers but the plan only shows work at the abutments on each structure. Will there be any work on the pier bearings? Q2: In C.1 of the specials it states to pull out the existing bolts and install new bolts in the existing holes. If the anchors break off in the holes while removing them or if they are already sheared off can they be cut off flush, and new holes drilled in the masonry plates for the new anchors? | A1: Only bearings at the abutments are to be worked on. No work on the pier bearings. A2: If the anchor bolts cannot be pulled out, the fix will be to cut anchor bolts flush with the concrete and drill new holes for new anchor bolts. | Scott Lawry | 1 | 2017-03-22 12:23 | 2017-03-24 13:04
20170411 | 20170411004 | 4 | Integral Barrier Wall Height | Please clarify the height of the integral barrier walls. Plan sheets #74 and #82 show wall details and indicate a dimension of 4'3" at full height. The cross section details in the upper left show this dimension from the bottom of the slope paving to the top of the wall. Should this dimension be from the top of footing to the top of wall? | The 4â€™-3â€ dimension is from the top of the slope paving to the top of the wall. This is the maximum distance the wall is allowed to cantilever above the ground on the back side. | Scott Lawry | 2 | 2017-03-22 13:38 | 2017-04-03 10:07
20170411 | 20170411004 | 4 | Bearing Maintenance - Remove Anchor Bolts | SPV.15 - Bearing Maintenance indicates that the existing anchor bolts are to be pulled out and new anchors installed in the existing holes. Would it be acceptable to drill new holes in the opposite corners of the masonry plates and install new anchor bolts in new holes instead? | Yes, it is acceptable to cut the existing bolts off flush and drill new holes in the opposite corners. | Scott Lawry | 3 | 2017-03-22 13:44 | 2017-03-27 12:42
20170411 | 20170411004 | 4 | Square footage for Line 0340 & 0350 Item 517.3000.S | What is the total square footage of steel that needs to be painted for line items 0340 and 0350? | Please review the special provisions for this item, this information is article 13 that can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2017/04April_11/20170411004proposal.pdf | Scott Lawry | 4 | 2017-04-05 15:05 | 2017-04-07 11:17
20170411 | 20170411005 | 5 | Milling/HMA next to SPBG | Plan shows the existing SPBG will remain in place during the project with areas where the face of the rail is at the outer edge of the existing shoulder. A small portion of the existing shoulder next this rail will have to be left in place as equipment can not fit with the rail left up. Would assume this was the intent and will be acceptable. Also, if rail is left up that no new 3/4" BAD will be placed behind this rail as it would have to be all done by hand. | As the plan indicates, the entire shoulder is to be removed and replaced. Handwork may be required to remove the existing shoulder material and/or place the 3/4 â€“inch base aggregate dense around the existing beam guard. The contractor should bid the job accordingly. | Scott Lawry | 1 | 2017-03-29 12:12 | 2017-04-03 10:59
20170411 | 20170411006 | 6 | Asphalt Paving | 1. Plan sheet 3 Typical shows 2.5" AS in median and plan sheet 8 median detail shows 3" AS in median. Which is correct? 2. The HMA specified is 4 LT 58-28 S. Wondering if a 4 MT 58-28 S -or- a 4 LT 58-28 H would be better due to the stopping, starting, and turning traffic? | A1--2.5â€ AS should be included in the median. Match Existing A2--No change is recommended to the HMA Pavement type. Use HMA Pavement 4 LT 58-28 S as-is currently in the plan. The calculated ESALâ€™s (Equivalent Single Axle Loads) for CTH P is 310,000 which is well below the 2,000,000 threshold for the use of LT mixes. USH 51 mainline traffic will not be utilizing the new pavement. | Scott Lawry | 1 | 2017-03-23 11:29 | 2017-04-03 09:59
20170411 | 20170411010 | 10 | 0670 SPV.0125 9.600 MI Special 01. Sealing Asphaltic Pavement Cracks, STH 19, Dane County | After evaluating the project. We feel that STH 19 is deteriorated beyond the extent of crack repair. We do not think that crack repair would do this road justice. Therefore, we recommend that the road be reconstructed. | The department is aware of the condition of the existing roadway. The proposed project is to extend the pavement life until a more substantial repair of the roadway can be completed. | Scott Lawry | 1 | 2017-03-29 10:26 | 2017-04-03 10:58
20170411 | 20170411010 | 10 | Removing Asphaltic Surface Milling | The proposed typical section on page 4 of the plan set shows the item Removing Asphaltic Surface Milling with additional information stating (3-inches depth; 4-foot width). However, the typical section also shows only a 3-foot width of existing asphalt being removed. The miscellaneous quantities also equates to a 4-foot width to be paid. Will the contractor be paid for the 4-foot width even though 3 feet of asphalt is being removed? | Yes, the contractor will be paid a 4-foot width for the Removing Asphaltic Surface Milling item. 4 feet of material will need to be removed to install the new asphalt, and it was anticipated the contractor would utilize a 4 foot mill to perform the work. | Scott Lawry | 2 | 2017-03-31 16:26 | 2017-03-31 16:26
20170411 | 20170411010 | 10 | Salvaged Asphaltic Shoulder Material | The proposed typical section on page 4 of the plan set shows the entire gravel shoulder to be Salvaged Asphaltic Shoulder Material. Is the intent to remove the existing shoulder gravel to install a full 3-inch depth of salvaged material? | No, the intent is not to remove the existing shoulder gravel. The Salvaged Asphaltic Shoulder Material item will be used to place material as needed on the existing shoulder. However, based on field visits, the existing shoulder is low, so it will require material to bring it up to the finished grade. Per 305.2.2.1 (2), limit the allowable reclaimed asphalt content to 50 percent or less. | Scott Lawry | 3 | 2017-03-31 16:27 | 2017-03-31 16:28
20170411 | 20170411010 | 10 | Asphaltic Binder Enhanced Friction Surface Treatment | For the item Asphaltic Binder Enhanced Friction Surface Treatment, it states that the products used for HMA are fully cured before placing the EFST. How long does it take for HMA to cure? | There is typically not a standard cure time for HMA pavement. The contractor should follow the recommendations of the manufacturer that is providing the enhanced friction surface treatment. | Scott Lawry | 4 | 2017-03-31 16:28 | 2017-03-31 16:29
20170411 | 20170411010 | 10 | Asphalt Binder Enhanced Friction Surface Treatment | For cure time on HMA pavement the EFST manufacturer is recommending 1 year for cure. The Completion date for this project is August 18, 2017. Can the EFST be installed next year to give the new HMA proper time to cure? | Based on observations from previous projects and assuming similar performance, the contract remain as-is and applying the Enhanced Friction Surface Treatment. | Scott Lawry | 5 | 2017-04-03 13:09 | 2017-04-04 15:40
20170411 | 20170411010 | 10 | Cracksealing Question | Considering the condition of the existing pavement. There is a concern for mechanically routing the cracks and potentially creating more damage to the already deteriorated pavement. We recommend that the agency instead utilize the clean and seal method using a fiberized crack sealant material such as Polyfiber. | An addendum will be developed to address this issue | Scott Lawry | 6 | 2017-04-03 13:34 | 2017-04-04 16:15
20170411 | 20170411011 | 11 | Square footage of line item 0220 517.3000.S | What is the total square footage of steel that needs to be painted for line item 0220 517.3000.S? | The total square footage of steel that needs to be painted for line item 0220 517.3000.S is 20 SF | Scott Lawry | 1 | 2017-04-05 15:07 | 2017-04-06 12:54
20170411 | 20170411011 | 11 | Overlay limits | The overlay is shown to extend to the face of the existing Type F rail. This is problematic due to the removal and placement operations necessary to complete the concrete overlay work, i.e. the railing has to be removed and replaced(not possible without causing a large fall protection hazard) or the overlay extents can be moved 6" away from the face of the railing. Please determine which one will be allowed if possible or if both are possible that is fine as well. | The expectation is that the overlay limits are as close to the railing as possible and as depicted in the plans. The plans will not be revised at this time. | Scott Lawry | 2 | 2017-04-10 13:40 | 2017-04-10 15:08
20170411 | 20170411015 | 15 | UTILITY LINE OPENING | WHERE ARE THE ANTICIPATED 66 UTILITY LINE OPENINGS LOCATED? | Please review the miscellaneous quantities pages within the plans for the locations. Page 41--47 total Page 232--4 total Page 344--15 total | Scott Lawry | 1 | 2017-03-22 14:15 | 2017-03-24 12:29
20170411 | 20170411016 | 16 | Signing | The street name sign plate on p. 176 states that all signs are Type II, Type SH. There is no quantity in the bid items for this. Is the correct sheeting listed? | The detail has a typo, it should be type H not type SH sheeting. The items listed in the proposal are correctly specified as requiring Type H sheeting | Scott Lawry | 1 | 2017-03-21 09:22 | 2017-03-24 08:29
20170411 | 20170411017 | 17 | Earthworks | Are there soil borings available for this project? | No soil boring data is available for this project. | Scott Lawry | 1 | 2017-03-30 09:03 | 2017-04-05 14:38
20170411 | 20170411017 | 17 | Can the Design Schedule be provided? | Can the Design Schedule be provided? | The schedule can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170411017/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 2 | 2017-04-03 15:22 | 2017-04-06 09:51
20170411 | 20170411017 | 17 | Excavation Quantity. | Can WisDOT correct the Common Excavation table on sheet 236 of the plans? | Contractors should prepare bids based on the quantity provided in the plan. | Scott Lawry | 3 | 2017-04-05 10:27 | 2017-04-07 10:21
20170411 | 20170411017 | 17 | Concrete Sidewalk Closure | Will the construction of the new sidewalk be limited to off peak hours only? The specification states that sidewalk closures may only occur from 10:00 pm to 5:00 am. Does this require the sidewalk areas to be removed, excavated, and replaced all in one off peak hour shift? Will closures be allowed during peak hours? | Sidewalk work can be completed during peak hours but the use of the Temporary Pedestrian Items, provided on sheet 250 of the miscellaneous quantity sheet, will be required. | Scott Lawry | 4 | 2017-04-06 16:38 | 2017-04-07 12:29
20170411 | 20170411017 | 17 | Is the new 9" Concrete pavement to be reinforced or not? | The plan does not call for reinforced concrete pavement in the proposed cross sections. Is the new pavement to be doweled or not? | The pavement is to be doweled. Please refer to the Standard Detail Drawings (SDDs) location in the plan for additional details. SDDs 13-13C01-18, 13C08-02, 13C13-08, 13C14-06A thru C and 13C18-03A thru D all provide additional information for the pavement reinforcement. | Scott Lawry | 5 | 2017-04-09 17:08 | 2017-04-10 08:25
20170411 | 20170411018 | 18 | Electronic file availability | We would like to request the following CAD files to assist with our planning and quantity verification processes. 1. Existing Conditions Survey Surface CAD files (Format: LandXML, .Dwg or .DGN) 2. Existing Condition Survey Mapping CAD files (Format: LandXML, .Dwg or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .Dwg or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .Dwg or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .Dwg or .DGN) We understand the PDF plans are the contract documents and any CAD files provided will be for information only and may not match the PDF plans. | The files can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170411018/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Scott Lawry | 1 | 2017-03-23 13:50 | 2017-03-24 12:49
20170411 | 20170411018 | 18 | Soils Report | Are soil borings available for this project? Also, is there a proposed schedule that the Department has? Any questions please let me know. | The files can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170411018/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx The time chart provided is considered draft and not for bidding purposes. The contractor is required to develop a schedule and bid that adheres to the requirements of the plans, provisions, standard specifications and any addendum that are developed. | Scott Lawry | 2 | 2017-03-23 13:54 | 2017-03-24 13:00
20170411 | 20170411018 | 18 | Culvert and Storm Sewer | Based on ADT from CTH C to STH 20 below 7000 ADT, will contractors be permitted to use alternative/competitive specifications for storm sewer and culvert bid items? | The department stayed with concrete pipe since so many of the pipes were within 2ft of subgrade. For efficiency and practicality for both design and construction, the department stayed with one material of pipe. | Scott Lawry | 3 | 2017-03-27 11:30 | 2017-04-03 10:04
20170411 | 20170411018 | 18 | Traffic Flashing Beacon System, Solar | I have a question regarding the Solar Flashing Beacon Systems; SPV.0060.05 & SPV.0060.06. Will you allow the Carmanah Beacon(s) to be bid as an approved equal? We would most likely bid the Solar Panel from the R247-E system, and the Beacon/components from the R247-G System. Please contact me if you need further information. Thanks! | An addendum was developed to address this issue. | Scott Lawry | 4 | 2017-03-31 15:59 | 2017-04-04 16:10
20170411 | 20170411018 | 18 | Earthwork | Are the earthwork data sheets available in excel format for this job? | The excel file can be found at http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx or ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170411018/ | Scott Lawry | 5 | 2017-04-03 10:47 | 2017-04-04 16:01
20170411 | 20170411019 | 19 | Geotechnical Investigation | Can the Department provide a copy of the subsurface exploration? | The report can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170411019/ | Scott Lawry | 1 | 2017-04-03 11:01 | 2017-04-06 09:54
20170411 | 20170411019 | 19 | hydrant relocation | two of the hydrants call for abandoning existing tee. The new location of the hydrant will require a new connection to existing 16" watermain. The new connection is not addressed in the special conditions. Can you address that issue ? | Please see page 45 of the plan, the Water Main Relocation Plan calls out the location of the hydrants. | Scott Lawry | 2 | 2017-04-10 11:47 | 2017-04-10 14:41
20170411 | 20170411020 | 20 | Split Faced Field Stone Masonry | Shouldn't the split faced field stone masonry be paid for by the SF instead of the CY? | The split faced field stone masonry is being paid for by the CY since the wall thickness is not uniform. This special item was created based on specials for the previous bridge project in Whitnall Park. That project had new bridges built with consistent flat concrete surfaces and so they used SF as the thickness was uniform. The use of the special measured by CY as the thickness is not uniform and there are single faced (with concrete back up wall) and double faced walls (with no concrete back up) on the top of the wingwall being rehabilitated. | Scott Lawry | 1 | 2017-04-03 08:48 | 2017-04-04 16:13
20170411 | 20170411020 | 20 | Bypass | Will a temporary diversion channel be allowed, similar to what is used in box culvert construction. Open trench with plastic sheeting and course agg. in the bottom? | Temporary diversion channel is allowed as per plans and specifications thru diversion pipe, similar to what is used in some box culvert construction. Any open trench diversion channel and corresponding ECIP can be proposed and coordinated/approved by construction engineer, WisDOT and DNR. | Scott Lawry | 2 | 2017-04-05 11:30 | 2017-04-07 10:09
20170411 | 20170411021 | 21 | Preboring Piles | Can the department provide clarification on the Preboring Unconsolidated Material and Preboring Rock or Consolidated Material quantities called out on the Estimate of Quantities Table (Sheet 84)relative to the denoted piles to be prebored on Sheet 89? The quantities don't seem to match up with estimated pile lengths? Are there more than just the 8 locations depicted on Sheet 89 that get prebored? | Preboring Unconsolidated Materials as noted on sheet 84 is for the purpose of locating underground utilities and reducing vibration to those utilities, specifically the 96" MMSD concrete pipe. â€¢ At the South abutment there are two piles circled for preboring, at 30ft length for a total of 60LF. â€¢ At the Pier 1 there are two piles circled for preboring, at 25ft length for a total of 50LF. â€¢ At the Pier 2 there are two piles circled for preboring, at 25ft length for a total of 50LF â€¢ At the North abutment there are two piles circled for preboring, at 35ft length for a total of 70LF. Preboring Rock or Consolidated materials is not specifically called out on the plans. As noted in the geotechnical report and sheet 88: â€¢ The hard dense layer at the abutments is at an approximate elevation of 40'.0. Based on expected refusal depth and required bearing elevations it was determined that the piles would require approximately 2' of hard rock coring to reach required driving depths and bearing capacity. There are 12 piles per abutment multiplied by 2' for 24LF per abutment. â€¢ The hard dense layer at the piers is at an approximate elevation of 43.0. Similar reasoning for the calculated driving depths and bearing capacity determines that each of the 24 piles per pier may require hard boring for 2' for a total of 48LF per pier. Pile points are calculated at the piers for all piles not being prebored at the utility due to the possible presence of cobbles in the waterway. Per the Bridge Manual, all pile lengths are rounded up to the nearest 5' in the estimate of quantities. The contractor should reference the geotechnical report and field conditions to determine final pile lengths, bearing depths, and driving requirements of all piles to reach the capacities as noted in the 'Foundation Data' on sheet 83. | Scott Lawry | 1 | 2017-04-05 10:22 | 2017-04-06 10:12
20170411 | 20170411022 | 22 | Culvert Bid Items | Based on ADT, will contractors be permitted to use competitive bid items for culvert bid items? | The maintaining authority is Kenosha County, their preference has always been either steel plate or concrete. | Scott Lawry | 1 | 2017-03-27 11:55 | 2017-04-03 11:15
20170411 | 20170411024 | 24 | Asphalt Paving | 1.On page 6,the typical shows the median 6â€™ shoulder to be paved with a 3 LT and a 4 LT material. The contractor would like to pave the 12â€™ mainline and 6â€™ shoulder integrally using the 3 HT 58-28 S for the binder and the 4 HT 58-28 S for the surface, which would eliminate the joint and provide a better quality product for the DOT. Also, I see the existing and proposed shoulder slope is called out as a 6%. I just want to verify that this is what was intended as typically the shoulders do not exceed 4% unless they are in a super elevation? 2.On page 7, the ramp typical calls out LT and HT mixes on different areas of the shoulders. With the short length of the tie-ins on the ramps, would the contractor be able to use all HT in order to try and eliminate the joints at the shoulders? 3.On page 12, the butt joint detail calls out 200â€™ for mainline and ramps but the miscellaneous quantities seem to be using 50â€™ as the limits for the ramps. I would just like to verify which one is correct. | A1--For the 6 â€˜ shoulder the Department would like to pave LT mix on shoulder, so paving integral with HT mix is not an option, bid as shown in plans. 6% shoulder slope is existing, overlay to plan thickness. A2--Pave as shown in typical sections with HT and LT mixes A3--The addendum addresses this detail. | Scott Lawry | 1 | 2017-04-07 08:48 | 2017-04-07 09:03
20170411 | 20170411024 | 24 | Pavement Marking | I have a question regarding the temporary paint item on this project. On sheet 48 it shows temporary on the lower layer for the edge lines and skips and the quantities seem to support that scenario. My question is what is the plan for the surface layer in terms of temporary as there does not seem to be any allotted for that. Also, the surface layer permanent edge lines, it appears, will not have to go down nightly seeing as there is no same day epoxy item or any notes indicating that. | Follow the existing spec language, there is no temporary paint for edge lines on the surface layer, the permanent edgeline shall go down within 7 days. | Scott Lawry | 2 | 2017-04-07 09:04 | 2017-04-07 09:05
20170411 | 20170411025 | 25 | Machinery Room enclosures | What is the finish requirement for the new 4x4x3/8 angles that are required for attaching the new polycarbonate sheeting? Is the rubber gasket required at all 3 interfaces with the new angles? Are attachments required at all three angles? | A1--See Note 6 on S-6 and Steel Painting Notes on S-2. A2--Provide seals and gaskets as stated in Note 7 on Sheet S-6. A3--As per the special provisions, attach sheeting to the framing with stainless steel bolts and nuts with double washers placed at 1-foot maximum centers. Framing consist of top, bottom and middle support angles. | Scott Lawry | 1 | 2017-04-03 10:19 | 2017-04-04 16:11
20170411 | 20170411027 | 27 | Type 10 and 13 Footings | Are there any borings for the locations of the 5 footings that need be drilled into rock? Is it assumed that it is just those 5 special footings and the other 7 will not be in rock? | The file has been posted. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170411027/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nc.aspx The contractor is correct in assuming bedrock will only be encountered at the 5 locations with the special footings. The other 7 signal base locations should not encounter bedrock according to the boring logs provided | Scott Lawry | 1 | 2017-03-27 15:23 | 2017-04-06 07:58
20170411 | 20170411027 | 27 | Lane Closures | Will outside lane closures be allowed in the non-construction portion of the project, from station 141+00 to 167+00 and station 192+00 to 194+00? If so, when would they be allowed? | Isolated lane closures in the non-construction portion of the project will be allowed, however they should be minimized to maintain safe traffic flow. Construction of Stage 1 and Stage 2 can be worked on concurrently. | Scott Lawry | 2 | 2017-04-06 10:42 | 2017-04-07 12:30
20170411 | 20170411028 | 28 | Pipe Bid Items | Based on low ADT, will contractors be permitted to bid with alternate bid items for storm sewer and culvert bid items? | The storm sewer required for this project is being retrofit into an existing concrete system run in heavy clay soil that also has intermitted beaker run material in the road bed for stability. We prefer to see concrete maintained for system uniformity. The cross drain culvert pipes are also run in the same soils as the retrofit storm sewer, and has minimal cover. The pipes should be bid as per the plan. | Scott Lawry | 1 | 2017-03-27 12:07 | 2017-03-29 08:25
20170411 | 20170411030 | 30 | Grade, Shape, Finish Barrier Terminals | What is being done at these locations? The misc quantities call for 962 CY of common ex, not counting the two fill pads. The cross sections show these areas by the guardrail being cut out resulting in the material being waste, for the most part. There are not any quantities for these to be backfilled with base aggregate. | Please watch for addenda. Cross Sections and Misc Quantities will be modified to eliminate the â€œcutâ€ area on the shoulder in the EAT locations. | Scott Lawry | 1 | 2017-03-28 15:15 | 2017-04-03 09:43
20170411 | 20170411030 | 30 | Milled Surface Traffic | After the milling of a lane will you allow the traffic to run on the milled surface until the binder is installed? From my understanding we need to have the traffic control removed each day from 4-6pm. This would allow for fewer mobilizations for the project. | Yes, the plan intent is to allow traffic to use the milled surface in order to facilitate having the traffic control pulled back and lane open for traffic during daily peak travel times. | Scott Lawry | 2 | 2017-04-07 09:19 | 2017-04-07 15:13
20170411 | 20170411030 | 30 | Length of Pavement Repairs. | The Concrete Pavement Repair Doweled Special show lengths of 3' to 10' on sheet 20 of the plans. The standard detail drawings for Concrete Pavement Repairs show a minimum lenght of 6'. The drills used for drilling the dowel bar hole are 60 inches in length and the repair has to be long enough to accomodate a drill in order to drill a true and straight hole for the dowel bars. Please clarify if WisDOT will lengthen the repairs enough to accomodate the drills necessary for drilling the dowel bar holes. | Yes, the repairs can be lengthen to 6' minimum to accomodate the drills necessary for drilling the dowel bar holes | Scott Lawry | 3 | 2017-04-08 10:29 | 2017-04-09 07:50
20170411 | 20170411031 | 31 | Total square footage of line item 0230 517.3000.S | What is the total square footage of steel that needs to be painted for line item 0230 517.3000.S? | The Total Square Footage of Steel that needs to be Painted for Line Item 0230 517.3000.S is to be 4,400 Square Feet. This can be found on Page 18 of 23 in the Standard Special Provisions included in the Proposal under the Item â€˜Structure Overcoating Cleaning and Priming B-18-5, Item 517.3000.S.01â€™. This Item calls out 900 Square Feet of 2-Coat Painting Area and 3,500 Square Feet of 3-Coat Painting Area. These total to 4,400 Square Feet Total. | Scott Lawry | 1 | 2017-04-05 15:08 | 2017-04-06 12:48
20170411 | 20170411033 | 33 | Water elevation | Is the water elevation at construction, going to be Regulatory water elevation or the water elevation shown in the plans? | The water elevation shown on the plan of 770.0 was surveyed on 7/13/13. Water elevation at time of construction is anticipated to be similar to the surveyed elevation given that Half Moon lake fluctuates little, but the water elevation at time of construction cannot be guaranteed. | Scott Lawry | 1 | 2017-03-31 07:51 | 2017-04-03 11:31
20170411 | 20170411033 | 33 | Flagstone Pavers | Are the flagstone paving stones supposed to be irregular shaped as shown in the plans or rectangular and square as described in the specs? Please clarify which stone retaining walls require a seat ledge. Also, the misc quantities show 5 stone retaining walls, looks like the plans show 6, please verify the correct quantity. Is there a specific color that should be required for the stone screenings with binder? | Flagstone Paving, Item SPV.0165.xx Clarification: Contractor shall use irregular shaped flagstone, as shown on plans. Addendum will clarify in special provision. Stone Retaining Wall, Item SPV.0165.xx. Clarification: Three retaining walls with ledge seat are required as indicated on the site materials plan. Clarification: Six total walls required. Wall at 202+35, 65RT, 120 SF is not currently shown on the miscellaneous quantities sheet or in total quantities. New stone retaining wall total is 560 SF. Addendum will clarify. Stone Screenings with Binder, Item SPV.0195.xx. Clarification: Color is to be selected by city from the manufacturerâ€™s standard product colors. Addendum will clarify in the special provision. | Scott Lawry | 2 | 2017-04-06 06:08 | 2017-04-06 12:50
20170411 | 20170411034 | 34 | Culvert Bid Items | Based on low ADT, will contractors be permitted to bid with alternate/competitive bid items for culvert items? | The soils in the area are very corrosive, therefore an aluminized pipe was specified. | Scott Lawry | 1 | 2017-03-27 12:13 | 2017-04-03 10:41
20170411 | 20170411036 | 36 | Asphaltic Surface | Just reading through the proposal and I noticed that the asphaltic surface for the lower lift is specifying a 58-25S? And specifying a #3 (19mm) surface mix? Can you please clarify these? | NWR has started using the standard spec for Asphaltic Surface on most projects so Article 16 Asphaltic Surface will be removed from the special provisions by addenda. | Scott Lawry | 1 | 2017-03-15 14:04 | 2017-03-15 14:05
20170411 | 20170411036 | 36 | Galvanizing requirements | Can you clarify the galvanizing requirements in the general notes on plan sheet 37. | An addenda will be submitted to clarify what hardware needs to be galvanized and add a note saying the weld needs to have cold galvanizing applied. | Scott Lawry | 2 | 2017-04-04 16:21 | 2017-04-04 16:22
20170411 | 20170411036 | 36 | Helical Tieback Anchor Loads | The helical tieback anchor called out has a ultimate capacity of 160 kips however the limiting factor of the anchor is the bolted connection between section. The ultimate capacity of the bolted connection is 150 kips. Is the 150 kip ultimate load acceptable to the department? If not can the two middle anchors at each wing wall be shifted towards the 160 kips anchors, thus reducing the 160 kip loadings and increasing the 50 kips loadings on anchors #1 and #8? | The contract calls for a minimum 150 KSI tensile strength threaded bar on the end of each helical tieback anchor and also requires that tiebacks #4 and #5 have a minimum anchor capacity of 160 KIPS. These requirements are not in error and will not be changed. | Scott Lawry | 4 | 2017-04-07 09:48 | 2017-04-07 15:09
20170411 | 20170411036 | 36 | Helical Tieback Anchors | Referencing the special provisions #20 Helical Tieback Anchors (Section B.7 Concrete Core Hole Grout on Sheet 24), the spec states to preserve and utilize the existing reinforcing steel, â€œblasting it clean and retieâ€. This is not feasible with a cored hole. Can drilled dowel bars, epoxied in, be utilized and if so can a detail be provided? Can a 4000 PSI neat cement grout be used to fill the cored holes to eliminate the high cost of concrete delivered including partial load costs? | The plan requires a 1â€™ 6â€ diameter cored hole through the existing wing. The special provisions require that the contractor preserve and utilize the required remaining existing reinforcing steel. The required existing reinforcing steel is the steel in the wing wall that is not removed in the core meaning that they core through the wing and are not to damage any of the steel in the area that they donâ€™t core. The special provisions require the contractor to blast, align and retie the existing reinforcing steel to be reused. The plan does not show any of the existing steel that is removed in the coring as being reused so this section of the special provisions will not apply to this project because this situation does not exist. | Scott Lawry | 5 | 2017-04-07 10:02 | 2017-04-07 15:35
20170411 | 20170411037 | 37 | Culvert and Storm Sewer Bid Items | Based on low ADT, will contractors be permitted to bid with alternate/competitive storm sewer and culvert bid items? | The bid items shown for the culvert pipes are correct and these should be used for developing bids. There are many pipes on this project that would not meet the necessary fill requirements. Therefore we want to stay with the materials that we have specified. | Scott Lawry | 1 | 2017-03-27 12:21 | 2017-03-29 08:18
20170411 | 20170411038 | 38 | Addendum Traffic Control Sheets | The added "Construction Staging and Traffic Control Sheets", 277AS, 277AT, 277AY, & 277AZ are labeled as traffic control plansheets for stage 4. However, these appear to show and describe workzones that exist during stage 1. Are these plansheets mislabeled? | Sheets 277AS, 277AT, 277AY, and 277AZ include temporary widening/temporary pavement and other work that must be completed along CTH TT and USH 18 during Phase 1 Stage 4 in preparation for Phase 2 construction. Phase 2 Stage 2A shows traffic shifted onto these areas that were constructed under Phase 1 Stage 4. | Scott Lawry | 1 | 2017-04-03 13:52 | 2017-04-04 16:07
20170411 | 20170411038 | 38 | Concrete Paving | Can the mainline concrete pavement be paved at 26-ft wide vs. 24-ft wide through the right turn lanes? | No, due to bicycle lane accommodations, the mainline cannot be paved at 26-ft wide through the right turn lanes. The longitudinal joints would not align for the bike lane between the through lane and right turn lanes. | Scott Lawry | 2 | 2017-04-05 14:37 | 2017-04-05 14:37
20170411 | 20170411038 | 38 | Geotechnical Information | Are soil borings available for this project? Also, is there a proposed schedule that the Department has? | The soils report and time chart can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170314037/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 3 | 2017-04-05 14:46 | 2017-04-06 07:57