## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170509 | 20170509001 | 1 | C-13-3089 & C-13-3084 Construction | Are these culvert extensions to be done during nighttime working hours? | There should be no reason these structures cannot be constructed during the daytime. C-13-3089 is currently protected by existing beam guard. If for some reason the beam guard is removed prior to completion of the C-13-3089 extension, temporary protection of the workzone would be required. The C-13-3084 workzone is outside the required clear zone. All deliveries of equipment and materials would still need to follow the language in the traffic section of the special provisions, as well as on-site storage of materials, etc. | Scott Lawry | 7 | 2017-05-08 09:19 | 2017-05-08 14:16
20170509 | 20170509001 | 1 | Travel counter-directional adjacent to IH 39 | Can construction traffic travel counter-directional adjacent to IH 39 traffic without being behind temporary concrete barrier if outside of the clear zone? | No, that will not be allowed. | Scott Lawry | 1 | 2017-04-11 10:41 | 2017-04-20 09:49
20170509 | 20170509001 | 1 | Geotech Report | Is there a geotechnical report that the Department could provide? | The file has been posted: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170509001/ And on the SW page https://dot-auth-prod.wi.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx | Scott Lawry | 5 | 2017-05-04 11:19 | 2017-05-04 16:42
20170509 | 20170509001 | 1 | Prestress Girder Type I-28" Quantity, Bid Item 680 | It appears that the quantity for Bid Item 680, Prestress Girder I28" is incorrect. The error seems to be in the quantity for B-13-140 which is listed at 416 LF. In looking at the girder data the quantity should be closer to 674 LF, this would put the total bid item at approximately 2,274. | There is an error in quantity for the question above. An addendum has been prepared and should be submitted shortly. | Scott Lawry | 2 | 2017-04-20 11:10 | 2017-04-24 16:23
20170509 | 20170509001 | 1 | Blasting Rock along IH-39 | The Rock Excavation on this project is located very close to traffic. Usually traffic is stopped while it is blasted for safety. There will be multiple blasts on this project, more than 40 times, one per day spread over multiple weeks and months. What time frames are allowable for this operation? How are these rolling stops paid for and who covers the cost of the police office? | Allowable time frames will be based on corridor traffic volumes and what is allowed by law. Historically, costs for police officers used during traffic slowdowns have been paid for by WisDOT. | Scott Lawry | 6 | 2017-05-04 21:27 | 2017-05-08 16:08
20170509 | 20170509001 | 1 | 1007-10-88 CTH W- Soil Consolidation Area | Where is the "grading detail" located that is referred to in the bottom-left corner of sheet 44 in the 1007-10-88 planset? | The grading detail was left out of the plan set in error. An addendum will be issued that will include the detail. | Scott Lawry | 3 | 2017-05-01 10:56 | 2017-05-02 11:24
20170509 | 20170509001 | 1 | WisDOT Site | Will the WisDOT site north of East Church Rd. be available to crush aggregate for projects 1007-00-84 and 1007-00-88? | No. The site north of East Church Rd will not be available for use by any other WisDOT project while project 1007-11-75 is active. | Scott Lawry | 4 | 2017-05-03 09:26 | 2017-05-05 14:10
20170509 | 20170509003 | 3 | Haul Roads | What are the approved haul roads to get the borrow and base to the project, north and south of the railroad tracks. North of the railroads tracks is pretty self explanatory, wondering more about getting to project south of railroad tracks. | The contractor shall coordinate with Green County the availability of the proposed haul road. | Scott Lawry | 1 | 2017-04-18 19:23 | 2017-04-24 16:13
20170509 | 20170509006 | 6 | temporary markings | On page 4 of 25 it states temporary or permanent centerline markings shall be applied before opening lanes to traffic and it also states lanes must be open daily. With the 5 day waiting period before we can groove in the wet reflective contrast centerline epoxy markings, temporary markings will need to be placed daily to accommodate the note on page 4 of 25. There is no temporary item included in the proposal and it does not state it is incidental so I am looking to have a temporary item added to this project in order to accommodate the project requirements. Thank you. | An addendum was issued today to address the issue. | Scott Lawry | 1 | 2017-05-03 10:44 | 2017-05-04 16:48
20170509 | 20170509007 | 7 | Asbestos Report | Can the asbestos report be made available? | This has been posted http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170509007/ | Scott Lawry | 1 | 2017-05-01 16:48 | 2017-05-01 17:15
20170509 | 20170509008 | 8 | Asphalt Paving | 1â€“On sheet 2, the outside mainline shoulder, the inside shoulder in the diamond grind area and the ramp shoulders are called out as a single layer, 4â€ pavement with 4 MT58-28S. I know that the intention in the mainline overlay sections is to construct this outside shoulder in 2 lifts. What is the intention on the ramps and in the diamond grind area? 1 lift or 2? 2- Given that the outside mainline shoulder is to be constructed in 2 lifts along with the mainline pavement, why would the design call for a different lower layer gradation between the mainline outside shoulder and the mainline driving lanes. We cannot pave the shoulder and lane in tandem with 2 different mixes. The plan currently calls for a lower layer of 3MT58-28S in Lane 2 and 4MT58-28S in the outside shoulder. | Answer 1: 1 lift but 2 lifts are acceptable if staging requires it. Answer 2: The outside shoulders where 2 lifts are required due to staging should have a 3MT58-28S lower lift gradation and 4MT58-28S upper lift gradation. An addendum will be issued to correct the asphalt table and miscellaneous quantities. | Scott Lawry | 3 | 2017-05-04 09:21 | 2017-05-04 09:21
20170509 | 20170509008 | 8 | Earthwork Summary | After performing our own takeoff for the project, we are unable to come close to matching the earthwork summary table in the miscellaneous quantities section of the plan. Is it possible to have this reviewed because not only the common excavation quantity could be affected, but the Breaker Run quantity as well. | There is an error in the earthwork table and will be corrected with an addendum. | Scott Lawry | 2 | 2017-05-02 11:48 | 2017-05-03 14:44
20170509 | 20170509008 | 8 | Concrete Pavement Repair | Concrete pavement partial depth joint repair calls for 12â€ maximum width or it becomes surface repair in the S.D.D. The special provision calls for milling and a 20â€ drum is the minimum standard size. | Answer: After reviewing the work the concrete pavement partial depth joint repair item will be removed from the contract and this work added to the joint and crack repair item by addendum. | Scott Lawry | 5 | 2017-05-04 09:40 | 2017-05-04 10:53
20170509 | 20170509008 | 8 | Asphalt Paving | Given that the surface course on the shoulders is different than the mainline and we will not be able to pave them in tandem, I would like to know whether we will be required to ramp the joints between the time the mainline is paved and the time we come back for the shoulder. | Answer: Lifts will be the same with the addendum. Dropoffs greater than 2â€ between the travel lane and shoulder shall be ramped. | Scott Lawry | 4 | 2017-05-04 09:23 | 2017-05-04 09:29
20170509 | 20170509008 | 8 | Pavement Marking | On the surface layer the Department is calling for Temporary Removable Tape for the skips. This will be replaced by the Wet Reflective Contrast Tape. Why are you not using temporary 4" paint? It would be cheaper, and quicker on both the install of the temporary, and the permanent markings. Also, there is a potential for the glue to stay on the final surface in areas that it does not line up with skip pattern. Who is responsible for the removal of the temporary tape skips? The removal of the paint would be incidental to the tape install on the surface layer. This has been the process on other projects. Cost, and Time efficient. Can this be changed to temporary paint? | Temporary paint is allowed where permanent pavement markings are placed in the same location. An addendum will be issued to update the miscellaneous quantities. Removing temporary tape is included in the item temporary pavement marking removable tape. | Scott Lawry | 1 | 2017-04-26 16:51 | 2017-05-02 11:07
20170509 | 20170509008 | 8 | Sign Bolts | Please clarify item 635.0300 'Sign Supports Replacing Base Connection Bolts' Misc. qtys is showing 2 ea. per sign location while the standard specification states: 635.3.2 Replacing Base Connection Bolts (1) Install new bolts at locations the contract specifies conforming to torque requirements in the plan details. Repair or replace existing posts, base plates, and stiffener plates damaged during bolt replacement 3) Payment for Sign Supports Replacing Base Connection Bolts is full compensation for providing new bolts for each contract designated sign; and for repairing damage done during bolt replacement | Answer: The item will be paid as shown in the miscellaneous quantities and estimate. | Scott Lawry | 6 | 2017-05-04 11:34 | 2017-05-04 11:34
20170509 | 20170509008 | 8 | Base Patching Concrete SHES for CRCP Pavement. | Please confirm the SHES Base Patching shall follow the associated S.D.D. 13 C-14-6b anc 6c. | That is Correct. | Scott Lawry | 7 | 2017-05-07 19:36 | 2017-05-08 11:04
20170509 | 20170509009 | 9 | Structure overcoating | The specifications call out for certain areas to be overcoated or blasted on existing structures B-40-470 and B-40-471 as noted. However, the specific areas areas not noted on the drawing nor defined in the specifications. Can you please provide a detail or more clearly define the specific areas on the existing bridge structures B-40-470 and B-40-471 which are to be overcoated or blasted? | It is the structure overcoating that takes place on Span 2 for each structure over the Canadian Pacific Railroad tracks. | Scott Lawry | 1 | 2017-05-05 12:30 | 2017-05-05 16:08
20170509 | 20170509010 | 10 | inlet covers type 57 | 47 out of the 64 total units of type 57 inlet covers are shown on sheet 179. Is the rest of the quantity shown elsewhere in the miscellaneous quantities? there is not an inlet adjust item on the contract. Are the adjusts of the 17 castings to be considered incidental to the item. The special provisions account for the adjustment of the City of Milwaukee castings in the casting item, however sheet 180 has a manhole adjust item being shown with new 58A manhole covers. (the 16 shown on sheet 180 in addition to the total installed on new structures on sheet 179 of 40 equals the plan quantity of 56) | There are 17 Type 57 Inlet Covers in Phase 1 as shown in the subtotal on sheet 176 and 47 Type 57 Inlet Covers in Phase 2 as shown in the subtotal on sheet 179 for a total of 64 total Type 57 Inlet Covers. | Scott Lawry | 1 | 2017-05-04 12:16 | 2017-05-04 17:03
20170509 | 20170509010 | 10 | Existing Concrete Pavement | Is the 8â€ concrete pavement dowelled? | The existing pavement is Non-Doweled Pavement | Scott Lawry | 2 | 2017-05-08 10:19 | 2017-05-08 10:20
20170509 | 20170509011 | 11 | Asphalt Paving | Question: Typical sections indicate 2â€ Removing Asphaltic Surface Milling and 2â€ HMA Pavement. Milling quantity is 13,420 tons and HMA Pavement quantity is 15,175 tons. Why is there a difference? | Answer: HMA Pavement was calculated using 2.25â€ thickness to account for variations and deformations in the existing pavement including cross slopes, wheel ruts and patches. There is also an additional 15 tons for Elm Street culvert replacement and radius improvement. | Scott Lawry | 1 | 2017-05-04 17:23 | 2017-05-04 17:23
20170509 | 20170509012 | 12 | Storm Sewer Lateral SPV.0090.101-SPV.0090.103 | is there a detail drawing for the construction of the temporary surfaces listed in the specification? | No detail drawing is provided for the temporary surfaces. | Scott Lawry | 4 | 2017-05-04 10:20 | 2017-05-04 16:57
20170509 | 20170509012 | 12 | Prosecution and Progress | Says Complete all work within the Belgium Community Park property within 90 calendar days from the start of any work within the Park Property. What does work within constitute? We have differing opinions in our office as to what this means. Any work in the ROW across the front of the property? Removing the Curb & gutter and drives across the front of the property? Connection of the 60" Storm sewer to the existing box will most likely encroach on park property, does that connectional alone start the 90 calendar day window? | Work within the Belgium Community Park property constitutes any work outside of the existing right-of-way. As soon as there is disturbance within the Belgium Community Park property, the 90 calendar day timeframe begins. | Scott Lawry | 3 | 2017-05-04 06:43 | 2017-05-04 16:55
20170509 | 20170509012 | 12 | Proposal pages | Some of the printed copies of the proposal are missing a portion of article 38 on page 47 of the proposal. | The proposal for 20170509012 that is posted on the departments website at ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2017/05May_09/20170509012proposal.pdf has the correct number of articles and the ones that industry should be using. An addendum will be issued to show the correct page. | Scott Lawry | 2 | 2017-05-03 14:17 | 2017-05-03 14:18
20170509 | 20170509012 | 12 | SPV.0060.202 | SPV.0060.202 LINE 27 ON THE DECRATIVE FIXTURE ASSEMBLY Please advise if a one piece seamless injection molded DR acrylic globe can be furnished on the fixture in lieu of the glass globe | This issue was addressed via addendum earlier today 5-4-17. | Scott Lawry | 1 | 2017-05-01 10:38 | 2017-05-04 17:11
20170509 | 20170509015 | 15 | Removing Asphaltic Surface Butt Joints | On page 22, STA 202+00 - 203+75 LT and 202+00 - 203+75 RT shows 60 sy each of butt joints. The detail on sheet 10 shows a 2' pay limit for the Butt Joint. Do you intend to pay the entire 50' as a butt joint? If not, do the square yards need to be adjusted? | Butt Joint Detail for Milled Asphaltic Pavements 2â€™ pay limit is correct. The 60 SY former quantity was incorrectly calculated using the concrete butt joint detail (45â€™) pay limits. Square yards will be adjusted via addendum. | Scott Lawry | 1 | 2017-04-26 14:25 | 2017-04-28 11:46
20170509 | 20170509015 | 15 | Shoulder Replacement | The detail shows removing the existing asphalt shoulders, adding approximately 1" of gravel and repaving. In lieu of this would it be acceptable if the existing asphalt was removed by milling 2" out to the required slope and grade and overlaying with asphalt instead? | WisDOT want the entire 3 inches of shoulder pavement removed. | Scott Lawry | 3 | 2017-05-08 11:49 | 2017-05-08 12:49
20170509 | 20170509015 | 15 | Project Timeline | This contract is a 25 day working contract. Based on the schedule of operations, specifically concrete base patching (not being specified as HES or SHES), concrete cure time before other operations can start and the 5 day wait after asphalt paving, before grinding for pavement marking, the contractor requests 37 working days for this project. | The department feels 25 working day is enough time to complete the work. | Scott Lawry | 2 | 2017-05-04 16:51 | 2017-05-05 13:39
20170509 | 20170509016 | 16 | Waste Common Excavation | Can waste common excavation be taken to fills at Midway/US 441 in both 2017 and 2018? | Contractors should not assume that waste common excavation can be taken to fills at Midway/US 441 in either 2017 or 2018. The department is letting project 1517-75-72 Midway Interchange Mainline in June with an anticipated start of mid-July which is prior to when work will start on 1517-75-83. | Scott Lawry | 1 | 2017-04-14 07:45 | 2017-04-21 16:11
20170509 | 20170509016 | 16 | Quantity for Salvage / Unusable Pavement | In the miscellaneous earthwork quantities there is not a quantity for salvage / unusable pavement. Why isn't a quantity listed? | Earthwork for this project was determined by taking the difference between existing surface and proposed subgrade. Cut volumes include the removal of existing salvageable pavement material as indicated in note 2 of the earthwork table. | Scott Lawry | 5 | 2017-05-04 09:42 | 2017-05-04 17:01
20170509 | 20170509016 | 16 | Backfill for Storm Sewer Removal items | Is native backfill wanted in the storm sewer removal trenches (not common with new work) in order for these trenches to follow the precedence set by the detail shown for new piping on plan sheet 22? | Backfilling of trenches from pipe removals should be done in accordance with the standard specifications. | Scott Lawry | 4 | 2017-05-02 06:55 | 2017-05-03 14:20
20170509 | 20170509016 | 16 | Tack? | The pavement sections on this project are detailed as 5" and 6". Will Tack be added to this project for multiple lift construction? | Tack will not be added to the plan and should not be needed. 5-inch asphaltic surface is intended to be temporary until a subsequent project and can be placed in one lift. There is no 6-inch asphaltic surface. | Scott Lawry | 3 | 2017-04-24 12:39 | 2017-04-26 11:12
20170509 | 20170509016 | 16 | Complettin Schedule for Valley Road / Oneida Street | The schedule state that Midway Road / USH 10 to be completed by Nov 15, 2017; When does Valley Road / Oneida Street need to be complete? | The Valley Road/Oneida Street intersection needs to be complete by the contract completion date, June 29, 2018. | Scott Lawry | 6 | 2017-05-04 09:44 | 2017-05-04 17:00
20170509 | 20170509016 | 16 | Asphalt Paving | This project shows a start date after September 4th. It also has an interim completion date of November 15, 2017 and final completion of June 29, 2018. With the amount of work needed during these stages, and the timing of the interim completion date, will cold weather paving be added to the project? | Cold weather paving will be added to this project via addendum. | Scott Lawry | 2 | 2017-04-24 12:34 | 2017-04-26 11:11
20170509 | 20170509016 | 16 | Item SPV.0090.850 Railing 36-Inch | With respect to Item SPV.0090.850 Railing 36-inch and plan sheet 28, there is no sizes given for the railing pipe. Please clarify. | The railing should be a 2" diameter pipe. | Scott Lawry | 7 | 2017-05-04 14:21 | 2017-05-08 16:34
20170509 | 20170509017 | 17 | Earthwork Quantites | Is there incremental breakdown by station available for the earthwork? There is nothing in the plan in front of the cross-sections | An addendum was prepared for the proposal to revise a separate bid item. The earthwork tables noted in the question below were included with the addendum when it is published over the next couple of days. | Scott Lawry | 1 | 2017-04-21 08:36 | 2017-04-25 17:09
20170509 | 20170509017 | 17 | Storm Sewer Bid Items | Will contractors be permitted to bid using updated, competitive storm sewer and culvert items based on updated FDM verbiage? From FDM Chapter 13 - "Similarly to culverts, beginning with the 2016 Standard Specifications, two new series of bid items were added to Section 608 Storm Sewer; Storm Sewer Pipe Class III-A, and Storm Sewer Pipe Class III-B. These Class III-A and Class-III B bid items allow the contractor to choose from multiple pipe materials including thermoplastic pipe (corrugated polyethylene and corrugated polypropylene) for sizes up to 36 inches in diameter. Previously, thermoplastic pipe could only be specified via STSP. As described in FDM 13-1-17.3.1, the intent of these Class III-A and Class-III B items is to introduce potential project cost reductions into the competitive bid process by allowing the contractor to select from multiple material options for pipes sized up to 36 inches." | The contractor will be permitted to use alternative pipe materials for the storm sewer. An addendum was issued on May 2, 2017 to address the issue. | Scott Lawry | 2 | 2017-04-30 21:45 | 2017-05-03 14:35
20170509 | 20170509018 | 18 | Utility Clearance at Bridge | It does not appear that there is going to be sufficient clear distance between the overhead power lines to construct the bridge. OSHA minimum clearance is 20'. Based on scaling plan dimensions and looking at google imaging, the lines will be less than 10' from the eastern most piling in each abutment as well as the exterior box girder. Are there provisions to insulate or take the lines out of service during these operations? | Per Special Provision #11 Utilities, under the â€œWisconsin Public Service Corporation-Electricityâ€ heading, there are provisions for the utility to relocate the facilities temporarily to facilitate the construction of the bridge. Please see the special provisions for additional information. | Scott Lawry | 3 | 2017-04-26 14:08 | 2017-04-27 10:11
20170509 | 20170509018 | 18 | Follow Up to Utility Clearance at Bridge Question and Answer | Per Special Provision #11, WPS is to install new taller poles on the current alignment. The only relocation is moving the lines temporarily to the east side of the pole which might gain 5' of horizontal clearance. Since the bridge is also widening 5' to the east, the position of the lines is effectively unchanged. Based on my measurements this will not meet the OSHA minimum clearance regulations for pile driving or beam setting operations and is in fact a conflict. Adding 10' vertically does not alleviate the problem. This needs to be looked at again if the line is in fact staying on the current alignment. | WPSâ€™s current relocation plan includes placing temporary arms supporting the overhead 25 kV distribution lines at least 6-ft east of the existing pole to pole alignment (approximately 27 to 28-ft from the STH 57 reference line). The online OSHA minimum clearances note a 10-ft minimum clearance required for a 25kV line which should be possible given the current structure layout. | Scott Lawry | 4 | 2017-04-27 10:29 | 2017-04-27 14:14
20170509 | 20170509018 | 18 | Project Schedule | The project is in the northern end of Door County with cooler average high and low temperatures in the fall than spring months. Paving during this time period would likely require cold weather paving for portions of the binder layer and potentially all of the surface layer. Additionally, there are culvert pipe replacements and a new bridge that may benefit from allowing settlement over the winter months. Allowing paving into the spring of 2018 would provide a higher quality final product. Would there be consideration to allow the paving of asphalt and other items into the Spring of 2018? | Schedule modifications are in progress. See addendum for any changes. | Scott Lawry | 2 | 2017-04-26 11:15 | 2017-04-26 11:15
20170509 | 20170509018 | 18 | Culvert Pipe | Will contractors be allowed to utilize local aggregates for pipe backfill rather than as spec'd in 608.2.2? | The expectation is that the contract documents and specifications will be adhered to. | Scott Lawry | 6 | 2017-05-06 15:42 | 2017-05-08 12:01
20170509 | 20170509018 | 18 | Culvert Bid Items | Will contractors be permitted to submit bid prices based on current, competitive bid items for culvert bid items? FDM Chapter 13 15.2- "Culvert Pipe Class III-A, Culvert Pipe Class III-A Non-metal, Culvert Pipe Class III-B, and Culvert Pipe Class III-B Non-metal under Standard Spec 520 shall be specified for culverts where ADT is less than 7,000." | Bid as per plan no changes will be made because 2â€™ minimum cover is not maintained at culvert installations. | Scott Lawry | 5 | 2017-04-30 21:53 | 2017-05-01 16:39
20170509 | 20170509018 | 18 | Milling | Will the 72 hour milling rule apply in the area of highway that are closed? | The 72 hour milling rule does not apply under closed and detoured conditions; however, schedule modifications are in progress. See addendum for any changes. | Scott Lawry | 1 | 2017-04-26 11:13 | 2017-04-26 11:13
20170509 | 20170509020 | 20 | HMA Density / Mix testing | This project calls out 24 Ton of 3 LT 58-28S and 19 Ton of 4 LT 58-28S. There is an item for incentive density, but there isn't enough tonnage for a density test. Also, with having less than 50 tons of a mix, the project will not meet the minimum sampling tonnage for mix testing. Will these items be removed from the project? | An addendum will be issued to clears up the issue. The incentive density HMA bid item will be removed. | Scott Lawry | 1 | 2017-04-12 09:38 | 2017-04-20 09:46
20170509 | 20170509021 | 21 | Cleaning Culverts | Other than the Cleaning Culvert Breakdown in the Miscellaneous Quantities on Plan Sheet 103 is there additional information available? Pipe sizes? The existing storm sewer all appears faintly on the plan detail pages and although I can find most of the locations a couple do not seem right. Location at 46+94 should this be 45+94? Location at 110+94 WB Left, I think I found it but it is off the west end of the project and while it maybe left as you travel west bound it is actually on the right side as you go up station. To further complicate this the pipe I think it is, is actually across the EAST BOUND Lanes. Not even sure if this is supposed to involve cleaning 3 runs of pipe between 3 inlets and one end wall. | An addendum will be developed to clarify the intent and location of the pipes to be cleaned. | Scott Lawry | 3 | 2017-05-01 17:53 | 2017-05-03 14:42
20170509 | 20170509021 | 21 | Asphalt Paving | Q1. At Butt Joint locations there is a quantity for saw cutting. If the vertical face of the butt joint can be achieved by milling are the saw cuts in those areas necessary? Q2. The existing typical shows the slope of the pavement at either a 1% or 2% slope, and the finished is at 1.5%. Is the thought of the 3/4" wedging course to correct the crown or is it going to be a nominal 3/4" at the existing slope? Q3. If this is going to be a crown correction cross section be, i.e. 3/4" at Centerline and 1.5% cross slope to the outside edge? | A1. The vertical face is necessary. The method to create it is the contractors choice. If the contractor decides to create the vertical face via milling operations and not by a separate (sawing) operation, the department will not pay for the sawcut. If the vertical face is created via sawing, the sawcut will be paid. A2. As noted on the typical sections, the 3/4" layer is a â€œleveling layerâ€ that is intended to correct the crown ahead of the upper layer placement. A3. Yes | Scott Lawry | 1 | 2017-04-20 10:03 | 2017-04-20 10:07
20170509 | 20170509021 | 21 | Asphalt Paving | Q1. The wedging course does not meet the minimum thickness standards for layer thickness. Usually when this occurs a special provision is written in to exclude this from density incentive and disincentive. Q2. There is an item for Incentive for Air Voids. Since this is a Non-PWL job there is no specification language specifying how this incentive/disincentive is to be paid. Q3. In the staging section of the special provisions there is a mention of placing temporary asphalt at the bridge end locations after the each overlay has been completed. There is no quantity for this work in the plans. | A1. An article will be added via Addendum to exclude the density incentive/disincentive and address gradation requirements for the leveling layer. A2. The 460.2010 Air Void Incentive item will be removed from the contract via Addendum. A3. The intent of this is to just include a very small wedge (tonnage would be negligible to quantify) to blend in to existing pavement (w/paper joint) in a temporary condition. Dependent upon staging sequencing the final pavement may already be blended to final bridge deck overlay elevations. | Scott Lawry | 2 | 2017-04-20 10:10 | 2017-04-20 10:11
20170509 | 20170509022 | 22 | Saw Cut @ Butt Joint Locations | At Butt Joint locations there is a quantity for saw cutting. If the vertical face of the butt joint can be achieved by milling are the saw cuts in those areas necessary? | Saw cuts are not necessary if vertical face shown on the butt joint construction detail is establishes. | Scott Lawry | 4 | 2017-04-24 14:30 | 2017-04-27 10:07
20170509 | 20170509022 | 22 | Pavement Markings | Couple questions regarding the temporary and Same day epoxy quantities. 1. Is the temporary Paint quantity for a double yellow through the entire project? 2. Temp Epoxy looks to be on the surface, and matches the quantities for a double yellow through the entire project. Some of those markings would not be removed by the rumble strips, and would leave markings on the final surface. The Same Day Epoxy item is also for the surface layer, and matches the final installation of Regular 4" epoxy on the rumble strips. Does the project need both of these items? | A1--649.0402 Temporary Paint is for the entire project to be applied to the milled surface. A2--649.0403 Temporary Epoxy is to be applied to the roadway portion south of the roundabout prior to rumble strip placement. A3--646.0406 Same Day Epoxy is to be applied to the roadway portion north of the roundabout A4--646.0106 Epoxy is to be applied to the roadway portion south of the roundabout and the roundabout. | Scott Lawry | 3 | 2017-04-21 09:44 | 2017-04-27 10:06
20170509 | 20170509022 | 22 | Item 624.0100 Water | Is the quantity of 280 MGAL correct? This seems like a rather large quantity for the amount of shoulder material to be placed. Thank you. | The quantity for Item 624.0100 Water is incorrect. There was a conversion error in the calculation. The correct quantity will be updated to reflect this change in an addendum. | Scott Lawry | 2 | 2017-04-19 07:41 | 2017-04-20 13:05
20170509 | 20170509022 | 22 | Safety Edge | Is the safety edge (typ) detail shown on the finised cross section for STH 55 (sta 91+74 to sta 196+47 & sta 201+09 to sta 235+45)on sheet 5 correct? Typically the safety edge would extend out and on top of the existing shaped shoulder. This detail shows the safety edge extending to the bottom of the existing hma pavement shoulder which would require the existing shoulder to be cut out along the edge of the pavement. Could you please clarify the intent. Thank you. | The safety edge is to follow typical installation on the existing shaped shoulder. A revised typical sheet will be included in a future addendum. | Scott Lawry | 1 | 2017-04-05 13:40 | 2017-04-10 16:22
20170509 | 20170509022 | 22 | Pavement Markings | Thank you for replying to the pavement marking questions I submitted. I have additional questions. 1. You stated the temporary epoxy is applied to the south of the round-a-bout prior to rumble placement which is fine with the exception that you also, per page 18, have same day epoxy for the area south of the round-a-bout. You stated the same day epoxy would be placed north of the RAB but also have temporary epoxy and permanent epoxy north of the RAB. It also appears the temporary epoxy quantities are overstated as the final markings south of the RAB are 12,300, the same day markings south of the RAB are 12,300, and the temporary epoxy quantities south of the RAB are 20,300. 2. Per page 17, the rumbles are from station 91+74 to station 196+45 (south of the RAB). You have same day epoxy for this area, temporary epoxy for this area, and permanent epoxy for this area? You would most likely only need the same day or the temporary in conjunction with the permanent. | These issues should be resolved via addendum in the next day or two. | Scott Lawry | 7 | 2017-05-01 16:48 | 2017-05-02 16:24
20170509 | 20170509022 | 22 | Roundabout Asphalt Mix Type | The plan shows that the a 4 LT 58-28 S is to be used in the roundabout. Would the department consider an addendum to change to a higher grade mix? Typically, in roundabouts with the increased slow turning movements would be a 4 MT 58-28 H. | The department is comfortable with the mix specified in the plans. The department is not issuing an addendum to change to a higher grade mix. | Scott Lawry | 6 | 2017-04-28 14:16 | 2017-05-04 16:53
20170509 | 20170509022 | 22 | Asphaltic Surface Patching | There is a quantity for Asphaltic Surface Patching with a undistributed quantity. It is noted that this work is for major rutting areas. Could a detail and locations be provided to better bid this work? | The Asphaltic Surface Patching quantity is for maintaining traffic during construction. | Scott Lawry | 5 | 2017-04-25 09:55 | 2017-04-27 10:07
20170509 | 20170509023 | 23 | Temporary Concrete Barrier | For the work over the Fox River, can the temporary concrete barrier be installed on either STH 441 northbound or southbound? | No. The traffic control details in the plan show the temporary concrete barrier to be installed on STH 441 northbound only. The temporary concrete barrier cannot be installed on STH 441 southbound, as such a closure in the southbound direction would interfere with the on-ramp traffic from the Northland Avenue (CTH OO) interchange. | Scott Lawry | 2 | 2017-04-18 18:25 | 2017-04-18 18:25
20170509 | 20170509023 | 23 | Daytime lane closures | Is it permissible to install daytime single lane closures on both northbound and southbound STH 441 to install the cable system and containment over the Fox River? | Daytime lane closures on STH 441 are not allowed on this project per the special provisions. The proposal and plans include necessary quantities and provisions to shift STH 441 northbound traffic to provide a protected area to work from behind barrier along the outside parapet. | Scott Lawry | 10 | 2017-05-08 13:05 | 2017-05-08 13:06
20170509 | 20170509023 | 23 | Night work | Is only night work allowed and does the temporary concrete barrier need to be installed/removed nightly? | No. The night time periods noted in the Traffic article describe when single lane closures are allowed and when construction equipment and vehicles may occupy closed STH 441 shoulders. These night time periods are not defining when work may occur. The primary intent of the night time periods for STH 441 northbound lane closures is to define the time during which the process of installing and removing the temporary concrete barrier may be done. The temporary concrete barrier may remain in place and work may proceed from behind it continuously through daytime periods, provided the two STH 441 northbound lanes are open to traffic. | Scott Lawry | 1 | 2017-04-18 18:23 | 2017-04-18 18:24
20170509 | 20170509023 | 23 | As-Built Plans | Is there a copy of the as built drawings showing the structural steel framing plan for the bridge over the Fox River that can be made available? | The requested file has been posted: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170509023/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx | Scott Lawry | 4 | 2017-04-26 07:52 | 2017-04-26 12:29
20170509 | 20170509023 | 23 | Night-time lane closures | It appears only night-time lane closures were allowed over the river, why would department not allow a lane to be closed nor work during the daytime? | There was a detail for a STH 441 northbound lane shift in the plan, which provides the contractor the ability to work from a protected area on northbound, between the temporary barrier and the outside parapet. The night time periods noted in the Traffic article describe when single lane closures are allowed and when construction equipment and vehicles may occupy closed STH 441 shoulders. These night time periods are NOT defining when work may occur. The primary intent of the night time periods for STH 441 northbound lane closures is to define the time during which the process of installing and removing the temporary concrete barrier may be done. The temporary concrete barrier may remain in place and work may proceed from behind it continuously through daytime periods, provided the two STH 441 northbound lanes are open to traffic. The Traffic article also allows STH 441 southbound lane closures at night-time to assist construction operations. | Scott Lawry | 6 | 2017-04-26 07:58 | 2017-04-26 08:00
20170509 | 20170509023 | 23 | Access to the Structure | Other than the work over the river from behind the STH 441 northbound temporary concrete barrier, is the contractor free to work from below? | For the most part, yes. The contractor must abide by restrictions noted in the special provisions. Details regarding access to the various parts of the structure are described in the Prosecution and Progress article. | Scott Lawry | 3 | 2017-04-18 18:27 | 2017-04-18 18:27
20170509 | 20170509023 | 23 | Existing Bracket/hanger assemblies | Q: Can the brackets/hanger assembly that supports the Department Fiber Optic and ITS Facility be removed from the structure to accommodate bridge painting operations? | A: No. This facility must be left in place, covered, and protected during blasting and painting operations according to Article 8 of the special provisions. | Scott Lawry | 8 | 2017-05-02 16:30 | 2017-05-02 16:31
20170509 | 20170509023 | 23 | Sound Wall | Q: Can the wooden sound wall connected to the parapet walls on the south end of the structure be removed to accommodate access from the bridge? | A: No. Our proposal includes no provisions for allowing removal of the sound wall. | Scott Lawry | 7 | 2017-05-02 16:28 | 2017-05-02 16:29
20170509 | 20170509023 | 23 | Painting Questions | Q1: Does the temporary concrete barrier need to be removed and does the highway need to be entirely opened back up to traffic during winter shutdown. Q2: Is the existing paint on the bridge zinc based? Q3: Can the area under the bridge between the north bank of the Fox River and STH 96 be used to store equipment during the winter shutdown months? Q4: Does the Migratory Bird Depredation Permit issued to the Department for period 2/27/2017 to 3/31/2018 allow the contractor to destroy active nest (with eggs or hatchlings) during that time? | A1: Yes. Article 3 of the special provisions, Prosecution and Progress, limits the use of the concrete barrier and lane shift over the Fox River to just one construction season. Article 4 of the special provisions, Traffic, also limits lane closures to the length and time necessary as generated by construction operations. Also, per Article 3 of the special provisions, the Department will suspend work during winter shutdown. A2: We are unsure of the paint type or chemical make-up on the bridge. The Department assumes and treats all paint equally â€“ as a hazardous material that must be properly contained and disposed of. A3: Yes. A4: Yes. See Article 3 of the special provisions for additional information on this topic. | Scott Lawry | 9 | 2017-05-02 16:33 | 2017-05-02 16:34
20170509 | 20170509023 | 23 | Contract time | There appears to be a lot working days (170) allowed on this contract. Is this accurate? | The production rates for the work items on the project are based on recent project history in the area, and assuming one typical sized crew. The assumption is that the contractor would NOT heat the containment, hence, allowing only the months of May through September for adequate climate for performing this work. Any heating of containment area would be at the contractors own cost. | Scott Lawry | 5 | 2017-04-26 07:54 | 2017-04-26 07:57
20170509 | 20170509024 | 24 | Erie Street-Removing Pavement | Is this the correct Item? Shoud the Item be Removing Asphalt Surface Milling? Will the City of De Pere project be restored with asphalt or base aggregate? Is the quantity for this Item correct? Thank you. | A1--No, it will be updated to Removing Asphaltic Surface. A2--No, it will be updated to Removing Asphaltic Surface. A3--It will be restored with base aggregate. A4--Yes, the pavement removal quantity is correct, however the common excavation quantity will be updated to reflect removing the 5â€ of base aggregate that was restored by the City project via addenda. | Scott Lawry | 1 | 2017-04-07 10:55 | 2017-04-10 16:25
20170509 | 20170509024 | 24 | Unclassified Excavation | The addendum added quantity to the unclassified excavation item for base course removal in the trenches on Erie Street. How will removal of the material in the trenches on Allard and Helena be paid for? | There will not be any trenches on Allard as there are no City replaced underground utilities on this project. On Helena, the City will come in after the pavement is milled and once they are complete with their utility replacements, they will restore the binder. There will be no material for the contractor to remove. The work by the City and the placement of the binder is noted in the utility special. | Scott Lawry | 2 | 2017-05-03 08:29 | 2017-05-03 14:21
20170509 | 20170509027 | 27 | Existing Wall Used as Shoring | Page 1 of the C-44-132 plans indicate that the existing box culvert wall should remain and be used as shoring to protect the adjacent building foundation. Has the Department verified this existing walls stability with the floor and the roof of the culvert removed? Who takes liability of the existing building foundation if the existing culvert wall fails? | It is our judgement that the wall will remain stable with the building removed. It appears to be independent of the rest of the building. We are not aware of any plans for the existing wall, the existing building foundation, or the neighboring building foundation. Without knowing how each was constructed, we canâ€™t make a definitive statement that the wall will provide adequate shoring. After building removal, the Contractor will need to make an assessment of the wallâ€™s stability and determine its adequacy for shoring. If deemed inadequate develop a shoring plan and protect the property in accordance with Section 107.11. | Scott Lawry | 2 | 2017-05-02 12:54 | 2017-05-04 16:45
20170509 | 20170509027 | 27 | Storm Sewer Bid Items | Will contractors be permitted to submit bids for storm sewer items with current, competitive bid items? From FDM Chapter 13 - "Similarly to culverts, beginning with the 2016 Standard Specifications, two new series of bid items were added to Section 608 Storm Sewer; Storm Sewer Pipe Class III-A, and Storm Sewer Pipe Class III-B. These Class III-A and Class-III B bid items allow the contractor to choose from multiple pipe materials including thermoplastic pipe (corrugated polyethylene and corrugated polypropylene) for sizes up to 36 inches in diameter. Previously, thermoplastic pipe could only be specified via STSP. As described in FDM 13-1-17.3.1, the intent of these Class III-A and Class-III B items is to introduce potential project cost reductions into the competitive bid process by allowing the contractor to select from multiple material options for pipes sized up to 36 inches." | The City of Seymour is the maintaining authority and they prefer stay the with pipe specified in the contract. | Scott Lawry | 1 | 2017-04-30 22:04 | 2017-05-03 10:46
20170509 | 20170509029 | 29 | Wetland information | Does the department have any information regarding wetland limits around the overpass for contractors to consider excavation outside the right-of-way at borrow sites to be determined by the contractor? | The information available has been posted ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170509029/ ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170509029/STH%2029%20and%20156_Exhibit_2017-04-27.pdf | Scott Lawry | 2 | 2017-04-28 08:16 | 2017-04-28 08:19
20170509 | 20170509029 | 29 | Select Borrow | How will the select borrow be measured? In place or from original position? | The preferred method of measurement is in the original position. If an alternative method of measurement is required due to the source we will follow section 208.4 for the measurement. | Scott Lawry | 3 | 2017-05-03 09:00 | 2017-05-03 12:05
20170509 | 20170509029 | 29 | Geotechnical Information | Is there any additional (other then provided in a plan) soil borings or other geotechnical information available for this project? | The files have been posted: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170509029/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nc.aspx | Scott Lawry | 1 | 2017-04-19 12:02 | 2017-04-21 16:13
20170509 | 20170509030 | 30 | temporary markings | it appears that you have the same day markings taken care of on the upper layer but do not have any included for the lower layer? what is your plan to provide temporary markings on the lower layer? Thank you. | The temporary pavement markings were erroneously left out of the plan quantities. An addendum will be issued to add a temporary pavement marking quantity to account for the lower layer of pavement. | Scott Lawry | 1 | 2017-04-24 12:06 | 2017-04-25 08:06
20170509 | 20170509030 | 30 | Common Excavation | There is a quantity figured in the common excavation item to remove 4â€ of the existing shoulder gravel. Could this material just be pulverized and graded with the new base? | Yes, the 4â€ shoulder gravel material can be either removed or pulverized and graded with the new base. | Scott Lawry | 2 | 2017-04-27 09:10 | 2017-04-27 16:48
20170509 | 20170509031 | 31 | Structural Backfill Payment | There appears to be a discrepancy between payment terms for structural backfill. On plan sheet 4 - construction details, it depicts a required 8.8:1 transition cut, which is called out as excavation common & structure transition. There is also a note about utilizing the existing material being reused as backfill. The structure plans page 2 of 6 for C-63-13 depict the structure excavation limits and indicate that all volume outside of the perimeter depicted is incidental to the excavation for structures. Can the payment terms surrounding the transition,excavation common, structure excavation, structural backfill and where the existing material can be used be better defined? | This issue was address via addendum posted earlier today. | Scott Lawry | 1 | 2017-05-02 16:46 | 2017-05-04 17:08
20170509 | 20170509033 | 33 | Culvert pipe work and associated items at station 509+58 | Can the two local properties within the closure area be directed to use Marsh Road for access during the work between station 509+58 & 522+07. If construction is staged to maintain at least one lane of local traffic, a temporary diversion channel will not be practical. | No the two local properties within the closure area canâ€™t be directed to use Marsh Road for access during the work between station 509+58 & 522+07 A separate bypass channel is not necessarily required for this work or mandated by the SPV. Temporary water diversion to maintain channel flow for this location (509+58) could be provided by utilizing a by-pass culvert, by-pass pumping, or utilizing the existing pipes with water diverted by sandbags wrapped in plastic, sheet piling or other non-erodable materials approved by the engineer (method to be outlined in the ECIP) | Scott Lawry | 2 | 2017-04-27 07:50 | 2017-05-02 11:20
20170509 | 20170509033 | 33 | HMA Pavement Shoulder Slope | The typical finished sections show the paved shoulders at a 4% slope. Could you please verify that this is correct? The project from the Royalton overhead to the east constructed in 2016 had a 2% shoulder slope. A 4% slope may present some issues. Thank you. | The department will allow a 2% paved shoulder slope, if the lane and shoulder are paved in one pass/integrally. | Scott Lawry | 1 | 2017-04-14 12:24 | 2017-04-21 16:12
20170509 | 20170509033 | 33 | Structure Backfill and Transition Cut | There appear to be conflicting details regarding the structure backfill type B payments. Page 10 construction details indicate a transition cut of 10:1 from the box culvert B-68-140 to the roadway height. The notes indicate that this area will be paid using Type B structural Backfill. The Culvert plans for B-68-140 - page 4 indicate that all volume outside of the depicted perimeter of the box culvert is incidental. How will payment for this be handled? | This issue was addressed via addendum earlier today. | Scott Lawry | 3 | 2017-05-02 15:02 | 2017-05-04 17:12
20170509 | 20170509036 | 36 | Chip Seal | In order for chip sealing to be completed within there construction dates, can time be suspended in the fall of 2017 to complete the chip seal in 2018 or can the chip seal be done first and then have the time suspended. | The department will allow the contractor to complete the chip seal first and suspend time until they can come back and complete the milling and paving section, but all work needs to be completed in 2017. There is ample time in the contract to complete all areas of work within the 2017 construction season. All traffic control signs need to be covered or removed while work is suspended and the costs would be the responsibility of the contractor. | Scott Lawry | 2 | 2017-04-25 14:18 | 2017-04-26 10:59
20170509 | 20170509036 | 36 | Mix Type | Is 3 LT the correct aggregate size mix for this project? | An addenda will be prepared to change to 4 LT 58-25 S. | Scott Lawry | 1 | 2017-04-17 14:59 | 2017-04-20 09:48
20170509 | 20170509037 | 37 | Ptoposal # 37 9120-09-70 | There was an addendum on this project in regards to the Salt Storage Facility. Are you going to change the EBS file to show this addendum ? Addendum #1 | There were no item quantities that were changed with addendum #1. The EBS file would only be updated if there were changes to the quantity of an item. | Scott Lawry | 1 | 2017-05-08 07:01 | 2017-05-08 08:18
20170509 | 20170509037 | 37 | 2nd Addendum | You need to update the EBS file with the 2nd addendum | There were no item quantity changes with the addendum. The EBS file is not updated unless there are quantity changes. | Scott Lawry | 2 | 2017-05-08 09:05 | 2017-05-08 09:39
20170509 | 20170509039 | 39 | pavement markings | on page 2 of 33 in the proposal, it states that, in constructing the surface layer of pavement, work on each side of the centerline must be matched up at the end of each day so that permanent same day centerline pavement marking can be applied. a couple of questions. 1. there is no same day item and 2. the permanent centerline markings are grooved in markings that cannot be grooved on asphalt for 5 days after paving per C.5.2. 3. With this in mind and the temporary markings being for the milled and lower layer, how do you plan to account for the centerline markings that need to be on the surface course between paving and the 5 day wait prior to grooving and do we need additional temporary markings to cover this? last question 4. with 6 mile lane closures being allowed, will they need to be taken down daily? Thank you | The Language requiring the pavement to match each day will be removed by addendum. A1--We donâ€™t need same day item. Temporary paint on center line will be applied, after 5 days the temporary pavement marking will be replaced with grooved contrast wet reflective epoxy 4-inch pavement marking at the locations. A2--Because one lane is closed at a time with drums, we can utilize the closure to wait for 5 days to be grooved half of the center line and both edge lines during road closed. A3--Yes, We need additional temporary marking to cover 6 mile center lane, (for first half of project length), which will be replaced after 5 days with grooved contrast wet reflective epoxy 4-inch pavement marking at the same locations. We also utilize one lane closure at a time to groove the other half center line and both edge lines. A4--No | Scott Lawry | 1 | 2017-04-24 11:52 | 2017-04-28 13:49
20170509 | 20170509040 | 40 | Can the epoxy overlay worked planned in Stage 4 be moved up in the schedule. | Can the epoxy overlay work shown in stage 4 be moved up and performed immediately after the completion of the epoxy overlay work in stage 1? | The contractor shall bid the project as detailed and specified. Any changes to the staging of the project will require the contractor to submit a revised staging plan and a schedule prior to construction which will be reviewed and approved by the department. | Scott Lawry | 4 | 2017-05-06 20:26 | 2017-05-08 09:37
20170509 | 20170509040 | 40 | Contract time | Is there any possibility of starting the project associated with this Proposal a little later and completing it no later than Mid October. I think moving the date back some would increase competition and result in better pricing for the department and tax payers. Please let us know if the completion date can be moved back somewhat. | The completion date will be modified to mid-October, however, the polymer overlay of the structures is weather dependent, and there will be no allowances or exceptions for this work. | Scott Lawry | 1 | 2017-04-18 18:21 | 2017-04-18 18:22
20170509 | 20170509040 | 40 | Cleaning and Patching Concrete Joints and Cracks | There are two sections of mainline USH 8. One will remain concrete and the other will be milled and overlaid with hot mix asphalt. Will the Cleaning and Patching Concrete Joints and Cracks item be paid for both sections. In the miscellaneous quantities it states this item is only for longitudinal cracks. The area from STH 87 to the West where the concrete milling takes place, there are transverse as well as longitudinal cracks. There is an item for Prep of Foundation for Asphalt Paving, however it is the standard bid item and not the special provision item that we have seen in previous projects such as this. | Standard item 211.0100 Prep of Foundation for Asphalt Paving is intended for 6+62E to 18+00 E. The undistributed amount of SPV.0090.02 Cleaning and Patching Concrete will be used if the engineer deems longitudinal or transverse joints need to be addressed prior to asphalt paving in this area. | Scott Lawry | 2 | 2017-04-26 11:01 | 2017-05-01 10:49
20170509 | 20170509040 | 40 | Can the Design Schedule be provided? |  | The requested file has been posted. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170509040/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nw.aspx The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 3 | 2017-05-06 13:20 | 2017-05-08 12:38
20170509 | 20170509044 | 44 | Clearing | Q1: The standard specifications do not indicate the amount of cutting that will be done in the roadside clearing limits. How much clearing will be done? Q2: How will the roadside clearing be staked? Q3: Is a station of roadside clearing one side of the road only or both sides. The miscellaneous quantities show some stations with roadside clearing on side of the road only or both sides. Q4: Where is the 10 stations of undistributed roadside clearing? | A1: Generally all trees and brush in the roadside clearing limits will be cut. Under 202.3 the engineer may designate tress to be saved and there will be some trees within the roadside clearing limits that will be marked by the engineer and saved. A2: The roadside clearing limits are given by the station and distance from centerline. Any trees that are to be saved will be marked by the engineer. All trees/brush within the roadside clearing limits that is not marked to be saved will be cut. If the contractor needs any staking for this operation is covered under 105.6.2(2) and 105.6.2(3). A3: A station of roadside clearing includes all roadside clearing on both sides of the road for that station. In some cases all roadside clearing will only be on one side which is indicated in the miscellaneous quantities. A4: The 10 stations of undistributed roadside clearing may be anywhere on the project on one side or both sides of the road. | Scott Lawry | 2 | 2017-05-05 16:15 | 2017-05-05 16:17
20170509 | 20170509044 | 44 | Joint Heater and contract time | Question: Can the joint heater requirement be removed Question: Can the traffic control requirements regarding length of work zone and distance between work zones be modified to allow more efficient hauling operations and a lower bid price Question: The contract time does not allow enough time for roadside clearing | Answer 1: No Answer 2: Yes, the department issued an addenda to address Answer 3: The department issued an addenda to address | Scott Lawry | 1 | 2017-05-04 17:20 | 2017-05-04 17:21
20170509 | 20170509045 | 45 | Special Provision #12 Section C.4 Road Surface Preparation | Regarding Question #1. To address the allowance for CRS-2P to be used in replace of marking removal. Fogging over existing paint lines does not eliminate the delamination that will occur even when fogged with CRS-2P. The only way to prevent this issue to perform the work as originally specified which is to remove the lines. The industry has worked very hard to correct the delamination issue that will occur if the lines are fogged and not removed. If the agency is going to allow CRS-2P in replace of marking removal. Will there be an addendum issued on the project? | The Removal of the pavement marking is required as part the item of Chip Chip Seal, SPV.0180.01 under section C.4 Road Surface Preparation. At this time the method of spraying over the marking is not specified should not be bid in this manner. | Scott Lawry | 3 | 2017-05-08 13:05 | 2017-05-08 14:34
20170509 | 20170509045 | 45 | Special Provision #12 Section C.4 Road Surface Preparation | Will tacking over the pavement markings with CRS-2P be allowed instead of removing all pavement markings? Spraying over the markings is what is done specified with the Minnesota and Michigan DOT's when chip sealing over newer striping or epoxy. | The Removal of the pavement marking is required as part the item of Chip Chip Seal, SPV.0180.01 under section C.4 Road Surface Preparation. At this time the method of spraying over the marking is not specified should not be bid in this manner. | Scott Lawry | 1 | 2017-05-04 13:26 | 2017-05-08 11:32
20170509 | 20170509045 | 45 | Fog Oil | Would the agency issue an addendum to allow CSS-1H as a fog oil. This is standard fog oil material on chip seals. | The contractor should bid the project based upon the material specified in the contract. | Scott Lawry | 2 | 2017-05-08 08:13 | 2017-05-08 14:34
20170509 | 20170509047 | 47 | Structure R-57-1, mse WALL | As per sheet 96 (sheet 3 of 6), typical section thru retaining wall, see table for top of wall elevations. The contract do not contain the table with the top of wall and finish grade elevations at bottom of wall. Please provide the the table with the top of wall and finish grade elevations at bottom of wall | The geometry table is on sheet 2 of 6 of the structure plans. | Scott Lawry | 1 | 2017-04-11 18:59 | 2017-04-20 09:46
20170509 | 20170509047 | 47 | Piling Lengths and plan quantity | Sheet 1 of the structure plans indicate piling lengths of 15' for the north abutment and 16' for the south abutment. There are ten piling in the south abutment (160' total) and 9 piling in the north abutment (135' total). The plan quantity for the project is 335', but the plan details would indicate 295'. Which is correct? | The pile lengths listed on the plan view are from the bottom of the abutment to the tip of the pile and donâ€™t include the 2â€™ minimum embedment into the abutment. So, the 40â€™ discrepancy is from the 2â€™ embedment with rounding to the nearest 5â€™ on the totals. The Total Estimated Quantity values listed on page 2 of the structure plan are correct. | Scott Lawry | 2 | 2017-04-27 12:38 | 2017-04-27 16:33