## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170613 | 20170613001 | 1 | Pavement Markings | 2 questions. 1 - Bid item #0780 calls for 244,240' of 4" epoxy. The Misc. quantities for that item on page 79 of the plans only add up to 121,952. Looks like it is only showing quantities for 1 edge line and not two. Quantities should double. 2 - Missing quantities for on top of the rumble strips. Temp paint is on lower lift, same day epoxy is on final surface (layout for Rumbles), 4" Epoxy should increase by nearly the same quantity as the same day epoxy for after the rumbles are installed. Please advise. Thank you. | Answer #1 The quantity of 121,952 LF is correct, but due to Question #2 it will be changing. The quantity break down in the Misc. Quantities is for both the LT and RT side, but the sum of 244,240 is incorrect. This will be fixed with an upcoming addendum. Question #2 Item 649.0402 is for the lower lift. Item 646.0406 will be removed. New item of 649.0403 Temporary Pavement Marking Epoxy 4-INCH will be added by addendum, 67922 LF. This quantity will be used on the final lift prior to milling of rumble strips. 77573 LF will be added to item 646.0106 Epoxy 4-INCH for the final centerline epoxy after rumble strips have been milled in. | Scott Lawry | 1 | 2017-05-17 10:11 | 2017-05-22 17:42
20170613 | 20170613001 | 1 | HMA Mix Designs | Will more than one mix design for each type of mix required be approved by the engineer, as allowed in the special provisions section 14,B? | It is the intent of the special provision that only one mix design will be used. If there are extenuating circumstances, the Department will consider a request for an additional design. | Scott Lawry | 2 | 2017-06-05 17:02 | 2017-06-07 15:37
20170613 | 20170613001 | 1 | 204.0125 Removing Asphalt Surface Milling | Typical Sections shows 3" removals and MQ's indicate 4" removals. Plan quantity tonnage appear to be at 4" depths not 3". Please advise. | The 3â€ shown in Typical Sections is correct. An addendum will be issued to correct the plan quantity. | Scott Lawry | 3 | 2017-06-06 14:57 | 2017-06-07 09:01
20170613 | 20170613003 | 3 | Pavement Markings | can you clarify where the wet reflective tape markings go on this project? Per plan sheets 24 and 25, there is one section of 8" that is approximately 185 feet long=/- and 5 4" skips @ 12.5 feet long for a total of 60 feet. Thank you. | Skips are not to scale in the drawing, need skips US 12 EB from the bridge deck station 148+40 to 155+80 and the 8 inch channelizing from station 152+35 â€“ 155+80 on a curve. | Scott Lawry | 1 | 2017-05-30 10:04 | 2017-05-30 13:25
20170613 | 20170613004 | 4 | Type H Railing | Can an aluminum rail be used as an alternate to steel? | No, the railing shall be steel as indicated in the structure plans. | Scott Lawry | 1 | 2017-06-11 13:00 | 2017-06-12 08:11
20170613 | 20170613005 | 5 | staking structure | are you going to add the item staking structure | Yes. it will be included in a addendum. | Scott Lawry | 1 | 2017-05-21 10:57 | 2017-05-22 13:20
20170613 | 20170613006 | 6 | Addendum #2 | I believe there is a misprint concerning Interim & Final Completion of Work. Paragraph 2 indicates "If the contractor fails to complete the work necessary to reopen CTH K, adjoining ramps and frontage roads, and adjoining municipal streets to through traffic prior to 12:01 AM December 15, 2015, the department will assess the contractor $2,065 for damages in interim liquidated damages for each calendar day that the roadway remains closed after 12:01 AM December 15, 2017." Is the date December 15, 2015 incorrect? | This is a typo and will be correct via addendum. | Scott Lawry | 1 | 2017-06-06 09:46 | 2017-06-06 12:38
20170613 | 20170613006 | 6 | Can the design schedule and the soil borings be provided? |  | The requested files have been posted. http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613006/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 2 | 2017-06-06 15:43 | 2017-06-07 15:20
20170613 | 20170613007 | 7 | Polyester Polymer Concrete Overlay with milling | Can you provide the bidders with the square yardage numbers for the milling included in the CY pricing? | Please review the structure plans contained in the plan to locate the dimensions of the proposed Polyester Polymer Concrete Overlays Page 308 is an example. | Scott Lawry | 1 | 2017-05-19 13:11 | 2017-05-19 13:27
20170613 | 20170613007 | 7 | Epoxy Crack Sealing - Concrete overlays | In the General Notes on the structure plan sheets for the concrete overlay structures it states â€œ cracks in the overlay shall be sealed with a low viscosity crack sealer (see standard specifications section 502). Cost is included in the Bid Item â€œConcrete Masonry Overlay Decksâ€. Generally the epoxy crack sealing for overlay projects is referenced to cracks in the existing deck to be sealed prior to placing the new overlay. Is this what is meant by the referenced General Note? At times this is paid via bid item. If not , sealing cracks in the new overlay that is poured under traffic and not under the contractor control is a difficult item to quantify. Would the DOT entertain providing an item with an estimated footage to establish a unit price for the epoxy crack sealing? | This note is just reinforcing provisions already included in the Standard Specifications Section 502.3.13.1. As stated it is for sealing cracks that develop in the newly placed concrete overlay. It is not intended for sealing cracks in the deck prior to placement of the new overlay. In the past, Bridge Maintenance has requested that this note be included for concrete overlays, which is what we have done. The crack sealing is incidental to the concrete overlay just as it would be for a new deck or deck replacement, and as such a bid item is not warranted. It is a very low cost item, relative to the overlay. The quantity of sealing required is not easy to quantify, for us or the contractor. However, cracking of the overlay is most typically related to drying shrinkage of the concrete and is minimized by following proper curing procedures. | Scott Lawry | 2 | 2017-06-07 11:32 | 2017-06-08 10:09
20170613 | 20170613007 | 7 | CRASH CUSHIONS PERMANENT LOW MAINTENANCE | Could you please provide me with the answers to the questions below? â€¢ Width of Crash Cushion needed to protect the barrier? â€¢ Type of barrier it is protecting, and the width of the barrier 2 Type HF Parapets. â€¢ Test Level Requirements should this be an TL-2 unit or TL-3 â€¢ Location of Crash Cushion (Gore, median, roadside) â€¢ Confirmation that Low Maintenance unit is required. | A1--Per page 4 of the plan set: 5â€™-10 ½â€ at the barrier A2--2 Type HF Parapets. 1â€™-5 3/8â€ each A3--TL-3 A4--gore A5--Yes | Scott Lawry | 3 | 2017-06-08 09:10 | 2017-06-08 15:49
20170613 | 20170613007 | 7 | Polyester Modified Overlay Milling | In the plan for the polyester polymer concrete overlay it requires that the area to be milled 3/4" prior to cleaning and placing polymer. Due to the short windows of closures can the milling be done on a night in advance of the cleaning and placement of the polymer? Traffic would be running on the milled surface prior to cleaning and placement due to the short closures. | Yes, the milling can be done in advance of the cleaning and placement of the polymer overlay. The cleaning however has to be done on the same night as the overlay is placed, as stated in the specification. Only the milling can be done in advance. Per the spec: Do not perform surface preparation more than 24 hours prior to the application of the primer. Blasted surface shall not be exposed to vehicular or pedestrian traffic other than that required for overlay placement. | Scott Lawry | 4 | 2017-06-08 10:58 | 2017-06-08 15:52
20170613 | 20170613011 | 11 | Shoulder Widening | Is it the intent of the plan from station 79+97 - 307+25 to remove existing gravel and replace with new 3/4" gravel? | Yes. The intent of the plan is to remove all existing shoulder gravel from station 79+97 to 307+25, and replace it with new ¾ inch gravel. This removal of the existing gravel is considered part of the Preparation of Foundation for Asphaltic Shoulders item. Existing base material removal shall performed as the sections show, as required by Standard Specification 211.3.7 (1) under â€œOther Workâ€. | Scott Lawry | 1 | 2017-06-06 08:57 | 2017-06-06 17:25
20170613 | 20170613013 | 13 | Temporary markings | It appears you have a temporary quantity that matched the edge lines rather than matching the yellow center lines. Please verify your intention on these markings as they should be the same quantity as the center lines rather than the edge lines. | An addenda will be issued to revise the quantity | Scott Lawry | 1 | 2017-05-25 14:40 | 2017-05-31 09:17
20170613 | 20170613016 | 16 | Fiber Wrap | We have identified a contradiction on the bid documents regarding the Fiber Wrap shear reinforcement on this project. Fiber Wrap Reinforcing Structural, Item SPV.0165.01 - B.2 Design states - â€œFor shear applications, U-wraps or complete (full) wraps must be used; side bonding is not allowed.â€ However, Section A-A on sheets 26 through 30 shows a 2-sided wrap or side bonding application, not a U-wrap or complete wrap. Please clarify the requirements of Bureau of Structures. | Please follow the special provision. Per standard specification 105.3 when a discrepancy between documents occurs, the special provisions would take precedence over a general note in the plan. | Scott Lawry | 1 | 2017-06-06 12:50 | 2017-06-06 12:52
20170613 | 20170613017 | 17 | Noise Walls | In reviewing the noise walls specifications, there are no aestheticâ€™s details for the panels shown on the plans. Also in the written specifications for the noise walls, under color it says none, is this accurate? | Your interpretation of the special provisions language is correct. The departments policy is to apply no color treatment to the concrete used in the noise barrier, so we put â€œnoneâ€ for the color section. The aesthetic texture that was chosen was â€œnatural stone,â€ which is not detailed in the plans. An addendum will be issued to clarify the intent of the department regarding the color and any texture necessary for the walls. | Scott Lawry | 1 | 2017-05-10 15:45 | 2017-05-10 16:05
20170613 | 20170613017 | 17 | Can we get a link or some form of the design schedule? |  | The requested file has been posted. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613017/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nw.aspx The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is issued. | Scott Lawry | 2 | 2017-05-11 18:43 | 2017-05-16 12:09
20170613 | 20170613017 | 17 | Precast Panels | Is there an exact locations for the precast panels? | The amount of precast patching was quantified in the plan and that the exact location was not identified but the precast panels are only on the interior lanes. The final location, size and quantity would be determined in the field when construction begins. | Scott Lawry | 3 | 2017-05-17 12:52 | 2017-05-17 12:53
20170613 | 20170613017 | 17 | Temporary Widening concept | Sheet 657 & 686. In the notes Temp Widening Notes. Note 11 states Temporary Widening to have conc deck, conc end diaphragm, paving ledge and single slope parapet. The note in the box above the title block states "This sheet is for information only. The contractor is responsible for supplying means and methods for temp widening ...including calculations and plans. Is note 11 "information only" or requirements? Is the conc in note 11 referring to cast in place conc or can precast concrete {where feasible} be used? Example instaed of the single slope parapet can Temp Barrier (anchored) be used on the edge of deck similar to the edge of deck in stage 2? | The contractor is required to provide the temporary widening structure calculations and plans that meet the geometric plan and elevation details and notes on the sheet. The barrier may be a precast concrete anchored temporary barrier, provided that the deck width and anchorage details are accounted for in the contractor's design and plans. | Scott Lawry | 4 | 2017-05-19 16:01 | 2017-05-23 10:47
20170613 | 20170613017 | 17 | Prosecution and Progress | During the 2018 Construction can Zone 1 stages & Zone 2 stages take place concurrently? | Yes, as long as the lane closure restrictions are adhered to | Scott Lawry | 5 | 2017-05-22 16:04 | 2017-05-23 12:46
20170613 | 20170613017 | 17 | Noise Wall design | Plan notes of N-55-1 and N-55-2 do not call for AASHTO LRFD design specifications, but call for 1989 guide specifications. Specifications ask for AASHTO LRFD. Which is accurate? | An addendum will be developed to address this issue and clarify the expectation. | Scott Lawry | 6 | 2017-05-23 12:26 | 2017-05-23 12:27
20170613 | 20170613017 | 17 | Asbestos Report | Is there a report available for this project? | This has been posted ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613017/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nw.aspx | Scott Lawry | 7 | 2017-05-30 09:25 | 2017-05-30 11:21
20170613 | 20170613017 | 17 | B-55-148 Steel Diaphragms | This question is regarding Bid Item 790, Steel Diaphragms for B-55-148. On plan sheet number 700 - STEEL DIAPHRAGM FOR B-55-148, detail Section B-B states "Core 1 1/4" dia holes in web (core through EXIST INSERT per girder manufacturer and design engineer specifications." Would it be acceptable to have the new steel diaphragms for the widening offset slightly to miss the existing diaphragms and leave the insert in the existing exterior girder as is? | The contractor, at his option, may core drill 1 1/4" holes in the existing beam web of B-55-148 up to 0'-8" from the existing diaphragm inserts for installation of the new diaphragms. Care must be taken to not damage or cut prestressing strands or reinforcement in the existing beam web. The contractor will also need to make the same hole location change for the diaphragm location in the new beams. | Scott Lawry | 8 | 2017-06-02 11:34 | 2017-06-05 14:02
20170613 | 20170613017 | 17 | Earthwork tables | Would you be able to post the spreadsheet of all of the Earthwork Data for the Hudson-Baldwin project? | The requested files have been posted ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613017/ | Scott Lawry | 9 | 2017-06-05 13:16 | 2017-06-05 13:17
20170613 | 20170613017 | 17 | Waste Site Availability | Can the old STH 35 South Interchange located to the east of the current STH 35 South interchange be used as a waste site? | The department can not make any commitments to the usage of this area for a waste site. | Scott Lawry | 10 | 2017-06-05 15:41 | 2017-06-05 15:45
20170613 | 20170613017 | 17 | Earthwork Data tables do not match the Summary | Could the Department provide the tables that correspond and match the earthwork summary page? It appears to the data does not match currently. | This was addressed with addendum number 3. | Scott Lawry | 11 | 2017-06-06 11:06 | 2017-06-08 16:47
20170613 | 20170613017 | 17 | Asphaltic Surface Temporary | Special Provisions: "Engineer will review temporary pavements to remain in place as permanent work. Any pavements determined by the engineer requiring replacement are considered incidental to bid item with no additional payment." This is very subjective. There needs to be some criteria laid out. Why bid it as Asphaltic Surface Temporary if you really want a permanent pavement? Would it not be easier to write a special provision for an "MT" or "HT" mix that provides the contractor the maintenance as the Asph Surf Temp does and then the department can specify the mix/ac type they want for a permanent pavement? | This was addressed with addendum number 3. | Scott Lawry | 12 | 2017-06-06 12:19 | 2017-06-08 16:52
20170613 | 20170613017 | 17 | Fill and Restore Existing Concrete Rumble Strips | Through asking questions of industry professionals, it appears this is hand work for both placement and removal of the hot mix. If this work is to last over the winter I would be hesitant to expect the hot mix to hold into the rumble strips groves over the winter. Appears in other regions this has been accomplished by milling out the concrete, pouring a new section and milling the rumble strips after the completion of the project. | The rumble strips to be filled are at the east end of the project near the structures to be widened. This structure work will not be done until the 2018 construction season, so there would be no reason to fill the rumble in 2017. | Scott Lawry | 13 | 2017-06-06 12:29 | 2017-06-06 17:16
20170613 | 20170613017 | 17 | Is there an "optional" Construction Joint for the Pier 2 & East Abutment Diaphragms on B-55-65 | Please refer to sheet 24 of 38 B-55-65 page 646. Typically the joint where the abutment and pier diaphragms meet the deck is listed as "optional". See note on B-55-148 sheet 15 of 17 page 703. Is there an "optional" joint for the diaphragms on Bridge B-55-65 or is the joint "required"? | Yes an optional joint will be permitted. | Scott Lawry | 14 | 2017-06-07 11:23 | 2017-06-08 14:32
20170613 | 20170613017 | 17 | R-55-19 Utility Conflict | It appears there is not enough room to excavate for the MSE Wall Straps with the Fiber Optic in its current location. Will this fiber be moved before construction? If not moved how will DOT protect it during construction. Please advise. | No, the fiber will not be moved prior to construction. It will likely be exposed during construction and will be directly coordinated with the utility as a fiber watch on site to protect. | Scott Lawry | 15 | 2017-06-12 09:28 | 2017-06-12 12:09
20170613 | 20170613017 | 17 | Please confirm all dowel bars drilled into the existing pavement will be paid. | Please confirm all dowel bars drilled into the existing concrete pavement associated with Concrete Pavement Repair Precast 12-inch will be paid for under the Drilled Dowel Bar item. | Under the payment section of Article 58. Concrete Pavement Repair Precast 12-Inch, Item SPV.0180.001--Sawing concrete, according to Sawing Concrete Precast Panel Installation, and Drilled Dowel Bars will be paid separately. | Scott Lawry | 16 | 2017-06-12 12:16 | 2017-06-12 16:01
20170613 | 20170613019 | 19 | Concrete Masonry Overlay, Approaches | The plan indicates there is 36 CY of Concrete Masonry, Approaches located on I-39 NB. Can the DOT verify this is for the approaches to structure B-11-58? | The quantity of 36 CY for Bid item 509.2600 Concrete Masonry Overlay Approaches is for the concrete travel lanes on the north and south approaches to the deck overlays on railroad structures B-11-58 and B-11-59. | Scott Lawry | 1 | 2017-05-23 15:33 | 2017-05-30 12:15
20170613 | 20170613019 | 19 | 20% DBE GOAL | The 20% DBE Goal will be hard to meet on this project. Our initial review of the pay Items and search for qualified sub contractors does not look good. Can the DBE Goal be reduced to 4%? | The goal will not be reduced. The requirements regarding DBE participation, including the Good Faith Waiver Process is covered under ASP 3. Please review pages 69-88 of the proposal to better understand the requirements. ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2017/06June_13/20170613019proposal.pdf | Scott Lawry | 2 | 2017-05-30 12:27 | 2017-05-30 12:41
20170613 | 20170613019 | 19 | Structual Steel Framing Plans | Can the structural steel framing plans be available for downloading for structures B-11-55, B-11-56, B-11-58, B-11-59. The information is needed to calculate the surface areas of the steel to be cleaned and coated. | The files are located at http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613019/ The original plans may not accurately reflect current field conditions and should be used for the bidders general knowledge only. A field review should be conducted by the Contractor per specification section 102.5 to confirm the conditions the bidder will encounter in the field. | Scott Lawry | 3 | 2017-05-30 14:55 | 2017-06-02 06:39
20170613 | 20170613021 | 21 | Earthwork Summary | There is no earthwork summary in the miscellaneous quantities, can that be provided? | An addendum will be issued to address this issue. | Scott Lawry | 1 | 2017-05-15 11:07 | 2017-05-16 12:08
20170613 | 20170613021 | 21 | Line # 100 | For the Abandoning Culvert Pipes item we are wondering if the intent by DOT is to have these pipes slurry filled? Per the specs it does not require slurry but from past experiences from pipes that get abandoned under roads like 151/18 in most all cases they intended them to get slurried. | The department is comfortable with closing in the ends and buried without filling with slurry because of the size and class of the pipe. | Scott Lawry | 2 | 2017-05-17 15:18 | 2017-05-30 17:04
20170613 | 20170613021 | 21 | Geotechnical Report | Can a geotechnical report be provided for the project. | The requested file has been posted. http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613021/ | Scott Lawry | 3 | 2017-05-17 16:53 | 2017-05-18 16:55
20170613 | 20170613021 | 21 | Schedule | Can DOT provide a project schedule? | The requested file has been added to the SW page http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-sw.aspx ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613021/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 4 | 2017-05-25 12:13 | 2017-05-31 08:53
20170613 | 20170613021 | 21 | HMA Paving | Per plan and bid item, there is currently a 3 MT HMA being used for all 3 Lifts including upper on STA 1120+00 thru 1138+05. This is shown on the typical finished section on sheet 7. Is a 3 MT desired for a Surface lift? There is also no safety edge or notched wedge called out for in the plan. Does the Department anticipate either of these items being needed? If yes, what locations? | 1. The mix type will be the same for all three layers of the 10â€ HMA Pavement because of quantity of mix and thickness of layers. 2. Safety edge is not needed unless the paved shoulder width is 3â€™ or less in width. 450.3.2.11 3. The notched wedge longitudinal joint is required by the standard specifications unless the engineer directs or allows an alternate joint. 450.3.2.8 (3) | Scott Lawry | 5 | 2017-05-31 08:36 | 2017-06-01 08:19
20170613 | 20170613022 | 22 | Shoulders | Can the department confirm the requirements of grading on the gravel shoulders for the project as they are 3â€™ paved 3â€™ gravel. Is there any grading of the 4:1 slopes to match into the gravel shoulder? | The plans indicate the shouldering is for the 3â€™ width as shown and any shouldering would stop at the foreslope. No grading would be completion of the shoulders. | Scott Lawry | 1 | 2017-06-06 13:01 | 2017-06-06 13:02
20170613 | 20170613024 | 24 | Temporary Epoxy | Can you clarify why the large difference in temporary epoxy (pre-rumbles) compared to regular epoxy (post rumbles)? It appears the temporary is only placed once after each day's paving run. Thank you. | It is anticipated that the contractor will mill and overlay the asphalt one direction at a time. After the first pass of paving, temporary epoxy will be required to be placed only on the new asphalt since the other lane will have existing pavement marking. After the second pass of paving, temporary epoxy will be required to be placed on both sides. This will ensure the proper width is maintained between markings. The permanent epoxy will then be applied after the centerline rumble strips are installed. | Scott Lawry | 1 | 2017-06-01 13:28 | 2017-06-05 10:45
20170613 | 20170613026 | 26 | Asphalt Surface Drives | The plan detail shows a sawcut for asphalt drives at 5' from existing paved shoulder. If that is the case then when we pave the HMA surface 2' wider than existing we should be able to wing out and catch the 3' asphalt drives as we go by. It will be easier to track tonnage for the drives if the asphalt for the drives is part of HMA item. If the plan detail is incorrect and the sawcut for the AS Drives is at 5' from the new edge of paved shoulder then the paver will have to come back through and pave each drive after the HMA is complete. If that is the case then leave the item Asphalt Drives as is separate from the HMA item and change the detail to say 5' from new edge of paved shoulder. | The typical saw joint location should be 7 ft. (TYP) from the existing paved shoulder edge. (5 ft. from new paved shoulder edge) An addendum will be created for this change to the detail showing this. The item of Asphaltic Surface Driveways and Field entrances should remain and that the Engineer in the field will determine final saw cut locations. | Scott Lawry | 1 | 2017-05-18 11:58 | 2017-05-19 13:16
20170613 | 20170613026 | 26 | Removing Distressed Pavement Milling | Can a construction detail be provided for this item? A depth of cut and minimum width would be helpful. The special provision for this item does not provide this information. Thanks | an addendum will be issued to add a detail for this item. | Scott Lawry | 2 | 2017-05-23 11:57 | 2017-05-30 12:49
20170613 | 20170613026 | 26 | Removing Distressed Pavement Milling -vs- Same Day Mill and Fill | Per addendum #1 "Paving Operations" requires milled surface to be paved back by end of each day. This does not leave time for removing distressed pavement milling and HMA patching. Stopping and starting a same day mill & fill job is very costly to put crews, trucks, and equipment on hold. How do you plan to handle this? | The department has used the same specifications on two previously let projects out of the Madison Office. The mainline pavement was milled, distressed areas were marked, milled with a 4â€™ mill, filled gap in with a smaller crew, then paved mainline. It does require some additional coordination, but department does feel it is possible. | Scott Lawry | 3 | 2017-05-30 17:26 | 2017-06-05 15:54
20170613 | 20170613030 | 30 | Earthwork Sta. to Sta. listing | Earthwork Summary does not match the Earthwork Tables. Can you please quickly post correct station to station listings to match earthwork summary? | We will update the earthwork table and summary table via addendum so that they show matching station to station limits. | Scott Lawry | 1 | 2017-05-11 07:54 | 2017-05-12 14:47
20170613 | 20170613030 | 30 | Earthwork for Strip Drains | Can you provide the Station to Station listings to go with the cross sections for the Strip Drains in Stage 1A (sheets 547-567) and Stage 2A (sheets 696-706)? That quantity should be separated (or quantified)from the rest of the earthwork because it happens below the drainage blanket. | The department does not plan to provide the requested station to station earthwork listings for only the strip drains in stage 1A and stage 2A. While the plans show sections for the wick drains, the requested earthwork table information has not been provided separately in previous corridor plans which has typically only shown the drainage blanket on the final stage cross section. | Scott Lawry | 2 | 2017-05-11 16:32 | 2017-05-17 10:51
20170613 | 20170613030 | 30 | Missing sign bridge plans | There appears to be a few sign bridge plans missing from the plans posted on line. | There were 4 sign bridges S-70-218 S-70-226 S-70-227 S-70-201 That were inadvertently left out of the plan, they will be added via addendum. | Scott Lawry | 3 | 2017-05-17 08:24 | 2017-05-17 08:25
20170613 | 20170613030 | 30 | Medium Riprap | Can you please provide a location and quantity breakdown of the Medium Riprap? All that can be found is 8 or 9 locations for pipe outfalls and 868 CY seems like an extremely large quantity for just those. Cannot find any other locations in the plans other then what's on the erosion control drawings. | The correct quantity for stage 1A should be 36 CY and the total Medium Riprap quantity 64 CY. This change will be reflected in an addendum. | Scott Lawry | 4 | 2017-05-17 10:27 | 2017-05-18 07:53
20170613 | 20170613030 | 30 | Concrete Barrier Wall & Transitions | Where are the two concrete trasitions called out on the plan details ? Also can't find in the MQs that random S32 (CB05) on the back side of R-70-142, looks as if its in a parking lot, Just wondering if that is on this project ??? | The missing quantities should been addressed in an Addendum and the S32 barrier in question is part of the project scope. | Scott Lawry | 5 | 2017-05-18 09:09 | 2017-05-30 12:44
20170613 | 20170613030 | 30 | Geotechnical Borings in Wick Drain Areas | Can the geotechnical borings that were conducted in the wick drain areas be provided? | The files can be found at the following location. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613030/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx | Scott Lawry | 6 | 2017-05-22 14:42 | 2017-05-26 11:39
20170613 | 20170613030 | 30 | Schedule | Can DOT provide a construction schedule? | The file is located at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1517-75-72/ or http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 7 | 2017-05-25 12:21 | 2017-05-30 12:34
20170613 | 20170613030 | 30 | Storm sewer structures | The storm sewer tables in the misc. quantities only give rim elevation relative to each structure. Reviewing the storm sewer plan profile there are some structure that appear to show sumps but are not itemized for a Catch Basin item which requires sumps per standard detail. Inlets 4 ft dia. #141,142 and 143 Inlets Median Type 2 #321,322 and 332 Inlets 2' x 2.5' #142B,143A and 171 Are these sumps to be considered incidental to the various inlet items? | An addendum will address the depths of storm sewer structures. The inlets in question are not in a sump condition but are drawn on the plans that way due to constraints in the design software when inlet depths are less than 3â€™. Refer to depths and elevations called out on Storm Sewer detail sheets and on the MQ sheets. | Scott Lawry | 8 | 2017-05-30 09:18 | 2017-05-30 12:46
20170613 | 20170613030 | 30 | Ramp Closure | What is the current scheduled permanent closure of the USH 10WB to USH 41SB Ramp in the NW Quad of the Interchange? Is it only tied to the start of Stage 2A or is it getting closed before that traffic switch? | This loop ramp will be closed in mid-July 2018 and traffic making the USH 10 WB to I41 SB traffic movement will be switched to the new flyover ramp. After this time, vehicles heading west on USH10 that would like to turn around and head back east will need to continue west to the CTH CB interchange or south to the CTH II interchange. This traffic switch will need to be completed in mid-July by both the 1517-07-80 and the 1517-75-72 project contractors. The break between the traffic control switch on the two projects is around STA 212+00. Traffic control (signing, temp barrier, pavement markings) will need to be completed under both projects to make the switch happen. | Scott Lawry | 9 | 2017-05-30 15:49 | 2017-05-31 12:37
20170613 | 20170613030 | 30 | CAD Files | Can we get the CAD Files for this Project? | The requested files have been posted. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613030/ | Scott Lawry | 10 | 2017-06-02 16:57 | 2017-06-07 17:44
20170613 | 20170613030 | 30 | MSE Backfill Quantity | Are the Wall Wire Faced Mechanically Stabilized Earth backfill quantities (temporary and/or permanent) included in the Embankment quantity? | The estimated volume of backfill will be removed from the Embankment quantity and will be shown on the miscellaneous quantity earthwork table with an addendum. | Scott Lawry | 11 | 2017-06-05 15:35 | 2017-06-07 14:24
20170613 | 20170613030 | 30 | Midway Drive Haul Road | 1.) Will over-sized loads be allowed to travel the Haul Road as detailed on the Traffic Control Typical Section 1A of existing Midway Road 2.) How is the repair of this section of road handled if repairs are required? 3.) When is this section of Midway Road scheduled to be reconstructed? | Midway Road will continue to carry traffic until 2019. It will need to be kept in a drivable condition and drainage will need to be maintained throughout the interchange. Any damage to storm sewer pipes, etc. will need to be repaired. The haul road lanes will remain unused after this project though and should not need pavement repairs completed. Any repairs required would be considered haul road repair and paid under the maintenance and repair of haul road item. | Scott Lawry | 12 | 2017-06-05 21:17 | 2017-06-07 15:25
20170613 | 20170613030 | 30 | Removing Asphaltic Surface | Qâ€”Will the removal of the asphaltic surface be paid for under item 204.0110 Removing Asphaltic Surface within the cut sections or will it be incidental to the item of 205.0100 Common Excavation? | Aâ€”The removal asphaltic surface will be paid for under item 204.0110 Removing Asphaltic Surface. | Scott Lawry | 13 | 2017-06-08 14:26 | 2017-06-08 14:27
20170613 | 20170613030 | 30 | SPV item 0090.017 Temporary Shielding | The spec does not give us a whole lot of guidance, no detail, just tells us to design something. What are we trying to stop? Rocks/ aggregates, a concrete pipe that rolls off a truck? I can see a wide variation of the interpretation of what is acceptable to satisfy this spec. Is something as simple as precast barrier adequate? Some sort of reinforced silt fence? Not sure how to price out this item. | The intent of the temporary shielding is to prevent debris or loose aggregate that could be kicked up from adjacent equipment use from falling onto the mainline traffic below the temporary MSE wall in Stage 1. On past projects a contractor has used chain-link fencing material with a geotextile fabric to prevent the material from falling into traffic. It does NOT need to provide any structural or crashworthy protection. | Scott Lawry | 14 | 2017-06-08 15:23 | 2017-06-09 08:34
20170613 | 20170613030 | 30 | Soil Information for existing soils on the project | Can you provide soils information such as moisture, soil types, and borings that have been done in the areas of common excavation. There is not enough time to do our own analysis. We would need to get a traffic control plan and get permission to excavate areas for samples. Proctors would take an additional 3-5 days. Can you provide original sources of the fill for these areas Sta 243-270 that would be very beneficial also. Please give all information that would be required so we can determine production rates and drying time etc for the excavation. Can you also provide the number of days that will be added to the schedule for this additional item. | An Additional file has been posted. The existing soils information available is posted at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613030/1517-75-72%20Soils%20Information/ | Scott Lawry | 15 | 2017-06-09 09:46 | 2017-06-09 10:40
20170613 | 20170613030 | 30 | Sign Bridge Sheets | There were sign bridge plans added via addendum 2. Only sheet 6 of 11 was added for S-70-218, S-70-226, & S-70-227. Will sheets 1-5 & 7-11 be added as well? | The entirety of the sign bridge plans were added via addendum #1. Sheet 6 of 11 that was added via addendum #2 was to replace the sheet that was added in addenda #1. | Scott Lawry | 16 | 2017-06-09 10:00 | 2017-06-09 10:39
20170613 | 20170613030 | 30 | Embankment Volumes | Question: Do the station to station embankment volumes shown in the earthwork table account for the volume of structure backfill behind MSE walls. | Answer: In the advertised plans some of the MSE Wall backfill was accounted for in calculating the volume of embankment but only to a width of 10â€™ behind the wall, as can be seen in the cross sections. Stations requiring additional width of MSE Wall backfill based on wall height are not accounted for in the embankment tables. The estimated MSE Wall backfill quantity shown in the addendum earthwork table is estimated for all MSE Wall backfill and has not been adjusted for the 10â€™ width that was previously accounted for. The contractor designed MSE wall will ultimately determine the amount of backfill, therefore all quantities are just estimates. | Scott Lawry | 17 | 2017-06-09 10:37 | 2017-06-09 10:37
20170613 | 20170613030 | 30 | Pre-fill Elevations | 1.) When was the last time the pre-fill area (placed by previous contract) was surveyed? Do the cross sections provided accurately represent the existing conditions? 2.) What was the planned settlement of this area? 3.) What was the actual settlement of this area? | A1) The survey of the existing surface used for the plan sections was dated 1/4/17 and was shot after completion of fall 2016 work. Additional work has taken place in the area and survey updates have since been completed in April and May but no more recent adjustment has been made to the existing surface shown in the plans. A2) The planned settlement of this area varies by station range and can be found the Zone 2 Embankment report posted to HCCI ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613030/1517-75-72%20Soils%20Information/ In general, the largest expected settlement is 20 to 28 inches. A3) Settlement data taken in the fall of 2016 did not yet show significant settlement but no more recent settlement information is available. Settlement gauges will be surveyed prior to the start of construction but we are unable to provide updated information prior to Letting. | Scott Lawry | 18 | 2017-06-11 23:16 | 2017-06-12 13:49
20170613 | 20170613030 | 30 | ASP-5 Fuel Cost Adjustment | The ASP-5 table provided with the proposal does not included the Roadway Embankment item. It was our understanding that proposals that utilized the the Roadway Embankment item would have it added to the list. Please advise. | See article 10.3 Roadway Embankment, Item SPV.0035.003 after the payment section. ASP-5 will be applied to this item. The fuel usage factor for this item is 0.23. | Scott Lawry | 19 | 2017-06-12 08:23 | 2017-06-12 08:30
20170613 | 20170613030 | 30 | Temporary Raised Pavement Markers, Type I | The addendum came out calling for Temporary Raised Pavement Markers, Type I however it calls for LF not "each". The quantity shown is for 13,162 LF. How are we to measure the quantity and also, in the plan detail for Stage 1A it calls for Temporary Raised Pavement Markers, Type II? Can you explain the differences? | The addendum that was issued correctly has the schedule of items listed as 649.2100 Temporary Raised Pavement Markers Type I, shown as 13,162 EACH. There was a typo on the addenda form and on the detail sheets. The project only needs the Type I markers and item 649.2100 is an each item not a LF item. | Scott Lawry | 20 | 2017-06-12 11:00 | 2017-06-12 11:44
20170613 | 20170613031 | 31 | HMA Percent Within Limits | Please confirm that the HMA Percent Within Limits (PWL) Test Strip & HMA Pavement Percent Within Limits QMP is for Item 460.5224 HMA Pavement 4 LT 58-28 S only and that Item 460.5223 HMA Pavement 3 LT 58-28 S, Item 465.0105 Asphaltic Surface & Item 465.0110 Asphaltic Surface Patching are excluded from these requirements. Thank you. | The requirements for HMA Pavement Percent Within Limits QMP and HMA Percent Within Limits (PWL) Test Strip are only for item 460.5224 HMA Pavement 4 LT 58-28 S. Items 460.5223 HMA Pavement 3 LT 58-28 S, 465.0105 Asphaltic Surface, and 465.0110 Asphaltic Surface Patching are not included with the PWL requirements. The Miscellaneous Quantities will be updated via an addendum summarizing the eligible PWL tonnages for item 460.5224 HMA Pavement 4 LT 58-28 S. Additionally, item 460.2000 Incentive Density HMA Pavement, will be added to the contract via an addendum taking in account the small quantity of item 460.5223 HMA Pavement 3 LT 58-28 S and will also be summarizing eligible tonnages within the updated Miscellaneous Quantities. | Scott Lawry | 1 | 2017-05-12 14:36 | 2017-05-17 08:27
20170613 | 20170613031 | 31 | Earthwork Summary | Earthwork Summary does not match the Earthwork Tables. Can you please quickly post correct station to station listings to match earthwork summary? | There is a station error within both the earthwork summary in the miscellaneous quantities and the table in the earthwork details that will be addressed via an addendum. The correct station to station is 92+64 to 96+45 in the earthwork summary. The correct stations for the table within the earthwork details are 92+64, 93+20, 93+77, 94+75, 95+45, 96+05, and 96+45. | Scott Lawry | 2 | 2017-05-16 12:16 | 2017-05-16 12:16
20170613 | 20170613031 | 31 | Railroad Flagger | Will the contractor have to arrange and pay for a railroad flagger for the work at the railroad crossings located between sta 92+64 and sta 96+13 during the maximum of 10 working day closure? Thank you. | Flagging is incidental to the contract and the contractor will not be reimbursed. Please see article 7. Railroad Insurance and Coordination for contact information for the railroad. | Scott Lawry | 3 | 2017-05-17 14:45 | 2017-05-22 17:39
20170613 | 20170613031 | 31 | Railroad Flagger | Thank you for your response to the original question regarding the need for railroad flagging during the closure between sta 92+64 and sta 96+13. However we would ask that the question be more specifically answered. Article 7 A.2 discusses work by the railroad. Since the railroad is working along side of and coordinating with the contractor at this location to remove and replace the tracks will the contract have to provide for a railroad flagger or will the railroad provide the flagger as part of their work and at their cost. Thank you. | A flagger may not be required when the railroad is on site to participate in the reconstruction of the railroad crossings. However, it is up to the contractor to contact the railroad to see if and when they require flagging. Prior to the track window and highway closure to replace the two at-grade crossings surfaces, the 4085-61-60 contractor shall set up a meeting with the Railroad and Department to coordinate final construction details and staging. Close coordination with the railroad is required, especially with regards to the installation of the new crossings. | Scott Lawry | 4 | 2017-05-23 11:42 | 2017-05-26 12:08
20170613 | 20170613031 | 31 | Micromilling, Item SPV.0180.01 | Is a micro-milling cutter drum pattern on the mandrel of the milling machine necessary to perform item Micromilling, Item SPV.0180.01? | Any cutter drum pattern on the mandrel of the milling machine can be used to perform item Micromilling, Item SPV.0180.01. | Scott Lawry | 5 | 2017-06-07 15:28 | 2017-06-07 15:33
20170613 | 20170613032 | 32 | Cold In-place Recylcing (CIR) | On page 8, the intersection cold in-place recycling (CIR) detail, it shows CIR through the intersections at a width of 22â€™. Throughout the rest of the mainline the CIR width is 34â€™. Is WisDOT open to allowing the CIR at a constant width of 34â€™ even through the intersections? In areas were the asphalt is thin along the gutter and base is incorporated into the CIR mix, the oil being added can be adjusted. This would be preferred over transitioning the CIR operation from 34â€™ to 22â€™ back to 34â€™ at the intersection locations. | The Region is open to cold in-place recycling (CIR) at a width of 34â€™ as long as the amount of oil being incorporated is properly adjusted to fit the conditions. | Scott Lawry | 1 | 2017-06-05 14:58 | 2017-06-05 14:58
20170613 | 20170613032 | 32 | Asphalt Pavement | Q1. Can you clarify removing asphaltic surface butt joints on page 34. Are butt joints to be cut at the intersection as well as mainline? Q2. Typical finished cross sections show a 4 MT 58-28 S. Sheet 31, Estimate of quantities shows a 4 LT 58-28 S and the miscellaneous quantities on sheet 35 refer to 4 MT 58-28 S. Should the item in the estimate of quantities be 4 MT 58-28 S? Q3. Per PWL spec NEA believes that item 0120 â€˜Incentive Density HMA Pavementâ€™ should be removed from the job. The QMP on this job for that area should be by DOT acceptance and there should be no incentive or disincentive for that area. Could you please verify? | A1. Butt joints are to be cut along mainline at the project limits and on each side of the railroad crossing, at the driveways, and along the side roads at intersections. The miscellaneous quantity table on page 34 summarizes the butt joints that are within the range of stations shown. A2. The item in the estimate of quantities should be 4 MT 58-28 S. 4 LT 58-28 S will be removed and 4 MT 58-28 S will be added with an addendum. A3. Incentive Density HMA Pavement will be removed from the job with an addendum. The pavement in this area will be tested by DOT Acceptance with no incentive or disincentive. | Scott Lawry | 2 | 2017-06-06 12:41 | 2017-06-06 12:42
20170613 | 20170613032 | 32 | Asphalt Surface Item | Q1. Could an Asphaltic Surface item be added to the job for the following reasons? a. Per the specials on page 42, #28 Prepare Foundation for HMA Layer, this special pertains to work done after the CIR is complete. When reading through the special the last paragraph talks about the department paying separately for the Asphaltic Surface that would have to be placed per the special. b. The asphaltic surface item (465 item) should be used for the pipe patching as well as those pipe patch areas should not have testing on them due to it being a patch and not be able to establish a rolling pattern. Secondly, when the mainline item is blended with patching work it drives the price of that item up and does not reflect the true cost of that item. | A1. Item 465.0120 â€˜Asphaltic Surfaceâ€™ will be added with an addendum and an undistributed quantity will be included to correct potentially yielding areas. The construction detail for the culvert pipe replacements will also be modified to specify asphaltic surface for the pipe patch areas. | Scott Lawry | 3 | 2017-06-06 12:45 | 2017-06-06 12:46
20170613 | 20170613032 | 32 | Reconnect Existing Storm Sewer | Q1. Item 0660 â€˜Reconnect Existing Storm Sewerâ€™ 3 EA, is there a detail or miscellaneous quantity that shows where these 3 are? | The Culvert Summary table within the miscellaneous quantities will be modified to show the location of the reconnect existing storm sewer item. All three locations are adjacent to the culvert being replaced at Station 409+10/409+12. | Scott Lawry | 4 | 2017-06-06 12:48 | 2017-06-06 12:48
20170613 | 20170613036 | 36 | Completion Date | Can the completion date for this project be changed to allow the contractors more time to schedule the project? | With the issuance of addendum #2, the completion date has been revised from a completion date of September 1, 2017 to a completion date of September 30, 2017. | Scott Lawry | 1 | 2017-05-23 09:33 | 2017-05-23 13:13
20170613 | 20170613036 | 36 | Mix Type | General note #7, on plan sheet 2 lists a 9.5 mm mix to be used on the lower layer. The bid item is for a 4 mix. Which is correct? | The special provisions, typical sections, and all bid items on the plan are correct. The general note should read the lower lift of 1.5â€ thickness having a 12.5mm aggregate size, not 9.5 mm as currently shown. Per standard specification 105.3 when a discrepancy between documents occurs, the special provisions would take precedence over a general note in the plan. | Scott Lawry | 2 | 2017-06-05 09:36 | 2017-06-06 11:29
20170613 | 20170613037 | 37 | 4LT 58-34S | The bid proposal shows item 460.5244 HMA 4LT 58-34S with a plan quantity of 43 ton. Standard specifications have the following for QMP HMA. Test each design mixture at a frequency at or above the following: TOTAL DAILY PLANT PRODUCTION Effective with the December 2016 Letting 181 2017 Standard Specifications FOR DEPARTMENT CONTRACTS SAMPLES in tons PER DAY[1] 50 to 600 1 601 to 1500 2 1501 to 2700 3 2701 to 4200 4 greater than 4200 see footnote[2] [1] Frequencies are for planned production. If production is other than planned, conform to CMM 8-36. [2] Add a random sample for each additional 1500 tons or fraction of 1500 tons. Since the plan quantity is <50 ton, there would be QMP testing, so why not just make this a Asphaltic Surface item? Possibly Asphaltic Surface Special then list the 4LT 58-34S? | The bid item will remain unchanged, however, testing will not be required if less than 50 tons per day, per the specifications. | Scott Lawry | 1 | 2017-05-23 07:09 | 2017-05-30 12:16
20170613 | 20170613037 | 37 | Utility - Gas Line Location | Under the utility section and as shown in the plans, it appears there would be no conflict with the existing gas line at this project. Upon visiting the site, there are gas line markers located within 4 to 5 feet from the existing bridge wings. Would the DOT be able to verify that what is shown in the plans is correct? | The gas line location shown on the plans is based on markings provided by Diggers Hotline that were picked up during the field survey. WE Energies also provided the system maps that appear to agree with what was surveyed and what is shown on the plans. The contact information for WE Energies can be found on page 2 of the plan. WE ENERGIES 104 W, SOUTH STREET RICE LAKE, WI 54868 ATTN: LEWIS KNAPP 71S-234-9605 715-419-2196 (CELL) lewis.knapp@we-energies.com | Scott Lawry | 2 | 2017-05-23 15:25 | 2017-05-26 12:04
20170613 | 20170613038 | 38 | Structural Steel Framing Plans | Can the structural steel framing plans and details be available for downloading for structure B-17-0638? We need this information to calculate the surface area to be cleaned and coated. | The original structure plans can be found at the following location ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613038/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nw.aspx The original plans may not accurately reflect current field conditions and should be used for the bidders general knowledge only. A field review should be conducted by the Contractor per specification section 102.5 to confirm the conditions the bidder will encounter in the field. | Scott Lawry | 1 | 2017-05-30 15:03 | 2017-06-01 13:04
20170613 | 20170613041 | 41 | As-built plans | Can the as built structural steel framing plan and details for structure B-59-0154 be made available? | The file can be located at: http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-ne.aspx or ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170613041/ The original plans may not accurately reflect current field conditions and should be used for the bidders general knowledge only. A field review should be conducted by the Contractor per specification section 102.5 to confirm the conditions the bidder will encounter in the field. | Scott Lawry | 1 | 2017-05-30 14:50 | 2017-05-30 14:50
20170613 | 20170613041 | 41 | 509.9020.S Epoxy Crack Sealing | Are the products on the WisDOT approved products list for "Low Viscosity Crack Sealers for Bridge Decks" acceptable for SPV item 509.9020.S? | WisDOT-approved â€œLow Viscosity Crack Sealers for Bridge Decksâ€ are acceptable for sealing the cracks on the top surface of the deck, however cracks on vertical or overhead surfaces (deck underside, sidewalks, abutments, wingwalls, piers, etc.) will require a different procedure and potential additional product as recommended for the application by one of the manufacturers listed in the special provision. | Scott Lawry | 2 | 2017-06-05 11:18 | 2017-06-06 14:04
20170613 | 20170613041 | 41 | Cylinder Bearings | Q1. On sheet #53 of the proposal under â€˜Items to be repaired or rebuildâ€™: QTY 4 - Cylinder Rod end Bearing â€“ 16.5354â€ Bore Spherical Roller Bearing. Section C.10.5.1 on page 75 indicates that the intent is to rotate these bearings in place, document any abnormalities, turn them 180 degrees and reassemble. However, they are listed to be repaired or rebuilt. If all 4 were to be replaced, this is potentially a significant increase. I am not clear on whether or not this needs to be included. Further, if we inspect the bearings and find them to be fine once rotated there is no indication that a credit to the department would be warranted. 2. Same issue with the Cylinder Trunnion Bearings, although the price point to replace these is lower. | The scope of work for the cylinder rod end bearing and cylinder trunnion bearing is simply to inspect and make sure that they are re-installed 180 ° from existing position, not to replace. In the unlikely event that these would require replacement and if directed to do so by the engineer, a change order would be warranted. | Scott Lawry | 3 | 2017-06-11 13:49 | 2017-06-11 13:49
20170613 | 20170613041 | 41 | Hard Line Hydraulic Piping Sections | On sheet #53 of the proposal under â€˜Items to be repaired or rebuildâ€™: QTY 16 - Hard Line Hydraulic Piping Sections Approximately 200 lf, 0.75â€ to 4â€ O.D. First off, is this saying that there is potentially 200â€™ of hard line piping in 16 locations that may need to be repaired or rebuilt? If so, you are asking us to bid an item that will require repairing or rebuilding somewhere between 0 LF and 3,200 lf of hard line piping varying from ¾â€ dia. to 4â€ dia. as part of the pump sum item. Rough estimates for this range between $0.00 if all hard line piping is acceptable to a few hundred thousand dollars if it is all found to be deficient. Again, nothing mentioned of an assumed quantity to base the bid price on or if a credit to the owner would be warranted if no pipe work was required. | The 200 LF hard line hydraulic piping was intended as a total (not to be multiplied by 16). This is an estimate of the piping that needs to be removed in order to remove the cylinders from the pier, as noted on the mechanical drawing as â€œhydraulic piping to be removed if necessary," assuming the contractorâ€™s means and methods require the space on the floor under the cylinder to be clear as part of the cylinder removal plan. | Scott Lawry | 4 | 2017-06-11 13:52 | 2017-06-11 13:53
20170613 | 20170613041 | 41 | Spare Parts | Page #53 of the proposal under Spare Parts: The recommended PVV-250 pump will not provide the same lifting speed as the existing pumps unless it is run at a significantly higher RPM. This would mean that the existing electric motors would also need to be replaced. Should the cost of new motors be included? Also, there is no way to provide a system that is drop in ready as indicated in the proposal, and a test fit-up would require destruction of existing mounting plates, weldments, etc. The spec indicates that the spares may require a test fit-up. This will be a substantial undertaking and seems to be a waste of time and money. The current system would have to be dismantled and portions destroyed to install the spares. This would then be tested, approved, and then removed to replace the original components. New mounting plates and piping connections would be required and all testing performed again. All of these operations potentially adding contamination to the hydraulic system. | A test fit-up is required. The department would be open to allowing just one test fit up, leaving it installed and use the existing as the spare. Regarding the PVV-250: Spare parts - Purchase, Package, & Deliver: (QTY. 4) Oilgear Legacy PVK-370 Variable Displacement Hydraulic Pump â€“ Oilgear recommends their PVV-250. Replace with Oilgear, Bosch Rexroth, Parker, or equal. We specify that the contractor is to supply spares that are equivalent to existing with the above statement. It is not the intent to replace the motors. | Scott Lawry | 5 | 2017-06-11 14:02 | 2017-06-11 14:03