## qandasearchletting_results
2018-02-12 20:00
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20180213 | 20180213001 | 1 | DESIGN FILE DATA | 1- IS THERE ANY DESIGN FILE DATA AVAILABLE? 2- IS THERE ANY SOIL BORING DATA? | The soils boring can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213001/ The design files can be found at: The files can be located here: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213001/ | Scott Lawry | 1 | 2018-01-15 16:43 | 2018-01-16 13:36
20180213 | 20180213002 | 2 | Install City Furnished Street Signs, SPV.60.05 | The Specials state that the contractor is to install the No Parking and Street Name signs at the location shown in the plans The signing plan, starting on p. 20, seem to indicate that the Street Name signs are on top of the STOP signs. I do not believe this is allowed per WisDOT signing standards. In addition, the post being used is a U-Channel post. If the sign is mounted on the STOP sign or on another post next to it, what system or method exists for mounting Street Name Signs on this type of post? Please provide direction. | Street name signs will be mounted on their own separate sign posts and the City of Beaver Dam will furnish the mounting hardware for the street name signs to the Contractor â€“ a forthcoming addendum will address these changes. | Scott Lawry | 1 | 2018-01-18 09:16 | 2018-01-23 09:39
20180213 | 20180213002 | 2 | Curb and Gutter | Is it possible to pour the curb integral to the concrete pavement in the block from Maple to Third, similar to the rest of the project? The plans show the curb being hung onto the concrete pavement section in this location. | It is at the Contractorâ€™s discretion to pour that section of curb integrally, as long as all other requirements of the contract documents are met. | Scott Lawry | 2 | 2018-02-12 16:42 | 2018-02-12 16:42
20180213 | 20180213003 | 3 | Cad files | Can you please release the cad files for this project? Thank you. | The zip file has been posted at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213003/ | Scott Lawry | 1 | 2018-01-11 14:04 | 2018-01-16 08:11
20180213 | 20180213003 | 3 | Earthwork Data Documents | Can the Earthwork Data - Excel documents be posted? Thanks | The excel file was included with the zip file that contained the other design files. The earthwork file has been pulled copied and placed at the same location for ease in getting to the file. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213003/ | Scott Lawry | 2 | 2018-01-15 15:15 | 2018-01-16 13:14
20180213 | 20180213003 | 3 | Temporary Signals | Q: Will WisDOT consider an approved alternative or equal for Bid Item 661.0200 Temporary Traffic Signals for Intersections (STH 19 & STH 113), which would include a portable temporary traffic signal? | A: All products must also be on the Qualified Electrical Products List (QPL) unless specified otherwise. The department will not allow a portable temporary traffic signal to be used on this project due to the number of lanes and complexity of the intersection(s). | Scott Lawry | 3 | 2018-01-16 08:15 | 2018-01-16 08:15
20180213 | 20180213003 | 3 | Soil Borings | Can the soil borings be posted? Thank you | A summary of the soil borings can be found in the plan on page 38. Additional information regarding the borings can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213003/ | Scott Lawry | 4 | 2018-01-19 10:28 | 2018-01-22 11:52
20180213 | 20180213003 | 3 | Temporay Marking | The plan calls for 36,575 LF of Temporary Marking Line Removable Tape (4-inch & 8-inch) and does not include a quantity of wet reflective tape as shown on the advertisement. The advertisement shows Marking Wet Reflective Tape, 36,575 LF. Which is correct? | The plans and specials provisions can be found at: Plan: ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2018/02February_13/20180213003plan.pdf Proposal: ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2018/02February_13/20180213003proposal.pdf These documents and any addenda that are developed are the correct bidding documents. | Scott Lawry | 5 | 2018-01-22 14:31 | 2018-01-22 14:34
20180213 | 20180213003 | 3 | Wet Reflective Contrast Epoxy | Good morning. Can you please check the quantity of the wet reflective contrast epoxy for this project? It appears the quantity is road length quantity rather than the quantity that will actually be placed. Thank you. | The design team reviewed the plan quantity. Wet Reflective Contrast Epoxy is used for the white lane line of the divided highway of STH 19/113 and STH 113 and for the edge lines of STH 19 two lane section. Please see pavement marking plan for more clarification. Regular epoxy is used for all other markings. | Scott Lawry | 6 | 2018-01-23 09:42 | 2018-01-23 12:31
20180213 | 20180213006 | 6 | Storm Sewer and Sanitary Sewer elevation information | There are a two structure replacements on the project but elevation information and pipe sizes are missing. What are the elevations for the structures? at: STA 105+10 - storm sewer inlet STA 109+40 - sanitary sewer manhole | An addendum will be developed to add pipe locations, the structure rim/invert elevation information, and structure depth information to the plan and profile sheets and the miscellaneous quantities. | Scott Lawry | 1 | 2018-01-23 09:42 | 2018-01-23 09:43
20180213 | 20180213006 | 6 | Sewer Utility Questions | Q: Under the tab for this item on sheet 23 of the plan set, two of the structures require â€œReplace storm casting and top 1â€™ of structure.â€ Can you elaborate on what is expected at those two structures? Are we replacing precast lids? Relaying a course of block on a block built structure? Q: Note also that the special provision says that the materials will be supplied by the city. Does this mean only the frame and ring castings will be provided by the city, or will all the materials including rings and the â€œ1â€™ of structureâ€ materials also be provided by the city? | A1: No structure work is expected. This work refers to replacing the frame and ring casting and the adjusting rings. A2: Only the frame and ring castings will be provided by the City. | Scott Lawry | 2 | 2018-02-12 15:41 | 2018-02-12 15:42
20180213 | 20180213006 | 6 | Sewer Utility Questions | Q: Are chimney seals required on any structures? Special Provision #16 references using the cityâ€™s specifications for the construction of sewers. In the cityâ€™s specifications, there are references to â€œClass Wâ€ manholes on which it appears that exterior chimney seals are required. While I donâ€™t notice any of the manholes on this plan called out specifically as â€œClass Wâ€, I just want to make sure that no one is expecting Chimney Seals. Q: Adjusting Rings: I am assuming that concrete adjusting rings are acceptable for all new and adjusted castings on the project. I just want to make sure this is the case as I noticed under Special Provision 12 (now deleted by addendum #1) that the Engineer intended to have â€œRubber Adjustment Rings.â€ I know this structure and special provision have been eliminated, but I just want to ensure that there are no requirements for either â€œrubberâ€ or HDPE adjustment rings. | A1: No structure work is expected. Chimney seals are not required. A2: Rubber or HDPE adjustment rings are not acceptable. Concrete adjusting rings are acceptable for all new and adjusted castings on this project. | Scott Lawry | 3 | 2018-02-12 15:43 | 2018-02-12 15:43
20180213 | 20180213007 | 7 | Concrete Quantity at Piers for B107 | I believe the concrete quantity is incorrect for the round column pier extensions. Please check. I find an approx quantity of 42 CY vs 28 CY. | This was addressed via addendum | Scott Lawry | 1 | 2018-02-05 15:36 | 2018-02-08 17:08
20180213 | 20180213007 | 7 | Welded Shear studs 3/4" x 6" Bid item 96 | It appears that the quantity for this bid item is incorrect. The total number of studs listed is 866 but it seems like the quantity should be closer to 2,046. 1,446 for the new girders and approximately 600 added to the existing girders. | The quantity will be corrected via addendum. | Scott Lawry | 2 | 2018-02-06 12:51 | 2018-02-07 09:31
20180213 | 20180213007 | 7 | Utility Issues - Piling | The special provisions state this project comes under Administrative Rule Trans 220. It also states that the six overhead ATC lines over the North abutment "cannot be deenergized during construction" Per OSHA standards we have to maintain a minimum clearance of 15 feet from the lines. Due to the utility restraint the piling for the North abutment can only be driven in 8 foot lengths. With that length we can't meet the standard specification requirements of 550.3.3.1 of max field splices of 4 for the designed pile length. How does the owner want us to proceed with operations that don't meet specification or jeopardize OSHA standards | Eight foot pile lengths can be used for the north abutments provided the splicing details in the plans are followed by the contractor. | Scott Lawry | 3 | 2018-02-07 09:12 | 2018-02-09 17:32
20180213 | 20180213007 | 7 | Project Schedule | The original schedule was very tight for this project. Addendum 1 just came out and added a bunch of additional work that drastically affects the schedule. The addendum did not address a revision to the schedule. Has the schedule been reviewed by the owner, after this addendum has been added, to see if this project can be safely completed? Can the owner provide a copy of the revised schedule for the contractors to review? | The contract completion time was a topic that was discussed early in the project as it related to the overall Zoo I/C construction completion. Due to the construction completion dates being discussed at the time, Zoo I/C construction as well as design staff reviewed the contract time for completion we provided and associated quantities as submitted and concluded as we did, that there was adequate time to complete construction operations prior to the completion date listed in the specs, particularly with the expedited contract award/NTP process being utilized. Additional structure construction work was added to the contract as Addenda No. 1 did mandate the complete replacement of the backwalls on both structures. Addenda No. 1 also significantly reduced the associated roadwork within the contract by removing the concrete pavement south of the structures and replacing it with a mill and overlay. Even post Addenda No. 1, the contract time provided is sufficient to complete the project. | Scott Lawry | 4 | 2018-02-07 09:16 | 2018-02-09 17:34
20180213 | 20180213007 | 7 | SPV.0090.4400. | In SPV.0090.4400 Drilled Shaft Foundation 60 Inch item C.2.8.9 Test Core Calls for the completion of a NQ core. Can we assume that no NQ coring needs to be completed since this shaft is not being embedded into rock? | The department agrees with the assumption of no NQ core, but would still require a boring at the drilled shaft location. Sample every 5 feet with a standard penetration test until 10 feet below the drilled shaft tip is reached. | Scott Lawry | 5 | 2018-02-08 11:10 | 2018-02-08 16:54
20180213 | 20180213007 | 7 | Fast Track Concrete Pavement | I did not see a special provision attached to the addendum to address the 2 new bid items of Fast Track Conc. Pvmt. What are the design strengths & timing that DOT is looking for on this project? | Please pages 7 and 8 that was posted as part of addenda #1 http://wisconsindot.gov/hccidocs/bid-let/2018/20180213/addenda/007-soi.pdf | Scott Lawry | 6 | 2018-02-09 12:16 | 2018-02-09 12:47
20180213 | 20180213009 | 9 | Soils Report | Can the soils report be provided? | The report can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213009/ | Scott Lawry | 1 | 2018-01-22 18:17 | 2018-01-23 10:49
20180213 | 20180213009 | 9 | Removal of Brick Roadway Base | In the removal plans, there is a general note that states the "Removal of Brick Roadway Base will be paid for as Common Excavation." Is the brick roadway base referring to the concrete or granite block base under the existing trolley rails as depicted in the typical Existing Section for Douglas Ave as shown on plan sheet 4? Please clarify. Thank you. | The removal of brick roadway base is for Hamilton Street that has a 6â€ brick base under the asphalt. The concrete or granite block under the trolley tracks is paid for separately under the Removing Trolley Tracks bid item (204.9090.S.01). The trolley tracks do not run down Hamilton Street so there should not be any overlap. | Scott Lawry | 2 | 2018-01-23 12:10 | 2018-01-24 11:10
20180213 | 20180213009 | 9 | Earthwork Volumes / Trolley Track Removal | Does the earthwork cut/fill volumes take into account the volumes of the trolley ties and concrete/granite block base removals? Please clarify. If the trolley track concrete/granite block base is below the proposed subgrade elevation, can the concrete/granite block base remain in place? Please clarify. | The earthwork cut was only calculated to the bottom of the proposed roadway subgrade which includes the trolley rails and ties. It did not include any of the concrete/granite block that is below the proposed subgrade. The concrete/granite block removal is part of the bid item Removing Trolley Tracks, Item 204.9090.S.01 and any excavation needed to remove the concrete/granite blocks or any fill needed to bring it back up to subgrade was considered incidental to that bid item. The trolley track concrete/granite base should also be removed in their entirety since it is part of the bid item description. Also, according to 204.3.2.1 (2) removals within the roadbed should be done to a depth of 2 feet below subgrade. | Scott Lawry | 3 | 2018-01-24 09:45 | 2018-01-25 06:36
20180213 | 20180213009 | 9 | Special provision #82 & #83 for colored concrete paving | The color to be used is to be determined. Since the price of the color can vary a lot, please specify what color you want. Also, WDOT has been using a bid item of Color Concrete paid by the CY. Can you add addenda please. | The colored sidewalk is Federal color #23522, the colored concrete crosswalk is Federal Color #30215. Special Provision 81 is for colored stamped sidewalk and similar to special provisions 82 and 83 so we will add an addenda for these items to replace Special Provisions 81, 82 & 83. It will be submitted sometime next week. | Scott Lawry | 4 | 2018-01-24 11:15 | 2018-01-26 13:09
20180213 | 20180213009 | 9 | Design Schedule | Can we get a copy of the design schedule? | The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213009/ | Scott Lawry | 5 | 2018-01-26 16:06 | 2018-01-29 14:04
20180213 | 20180213009 | 9 | Pavement Removal | Please confirm the area for the rail road tracks will be paid as pavement removal as indicated by the quantities in the Miscellanious Quantity Sheets. | Any concrete pavement up to and between the trolley tracks is included as part of pavement removal. Anything else associated with the track (rails, ties, concrete/granite base, etc.) is paid for under the removing Trolley Tracks bid item. | Scott Lawry | 6 | 2018-01-30 10:23 | 2018-01-30 13:57
20180213 | 20180213009 | 9 | Colored & stamped colored concrete | Per Add. #1, the CY coloring concrete custom & stamping colored were added. Will the measurement for the area (Labor, equipment, misc. materials) be paid for under Item #602.0405 for the colored & stamped colored walk & item #415.0080 for the 8" colored concrete crosswalks? | The colored areas will also be measured under items 415.0080 and 602.0405 for costs not included in the 405 bid items. | Scott Lawry | 7 | 2018-02-07 08:51 | 2018-02-07 11:41
20180213 | 20180213009 | 9 | Plant Bedding Areas | How is the payment for excavation of the plant bedding areas going to be handled? It appears that the plant areas have 18" of plant bedding material along with 3" of mulch, so a total section of 21". We did not find that there were cross sections or anything in the earthwork tables quantifying the excavation needed in these areas. | Payment for excavating the plant bed areas is included as part of SPV.0035.01. | Scott Lawry | 8 | 2018-02-08 11:25 | 2018-02-08 16:49
20180213 | 20180213009 | 9 | Special Provision #80 - Temporary Traffic Signal Modifications, Main Street & Goold Street | Where can the plan for the requirements of the Temporary Traffic Signal Modifications at Main Street & Goold Street be found? Please provide if this is not in the current plan set. | This is what is required for the signal at the intersection of Goold Street and Main Street. For the northwest signal: 1. Replace existing pole and pedestal base with 15-Ft traffic signal standard and pedestal base on existing concrete base. 2. Reuse southbound 3 section head, pedestrian push buttons and pedestrian head. 3. Replace northbound 3-12 inch signal head with 5-12 inch vertical signal head with backplate. 4. Rewire all heads from signal base to signal heads using traffic signal cable 14AWG. 5. Relocate existing signs to new signal pole For the northeast signal: 1. Replace northbound 3-12 inch signal head with 5-12 inch horizontal signal head with backplate on existing trombone arm. 2. Rewire 5 section head from signal base to signal head using traffic signal cable14 AWG. For intersection: 1. Construct traffic signal work while traffic signal is operational. Only one primary signal indication may be removed at one time. 2. City of Racine forces will complete final cabling in traffic signal cabinet and make necessary timing revisions to controller. 3. The City of Racine will be responsible for operating and maintaining the traffic signal once the temporary traffic signal modifications have been acceptably completed. 4. Once the STH 32 detour is no longer in place, the contractor shall return the traffic signal to its initial operations condition. | Scott Lawry | 9 | 2018-02-09 07:04 | 2018-02-09 17:30
20180213 | 20180213010 | 10 | Colored Concrete | I do not see any special provision clarification for the colored or stamped colored concrete item as typical. with that said, can you clarify the % loading of color for this item? Also, will the color concrete (16 CY) be inclusive of the stamped and colored volume? Thus the stamped concrete is labor only or is the stamped concrete (4 CY) for color additive and stamping labor? Lastly, will a mock up (test sample) be required for either the colored concrete or the stamped colored concrete or both? | A1--A special provision was not needed because the color is not being modified from what is in the Standard Spec Book. A2--No â€“ The 16 cy of Colored Concrete are for ramp areas (where stamping is not allowed) and the 4cy of stamped & colored concrete is for the terrace areas. They are not inclusive - 20 cy of concrete will be used. A3--Payment for the Stamping Colored Concrete is full compensation for coloring and stamping. A4--Payment for the Coloring Concrete bid item includes providing sample panels and test slabs (p.143). These are not required for Stamping Colored Concrete Please read the standard specification for the item at: http://wisconsindot.gov/rdwy/stndspec/ss-04-05.pdf#ss405 | Scott Lawry | 1 | 2018-01-30 08:46 | 2018-02-01 14:28
20180213 | 20180213012 | 12 | Aesthetic Provisions for MSE Wall | Hello - the Mechanically Stabilized Earth Wall general notes state "see special provisions for aesthetic treatment to wall." The special provisions do not outline an aesthetic guideline for the wall panels. Can The Department please provide specific examples/guidelines of the desired architectural finish for the MSE walls? Thank you. | An addendum will be developed to address this issue. We are not requiring any aesthetic treatment to the MSE Walls outside of the WisDOT Standard. | Scott Lawry | 1 | 2018-01-23 09:34 | 2018-02-01 15:52
20180213 | 20180213012 | 12 | MSE Walls | â€¢ Maximum factored bearing resistance of 4500 psf is not attainable with walls 31â€™-32â€™ tall. Weâ€™re getting over 7 ksf factored bearing pressures. â€¢ General notes for each wall say TOP OF CONCRETE LEVELING PAD TO BE AT SAME ELEVATION AS TOP OF PROPOSED ABUTMENT FOOTING. The elevations given do not agree with the elevations shown on the wall elevations. | We have consulted with our Geotechnical consultant for the project regarding the question/concern raised by the prospective bidder and we are comfortable with the MSE walls as designed and like to proceed with our proposed design. | Scott Lawry | 2 | 2018-02-05 17:57 | 2018-02-12 16:50
20180213 | 20180213013 | 13 | Prevailing Wage Rates | Are Prevailing Wage Rates applicable for this project? | Please review the proposal for the project that is located at: ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2018/02February_13/20180213013proposal.pdf There are no Davis Bacon Prevailing Wage Rates included in the proposal. | Scott Lawry | 1 | 2018-02-07 13:56 | 2018-02-07 14:06
20180213 | 20180213014 | 14 | Special Provisions - Traffic | It states in the Traffic Section in the Special Provisions that the contractor cannot close Hoitink Road and Risseeuw Road at the same time. Would it be possible for the contractor to close the second bridge once the first bridge has been completed while the roadway items are being completed? If this were allowed both roads would be closed at the same time for roughly 2-3 weeks. There would be a significant savings to the department in the mobilization costs if this were allowed. | An addendum will be developed indicating that the Hoitink and Risseeuw Road Bridges will not be closed at the same time for more than a period of 3 weeks. | Scott Lawry | 1 | 2018-01-31 15:34 | 2018-02-01 15:49
20180213 | 20180213015 | 15 | Underwater concrete pouring | Per standard specification 502.3.5.3 (1) Deposit concrete underwater "only" if the engineer orders, the plans show, or the contract specifies. Section 13.1.3 of the bridge manual states that placing concrete underwater is acceptable for the construction of pile-encased piers. Will underwater concrete pouring be allowed on this project? I cannot find reference to it anywhere in the plans or specifications. If underwater depositing of concrete is allowed, is the cofferdam item for containment of â€œsolid wasteâ€ excavated material required for pier construction? Will complete dewatering of the cofferdam be required? | The cofferdam should remain in the plans to contain the riverbed excavation considered by the DNR to be solid waste for disposal. Because the cofferdam was included, the department assumed dewatering and therefore underwater pouring of the concrete would not have been necessary. That said, we do not care if they completely dewater the cofferdam. If they believe there is a cost savings and want to pour the concrete underwater, that is acceptable as long as they follow the specifications for underwater pouring in Section 13.3.3 of the bridge manual. | Scott Lawry | 1 | 2018-01-23 09:26 | 2018-01-25 06:34
20180213 | 20180213015 | 15 | Estimated Pile Length - Bid quantity don't match | Sheet 50 of the plans state that the pile lengths for the pier are estimated at 32 lf. Sheet 51 of the plans show in the Estimate of Quantities 192 LF of piling at the pier, which if they are 32 lf long that would be 6 pile total at the pier 6 x 32 = 192 LF Sheet 58 shows 9 pile in the pier & the note in the end view detail estimates the length at 27 lf . 9 x 27 = 243 LF. Which is the correct estimated quantity? | This will be addressed via addenda. | Scott Lawry | 2 | 2018-01-24 16:31 | 2018-01-26 13:07
20180213 | 20180213015 | 15 | Solid Waste River Sediment | Some licensed solid waste haulers have asked the following questions : Who is considered the â€œgeneratorâ€ of the solid waste? It will need to be documented on the paper work required for disposal. Has this sediment been tested to verify that it does not fall into the solid waste â€“ contaminated waste category? Solid waste is a broad category which also includes contaminated waste. Approved landfills could vary depending on classification. Can the excavated river sediment be placed on site, contained by silt fence and erosion bales, until it dries out enough to be trucked away safely and efficiently? | This will be addressed via addenda | Scott Lawry | 3 | 2018-02-01 11:21 | 2018-02-07 13:45
20180213 | 20180213020 | 20 | Storm Sewer | In the misc quantity sheets 424-427 for Storm Sewer there are 162 Joint Ties listed. Per the storm sewer schedule there are 6 joint ties for each reinforced concrete endwall on those pages. Where or how are the joint tie quantities to be applied to the remaining storm sewer where there are no endwalls? There is no note or label applied to the storm sewer plan and profile pages. | Joint ties are only required at the apron end-wall locations. There are six end-wall locations that require the last three joints tied. This equates to 36 total joint ties required in the storm water system. The other joint ties were inadvertently included in the joint tie miscellaneous column. | Scott Lawry | 1 | 2018-01-15 09:35 | 2018-01-16 13:19
20180213 | 20180213020 | 20 | QMP Base Aggregate Lab Location | In the special provisions it states that you guys are requiring a mobile lab within 30 miles of the project. Is this for all of the samples to be ran or just the base or just the compaction samples from the compaction spec that is on the job. | The department has reviewed the provisions and will be issuing an addendum to remove the 30 mile mobile lab requirement; as well as the base compaction QMP provision. | Scott Lawry | 2 | 2018-01-26 13:22 | 2018-01-26 13:23
20180213 | 20180213020 | 20 | Line Item # 550 SPV.0165 Special 01 Stained Concrete Terrace | After reading the description of this item in the specials it sounds like you are specifying a colored concrete to be uniformly mixed in at the batch plant, not a stain or a shake on color. The item title is confusing could you clarify this? Can a contractor use materials from WISDOTs approved list to obtain the specified color Desert Tan matching the terrace in the Town of Woodruff? I consider "Staining" a process that is performed after the concrete is poured and struck off. | The concrete is to be colored in such a way that the color is uniform throughout. Products applied to the surface (i.e. a painted or shaken on stain) after placement will not be allowed. This is specifically mentioned in sections B.3 and C of the SPV.0165.01 article. These sections require that the coloring be integral to the concrete and expressly prohibits applying it separately to the top surface. | Scott Lawry | 3 | 2018-02-06 13:45 | 2018-02-08 08:13
20180213 | 20180213020 | 20 | SPV.0165.01 Stained Concrete Terrace 6â€ | The standard specification does not include a loading rate of desert tan color. Are we supposed to assume the standard 6% that is used on DOT red? | The SPV requires that the color match the desert tan provided match the existing desert tan in Woodruff (installed on the previous USH 51 project). The loading rate to achieve that will be dependent on the concrete mix design and colorant products used. The 6% identified in Standard Specification 405 for WisDOT red is a minimum loading rate for that specific pigment. That 6% minimum value should not be assumed to be standard for other colors, pigments, or colorants. | Scott Lawry | 4 | 2018-02-08 08:16 | 2018-02-08 08:17
20180213 | 20180213020 | 20 | 204.9105.S Removing Signs 01-14 | With the added sign removals are the concrete bases included in the removal of the sign or will they be paid as a 204.0195 Removing concrete Bases? Are the signs to be the property of the contractor, state, and or the land owner? Are they to be reinstalled? Salvaged? | As per the note on the miscellaneous quantity sheets included with the addendum, removal of the concrete bases will be incidental to the removal of the sign. Signs will become the property of the contractor. | Scott Lawry | 5 | 2018-02-09 10:48 | 2018-02-09 11:34
20180213 | 20180213020 | 20 | Removing Sings 01-14 | Who will be responsible for removing, Cutting, Disconnecting Electricity / Wiring? | The contractor will be responsible for removing or abandoning the existing electrical. The electrical facilities may be abandoned in accordance with all applicable codes. | Scott Lawry | 6 | 2018-02-09 11:02 | 2018-02-09 12:21
20180213 | 20180213021 | 21 | Project Schedule | Does WisDOT have a preliminary schedule they used to calculate working days? | The draft schedule can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213021/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 1 | 2018-01-10 08:58 | 2018-01-11 16:21
20180213 | 20180213021 | 21 | Thrie Beam Backing Plate | When will this be required? | The Thrie Beam Backing Plate is required at the posts located in the center of a rail. (The posts where there is no rail splice) | Scott Lawry | 2 | 2018-01-10 10:29 | 2018-01-11 16:25
20180213 | 20180213021 | 21 | Borings for Cable Anchors | Can WisDOT provide a link to the boring information? | The soil borings can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213021/ Boring locations are labeled on the 1510-00-71 plan sheets | Scott Lawry | 3 | 2018-01-11 15:08 | 2018-01-12 12:03
20180213 | 20180213021 | 21 | Project 1510-00-71 Construction Staking Slope Stakes | Project 1510-00-71 has 16,447 LF of slope staking. There is only about 1,100 LF of cross sections in the plan. Are there additional cross sections that will be added to the plan or is the staking quantity incorrect? | This will be corrected via addenda. | Scott Lawry | 4 | 2018-02-07 11:38 | 2018-02-07 13:44
20180213 | 20180213022 | 22 | In Stream Disturbance | According to the special provisions there can be no instream disturbance from March 1 through June 15. Can the riprap around the piers be placed prior to June 15 in order to not overly compress the construction schedule? | Riprap can be placed as early as May 15th as long as no bed excavation will occur, clean rock is used, and the placement is conducted in a careful and targeted manner that prevents bed disturbance and sediment suspension. An addendum will be issued to address this in the contract. | Scott Lawry | 1 | 2018-02-09 09:45 | 2018-02-09 09:45
20180213 | 20180213023 | 23 | Fog Seal, SPV .0180.003 | Spec. states that the CSS-1H and CQS-1H shall be produced by using polymer modified based asphalt only. This statement contradicts itself because CSS-1H and CQS-1H are not polymer modified by designation. I believe the intent of the agency is to use CSS-1H and CQS-1H which do not have a polymer base. | An addendum will be developed to change the specifications. | Scott Lawry | 1 | 2018-01-19 16:13 | 2018-01-23 10:04
20180213 | 20180213024 | 24 | Fog Seal, SPV.0180.003 | Spec. states that the CSS-1H and CQS-1H shall be produced by using polymer modified based asphalt only. This statement contradicts itself because CSS-1H and CQS-1H are not polymer modified by designation. I believe the intent of the agency is to use CSS-1H and CQS-1H which do not have a polymer base. | An addendum will be developed to make the necessary changes. | Scott Lawry | 1 | 2018-01-19 16:14 | 2018-01-23 10:05
20180213 | 20180213025 | 25 | Concrete Milling- CTH S | Existing Pavement on CTH S is shown to be 9" doweled concrete. Are there any records of how far the dowel bars are from the surface of the pavement? The USH 53 Ramps/CTH S intersection areas were previously milled and overlaid. What depth of cut was the concrete milling for that work? Thanks, | A1--As-built information is limited and the exact depth of dowel bars is unknown. We anticipate that the pavement was constructed to WisDOT standards at the time A2--As-built information is unavailable. Based on historic maintenance type projects, it is likely 2-inches of concrete was milled and overlaid. | Scott Lawry | 1 | 2018-01-30 12:38 | 2018-02-01 14:15
20180213 | 20180213025 | 25 | 5HT | Some ramp shoulders are shown to be 3 1/2" 5HT. Since there is a 4HT bid item on the project, which would be cheaper than the 5HT, would the department consider using 4HT in place of the 5HT on the 2" lower layer of the ramp shoulders? This would leave a 1 1/2" upper layer of 5HT. The other option is to eliminate the 5HT shoulder mix and place the shoulders in two 1 3/4" lifts of 4HT. | The plans were prepared per the WisDOT determined pavement design. Please bid the project as shown. | Scott Lawry | 2 | 2018-01-30 15:44 | 2018-02-01 14:18
20180213 | 20180213025 | 25 | USH 53 / CTH M Ramps | The CTH M ramps need to remain open to traffic. Therefore the milling and paving needs to be completed 1/2 lane at a time. The typical section shows the shoulder has a different slope than mainline. This is not possible to construct while maintaining traffic on the ramps. Typical reconstruction such as this the ramps are paved the same slope. | The proposed staging can be constructed as shown. Please bid the project as shown in the plans. | Scott Lawry | 3 | 2018-01-30 15:46 | 2018-02-01 14:30
20180213 | 20180213025 | 25 | Asphalitc Surface Patching | Special provisions require the Asphaltic Surface Patching item to be completed prior to milling. Is this only for the milling that will be completed on the existing concrete pavement? | The Asphaltic Surface Patching item is intended to be used for two primary uses. The patching related to the Prepare Foundation for Asphaltic Paving supplemental special provision should be placed after the milling. The patching of asphaltic shoulders around any concrete pavement repairs/replacements or the concrete surface drain work on CTH M should be placed prior to completing the mill and overlay of those areas. | Scott Lawry | 4 | 2018-01-30 15:48 | 2018-02-01 14:20
20180213 | 20180213025 | 25 | Covering Signs Type I | Why is the quantity for Covering signs Type I so high? There are no restrictions on these ramps so we were assuming that the ramps would only be closed once while all work is completed so the signs would be covered and then uncovered, Thanks | Per the special provisions, â€œRamp closures at 50th Avenue, CTH X, and CTH S shall only occur when construction operations are being performed. Perform work in a manner to minimize the number and length of ramp closures.â€ The Contractorâ€™s means and methods will dictate if multiple cycles will be necessary . If no work is being performed, the ramps shall be re-opened to traffic and signs uncovered. | Scott Lawry | 5 | 2018-02-02 08:34 | 2018-02-05 11:11
20180213 | 20180213026 | 26 | 4SMA 58-34H (aggregate size) | Earlier versions of the SMA specification allowed the contractor to choose between 12.5mm (4) and 9.5mm (5). The current specification does not allow the contractor to make a choice. We completed a project for WI DOT in 2016 using a 5SMA and the SMA QMP production testing worked out very well. The contractor QC testing was considerably more consistent than the 12.5 mm SMA mixes and the department verification testing consistently returned results similar to the QC testing. Considering how well the 5SMA tested in 2016 and how much variability we have seen in 4SMA testing over the years, would the department consider either switching the bid item to 5SMA or allowing the contractor to choose between 4SMA and 5SMA? | This will be addressed via addenda. | Scott Lawry | 1 | 2018-01-18 15:10 | 2018-01-24 08:36
20180213 | 20180213026 | 26 | 4SMA 58-34H (asphalt binder) | Current requirement is for 58-34H asphalt binder, we would like to suggest PG 58-34V. This will reduce the risk of drain down of the asphalt cement during construction and result in better in service performance. Prior to 2017, all SMA bid in the Northwest Region had the option of using either PG 70-28 or PG 64-34P these grades were specified under AASHTO M320. The current binder grading system is AASHTO M332 and the equivalent grades are PG 58-28V and PG 58-34V. The department and the contractor have been satisfied with performance of the asphalt binder in the SMA bid prior to 2017. | This will be addressed via addenda. | Scott Lawry | 2 | 2018-01-18 15:24 | 2018-01-24 08:37
20180213 | 20180213026 | 26 | Asphaltic Surface | The special provisions call for Asphaltic Surface to a 4MT 58-28S with the mix being used for intersections and cross overs. There is a 4MT 58-34S bid item on the project. I understand the benefits of Asphaltic Surface bid item for the department and contractor. However to eliminate a potential conflict at the asphalt plant storing asphalt cement, would it be possible to change the Asphaltic Surface bid item from 4MT 58-28S to 4MT 58-34S? | This will be revised with an addendum. | Scott Lawry | 3 | 2018-01-23 13:47 | 2018-01-24 14:10
20180213 | 20180213026 | 26 | Asphaltic Surface Butt Joints | The typical section shows a 50 foot transition to the butt joint or engineers approval. The 2016 Southbound project had 200 foot transitions to the butt joint. 200 foot provides a better opportunity to achieve a smooth transition from the new asphalt overlay to the existing pavement. Is the plan quantity large enough to cover the 200' transition? | The design team will adjust the butt joint quantity by addendum to provide for a 200-foot butt joint at the north project terminal and 50 foot butt joints at the bridge approaches and the South project terminal. | Scott Lawry | 4 | 2018-01-30 08:58 | 2018-02-01 14:04
20180213 | 20180213027 | 27 | Fog Seal, SPV.0180.02 | The fog seal oil typically has been CSS-1H and/or CQS-1H. Will the agency allow this typical fog oil be applied on this job? If so, the polymer modifier language would need to be removed. | We will allow the substitution of CSS-1H or CQS-1H for the fog seal oils specified in the contract. The polymer modification language is necessary in the specification if the original specified oils of CRS-2P and HFRS-2P are used in the work. | Scott Lawry | 1 | 2018-01-19 16:17 | 2018-01-23 16:52
20180213 | 20180213028 | 28 | Special Provisions | Fish Spawning provision states that there is no in-stream disturbance from April 15 to Sept 15. Please verify this time period of non disturbance. | The dates within the special provision are incorrect and will be corrected via addendum to show that the work must be within the window of April 15 and September 15. | Scott Lawry | 1 | 2018-01-11 09:20 | 2018-01-12 12:34
20180213 | 20180213028 | 28 | Prosecution and Progress | The proposal has a contract completion time of 55 working days with no water work allowed from April 15 to September 15th. There doesn't appear to be 55 working days available prior to April 15th or after September 15. is it the intent to begin in early spring, suspend time over the summer and resume in the fall? | The dates within the special provision are incorrect and will be corrected via addendum to show that the work must be within the window of April 15 and September 15. | Scott Lawry | 2 | 2018-01-11 16:18 | 2018-01-12 12:36
20180213 | 20180213028 | 28 | 4LT 58-34S | There is a 4LT 58-34S bid item with a quantity of 220 ton. Typical section shows a 2" lower layer of 4LT 58-28S and a 2" upper layer of 4LT 58-34S. With a small quantity of 220 ton would it make sense to switch this item to Asphaltic Surface and specify one mix type for both layers? | This will be addressed via addendum. | Scott Lawry | 3 | 2018-01-23 14:01 | 2018-01-30 12:31
20180213 | 20180213030 | 30 | Contractor Staking Structure | It appears this item was inadvertently not included in the plans and special provisions. Will the item be added? | The item will be added via addenda. | Scott Lawry | 1 | 2018-01-24 07:59 | 2018-01-24 07:59
20180213 | 20180213032 | 32 | SPV.0105.01 Survey Project 1021-03-74 | Why is this item being used instead of the individual surveying bid items. | The Department feels it would be more cost efficient to have the contractor prepare a bid for all survey work that would need to be performed to complete the project. The intent of item Survey Project is that the surveying contractor would work with the bidding contractor to determine the appropriate amount of survey required to complete the project, and prepare their bid accordingly. | Scott Lawry | 1 | 2018-01-23 12:24 | 2018-01-23 12:25
20180213 | 20180213034 | 34 | Design Schedule | Can the Design Schedule be provided? | The draft schedule can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213034/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 1 | 2018-01-12 18:59 | 2018-01-22 11:59
20180213 | 20180213034 | 34 | Concrete Barrier Temporary Precast Delivered Special | Can the Concrete Barrier Temporary Precast Delivered Special be used wall from the project? Does any of the Concrete Barrier Temporary Precast Delivered Special have to be new wall? | Revised response; item was originally to be eliminate via addendum, but is now included again: Concrete Barrier Temporary Precast Delivered Special may be new or used, provided it meets the requirements of the specifications and is approved for use by the engineer. | Scott Lawry | 2 | 2018-01-16 21:27 | 2018-01-24 07:54
20180213 | 20180213034 | 34 | CAD File Requests | Can the following CAD files be provided for this project: 1. Existing Conditions Survey Surface CAD files (Format: LandXML, .DWG or .DGN) 2. Existing Condition Survey Mapping CAD files (Format: LandXML, .DWG or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .DWG or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .DWG or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .DWG or .DGN) Thank you | The files are located at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213034/ | Scott Lawry | 3 | 2018-01-17 08:19 | 2018-01-25 07:00
20180213 | 20180213034 | 34 | Line Item 0334 Glare Screen left in place | In the special provisions on page 84 you list the manufacturers "or approved equal". What does that mean? Does not create an equal playing field. There is not an approved products list for this just what you have in the SP's. New/used? Should be made clear so everyone is bidding the same material. | Revised response; item was originally to be eliminated via addendum, but is now included The specification as written is adequate for purposes of bidding. | Scott Lawry | 4 | 2018-01-17 15:03 | 2018-01-24 07:53
20180213 | 20180213034 | 34 | Typical Section â€“ existing shoulder widths | Based on the typical sections shown on sheet 10 of the plans the existing outside shoulder widths of IH 94 are 10â€™ wide. Sheet 70 of the plans shows the proposed shoulder widths to remain 10â€™ with a temporary widening that varies from 0 â€“ 10.5â€™ wide. Sheet 70 also shows sawing concrete or asphalt along the outside of that 10â€™ wide shoulder. Based on this information why is it necessary to saw cut along a shoulder that is remaining the same width from the existing to the proposed widths? Is this saw cut actually necessary to construct the proposed section? Is the existing typical width for the outside shoulders being shown at 10â€™ wide correct? | A: The sawcut is necessary to achieve a clean edge of pavement at temporary widening locations. Ten feet is the typical width of the existing outside shoulders. | Scott Lawry | 5 | 2018-01-30 10:17 | 2018-01-31 11:33
20180213 | 20180213034 | 34 | Frozen Grade. | Will concrete repairs be allowed on Frozen grade. If there is frost in the ground will WisDOT pay to remove it or heat the ground where the repairs are to be performed? | This question will be addressed in an upcoming Addendum. | Scott Lawry | 6 | 2018-02-01 15:35 | 2018-02-01 15:52
20180213 | 20180213034 | 34 | Base Patching. | Please provide the location of the Base Patches. | Response: Base patch quantities were estimated during project design and based on similar projects, the exact locations will be determined by the construction engineer in the field. | Scott Lawry | 7 | 2018-02-03 09:45 | 2018-02-05 11:23
20180213 | 20180213034 | 34 | Base Patching. | Can we assume the Base Patching quantity is in the 1 and 3 lanes and the SHES is in the 2 lane? Are there other areas the base patching could be located? | The Typical Sections were updated in Addendum 1 with labels that show Base Patching applying to the outside shoulders. The Concrete Pavement Repair item applies to the lanes. The Base Patching SHES item is intended to apply at ramp locations. Specific locations of these items are to be determined by the construction engineer in the field. On a related note, SDD 13C9-14 Concrete Pavement Repair and Replacement will be included in Addendum that will be issued tomorrow. | Scott Lawry | 8 | 2018-02-05 14:01 | 2018-02-08 16:50
20180213 | 20180213034 | 34 | Concrete Barrier Temporary Wall | On sheet 114 of addendum No 1 there is a note for Concrete Barrier Temporary Precast Delivered and Installed but does not show up any were else. Can you clairify | The note on sheet 114 regarding Concrete Barrier Temporary Precast Delivered and Installed does not apply. The barrier was changed to drums under Addendum 1 and the note was inadvertently left on the plans. | Scott Lawry | 9 | 2018-02-06 10:07 | 2018-02-06 13:01
20180213 | 20180213034 | 34 | Waste Dirt Allowed to Stay on Site as Borrow for next project. | Will the WisDOT allow waste dirt from this contract to bel placed in one or more interchanges and left for borrow for next contract? | A: Waste dirt may be able to stay on site depending on need, location, and quality as approved by the Construction Engineer. | Scott Lawry | 10 | 2018-02-07 11:08 | 2018-02-08 08:41
20180213 | 20180213034 | 34 | Contract Award and ECIP Review | Due to the expedited nature of this contract, will there be an acceleration of contract award and also the ECIP review process? That is, compared to the standard contractual obligations of the department awarding the contract within 30 days and reviewing the ECIP within 14. | The Department will make every effort to review and process completed contract documents in an accelerated manner. Industry will be expected to do the same. | Scott Lawry | 11 | 2018-02-07 13:23 | 2018-02-09 09:51
20180213 | 20180213034 | 34 | Maintenance of Asphalt Surfaces | Under the â€œInterim Completion of Workâ€ it states that all work on this contract, except for maintenance of asphalt surfaces â€“ will be completed prior to 12:01 AM May 1st, 2018. What does the â€œmaintenance of asphalt surfacesâ€ entail? For example, does this only include asphalt that is installed during this contract or does it also include existing asphalt? Will all work associated with maintenance be directly compensated through pay items/change orders or is it considered incidental to the contract? | This spec is being modified in Addendum #2. The completion date of the contract will be modified to June 30, 2018. The contractor will maintain asphaltic items placed under this contract until that time. Maintenance is included in the items per Std Spec 465 and the special provision Hot Mix Asphalt Pavement. | Scott Lawry | 12 | 2018-02-07 13:57 | 2018-02-08 16:56
20180213 | 20180213034 | 34 | Frozen Grade in Regards to Concrete Repairs | In response to the note added by addendum that states: â€œAnticipate frozen grade/subgrade. Rework, heat, blanket, cover, compact, remove/replace such that the grade/subgrade is not frozen prior to placement of asphalt or concrete.â€ â€“ in regards to any base patching or concrete repairs, does any frozen ground below need to be removed or would heating the surface of frozen ground (that will contact the newly paved materials) be acceptable? Removing frozen subgrade below would possibly damage and undermine adjacent pavements and cause non-uniform settling of the road as it thaws. Please clarify what the departmentâ€™s intent is. | A: Subgrade should be heated such that it is workable with and in existing non-frozen subgrade below it. All methods to address frozen grade/subgrade must be approved by the Construction Engineer. | Scott Lawry | 13 | 2018-02-07 18:28 | 2018-02-08 08:33
20180213 | 20180213034 | 34 | Temporary Barrier Wall | Under bid item 603.8000 Concrete Barrier Wall Precast Delivered; will this wall need to be removed prior to the interim completion of May 1st? if not will it remain to the final completion of December 1st? | Any temporary barrier wall installed under the contract and not identified as Concrete Barrier Temporary Precast Delivered Special is intended to be removed from the project prior to the contract completion date. | Scott Lawry | 14 | 2018-02-07 20:16 | 2018-02-08 10:50
20180213 | 20180213034 | 34 | Location of Concrete Batch Plant | Will the WisDOT allow a Concrete Batch Plant to be setup within the HWY 11 Interchange within the South Bound Off Ramp or any other interchange. | A: WisDOT will not allow a batch plant to be setup within the STH 11 Interchange as most infields are environmentally sensitive. WisDOT will however assist the contractor to find suitable possible locations on state-owned ROW. WisDOT also expects the Contractor from seeking out or negotiating with private entities for use/lease of private lands for said purpose. | Scott Lawry | 15 | 2018-02-08 10:41 | 2018-02-12 16:47
20180213 | 20180213034 | 34 | Lane Rental Assesment question | Will the contractor be allowed to reduce SB Lanes at night( during the nighttime closure hours) down to ONE Lane without Lane Rental Assessment Fees being enforced? | After further review, the response has been modified. The contractor will be allowed to reduce lanes at night during the nighttime hours specified in Prosecution and Progress, down to one open lane per direction, without Lane Rental Assessment Fees being assessed. If the closure extends beyond the nighttime hours specified, Lane Rental Assessment Fees will be assessed. | Scott Lawry | 16 | 2018-02-08 11:49 | 2018-02-08 17:05
20180213 | 20180213034 | 34 | Maintaining Concrete Barrier Temporary Precast | Are we maintaining these barriers until 5-1-18 or the contract completion date of December 1, 2018 | This is being clarified, and the completion date is being modified, in addendum #2 later today 2-9-18 | Scott Lawry | 17 | 2018-02-08 11:51 | 2018-02-09 09:37
20180213 | 20180213034 | 34 | slotted vane drains | Under the Materials description it talks about 15" PVC with the Neenah Casting for Permanent drains and 15" Steel Spiral pipe for Temporary locations. Are all the locations considered temporary? Is there some sort of list to tell which ones are which or could there be two separate bid items? | All locations can be considered temporary. | Scott Lawry | 20 | 2018-02-08 11:56 | 2018-02-09 09:40
20180213 | 20180213034 | 34 | storm sewer | At least one of the storm sewer plan sheets tells us to refer to the traffic control plans to find the temporary storm sewer items. I did that and can still not find some of the temporary storm sewer pipe footages. Specifically the elliptical pipes. | Response: Storm sewer revisions will be forthcoming in Addendum 2, which contains revised storm sewer plans and miscellaneous quantities charts | Scott Lawry | 21 | 2018-02-08 12:00 | 2018-02-09 09:41
20180213 | 20180213034 | 34 | Plan Detail | Plan Sheet 11 of addendum 1, Lower right hand corner. It would appear there is a dark line on top of Lane 1, does that mean the this will be overlaid with asphalt? | The solid line shown at the surface of southbound Lane 3 (outside lane) in the typical section on sheet 11 of Addendum 1 should be a dashed line representing existing surface. There is no proposed overlay on this lane. | Scott Lawry | 22 | 2018-02-08 12:28 | 2018-02-09 09:44
20180213 | 20180213034 | 34 | Profile Milling | What final surface will be acceptable to the engineer? Will a standard spec'd milling drum be sufficient to achieve what the DOT is looking for? It does not call for a fine tooth drum but it also does not state what tooth spacing or finished surface will be acceptable. | A: A finished surface similar to that of a diamond-ground finished surface is the desirable final surface as directed by the Construction Engineer. | Scott Lawry | 23 | 2018-02-08 14:05 | 2018-02-12 12:20
20180213 | 20180213034 | 34 | Soil Report | Can the soil report be provided? | The files are located at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180213034/ Additional files have been stored at the above location. | Scott Lawry | 24 | 2018-02-09 14:46 | 2018-02-10 08:00
20180213 | 20180213034 | 34 | Concrete Pavement Repair Item | Are we to assume that the Concrete Pavement Repair item 416.1710 is for repairs of concrete shoulders in the median? | Response: See question #8 as well as addendum #1 and #2. | Scott Lawry | 25 | 2018-02-09 15:42 | 2018-02-10 07:27
20180213 | 20180213034 | 34 | Emergency Pull Outs. | Is the Department going to provide some sort of dimensions or thicknesses for the Emergency Pull Outs? There are no dimensions in the addendum. Also, the item is bid as Each. Can it be bid by the ton of Crushed Aggregate Base Course for the fill and the excavation volume added to the existing quantities? | Response: Emergency pull outs shall be bid under the item Temporary Emergency Pullouts, Item 205.3000.S (EACH). An average quantity is anticipated to be approximately 500 tons of aggregate. | Scott Lawry | 26 | 2018-02-11 14:19 | 2018-02-12 15:52
20180213 | 20180213034 | 34 | storm sewer | Addendum 2 shows 3 runs of 42"RCP Storm Sewer that goes from a new structure to existing, I can not tell are these North- South Runs or are we trying to go East- West across either NB or SB. Can not tell from the plan/addendums 1 & 2 what is the intent. | Assuming this is related to the pipes near Sta 956+25, the 42-inch pipes are crossing IH 94, so they are east-west pipes. There is a longitudinal (north-south) run of pipe to add inlets along SB 94 just south of this crossing and the pipe ties into WZ187. | Scott Lawry | 27 | 2018-02-12 07:46 | 2018-02-12 10:51
20180213 | 20180213034 | 34 | Barrier Wall Removal | Is the pavement sawing that is parallel to the barrier wall removal being paid for under the sawing pavement items? | The Removing Concrete Barrier item includes all required sawing per the special provision â€œRemoving Concrete Barrierâ€. | Scott Lawry | 28 | 2018-02-12 10:06 | 2018-02-12 16:48
20180213 | 20180213034 | 34 | STAGING | After completing the work required to complete Stage 1 A , STH 142 to STH 20 per addendum 2, will the contractor be allowed to start 1 B in this same section while also working on Stage 1 A North ( Sth 20 to CTH G )? | This would be allowed as approved by the engineer and as long as a traffic control plan change is prepared and approved as noted under "C Freeway Work Restrictions" in the article Prosecution and Progress. | Scott Lawry | 29 | 2018-02-12 10:14 | 2018-02-12 15:36
20180213 | 20180213034 | 34 | Overhead Sign Support | Can the installation timeframe for the Overhead Sign Support, that was added on Friday in Addendum 2, extend to the final completion date? | A: The contractor shall install the overhead sign support S-30-262 as soon as possible and with approval from the Construction Engineer, no later than the final completion date of 6/30/18. Contractor shall expedite ordering of the support materials and provide Construction Engineer with documentation indicating such. | Scott Lawry | 30 | 2018-02-12 11:35 | 2018-02-12 15:54
20180213 | 20180213034 | 34 | Quantity of Concrete Pavement Repair on the "mainline lanes" | Can we please be provided a quantity of Concrete Pavement Repairs on the "mainline Lanes"? This work is very different from the Concrete Pavement Repairs that will be performed on the median shoulders and we need a quantity to bid the two very different types of work in this mixed item. When the note was added on Sheet 226 of Addendum 2 no quantity was provided for this revision. | A: WisDOT estimated approx.. 5,100 SY in the lanes, and 9,700 SY in the median shoulder. | Scott Lawry | 31 | 2018-02-12 12:55 | 2018-02-12 16:46
20180213 | 20180213034 | 34 | Quantity of Concrete Pavement Repair on the "mainline lanes" | Can we please be provided a quantity of Concrete Pavement Repairs on the "mainline Lanes"? This work is very different from the Concrete Pavement Repairs that will be performed on the median shoulders and we need a quantity to bid the two very different types of work in this mixed item. When the note was added on Sheet 226 of Addendum 2 no quantity was provided for this revision. | A: WisDOT estimated approx.. 5,100 SY in the lanes, and 9,700 SY in the median shoulder. | Scott Lawry | 32 | 2018-02-12 12:55 | 2018-02-12 16:46
20180213 | 20180213034 | 34 | Concrete Barrier Wall | Would the Department Accept wall that does not meet Wisconsin standards as per SDD 14B7 | A: No. All Concrete Barrier Temporary Precast must meet the requirements and specifications as indicated in S.D.D. 14B7. | Scott Lawry | 33 | 2018-02-12 13:32 | 2018-02-12 18:13