## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190611 | 20190611001 | 1 | Full depth deck repairs-Reinforcing Steel B-12-27 | In the areas of the full depth repairs on B-12-27, some of this rebar will be very difficult to install as full length bars, mainly in the areas where the existing longitudinal reinforcement is not getting replaced. Will it be acceptable to cut and lap the rebar for installation purposes? | In areas where the existing longitudinal reinforcement is not getting replaced and the transverse steel is, installation of the new transverse steel will be permitted with laps (lap lengths to match those shown on the plans) provided a reasonable need to lap the reinforcement is demonstrated by the contractor (i.e. installation of full length bars without laps is not feasible/possible due interference with the existing structure to remain), subject to the approval of the engineer. However, the number of laps shall be limited to as few as possible, and used only when necessary, and shall be subject to the approval of the engineer. | Mike Coleman | 1 | 2019-05-20 14:12 | 2019-05-22 07:09
20190611 | 20190611001 | 1 | SPV #27 - Haunch Removal | SPV #27 - Haunch Removal indicates that the painting of the Top Flanges after concrete removal is defined in the SPV for Structure Spot Cleaning and Painting. There is no special provision for painting. SPV #27 Section C, paragraph 1 indicates that Concrete Haunch Removal is required over the entire length and width of the structure. This contradicts what is shown on Sheet 1 of 15 of the structure plan which indicates only Span 1 thru 4 are to have this work done. | Section C, Paragraph 3 can be ignored. Since there is no special provision for painting because the Structure Spot Cleaning and Painting item was removed, there will be no painting involved with the Haunch Removal. The only painting is that of the bearings at the abutments and piers 4 and 5, but that painting is included in the â€œCleaning and Painting Bearingsâ€ item. Section C, Paragraph 1 is incorrect. The correct limits are Span 1 thru 4 as shown on the structure plan. An upcoming addendum will correct this. | Mike Coleman | 2 | 2019-05-21 13:09 | 2019-05-28 07:09
20190611 | 20190611001 | 1 | Gland Replacement, Span #7 Modular Joint | How many of the glands in the modular joint in span #7 need to be replaced? | Only 1 of the glands in span 7 needs replacing. This is noted on the plan view. | Mike Coleman | 3 | 2019-05-28 15:07 | 2019-05-29 09:36
20190611 | 20190611001 | 1 | Railroad Flagging Costs | SPV #8 - Railroad Insurance & Coordination appears to be missing the follow: - Section B. Railroad Flagging - Section C. Flagging by Railroad - Railroad Does Not Pay Flagging Costs. Are we to assume that the costs of flagging will be 100% paid by WDOT? | For this project, the special provisions are correct. The contractor is responsible for the cost of the flagging per standard spec 107.17 Standard spec 107.17.1 (4) states... "Comply with the railroad's rules and regulations regarding operations on railroad right-of-way. IF the railroad's chief engineering officer requires, arrange with the railroad to obtain the services of qualified railroad employees to protect railroad traffic through the work. Bear the cost of these services and pay the railroad. Notify the railroad's chief engineering officer in writing at least 5 business days before starting work near a track. Provide the specific time planned to start the operations." | Mike Coleman | 4 | 2019-05-30 15:20 | 2019-06-04 06:41
20190611 | 20190611001 | 1 | Similiar Projects | It appears the polymer overlay bridge work on this project was also included on call #06 in January. Which project will this work be completed under? | Proposal #06 from the January 15, 2019 letting was rejected. | Mike Coleman | 5 | 2019-06-03 09:11 | 2019-06-03 10:10
20190611 | 20190611001 | 1 | Follow up to Question #3 Gland Replacement | Just to clarify, as there seems to still be some confusion between the material suppliers. The modular joint at hinge #1 Span 7 is a "three" (3) gland joint. The bid item "Strip Seal Gland Replacement" 1 Lump Sum is for replacing "one" (1) of the glands (approx 41 feet) in the 3 gland joint in span 7, along with replacing a single gland in the East Abutment joint (approx 41 feet) correct? | Yes, this is correct. | Mike Coleman | 6 | 2019-06-06 09:42 | 2019-06-06 10:51
20190611 | 20190611001 | 1 | Holiday Work Restrictions | Does the holiday work restrictions on page 5 of 29 in the proposal apply to the traffic signal/temporary concrete barrier stages? Can the barrier and signals remain up over the holiday as long as no work is occurring over the holiday period? | Yes, the barrier and signals will remain in place over the holiday, but no work will be occurring. | Jill Fehrman | 7 | 2019-06-07 14:20 | 2019-06-10 07:43
20190611 | 20190611001 | 1 | RE Railroad Flagging Cost & Availabilty? | Question #4 states that the railroad flagging is the responsibility of the contractor. We have asked the question to the DM&E (CN) contact listed special provisions and have not receieved any response regard rates & availability. Can the department provide a daily rate that the contractor can expect to pay for railroad flagging? |  |  | 8 | 2019-06-10 12:31
20190611 | 20190611003 | 3 | Schedule of Items | There are no schedule of items showing in the proposal. | An addendum will be issued to add the schedule of items. | Mike Coleman | 1 | 2019-05-20 10:56 | 2019-05-20 10:56
20190611 | 20190611003 | 3 | Soil Borings | Can we get the soil borings for the high mast tower locations? | The soil borings for the high mast tower locations can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190611003/ Also, here is the numbering system of the old HML vs. the new: â€¢ HML-40-34 replaced by HML-40-123 â€¢ HML-40- 35 replaced by HML-40-124 â€¢ HML-40-36 replaced by HML-40-125 â€¢ HML-40-37 replaced by HML-40-126 â€¢ HML-40-38 replaced by HML-40-127 â€¢ HML-40-39 replaced by HML-40-128 â€¢ HML-40-40 replaced by HML-40-129 | Mike Coleman | 2 | 2019-05-28 14:46 | 2019-06-03 06:49
20190611 | 20190611004 | 4 | Cold Weather Pavement Markings | Bid items 0186 and 0188 for cold weather pavement markings are missing from the Misc. Quantities in the plans. Can you please provide the breakdown of the Cold Weather markings in the Misc. Quantities? | Its anticipated that the cold weather marking will match the miscellaneous quantities for regular marking. If required, the contract time will be extended to allow permanent marking in the spring of 2020. | Mike Coleman | 1 | 2019-05-24 16:05 | 2019-05-28 12:30
20190611 | 20190611004 | 4 | Overhead Sign Supports | Both vendors are currently out 22-24 weeks delivery after approval. Approval drawings are currently at 4-5 weeks. B.O.S. review has been 4-5 weeks. This puts delivery at 30-34 weeks and does not include the time it takes for the state to award the contract. Will the State make an exception in regards to the completion date? | A time extension will be granted to allow the installation of overhead sign supports. An addendum will be issued to include this. | Mike Coleman | 2 | 2019-06-03 09:25 | 2019-06-05 10:44
20190611 | 20190611008 | 8 | EarthWork Calculations | In the Miscellaneous quantities Sheet 246 it is showing a Fill qty subtotal for 8349CY & 8438CY. However when looking at the subtotals for fill on the project in the station locations it is only tabulating to 180CY for Stage 3 & 154 CY for Stage 4. Is the calculated fill quantity 16,787 CY for these stages 3 & 4 or is the quantity 334 CY total? | The calculated fill quantity for Stages 3 & 4 should be 338 CY and not the 16,787 CY. An addendum will be issued to correct this. | Mike Coleman | 1 | 2019-05-31 11:40 | 2019-06-04 13:13