## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190813 | 20190813001 | 1 | Strapping Details | Detail A on sheet 78 of the plan set appears to show top and bottom plates welded to the new C6x13 channels but there are no details for these plates. Also the note for dimensions of the slotted holes needs to be fixed. | Typically, we donâ€™t provide dimensions for these plates as the contractor and the field engineer need to verify the exact bend angle, which dictates the length. Please use 1 1/16â€ x 2 ½â€ long slotted holes. | Fred Schunke | 1 | 2019-07-17 08:13 | 2019-07-18 10:08
20190813 | 20190813002 | 2 | Fence post removal & Concrete Surface Repair | Per details on Structure sheet 11 of 14, concrete surface repair is to be completed at each fence post on the bridge. There are a total of 50 posts, 25 on each side, and a number of these will be over traffic lanes. I don't see any provisions for handling traffic on the Beltline while these repairs are completed overhead. Please provide clarification on how the removals are to be done. | Removals are to be completed with use of lane closures on the beltline. An addendum will be submitted to clarify lane closure windows. | Mike Coleman | 1 | 2019-07-31 10:31 | 2019-08-05 08:13
20190813 | 20190813002 | 2 | Design Schedule. | Can a copy of the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813002/ | Mike Coleman | 2 | 2019-08-04 06:17 | 2019-08-05 09:13
20190813 | 20190813003 | 3 | Pile Point vs End Plates | On pages 514 & 540 of the plan set. There is a detail for End Plates for CIP Piling. There is also a bid item for "pile points". Am I correct in assuming that there will only be pile points required on this project? | Pile points will be required for B-13-794 and B-13-795. If the manufactureâ€™s specifications require an end plate, the end plate will be installed per manufactures specification. | Jill Fehrman | 1 | 2019-07-15 14:45 | 2019-07-22 12:40
20190813 | 20190813003 | 3 | Design Files | Could the Department supply the following: 1. Any design files/surfaces? 2. Any geotechnical reports 3. A design schedule? | The meta data files and soils reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813003/ The design schedule has been uploaded as well. | Mike Coleman | 2 | 2019-07-18 14:09 | 2019-07-24 12:14
20190813 | 20190813003 | 3 | CAD Files and Soils Reports | We would like to request the following CAD files to assist with our planning and quantity verification processes. 1. Existing Conditions Survey Surface CAD files (Format: LandXML, .Dwg or .DGN) 2. Existing Condition Survey Mapping CAD files (Format: LandXML, .Dwg or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .Dwg or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .Dwg or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .Dwg or .DGN) Could you also please include any relevant geotechincal/soils reports | The meta data files and soils reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813003/ The design schedule has been uploaded as well. | Mike Coleman | 3 | 2019-07-19 11:49 | 2019-07-24 12:15
20190813 | 20190813003 | 3 | Traffic Signal Work | Is the traffic signal cabinet to be furnished by the contractor, or will it be provided by the state? Also what are the specifications for the signal control cabinet & video detection. | The traffic control cabinet will be furnished and installed by WisDOT. The contractor needs to install the cabinet base which is addressed under item 654.0217 Concrete Control Cabinet Bases Type 9 Special. For the video detection, WisDOT will provide the camera for the contractor to install which is addressed under item 677.0200 Install Camera Assembly. The contractor shall also install the required cable to be provided by WisDOT under item SPV0105.07 Install State Furnished CAT5E Cable, STH 19 & Liuna Way/Tierney Crossing. | Mike Coleman | 4 | 2019-08-01 09:50 | 2019-08-05 10:38
20190813 | 20190813003 | 3 | Fill Existing Rumble Strip - Restore existing Rumble | The Fill existing rumble strip item calls for Type E-10 HMA. This mix type is no longer used. Please update. For the Restore existing rumble strip item I don't see it being possible to remove the HMA that is going to be placed and salvage the existing rumbles. They will be damaged in the removal of the HMA. Let alone how is the rumble supposed to be located once it is paved? These rumbles should be re installed or removed and replaced. Can this change be made? | The issues will be addressed in an upcoming addendum. | Mike Coleman | 5 | 2019-08-06 11:18 | 2019-08-07 11:28
20190813 | 20190813005 | 5 | Design Schedule | Please provide the design schedule. | The Contract Time of Completion files are saved here: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813005/ And linked on this page: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Jill Fehrman | 1 | 2019-07-14 13:27 | 2019-07-17 16:27
20190813 | 20190813005 | 5 | Work Schedule | Given the terrible weather we have experienced in recent years, why not allow all work possible, other than the asphalt pavement, to start this year and end November 15, 2019. This approach has been used on the I-43 Projects North of Ozaukee County and has worked well to assure timely completion. | The planned work for 2019 minimizes traffic disruptions and focuses on completion of cable guard on a high priority section of Interstate 41. | Jill Fehrman | 2 | 2019-07-14 13:31 | 2019-07-17 12:10
20190813 | 20190813005 | 5 | Work Schedule | Given the terrible weather we have experienced in recent years, why not allow all work possible, other than the asphalt pavement, to start this year and end November 15, 2019. This approach has been used on the I-43 Projects North of Ozaukee County and has worked well to assure timely completion. | The planned work for 2019 minimizes traffic disruptions and focuses on completion of cable guard on a high priority section of Interstate 41. | Jill Fehrman | 3 | 2019-07-14 13:31 | 2019-07-17 12:10
20190813 | 20190813005 | 5 | Missing timeframe for concrete base patching in contract time | After review of design schedule it appears there has been no time allocated for the concrete base patching operation. The special provisions state no base patching to occur prior to March 15, 2020. The design schedule illustrates contract completion base based on HMA milling and paving to start immediately after March 15th, 2020. Will there be contract time added to account for the concrete base patching activities? | Per the special provisions, â€œNo IH 41 mainline milling, paving, and base patching construction work shall occur prior to March 15, 2020.â€ The updated time schedule accounts for this and has been corrected due to a spreadsheet error. Please see the updated time schedules for 1100-27-70 and 1107-00-71 at the following location: The files are saved here: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813005/ And linked on this page: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Jill Fehrman | 4 | 2019-07-18 09:26 | 2019-07-22 12:53
20190813 | 20190813005 | 5 | Instream Disturbance | The special provisions state no instream disturbance of the Tributary to the East Branch Rock River from February 28th to June 15th, but the design schedule assumes Stage 3 structure work will be performed from March thru May. Please provide clarification on the allowable instream disturbances. | The stage 3 structure work will start after the winter shutdown. Turbidity barrier can be installed prior to the winter shutdown and stream restriction dates. | Mike Coleman | 6 | 2019-07-25 19:50 | 2019-07-30 06:41
20190813 | 20190813005 | 5 | Shear studs, Bid item 108 | It appears that the quantity for the Welded Shear Studs is only half of what it should be. Actual quantity should be approximately 56 based on the layout detail. | Thatâ€™s correct. The quantity should be 56. An addendum will be issued to correct the quantity. | Mike Coleman | 7 | 2019-07-29 09:45 | 2019-07-29 13:08
20190813 | 20190813005 | 5 | Design Schedule - Base Patching Rate of production. | Given the restrictions on the project, the time frames and production rate do not seem reasonable. Can WisDOT please review and provide more reasonable production and time frames? Starting this fall along with the excavation, cable guard and landscaping may be helpful. | Base patching will be allowed starting March 15, 2020. Based on recent similar projects WisDOT believes the production rates could be met. Base patching will be permitted for the duration of the project as long as the base patching operations are ahead of the paving operations. | Mike Coleman | 8 | 2019-08-04 08:01 | 2019-08-05 11:31
20190813 | 20190813005 | 5 | Base Patching Detail. | Can we be provided a detail drawing of the Base Patching showing if it is to occur to the top of the existing pavement or after milling. | Base patching will be done on existing pavement and the standard detail drawing should be used. | Mike Coleman | 9 | 2019-08-04 12:40 | 2019-08-05 11:30
20190813 | 20190813005 | 5 | Line #354 Quantity Verification | Bid Item "Monthly CPM Progress Schedule Update" (Line# 354) lists a quantity of 31 EA. Assuming 2 Ea prior to the winter shutdown and 7 ea following the winter shutdown, I am only calculating a quantity of 9 EA. Please clarify if the stated quantity of 31 EA is correct? | Quantity for Bid item â€œMonthly CPM Progress Schedule Updateâ€ is quantified by each individual project. After looking at this item, there is a quantity revision based on the latest schedule: 1100-27-70 = 6 1100-41-70 = 7 1107-00-71 = 9 Total = 22 An addendum will be issued to correct this. | Mike Coleman | 10 | 2019-08-05 13:55 | 2019-08-08 10:07
20190813 | 20190813005 | 5 | Design Schedule Time | The limiting factor on the Base Patching will be drilling of nearly 57,000 dowel bars into 9 inch pavement with mesh (the existing mesh greatly effects production). This is easily 57 days or work for two crews. The design schedule should account for a realistic time frame to perform the work. Will WisDOT adjust the time frame? | Based on recent similar projects WisDOT believes the production rates could be met. Base patching will be permitted for the duration of the project as long as the base patching operations are ahead of the paving operations. | Mike Coleman | 11 | 2019-08-06 07:07 | 2019-08-09 05:30
20190813 | 20190813005 | 5 | Earthwork | The 1100-27-70 / 1107-00-71 projects require the import of material and the Department has indicated that the Borrow required will be paid under 625.0105 Topsoil. Please clarify the Departments decision to utilize the 625.0105 Topsoil item versus the Borrow item. | Payment as topsoil is due to the relatively shallow cut/fills along IH 41. It is not expected that the full width of the median will need to be stripped, excavated and brought back up to grade along the entire limits of the project on IH 41. Topsoil is specified because the material to be placed is outside of the 1:1 slope from the roadway and will be suitable for growing proper vegetation. A similar method was used on IH 94 median project from STH 67 to CTH SS. | Mike Coleman | 12 | 2019-08-07 15:23 | 2019-08-09 05:32
20190813 | 20190813005 | 5 | Freeway Lane closure | The proposal information on lane closures peak times is unclear to us. Are there different lane closure times(peak Times) allowed south than north of STH 60 or what does the statement by Thursday mean? I read it as north of STH 60 lane closures are allowed is that right? | There are different lane closure times allowed south of STH 60 and north of STH 60. The Monday through Thursday peak hours restrictions apply only to south of STH 60. | Mike Coleman | 14 | 2019-08-08 14:08 | 2019-08-09 05:35
20190813 | 20190813005 | 5 | Active Work Zones and Closures | Traffic control plans restrict active work zones and lane closures along IH 41 to a maximum length of 2 miles at a time, unless otherwise approved by the engineer. Based on the length of the project and the distance between ramps, do you anticipate allowing a work zone / closure longer than 2 miles? |  |  | 15 | 2019-08-09 11:17
20190813 | 20190813005 | 5 | Work Zone / Lane Closure | Work Restrictions and traffic control plan indicate active work zones and lane closures along IH 41 shall be limited to a max length of 2 miles at a time. Given the anticipated duration of the project and the quantity of work to be performed, lengthier closures may be required to achieve the desired schedule. Is it anticipated that longer closures will be allowed? |  |  | 16 | 2019-08-09 16:23
20190813 | 20190813008 | 8 | Schedule | Can you please provide design schedule | The design schedule can be located at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813008/ | Mike Coleman | 1 | 2019-07-23 07:37 | 2019-07-24 07:13
20190813 | 20190813008 | 8 | paving and pavement markings | On page 3 of 40 in the proposal it says do not reopen USH 141 until completing the following work...lower layer of asphalt paving by 12:01 8/22/2020. On sheet 104 of the plan sheets, it states layers , pavement marking... by 8/21/2020, which is correct in terms of how the upper layer and associated pavement markings will need to be completed? Thank you. | Page 3 of the proposal has the correct language. The text in the plan sheet should read: CONSTRUCT THE LOWER LAYER HMA PAVEMENT FROM BETTERS COURT TO 4TH STREET. COMPLETE ALL CONSTRUCTION ACTIVITIES REQUIRED TO OPEN USH 141 TO THE STAGE NECESSARY TO REOPEN USH 141 TO THROUGH TRAFFIC, WITH FLAGGING OPERATIONS, PRIOR TO 12:01 AUGUST 22, 2020. An addendum will be issued to correct the note. | Mike Coleman | 2 | 2019-08-02 10:44 | 2019-08-06 14:15
20190813 | 20190813008 | 8 | Bid Schedule | Why is this project being let in August of 2019? Is all work to be done in 2020? | The prosecution and progress states that the contractor shall â€œBegin work within ten calendar days after the engineer issues a written notice to do soâ€. WisDOT NE Region will issue the written notice to proceed in the spring of 2020 and does not plan for this proposal to allow construction outside of the 2020 construction season. | Mike Coleman | 3 | 2019-08-05 10:46 | 2019-08-06 14:35
20190813 | 20190813008 | 8 | Staking for Variable Depth Milling | The typical finished sections for Sta 121+13 through 163+50 indicate that a minimum depth of 3.5" is to be removed via milling, but depths may vary in order to establish a 2% cross slope for the 12-ft travel lane, without exceeding maximum cross slopes for the shoulders. In order to insure that the appropriate depth can be achieved at the curb, it appears that a survey will need to be done to determine the height of the existing curb in order to calculate milling depths, and establish a profile for milling and paving. Milling depths will need to be identified at centerline and edge of lane in order to maintain a uniform profile. Is there a staking item for this work? | A staking item has not been provided for the described work for the cross slope correction. The contractor shall work with the engineer to make cross slope correction and verify milling depths in the field. | Mike Coleman | 4 | 2019-08-06 11:56 | 2019-08-07 06:21
20190813 | 20190813008 | 8 | Geotechnical Information | Is there any soil boring information that can be provided for the project area? | The geotechnical report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813008/ | Mike Coleman | 5 | 2019-08-08 15:37 | 2019-08-09 06:33
20190813 | 20190813008 | 8 | Storm Sewer Patches in Resurfacing Project | The existing typical pavement sections show variable depth asphalt surface throughout the resurfacing project, from 3 to 9 inches. The plan detail sheets for the resurfacing project show the storm sewer repairs to be re-paved with concrete base, and the 3.5" overlay. There doesn't appear to be any quantity for asphaltic surface base patching to replace the remaining depth of asphalt prior to constructing the mill and overlay. Is it the designers intention for the pipe trenches to be paved with concrete base, and filled the rest of the way with base course to maintain traffic until the 3.5" overlay is to be constructed? Or does the designer expect that the roadway surface will be milled prior to storm sewer construction so that the concrete base can be constructed to match the height of the milled surface prior to overlay? If asphaltic surface base patching is required to maintain traffic, will a bid item be added for this work? | The 3.5â€ of HMA pavement shall match the final pavement grades of the mill and overlay throughout the resurface project. The intent was to have roadway milled prior to the storm sewer construction so the concrete base can be constructed to match the height of the milled surface prior to the overlay. | Mike Coleman | 6 | 2019-08-12 05:37 | 2019-08-12 08:15
20190813 | 20190813008 | 8 | Asphaltic Mixture for Adjusting Manhole Covers | Article 26 of the special provisions indicates that asphaltic pavement mixture is to be placed at manholes in two stages, first when the cover plate is installed, and second after the manhole is adjusted prior to paving. This article also indicates that the asphaltic pavement mixture is to be paid for, but quantities are not shown in the miscellaneous quantities sheets to indicate which bid item this work would fall under. Is there an existing item that will be used to pay for the asphaltic pavement mixture to be used for filling around manhole adjustments? | The small quantity of asphaltic pavement mixture needed for adjusting manholes was not broken out separately on the Miscellaneous Quantities sheets, but instead was included in the overall HMA Pavement quantities within those particular station ranges. | Mike Coleman | 7 | 2019-08-12 05:47 | 2019-08-12 08:51
20190813 | 20190813008 | 8 | Reheating HMA Pavement Longitudinal Joints on Side Roads | The Miscellaneous Quantities sheets in the plan indicate that the side roads are included in the quantities for the Reheating HMA Pavement Longitudinal Joints item. In general, this is unconstructable. The joint heaters attach to a 30-ft long ski along the side of the paving equipment, which is impractical to use on side roads due to the short length and maneuvering that is required when paving these areas. Generally speaking, the full width of the side roads will be paved simultaneously for each layer of HMA Pavement. Can the quantities for reheating HMA Pavement Longitudinal Joints on side roads be eliminated? | The quantities for reheating HMA Pavement Longitudinal Joints on side roads can only be eliminated if the side roads are paved simultaneously while the pavement joint is still hot. If they are not paved simultaneously with a hot joint then the contractor will have to take the appropriate measures to reheat the HMA pavement longitudinal joint along the side roads. | Mike Coleman | 8 | 2019-08-12 05:55 | 2019-08-12 08:54
20190813 | 20190813009 | 9 | Diameter of Pipe Liner | We are looking to bid the 27â€ and 30â€ liner for this project and were wondering if 28â€ liner could be used in place of the 27â€ liner? Unfortunately we donâ€™t make a size 27â€. | The contractor can use a 28â€ pipe liner as long as it meets all of the project specifications and it fits in the existing pipe. The contractor is responsible for ensuring it will fit. | Jill Fehrman | 1 | 2019-07-16 16:56 | 2019-07-16 16:57
20190813 | 20190813009 | 9 | ASTM A-53-B casing pipe spec | Would casing pipe conforming to ASTM A-252 grade 2 or 3 and meeting the minimum yield strength of 35,000 psi be an acceptable alternative for the project? | ASTM A252 is the Standard Specification for Welded and Seamless Steel Pipe Piles. This is not a pile application therefore ASTM A-53-B should be used. | Mike Coleman | 2 | 2019-08-09 10:48 | 2019-08-12 12:19
20190813 | 20190813009 | 9 | Soils Info | Is there any geotech information available, particularly for the 36inch jack and bore crossing? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190813009/ | Mike Coleman | 3 | 2019-08-12 12:48 | 2019-08-12 15:38
20190813 | 20190813011 | 11 | Item No. 204.0110 Removing Asphaltic Surface | Would it be acceptable to remove the asphalt surface at each of the asphalt patch locations using a milling machine or does the asphalt patch have to be saw cut as shown in the detail on sheet 12 of the plans? Also can this work be performed prior to the mainline asphaltic surface milling? Thank you. | 1. Using a milling machine to remove the asphaltic surface at each of the asphalt patch locations is acceptable with the following expectations: - Remove existing asphaltic pavement or surface to the depth the plans show (full depth) by milling, chipping, or sawing and as specified under 204.3.2.2.2. - Mill transversely (perpendicular to centerline) when removing patches to provide a clean and true vertical transverse joint from the surface to the base course without leaving asphalt in the bottom corners as shown in the Asphaltic Surface Patching details. - Mill longitudinally (parallel to centerline) at the centerline joint when completing single lane patches to provide a clean and true vertical longitudinal joint from the surface to the base course without leaving asphalt in the bottom corners as shown in the Asphaltic Surface Patching details. - Additional milling passes required to provide the vertical joints are incidental to the Removing Asphaltic Surface bid item. No compensation will be made for the sawing asphalt bid item unless sawing is acceptably completed. - As outlined in the special provisions, match milling and paving edges of adjacent lanes prior to completing work at the end of each day. 2. The intent of the asphaltic surface patching is to patch the worst areas of deterioration and maintain traffic during construction. Removal of the deteriorated areas and patching is to be completed after the mainline asphaltic surface milling. Coordinate with the engineer to determine the areas of deterioration to be patched after mainline asphaltic surface milling and prior to placing the new HMA. | Mike Coleman | 1 | 2019-07-29 15:29 | 2019-07-31 14:16