## qandasearchletting_results
Date: | 2020-03-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200310 | 20200310002 | 2 | Asphalt Quantities | The plans have a table for tonnages for asphalt pavement and quantities for removal areas with starting and ending stations. However there is no indication of the depth of the milling and paving in these sections which would be found in the typical sections. Also there is no indication of the width which would typically be seen in plan sheets. Could the department add plan sheets showing how the milling and paving is supposed to occur? | The answers to the questions are in the plan and can be found in the upper left corner of sheet 5. | Mike Coleman | 1 | 2020-02-19 09:18 | 2020-02-20 07:21
20200310 | 20200310002 | 2 | Working Days | 50 working days is pretty stringent for the amount of scope of work that needs to be completed. Will WIDOT consider allowing additional working days in order to complete all scopes of work for this contract or is 50 working days set? | An additional 8 working days will be added via addendum. | Mike Coleman | 2 | 2020-02-24 12:54 | 2020-03-02 06:48
20200310 | 20200310002 | 2 | As Built/Design Plans | Can the existing bridge plans be made available for each Bridge? | The existing bridge plans can be accessed through the WisDOT HSI site. | Mike Coleman | 3 | 2020-03-02 19:20 | 2020-03-04 07:28
20200310 | 20200310002 | 2 | Working Days | The schedule seems aggressive for the amount of work especially the large amount of surface area to be cleaned and painted. More time is needed on the total working days and on each phase listed in the proposal. Please increase the overall working days and the working days per phase listed in the proposal. | The working days for this contract were changed in addendum #01 from 50 working days to 58 working days. | Mike Coleman | 4 | 2020-03-02 19:24 | 2020-03-06 06:51
20200310 | 20200310002 | 2 | Surface Area Information | 1. Plan Pages 54, 56 provides the estimated structural steel surface area for structures B-11-74 and B-11-75. The estimated area is not provided in the plans for B-13-288. Can that be added? 2. Page 8 of 15 of proposal. Surface areas listed per bridge do not match the areas listed on plan pages 54 and 56. The surface area given for B-13-0288 is not correct. It should be around 37,000 square feet. Can that proposal page be corrected so that the information on the plans and proposal match? |  |  | 5 | 2020-03-07 13:55
20200310 | 20200310003 | 3 | No ASP-5 | There is no ASP-5 for Fuel Cost Adjustment, should there be? | ASP-5 should have been in the proposal but was inadvertently left out. An addendum will be issued to add it in. Thank you for pointing this out. | Mike Coleman | 1 | 2020-02-12 09:29 | 2020-02-12 10:42
20200310 | 20200310003 | 3 | Electronic Data Request | Please provide these files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement and Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The files requested can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310003/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2020-02-13 13:13 | 2020-02-19 06:57
20200310 | 20200310003 | 3 | March letting Job 3 | Will the 8" concrete pavement pavement be doweled or non doweled pavement? | The 8â€ concrete pavement will be doweled. Dowels will be paid for under the bid item 415.0080 Concrete Pavement 8-Inch bid item. Dowel bars are not required at the match points located at the begin/end of project on USH 12. | Mike Coleman | 3 | 2020-02-21 16:29 | 2020-02-24 10:31
20200310 | 20200310003 | 3 | Line Item 0276 Basic Traffic Queue Warning System. | The Misc Qty's has 114 days north and south of the project. Can we get a breakdown of this? Which stage ETC 207 calendar days (plus of minus) and 114 days of the system. Thanks. | Per Joe Schneider, SWR Traffic Engineer, one system covers both ends of the project and shall be used beginning one week prior to Memorial Day and removed after Labor Day which works out to be 114 days. The computations can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310003/ | Mike Coleman | 4 | 2020-02-25 14:48 | 2020-02-26 08:51
20200310 | 20200310003 | 3 | Reinforcement in existing concrete pavement | Can you tell us what if any steel reinforcement is in the existing concrete pavement (doweled, mesh, longitudinal, none)? | Upon review of the 1942 As-Builts on this section of USH 12, it is not clear what type (if any) steel reinforcing was used in the existing concrete pavement. | Mike Coleman | 5 | 2020-02-28 15:10 | 2020-03-02 12:57
20200310 | 20200310003 | 3 | Salvaged Topsoil to USDA | Has the salvaged topsoil quantity to be removed from the project and hauled to the USDA been calculated into the borrow quantity for the project? If so how much borrow is anticipated to replace the salvaged topsoil removed from the project? | No the salvaged topsoil quantity was not calculated into the borrow quantity for this project. | Fred Schunke | 6 | 2020-03-04 16:30 | 2020-03-05 13:34
20200310 | 20200310004 | 4 | strand pattern dimensions | Please verify the strand pattern dimensions as the typical strand pattern provided appears to be incorrect. Specifically the height of the bottom flange printed as 3-3/4" typically 7.5" and distance to the first row of strand printed as 1" or the typical 2"? | It is our intent to use the typical dimensions and strand pattern for the 36W-Inch prestressed girders on this structure. The discrepancies in the â€œTypical Strand Patternâ€ detail on the Prestressed Girder Details sheet were caused by a dimension scaling issue and are not intentional. An addendum will be issued to correct the dimensions. | Mike Coleman | 1 | 2020-02-19 12:07 | 2020-02-20 07:50
20200310 | 20200310004 | 4 | Design Files | Can the Department Provide: 1. Soils Report 2. Design Schedule 3. Design Files (existing/proposed surfaces, prop line work, slope intercept drawings, retaining wall line work, etc.)? | The files requested can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310004/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2020-02-19 16:40 | 2020-02-25 07:58
20200310 | 20200310004 | 4 | MSE Walls Quantity | R-53-84 & R-53-85 MSE Wall quantities seem too high (if the front face wall elevation drawings are to scale). The plan quantity in the plan set is taken from the top of footing to the top of coping as shown in the front face elevation drawings. The quantity should be taken from 1'6" below finished grade to top of coping per the payment notes. Please review and adjust the plan quantity as necessary. | The walls have been designed to allow for future expansion of the railroad. Because of this, there is no option to step the leveling pads up at the ends as would be standard; they must be placed in the lower position all the way along the wall. That is what we are trying to convey with the notes, but the notes were not clear. We are planning to update the notes to clarify. The quantities in the plans are correct. | Mike Coleman | 3 | 2020-02-19 16:44 | 2020-02-21 06:56
20200310 | 20200310005 | 5 | Soil Borings | Are there soil borings available for the Village of Stoddard? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310005/ | Mike Coleman | 1 | 2020-02-17 08:19 | 2020-02-20 08:12
20200310 | 20200310005 | 5 | Select Borrow | Plan sheet 108 of plan set 5163-09-71, note number 11 states that EBS is to be backfilled with Select Borrow, item 208.1100. The project does not contain bid item 208.1100, what is the intent? | The note is incorrect. Backfill material is SPV.0195 16-Inch x 2-Inch Select Crushed Material. An Addendum will be issued. | Mike Coleman | 2 | 2020-02-25 07:55 | 2020-03-02 06:49
20200310 | 20200310005 | 5 | Cold In-Place Specifications | Specifications for CIR on this project require a mix design be performed which will identify the allowable tolerance for field adjustments to asphalt stabilizing agent and water limited to percentages which produce TSR values define in Table B.3 Mix Design requirements. Significant work was done by DOT staff and contractors over the last year to re-write these specifications, based on completed projects, to requiring a mix design be performed for informational purposes only and that the stabilizing agent and water will be 2.0 percent with +/- 0.3 percent field adjustment tolerance. Since asphalt stabilizing agent and water are the only contractor controlled variables in the CIR process is there any way that the CIR specification in this proposal be removed and updated to the current version? | Addendum #3 will be issued that will replace the CIR specification | Mike Coleman | 3 | 2020-02-28 08:53 | 2020-03-04 13:01
20200310 | 20200310005 | 5 | Mill and Relay | Mill and Relay to full depth of existing asphalt is specified at bridge approach sections. In all areas where mill and relay is required additional aggregate is also specified to meet new profile at the structures. Given that this work will need to be done in advance of CIR operations in order to establish the new profile for CIR to match and the fact that new aggregates are being used to achieve the design profile, can the mill and relay areas be pulverized and relayed? This will be a significant cost savings in mobilization and time to make this change. | The contractor should bid the project as shown in the plans and discuss alternate methods after the award of the contract | Mike Coleman | 4 | 2020-02-28 08:53 | 2020-03-04 13:01
20200310 | 20200310005 | 5 | CIR depths | Is the depth of milling for CIR 4â€ (this would make the relayed depth 3.33â€ in areas were width changes from 15â€™ existing to 18â€™ relayed)? Or does the contractor need to mill > 4" depth to relay material at 4â€ thick? | The depth of milling for CIR is 4â€ that will be spread to 18 feet wide, which will leave the finished product less than 4â€ thick | Mike Coleman | 5 | 2020-02-28 09:59 | 2020-03-04 13:02
20200310 | 20200310005 | 5 | Proposal schedule of items #46 | Item 46 listed in the proposal schedule of items is not listed on the bidx list of items. All items after 46 are off by 2 comparing bidx to the proposal pdf. | Addendum #02 fixed this issue. | Mike Coleman | 6 | 2020-02-28 10:43 | 2020-03-04 13:05
20200310 | 20200310005 | 5 | Silt Screen Depths | Is there an estimate of the depth that will be required for the silt screen? | The estimated depth of the silt screen is 6 feet. | Mike Coleman | 7 | 2020-03-02 15:55 | 2020-03-04 13:06
20200310 | 20200310005 | 5 | 066 Prepare CIR Foundation for HMA Layer | This item is for repairing raveled areas, rutted areas, areas of excess or deficient stabilizing agent, or deficient surface tolerance areas. The plan quantity is the same as the CIR plan quantity which implies that the whole CIR surface will need to be repaired. Should the quantity for this item be a small percentage of the CIR quantity since it is unlikely that the entire CIR surface will fail and need to be repaired? | The Region interprets the specification pay limits as the entire SY of CIR since inspection and moisture content testing is required for the entire area. In the field, if the CIR quantity changes from the plan quantity, this item would be adjusted as well. Any required non-structural repair is "at no additional cost to the department" per this specification. | Fred Schunke | 8 | 2020-03-04 16:19 | 2020-03-05 13:49
20200310 | 20200310008 | 8 | Completion date | Why is wisdot bidding a project in the march letting with a June 12 completion date. Most if not all contractors have there spring projects lined up already | This projectâ€™s timeline was advanced to avoid scheduling issues with Proposal 20191210007 which begins on June 15th and is adjacent to this project. Proposal 20191210007 has requirements that does not allow for flexibility within their schedule due to a utility project with their project limits and commitments made with local and environmental authorities. | Mike Coleman | 1 | 2020-03-03 21:35 | 2020-03-04 11:18
20200310 | 20200310009 | 9 | Traffic on Milled Surface | Will traffic be allowed to travel on a milled surface for any period of time? Given the tight window for work each night, milling ahead would significantly increase productivity and reduce the number of work nights. | Traffic will not be allowed to travel on a milled surface. | Mike Coleman | 1 | 2020-03-03 08:40 | 2020-03-04 07:26
20200310 | 20200310009 | 9 | Schedule of Operations | The schedule of Operations requires the stages to be completed sequentially. When Brewer games and/or Bucks games conflict with ramp and/or lane closures, will we be allowed to work out of sequence? We would want to work SB or WB on Brewer game nights and EB during Bucks games. | Operations are intended to be constructed as shown in the plans and special provisions but modifications can be submitted to the engineer for approval. | Mike Coleman | 2 | 2020-03-03 10:45 | 2020-03-04 07:27
20200310 | 20200310010 | 10 | Error and Omissions in the Plan in Regards to the Concrete Pavement Specified | First, the finished typical section does not contain any note indicating the presence of dowel bars. Then, the plan is missing Standard Detail Drawing SDD13C13-9, Urban Doweled Concrete Pavement. The combination of these two things is potentially leading your bidders to conclude this is an undoweled pavement. I do not believe that WisDOT would build an undoweled pavement. Second, under the 2020 standard specifications this pavement would require joint filling so the pay item 415.41 should be included in the contract. Please advise me if I am correct on both issues | The 8â€ concrete pavement is intended to be doweled with joint filling. An addendum will be issued to revise the typical sections to call for doweled pavement, SDD 13C13-9 Urban Doweled Concrete Pavement will be added to the plans, and item 415.4100 Concrete Pavement Joint Filling will be added to the project. | Mike Coleman | 1 | 2020-02-21 09:40 | 2020-02-24 12:12
20200310 | 20200310010 | 10 | March letting Job 10 | Will the 8" concrete pavement be a doweled or non doweled pavement. 8,560 sy | The 8â€ concrete pavement is intended to be doweled with joint filling. An addendum will be issued to revise the typical sections to call for doweled pavement, SDD 13C13-9 Urban Doweled Concrete Pavement will be added to the plans, and item 415.4100 Concrete Pavement Joint Filling will be added to the project. | Mike Coleman | 2 | 2020-02-21 16:20 | 2020-02-24 12:13
20200310 | 20200310010 | 10 | Inlet Protection Type A | What is the grate size for the Inlet Protection Type A? | The size varies depending on the type of inlet. Inlets with Type H covers have a 2â€™x3â€™ opening, 1G-MS structures have a 2â€™ 10.5â€ x 2â€™ 10.5â€ opening, and 2G-MS structures have a 2â€™ 10.5â€ x 5â€™ 8.5â€ grate opening. Refer to the Standard Detail Drawings for each inlet type to determine the dimensions of the inlet itself, and thus, the dimensions of the Type A inlet protection. | Mike Coleman | 3 | 2020-02-24 09:43 | 2020-02-24 12:13
20200310 | 20200310010 | 10 | Common Excavation Quantities - Retaining Pond Excavation | In the Earthwork Table for the project there is a Note stating *Storm water pond not shown in detailed earthwork tables. Includes excavation for Pond Clay liner. There is only Qty listed for Cut for 3136 CY for Clay liner is included in the Earthwork summary. Also in the earthwork cross sections the Pond is represented but noted "Proposed Storm water Pond (Shown for Information purposes only. Not included in 74th Street earthwork.) However there are no items listed for the excavation of the retention pond. Where will the associated costs for the excavation for the retention pond be paid for? Also what is the quantity for the Pond excavation? | The quantity of 3,136 CY in the Earthwork Summary includes the total amount of excavation needed for the pond, down to the bottom of the 2â€™ clay liner. It includes an estimated 2,366 CY to the bottom of the finished pond and 770 CY of excavation for the clay liner. The combined 3,136 CY will be paid under item 205.0100 Excavation Common, as listed in the Earthwork Summary table on page 63 in the plans. The pond excavation quantity was not included in the detailed earthwork summary sheets because it was determined more accurately by comparing the existing ground surface to the bottom of the proposed clay liner, not by cross sectional end areas. | Mike Coleman | 4 | 2020-03-04 16:16 | 2020-03-05 11:30
20200310 | 20200310011 | 11 | Item 0408 End Diaphragm Adjustment SPV 0060.003 | The specials for this item state to "Augment the bolts by placing 1/4" fillet welds along the sides of the channel where it is adjacent to the gusset plate." This is pretty vague and there is no weld detail for this work on page 366 of the plan where it details the modifications to the existing end diaphragms. Does it need to be welded all the way around or just on one side? Could a detail be provided to show the locations of the field weld that will be required for this work? Also, will a CWI be required to be onsite to inspect these welds? If so this will add a great deal of cost to this item. | An addendum is being issued to address these questions. | Mike Coleman | 1 | 2020-02-21 08:04 | 2020-02-26 07:03
20200310 | 20200310012 | 12 | Construction Staking Pavement Marking, Item SPV.0090.01 | Good afternoon. This is a new item that we have not seen before. Can you please elaborate on if this is to be completed by an engineer or consulting engineer. In reading through the specifics under standard specification 650, it appears this involves specialized equipment, etc. and I want to make sure what exactly is expected for this item. Thank you. | Bid item Construction Staking Pavement Marking, Item SPV.0090.01 is intended for the contractor. There are segments of the project where the pavement marking does not follow the alignment and curbs are not parallel. As a result, selected edgelines and centerlines were specified to be marked by surveyors prior to the arrival of the pavement marking subcontractor. A CAD file (.dwg format) will be provided to the survey subcontractor by the design team so that they can place marks on the pavement indicating the locations of the selected edgelines and centerlines. The CAD file can be loaded into standard survey equipment such as GPS or a Total Station. Note that the construction staking pavement marking item is not for all pavement marking, just for selected complex pavement marking lines. | Mike Coleman | 1 | 2020-02-18 15:00 | 2020-02-20 10:37
20200310 | 20200310013 | 13 | Contractor Data Packet | Can you provide the Excel Earthwork Sheets, Excel Storm Sewer Pipe Tables, Design Schedule and the Soils Reports? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310013/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-02-13 10:47 | 2020-02-20 07:05
20200310 | 20200310013 | 13 | Electronic Data Request | Please provide these files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement and Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310013/ | Mike Coleman | 2 | 2020-02-13 13:12 | 2020-02-20 07:16
20200310 | 20200310013 | 13 | Pavement Markings - Paint and Temp Paint | There are line items for both Paint, and Temporary Paint Markings in the proposal, and in the Estimate of Quantities pages of the plans, but they are not included in any of the Miscellaneous Quantities. Is the paint even needed? Will there be an addendum to correct the misc. Quantities? | Yes these items are needed. The MQ table for these marking items will be included in an addendum. | Mike Coleman | 3 | 2020-02-14 11:20 | 2020-02-27 07:08
20200310 | 20200310013 | 13 | Earthwork Summary Sheet into Stages | Can the Earthwork Summary Sheet be revised to show the earthwork breakdown per stage of work? | The design of this project did not include development of cross sections by stage. The requested Earthwork Summary information by stage is not readily available. | Mike Coleman | 4 | 2020-02-14 12:21 | 2020-02-25 07:17
20200310 | 20200310013 | 13 | Article 33 Excavation Below Subgrade | Why is Article 33 Excavation Below Subgrade changing the standard specification "205.5.2 Paragraph 2"? This Specification was just re-written. | With the recent update to the standard specification, the section referred to in Article 33 requires a revision. The revision will be included in a plan addendum. | Mike Coleman | 5 | 2020-02-14 16:12 | 2020-02-27 07:09
20200310 | 20200310013 | 13 | Railing Finish | The plans for structures B-67-0374, B-67-0375 and R-67-0154 indicate the railing is to receive touch-up painting after installation. There is no requirement for painting of the railing, it only states to galvanize after fabrication. Please confirm painting is not required on the railing. | The railing is galvanized after fabrication. No painting is required on the railing. | Mike Coleman | 6 | 2020-02-20 11:49 | 2020-02-25 07:19
20200310 | 20200310013 | 13 | Clearing and Grubbing | Please verify that the Clearing and Grubbing quantity includes both sides of the street, since there is only one reference line | Clearing and Grubbing is quantified by station and 1 STA includes both sides of the road. | Mike Coleman | 7 | 2020-02-24 09:15 | 2020-02-25 07:21
20200310 | 20200310013 | 13 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch and Breaker Run? | Item Description Conversion Factor (Tons/CY) 305.0110 Base Aggregate Dense 3/4-Inch 2 305.0120 Base Aggregate Dense 1 1/4-Inch 2 311.0110 Breaker Run 1.8 | Mike Coleman | 8 | 2020-02-26 16:07 | 2020-02-27 11:54
20200310 | 20200310013 | 13 | No Excuse Weather, Labor & Material Clause (Supplement standard spec 108.10) | This project doesn't seem to fit the requirements to have the No Excuse Weather, Labor Dispute & Material Deliveries included in the Special Provisions (Supplement standard spec 108.10). Please clarify this correct. | An addendum was issued to remove this language. | Mike Coleman | 9 | 2020-02-26 16:42 | 2020-03-04 06:55
20200310 | 20200310013 | 13 | Epoxy 6" Crosswalk | Line item 0484 the bid quantity for 6" Crosswalk do not match the quantities in the proposal? There is a 200 L.F difference? | The total on the MQ plansheet is the correct quantity, 5334 LF. The proposal will be corrected in an upcoming addendum. | Mike Coleman | 10 | 2020-02-27 10:25 | 2020-03-02 06:54
20200310 | 20200310013 | 13 | Stair Railing | Is there a bid item for the stair railing? | There is no bid item or estimated quantity for the railing. It is not anticipated that the railing will be needed as there are only 2 steps and the detail states â€œSteel reinforcement and pipe railing not required on steps with 2 risers or lessâ€. | Mike Coleman | 11 | 2020-03-05 09:15 | 2020-03-05 09:15
20200310 | 20200310013 | 13 | Paint Marking | What is the paint marking going to be for? There are a separate items for temporary paint marking, regular paint marking and epoxy marking. The plans are unclear, and I'm unable to find what the paint is going to be. | â€¢ Marking Line Paint is intended for marking on existing pavement for traffic during staged construction. See Traffic Control Plans. â€¢ Temporary Marking Line Paint is intended for marking on new pavement for traffic during staged construction that will eventually be removed. See Traffic Control Plans. â€¢ Marking Line Epoxy is intended for the permanent marking on new pavement. See Pavement Marking plans. â€¢ Refer to section 646 of the standard specifications for additional information. | Mike Coleman | 12 | 2020-03-05 10:03 | 2020-03-05 11:18
20200310 | 20200310013 | 13 | Asphaltic Surface Placement | Is the intent to place both binder and surface asphalt in each phase before moving to the next, or can all surface asphalt be placed at the end of the project? |  |  | 13 | 2020-03-06 12:45
20200310 | 20200310013 | 13 | Hydra CM Mulch | The Hydra CM Mulch you specâ€™ed is no longer being manufactured , the plant closed. Would Flex Terra HP or Bindex work? | The specification calls for â€œHydraCM by North American Green ®, A Tensar ® Company or equivalent material shall be used.â€ Per Specification, an equivalent material such as Bindex, Flex Terra, or other product, would be acceptable as per the manufacturers recommendation for the steepness of the slopes being covered. | Jill Fehrman | 14 | 2020-03-06 14:04 | 2020-03-09 07:35
20200310 | 20200310016 | 16 | Sign Structure Anchor Rod Repair | The sign structure anchor rod repair detail contains some contradictions which need clarification. 1. The detail calls for 6" A36 steel pipe. The standard grade of steel pipe is A53 Grade B. Please confirm the 6" steel pipe should be A53 Grade B pipe instead of A36 steel. 2. The detail calls for Schedule 80 x 0.28" thick pipe. 6" diameter Schedule 80 pipe is 0.432" thick. Please confirm that Schedule 40 pipe, which has a wall thickness of 0.28" is desired. 3. Please clarify what a Type S masonry anchor is. | 1. 6â€ diameter either A36 bent plate or A53 Grade B pipe is acceptable. 2. If A36 plate is used, it should be 0.25â€ thick. If pipe is used, the thickness should be per Schedule 40 or 0.28â€ thick. 3. A Type S anchor is a standard adhesive anchor (threaded rod usually). | Mike Coleman | 1 | 2020-02-10 17:24 | 2020-02-12 07:37
20200310 | 20200310018 | 18 | Metadata and Soils Report | Can we get the metadata packet and soils report? | The metadata and soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310018/ New and updated design files have been uploaded to the same ftp site listed above. | Mike Coleman | 1 | 2020-02-04 14:08 | 2020-02-04 14:09
20200310 | 20200310018 | 18 | Design Schedule | Please provide a copy of the Design Schedule. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Jill Fehrman | 2 | 2020-02-05 08:15 | 2020-02-10 15:42
20200310 | 20200310018 | 18 | Design Schedule | The previously provided design schedule appears to be for project #18 in the February letting, not the March letting as requested. | The schedule that was posted on February 10 was for a February letting. We will post the correct schedule when we receive it. We apologize for the confusion. The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2020-02-10 18:53 | 2020-02-12 07:20
20200310 | 20200310018 | 18 | March WisDOT Letting Proposal No 18 | Proposal No 18 will not download. Could you please check the file? | It appears to be downloading fine for us. Try the following link: ftp://ftp.dot.wi.gov/dtsd/hcci/plansandproposals/2020/03March_10/20200310018proposal.pdf | Mike Coleman | 4 | 2020-02-14 10:10 | 2020-02-19 07:02
20200310 | 20200310018 | 18 | Mitigation Site Design Files | Can the department provide Land XML files or Cad files (or both) for the Schaefer mitigation site? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310018/ | Mike Coleman | 6 | 2020-02-14 10:56 | 2020-02-24 08:14
20200310 | 20200310018 | 18 | Quantities | Looking through the plan / miscellaneous qtys and it looks like some of the items within the misc. qtys that are shown for the CTH G Interchange are not included for the whole bid total. I noticed it for clearing and grubbing and salvaged topsoil. | Actually, for the clearing (201.0105), grubbing (201.0205), and salvaged topsoil (625.0500) items, the entire project bid total seems correct and includes the CTH G interchange totals. The trick is that you need to add up all the â€œsubtotalsâ€ to get the â€œproject totalâ€. For example, to get the project total for salvaged topsoil, you need to add up all the subtotals under the columns on pages 465, 466, and 513 (495,338 + 399,568 + 103,770 = 998,676 SY). | Mike Coleman | 7 | 2020-02-19 07:19 | 2020-02-19 07:24
20200310 | 20200310018 | 18 | Quantities Subtotals | Why donâ€™t the miscellaneous quantity subtotals in the plan for item numbers <list item numbers> add up to the total estimate of quantities for the project? | The total estimate of the quantities for the listed items are in error as they did not include quantities from the borrow pit table on page 466 of the plan. The total estimate of quantities for these items will be corrected as part of a future addendum. | Mike Coleman | 8 | 2020-02-19 07:21 | 2020-02-19 07:28
20200310 | 20200310018 | 18 | Tie Bars | Why are tie bars shown on the two typical sections for turn lanes on the bottom of page 7 of the plan while no drilled tie bar item or quantity is included? | The two typical sections incorrectly show the new turn lanes being tied to EXISTING CONCRETE PAVEMENT. Instead, those typical sections should show the new turn lanes being tied to new CONCRETE PAVEMENT that is being installed as mainline pavement under the contract. The tie bars will be installed with the mainline paving and will need to be bent out prior to paving the turn lanes. Hence, no drilled tie bars are needed. These typical sections will be corrected as part of a future addendum. | Mike Coleman | 9 | 2020-02-19 07:32 | 2020-02-19 07:34
20200310 | 20200310018 | 18 | Missing Design Files and Issues with Cross-sections | Of the Metadata files that were provided, there is missing Datum information regarding the CTH G interchange location. There is no proposed surface for CTH G itself (including the roundabouts) or the CTH G service ramps. Can this please be provided as well. Also, there appears to be an issue with the cross-sections for the â€œCTH G CIRC. ROADWAY SOUTH RAB (â€˜APâ€™ LINEâ€™) shown on sheets 1444 and 1445 of the plans. These plansheets may need to be revised. | The CTH G files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310018/ | Mike Coleman | 10 | 2020-02-21 16:45 | 2020-02-26 07:24
20200310 | 20200310018 | 18 | Line # 6 & 10 | Shouldn't these items clearing & grubbing be by the acre, not by ID? | The clearing & grubbing items listed on Lines #6 & #10 are shown incorrectly. These items should be measured by the acre. The change in items will be corrected as part of a future addendum. | Mike Coleman | 11 | 2020-02-22 11:18 | 2020-02-26 08:41
20200310 | 20200310018 | 18 | Old Plank Trail - Quanities | There doesn't appear to be quantities for Old Plank Trail. | The Old Plank Trail quantities are shown throughout the Miscellaneous Quantities on the following sheets. Common excavation and embankment quantities (category 0010) are shown on sheet 427. The culvert pipe quantities (category 0010) are shown on sheets 447, 448, and 449. Rip rap quantity (category 0010) is shown on sheet 460. Restoration quantities (category 0010) are shown on sheets 465 and 466. Fencing quantity (category 0010) is shown on sheet 499. Staking quantities (category 0010) are shown on sheet 503. Base aggregate, asphaltic surface, and detectable warning field quantities (category 0060) are shown on sheet 514. | Mike Coleman | 12 | 2020-02-24 15:54 | 2020-02-26 08:42
20200310 | 20200310018 | 18 | DOT Owned Property | Will the property owned by the DOT along the project be available for the contractors to use? | DOT property along the project may be used by the contractors provided they complete the required environmental documentation and receive approval from DOT. See ASP-6 for new language for standard spec 104.8(2) that describes requirements for excavating materials on the right-of-way thatâ€™s not within the horizontal and vertical excavation limits the plans show. | Mike Coleman | 13 | 2020-02-27 07:51 | 2020-03-02 06:52
20200310 | 20200310018 | 18 | Steel Thrie Beam Bullnose Terminal | The detail for the bullnose is shown on p. 21 of the plan. It appears that either end of the bullnose will eventually terminate using the "Steel Thrie Beam Structure Approach" bid item at the 205 bridge. However, I can't decipher what the intended material is to be between the bullnose and the structure approach. Is it "Steel Plate Beam Guard Class A" as the MQ's (p.459) are implying? Generally, in a bullnose application, the bid item for "Steel Thrie Beam" is used, but it isn't present in this contract. Can you please explain what bid item falls between the bullnose terminal and the structure approach location on either side of the median? | The Miscellaneous Quantities incorrectly show â€œSteel Plate Beam Guard Class Aâ€ as being placed between the bullnose and â€œSteel Thrie Beam Structure Approachâ€. The quantity in this section should have been â€œSteel Thrie Beamâ€. The change in items will be corrected as part of a future addendum. | Mike Coleman | 14 | 2020-02-27 11:01 | 2020-03-02 06:57
20200310 | 20200310018 | 18 | Computations in excel format | Would you please send the earthwork computations found on sheets 884 thru 996 in an excel format to do our takeoff work? | The earthwork computations can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310018/ | Mike Coleman | 15 | 2020-02-27 12:14 | 2020-02-27 12:26
20200310 | 20200310018 | 18 | Line # 68 - Backfill Structure Type A | Is this item supposed to be bid by the CY or TON? Structure 205 shows 300 TON, 215 shows 156 TON, while 218 shows 1056 CY. Is structure 205 & 215 just a typo? | The backfill structure type A item listed on Line #68 is shown incorrectly. This item should be measured by the TON. The unit shown on the plan for B-20-218 should be TON. The change in item will be corrected as part of a future addendum. | Mike Coleman | 16 | 2020-02-27 13:52 | 2020-03-04 06:51
20200310 | 20200310018 | 18 | Temporary Stone Ditch Checks | Where are the temporary stone ditch checks going to be placed as they are not shown in the temporary erosion control plan? Seems to be an unreasonable quantity at 120 each? | The quantities for temporary stone ditch checks were calculated incorrectly in the Miscellaneous Quantities. The quantity should have been 15 each. The correct quantity and locations will be corrected as part of a future addendum. | Fred Schunke | 17 | 2020-02-28 09:25 | 2020-03-03 10:47
20200310 | 20200310018 | 18 | HMA Intersections/Turn Lanes Mix Design | The paving details and miscellaneous quantities call out a 3 LT 58-28 S and 4 LT 58-28 H (AP2) for the intersections and turn lanes adjacent to the HMA pavement mainline. HMA pavement mainline is 3 MT 58-28 S and 4 MT 58-28 S (AP6/AP4). With the 3â€™ and 6â€™ shoulders being 4 LT 58-28 S that will require 5 different mixes in relatively small areas. This will restrict what can be paved together cause increased joints. Would the department consider changing the intersections and turn lanes to the MT mixes to improve the constructability? The Sheyboygan County STH 23 project (1440-13-72) is designed with all MT on the intersections. | The HMA pavement types shown in the plan for intersections and turn lanes were verified with the pavement design engineer and are shown correctly in the plan as intended. Bidders should bid the project according to the HMA pavement types noted in the plan. | Mike Coleman | 18 | 2020-02-28 13:36 | 2020-03-02 13:00
20200310 | 20200310018 | 18 | Earthwork | In regards to the DOT property along the project. ASP 6 does not address using this property for excess excavation. Will this be allowed throughout the project as long as the property is not considered wetlands? | DOT property may be used as a waste site for excess excavation provided that the contractor completes required environmental documentation, obtains necessary permits, and receives written authorization from DOT. At the minimum, for DOT requirements, this includes completion of Section B of the Erosion Control Implementation Plan (ECIP Form DT1073) for the selected site on DOT property and acquiring approval from DOT to use the site as part of the ECIP approval. | Fred Schunke | 19 | 2020-03-04 10:33 | 2020-03-05 10:30
20200310 | 20200310018 | 18 | Earthwork | What are the specific limits of the QMP subgrade? is it just required within the assumed 1:1's of the subgrade areas for the roadway? Is it required for the Plank Trail? | The first paragraph under Article 29 QMP Subgrade states, â€œThis special provision describes requirements for subgrade materials within the roadway foundation as defined in standard spec 101.3.â€ The definition of â€œroadway foundationâ€ per standard spec 101.3 is, â€œThe area underlying the proposed roadway within the limits of assumed one-to-one slopes extending outward and downward from the subgrade shoulder point.â€ Construction & Materials Manual section 8-32.1 states that the Quality Control (QC) of QMP Subgrade will be understood to cover all subgrade construction on the mainline. However, in addition to STH 23, WisDOTâ€™s intent for this project is that QMP subgrade will also apply to all ramps, county roads, and local roads constructed under this contract. This will be clarified in a future addendum. Since section B.6.1(1)3 of Article 29 QMP Subgrade states that areas to be designated for control charts include embankments for Old Plank Trail except when independent of roadway fill, the only portions of the Old Plank Trail to be included in the QMP Subgrade requirement are those within roadway foundation limits constructed under this contract. | Fred Schunke | 20 | 2020-03-04 10:35 | 2020-03-05 10:31
20200310 | 20200310018 | 18 | Special Provision Section 3 Prosecution and Progress - Earthwork Staging (page 5/61) | Has the Department considered potential schedule impacts related to the Earthwork Staging requirements? Completing select crushed material, base aggregate and concrete pavement over any area where subgrade cut/fill has been constructed to the plan elevations will limit the construction time available to grading activities. Will consideration be made for areas that are cut to final subgrade but weather would not permit completing one or all of the lagging activities: select crushed material, base aggregate, and concrete pavement? | Yes, the department has considered the potential schedule impacts related to the Earthwork Staging requirements in the development of the contract time. The primary intent of the provision is to complete the placement of select crushed material, base course, and pavements during the same construction season to prevent the (high) potential of grade saturation without an impermeable surface over the winter. If the placement of the select crushed material, base course, and concrete pavement cannot be completed within the same construction season, the Department will not be responsible for the cost required to recondition, repair, or replace the subgrade, select crushed, and base aggregate materials to an acceptable condition per the specifications. | Fred Schunke | 21 | 2020-03-04 14:27 | 2020-03-05 14:02
20200310 | 20200310018 | 18 | Type I sign notes on permanent signing plan | Are there additional specifications or guidance for determining the number and size of bases and structural steel supports? There is not enough information provided in the plan to do this. | An addendum would be issued to correct the sign plate numbers in the note under the miscellaneous quantity table for Type I signs, remove the incorrect sign plates, and add the correct sign plates in the plan. Per the Northeast Region Traffic Unit, contractors will need to reference the sign locations noted on the plan, new sign plates, and cross sections to determine/estimate the number and size of bases and structural steel supports. | Fred Schunke | 22 | 2020-03-05 13:40 | 2020-03-05 13:41
20200310 | 20200310020 | 20 | Milling by the ton. | The milling item on the project currently by the ton, could this be changed to milling by the square yard? The differential depths in the milled area can be accounted for in either case and are clearly called out on the plan. | This was changed to SY in addendum 1 | Mike Coleman | 1 | 2020-02-25 13:44 | 2020-03-06 06:56
20200310 | 20200310020 | 20 | Reconstruction area typical | Per the typical section for the 2852+50-2856+50 area it appears that the asphalt gets removed and then 0-10" of base gets placed to bring the area up to the new grade. When looking at the cross sections they show the full 19" of pavement structure being excavated in all areas. If this is the case, the base 1 1/4" quantity does not appear to be enough. What is the intention for the excavation in this area? | We are proposing to submit an addendum to address an error in the earthwork quantities. The intent is to establish the new grade by adding base course as indicated in the typical. In reviewing this however we have found an error in the earthwork table that will change the project from a waste project to a borrow project and we will need to change the Removing Asphaltic Surface quantity. It would be our intent to revise the earthwork table, typical section and misc. quantities. | Fred Schunke | 2 | 2020-03-04 11:29 | 2020-03-05 08:38
20200310 | 20200310021 | 21 | Design Schedule | Can you post a copy of the design schedule? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310021/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-02-05 13:02 | 2020-02-05 13:02
20200310 | 20200310021 | 21 | shaping shoulders | On sheet #34 it shows to restore shoulder to be flush with the new asphalt for the weekend, which will be lower than the existing surface. Will there be a shaping shoulder item added for this operation and what will be expectation to do with the excess material as it will need to be cut down to achieve drainage off the road and this material will contain a lot of grass | The shaping shoulders bid item will be added by addendum. The existing shoulder material may be bladed onto the shoulder foreslopes to be reused in the finished shoulder. | Mike Coleman | 2 | 2020-02-28 15:33 | 2020-03-03 07:09
20200310 | 20200310021 | 21 | Ramp work | Although it is understood that the DOT provided schedule is not for bidding purposes, There is nothing in it to accommodate the work around the ramps, nor is there any direction on traffic control to phase around them. How does the department envision this work to be done as it will take up a lot of time to fill in the "gaps" | The traffic control for the ramps shown in the plan is the typical layout for when work is not occurring directly at the ramps. The traffic control at the ramps may be adjusted following the standard detail drawings to accommodate contractor staging. Nighttime ramp closures are allowed as specified in the special provisions. | Mike Coleman | 3 | 2020-02-28 15:45 | 2020-03-03 07:09
20200310 | 20200310021 | 21 | Draintile | Is there a contingency if the pavement patches can not be removed without damaging the drain tile system | Any damage done to the underdrain system will be the responsibility of the contractor to repair at their expense. | Mike Coleman | 4 | 2020-02-28 15:49 | 2020-03-03 07:10
20200310 | 20200310021 | 21 | 4 bag base patching mix. | Will the Department consider specifying some other mix rather than a 4 bag mix? A 4 bag mix is going to slow the project down while the Contractor waits for cure times. Virtually all divided highway projects require an SHES mix. Even a HES strength mix would have a substantial benefits in reducing time to construct. The design schedule does not take into consideration the substantial cure times required for a 4 bag mix. | The Base Patching Special item states that asphaltic patching can be installed over concrete base patching after curing for 24 hours. The intent is for the patches to be rubbilized and we are not concerned if the concrete cracks prior to the rubbilizing. The contractor may choose to use a HES or SHES mix with no additional payment. | Jill Fehrman | 5 | 2020-03-08 08:38 | 2020-03-09 11:49
20200310 | 20200310022 | 22 | Temporary Markings | Good morning. Could you please elaborate more on the timing and what all of the temporary paint markings will be used for? Stage 1 appears to be for the double yellow needed for head to head as well as one edge line. Stage 2 markings would most likely be needed for the lane line skips on the different layers of asphalt but the quantities included do not necessarily add up to any combination of this. Any clarification would be appreciated. Thank you. | Stage 1 we were calling for there to be a double yellow and 1 edge line and it calls for it to be split up pre and post Memorial Day. Stage 2 we were calling for there to be 2 edge lines in the SB and also the skips on the different layers of asphalt. | Mike Coleman | 1 | 2020-02-20 10:04 | 2020-02-20 14:01
20200310 | 20200310022 | 22 | Temporary Markings | Good morning. Could you please elaborate more on the timing and what all of the temporary paint markings will be used for? Stage 1 appears to be for the double yellow needed for head to head as well as one edge line. Stage 2 markings would most likely be needed for the lane line skips on the different layers of asphalt but the quantities included do not necessarily add up to any combination of this. Any clarification would be appreciated. Thank you. | Stage 1 we were calling for there to be a double yellow and 1 edge line and it calls for it to be split up pre and post Memorial Day. Stage 2 we were calling for there to be 2 edge lines in the SB and also the skips on the different layers of asphalt. | Mike Coleman | 2 | 2020-02-20 10:04 | 2020-02-20 14:01
20200310 | 20200310022 | 22 | Temp Paint and Marking Removals | With the addendum that came out, there are some errors in the misc. quantities. the new page 51, has a temp paint quantity of 561,650' There is also a quantity for Temp Paint on old page 54 of the plans for 186,000' Which quantity is correct? The new page 54 doesn't have any temp marking items. Also, the new page 53 has all the permanent markings, where the old page 53 had marking removals, and other items. Is there still a need for removals? Will that page be added back to the misc. quantities? Addendum #1 does not show a change in temp markings, or removal items, other than the misc. Quantities of the pages noted above. Please advise | With the addendum that came out, there are some errors in the misc. quantities. the new page 51, has a temp paint quantity of 561,650' There is also a quantity for Temp Paint on old page 54 of the plans for 186,000' Which quantity is correct? The new page 54 doesn't have any temp marking items. Regarding the answer for the first question the new page 51 has a temp paint quantity of 561,650' ; we discovered that page 2 of the 022-soi.pdf document (HCCI Bid Letting information, March 10, 2020, Addenda subparagraph) is incorrect with respect to bid item 649.0105 Temporary Marking Line Paint 4-Inch, for both â€œOld Quantityâ€ (410) and for â€œRevised Quantityâ€ (487). The quantities listed on page 2 of the 022-soi.pdf document for item 649.0105 should read 186000 LF for â€œOld Quantityâ€ and should read 561650 LF for â€œRevised Quantityâ€. Regarding the statement There is also a quantity for Temp Paint on old page 54 of the plans for 186,000' Which quantity is correct? question: The correct quantity for item 649.0105 Temp Marking Line Paint 4â€ should be 561650 LF Regarding The new page 54 doesn't have any temp marking items question: â€œnewâ€ plan sheet 54 contains Construction Staking pay items. The Temp Marking items are found on page 17 of the 022-soi.pdf document, on an MQ plan sheet with the sheet number 51 in the lower RT-hand corner With respect to: Also, the new page 53 has all the permanent markings, where the old page 53 had marking removals, and other items. Is there still a need for removals? Will that page be added back to the misc. quantities? There is still a need for marking removals. The Marking Removals (items 646.9000 and 646.9010) are found on sheet 53 of the 20200310022plan.pdf plan set. With respect to: Addendum #1 does not show a change in temp markings, or removal items, other than the misc. Quantities of the pages noted above. Please advise Addendum 1 requires editing for item 649.0105 Temp Marking line Paint 4â€. No edits or changes were made to Marking Removal item 646.9000 or item 646.9010 Errors will be corrected by a future addendum. | Mike Coleman | 3 | 2020-02-20 10:43 | 2020-02-21 06:54
20200310 | 20200310022 | 22 | Tack Coat in General Notes | The second and third notes within the general notes on Sheet 2 of the plans indicates that RS-1 or RS-2 emulsified asphalt shall be used as tack coat wherever asphaltic concrete pavement abuts or overlaps Portland cement concrete, more specifically whenever the thickness of asphalt resurfacing over concrete is less than 1.5 inches. The schedule of items for the project contains the item 455.0605 Tack Coat; under spec section 455.2.5 the types of tack coat covered by the standard spec for this bid item are listed, and RS-1 and RS-2 are specifically not on that list. These emulsified asphalt products required by these two notes come at a substantial increase in cost, relative to the normal products allowed per item 455.0605. Please indicate specifically where the RS-1 & RS-2 emulsified asphalts are to be used, provide a quantify of the specialty tack to be included in the contractor's bid, and explain what item will be used to pay for the special tack coat products. | The General Notes do not apply in this case. The thickness of HMA over concrete will not be less than 1.5 inches when placed over existing concrete. | Mike Coleman | 4 | 2020-02-27 14:54 | 2020-03-02 12:51
20200310 | 20200310022 | 22 | Approach Slab Overlay Sequence | On plan sheet 28 it states to place the approach slab concrete overlay after bridge deck concrete overlay. Would it be acceptable to place the approach slab overlay with the bridge deck overlay as is typically done when feasible? | It is acceptable to place the approach slab concrete overlay concurrent with the bridge deck concrete overlay. | Mike Coleman | 5 | 2020-02-28 12:24 | 2020-03-02 12:52
20200310 | 20200310022 | 22 | B-35-63 Bridge Work Schedule | Plan sheet 37 note B states all bridge repairs on B-35-63 are to be complete prior to the 4th of July. Why can't bridge work be completed in stage 3 after 9/8/20 and prior to the contract completion date? | Bridge repairs cannot be performed after 9/8/2020 as weather begins to impact structure construction timing and quality per FDM 19-10-30. Any delays would put meeting the Completion Date in jeopardy. | Mike Coleman | 6 | 2020-02-28 12:31 | 2020-03-02 12:59
20200310 | 20200310022 | 22 | RS-1 Tack | IN the general notes it talks about using RS-1 tack for asphalt abutting to or overlaying concrete. Due to the fact that this will require a separate tack truck for the small amounts that this will be, will the region consider eliminating this note | Because all anticipated HMA thicknesses (over concrete) will exceed the 1.5â€ specified in the Note, the Note can be disregarded. At this time the Region intends on letting the Note remain. | Mike Coleman | 7 | 2020-02-28 15:56 | 2020-03-02 13:00
20200310 | 20200310022 | 22 | PWL Density | In the misc quantities it shows PWL density being applied to the lower 3MT layer for the entire length of the project. From stations 1516+00 to the south end of the project the grade being paved over is changing from rubbilized to base coarse. There is also a crown correction taking place that will result in varying thicknesses throughout this entire section. For these reasons, the PWL density should be considered to be taken out of the section. | After consulting with the Region pavement engineer and with Steve Hefel (Bureau of Technical Services), we have concluded that PWL will be applied to the lower 3MT layer for the all of USH 51 SB. The 2020 Standard Specifications, 460.3.3.1 and Table 460-3 address and confirm this decision. Rubblized concrete pavement is considered a base course. | Mike Coleman | 8 | 2020-02-28 16:00 | 2020-03-02 13:02
20200310 | 20200310022 | 22 | Base Staking | On the Construction Staking Base item that was added in the addendum, is the department going to provide the layout and the elevation for this | The Department will provide a vertical profile for USH 51 SB at the horizontal reference line of USH 51 SB as part of the contractor data packet at the time of the Pre-Con. Additionally, Department field staff will, at the start of construction, gather survey data at the high side of the horizontal curves superelevations. | Mike Coleman | 9 | 2020-02-28 16:09 | 2020-03-02 13:01
20200310 | 20200310022 | 22 | Drop-off Hazard Protection | From the north project limits for the rubblized pavement removal (Sta 1751+90) to Traffic Crossover 6 (Approx. Sta 1741+50) the plan shows Removing Asphaltic Surface and Removing the Rubblized Concrete Pavement beneath the existing HMA surface. This operation will need to happen adjacent to a live lane of traffic, as this is upstream from the first traffic crossover for bi-directional traffic. Construction of the proposed section will create a drop-off of 16.5-inches at centerline adjacent to the open lane. How does the department intend for this hazard to be addressed? Will traffic be shifted laterally to create distance from the drop off, or will temporary precast barrier be used to protect this drop-off? There appears to only be a 3-ft paved shoulder on both sides in this area. | The Departments intent is for the contractor to protect the hazard according to Std Spec 104.6 | Mike Coleman | 10 | 2020-03-02 12:50 | 2020-03-02 14:48
20200310 | 20200310022 | 22 | Drop-off Hazard Protection | From the north project limits for the rubblized pavement removal (Sta 1751+90) to Traffic Crossover 6 (Approx. Sta 1741+50) the plan shows Removing Asphaltic Surface and Removing the Rubblized Concrete Pavement beneath the existing HMA surface. This operation will need to happen adjacent to a live lane of traffic, as this is upstream from the first traffic crossover for bi-directional traffic. Construction of the proposed section will create a drop-off of 16.5-inches at centerline adjacent to the open lane. How does the department intend for this hazard to be addressed? Will traffic be shifted laterally to create distance from the drop off, or will temporary precast barrier be used to protect this drop-off? There appears to only be a 3-ft paved shoulder on both sides in this area. | The Departments intent is for the contractor to protect the hazard according to Std Spec 104.6 | Mike Coleman | 11 | 2020-03-02 12:50 | 2020-03-02 14:48
20200310 | 20200310022 | 22 | Density Test Strip for Lower Layer 3MT | Article 18, regarding HMA PWL Test Strip Density Item 460.0110.S, indicates that â€œa density test strip is required for each pavement layer placed over a specific uniform underlying materialâ€. Addendum No. 1 changed the underlying base material between Sta 1516+50 and 1751+90 from rubblized concrete to 1-1/4â€ Base Aggregate Dense. Will an additional density test strip be added for the lower layer of 3MT 58-28S over gravel, in addition to the density test strip required for paving over the rubblized concrete base? | The Region pavement engineer (Tom Nelson) and Steve Hefel (BTS) reviewed the question and said to add two more test strips (1 test strip at each end of the project) for the first lift of 3MT pavement. An addendum will be issued. | Mike Coleman | 12 | 2020-03-02 12:53 | 2020-03-03 07:13
20200310 | 20200310022 | 22 | Asphaltic Surface Temporary for Crossovers | 252 Tons of Asphaltic Surface Temporary are shown in the Miscellaneous Quantities for Traffic Crossovers XO2-XO6. There doesnâ€™t appear to be a detail showing specifically where this is to be located. However, using sheet 42 for the Interchange Access Staging, and SDD 15D07 for guidance, it might be assumed that a 12-ft widening is intended, tangent to the SB lanes to facilitate the staged pavement repairs at the exit & entrance ramps. The existing typical sections indicate that there is only a 3-ft aggregate shoulder outside of the existing SB pavement. The underlying base course doesnâ€™t appear to provide adequate width for the proposed staged widenings. Will an additional quantity of base course be added to construct these widenings? Can you provide a detail showing the proposed locations for the Temp HMA? Will there be a quantity of Common Excavation or Removing Asphaltic Surface for deconstructing any of the asphaltic surface temporary work? | Another addendum (Addenda #3) will be provided shortly to address this concern. | Mike Coleman | 13 | 2020-03-03 06:50 | 2020-03-04 06:53
20200310 | 20200310022 | 22 | Crash Cushion & Temp Barrier Staging | The Miscellaneous Quantities on sheet 51 indicates a quantity of 1 Each for temporary Crash Cushions, and 400 LF of temporary barrier wall. The location referenced for the crash cushion indicates that it will be positioned south of traffic crossover 1. Following SDD 15D05-04, it shows that the crash cushion would be placed between NB and SB traffic during the bi-directional traffic configuration, where SB traffic would be diverted from NB through the crossover to the SB lanes. When 4-lane traffic is opened on holidays, and during stage 2, the crash cushion and barrier wall will need to be removed to accommodate the NB thru-traffic. Will additional quantities for multiple installations of a crash cushion and barrier wall be added to account for the staging? | Another addendum (Addenda #3) will be provided shortly to address this concern. | Mike Coleman | 14 | 2020-03-03 06:52 | 2020-03-04 07:25
20200310 | 20200310022 | 22 | Temporary Asphaltic Surface for Crossover #1 | Quantities for Asphaltic Surface Temporary as shown in the Miscellaneous Quantities table on Sheet 45 (from Add. No. 1) indicate that Temp HMA is needed to widen for the crash cushion, but it is unclear where this is intended. The stationing references STA 13011+00 which doesnâ€™t exist. Per SDD 15D05-04 shows the crash cushion arrangement but doesnâ€™t identify where asphaltic surface temporary should be required. The Traffic Control pages and Interchange Access Staging Details on sheets 39-42 donâ€™t show where Asphaltic Surface Temporary would be needed, since an existing crossover is already in place. Can you please provide a detail showing the anticipated location and dimensions for this work? | This quantity was provided in case the manufacturer product specifications require the asphaltic surface. A detail will not be provided. | Mike Coleman | 15 | 2020-03-03 06:53 | 2020-03-04 06:52
20200310 | 20200310022 | 22 | RS-1 or RS-2 Tack Coat | Previous questions were submitted regarding this topic, but not fully clarified. Note 2 in the General Notes indicates that "RS-1 or RS-2 emulsified asphalt shall be used as tack coat wherever asphaltic concrete pavement abuts or overlaps Portland cement concrete" (REGARDLESS OF DEPTH). In accordance with spec section 455.2.5, the types of tack coat used under the standard spec for this bid item are listed, but RS-1 and RS-2 are not specifically on that list. Will there be areas of the project where RS-1 or RS-2 emulsified asphalt will be required as tack coat? If so, please provide a quantity of this product, and explain what bid item will be used to pay for that work. | Another addendum (Addenda #3) will be provided shortly to address this concern. After review with the Region pavement engineer, he determined that these two notes ( â€œWherever asphaltic concrete pavement abutsâ€¦.â€, and â€œWherever the thickness of asphaltic resurfacingâ€¦â€) on sheet 2 of the General Notes shall be removed. Therefore, usage of RS-1 and RS-2 emulsified asphalt does not apply to this project. | Mike Coleman | 16 | 2020-03-03 07:47 | 2020-03-04 07:26
20200310 | 20200310022 | 22 | Project Schedule | Can the department provide plan holders with the project schedule that was used for design and development of the project? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310022/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 17 | 2020-03-03 09:08 | 2020-03-06 06:53
20200310 | 20200310022 | 22 | Temporary Marking Line Paint 4-Inch | Can you add the miscellaneous quantities to the increase with this item? That is a big increase with no information on where it goes or a time frame. | This was addressed in the previously posted Information Requested - Questions #1 & #2, which have been re-posted below: Stage 1 we were calling for there to be a double yellow and 1 edge line and it calls for it to be split up pre and post Memorial Day. Stage 2 we were calling for there to be 2 edge lines in the SB and also the skips on the different layers of asphalt. | Mike Coleman | 18 | 2020-03-03 16:49 | 2020-03-06 06:49
20200310 | 20200310022 | 22 | Concrete Surface Repair | Plan sheet 131 (bridge plan sheet 1) states 25 SY of concrete surface repair. This item is typically by the SF. In the estimate of quantities and the bid tab it is 25 SF. Please confirm that 25 SF is the estimated quantity by the designer. | This will be addressed in an upcoming addendum. | Mike Coleman | 19 | 2020-03-04 08:39 | 2020-03-04 10:50
20200310 | 20200310022 | 22 | B-35-63 Expansion Device | There is no expansion device SPV article in the proposal. STP-502-020 includes three different approved models for a 5" strip seal. The D.S. Brown strip seal model SSA2-ASR-XTRA has a minimum joint opening of 1/2" and a minimum installation width of 2". The R.J. Watson strip seal model RJA-RJ500 is no longer produced. The Watson Bowman Acme strip seal model A-SE500 has a minimum joint opening of 0" and a minimum installation width of 2". The only approved strip seal that meets the performance requirements of the provided temperature table is the Watson Bowman Acme A-SE500, but this model has a minimum installation opening of 2", which would be achieved under 45 degrees according to the provided temperature table. Based on project schedule, installation at this temperature is unlikely. The plan has a note about small joint opening and the potential necessity to pre-install the strip seal, but this is not constructible. | Corrections to be made to Expansion Device for B-35-63 Corrections to be addressed in upcoming Addendum 3 | Mike Coleman | 20 | 2020-03-04 10:10 | 2020-03-05 09:20
20200310 | 20200310022 | 22 | Temporary Pavement Markings & Removals | What is the 88,000 LF of item 646.9010, Marking Removal Line Water Blasting 4-Inch, intended for? The miscellaneous quantities indicate that this is for the NB Lanes, after Stage 1. It appears that the 88,000 LF would account for removal approx. 44,000 LF of the temporary double yellow centerline from the bi-directional configuration without permanent scarring of the concrete pavement to remain. However, there are no quantities shown for removal of the double yellow line for the Memorial Day holiday weekend, or for the end of the project after Stage 3. Will the Department allow the solid double yellow centerlines to remain in place over the holiday weekends during the short timeframes when the NB side must be open to 2 lanes of NB traffic? | This item applies USH 51 North Bound (NB) pavement marking. This is when the NB roadway has been modified & repainted to accommodate the counter-directional traffic flow (one-lane NB, and one-lane SB) and when the USH 51 South Bound (SB) roadway is closed to traffic and under closed road construction. This is for removal of the existing (pre-construction) pavement marking prior to counter-directional traffic on the NB roadway. The time frame is dependent on the prime contractors staging of work activities on a closed USH 51 SB roadway. | Mike Coleman | 21 | 2020-03-04 14:26 | 2020-03-06 07:39
20200310 | 20200310022 | 22 | HMA over culvert pipes | Would the department consider changing the lower layers of HMA paving over the culvert pipes and transitions from PWL to QMP in order to allow the culvert installation work to happen prior to the completion of a PWL Test Strip? | This answer has been revised. The plans are being left as is. If the contractor wants to do something with temporary asphalt, we can work it out with them during construction. | Fred Schunke | 22 | 2020-03-04 17:14 | 2020-03-05 13:48
20200310 | 20200310022 | 22 | Bridge Deck Cleaning | Is there an existing polymer chip seal overlay on the deck? | Yes. The two-layer, two-component epoxy overlay was installed in the fall of 2009 under project 1176-06-60, contract 20090609037 | Fred Schunke | 23 | 2020-03-05 11:33 | 2020-03-05 13:46
20200310 | 20200310022 | 22 | Temp paint did not answer the question | You added 375,650LF of paint with no miscellaneous quantities, are we supposed to guess how much is on each area of work? Trips? How much of it will be removed? ETC? |  |  | 24 | 2020-03-06 09:49
20200310 | 20200310023 | 23 | B-58-60 Removal Quantity | Removing Concrete Masonry Deck Overlay B-58-60 item quantity is 100 SY. The plan details a 47' 10 3/4" x 2' area for this item. Quantity appears to be overstated. | The area was calculated in SF instead of SY. This will be corrected to 11 SY on an upcoming addendum. | Mike Coleman | 1 | 2020-02-28 11:55 | 2020-03-02 14:40
20200310 | 20200310023 | 23 | B-68-30 Concrete Removal Saw Cut | Note on structure plan indicates a saw cut is required at the removal limits of the concrete deck overlay removal. How is this paid for? | The sawing is incidental to the concrete removal. This will be made clear on the structure plan in an upcoming addendum. | Mike Coleman | 2 | 2020-02-28 12:06 | 2020-03-02 14:41
20200310 | 20200310023 | 23 | 3LT lower lift in 6.25" pavement sections | The widening areas where the pavement thickness is 6.25â€ should be constructed weeks prior to constructing the 3LT test strip and the first layer over the base is not representative of mainline construction which the test strip represents. Can the in 1st layer (approximately 1500 tons) be constructed as asphaltic surface or under an added QMP item? | We agree with this suggestion as it will eliminate issues with test strips in the field for these widening areas. We are planning to issue an addendum ASAP to move this tonnage under a QMP item. | Mike Coleman | 3 | 2020-02-28 12:55 | 2020-03-02 14:47
20200310 | 20200310023 | 23 | covering milled surface | Under the prosecution and progress in the special provisions it states, â€œPlace the lower layer of HMA pavement the on the same working day as the milling operations.â€ It also states, â€œDuring non-working hours, adjacent travel lanes must be at the same elevation.â€ Why is the standard 72 hours to cover the milled surface with a notched wedge longitudinal joint per 450.3.2.8 not being applied in this instance? In addition, it will be costly and unsafe as you are milling 4â€ and only placing 2.25â€ of 3LT. Setting back during the middle of the day is a large safety issue due to having multiple operations in opposing lanes at the same time. | We coordinated the provisions with the Region during design. I followed up today with the Region to reconfirm and we will agree to revise the second requirement since the release of the 2020 specs will satisfy the project needs. â€¢ Due to a deep mill and thin remaining pavement, the lower layer of HMA pavement will need to be placed in the same working day as the milling operations. Do not run traffic on milled surfaces. â€¢ Regarding the elevation for adjacent travel lanes, the special provision will be removed and requirements will follow standard spec 104. We will include this in the addendum. | Mike Coleman | 4 | 2020-03-02 13:49 | 2020-03-03 07:12
20200310 | 20200310023 | 23 | B-58-60 Concrete Staining | Plan note on sheet 296 states to stain with TK 26 White. SPV article 35 indicates the parapets are to be sack rubbed, and does not list TK 26 White under the concrete staining materials list. Are the parapets to be sack rubbed and which stain is to be used. | â€¢ The repair work on the parapet should be sacked rub to finish it per the special provision. â€¢ The structure plans indicates the required staining product (TK 26 White) or approved equal and this should be followed for bidding. Follow up on staining special: â€¢ While the special provision has some of the approved equals including TK products, it doesnâ€™t list the requested specific TK26 White product in specials since this was added late in during final BOS review. After further review online, the TK 26 isnâ€™t covered under the specific TK options covered in the STSP. Clarification to the special provisions via a short addendum is proposed to avoid a CCO. | Mike Coleman | 5 | 2020-03-04 12:58 | 2020-03-05 06:17
20200310 | 20200310023 | 23 | Culvert Replacements | Per SP "upon completion of each culvert pipe installation, patch travel lanes with asphaltic surface prior to reopening STH 47 to traffic". Culvert replacements also include Transition Cuts and whole operations would not be completed in one day. Could traffic be allowed on gravel surface graded flush overnight until culvert installation and transition cut is done? | Due to traffic volumes and importance of this roadway, complete the culvert work in a continuous operation and run traffic on a paved surface once the culvert is completed per the special provisions. | Fred Schunke | 6 | 2020-03-04 14:33 | 2020-03-05 10:43
20200310 | 20200310023 | 23 | Transition Cut backfill | Notes for Transition Cut says that trench backfill used in transition cut area is incidental to pipe installation per spec 520. Spec 520 allows the use of material from the excavation that is free of large lumps, clods, rocks and other perishable and deleterious matter. If the engineer determines that material from the excavation is not suitable, backfill the trench with an engineer-approved material. What would be an engineer approved material, should item of select borrow of granular backfill be added to the project? | Per the construction detail on Page 26 of the plans, Trench Backfill And Foundation Backfill Used In Transition Cut Area Is Incidental To Pipe Installation (Per Std Spec 520) The predominant soil types along the project are loamy sands and fine sandy loams. Standard specification 520.5.2 will prevail if the material is not suitable. No new items are proposed to be added. | Fred Schunke | 7 | 2020-03-04 14:37 | 2020-03-05 10:55
20200310 | 20200310023 | 23 | Storm Sewer Backfill | Storm sewer for this project will be installed outside of the roadway. As a cost saving measure for Department, should the standard spec 608.2.2.3 Trench Backfill be waved and trench allowed to be backfilled with native materials? | Bid the storm sewer backfill per standard specs. Any cost saving measures can be determined in the field. No borings were completed in the area of the exact pipe location to determine if the material meets required specifications and the contractor should bid the backfill per specs. | Fred Schunke | 8 | 2020-03-04 14:43 | 2020-03-05 10:58
20200310 | 20200310023 | 23 | Transition Cut Backfill Question 7 | In reply to the answer on Question 7 Standard Spec 520.5.2 states"If material from the typical roadway section is not suitable for trench backfill, the department will pay separately for trench backfill under other contract bid items. (3) The department will pay separately for excavating unsuitable material and backfilling as specified in 520.3.2.1(10) as extra work" Does it mean that CCO will be issued for excavation and backfilling transition cut if materials are not suitable? | If the existing material is deemed not suitable for trench backfill by the field staff, replacement material will meet the requirements for trench backfill as stated in standard specification 520. Any additional payment for providing suitable materials will be handled in the field per standard specifications. | Fred Schunke | 9 | 2020-03-05 11:11 | 2020-03-05 13:35
20200310 | 20200310024 | 24 | Railing Elevation | There are no vertical dimensions listed for railing members on the typical railing elevation. Please confirm the railing will follow the WisDOT Standard Detail for Combination Rail Type C3. | Yes, the railing should follow the WisDOT Standard Detail for Combination Rail Type C3. | Mike Coleman | 1 | 2020-02-20 13:57 | 2020-02-21 06:51
20200310 | 20200310024 | 24 | Seed Water | Please verify the quantity of Seed Water for this project. 140,000 gallons seems high for 8 lbs of seed. | An addendum will be issued to correct this. | Mike Coleman | 2 | 2020-02-27 11:22 | 2020-03-02 06:56
20200310 | 20200310025 | 25 | Structure plan missing | The structure plan is missing from the plan set for this project. | An addendum is being issued to add the missing structure plans. The full-size plan set can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310025/ | Mike Coleman | 1 | 2020-02-05 09:18 | 2020-02-18 08:16
20200310 | 20200310026 | 26 | Excavation Common and Select Crushed | There are quantities labeled as EBS for Excavation Common and Select Crushed. Are these quantities undistributed? Do you feel the quantities will be used? Can you provide a construction detail for this work? | It is anticipated that the bid items will be used however the amount is undetermined. An addendum will be issued to add the construction detail. | Mike Coleman | 1 | 2020-02-25 09:26 | 2020-02-26 12:52
20200310 | 20200310026 | 26 | Sawing | I see removing of curb & gutter and also sidewalk removal but no sawing quantity. Will there be a sawing item added? | An addendum will be coming on a sawing item. | Mike Coleman | 2 | 2020-03-02 15:33 | 2020-03-04 07:01
20200310 | 20200310026 | 26 | SPV.0195 Base Course Stabilization Oil | The proposal specifies standard spec 455.2.4.3 and AASHTO M140 for anionic emulsified asphalts for the material on item SPV.0195. Standard spec 455.2.4.3 and AASHTO M140 cover all anionic emulsified asphalt, approximately 15 grades, which grade should be used? | Please use Emulsified Asphalt Grade SS-1 as specified in AASHTO M140. | Mike Coleman | 3 | 2020-03-03 15:42 | 2020-03-05 11:31
20200310 | 20200310028 | 28 | Soil Borings | are soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310028/ | Mike Coleman | 1 | 2020-02-19 12:00 | 2020-02-20 07:19
20200310 | 20200310028 | 28 | Pile Design | Canthe geotechnical engineer provide the following information so that we are able to perform a â€œL-Pileâ€ analysis. - Per the boring profiles, provide the â€œL-Pileâ€ soil model for each layer, (i.e. soft clay (Matlock), sand (Reese), etc.) - For each soil layer or model please provide the following information if applicable, effective unit weight, friction angle, undrained cohesion, strain factor (E50), and subgrade modulus â€œkâ€. | The design of this structure did not require the determination of the requested values, however they can be derived from the geotechnical report and soil borings. It is our understanding that the geotechnical report has already been provided to bidders, and the soil borings are included in both the geotech report and contract documents. The Geotech report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310028/ | Mike Coleman | 2 | 2020-02-26 08:58 | 2020-02-27 07:07
20200310 | 20200310028 | 28 | Traffic control barricades Type 3 | wondering if the number of t3 days needs to be higher. Maybe the barricades for the closure at the culvert were not included? | Bid the Type 3 Barricade concern according to the PSE package provided. | Mike Coleman | 3 | 2020-03-02 10:01 | 2020-03-02 14:48
20200310 | 20200310028 | 28 | Common Excavation | Earthwork Quantity shows 500cy of Culvert Pipe Transition Common Excavation. Is there a typical section available for this work? | No typical section is available. There is a construction detail in the plan for guidance. | Fred Schunke | 4 | 2020-03-03 13:38 | 2020-03-05 13:36
20200310 | 20200310028 | 28 | Temporary Diversion Channel | Is there stream flows available for calculating necessary pipe sizing to be used in the diversion channel? | Flow rates for the stream are provided on Sheet 55 of the Plan (Structures Plan sheet 1 of 10), and the stream flow rate data is available under the Hydraulic Data text box given on this sheet. Using this flow rate data, it is the contractorâ€™s responsible for determining the proper size of the water diversion device discussed in the â€œTemporary Water Diversionâ€ article of the project special provisions. | Fred Schunke | 5 | 2020-03-03 13:45 | 2020-03-05 13:37
20200310 | 20200310028 | 28 | Earthwork Table Clarification | The information on sheet 65 and the earthwork table on sheet 14 don't seem to match. Is there a possibility that you can clarify the information including useable fill, and waste if any? |  |  | 6 | 2020-03-04 09:29
20200310 | 20200310030 | 30 | Shaping Shoulders | There is not a shaping shoulders item. With the milling item there will be shoulder material that needs to be pushed back to allow water to drain off of the road as well as a need for shoulder material to be pulled up to the edge of the leveling and upper areas to protect the traveling public from edge drop off. | This contract requires paving an additional two feet of the existing 7â€™ aggregate shoulder. The finished typical for the shoulder will be 5 foot paved, 5 foot aggregate. Item 211.0400, Preparation of foundation for Asphaltic shoulders is called out in the plans for construction of this work. This item covers all necessary shaping of the existing aggregate shoulder as you mention below and as is specified in 211.3.5.1 &2 of the standard specs. Additional contract items will not be added or required due to contractor means and methods. Additional shoulder shaping for drainage is covered in 204.3.2.2.2 (5) | Mike Coleman | 1 | 2020-02-20 12:10 | 2020-02-21 06:57
20200310 | 20200310030 | 30 | Milling Concrete Curb & Gutter | Milling the concrete curb & gutter is incidental to the removing asphaltic surface milling item. Two points. Having items such as milling concrete curb & gutter incidental to the milling item increases the unit price for the milling item which skews the evaluation of this item with historical bid unit prices. We would suggest adding an item for milling the concrete curb and gutter. Also not all concrete curb & gutter is getting milled. We would suggest for consistency and overall appearance and performance that all the concrete curb & gutter be milled. | The project design engineer has observed gutter conditions that require maintenance. For safety (loose or missing debris) and drainage reasons some of the gutters will need to be covered with HMA pavement. To meet lines and grades the gutter will need to be milled as is noted on the plans. This is a relatively small percentage of the existing gutters within the project limits. Exact locations of gutter mill and overlay is best determined by the engineer in the field based on conditions observed at the time of construction. Much of the gutters are in good condition and do not require the additional treatment and money spent. In the absence of a standard item for milling gutters, this work is most closely related, similar to, and completed with the same operation and machinery as Removing Asphaltic Surface Milling. The deteriorated gutter sections provide the same or less resistance wear on the teeth of the milling machine. I am not convinced of any statistically significant price skews for this work. Historically, it has been requested in places and done without complaint. The standard Special item of Removing concrete surface Partial Depth is more related to milling concrete pavements and requires more control and specialized equipment. | Mike Coleman | 2 | 2020-02-20 12:14 | 2020-02-21 07:00
20200310 | 20200310030 | 30 | Asphalt Ramping | Sheet 3 of the plans. General Notes Line 16. Ramps shall be paved when the difference between the existing surface and milled surface is greater than 2" and is incidental to paving. Sheet 19 of the plans. Notes Line 3. â€¦..Asphaltic Surface Patching required for temp butt joints and will be paid for separately. Conflicting statements. We feel the department should pay for any and all ramping required for safe transition of the traveling public. | While there are known locations of required ramping/wedging (begin/end project, and bridge approaches) the vast majority of ramping will be dictated by the contractors means, methods, and progress. Ramps or transition milling will be required at the end of each dayâ€™s work. A days work can be dictated by weather, equipment breakdowns, work hours, etc. The quantity for ramping would vary wildly and could lead to abuse. Differences of 2 inches or greater are addressed in 204.3.2.2.2. We will eliminate the statement â€œAsphaltic Surface Patching required for temporary butt joint ramps or wedges will be paid for separately. â€œ from sheet 19 in the plans. And replace it with the statement â€œ Ramps shall be paved when the difference between the existing surface and milled surface is greater than 2 inches, and is incidental to the item of Milling. | Mike Coleman | 3 | 2020-02-20 12:18 | 2020-02-24 07:12
20200310 | 20200310030 | 30 | Turn Lane Shoulder HMA Paving Density | Sheet 36 of the plans. Density Acceptance Medians, Shoulders and Turn Lanes. Acceptance testing by the department; not eligible for incentive. We do not feel it is fair to test material with only the opportunity for disincentive. This practice will ultimately lead the contractor to add penalty to their unit prices to mitigate there risk. This is a lose for the department. | This project uses the standard statewide special provision for HMA pavement Percent Within Limits(PWL) QMP. Any concerns with this specification need to be brought to Steve Hefel in the Bureau of Technical Services at the following address: Steve Hefel, P.E. HMA Supervisor Bureau of Technical Services Wisconsin Department of Transportation 3502 Kinsman Blvd, Madison, WI 53704 608-246-7934 office 608-572-0891 cell Steven.Hefel@dot.wi.gov | Mike Coleman | 4 | 2020-02-20 12:22 | 2020-02-24 07:12
20200310 | 20200310030 | 30 | 3/4 inch Dense Aggregate Base | This item appears to be overstated. Our take-off is +- 50% of plan quantity. | Calculations for this item have been rechecked and the plan quantity is correct. Your calculations could be missing the fact that 2 feet of existing (4% cross slope) gravel shoulder will be paved at a 2% cross slope. This in effect, raises the entire finished gravel shoulder by 0.5 inches in addition to the 1.5â€ overall grade raise of the profile. The material generated by the excavation of that two feet by 1.75 inch area (Prep of foundation for asphaltic shoulders) is not accounted for in the typical rather it is assumed this material will restore the low shoulders to original grade. | Mike Coleman | 5 | 2020-02-20 12:23 | 2020-02-24 07:13
20200310 | 20200310030 | 30 | HMA Pavement for Culvert Patches | Is there a detail for the thickness of this patching? | There is not a detail for the one culvert needing repair. Existing adjacent pavement layer thicknesses from the plan typical sections will be matched with a couple exceptions. Base Aggregate Dense 1 ¼ inch will be used in place of the open graded material shown. Material excavated from below the gravel base layer shall be reused in backfilling. | Mike Coleman | 6 | 2020-02-20 12:24 | 2020-02-24 07:20
20200310 | 20200310030 | 30 | New Procedures | DOT has new procedures for longitudinal joints utilizing the notched wedge joint. This project as the special provision for Milling and Removing Temp Joint. Any interest from the department to eliminate this item and utilize the notched wedge? If the department keeps the remove temp joint item will the department be paying for the removed material. Also the department is eliminate the usage of the longitudinal joint heater. Is this something that would be consider for this project as well. | Iâ€™ve discussed this item with our Regional Pavement Engineer Devin Harings. The Reheating HMA Pavement Longitudinal Joints and the Special Milling and Removing Temporary Joint bid items are acceptable for this project and no changes are needed. However, my understanding is that beginning with February PS&E projects, these two items will no longer be used and the HMA Pavement Longitudinal Joint Density SPV and the associated incentive/disincentive item will be required for PWL projects. A wedge joint (notched or tapered) will be required for the HMA surface layer unless the contractor matches up daily. Consequently, the joint heater and joint milling will also be required. We are NOT ready with this project to implement the Joint density and incentive/disincentive items. Historically, the department has not made any deductions in HMA quantity for the milling removal of the wedge joint material. | Mike Coleman | 7 | 2020-02-20 12:27 | 2020-02-24 07:21
20200310 | 20200310030 | 30 | Traffic | Lane Closures shall not exceed 3/4 of a mile in length. Temperature is a key component to the manufacturing and laydown/compaction of hot mix asphalt. Which directly relates to the time required to keep traffic off of the newly paved hot mix. Limiting the lane closure to this distance will directly affect the production which will increase the laydown costs. The department as SDD 15c12-07 Traffic Control for Lane Closure with Flagging Operation. Under Flagging, 2nd paragraph When the distance between flaggers exceeds 2 miles, a pilot car is required. What makes this job different? We need room to work as well as allow tack coat to set so we don't track, allow laydown and compaction room as well as room for the density technician to completer there work. | USH 8 is a significant corridor in the NW region with heavy traffic volumes. Flagging operations cause traffic delay which can produce undesirable and unsafe traffic conditions. By limiting the flagging work zone we can also limit the amount of traffic delay. A balance must achieved for our highway projects. For this corridor a ¾ mile maximum flagged work zone was selected to limit excessive traffic delays and long vehicle ques. It is anticipated that, the engineer in the field will assess traffic delay on the project and allow longer work zones if conditions are favorable. This is not a new specification. Most other Northwest region paving contracts have included limits to flagged work zones. | Mike Coleman | 8 | 2020-02-20 12:37 | 2020-02-24 07:22
20200310 | 20200310031 | 31 | Shaping Shoulders | There is a shaping shoulders item however does not include quantity for the entire project. The items shows a remark to remove accumulated sediment along B.G. Is Shaping Shoulders the item for this? Would an excavation item for excavating and hauling excess material be a better chose. Also, this project is a milling project where aggregate shouldering material will need to be pushed away to allow water to flow off of the road as well as pull up this existing aggregate material to the leveling and upper layers to provide a safe shoulder for the traveling public. Therefore we feel the quantity should be increased for the entire job and an new item added to address the sediment at the beam guard areas. | The item of Shaping Shoulders is needed for this short segment of USH 8. The shoulder is already paved full width so no additional shoulder pavement will be added and the item of Preparation of Foundation for asphaltic Shoulders not needed. In the absence of this item, Shaping Shoulders is needed to blade shape and compact the existing shoulder and incorporate the excess material into the existing shoulder. Both items are fairly similar, and a typical mill resurface project will call for one or the other but not both for the same segment of roadway. As you have mentioned below, â€œShouldering material will need to be pushed away to allow water to flow off of the roadâ€¦â€¦â€¦â€ this is already covered under the item of removing asphaltic surface milling in 204.3.2.2.2(5) of the standard spec. Pulling up or pre-shouldering is a contractor means and methods issue that should not require additional contract items or dollars. | Mike Coleman | 1 | 2020-02-20 12:42 | 2020-02-24 07:40
20200310 | 20200310031 | 31 | Milling Concrete Curb & Gutter | Milling the concrete curb & gutter is incidental to the removing asphaltic surface milling item. Two points. Having items such as milling concrete curb & gutter incidental to the milling item increases the unit price for the milling item which skews the evaluation of this item with historical bid unit prices. We would suggest adding an item for milling the concrete curb and gutter. Also not all concrete curb & gutter is getting milled. We would suggest for consistency and overall appearance and performance that all the concrete curb & gutter be milled. | The project design engineer has observed gutter conditions that require maintenance. For safety (loose or missing debris) and drainage reasons some of the gutters will need to be covered with HMA pavement. To meet lines and grades the gutter will need to be milled as is noted on the plans. This is a relatively small percentage of the existing gutters within the project limits. Exact locations of gutter mill and overlay is best determined by the engineer in the field based on conditions observed at the time of construction. Much of the gutters are in good condition and do not require the additional treatment and money spent. In the absence of a standard item for milling gutters, this work is most closely related, similar to, and completed with the same operation and machinery as Removing Asphaltic Surface Milling. The deteriorated gutter sections provide the same or less resistance wear on the teeth of the milling machine. I am not convinced of any statistically significant price skews for this work. Historically, it has been requested in places and done without complaint. The standard Special item of Removing concrete surface Partial Depth is more related to milling concrete pavements and requires more control and specialized equipment. | Mike Coleman | 2 | 2020-02-20 12:43 | 2020-02-24 07:41
20200310 | 20200310031 | 31 | Special Driveway | At approximately station 1273+00 right, there is a note specifying asphaltic millings to be placed in lieu of aggregate base course. There is not item that compensates the contractor for this work. There should be a salavage asphaltic milling item paid by the ton that will compensate the contractor to load, scale, haul and place this material. | Yes, an item for salvaging the pavement has been used in the past to obtain reclaimed asphalt for project use. Usually this has been instances where a significant amount is required to be re-used on the project. The need for reclaimed asphalt on this project is very small. We will add a provision modification to the standard item of CABC ¾ inch for this project. It will require the substitution of reclaimed asphalt where noted on the plans. Measurement will be based on material volume in the truck and converted to weight by a factor of 1.3 Tons/CY. No material testing will be required. | Mike Coleman | 3 | 2020-02-20 12:46 | 2020-02-24 12:15
20200310 | 20200310031 | 31 | HMA Ramping | Sheet 3 of the plans. General Notes Line 16. Ramps shall be paved when the difference between the existing surface and milled surface is greater than 2" and is incidental to paving. We feel the department should pay for any and all ramping required for safe transition of the traveling public | While there are known locations of required ramping/wedging (begin/end project, and bridge approaches) the vast majority of ramping will be dictated by the contractors means, methods, and progress. Ramps or transition milling will be required at the end of each dayâ€™s work. A days work can be dictated by weather, equipment breakdowns, work hours, etc. The quantity for ramping would vary wildly and could lead to abuse. Differences of 2 inches or greater are addressed in 204.3.2.2.2. Ramps shall be paved when the difference between the existing surface and milled surface is greater than 2 inches, and is incidental to the item of Milling. | Mike Coleman | 4 | 2020-02-20 12:47 | 2020-02-24 07:41
20200310 | 20200310031 | 31 | HMA Pavement Density Incentive | Sheet 31 of the plans. Density Acceptance Medians, Shoulders and Turn Lanes. Acceptance testing by the department; not eligible for incentive. We do not feel it is fair to test material with only the opportunity for disincentive. This practice will ultimately lead the contractor to add penalty to their unit prices to mitigate there risk. This is a lose for the department. | Here is the specification language addressing his question. It is not up for debate. This is the specification. From the PWL STSP: Exclusions such as shoulders and appurtenances shall be tested and recorded in accordance with CMM 8-15. However, all acceptance testing of shoulders and appurtenances will be conducted by the department, and average lot (daily) densities must conform to standard spec Table 460-3. No density incentive or disincentive will be applied to shoulders or appurtenances. Offsets will not be applied to nuclear density gauge readings for shoulders or appurtenances. Unacceptable shoulder material will be handled according to standard spec 460.3.3.1 and CMM 8-15.11. | Mike Coleman | 5 | 2020-02-20 12:48 | 2020-02-24 07:43
20200310 | 20200310031 | 31 | 3/4" Dense Base | This item appears to be overstated. Our take-off is +- 50% of plan quantity. | Calculations for this item have been rechecked and the plan quantity is correct. Your calculations could be missing the fact that 2 feet of existing (4% cross slope) gravel shoulder will be paved at a 2% cross slope. This in effect, raises the entire finished gravel shoulder by 0.5 inches in addition to the 1.5â€ overall grade raise of the profile. The material generated by the excavation of that two feet by 1.75 inch area (Prep of foundation for asphaltic shoulders) is not accounted for in the typical rather it is assumed this material will restore the low shoulders to original grade. | Mike Coleman | 6 | 2020-02-20 12:49 | 2020-02-24 07:44
20200310 | 20200310031 | 31 | New Procedures | DOT has new procedures for longitudinal joints utilizing the notched wedge joint. This project as the special provision for Milling and Removing Temp Joint. Any interest from the department to eliminate this item and utilize the notched wedge? If the department keeps the remove temp joint item will the department be paying for the removed material. Also the department is eliminate the usage of the longitudinal joint heater. Is this something that would be consider for this project as well. | Iâ€™ve discussed this item with our Regional Pavement Engineer Devin Harings. The Reheating HMA Pavement Longitudinal Joints and the Special Milling and Removing Temporary Joint bid items are acceptable for this project and no changes are needed. However, my understanding is that beginning with February PS&E projects, these two items will no longer be used and the HMA Pavement Longitudinal Joint Density SPV and the associated incentive/disincentive item will be required for PWL projects. A wedge joint (notched or tapered) will be required for the HMA surface layer unless the contractor matches up daily. Consequently, the joint heater and joint milling will also be required. We are NOT ready with this project to implement the Joint density and incentive/disincentive items. Historically, the department has not made any deductions in HMA quantity for the milling removal of the wedge joint material. | Mike Coleman | 7 | 2020-02-20 12:49 | 2020-02-24 07:44
20200310 | 20200310031 | 31 | Traffic | Lane Closures shall not exceed 3/4 of a mile in length. Temperature is a key component to the manufacturing and laydown/compaction of hot mix asphalt. Which directly relates to the time required to keep traffic off of the newly paved hot mix. Limiting the lane closure to this distance will directly affect the production which will increase the laydown costs. The department as SDD 15c12-07 Traffic Control for Lane Closure with Flagging Operation. Under Flagging, 2nd paragraph When the distance between flaggers exceeds 2 miles, a pilot car is required. What makes this job different? We need room to work as well as allow tack coat to set so we don't track, allow laydown and compaction room as well as room for the density technician to completer there work. | USH 8 is a significant corridor in the NW region with heavy traffic volumes. Flagging operations cause traffic delay which can produce undesirable and unsafe traffic conditions. By limiting the flagging work zone we can also limit the amount of traffic delay. A balance must achieved for our highway projects. For this corridor a ¾ mile maximum flagged work zone was selected to limit excessive traffic delays and long vehicle ques. It is anticipated that, the engineer in the field will assess traffic delay on the project and allow longer work zones if conditions are favorable. This is not a new specification. Most other Northwest region paving contracts have included limits to flagged work zones. | Mike Coleman | 8 | 2020-02-20 12:50 | 2020-02-24 07:44
20200310 | 20200310031 | 31 | Prosecution and Progress | 4th paragraph. Begin after HMA paving work is substantially completed on WisDOT 1570-00-74/77. This statement could prohibit the department from lower unit prices through effective utilization of dump trucks by hauling hot mix to one project and millings from another project, or having to paving operations from separate facilities going at the same time. The RAB's in Turtle Lake make a natural buffer between the two projects. We feel the department should eliminate this requirement. | This statement was meant to prevent both projects from being constructed at the same time independently. The nodal traffic delay on USH 8 for construction of these two projects simultaneously would not be acceptable. The time analysis for the work involved shows that the two projects can be done (milling and paving) in succession without issue during the 2020 construction season. Milling of the second project can begin prior to paving completion on the first, to create a seamless progression of the work from west to east or vice versa. Work on other items not related to milling and paving and that do not create a traffic delay (flagging operation) can be completed concurrently. | Mike Coleman | 9 | 2020-02-20 12:54 | 2020-02-24 14:11
20200310 | 20200310032 | 32 | Soil Borings | Are there soil borings available? | There are. Soil boring data is included with the structure plans in the plan. | Mike Coleman | 1 | 2020-02-19 08:19 | 2020-02-20 07:52
20200310 | 20200310033 | 33 | Will steel pipe be allowed for the Culvert Pipe Class IV items? | If so, what thickness will be required? | Yes, the Standard Specifications will allow steel pipe for the Culvert Pipe Class IV items (see Standard Spec 520.2.1, TABLE 520-1 ALLOWABLE MATERIALS FOR CULVERT PIPE. https://wisconsindot.gov/rdwy/stndspec/ss-05-20.pdf). Wall thickness for steel Class IV pipes 12â€-24â€ in diameter shall be 0.064â€, and wall thickness for steel Class IV pipes 30â€-36â€ in diameter shall be 0.079â€ (see Facilities Development Manual 13-1 Attachment 25.2 Fill Height Table-Corrugated Steel, Aluminum, Polyethylene, Polypropylene and Reinforced Concrete Pipe, HS20 Loading, 2- 2/3in x 1/2in Corrugations. https://wisconsindot.gov/rdwy/fdm/fd-13-01-att.pdf#fd13-1a15.1). | Mike Coleman | 1 | 2020-02-18 15:59 | 2020-02-24 07:07
20200310 | 20200310033 | 33 | Soil Borings | Are there soil borings available? | No soil borings are available. | Mike Coleman | 2 | 2020-02-19 08:20 | 2020-02-24 07:08
20200310 | 20200310033 | 33 | Pavement Markings - 2 part question | Part 1 - Looking at the quantities for the temporary 4" paint item, it looks like it is double what is needed. Page 2 of 29 of the proposal under Section 3 prosecution and progress states that the milled areas must be repaved the same days as the initial milling. Therefore the temp paint is only needed on the lower layer. The same day epoxy will be used on the surface layer prior to rumbles being installed, then the regular 4" epoxy item on top of the rumbles. Part 2 - if part 1 is correct, what is the departments plan for the edge lines? There are no quantities for the white edge lines. Is the department looking to use Wet Reflective Edge lines like other projects that are similar to this? Please advise. Thank you. | Response to Part 1: It is assumed that the binder lift will require a double application of temporary pavement marking due to the narrow lane width. First application will be placed on centerline of binder and second application will be placed after first lane of surface is applied and offset from the wedge joint on binder to allow for single lane paving of surface lift. Response to Part 2: Quantity for edge lines utilizing marking lines epoxy 4-inch added to project quantities. | Mike Coleman | 3 | 2020-02-20 14:14 | 2020-02-27 07:11
20200310 | 20200310033 | 33 | Ditch Cleaning | Will the salvaged topsoil, seed, fertilizer, and erosion mat be paid separately as shown in the misc quantities? If not, could the ditching item be paid by the linear foot considering one of the ditch cleanings is 1000' long? | See Standard Specification 105.4. Cleaning Ditch will be paid by the EACH. Salvaged topsoil, seed, fertilizer, and mulch required for cleaning ditches will be incidental to the CLEANING DITCH (EACH) item as detailed in the Special Provisions. If required as determined by the engineer, erosion mat will be paid separately as noted in the miscellaneous quantities. | Mike Coleman | 4 | 2020-03-05 09:56 | 2020-03-06 08:31
20200310 | 20200310036 | 36 | Soil Borings | Are there soil borings available? | No geotechnical exploration was performed. | Mike Coleman | 1 | 2020-02-19 08:20 | 2020-02-20 07:26
20200310 | 20200310038 | 38 | Soil Borings | Are there soil borings available? | No soil borings are available for this project. | Mike Coleman | 1 | 2020-02-19 08:20 | 2020-02-20 07:51
20200310 | 20200310038 | 38 | Temporary Markings | Good afternoon, in looking at this project, it appears the road is open during construction which would indicate the potential need for temporary markings on the milled surface, the lower layer, and the upper layer so that the roadway is safe for the traveling public. Is this something the department will issue an addendum for or is it the intent to use no center stripe signs as part of the traffic control bid item? Thank you. | An addendum will be issued to address these items. | Mike Coleman | 2 | 2020-02-24 14:40 | 2020-02-26 07:02
20200310 | 20200310038 | 38 | Pavement Markings | Good morning and thank you for addressing the temporary markings needed for the lower layer. What is the plan for the markings that will need to be placed on the surface layer after each days paving run? On similar projects, a same day item is included for this purpose. Will the agency be issuing an addendum to address the same day surface markings? Thank you. | â€˜No Centerlineâ€™ traffic control signs were added in a previous addendum to capture the couple of periods pavement markings could not or would not be installed immediately after a construction operation. These periods include after the pavement is pulverized and when surface layer is placed. | Mike Coleman | 3 | 2020-02-28 09:20 | 2020-03-02 12:56
20200310 | 20200310039 | 39 | Soil Borings | Are there soil borings available? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200310039/ | Mike Coleman | 1 | 2020-02-19 08:21 | 2020-02-20 07:25
20200310 | 20200310041 | 41 | 4" Bid Item Quantity | The bid item for 4" Epoxy has a total of 1,332,929 in the proposal, and a total of 1,534,204 in the misc. quantities and EOQ. Will there be an addendum to correct the bid item quantity? | An addendum will be issued to correct the quantity. | Mike Coleman | 1 | 2020-02-18 16:33 | 2020-02-19 08:18
20200310 | 20200310041 | 41 | 8" Epoxy Quantity | The 8" Bid item quantity has a totla of 43,812 in the proposal and 54,594' in the mis. quantities, and EOQ. Will there be an addendum to correct the bid item quantity? | An addendum will be issued to correct the quantity. | Mike Coleman | 2 | 2020-02-18 16:50 | 2020-02-19 08:19
20200310 | 20200310021 | 21 | Base Patching Concrete | Base Patching Concrete Special Provisions states, Cure exposed patches as specified for concrete pavement in standard spec 415.3.12. Use wax-based curing compound conforming to standard spec 501.2.9. Protect as specified for concrete pavement in standard spec 415.3.14. Asphaltic patching can be installed over concrete base patching after curing for 24 hours. Is there a strength requirement on the base Patches before allowing the installation of the Asphalt? | No. Since the intent is for the concrete patch to be rubbilized anyway, we are not concerned if the concrete cracks prior to rubbilizing. | Jill Fehrman | 6 | 2020-03-09 11:51 | 2020-03-09 11:55
20200310 | 20200310021 | 21 | Base Patching | 1. Once the base patches have been poured, what is the Department looking for in relation to the rubblization of the new base patch (size of pieces)? 2. How long can the base patch areas be left open after pouring? | 1. The goal is to have a rubbilized pavement similar to the surrounding rubbilized concrete. Sizes similar to what is specified in 335.3.2. 2. The provisions state that asphalt can be placed over the patch after 24 hrs. The maximum time the patch can remain open prior to overlaying with asphalt is defined per Section 104.6.1.2.3. | Jill Fehrman | 7 | 2020-03-09 11:53 | 2020-03-09 11:54
20200310 | 20200310036 | 36 | culvert liners | on page 67 of the plan, Station 660+86 shows a 36" Culvert Pipe to be lined, there is no corresponding bid item. will you add an additional bid item? |  |  | 2 | 2020-03-09 12:23