## qandasearchletting_results
Date: | 2020-10-12 16:30
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20201013 | 20201013001 | 1 | CAD Files | Can CAD files be made available with existing and proposed surfaces in one of the following formats (LandXML, .Dwg or .DGN) | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 1 | 2020-09-08 16:52 | 2020-09-16 09:35
20201013 | 20201013001 | 1 | Drainage Tables in Excel Format | Can the drainage tables be made available in excel format for bidding purposes? | The drainage tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 2 | 2020-09-09 06:43 | 2020-09-14 07:47
20201013 | 20201013001 | 1 | Structure B-40-878-flange angles | Design for structure B-40-878 calls for flange angles L10x10x1-3/8 and L10x8,x1-3/8. Nobody in USA is producing such angle sizes, only ARCELOR INTERNATIONAL has L10x10x1-3/8, no L10x8x1-3/8. Per special provision â€œBuy America Provisionâ€ only exemption of this requirement is if cost of material does not exceed 1% of total contract cost or $2,500.00, whichever is greater. Cost of flange angles will be much higher than $2,500.00. Please advise. | The project team followed up with Dave Platz today at FHWA and discussed the Buy America Provisions. For the Buy American Provision, FHWA's regulations permit a minimal use of foreign steel and iron in the amount of $2,500 or one-tenth of one percent, whichever is greater, to be used in a Federal-aid project. For a project of this size, the value would therefore be estimated based on the one-tenth of one percent of the project amount. The cost calculation includes the cost of the materials, and it also includes the cost to deliver the materials to project site. | Mike Coleman | 3 | 2020-09-14 09:53 | 2020-09-16 06:22
20201013 | 20201013001 | 1 | Earthwork Tables in Excel Format | Can the earthwork tables be made available in excel format for bidding purposes? | The earthwork tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 4 | 2020-09-15 09:25 | 2020-09-17 05:54
20201013 | 20201013001 | 1 | R-40-561 & R-40-564 - MSE Walls - Minimum Ground Reinforcement Lengths | Contract drawings do not provide the minimum ground reinforcement lengths (strap lengths) for Walls R-40-561 and R-40-564. Please provide the same to complete internal stability design. | The minimum reinforcement length will be added to the contract plans for these structures in an upcoming addendum. | Mike Coleman | 5 | 2020-09-15 14:43 | 2020-09-22 11:48
20201013 | 20201013001 | 1 | Permits | Can you please provide the Army Corps Permit and the WPDES Storm Water Permit? | The Permits can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 6 | 2020-09-16 06:04 | 2020-09-16 06:17
20201013 | 20201013001 | 1 | Geotechnical Reports | Can you please provide the Geotech Reports for the project? | The Geotech Reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ Note: The Geotech reports for R-40-573 and R-40-576 are not finalized at this time. These two retaining walls are being updated as part of an upcoming addendum. The Geotech Reports for R-40-573 and R-40-576 can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 7 | 2020-09-16 06:07 | 2020-09-16 06:19
20201013 | 20201013001 | 1 | BIM Deliverables | Is there a format you are able to send us? | The following formats will be provided for the BIM model deliverables: â€¢ AMG model with finish grade and subgrade surfaces in DWG, XML, and TTM format. â€¢ 3D lines and points (for bridge, retaining wall, storm sewer, sanitary sewer, and water main layout) in DXF and CSV format. Per the â€œBIM for Infrastructure Model Specification for Zoo IC North Leg Projectsâ€ Article 36, these items will be provided to the contractor prior to construction. | Mike Coleman | 8 | 2020-09-17 05:56 | 2020-09-17 05:56
20201013 | 20201013001 | 1 | Bid Item# SPV.0060.4088, .4108 & .4128 | In the proposal (page 289 of 505); A.1 Manufacturer: It state the HLMR Bearings can only be supplied by an approved UPRR FABRICATOR. We are requesting this requirement be removed or the Bid Items be removed due to single sourcing of the bearings. This is eliminating the competitive bidding ( collusion ) of the bearings for this structure and providing an unfair advantage for the UPPR FABRICATOR to be awarded the bearings used on structure B-40-877. | The Union Pacific Railroad requires fully designed & detailed bearings (Shop Drawing level of detail) in order to receive Union Pacific Railroad approval during the design phase. Therefore, approvals were obtained during the design phase of this project to single source their use on this project. | Mike Coleman | 9 | 2020-09-17 10:14 | 2020-09-24 16:42
20201013 | 20201013001 | 1 | Railroad Ties | B-40-878: Do not see bid items or information regarding the temporary or permanent Railroad Ties. What bid items are the RR ties paid under? | Supplying and placing wood railroad ties is paid under bid item â€œConstruct 136LB ISHH CWR on Wood Ties, Item SPV.0090.0805â€. It is paid by the linear foot. It does not matter if they are temporary or permanent condition as they both are paid in the same manner. | Mike Coleman | 10 | 2020-09-18 15:29 | 2020-09-24 16:44
20201013 | 20201013001 | 1 | Existing Utility Map | Can an existing utility map be provided for bidding purposes as was in previous Zoo IC projects? | There is not an existing utility map available for this project. For your information we are providing the available MicroStation and AutoCAD utility files. The Utility Cadd Files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 11 | 2020-09-21 08:36 | 2020-09-24 16:56
20201013 | 20201013001 | 1 | Special Provision Article 155 | Plan sheet 1014, note 7 indicates to cap the Excavation, Hauling and Reuse of Low-Level Contaminated Soil Item with a 2-ft clay cap (clay cap paid separately). Special Provision article 155 (Excavation, Hauling and Reuse...) section A.3 indicates to cap 1 to 2 ft of soil. Is a 2-ft clay cap needed for the Reuse of Contaminated Soil? If yes, there is no pay item for this. Please clarify. | In an upcoming addendum, a clay cap bid item will be added to the contract and the special provisions will be revised to state a 2-ft clay cap. | Mike Coleman | 12 | 2020-09-21 08:39 | 2020-09-24 16:58
20201013 | 20201013001 | 1 | Temporary Access Gates Detail | Sheet 66 of the plans has a detail for Temp. Access Gates but no bid item is associated with these and I cannot find any language in the special provisions noting them as incidental to another item. Please provide a bid item for these gates or what item they are incidental to, as well as where they can be found in the plans to be quantified. | The Temporary Access Gate detail shown on Plan Sheet #66 is for gates to be constructed at the two temporary Canadian Pacific Railroad crossing shown on Plan Detail Sheet #134. The plan details will be updated and pay items will be added by an upcoming addendum. | Mike Coleman | 13 | 2020-09-22 06:33 | 2020-10-05 09:37
20201013 | 20201013001 | 1 | Buy America | With reference to question and answer 3 "Buy America" Special Provision, we have received more information from suppliers for the L 10 x 10 x 1-3/8 (produced in Germany) and HSS 22 x 22 x .875 wall (produced in Japan) We thought that this information needs to be brought to your attention. Our direct cost for this material will be approximately $200,000.00. If we understand calculation correctly as 1/10 of 1% total project value would have to be $200,000,000.00 correct? | In the lower right corner on Sheet 52 of 78 of the B-40-78 Structure Plans, the plan shows an alternate fabricated box section for the HSS 22 x 22 x 0.875, composed of four 7/8â€ thick plates. | Jill Fehrman | 14 | 2020-09-23 14:57 | 2020-09-28 20:43
20201013 | 20201013001 | 1 | MANHOLE SIZE REDUCTION | IS IT ALLOWABLE TO REDUCE THE INSIDE DIAMETER OF THE LARGER MANHOLES (5 FT DIAMETER AND LARGER)TO 4 FT DIAMETER ABOVE THE PIPE CONNECTIONS? THIS WOULD WORK ON A NUMBER OF THE DIFFERENT DIAMETER MANHOLES THAT ARE DEEPER THAN 12 VF. REDUCTION WOULD BE AT A MINIMUM OF 6 VF ABOVE THE LOWEST PIPE. MANHOLES WITH PIPE CONNECTIONS HIGHER THAN THE TOP OF THE OUTGOING PIPE WOULD BE REDUCED AT A HIGHER ELEVATION BASED ON THE INVERT AND SIZE OF THE INCOMING PIPES. | This question has been asked previously on another Zoo Interchange let project. We would not allow a smaller section, because, the use of a smaller riser section will prevent future connection of large pipes within the riser barrel section, in case if we need it. Contractor should bid and build the manhole as shown on the plan. | Mike Coleman | 16 | 2020-09-23 16:34 | 2020-09-24 16:58
20201013 | 20201013001 | 1 | File Requests | Can you post the following information: â€¢ Design Study Report â€¢ Exceptions to Standards Report â€¢ Pavement Type Selection Report â€¢ Environmental Document â€¢ As-Built Drawings â€¢ Preconstruction Survey â€¢ Traffic Management Plan | The requested information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 17 | 2020-09-24 10:09 | 2020-09-24 13:35
20201013 | 20201013001 | 1 | Watermain Specifications | The project specifications for water main construction makes several references to the spec requirements of the City of Wauwatosa. We are unable to locate these specifications online. Please provide the City of Wauwatosa standard specifications for water main construction and any standard drawings that may be applicable. | Adam Florin from Wauwatosa Water Works was contacted to get clarity. The project specifications related to water main refer to "conforming to the Standard Specifications for Sewer and Water Construction in Wisconsin" which is what should be used for the project. In some of the project special provisions it states: Adam Florin referred us to a recent City of Wauwatosa water main project which spells out specific tables and sections in the â€œStandard Specifications for Sewer and Water Construction in Wisconsinâ€ for material and gradation for the bedding, cover, and backfill material which the City of Wauwatosa wants. The bedding cover and foundation material specification can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 18 | 2020-09-24 12:59 | 2020-09-24 13:36
20201013 | 20201013001 | 1 | UPRR Structure CAD Files | Can the railroad bridge plans be posted in Cadd format? | The requested information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 19 | 2020-09-24 13:10 | 2020-09-24 13:34
20201013 | 20201013001 | 1 | Item #26 - Removing Old Structure STA 114NO+00 | Is this item for the removal of the existing Modular Block Retaining Wall in front of the Denny's parking lot? If so, is there any information on this wall? | The bid item Removing Old Structure STA 114NO+00 (Structure R-40-569, Sheet #2254) is intended for the removal of the existing modular block wall in front of the Dennyâ€™s parking lot. We do not have any additional information on this wall. | Mike Coleman | 20 | 2020-09-24 14:29 | 2020-10-05 09:39
20201013 | 20201013001 | 1 | 315. Control of Water, Item SPV.0105.5245 & 318. Control of Water Storm Sewer, Item SPV.0105.8098 | These items (315. Control of Water, Item SPV.0105.5245 & 318. Control of Water Storm Sewer, Item SPV.0105.8098) in the Special provision are identical. Where on the project does the Department expect the need for this special provision? If not needed please remove these items. | The first one listed 315. Control of Water, Item SPV.0105.5245 is for Wauwatosa water main. The second one listed 318. Control of Water Storm Sewer, Item SPV.0105.8098 is for roadway storm sewer. | Jill Fehrman | 21 | 2020-09-24 16:42 | 2020-10-01 17:39
20201013 | 20201013001 | 1 | UPRR Temporary Railroad Bridge - Shoring System Walers | Are the C15x40 channel wales shown in the detail drawings (sheets 2046 and 2048) required to be fully connect at the joints? If so, is this connection via a splice plate(s) and will it be welded or bolted? Please provide a detail. | Any joints used along each channel wale must be at centerline of soldier pile and are not required to be fully connected. | Jill Fehrman | 22 | 2020-09-25 10:59 | 2020-10-01 17:34
20201013 | 20201013001 | 1 | 614.0805 Crash Cushions Permanent Low Maintenance | Hello, looking at the Misc Qty tables on pages 981 and 1102, should there be a new item created for Crash Cushions Temporary Low Maintenance? Sheet 981 shows 7 total crash cushions that will be installed permanently, and sheet 1102 shows 15 that will be used in a temporary application. It would be more cost effective to price these items separately. Thanks | In an upcoming addendum, a new bid item for Crash Cushions Temporary Low Maintenance will be added to the contract. | Jill Fehrman | 23 | 2020-09-25 12:13 | 2020-10-01 17:40
20201013 | 20201013001 | 1 | Base Patching | Can the locations of the Base Patching be provided in a Misc. Sheet or some other location. Can a typical cross section of the Base Patching be provided? | Locations of base patches will be determined by the engineer in the field. A typical cross section will not be provided. In pavement areas where the existing concrete pavement has an existing asphalt overlay, the base patch is to be placed from top of existing asphalt surface to bottom of concrete pavement. Special provision language will be added by an upcoming addendum to include this statement. | Jill Fehrman | 24 | 2020-09-26 11:46 | 2020-09-30 16:58
20201013 | 20201013001 | 1 | Design Schedule | Can the Design schedule be provided? | The Design schedule can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Jill Fehrman | 25 | 2020-09-26 11:46 | 2020-10-01 17:59
20201013 | 20201013001 | 1 | Pre-Certified Drilled Shaft Contractors List | Can the pre-certified drilling contractors list, that was referenced in the pre-bid meeting, be provided? | There is not a pre-qualified list for the drilling contractors on this contract, however there are contractor qualifications listed in the special provisions for applicable construction operations that will need to be met. Contractor qualifications will need to be submitted and approved by the construction team prior to starting these field operations. | Jill Fehrman | 26 | 2020-09-29 09:07 | 2020-09-30 17:00
20201013 | 20201013001 | 1 | Fence Decorative Wall | On drawings 2233 and 2263 for structures R-40-567 and R-40-569, the notes reference the steel mesh to be tacked to the 2-3/4 x 1/4 frame. If the steel mesh is to be polymer coated and the frame is to be epoxy painted, how can the 2 components be welded together? | Small areas of polymer coating and epoxy paint will need to be removed to facilitate the tack welding. Areas should receive touch up painting once tack welding is complete. | Mike Coleman | 27 | 2020-09-29 14:12 | 2020-10-12 06:31
20201013 | 20201013001 | 1 | Material Specification Structures & Pipe | Per the detail on page 351 the material below both structures and pipe is to meet section 209 of the standard specifications. Will material meeting section 608, specifically 608.2.2.2 be acceptable? | Yes, 608.2.2.2 is acceptable bedding material for pipe and structure. We will update the detail on Sheet 351 as part of an upcoming addendum. | Jill Fehrman | 28 | 2020-09-29 15:02 | 2020-10-02 07:41
20201013 | 20201013001 | 1 | Contaminated Soil Quantities | There are multiple locations in the plans with 3 different types of contaminated soils. There is not consistency in the quantities. Generally the Earthwork MQ + Structure Qty add up to the Est. of Quantities however, the special provision quantities identified in article 76, 155, and 343 are not consistent wit the estimate of quantities. Please clarify | The contaminated soil quantities will be updated as part of an upcoming addendum to provide consistency between the plan sheets and the special provisions. | Jill Fehrman | 29 | 2020-09-29 15:07 | 2020-10-02 07:43
20201013 | 20201013001 | 1 | B-40-793 beveled anchor plate | page 12 (prestressed girder details page) calls out a beveled anchor plate referring to the Bearing details sheet for specs; however, there is no bearing details sheet included for this structure. Please confirm if there is a beveled anchor plate, and if so, please provide the specs. | A beveled anchor plate is not required on the prestressed girders for B-40-793. The plans will be updated to show this, and included in a future addendum. | Mike Coleman | 31 | 2020-09-29 17:14 | 2020-10-05 09:41
20201013 | 20201013001 | 1 | Location of sign structure S-40-442 | The general plan sheet of Structure S-40-442 (Sheet 2443) shows stationing approximately 371+00. Sheet 9 (Project overview) and Sheet 1262 (Plan & Profile IH 41 SB) show it located at approximately Sta 416NS+26 , 98' ï¿½ Rt. Please confirm location | The correct station location for S-40-442 is 371+05 NS. This station location is shown correctly in the Sign Structure Plans for S-40-442 on Sheet #2443. The sign structure S-40-442 is also shown in the correct location on Plan Detail Sheet #127. Please disregard the incorrect call-out labels shown on sheets #9, #1262 and #1268. | Jill Fehrman | 33 | 2020-10-01 07:25 | 2020-10-02 07:46
20201013 | 20201013001 | 1 | Missing Plan & Profile Sheets Mainline IH41 NB? | There appears to be missing Plan & Profile sheets for the NB IH 41 alignment. Sheet 1255 ends at approx sta 414NS+00 and Sheet 1256 begins at approx 446NS+00. Missing approx 3200 ï¿½ LF of NB Plan & Profile. Please advise. | The vertical profile for this segment of IH 41 northbound is referenced off of alignment â€œR/L NSNBâ€ on Plan and Profile Sheets #1268 and #1269. | Jill Fehrman | 34 | 2020-10-01 07:34 | 2020-10-02 07:44
20201013 | 20201013001 | 1 | Removing Wood Poles UPRR, Item SPV.0195.5001 | Can the Department provide the location(s) and approximate number of wood poles that need to be removed? | For Removing Wood Poles UPRR, Item SPV.0195.5001, an MQ table is in the planset on Page 1224 which shows the locations (see below). There are 15 poles total that need to be removed. The conversion factor used is 0.4 Ton = 1 Wood Pole. (Side note, when you see 0.8 TON in the table, it is two poles right next to each other which share the same cross arm.) | Mike Coleman | 35 | 2020-10-01 12:04 | 2020-10-05 09:22
20201013 | 20201013001 | 1 | Decorative Fence - Sample Mock-up | Can the Department provide more than 60 days for delivery of the sample decorative fence? Many of the parts are custom manufactured, most concerning is the lead time of the mesh infill. | Article 290 (Fence Decorative Bridge, Item SPV.0090.4100; Fence Decorative Wall, Item SPV.0090.4105), states under section C Construction â€œProvide a full sized painted 6-foot by 10-foot long fence test panel. Deliver the test panel to the job site within 60 days of the award of the contract. Unload and set up the test panel in an area designated by the engineer. Obtain test panel acceptance prior to beginning fabrication of fences.â€ This special provision will be updated by an upcoming addendum to extend the test panel requirement from 60 days to 120 days. Fabrication and installation of final panels is required to meet 2021 interim completion dates defined in the prosecution and progress article of the special provisions. | Mike Coleman | 36 | 2020-10-01 12:26 | 2020-10-05 09:39
20201013 | 20201013001 | 1 | Structural Steel Carbon - Bridge B-40-878 | Sheet 2036 (52 of 78) note 8 seems to indicate the Sacrificial Beam is paid under Structural Steel Carbon, or is it the intent that just the connection items are paid under this item not the beams themselves? Please clarify. Can the engineer give a detail list of the items included in Structural Carbon Steel for Bridge B-40-878 for both the permanent and temporary structure? | The sacrificial beam is paid for under Structural Steel HS. The sacrificial beam connection items are paid for under Structural Steel Carbon. The following is a list of items paid for under Structural Steel Carbon - Permanent Structure: Embedment plates on abutments; walkway plates, flashing plates and sacrificial beam connections on superstructure. Temporary Structure: Embedment plates on abutments; flashing plates on superstructure. The walkway plate on the permanent structure will be counted in the Structural Steel Carbon quantity in Addendum #5. Note 2 under Walkway Plating will be revised to indicate that walkway plating is paid for under Structural Steel Carbon; this will occur in a future plan revision after project letting. The embedment plates on abutments of the temporary structure are 5/8â€ x 8â€ x full length of backwall and will be noted as such in a future plan revision after project letting. | Jill Fehrman | 37 | 2020-10-01 15:51 | 2020-10-09 06:48
20201013 | 20201013001 | 1 | Storm Sewer - Backfill Slurry | Will the backfill slurry detail on page 351 for both pipe and structures be required for temporary pipe and structures that are both installed and removed under this contract? | Backfill slurry is not required for temporary pipe and structure that are both installed and removed under this contract. Conform to section 608.2.2 for backfill material at these locations. | Mike Coleman | 38 | 2020-10-01 21:24 | 2020-10-05 09:24
20201013 | 20201013001 | 1 | Trench Width | Will the trench width be allowed to be reduced for both the slurry backfill and granular backfill following standard specification trench sizing as described in 608.3.11(3), or will the trench width be required to be the width as stated in both the tables and detailed drawing provided on page 351 of the plan set? | The backfill slurry structures and backfill slurry trenches tables shown on page 351 are for information only. Conform to section 608.3.1.1 (3) for trench widths. | Mike Coleman | 39 | 2020-10-01 21:27 | 2020-10-05 09:29
20201013 | 20201013001 | 1 | Traffic Calm Sequential Warning System | Is the Traffic Calm Sequential Warning System is an approved product (Article 317)? | The Traffic Calm Sequential Warning System is an approved product. | Jill Fehrman | 40 | 2020-10-02 07:55 | 2020-10-02 07:59
20201013 | 20201013001 | 1 | Bridge Asbestos Reports | Please provide any bridge asbestos reports that are available. | Asbestos reports for structures: B-40-135/136/137/138/139/259 will be posted at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Jill Fehrman | 41 | 2020-10-02 07:57 | 2020-10-02 08:03
20201013 | 20201013001 | 1 | Decorative Fence Panels | In regards to the fence panels that are on a grade. Is the welded wire mesh required to have it's wire components perfectly vertical and horizontal? Or can the horizontal mesh run parallel with the grade with the vertical members being perpendicular to grade? If the mesh needs to run perfectly horizontal, it results in panel sizes that are too large for some welded wire fabric manufactures. I have currently gotten all no quotes from large and small vendors. | Vertical members are vertical plumb (not perpendicular to top of wall). Mesh horizontal wires are level (not parallel to top of wall) and mesh vertical wires are plumb (not perpendicular to top of wall). Nearby examples of this construction are Pedestrian Bridge B-40-881, Center Street Bridge (B-40-880), and Swan Blvd Bridge (B-40-775). | Mike Coleman | 42 | 2020-10-05 13:51 | 2020-10-12 06:34
20201013 | 20201013001 | 1 | Temporary RR Bridge Item Clarifications | 1. Deck plate welding (sheet 71) â€“ Are the welds shown on the deck plate detail going to be done in the field, our thought is that they will because they are drop in plates? The weld at the fill gap doesnâ€™t show any weld symbol and the underside weld on the left side doesnâ€™t show a weld symbol. It would be great if all field welds needed were clearly labeled. 2. Carbon Steel â€“ We need clarification of what it exactly is on the temp. bridge. | 1.On sheet 71, all welds called out are shop welds; (although there is an option for the longitudinal fillet welds between deck plate weld and steel beams to be either shop or field welded, as called out in the weld note of the Deck Plate Detail). For the drop-in plates, the field welds are called out on sheets 69 and 70. 2.Please see the response to Question #37 for Carbon Steel clarification on the temporary bridge. | Jill Fehrman | 43 | 2020-10-05 14:50 | 2020-10-09 06:31
20201013 | 20201013001 | 1 | Bridge B-40-138 Carbon Steel | We cannot find the carbon steel on the drawings for bridge B-40-138. On page 1692 there is a note that says all new structural steel is High Strength? What steel is carbon? | The bid item for Carbon Steel is used to pay for the Protection Angle Armor, as shown on page 24 of the B-40-138 structure plan. | Mike Coleman | 44 | 2020-10-05 14:54 | 2020-10-09 08:48
20201013 | 20201013001 | 1 | Utility Poles/Lines at UPRR Tracks - 3-part question | The language in the utility section of the special provisions appears to indicate the lines on the West side and East side of the UPRR tracks do not get adjusted or relocated, but the plan and profile sheets 1294 to 1304 seem to indicate they will be rerouted. Please confirm if the lines will or will not be relocated to facilitate construction. If not relocated, please indicate if outages will be allowed by WE Energies for construction activities. Particularly for demolition, pile driving, drilling, and erection activities. If no outages are allowed, please indicate how the temporary bridge is to be constructed and if the current poles are to be located in the center of the double tracks. | Listed below is the current status and disposition of the overhead wires on the west and east side of the UPRR in the area where it crosses the freeway (all offsets are relative to the 'RDE' reference line to be consistent with the utility special provisions): ~ West side (60' LT of RDE): existing We Energies' overhead lines are discontinued. WisDOT is working with We Energies to drop and remove these wires across the freeway using a rolling closure. This will take place prior to roadway construction. ~ West side (48' LT of RDE): existing UPRR overhead lines are discontinued. Contractor will need to drop and remove these wires across the freeway using a rolling closure as part of the project. Contractor will also need to remove the wood poles north and south of the freeway as specified under the item "Removing Wood Poles UPRR". ~ East side (36' RT of RDE): existing We Energies' and AT&T Local Network overhead lines are discontinued. Charter Communications overhead lines are still live and will be discontinued sometime this week once they finish their underground splicing. WisDOT is working with We Energies, AT&T Local Network, and Charter to drop and remove these wires across the freeway using a rolling closure. This will take place prior to roadway construction. | Jill Fehrman | 45 | 2020-10-05 16:54 | 2020-10-09 06:39
20201013 | 20201013001 | 1 | Select Crushed Material | Does a jaw crusher have to be used so that less fines are made? | The department does not specify the primary crusher type to be utilized for producing Select Crushed Material. The contractor is responsible to provide the appropriate crushing and screening equipment necessary to ensure the Select Crushed Material will conform to the gradation requirements listed in 312.2(4) | Mike Coleman | 46 | 2020-10-06 10:53 | 2020-10-07 06:34
20201013 | 20201013001 | 1 | UPRR Access point from North Ave (001d-soi, Article 5) | Will quantities be adjusted to account for additional clearing, grubbing, curb sawing, removals, excavation and base aggregates for this access? What clear width do they require? Will this fit in there with the overhead lines and fiber optic running on that same path? | The construction access will be coordinated with Union Pacific Railroad during construction. Clearing and grubbing limits will be adjusted in the field as needed for the access construction. Undistributed quantiles in the plan would be utilized to pay for the access construction. | Jill Fehrman | 47 | 2020-10-07 07:39 | 2020-10-09 06:41
20201013 | 20201013001 | 1 | Concrete Pavement Repair SHES and Replacement SHES | Are there plans sheets or appx. locations associated with these items, or are they undistributed quantities? Items 416.1715 and 416.1725. We cannot find reference to locations in the plans or specs. | Concrete Pavement Repair SHES and Replacement SHES are undistributed items in the contract to be placed at locations in the field as determined by the engineer. Construction during nighttime hours is anticipated for these items. | Jill Fehrman | 48 | 2020-10-07 09:11 | 2020-10-09 06:58
20201013 | 20201013001 | 1 | 10" Angle materials - Question #3 and #14 Follow up | Due to the limited availability of the 10" angles will a fabricated angle section be allowed similar to the allowance of a fabricated Structural Tube section. If allowed, will any type of calculations, design drawings, PE stamps be required above the normal PE stamp of the steel shop drawings. | The contractor will need to obtain UPRR approval for replacement of the 10â€ angle with a built-up section. UPRR will require Wisconsin PE stamped calculations and details of the plates and connections used to fabricate the angle section, before UPRR will consider this change. | Jill Fehrman | 49 | 2020-10-07 09:44 | 2020-10-09 06:29
20201013 | 20201013001 | 1 | Existing Pavement Marking Removal | Project ID 1100-18-73 does not include an item for existing pavement marking removal, please advise as to how this work is paid for or what item it is incidental to. | Pavement marking removal quantities have been added to the contract with Addendum #5. | Jill Fehrman | 50 | 2020-10-07 11:11 | 2020-10-09 06:33
20201013 | 20201013001 | 1 | R-40-567 Change in Cored Hole Diameter | For R-40-567, on page 2267, it references an assumed 7â€ diameter cored hole through the tangent pile for tieback construction. In order to make our design work, we would need a 9â€ diameter cored hole. Is this acceptable? | A 9â€ hole is acceptable, as long as no more than 2 bars are in conflict/damaged, as stated in the plans. | Mike Coleman | 51 | 2020-10-07 11:47 | 2020-10-08 13:24
20201013 | 20201013001 | 1 | Timber Lagging Spec | The timber lagging spec for the retaining walls has a very high Modulus of Elasticity strength requirement in the Design Data Tables on the drawings. I know from previous experience on other DOT phases that we and other contractors performed for the Zoo and Mitchell Interchanges, we were able to use mixed oak hardwood lagging boards which has a lower Modulus of Elasticity then what is being asked for. Would this material be acceptable to use on R-40-569, R-40-573 and R-40-576? | The contractors should bid this item as the plans show. | Mike Coleman | 52 | 2020-10-07 11:48 | 2020-10-12 06:54
20201013 | 20201013001 | 1 | B-40-876 Pier 4 Elevation | Please confirm the bottom of footing elevation of 679.31 at pier 4 at structure B-40-876 is correct. The footing elevation at pier 4 of structure B-40-875 is in line with this pier and has a bottom of footing elevation of 688.91, almost 10' higher. The 679.31 elevation will be below water elevation right next to Underwood Creek; if this is correct would the department consider adding a pay item for sheeting at this location? | The elevations of the bottom of footings for B-40-875 and B-40-876 are correct. | Mike Coleman | 53 | 2020-10-07 11:56 | 2020-10-08 12:35
20201013 | 20201013001 | 1 | supplier questions | Mueller doesnâ€™t make a 16â€ X 1-1/4â€ CC BR2B Saddle. Romac or Smith Blair equal ok? Casing Spacer End Seal specifications says 316SS Link Seal. Those are 2 different things. Link Seal wonâ€™t work for this application. Manufacturers donâ€™t make the Casing Spacer End Seals with 316SS. Only 304SS. Will this work? | The required service saddle for 2-inch and smaller is the stainless steel Smith Blair 372. This is referenced in the City of Wauwatosa water specifications under â€œG. Service Saddle, Nonmetallic Pipeâ€. You can replace the Link Seal Modular Seals with Malony Multiflex Casing End Seal, or with 12-inch concrete bulkhead, or equal at each end of the casing pipe after sewer installation in conjunction with backfilling. | Jill Fehrman | 54 | 2020-10-07 14:31 | 2020-10-09 12:29
20201013 | 20201013001 | 1 | Plan Details - Pavement Types | Sheet 146, 147 and 148 call out pavements "AP10 and AP11." These call-outs are not described on the legend (sheet 126). What pavement types are these, are details provided for them? | The HMA pavement type and layer thicknesses for AP10 and AP11 are shown in the table on Sheet 6. | Jill Fehrman | 55 | 2020-10-07 15:49 | 2020-10-09 06:37
20201013 | 20201013001 | 1 | Variation in thickness of existing asphalt Pavement on the North Bound and South Bound Lanes. | Can we be provided the variation in thickness of the existing asphalt overlay on the North Bound and South Bound Lanes? For example can we be provided the range in thickness like 4 to 8 inches? | Some existing asphalt depth thicknesses information is provided in the â€œZoo IC North Leg Soils Report.pdfâ€, which was posted as part of Question #18. | Jill Fehrman | 56 | 2020-10-08 08:52 | 2020-10-09 06:36
20201013 | 20201013001 | 1 | L.11 Interim Completion of Work September 1, 2022 - clarification for work at bridges | The special provision language for this interim completion milestone suggests that all street work needs to be complete on North Ave from Mayfair Rd to 116th St. by end of North Av. Stage 1B, but the traffic staging plans for North Ave. show work for concrete curb and gutter and sidewalk taking place at the bridges in North Ave. Stage 2A. Please confirm the concrete flatwork at the bridges described in North Ave. Traffic Stage 2A (plan sheet 860) at the bridge is not part of this interim completion milestone. | Confirmed, the sidewalk and curb & gutter adjacent to the IH 41 SB bridge does not need to be completed by this interim date. All other work necessary to open North Avenue to | Jill Fehrman | 57 | 2020-10-08 09:47 | 2020-10-09 06:32
20201013 | 20201013001 | 1 | SPV0060.1013 Lighting Control Cabinet Wauwatosa | The special provisions in the 2nd paragraph mentions it is a NEMA 3R aluminum cabinet. section B.1 states it is a Nema 3R 304 Stainless steel cabinet Which is correct- there is a substantial price difference. | The cabinet (enclosure) shall be NEMA 3R stainless steel per Wauwatosa. | Mike Coleman | 58 | 2020-10-09 06:42 | 2020-10-12 06:35
20201013 | 20201013001 | 1 | SHES Concrete Repairs and Replacements - locations of work or will the quantities be changed? | Most of the work is shown to be on Watertown Blank and 124th St. However, these are new pavements and not in need of repair. Will the quantities be reduced or will the locations of the work be provided in revised Misc. sheets? | SHES Concrete Repairs and Replacements estimated quantities are called out in a table â€œDesignated Haul Route Repairsâ€ (Sheet 1010). There is a detail sheet showing the limits of the haul routes, â€œTraffic Control â€“ Local Road Haul Route Detailâ€ (Sheet 722). The limits on Watertown Plank are UPRR overpass to 113th. The limits on 124th are North Ave to Burleigh. | Jill Fehrman | 59 | 2020-10-09 07:08 | 2020-10-09 11:09
20201013 | 20201013001 | 1 | Additional Geotech Reports | Can you post the Geotech reports for these structures as well? - B-40-792, 793, 794, and 879 - R-40-570, 573, 576 | The Geotech Reports for B-40-792, 793, 794 and 879, and R-40-570, 573, 576 can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201013001/ | Mike Coleman | 61 | 2020-10-09 07:26 | 2020-10-09 07:31
20201013 | 20201013001 | 1 | Variation in thickness of existing asphalt pavement on the North Bound and South Bound - follow up. | This is a follow up question. There is a geotechnical report in question 7 (we did not find a geotechnical report in 18). The geotechnical report has asphalt overlay thicknesses north of Station 392+00 that range from 3 to 5 inches. Can we rely on these thicknesses for bidding purposes? The Pavement Thickness table of the report for the MAINLINE includes borings No. 3 through No. 17 of representing the thickness of the existing asphalt pavement north of Station 392+00? Is there a different pavement thickness that we should rely on? | The geotechnical report is the only verification we have of the information within the as-built plans. | Jill Fehrman | 62 | 2020-10-09 07:36 | 2020-10-09 11:22
20201013 | 20201013001 | 1 | SPV Section 106 - Shop and Field Weld Inspection and Testing | Will independent weld testing services be required for field welding? If required for filed welding, can we employ an individual to perform the welding on these bridges and also use that individual to do our weld inspection if he is certified as both a weld inspector and certified to perform Mag Particle testing? | SPV Section 106 was inserted to comply with UPRR standards, which supplements subsection 506.3.19.1 and replaces subsection 506.3.19.4 of the standard specifications. The last sentence of Subsection 506.3.19.4 (1) states to use an independent weld testing service, which is required for both shop and field welding. Therefore the welder and inspector must be from separate companies. A weld inspector that is also certified to perform Mag Particle testing may perform both inspection and MP testing. | Mike Coleman | 63 | 2020-10-09 12:57 | 2020-10-12 16:17
20201013 | 20201013001 | 1 | Designated Haul Route Repairs | where and when are the items to be used for the Designated Haul Route Repairs? | HMA Pavement, and SHES Concrete Repairs and Replacements estimated quantities are called out in a table â€œDesignated Haul Route Repairsâ€ (Sheet 1010). An overview sheet showing the limits of the haul routes is shown on the â€œTraffic Control â€“ Local Road Haul Route Detailâ€ (Sheet 722). The majority of these items will be used in 2023 near the end of the project completion to rehabilitate the haul routes. Additionally, some repairs using these items will occur throughout the project for maintenance of the haul routes. | Mike Coleman | 64 | 2020-10-12 06:51 | 2020-10-12 06:52
20201013 | 20201013001 | 1 | Concrete Barrier | 1) Is there a detail for 603.1442 â€“ Conc. Barrier Type S42C? 2) What barrier wall types are to be placed on a concrete pavement, with the concrete pavement under the walls paid for as concrete pavement, and what types are to have a footer which is incidental to the wall. Type S42C Special has a detail for the footer, but no other walls seem to state whether the footer is part of the wall bid item. 3) Sta. 385+90 â€“ 477+00 show a S42 wall on top of asphalt. Is this accurate? 4) Are the Misc. Quantity sheets broken down by Stages at all? | 1) The detail is SDD 14B 41-3a/b Single Slope Roadside Retaining Wall. This detail was added to the contract as part of Addendum No. 3. 2) The concrete barrier footing area that is reinforced with steel rebar is paid as part of the concrete barrier item. 3) Some of the median barrier is poured on top of asphalt pavement in the IH 41 median (approximately Sta 477+00 to 485+75) (Plan Detail Sheets #146-148). 4) Stage numbers are listed in the miscellaneous quantity tables in the plan on Sheets #987-989. | Mike Coleman | 65 | 2020-10-12 13:28 | 2020-10-12 13:31
20201013 | 20201013001 | 1 | Follow-up regarding Question #43 and Welding | There is a lot of welding on the temporary bridge between the deck plates and the girders. The Deck Plate Detail shows welds that are not called out. Does the deck plate need to be welded top and bottom, (top-side and under-side) to the girders? Since it is a temporary bridge in place less than a year, it seems the amount of weld is excessive. | UPRR requires temporary bridges to be built to the same level of load carrying capacity as permanent bridges and the amount of weld indicated is consistent with UPRR standard details. The Beam Unit Detail on sheet 71 indicates that the deck plate is shop welded top and bottom, (top-side and under-side) the full length of each girder. The plan views on sheets 69 and 70 indicate that the drop-in plates are field welded, on the top-side only, on both edges full length. The objective of the Deck Plate Detail on sheet 71 is to describe how to protect the gaps between plates, and to allow the option for field welding of the deck to girder rather than shop welds. | Mike Coleman | 66 | 2020-10-12 13:35 | 2020-10-12 13:39
20201013 | 20201013001 | 1 | sanitary sewer backfill specifications | 1.25" Crushed Recycled Concrete Table 37 has been the standard backfill material for sanitary sewer in the City of Wauwatosa for the projects we have been involved with. Is this the backfill material required for the PVC pipe installation items? Slurry backfill was mentioned in the SPV manhole, abandoning, and adjusting sanitary sewer items. Would slurry backfill be required for the PVC pipe installation items? | All materials and work required to install the sanitary sewer pipe will conform to the Standard Specifications for Sewer and Water. Granular backfill of the trench shall follow Section 8.43.4 which includes Table 37. | Mike Coleman | 67 | 2020-10-12 14:13 | 2020-10-12 14:14
20201013 | 20201013001 | 1 | Clearing and Grubbing for sanitary sewer | Referencing plan sheets 114 & 443: The clearing and grubbing limits between ~STA. 15TA-19TA need to be extended west to facilitate the deeper open cut installation of the 10â€ sanitary sewer. These trees will be compromised from excavation through the roots and the need to remove the tree branches/limbs hanging east in conflict with the deeper sanitary sewer work. | There are some TLE's for sidewalks and driveways in this area but no intentions of clearing or grubbing on private property. Some of the larger trees on private property do have canopies that will overhang the sanitary sewer trench. Trimming of the trees would be covered under Section 201 of the Standard Specifications. The contractor and construction staff during construction would work together to identify and minimize the impacts to the overhanging trees. | Mike Coleman | 68 | 2020-10-12 16:22 | 2020-10-12 16:24