## qandasearchletting_results
Date: | 2021-01-11
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210112 | 20210112002 | 2 | Design Files | Can the Department provide Meta-Date (ex-surf, prop-surf, alignments, linework, etc.) for this project? | The Metadata packet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112002/ | Mike Coleman | 1 | 2020-12-09 08:08 | 2020-12-17 06:03
20210112 | 20210112002 | 2 | milling on Airport Rd | Sheet 27 shows milling on I-94 at Airport Rd. This is not accounted for in the quantities. Is there milling of the 2' sections on on IH-94 near Airport Rd or is this only for the section of I-94 at CTH A? | A quantity for Removing Asphaltic Surface Milling was added as part of Addendum No. 1 to address the milling along I-94 underneath Airport Road. | Jill Fehrman | 2 | 2020-12-29 14:56 | 2021-01-11 09:19
20210112 | 20210112002 | 2 | Construction Staging Question | In the Special provisions Page 3 of 32 through 5 of 32 there is listed detailed stages for both the CTH A location and the Airport Road location. In the section regarding Airport Rd the "repainting" of the bridge is specifically called out as which stages the painting is to be done in. The CTH A section does not address the repainting. What is the intent as when the "repainting" of the CTH A bridge is to take place? | The timing of the repainting of the structure at CTH A was left for the contractorâ€™s means and methods to determine. It was intended that this work would be completed within the stages detailed in the plans. The repainting of the Airport Road bridge was detailed by stage because this was the only task being completed at this location. | Mike Coleman | 3 | 2021-01-05 11:39 | 2021-01-06 05:15
20210112 | 20210112002 | 2 | Follow up to question #3 Construction Staging | We have analyzed the schedule and work progression and discussed with the painters. We feel more time is necessary to complete the CTH A bridge on-time. If the painting is done during the deck forming process it is still a linear working item and cannot be done concurrently with the decking process. If the painting is done after the deck is stripped that would add approximately 25 working days of painting to the end of the project along with the additional stages of traffic control to facilitate the painting. We feel an additional 25 working days is needed. Please advise. |  |  | 4 | 2021-01-06 09:01
20210112 | 20210112003 | 3 | Drilled tie bars | In the Miscellaneous Quantities under Concrete Pavement items it calls out 28 Drilled tie bars 416.0610, however there is no line item for that. | This was addressed in Addendum #1 issued on January 5, 2021. | Jill Fehrman | 1 | 2020-12-30 09:25 | 2021-01-11 06:15
20210112 | 20210112004 | 4 | Working Days | This looks like a standard small bridge project which is typically a 35 WD contact. How did the designer come up with 27 WD? Where can we view the schedule? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112004/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-12-11 13:50 | 2020-12-14 09:25
20210112 | 20210112004 | 4 | Construction Schedule | It seems the design may have overlooked concrete curing in the design schedule. 8 days to complete 2 abutments with 48 hours of cure required before setting falsework on each only allows 2 days per abutment. 9 days to complete and cure the deck is unreasonable considering the specification requires 7 days of wet cure. 2 days to form the deck, tie the iron, and pour is extremely aggressive. Under the provided days and schedule contractors would likely need to build both abutments simultaneously. Is the extremely tight timeframe required and thus WisDOT intends contractors to provide expedited forces (multiple crews)and equipment on this project, or could additional days be included to reduce mobilization and equipment costs? | The design team has reviewed the schedule believe the 27 working days is appropriate. Please bid accordingly. | Jill Fehrman | 2 | 2020-12-17 13:50 | 2020-12-18 15:29
20210112 | 20210112004 | 4 | Start notice | Will the Department consider allowing the contractor to start this project in Late February if weather conditions permit? |  |  | 3 | 2021-01-08 11:30
20210112 | 20210112005 | 5 | Storm Sewer Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | Class IIIA and Class IIIB storm sewers will not be allowed on this project due to previous commitments to the local municipality which owns and maintains the downstream storm sewer system | Jill Fehrman | 1 | 2020-12-10 08:50 | 2020-12-11 07:40
20210112 | 20210112005 | 5 | 643.0920 Covering Signs Type II | Hello- For item 643.0920 Covering Signs Type II, it appears the quantity was tabulated as "Days" and not as "Each". There are 7 signs to cover and the detour will be in place for 21 days, which equals the quantity of 147 as shown on the table in the Misc. Qtys. Should this quantity be 7? Thanks | Yes, you are correct, the quantity should be 7. An Addendum with the Miscellaneous Quantity plan sheet to update the quantity to 7 is forthcoming. | Mike Coleman | 2 | 2020-12-16 09:56 | 2020-12-16 12:20
20210112 | 20210112005 | 5 | Cad Files | Can you please provide the cad files for this project? Thank you. | The Metadata packet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112005/ | Mike Coleman | 3 | 2020-12-16 13:49 | 2020-12-17 09:05
20210112 | 20210112005 | 5 | Soil Borings | Are there any soil borings available for the project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112005/ There is also a table showing soil boring information on Sheet 12 of the plans. | Mike Coleman | 4 | 2020-12-16 16:16 | 2020-12-17 09:32
20210112 | 20210112005 | 5 | Earthwork tables | If available, would you please provide the earthwork tables in excel format? | The earthwork tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112005/ | Mike Coleman | 5 | 2020-12-18 16:08 | 2020-12-21 08:15
20210112 | 20210112005 | 5 | Vanguard Electric Conflict | Page 10 of the Special states that Mazomanie Electric has moved their service to the south r/w line with a crossing at 46+25. In the plan on page 191, it's showing a Vanguard Electric line that is crossing through the new guardrail at least twice. Is this the Mazomanie Electric that has been moved or is this a separate utility? Is this line still in conflict with the new guardrail between 46+75 - 47+60? | The Vanguard electric line feeds street lights and will be de-energized and abandoned prior to the installation of the beam guard so there will be no conflict. | Jill Fehrman | 6 | 2020-12-22 10:13 | 2021-01-04 08:10
20210112 | 20210112005 | 5 | Railroad Flagging | Is the proposal line number 0360, Railroad Flagging Reimbursement intended to cover the entire cost of railroad flagging or 50%. | Due to the nature of the work, the item 801.0117 Railroad Flagging Reimbursement will be eliminated, and the cost of the railroad flagging will be 100% on the contractor if the railroad deems it necessary for the work operations. An Addendum with this change is forthcoming. | Jill Fehrman | 7 | 2020-12-23 13:37 | 2020-12-29 02:20
20210112 | 20210112005 | 5 | Temp Design Files | Can the Department provide temp surface datum .xml's and temp linework .dwg's for the staged work? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112005/ | Mike Coleman | 8 | 2021-01-04 08:22 | 2021-01-04 13:23
20210112 | 20210112005 | 5 | stage 5 asphalt items | what is the intent for the 100 ton (undistributed) of 4 MT 58-28 HMA | The intent for the 100 ton undistributed 4 MT 58-28 S HMA is to fill a gap between the roadway pavement and the new curb and gutter being placed along the sawcut pavement in Stage 5 . It was assumed that a curb machine would be used to place the curb and gutter and that it wouldnâ€™t be constructed flush against the pavement, so the gap would require 3.5â€ depth of 4 MT 58-28 S HMA. | Fred Schunke | 10 | 2021-01-07 13:07 | 2021-01-07 15:09
20210112 | 20210112005 | 5 | Lane Restrictions | In the Special Provisions on page 18(or 5 of 23) it states the designated peak hours in which a lane closure is not allowed are: Monday through Friday , 6 am to 8 Pm. Should it not be 6am to 8am? |  |  | 11 | 2021-01-08 15:29
20210112 | 20210112014 | 14 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, there appears to be numerous runs of SSPRC Class IV that have adequate cover for Class IIIA and IIIB bid items. Will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class IV in areas that meet this design guidance? | RCP Class IV has been specified for storm sewer in areas where fill height is less than 2-feet from the top of subgrade per Table 17.1 of FDM 13-1-17. Subgrade is noted as the bottom of the select crushed material. There are a few segments where a portion of a run between structures exceeds the 2-feet of cover, but the remainder of the run is less than 2-feet of cover. In this situation a SSPRC Class IV was denoted to avoid a change in pipe material between manholes. | Jill Fehrman | 1 | 2020-12-10 11:44 | 2020-12-11 07:38
20210112 | 20210112014 | 14 | Geotechnical Data | Is there soil boring data for this project that can be shared with the contractors? | The geotechnical data can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112014/ | Mike Coleman | 2 | 2020-12-10 14:01 | 2020-12-14 06:33
20210112 | 20210112014 | 14 | Tack Coat | Will an item be added for tack between the layers of asphalt? | Addendum #1 will be issued to add Item 455.0605, Tack Coat | Mike Coleman | 3 | 2021-01-05 09:03 | 2021-01-07 07:09
20210112 | 20210112014 | 14 | Pavement Removal for Offsite Utility work ( Outside Reconstruction) / Salvaged Unsalvaged Material | In the plan set in the Construction Details page 11 of the plan set. There is a note stating that Removal of Existing Pavement Structure is Incidental to Grading operations. Is this Asphalt for the Trench removal reflected in the Earthwork Summary? Second Question - In the Earthwork Summary sheet what comprises of the Salvaged / Unsalvaged Material that is quatified in the summary. Does this quantity include Concrete Pavements, Curb & Gutter, Sidewalk? Does this quantity include the Asphalt pavements that are to be removed on the project as well? Or Is this quantity just reflective of existing Concrete pavements to be removed? | 1. The asphalt removal within the trench is not reflected in the earthwork summary. 2. The salvaged / unusable material was calculated as the existing concrete pavement and asphalt pavement within the roadway limits of the reconstruct portion of the project. The quantity did not include curb and gutter, sidewalk, driveways throughout the project or pavement outside of the reconstruct limits. | Mike Coleman | 4 | 2021-01-06 08:48 | 2021-01-07 07:12
20210112 | 20210112014 | 14 | Service, corps, stops, & boxes to be 1-1/4 | Pg. 34 of the spec book calls out for all service, corps, stops, & boxes to be 1-1/4. After going through the Mueller Catalog they do not make the Curbs & Corps called out in 1-1/4. Would Ford or AY be an acceptable manufacturer? (as long as it meets Buy American Standards) Or could we upsize/downsize the service line? |  |  | 5 | 2021-01-08 09:58
20210112 | 20210112015 | 15 | Cleaning and sealing of concrete girder ends | My question is in regards to the Cleaning and sealing line item on page 9 of the specifications. B.1. Reference is made to furnishing a non-pigmented epoxy conforming to AASHTO M-235 Type 3,grade 2, class B or C. I have checked with many of our material suppliers and they have been unsuccessful in finding a specific product meeting these standards? Could you please lead us to a product or one that is equivalent that this specification was derived from? Thank you | Multiple products including Dynapoxy Low-Mod Epoxy from Pecora Corp, Fastrac CE330, which would need verification that it meets the Grade 2 requirement, and Sikadur â€“ 22 Lo-Mod by Sika are marketed as meeting the AASHTO M-235 requirements. Some of the other products on this approved products list may meet the requirements as well, but again, your supplier will need to contact the manufacturer for verification: https://wisconsindot.gov/Documents/doing-bus/eng-consultants/cnslt-rsrces/tools/appr-prod/ap-current/polymer-liquid-binder-2-27-2020.pdf | Fred Schunke | 1 | 2021-01-05 13:15 | 2021-01-07 15:07
20210112 | 20210112015 | 15 | SPV.0165-02-FIBER WRAP REINFORCING STRUCTURAL | Strengthening location F shows the flexural existing capacity of 1,107kip-ft and flexural demand of 2,234 kip-ft. FRP materials cannot provide the requested flexural demand. Can the demand be reduced, existing capacity increased, or should we consider other conventional ways of strengthening such as enlargement? |  |  | 2 | 2021-01-11 09:02
20210112 | 20210112018 | 18 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-12-13 08:39 | 2020-12-14 09:29
20210112 | 20210112018 | 18 | Galvanic Anodes | I was reviewing the Milwaukee Zoo Freeway specification for galvanic anodes. I only received partial information. I do see that it has the â€œminimum 1.3 ounceâ€ specification so commonly used for WIDOT. This is approximately 36 grams of zinc, which is quite small. When I start quoting to the contractors I would like to be sure I quote the correct size required for the project. I am attaching our data sheet for your review. As you know the galvanic anode is used to meet the desired life of the repairs, and the size makes a difference in the protection and length of time it lasts. I have been always quoting the XPT which is almost three times the size of the competitive 1.3 ounce galvanic anode, simply because I think it is the minimum I would use on bridge/roadways. However, often I see XP2 or XP4 specified for these projects. I want to be sure I get the size that you think meets your desired repair. | The plans and specs appear to be in-line with past projects for bidding purposes, which provides the minimum requirements when supplying galvanic anodes. I believe the intent thereafter is for the contractor to install the galvanic anodes according to the manufactureâ€™s recommendations, which is based on the reinforcement density, the corrosion environment, and the anode size. The contractor will need to work with their galvanic anode supplier to determine the number of anodes once the removals are completed, so the plan quantity is an estimate and very likely may be adjusted in the field. This determination will be based on the reinforcement density, the corrosion environment, and the anode size. If the anode supplier has a preference on sizing or spacing, which meets the requirements of the specs, we should/would accept that. | Mike Coleman | 2 | 2020-12-16 07:51 | 2020-12-16 07:59
20210112 | 20210112018 | 18 | B-40-248 Concrete Masonry Deck Patching | Note 11 in the general notes section of B-40-248 indicates that concrete used for the deck and paving blocks is to be paid for under the Concrete Masonry Deck Patching item. Structure B-40-248 does not contain a Concrete Masonry Deck Patching item. Please advise how payment will be made for the concrete. | The 11th General Note should read: NEW CONCRETE FOR THE DECK AND PAVING BLOCKS AT THE JOINT REPAIR TO BE PAID FOR UNDER THE BID ITEM â€œCONCRETE MASONRY DECK REPAIRâ€. An addendum will be issued for clarification. | Jill Fehrman | 3 | 2020-12-18 12:07 | 2020-12-21 11:05
20210112 | 20210112018 | 18 | B-40-249 Concrete Masonry Deck Patching | Note 11 in the general notes section of B-40-249 indicates that concrete used for the deck and paving blocks is to be paid for under the Concrete Masonry Deck Patching item. Structure B-40-249 does not contain a Concrete Masonry Deck Patching item. Please advise how payment will be made for the concrete. | See question 3 for this proposal. | Jill Fehrman | 4 | 2020-12-18 12:09 | 2020-12-21 11:06
20210112 | 20210112018 | 18 | B-40-939 & 940 Joint Repair Concrete | Note 15 under the general notes section for both B-40-939 and B-40-940 indicates that the new concrete for the deck and paving blocks at joint repair area is paid under the Rapid Set Deck Repair bid item. For both structures, the Rapid Set Deck Repair item has a qty of 1CY is this qty correct? | The 15th General Note should read: NEW CONCRETE FOR THE DECK AND PAVING BLOCKS AT THE JOINT REPAIR TO BE PAID FOR UNDER THE BID ITEM â€œCONCRETE MASONRY DECK REPAIRâ€. An addendum will be issued on this proposal for clarification. | Jill Fehrman | 5 | 2020-12-18 12:15 | 2020-12-21 11:08
20210112 | 20210112018 | 18 | Abate Asbestos B-40-369 | Item 10, Abatement of Asbestos, applies to the gaskets under the tubular railing on the B-40-369 structure. Do you need to abate the asbestos under all of the railing posts or just under the posts that to be removed for items 178 (railing Tubular Type H) and 180 (removing and resetting tubular railing)? | Only the asbestos under the railing posts that are to be removed needs to be abated. | Jill Fehrman | 6 | 2020-12-21 09:01 | 2020-12-23 08:32
20210112 | 20210112018 | 18 | Steel Crack Repair SPV.0060.56 B-40-939/940 | The plans and special provisions on the steel crack repair bid item, SPV.0060.56 for B-40-939/940 are vague as to the location of these repairs. Is there any detail as to where, and how many locations on the structures these repairs will be required? | All steel girder cover plate ends are to be inspected and tested under item SPV.0060.55 Steel Cover Plate Weld Testing Special. The findings of this inspection and testing will determine the location and required number of repairs to be performed and paid for under Item SPV.0060.56 Steel Crack Repair Special. For bidding purposes, the estimated number of cover plate end repairs is two (2) each for B-40-939 and B-40-940. Actual repair quantities could be more or less at each bridge. | Fred Schunke | 7 | 2021-01-04 14:28 | 2021-01-05 15:51
20210112 | 20210112018 | 18 | SPV.0180.50 Polyester Polymer Concrete Overlay Material | Would the material EPC OVERLAY by E-Chem be considered and approved as an equal alternate for the Polyester Polymer Concrete Overlay, Item SPV.0180.50? The EPC OVERLAY meets all physical property requirements of the system, barring thenne polyester specific properties: i.e. styrene content and silane coupler. We are making the request based on our own experience in use of this product and an outright concern for our workers safety when installing these products. The EPC Overlay is a 100% solids product, 0 V.O.C., non-flammable and does not present respiratory tract or mucous membrane irritants to our employees and adjacent personnel. We can submit the Technical Data Sheet, SDS sheets and Independent testing to verify the required physical properties that you are specifying. | An epoxy polymer concrete overlay would not be considered as an alternate for the polyester polymer concrete overlay. Only polyester polymer concrete overlays meeting the requirements of the special provisions are acceptable for use on this project. The Department has received information for the EPC overlay by E-Chem and will review it for potential future consideration of use, but it will not be allowed for this contract. | Fred Schunke | 8 | 2021-01-05 08:56 | 2021-01-07 15:02
20210112 | 20210112018 | 18 | B-40-354 Cleaning Decks | Under the Total Estimated Quantities, the cleaning deck item is 1609 Sy and the Polyester polymer concrete overlay item is 1069 Sy. This must be a key stroke error. Please revise the quantities to match. Thank You. | The quantity for 509.0500 Cleaning Decks should read 1,069 SY (1,069 SY is correctly shown as the total quantity in the plans, the typo is in the superstructure column. An addendum will be issued to correct this. | Mike Coleman | 9 | 2021-01-05 11:09 | 2021-01-06 12:13
20210112 | 20210112018 | 18 | B-40-939/940 Heat Straightening | SPV Article 3 under the Appleton Avenue Interchange section has a note for work included as "Heat straightening for girders B-40-939 and B-40-940" and "Repair at Girder #1 at bridge B-40-939". Please advise as to what bid items these repairs and heat straightening are paid for under as the plans for these structures do not indicate either of these items. | The Heat Straightening for B-40-939 and B-40-940 was originally part of the project but it was removed. The following bullet points will be removed from Article 3 of the Special Provisions via addendum: â€¢ Heat straightening for girders at bridges B-40-939 and B-40-940. â€¢ Repair at Girder #1 at bridge B-40-939. | Mike Coleman | 10 | 2021-01-05 12:31 | 2021-01-06 12:18
20210112 | 20210112018 | 18 | Cleaning and Sealing - Line Item on 98 of the specifications | My request for information derives from the Cleaning and sealing line item on 98 of the specifications. Reference is made to furnishing a non-pigmented epoxy conforming to AASHTO M-235 Type 3,grade 2, class B or C. I have checked with our material suppliers and they have been unsuccessful in finding a product? Could you please lead us to a product or one that is equivalent that this specification derived from? | The following product is marketed as meeting the AASHTO M-235 requirements: https://usa.sika.com/en/construction/repair-protection/multi-purpose-epoxies/overlays/sikadur-22-lo-mod.html This product does not specifically state that it meets the Grade 2 requirements, so your supplier will need to contact the manufacturer: https://ccmaterial.com/epoxy-binder/ce330-epoxy-binder/ Some of the other products on this approved products list may meet the requirements as well, but again, your supplier will need to contact the manufacturer for verification: https://wisconsindot.gov/Documents/doing-bus/eng-consultants/cnslt-rsrces/tools/appr-prod/ap-current/polymer-liquid-binder-2-27-2020.pdf | Fred Schunke | 11 | 2021-01-05 15:33 | 2021-01-05 15:34
20210112 | 20210112018 | 18 | Staging | Can stages 1 and 2 at Capitol and Hampton be performed at the same time? | Please bid per traffic staging provided in Article 5. Traffic of the special provisions. Any modifications to the traffic staging would need to be reviewed at the time of construction. | Jill Fehrman | 12 | 2021-01-09 14:42 | 2021-01-11 11:34
20210112 | 20210112018 | 18 | Concrete Pavement | Will the new concrete pavement require dowel basket assemblies at the contraction joints? Typically in the City of Milwaukee they are not required. | Dowel basket assemblies are needed at contraction joints. | Jill Fehrman | 13 | 2021-01-10 11:01 | 2021-01-11 11:15
20210112 | 20210112018 | 18 | Turn Lane Work on Silver Spring. | Can this work be performed during the daytime? | Please bid per traffic staging provided in Article 5. Traffic of the special provisions. Any modifications to the traffic staging would need to be reviewed at the time of construction. | Jill Fehrman | 14 | 2021-01-11 09:12 | 2021-01-11 11:34
20210112 | 20210112019 | 19 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112019/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-01-04 16:54 | 2021-01-05 10:02
20210112 | 20210112019 | 19 | SPV 9 | What is the ultimate goal of writing SPV 9? How is one supposed to achieve this direction provided slurry is hard with a couple hours? This should be revised to state saw slurry should be squeegeed onto sections of roadway intended to be removed immediately after sawing. This is a practical method witnessed in roadway construction, because the proper time to move the slurry with a squeegee is immediately after sawing when the slurry is still yet plastic. This would be a practical means of keeping the roadway area free of residual saw slurry, if in fact that is the goal of this SPV. | This SPV is intended to emphasize what is expected of the Contractor per standard spec 690.3 and that the means and methods of managing the sawing slurry must be included in the ECIP process. The slurry is not to be left within the roadway for an extended period of time. | Mike Coleman | 2 | 2021-01-05 14:31 | 2021-01-06 12:22
20210112 | 20210112019 | 19 | SPV0060.01 LED Luminaires | The specifications don't address what lumen levels are required. Please advise |  |  | 3 | 2021-01-07 15:59
20210112 | 20210112019 | 19 | Joint and Crack Repair | Can a construction detail be provided for the Joint and Crack Repair SPV item? There is generally a maximum width and depth of exploration that will provide guidance to help determine when the HMA repair should turn into a full depth concrete repair. We have witnessed when a third or more of the existing pavement thickness has deteriorated the HMA repair turns into full depth concrete repair. How will WisDOT handle joints that are discovered to be deteriorated to this degree upon the removing/cleaning process? | A construction detail will not be provided. | Jill Fehrman | 4 | 2021-01-08 16:20 | 2021-01-11 12:17
20210112 | 20210112019 | 19 | Joint and Crack Repair | Can a construction detail be provided for the Joint and Crack Repair SPV item? There is generally a maximum width and depth of exploration that will provide guidance to help determine when the HMA repair should turn into a full depth concrete repair. We have witnessed when a third or more of the existing pavement thickness has deteriorated the HMA repair turns into full depth concrete repair. How will WisDOT handle joints that are discovered to be deteriorated to this degree upon the removing/cleaning process? | A construction detail will not be provided. | Jill Fehrman | 5 | 2021-01-08 16:20 | 2021-01-11 12:18
20210112 | 20210112020 | 20 | 643.1205.S Basic Traffic Queue Warning System | Hello, please clarify the quantity for item 643.1205.S Basic Traffic Queue Warning System. The Misc Qty table shows 3 systems per day, per direction - are there going to be three separate systems on both Northbound and Southbound I-43? Or is each Flashing Beacon Trailer counted individually per day per direction? Similar past projects have counted all FBT per direction as a single system. Thanks | The quantity was revised with Addendum #1 for this proposal. | Jill Fehrman | 1 | 2020-12-17 08:58 | 2021-01-11 06:02
20210112 | 20210112020 | 20 | Cleaning Culvert Pipe Sizes | In the MQ's on page 37 of the plan, it lists 6 pipes that are 18-inch storm sewer outfalls. However there are 3 pipes in the Plan Sheets listed differently. Page 55 states that the pipe at 295+55 is a 42-inch pipe. Page 57 states that the pipe at 412+00 is a 24-inch pipe. Likewise on page 58, the pipe at 443+40 is also a 24-inch pipe. Which information is correct? | The pipes listed on the plan sheets show the correct pipe sizes. Miscellaneous quantities sheet 37 will be updated in upcoming Addendum. | Jill Fehrman | 2 | 2020-12-22 11:46 | 2021-01-04 08:24
20210112 | 20210112020 | 20 | HMA Test Strips | There are 4 PWL Strips and 1 SMA Test Strip in the miscellaneous quantities? The PWL test strips are called out for lower and upper lift on NB and SB? What is the Departmentâ€™s intention with these? Wouldnâ€™t only 1 PWL Test Strip be required for the 3 HT mix? | There should be 1 PWL Test Strip for Volumetrics and one for Density, for the 3 HT mix. This information will be included with Addendum No. 2. | Mike Coleman | 3 | 2021-01-04 19:04 | 2021-01-07 07:14
20210112 | 20210112020 | 20 | IH 43 Inside Shoulder Slope | The typical section shows the inside shoulder slope at 4%. Would the department allow this to be milled and paved at a 2% to match the lane? | The department would like the inside shoulder to be milled and paved at a 4% slope. | Mike Coleman | 4 | 2021-01-04 19:05 | 2021-01-07 07:14
20210112 | 20210112020 | 20 | Ramp Closures | The specials allow for 2 "consecutive" days of ramp closures. Due to order of operations (Mill Mainline, Mill Ramps, Binder Mainline, Binder Ramps, Surface Mainline, Surface Ramps), would the department allow for short term closures to mill past and pave past the ramps and longer closures to pave the ramp tie ins on separate days? | The department will allow for short-term closures but would like the â€œ2 consecutive daysâ€ of ramp closures for milling and paving. | Mike Coleman | 5 | 2021-01-04 19:07 | 2021-01-07 07:15
20210112 | 20210112020 | 20 | Earthwork Summary | The Earthwork Summary table shows 111 CY of Salv/Unusable Pvmt. There is 2262 SY of 8 Inch concrete pvmt shown in the Typical section for this area. That would be just over 500 CY of concrete which I'm guessing you dont want in the shallow fills. This would create a deficit for building the fills shown on the table. Do you want to revise the qtys and add a Borrow item? | Yes â€“ the borrow quantity is 187 CY and the excavation is 6 CY. This will be included in Addendum No. 2. | Mike Coleman | 6 | 2021-01-05 09:49 | 2021-01-07 07:15
20210112 | 20210112020 | 20 | IH 43 Lane Closures/ STH 32 Closure | Page 5 of the special provisions details the closures for each layer of milling and paving. Are the lane closure restrictions bulleted under the line starting with â€œDuring the STH 32 detour for 4540-27-74â€¦â€¦â€ for the entire project duration or just while the STH 32 detour is in affect? Is it correct that the NB lanes have to be open on Thursdays 3:00 pm â€“ 6:00 pm? What are the lane closure restrictions for the concrete patching operation? | The bullet should precede the line starting with â€œDuring the STH 32 detour for 4540-27-71â€¦â€ The NB lanes have to be open on Thursdays from 3:00 pm â€“ 6:00 pm. The lane closures listed are correct and apply to the concrete patching operations. | Mike Coleman | 7 | 2021-01-05 10:15 | 2021-01-07 07:16
20210112 | 20210112020 | 20 | Railroad CE/Consent Letter | Page 11 Article 9 of the specials state the contractor will need to obtain a Contractor Endorsement and fill out a Consent Letter Application. There is a Consent Letter in the specials for a project in Eau Claire County? Is this the wrong consent letter or was it just included as an example? The paragraph says the CE will be issued at no cost to the contractor but then states if the contractor pays the CE fee it will be at the contractors expense. Who is paying the fee? | The consent letter is an example. There is no cost to the contractor for the Contractor Endorsement. However, if the contractor pays the fee, it will not be reimbursed. | Mike Coleman | 8 | 2021-01-05 10:16 | 2021-01-07 07:17
20210112 | 20210112020 | 20 | Concrete Base Patching | The detail for concrete base patching on SHEET 9. This indicates that there are no dowels in the base patches. SHEET 33, Miscellaneous Quantities, Concrete Base Patching and Sawing Summary. It appears that each base patch has drilled dowels dedicated to them. So, the question is, are these Concrete Base Patches dowelled or not? | No â€“ dowel bars and tie bars are not required. This will be revised with Addendum No. 02. | Mike Coleman | 9 | 2021-01-05 10:48 | 2021-01-07 07:17
20210112 | 20210112020 | 20 | Concrete Base Patching | The Detail for Concrete Base Patching on plan sheet #9 indicates the patches are 3' normal for length. Will the patches be 3' in length? | The patches vary in length. Minimum length is 6â€™. Minimum width is 2â€™. The construction detail will be updated in Addendum No. 2. | Mike Coleman | 10 | 2021-01-06 10:58 | 2021-01-07 07:18
20210112 | 20210112020 | 20 | Base Patches | Is the existing pavement continuously reinforced, doweled or plain concrete? The plan states it is "JRCP", Continuously reinforced, and yet dowels are being required. All the above are not consistent with each other. If memory serves us correctly, this pavement was plain. |  |  | 11 | 2021-01-10 15:39
20210112 | 20210112020 | 20 | Base Patches | Base Patches 2 foot wide do not work. The Northwest region once used 3 foot base patches and they started to reflect through the new asphalt before the project was complete. They will also crack up longitudinally and behave like a beam rather than a slab of concrete. There is engineering reason why the Standard plates are drawn as they are at 6 foot minimum. | The intent of the concrete base patching item is to only remove the deteriorating joint and not the entire slab. | Jill Fehrman | 12 | 2021-01-11 08:51 | 2021-01-11 14:01
20210112 | 20210112020 | 20 | Revised Earthwork Summary | Do you have new cross sections that reflect the quantities shown in the new earthwork table? These quantities do not seem to match the plan cross sections. I see Removing Concrete Pavement is not in the summary table but it still gets paid as Common Excavation. Can you send out a special notification if you do make revisions, if we don't see anything soon we will bid according to your numbers. |  |  | 14 | 2021-01-11 10:59
20210112 | 20210112021 | 21 | Cable Barrier System | Manitowoc County has two cable barrier systems on the approved products list. Sheboygan County does not have any cable barrier systems listed. What are we supposed to bid in Sheboygan County? | Per Article 11. Cable Barrier Type 1, Item 613.1100.S; Cable Barrier End Terminal Type 1 Item 613.1200.S., the Safence TL-3 system manufactured by Safence should be supplied for locations in both counties. The APL will be updated to include Safence. | Jill Fehrman | 1 | 2021-01-11 08:37 | 2021-01-11 12:34
20210112 | 20210112022 | 22 | Asphaltic surface | In the traffic section of the special provision it states, â€œdo not allow travel lanes consisting of a gravel surface to remain in place for longer than 5 days.â€ To construct these areas in an proper manner a majority of this paving should take place prior to constructing a test strip. As all the asphalt in this project currently under PWL specifications, could an asphaltic surface item be added to patch these areas? | An asphaltic surface item will not be added to patch the twin culvert or box culvert areas. Rather. A future addendum will be issued to simplify staging of construction operations. The addendum will: Remove the last paragraph under the Road Surface Restrictions subsection of Article 4. Traffic â€œWhen this section of roadway is closed to through traffic but open to local traffic (detour is in place), do not allow travel lanes consisting of a gravel surface to remain in place for longer than 5 days (Excludes Box Culvert Replacements Areas).â€ Add new language stressing the importance of maintaining gravel surfaces open to local traffic at specified locations during the closure/detour according to standard spec 104.6 and the direction of the engineer. Revise the PWL special provisions to include coring as an acceptable means of PWL density acceptance at specified locations. | Jill Fehrman | 1 | 2020-12-18 10:57 | 2020-12-28 07:31
20210112 | 20210112022 | 22 | Earthwork Quantities | Are the quantities shown in the mass ordinate and waste columns of the earthwork summary table incorrect? | Yes. The quantities shown in the mass ordinate and waste columns are incorrect. The earthwork table will be corrected as part of a future addendum. | Jill Fehrman | 2 | 2020-12-18 15:33 | 2020-12-18 15:33
20210112 | 20210112022 | 22 | Structure c-31-57 | Instead of this being a two-cell structure, could it be two precast 7ft or 8ft by 10ft boxes laid next too each other to create a two cell | The contractor may furnish a pre-cast concrete box culvert in lieu of the cast-in-place box culvert with the acceptance of shop drawings by the structure design section (BOS). Additional details are included on structure plan sheets (sheet #130 and #135). On previous state highway projects, the department has allowed two separate precast structures to be assembled to form a single structure with the acceptance/approval of shop drawings by BOS. The contractor will need to verify that the hydraulic capacity of the box culvert remains per the contract plans. Additionally, any potential approval by BOS will require details following what is shown on Bridge Standard 36.05, modified apron details meeting the new cross-sectional width of the box culvert, and modified details between the connections of the box culvert/apron and box culvert/wingwalls. | Jill Fehrman | 3 | 2020-12-22 09:00 | 2020-12-29 02:26
20210112 | 20210112022 | 22 | Structure 31-57 | Can structure 31-57 be two single cell boxes laid next to each other instead of one two cell structure | The contractor may furnish a pre-cast concrete box culvert in lieu of the cast-in-place box culvert with the acceptance of shop drawings by the structure design section (BOS). Additional details are included on structure plan sheets (sheet #130 and #135). On previous state highway projects, the department has allowed two separate precast structures to be assembled to form a single structure with the acceptance/approval of shop drawings by BOS. The contractor will need to verify that the hydraulic capacity of the box culvert remains per the contract plans. Additionally, any potential approval by BOS will require details following what is shown on Bridge Standard 36.05, modified apron details meeting the new cross-sectional width of the box culvert, and modified details between the connections of the box culvert/apron and box culvert/wingwalls. | Jill Fehrman | 4 | 2020-12-23 08:25 | 2020-12-29 02:27
20210112 | 20210112023 | 23 | Fish Spawning Restriction | Looking at the box culvert extension there is a restriction due to fish spawning (March 1st â€“ June 16th) on the unnamed tributary to Sorenson Creek. On page 98 on the Plan and Profile it shows it being on the unnamed tributary to Bower Creek and on the cover sheet for the structure it shows tributary to Sorenson creek. Also, in the specials under Removing Old Structure Over Waterway station 159+03 it states that it is on the unnamed tributary to Bower Creek. Which one is it? | The difference has to do with how DNR has referenced the creek (which is whatâ€™s in specials) vs how it shows up in our Highway Structure Information system (which is what made it onto the structure plans). All plan documents are referring to the same waterway. | Mike Coleman | 1 | 2020-12-16 08:06 | 2020-12-16 08:07
20210112 | 20210112023 | 23 | Storm Sewer Outfall | Per page 153 the existing storm sewer outfall is in wing 3. I don't see any change in reinforcement to allow the pipe though the wall. How is this being address? | An upcoming addenda will address this issue. | Jill Fehrman | 2 | 2021-01-04 12:36 | 2021-01-05 07:18
20210112 | 20210112023 | 23 | Schedule | Is there a design schedule for this project? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112023/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2021-01-06 17:57 | 2021-01-07 08:49
20210112 | 20210112023 | 23 | Access to residential/business | Normally the department provides an undistributed base aggregate quantity for access for the contractor to use in order to provide property owners access to their driveways. Can this be changed into the project? | The department will not be adding an undistributed quantity for access. There is minimal grading and the contractor should be able to use existing material for the minimal ramping of driveways that will be required. | Mike Coleman | 4 | 2021-01-06 17:59 | 2021-01-07 09:54
20210112 | 20210112023 | 23 | Utilities lowering | Since the project includes over 100 manholes and water valves in the roadway. The contractor and construction traffic will have to work around these structures. Would the department consider a temporary lowering item for the contractor to install temporary steel plates over each structure? | No. The department will not be adding a temporary lowering item. | Mike Coleman | 5 | 2021-01-06 18:00 | 2021-01-07 10:00
20210112 | 20210112023 | 23 | Typical Section | Normally a driveway typical section is provided. Just trying to determine the overall material types and thickness. | This was addressed in Addendum #1 | Mike Coleman | 6 | 2021-01-06 18:05 | 2021-01-07 10:01
20210112 | 20210112023 | 23 | Manitowoc Road - Sidewalk | Per the finish typical section for Manitowoc Road. What is the thickness of the base aggregate under the new concrete sidewalk? | This was addressed in Addendum #1 | Mike Coleman | 7 | 2021-01-06 18:09 | 2021-01-07 10:02
20210112 | 20210112024 | 24 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, there appears to be numerous runs of SSPRC Class IV that have adequate cover for Class IIIA and IIIB bid items. Will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class IV in areas that meet this design guidance? | This project is a local program project and the local unit of government has elected to use the pipe material specified. | Jill Fehrman | 1 | 2020-12-10 11:49 | 2020-12-11 07:37
20210112 | 20210112024 | 24 | Structure Backfill | The Brown County Sheeting project just changed the specifications for the Backfill by eliminating all the material tests except internal angle of friction. Will the specifications for this project be changed to mirror the County project since they tie together? | The sheet pile wall backfill specification will be changed by addendum to remove the additional material testing except internal angle of friction. | Mike Coleman | 2 | 2020-12-16 11:16 | 2020-12-17 05:35
20210112 | 20210112024 | 24 | Base Aggregate Fine Grading | With Brown County doing asphalt paving on this project, who's responsibility is it to fine grade base course for asphalt paving operations? | The contractor will be responsible for the fine grading. This will be clarified by addendum. | Jill Fehrman | 3 | 2020-12-18 09:27 | 2020-12-21 10:59
20210112 | 20210112024 | 24 | Steel Sheet Pile Coating | Section 17: Steel Sheet Piling refers to Standard Spec 512.2.1. which is inclusive to 512 Steel Sheet Piling. Within this standard spec, section 5.12.3.3 describes painting the steel sheet piling. The Brown County project 3-21 eliminated this requirement. Please confirm painting of the steel sheet pile is NOT required. | Per Addendum 2 painting steel pile is not required. | Jill Fehrman | 4 | 2020-12-30 12:51 | 2021-01-04 10:19
20210112 | 20210112024 | 24 | Can tie-back wall be backfilled with sheet pile wall backfill or native material? | On page 81, one of the plans under the general notes: â€œAll spaces excavated and not occupied by the new structure shall be backfilled with sheet pile wall backfill as shown on the plans.â€ Per the cross sections the limits of pay for the sheet pile wall backfill do not cover the region excavated to install the tie-back wall. Is the region excavated to install the tie-back wall to be backfilled with Sheet pile wall backfill or can native material be used? |  |  | 5 | 2021-01-08 05:47
20210112 | 20210112026 | 26 | Start Date | If awarded can this project be started in February as long as we are out of the water by March 1st? | Brown County does not want a closure prior to June 16th. A notice to proceed will not be issued before that date. | Mike Coleman | 1 | 2020-12-10 14:25 | 2020-12-16 11:47
20210112 | 20210112026 | 26 | Abutment Piling | Pile 1 & 9 at both abutments appear to be in conflict with the existing abutment footing. Existing footings look to be sitting on rock. Can pile be driven onto existing footing at north abutment or will existing footing removal be required where in conflict with proposed pile? At south abutment pre-bore is 4.5' into rock. Where in conflict with pre-bore & piling will required excavation & removal of existing footing be considered incidental? Will structure backfill material be required and if so will it be paid at unit price? | The existing abutment footing is expected to be in conflict for piles 1, 2, 8 and 9 at each abutment. It could not be verified if the either abutment is founded on rock as existing plans do not indicate and the borings are not close enough to determine. Piles cannot bear on existing footings. Any portion of existing footings that must be removed is included in the item 206.0600.S Removing Old Structure over Waterway with Minimal Debris. Granular material removed from behind existing abutments may be used to backfill below structure backfill limits depicted in the plans. | Fred Schunke | 2 | 2021-01-05 11:42 | 2021-01-07 14:18
20210112 | 20210112028 | 28 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers and culverts shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges - Culvert installations at ADT of 20k or less Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified CPCS, SSPRC, and CPRC Class III? | This project includes replacing pipes with less than 2 feet of subgrade cover and per the FDM the Class IIIA and IIIB pipe items are not allowed. The project also involves extending existing concrete culvert pipes. Per FDM 13-1-15.3 Special Situations, specific type of pipes can be used in these situations. | Jill Fehrman | 1 | 2020-12-10 11:51 | 2020-12-11 07:48
20210112 | 20210112028 | 28 | Soil Borings | Can you post the soil boring? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112028/ Deanna, please create a link in the NC Region Preliminary Plans Page for proposal #28. | Mike Coleman | 2 | 2020-12-11 08:01 | 2020-12-11 08:04
20210112 | 20210112028 | 28 | Earthwork Summary | According to the earthwork summary the Common Exc. and the Available Material is the same quantity. Note 2 states, Salvaged/Unusable Pavement Material is included in Cut, and Note 3 states Available Material = Cut - Salvaged/Unusable Pavement Material. This project has 24,265 s.y. of the Removing Concrete Pavement item. The earthwork quantities and the earthwork summary notes are conflicting, could you please verify. | The existing pavement volume is not taken into account for the earthwork. For sheet 73 (MQâ€™s), the notes should be revised as follows: Note 2 should be deleted. Note 3 should read as follows: â€œAvailable Material = Common Excavationâ€ An addendum will be issued to correct this. | Mike Coleman | 3 | 2020-12-11 11:47 | 2020-12-15 07:55
20210112 | 20210112028 | 28 | Remove & Reinstall Light Poles | Several of the electricians I have requested quotes from have told me that the two light poles in the 5th Avenue intersection with STH 73 are Utility Owned Poles. They say that they will not quote as they should be removed and reinstalled by the Utility. Is this correct, or are these poles owned by the State or other governing body ? If owned by the Utility, can they remove & reinstall, and you remove these from the project ? | The poles in question are owned by Alliant Energy and should be removed and reinstalled by Alliant. However, the pole moves are not compensated under the WisDOT Utility policy and there may be a cost to have them moved. Because of this the cost to moving the poles needs to be handled as a bid item to incorporate it into the project. During design it was thought that the utility would not move the poles, but that has since been clarified. Contractor needs to coordinate with Alliant to move the poles and pay any associated costs which will be compensated through the bid item. | Fred Schunke | 4 | 2021-01-04 13:38 | 2021-01-05 14:54
20210112 | 20210112028 | 28 | Staking Items | The items of Construction Staking Subgrade (LF) and Construction Staking Slope Stakes (LF) seem to be missing ?? Should they be added to the contract ?? |  |  | 5 | 2021-01-07 12:54
20210112 | 20210112029 | 29 | Temporary markings before rumbles | Good morning. On projects similar to this one, there would typically be a temporary epoxy bid item to be placed prior to the rumble strips rather than a temporary paint bid item as the temporary epoxy line that remains after the rumbles are installed would not need to be removed prior to placing the final epoxy after the rumbles have been installed like it will/would if a temporary paint item is used. Will the department issue an addendum to address this concern? Thank you. | An addendum will be submitted to address the epoxy and the contractors concerns. | Fred Schunke | 1 | 2020-12-29 09:15 | 2021-01-05 15:26
20210112 | 20210112029 | 29 | Milling Depth | What is the reasoning for a 3" mill and pave depth as the thickness of this lift in this type of an operation will be very difficult to make a quality end product | The 3" mill depth was proposed and approved to address the deteriorated centerline joint and ensure adequate pavement remains along the centerline after rumble strips are installed. | Mike Coleman | 2 | 2021-01-06 11:33 | 2021-01-07 07:21
20210112 | 20210112030 | 30 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | An addendum will be issued to address locations where Class IIIA and Class IIIB (non-metal) culverts are able to be installed. | Jill Fehrman | 1 | 2020-12-10 11:54 | 2020-12-11 08:36
20210112 | 20210112030 | 30 | Project Schedule | Will the Department please provide the preliminary project schedule used for design? | The preliminary project schedule has been posted at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112030/ | Jill Fehrman | 2 | 2020-12-18 08:28 | 2020-12-23 10:48
20210112 | 20210112030 | 30 | HMA PWL Density Test Strip Quantity Verification | Each project ID has a quantity of 0.5 Each allocated to it for item 460.0105.S, HMA PWL Test Strip Volumetrics, for a total of 1 Each combined, whereas each project ID has a quantity of 1.0 Each allocated for item 460.0110.S, HMA PWL Test Strip Density, for a total of 2 Each. Project ID 9304-12-70 doesnâ€™t have enough HMA Pavement quantity to be statistically relevant as a standalone PWL project, and the HMA Pavement is specified to be a 4MT 58-28S for both project IDâ€™s. Will two (2) density test strips be required, and if so, for what purpose? | The PWL requirements are developed for the contract tonnage of a given mix. This project calls for 2 test strips for Density and 1 test strip for Volumetrics. The same material is being used for the entire contract and therefore the quantity for the test strip for Volumetrics was broke between the two project ids. As there are varying depths of existing pavement structure between the two projects, a different density test strip is needed for each project id. | Jill Fehrman | 3 | 2020-12-22 11:11 | 2021-01-04 10:36
20210112 | 20210112030 | 30 | Traffic Management for Culvert Removal & Replacement | Article 3 of the Special Provisions, Prosecution and Progress, paragraph 6 begins by stating â€œConstruct the project under traffic, with one lane to remain open during construction at culvert removal and replacement locationsâ€¦â€. Article 4, Traffic, paragraph 1 states: â€œâ€¦All the culvert removal and replacement operations will take place under a detour.â€ These two statements seem to be contradictory. There is no item for lane shifts at the culvert locations typically included when required maintain 1 lane of traffic during the culvert removal and replacement work. Will the contractor need to maintain 1 lane of traffic for culvert work, or will the provided detour be sufficient for traffic management? | The culverts are intended to be completed under detour. Addendum #2 for this project will provides clarification. | Jill Fehrman | 4 | 2020-12-22 11:13 | 2020-12-23 11:27
20210112 | 20210112030 | 30 | Granular Backfill for Structure Removal | Will Granular Backfill be for backfilling the Cattle Pass Structure removals. There is an item and quantity for Job 9304-12-70, but not for Job 9304-11-70? | The item of Granular Backfill is listed as Undistributed and may be used on any item that requires it on the contract due to poor soil conditions. It is not only associated with the Cattle Pass Removals. | Jill Fehrman | 6 | 2020-12-30 09:36 | 2021-01-05 06:06
20210112 | 20210112030 | 30 | 3/4-Inch Base Aggregate Dense | The typical section for Station 230+50 to 413+10 on the 9304-11-70 plan shows 3/4-inch Base Aggregate shoulders to be constructed outside of the widened pavement, though no quantities are shown for this length of roadway in the Miscellaneous Quantities table. Will additional quantity of 3/4-inch base be added for constructing these shoulders? | The excavating and shaping in preparing the foundation for the asphaltic shoulders will leave enough aggregate material for the final shoulders. The excavating and shaping of the shoulders are incidental to the bid item Prepare Foundation for Asphaltic Shoulders. Contractors should bid according to the planâ€™s miscellaneous and estimate quantities. | Mike Coleman | 7 | 2021-01-06 12:27 | 2021-01-08 10:03
20210112 | 20210112030 | 30 | Curb & Gutter Patching HMA Mix Testing | In Project 9304-12-70, the construction detail for asphalt patching in front of curb and cutter shows that this Asphaltic Mixture would be considered HMA Pavement 4MT 58-28S, item 460.6224. Only the asphaltic mixture for areas behind curb & gutter replacements is called out as Asphaltic Surface, item 465.0105 per the note in the miscellaneous quantities table. The PWL Mixutre Use Table doesn't specifically call out testing parameters for the mix for curb patching, but since it is implied to be paid as item 460.6224 per the construction detail, it would seem that QMP mix testing would be required. Due to the small tonnage for this work, it is unlikely that the contractor would reach the 50 ton minimum threshold for QMP mix testing in a given day to do this curb patching. Would the department consider changing the asphalt patching for front of curb replacements to item 465.0105 to eliminate confusion for tracking HMA tons for QMP mix testing? | The department will change the label â€œ 4â€ HMA Pavement 4 MT 58-28 S â€œ to â€œ 4â€ Asphaltic Surface â€ in the plan sheet Construction Detail for Curb and Gutter Removal/Replacement in order to eliminate potential confusion. The bid items 460.6224 HMA Pavement 4 MT and 465.0105 Asphaltic Surface in the miscellaneous quantities and contract estimate will be updated to reflect these changes. This will be part of Addendum 03. | Mike Coleman | 8 | 2021-01-06 13:01 | 2021-01-08 10:04
20210112 | 20210112030 | 30 | Asphaltic Surface Mix Testing | For both project ID's, the PWL Mixture Use tables show Mixture Acceptance in accordance with "QMP as per standard spec 460" for the Asphaltic Surface items, 465.0105 & 465.0110. Under standard spec 465.2(1), "the engineer will not require the contractor to the quality management program specified under 460.2.8". Mixture testing should not be required for the Asphaltic Surface and Asphaltic Surface patching items. Will the department correct the PWL Mix Use Tables? | QMP will be per the standard specifications and special provisions. See Special Provisions, Article 15 Asphaltic Surface for more details. There will be no change to this portion of the PWL tables. | Mike Coleman | 9 | 2021-01-06 13:22 | 2021-01-08 10:05
20210112 | 20210112030 | 30 | Shoulder HMA Testing | Project 9304-11-70, the HMA Pavement Mixture Use Table shows PWL Incentive Air Voids as the Mixture acceptance for surface layer on the 3-foot shoulder from Sta 17+56 to 230+50, with Acceptance Density Testing by the Department, not Eligible for Incentive. This table also shows QMP Testing for Mixture Acceptance on both lower layer and upper layer pavements from Sta 230+50 to 413+10, with the same Density Acceptance as the preceding stations. It would be typical for the lower layer widening to be tested under the QMP plan per SS 460 for mixture acceptance, but those should also be eligible for incentive density. Additionally, it would be typical for a PWL paving project for the surface layer for the 3-5 foot shoulders from Sta 230+50 to 413+10 to have the mixture acceptance listed as PWL Incentive Air Voids HMA Pavement 460.2010, but remain as Acceptance Density Testing by the Department; Not Eligible for Incentive. This is how the remainder of the shoulder surface layer is shown. | The department will change the mixture acceptance from â€œQMP as per Standard Specificationsâ€ to â€œPWL Incentive Air Voids HMA Pavement 460.2010â€ for the upper layer for paved shoulders between STA 230+50 â€“ 304+68 and STA 306+84 â€“ 413+10. The estimated quantity for 460.2010 will be updated to reflect these changes. The Density Acceptance for these sections will remain as is. This will be part of Addendum 03. | Mike Coleman | 10 | 2021-01-06 13:37 | 2021-01-08 10:05
20210112 | 20210112030 | 30 | Sideroad Intersection HMA Testing | Following the procedures of a typical PWL HMA Paving project, we would expect the sideroad intersections to be tested for mixture acceptance following the PWL Incentive Air Voids HMA Pavement 460.2010, with Acceptance Density Testing by the Department; Not Eligible for Incentive, no different than the 3 and 4-foot shoulders over the milled surface. The PWL Mixture Use Tables in both Project ID's show mix acceptance for the sideroad intersections by QMP per SS 460, and Incentive Density HMA Pavement 460.2000. Is there a reason why the department has chosen these acceptance methods for the sideroad intersections? For consistency of PWL project reporting, would the department consider revising the HMA Pavement PWL Mix Use Tables? | The Density Acceptance in the PWL table of Project ID 9304-12-70 for sideroad intersections will be changed from â€œAcceptance Testing by the Department not Eligible for Incentiveâ€ to â€œIncentive Density HMA Pavement 460.2000â€. This matches the acceptance methods of Project ID 9304-11-70. Since the sideroad intersections are not part of STH 101 mainline, this quantity of HMA is not covered under the PWL Specifications. The current estimated quantity for 460.2000 is correct and will remain as is. This will be part of Addendum 03. | Mike Coleman | 11 | 2021-01-06 13:46 | 2021-01-08 10:05
20210112 | 20210112030 | 30 | Asphaltic Surface Patching, Undistributed Quantity | Project 9304-11-70 includes 675 tons of Asphaltic Surface Patching, item 465.0110, to correspond with the 5300 SY of Special Milling Roadway Repair, SPV.0180.02. However project 9304-12-70 also contains 540 tons of undistributed quantity under this item, with no further explanation as to what it should be used for. The bid pricing for 465.0110 will need to be figured as a blended rate for the patching on both project ID's, but the scope may vary significantly for this item between the two projects depending on the required use. Can the department provide further detail about how the 540 tons of undistributed Asphaltic Surface Patching will be used, and if it is unknown whether it will be needed, would the department consider reducing the quantity under 9304-12-70, so that it is not 45% of the scope/quantity of this bid item, for work that may or may not be needed? | A quantity of Asphaltic Surface Patching is to be included on all asphaltic pavement resurfacing contracts that are open to traffic. This item provides the contractor with the means to make minor repairs, such as filling potholes or pop outs that occur under traffic handling and milling operations. The difference in the repair operations between the projects is already accounted for in the special provisions (SPV.0180.01 Removing Asphaltic Surface Milling). No change is to be made in the contract quantities. | Mike Coleman | 12 | 2021-01-06 14:39 | 2021-01-08 10:07
20210112 | 20210112030 | 30 | Traffic Control - Pipe Installation | Addendum #2 says.. "Maintain access for through and local traffic, including emergency vehicles, at all times during construction." Several of the pipes are too deep to allow traffic to bypass without significant work to add a lane alongside the existing roadway. Will we be allowed to install those pipes under a complete road closure? | Per Article 3. Prosecution and progress, â€œone lane of traffic is to be maintained if the detour is not in placeâ€. Per Article 4. Traffic, â€œCulverts Replacement/Restored/Removed: All the culvert removal and replacement operations will take place under a detour.â€ While traffic is detoured the contractor will be able to close the roadway at that location. Local traffic must be able to exit from the area from a minimum of one direction. Work at multiple locations will not be allowed if local traffic is restricted. | Mike Coleman | 13 | 2021-01-06 15:56 | 2021-01-08 10:07
20210112 | 20210112031 | 31 | Existing footing removal and backfill pay limits | Both structures on this project show deep existing footings to be removed. The plan also shows the standard detail for pay limits of structure backfill. Historically, WisDOT had stated that if there are existing structures to be removed in front or below new structures the standard detail for pay limits of structure backfill would not be used and proper backfill quantities required for construction would be included. Is the intent to pay only backfill in the pay limits shown and contractors should include the cost of backfill needed to replace the existing structure in other line items? | Additional backfill required beyond the pay limits shown on the plans should be included in â€œexcavation for structures.â€ as noted on sheet 2 of the structure plans. | Mike Coleman | 1 | 2020-12-16 10:32 | 2020-12-18 07:00
20210112 | 20210112031 | 31 | backfill for structure under abutments | Based on as-builts and observations, the existing footings that need to be removed are roughly 6' under water. Given the cobble in the soil borings, dewatering to that level may be difficult for backfill purposes. Would the department allow a small masonry seal to be poured (presumably at contractor expense) if needed to dewater for backfill purposes | The design engineer is not opposed to a masonry seal at the contractors expense if that is their means to construct the abutments. They should be aware of any conflicts that could create with piling. | Mike Coleman | 2 | 2021-01-07 13:58 | 2021-01-08 10:13
20210112 | 20210112033 | 33 | Structure plan for C-55-19 | It appears that the structure plan for the culvert extension on C-55-19 was not included in the plan set. | The structure plan for the culvert extension on C-55-19 was inadvertently missing in plan set. The plans were added via addendum 1. | Jill Fehrman | 1 | 2020-12-17 11:40 | 2021-01-04 10:16
20210112 | 20210112033 | 33 | B-55-12 Widening | Traffic Control plans (sheet 74) reference the B-55-12 widening - see structure plans. We do not see anything for this structure widening in the structure plans. Are there missing sheets for this? | The B-55-12 plan were inadvertently missed in the plan set. The plan sheets will be added by addendum. | Jill Fehrman | 2 | 2020-12-21 10:03 | 2020-12-23 08:16
20210112 | 20210112033 | 33 | Temporary Bridge Widening B-55-12, Item SPV.0105.05 | It appears the the temporary bridge widening details for B-55-12 were not included in the plans. | The B-55-12 plan sheets were inadvertently missed in the plan set. The plan sheets will be added by addendum. | Jill Fehrman | 3 | 2020-12-21 11:00 | 2020-12-23 08:22
20210112 | 20210112033 | 33 | B-55-12 | Traffic control plans reference B-55-12 widening - see structure plans (note on sheet 74). There does not appear to be any information on the B-55-12 widening in the structure plans. Are there additional plans on this forthcoming? | The B-55-12 plan sheets were inadvertently missed in the plan set. The plan sheets will be added by addendum. | Jill Fehrman | 4 | 2020-12-21 11:15 | 2020-12-23 08:23
20210112 | 20210112033 | 33 | Item 08 203.0200 | Item 8 - 203.0200 description is Removing Old Structure 158+25.29 WB, should this be EB not WB? | Item 8 â€“ 203.0200 description should be Removing Old Structure 158+25.29 EB. | Jill Fehrman | 5 | 2020-12-21 13:47 | 2021-01-04 08:29
20210112 | 20210112033 | 33 | Thrie Beam Bullnose Terminal | There is not a standard detail in the plans for the bullnose terminal or thrie beam and the new detail is substantially more costly than the old detail. Also, the misc quantities on sheet 130 shows 3 terminals while the bid quantity is only 1, which is correct? | SDD 14B26 is the correct SDD to be used for the bullnose terminal or thrie beam. The bid quantity should match the miscellaneous quantity sheet with a quantity of 3 each. An upcoming addenda will address these issues. | Jill Fehrman | 6 | 2020-12-23 09:23 | 2021-01-04 10:11
20210112 | 20210112033 | 33 | High Tension Cable Barrier | Are driveable sockets an option for the HTCB given that the select crushed material is remaining in place? You cannot drill a 12" diameter hole through select crushed material. | Drivable sockets are not a currently allowed method. Please bid accordingly. | Jill Fehrman | 7 | 2020-12-23 10:40 | 2021-01-05 06:05
20210112 | 20210112033 | 33 | 4MT 58-34S | On Plan sheet 12 the typical sections show a 4MT 58-34S for the upper layer of the 7" HMA pavement. There is not a bid item with the 58-34S asphalt cement. We are thinking this should be 4MT 58-28S? | 4MT 58-34S for upper layer is correct. Th bid item will be added per addendum. | Jill Fehrman | 8 | 2020-12-28 11:22 | 2021-01-04 10:13
20210112 | 20210112033 | 33 | 4" HMA Pavement - Sheet 12 | The 4" HMA Pavement on sheet 12 of the plans shows a 3MT 58-28S for both layers. This should likely be a 4MT 58-28S for both layers? | AC Mix Specification: 4 MT 58-34 S (upper), 3 MT 58-28 S (lower) The typical section on sheet 12 will be updated via addendum.. | Jill Fehrman | 9 | 2020-12-28 12:36 | 2021-01-04 10:14
20210112 | 20210112033 | 33 | Electronic GPS Data Request | Please provide these files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112033/ Deanna, please create a link in the NW Region Preliminary Plans Page for proposal #33. | Mike Coleman | 10 | 2021-01-04 11:54 | 2021-01-11 13:59
20210112 | 20210112033 | 33 | Data Request | Please provide these files below: 1. Earthwork data, Excel spreadsheet xlsx file(s). 2. Design Schedule 3. Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112033/ | Mike Coleman | 11 | 2021-01-04 11:56 | 2021-01-11 14:00
20210112 | 20210112033 | 33 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch, Breaker Run and Select Crushed? | Base Aggregate Dense 3/4 Inch: 2.1 TON/CY Base Aggregate Dense 1-1/4 Inch: 2.0 TON/CY Breaker Run and Select Crush are in CY and no conversion factor was used. | Fred Schunke | 12 | 2021-01-04 11:58 | 2021-01-05 15:46
20210112 | 20210112033 | 33 | Breaker Run & Select Crushed Bid units to Tons | Can the Breaker Run & Select Crushed items be bid by the Ton vs the CY? By the TON would be the easiest method to measure in the field and the most accurate. If not acceptable, please give us the Departments conversion factor from TONS to CY that will be used during construction. | Select Crush can be changed to TON per addendum. Breaker Run is a small quantity for box culvert construction and will remain as it is. | Fred Schunke | 13 | 2021-01-04 12:07 | 2021-01-05 15:47
20210112 | 20210112033 | 33 | B.A.D 3/4 inch under Asphalt Shoulders | The plans shows using B.A.D 3/4 inch under the asphalt shoulders adjoining the PCC mainline pavement. B.A.D 1 1/4 inch is generally specified under pavements. Should the typical section show 1 1/4 base or is 3/4 base required in this instance? | Both B.A.D 3/4 inch or 1 1/4 inch are allowed under paved shoulders. The proposed typical referenced shows B.A.D 3/4 inch. | Mike Coleman | 14 | 2021-01-05 16:20 | 2021-01-06 12:25
20210112 | 20210112033 | 33 | Aggregate Design Conversion Factors vs Payment Conversion Factors (TONs/CY) | Will the department pay the contractor the Design Conversion Factors for Base Course and Select Crushed Items, if the material is measured inplace by the CY to convert to the TONs placed which then can be paid under the respective line item? If not what are the acceptable Payment Conversion Factors for these items: 3/4" Base Aggregate, 1-1/4" Base Aggregate & Select Crushed? | 3/4" Base Aggregate and 1-1/4" Base Aggregate are measured in TON Select Crushed Material will be changed to TON via addendum | Mike Coleman | 15 | 2021-01-05 16:28 | 2021-01-06 12:27
20210112 | 20210112033 | 33 | Chunked/Removed Asphalt & Concrete (Pavements) to be used in the Embankments | Will this project allow Chunked/Removed Asphalt & Concrete (Pavements) to be used in the Embankments? The earthwork summary says "Pavements is considered salvageable for other purposes and is not included in the quantity of useable material." If the contractor determines the cheapest use for the Pavements is Borrow/Embankment Material, can the contractor place it into the fills on the project? If not where in the specifications is that stated? | Standard Spec 207.2(1) -- For embankment, use engineer-approved materialsâ€¦ and we do not approve asphalt in fill. | Mike Coleman | 16 | 2021-01-05 16:57 | 2021-01-06 12:30
20210112 | 20210112033 | 33 | Structure C-55-19 | Can structure C-55-19 twin cell box culvert be two single cells laid side by side to create a twin cell | The contractor may furnish a two single cell precast concrete box culverts in lieu of the two-cell cast-in-place box culvert as shown in the plans with the acceptance of shop drawings by the Bureau of Structure Design Section. The contractor will need to verify that the hydraulic capacity of the box culvert remains per the contract plans. Specifically, the contractor will need to align the interior walls of any precast option with the existing interior wall of the box that is being extended as a part of this contract. Additionally, any potential approval by BOS will require details following what is shown on Bridge Standard 36.05, modified apron details meeting the new cross-sectional width of the box culvert, and modified details between the connections of the box culvert/apron and box culvert/wingwalls. | Mike Coleman | 17 | 2021-01-06 08:08 | 2021-01-06 12:04
20210112 | 20210112033 | 33 | Guardrail and HTCB | There is not an item for the Thrie Beam. Also, where is the HTCB being installed on the 1021-00-78 project? 2875' and 4 anchors are shown on the estimate but it does not appear to be in the plans or misc quantities. Are there borings for the HTCB anchor locations? | Thrie Beam item will be added per addendum. There should be no HTCB on CTH NN projects, those quantity will be removed per addendum. There are Cable Barrier Borings done on Carr Creek projects that will be added per addendum. | Mike Coleman | 18 | 2021-01-06 08:20 | 2021-01-07 07:08
20210112 | 20210112033 | 33 | Carr Creek Structures - Piers/Cofferdams | Structures 281, 282, 285 and 286 all have piers located within Carr Creek. Will underwater concrete pours of the piers be allowed? There is also minimal debris spec for the existing structure removals but no environmental protections designed for existing pier removals (281 & 282) and new pier construction (all 4 over Carr Creek). The existing pier footings at 281 and 282 appear to be in conflict with the piling of the new piers and will need to be removed. These footings are approximately 5-6' below the top of water and will take some time to be removed. In order to complete this work as well as construct the new piers on all 4 structures, without a cofferdam, it will require opening up an oversized excavation that will potentially encroach in the middle of the waterway. There is shoring designed to hold up the existing roadway by the piers but that does not seem adequate from an environmental standpoint. Should cofferdam bid items be added to the piers on all 4 structures? | Underwater concrete pours for the pile encased piers for bridges B-55-281/282/285/286 will be allowed. The existing bridge pier footings and piling do not need to be fully removed as a part of this project and the new pier piling should be able to be installed per plan accordingly. Per the specifications, removal of the existing structure needs to be done to an elevation at least 2 feet below finished ground line. Cofferdams are not needed for pier construction on this project. | Fred Schunke | 19 | 2021-01-07 08:30 | 2021-01-07 14:08
20210112 | 20210112033 | 33 | Question #14 - B.A.D 3/4 inch under Asphalt Shoulders | Based on the answer of Question #14, Please update the proposed typical section to allow both B.A.D 3/4 inch and/or 1 1/4 inch under the Asphalt Shoulder at the contractor option in an addendum so that during construction there is no confusion what is allowable. |  |  | 20 | 2021-01-07 08:42
20210112 | 20210112033 | 33 | Impossible Schedule | Both projects have 2 mostly full construction years to complete the designed work but for some reason the work is not split equally between the construction years making the work in 2021 impossible to be completed by October 15th. On Project 1021-78/79, Please move stage 2B completion to year 2022. By changing the Interim Completion to complete Stage 2A by November 12th, 2021 and move traffic to its respective lanes over winter (this will save the tax payers money because there is one less traffic switch required on EB Lanes). On Project 1021-77/78, Please move stage 4 completion to year 2022. By changing the Interim Completion to complete Stage 3 by November 12th, 2021 and move traffic to its respective lanes over winter (this will save acceleration costs). Also for both projects, please remove the October 15th date in both years 2021 & 2022 requiring Asphalt and Concrete to placed by this date (this is not achievable, the full construction year is required). | Contractor will be required to meet the project schedule as is and should bid accordingly. | Mike Coleman | 21 | 2021-01-07 09:32 | 2021-01-08 10:12
20210112 | 20210112033 | 33 | 18-Inch Temporary Culvert Pipes | What is the material specifications for the 1,400 LF of 18-Inch Temporary Culvert Pipes? | (3) Under the Culvert Pipe Temporary bid items, use either new or used culvert pipe in a condition suitable for the purpose intended. | Mike Coleman | 22 | 2021-01-07 14:22 | 2021-01-08 10:11
20210112 | 20210112033 | 33 | Design Schedule | Please provide the Design Schedule. |  |  | 23 | 2021-01-08 12:42
20210112 | 20210112034 | 34 | IRI Ride | This project has the item for IRI ride. We do not see any continuous pavement surfaces that meet the minimum 1,500 LF requirement? | That is correct, there is not 1500 LF of continuous pavement in this project. The IRI ride item will be removed via upcoming addenda. | Jill Fehrman | 1 | 2020-12-29 13:51 | 2021-01-05 06:10
20210112 | 20210112034 | 34 | Common Excavation | Stage 3 common ex. Sheet 37 Is there 1206 cy of total waste or is there more available fill? |  |  | 2 | 2021-01-07 10:39
20210112 | 20210112034 | 34 | Conduit Quantities | Are the 3" Nonmetallic and 2" Conduit Special quantities accurate? It seems as though they may be reversed in the quantities. | The 3" Nonmetallic and 2" Conduit Special quantities were reversed in the project Miscellaneous quantities table. The Conduit was labeled correctly on the plan sheets. The quantities of each are : 652.0235 Conduit Rigid Nonmetallic Schedule 40 3-Inch = 30 LF 652.0605 Conduit Special 2-Inch = 288 LF | Jill Fehrman | 3 | 2021-01-07 18:01 | 2021-01-11 10:09
20210112 | 20210112035 | 35 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112035/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-12-13 08:38 | 2020-12-14 11:38
20210112 | 20210112035 | 35 | Staging. | Is there a reason why the curb and gutter and related work can't be performed in Stages 1 and 2 and is shown as being performed in Stage 3? | The Traffic Control Stages 1, 1A, 1B, 2 and 2B found on Pages 76-100 of 20210112035plan.pdf, includes a legend and work zone that shows that the curb and gutter and related work is anticipated to be completed during Stages 1, 1A, 1B, 2 and 2B. | Jill Fehrman | 2 | 2020-12-27 18:18 | 2020-12-29 02:21
20210112 | 20210112035 | 35 | Temp. pavement marking on page 74 | On plan sheet 74 temp pavement marking is shown for temp crosswalks, there is no quantity listed in the quantities. Will this be paid for as 4"removable tape? | Yes, this quantity will be paid for as Temporary Marking Line Removable Tape 4-Inch. | Fred Schunke | 3 | 2021-01-06 09:03 | 2021-01-07 14:40
20210112 | 20210112035 | 35 | Adjusting Manhole Covers | In the specials item #34 Adjusting manhole covers does not match what was done on the previous project. The best way to construct these due to the SMA and traffic is to raise them after the surface layer of HMA is completed. Concrete was poured around them after they were raised. There was an addendum in the previous project (Proposal 29 December 2019 Letting) attempting to address this. They missed the part where we wait until surface is completed to raise them, but that is the way it was constructed. It does at least specify the concrete will be poured around them. Will the manhole adjustments be completed in the same manner as the previous project with concrete poured around them? | Yes, the intent is to complete the manhole adjustments in the same manner as the previous project with concrete poured around them. An addenda was just submitted. | Fred Schunke | 4 | 2021-01-07 08:51 | 2021-01-07 14:58
20210112 | 20210112036 | 36 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2020-12-10 11:59 | 2020-12-15 12:21
20210112 | 20210112036 | 36 | Grade Shape Finish Item | What work is getting completed under this item? The cross sections seem to show full roadway reconstruct through the guardrail areas. The section from 795 to 801 gives a quantity of 13,200 CY of common ex that may be questionable. Thanks | Work under the Grade Shape and Finish item is detailed in section 614.3.2.5 of the standard specification and relates only to embankment items. No roadway work is included in this item. Full roadway reconstruct is not required for these areas. Quantities will be double checked and an addendum issued if appropriate. | Jill Fehrman | 2 | 2020-12-14 08:02 | 2020-12-28 06:56
20210112 | 20210112036 | 36 | 209.1500 Backfill Granular Grade 1 | Is the Granular Backfill 1 the only material being used to backfill pipes or is Granular backfill 2 also being used to backfill the pipes? | Yes, Backfill Granular Grade 1 is the only material being used to backfill the pipes. The construction detail indicating use of Backfill Granular Grade 2 will be corrected with a forthcoming addenda. | Jill Fehrman | 3 | 2020-12-29 09:58 | 2021-01-05 06:12
20210112 | 20210112036 | 36 | #220 Special 02. HMA Lane Repair | SPV 02 HMA Lane Repair is being paid for by the linear foot. Is there an intended minimum or maximum width to this repair? Thanks. | Yes, the estimated dimensions of the Lane Repair are a minimum repair width is 5â€™ and a maximum repair width is 14â€™. | Jill Fehrman | 4 | 2021-01-04 16:31 | 2021-01-11 11:40
20210112 | 20210112037 | 37 | Winter Suspension | Will the roadway need to be re-opened to traffic for the Winter Shutdown? | No. Bridge work is not anticipated to be complete to a stage that would allow re-opening to traffic during Winter shutdown. | Jill Fehrman | 1 | 2020-12-18 16:33 | 2021-01-11 08:57
20210112 | 20210112038 | 38 | Design Questions | We have some concerns regarding the 2" CIR over base and completing this within in such a short distance which also has turnlanes/intersection. Also we concerned about the process of boring our ahead of the Milling/CIR process per the * comments on the cross sections. |  |  | 2 | 2021-01-06 16:53
20210112 | 20210112040 | 40 | #40 STH 81 Lancaster - Platteville | 1) Please provide CAD Files & Surfaces in .XML format both existing and Proposed tops of Subgrade. 2) Please provide Earthwork tables & end areas in excel format. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210112040/ | Mike Coleman | 1 | 2020-12-14 15:46 | 2020-12-15 12:41
20210112 | 20210112040 | 40 | Fuel Cost Adjustment | Will ASP 5, Fuel Cost Adjustment be added to the contract? | ASP-5 was inadvertently omitted from this proposal. An addendum has been issued to add ASP-5 to the proposal. | Jill Fehrman | 2 | 2020-12-23 13:53 | 2020-12-29 02:43