## qandasearchletting_results
Date: | 2022-03-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220308 | 20220308001 | 1 | Abatement Quantities | Are there asbestos-containing material quantities listed for this project? | Structures B-11-0137, B-11-0138, B-11-0104 were tested and no asbestos containing materials were found. Structure B-11-0001 was tested and asbestos was found in the gaskets for the railing mounting brackets. The work on this structure will not impact this material so no quantities for asbestos abatement were provided. The asbestos reports can be found at the following location: https://wisdot.box.com/s/3ihaonzi3rcawwp79m1vdipxkfzpjjxa or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-02-22 09:12 | 2022-02-23 09:14
20220308 | 20220308002 | 2 | Removal of wings & abutment backwalls on B-29-21 & B-29-22 | How is the removal of the wings & abutment backwalls paid for on structures B-29-21 & 22? Will a Removing Existing Structure item be added? | An addendum will be prepared to add the item 203.0220 Removing structure. | Mike Coleman | 1 | 2022-02-23 15:15 | 2022-03-01 07:08
20220308 | 20220308002 | 2 | Concrete Masonry Decks Vs Concrete Masonry Bridges B-29-21 and B-29-22 | The plans do not call out which items will be paid for each location. Are we to assume Concrete Masonry Decks is the concrete for joint repair locations along with parapets while the Concrete Masonry Bridges are for backwall repairs/wing tops? | Concrete masonry decksâ€™ qty includes: areas of deck prep type1 and concrete for joint repair locations. Concrete masonry bridges includes: backwall replacement (minus 1â€™x1â€™ paving block for joint repair); upper-wing replacement; and new 30â€ tall parapet on abutment wings. | Mike Coleman | 2 | 2022-02-25 13:02 | 2022-03-01 07:09
20220308 | 20220308002 | 2 | Deck Patching | Will there be another item for filling in the Type 1 Deck Prep such as Deck Patching or will it be paid under another item? | Concrete masonry decksâ€™ qty includes: areas of deck prep type1 and concrete for joint repair locations. Concrete masonry bridges includes: backwall replacement (minus 1â€™x1â€™ paving block for joint repair); upper-wing replacement; and new 30â€ tall parapet on abutment wings. | Mike Coleman | 3 | 2022-02-28 15:23 | 2022-03-01 12:31
20220308 | 20220308002 | 2 | Shear Lug Detail | On sheet 1 of both B-29-21 and B-29-22 there is a shear lug detail. Is this for information only, or are we supposed to be adding these shear lugs. If so how will this be paid? | Shear lug detail, included on sheet 1 is for information purposes. Removal details on sheet 4 include note: "Completely remove existing concrete end diaphragm btwn. girders. During removal, avoid damage to exist. girders & shear lugs embeded in concrete. Replace damaged shear lugs as per detail shown on General Plan Sheet." If damage to shear lug occurs during concrete removal & it requires replacement payment would be incidental to joint repair bid item. | Mike Coleman | 4 | 2022-03-01 10:45 | 2022-03-02 09:30
20220308 | 20220308003 | 3 | Abatement Quantities | Are there asbestos-containing material quantities listed for this project? | There are asbestos-containing material quantities listed in the structure plan MQ table, Special Provisions and quantities for abatement in the quantities. | Mike Coleman | 1 | 2022-02-22 09:13 | 2022-02-23 11:04
20220308 | 20220308003 | 3 | Densities on 5 MT leveling layer | Just want to confirm with the Department that there will be no density requirements on the 1-inch leveling layer. | Correct, there are no density requirements on the 1-inch leveling layer. | Mike Coleman | 2 | 2022-02-22 10:22 | 2022-02-23 11:05
20220308 | 20220308003 | 3 | Concrete Barrier Surface Repair - Method of Measurement | Could the method of measurement for Concrete Barrier Wall Surface Repair be changed to SF rather than EA? This would be more in line with standard concrete repair items. | The same item and units were used on a previous project that repaired the NB barrier wall on I-39 at this location. (Proposal 20200414002) Item unit will not be changed. | Mike Coleman | 3 | 2022-02-23 11:34 | 2022-02-24 14:13
20220308 | 20220308005 | 5 | Notice to Proceed | Due to the time needed to award the project, execute contracts, approve schedule (14 days prior to preconstruction meeting) and ECIP, 7 day advanced closure notification, and any necessary utility relocations identified in the special provisions as TBD, the start date of April 18th 2022 seems unlikely. Will the Department consider removing the start date and will days be charged starting on April 18th regardless of construction activities and road closures starting? | The department will not remove the start date requirement, but will issue an addendum changing the current Article 3 Prosecution and Progress language to state â€œ The Notice to Proceed will be issued such that work shall start no later than May 2, 2022 â€. Time charges will start on May 2 to ensure the work is completed during the WIS 67 resurface project railroad crossing work stage that uses the same detour. | Mike Coleman | 1 | 2022-02-24 08:17 | 2022-02-24 14:12
20220308 | 20220308007 | 7 | Lane/ramp closures | What is the allowable lane closure hours for USH 51 SB right turn lanes to WB entrance ramp? | The USH 51 SB right turn lane to the STH 30 WB entrance ramp may be closed during the 28-day period that the STH 30 WB entrance ramp is being constructed. | Mike Coleman | 1 | 2022-03-03 13:53 | 2022-03-07 14:00
20220308 | 20220308009 | 9 | Aesthetic Details for R-13-360 and R-13-361 | This clarification request is regarding the architectural form liner details for MSE Walls provided on Sheets 617 and 625. Vendors have tried to make 12" coursing fit on 5-ft. high panel in the past and ended up with too many problems. If the panel joint does not match with the joint in the coursing, we have to make lots of liners for lots of special cases. We may have to make lots of liners to make very unique liners due to the break in the blocks at the panel joints. The industry experience during the last thirty years in using coursed forms liners on MSE walls with staggered horizontal joints suggests the use of 7.5â€, 15â€ or 30â€ coursing as other owners have used successfully in the past projects. Therefore, vendor requests the owner to reevaluate the form liner requirements for MSE Walls for this job. We request the use of 7.5â€, 15â€ or 30â€ instead of 12" courses. | 15â€ coursing will be acceptable for use on R-13-360 and R-13-361. | Mike Coleman | 1 | 2022-02-04 12:18 | 2022-02-11 10:05
20220308 | 20220308009 | 9 | Soil Borings | There are several borings shown near the deep 96" Storm Sewer Piping. In order to determine construction methodologies and staging, we need to see the soil borings the DOT has taken. Please provide a soils report and a geotechnical baseline report for the proposed tunnel work if available. Also due to the mixed face conditions i.e. bed rock and wet sands, please give us the compressive strength of the bed rock as well. | The geotechnical report can be found at the following location: https://wisdot.box.com/s/zqci595or7wz6hodjh2tw6xbaxcxo5ka or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-02-09 13:38 | 2022-02-14 14:10
20220308 | 20220308009 | 9 | Soil Borings | There are several soil borings indicated on the plans for the 96" Storm Sewer section that is in/out of rock. Can you please provide them as well as rock cores and compressive strengths for the rock? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/zqci595or7wz6hodjh2tw6xbaxcxo5ka or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-02-10 08:03 | 2022-02-14 14:10
20220308 | 20220308009 | 9 | 532.5120 Sturcture # Discrepancy | In the proposals schedule of items it identifies Structure #Sta. 143+10, but in the plans it looks like this structure is identified as Structure #Sta. 143+15. Can you please confirm the correct structure #? Also, in the proposals schedule of items it identifies Structure #S-13-856, but in the plans it looks like this structure is identified as Structure #S-13-586. Can you please confirm the correct structure #? | For the first question the proposal schedule should match the plans and be Sta 143+15. For the second question the structure number in the proposal schedule should be S-13-586 to match the structure plans. | Mike Coleman | 4 | 2022-02-10 08:49 | 2022-02-14 13:59
20220308 | 20220308009 | 9 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 5 | 2022-02-11 11:55 | 2022-02-14 13:44
20220308 | 20220308009 | 9 | 532.5120 Structure Elevations, Lengths and Heights | The following information is required for Structures 143+15, 142+63, 153+40, 154+06, and 160+47. This info was provided for Structure S-13-586; Foundation Elevation Road Elevation Lengths of sign arms Length of luminaire arms Luminaire mounting height | The information for these are included in the construction details. | Mike Coleman | 6 | 2022-02-21 11:05 | 2022-02-21 15:42
20220308 | 20220308009 | 9 | Soil Boring Clarifications | Soil borings B-12, B-11, B-10, B-9, and B-8 shown on plan sheets 315 and 316 do not coincide with the geotechnical report. the geotechnical report shows RB-1 thru RB-6 and B-7. Please clarify/provide boring logs for these. | The boring map and logs for the referenced boring numbers can be found at the following location: https://wisdot.box.com/s/zqci595or7wz6hodjh2tw6xbaxcxo5ka or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 7 | 2022-02-21 14:38 | 2022-02-22 13:16
20220308 | 20220308009 | 9 | University Bay Drive Closure for Pedestrian Overpass | Under Prosecution and Progress Article C5 it states that "University Bay Drive will be allowed to be closed for 1 night for the installation of the pedestrian overpass, and be open by 6AM". It does not state when University Bay Drive can be closed the previous day. What time can this closure be put into place? | The closure can take place at 7:00 PM after peak hour traffic. | Mike Coleman | 8 | 2022-02-22 09:04 | 2022-02-23 11:06
20220308 | 20220308009 | 9 | 532.5120 Structure Elevations, Lengths and Heights | Could you please direct me to the pages that include the following information for structures 143+15, 142+63, 153+40, 154+06, and 160+47. I cannot find in the Construction Details section. Foundation Elevation Road Elevation Lengths of sign arms Length of luminaire arms Luminaire mounting height | The details are on pages 57-61. | Mike Coleman | 9 | 2022-02-22 10:29 | 2022-02-23 09:16
20220308 | 20220308009 | 9 | Reinforcement Length for Back to Back Walls - R-13-360 and R-13-361 | Aspect ratio of a back to back wall is the width of the back to back wall to the height of the wall measured from the top of the leveling pad to the top of pavement. Note on Sheet 613 and 622 state that the back to back walls shall be tied together if the minimum reinforcement length of 70% of wall height can not achieved. Connecting back to back is not recommended since such designs had several performance and construction issues. We definitely would want to overlap instead. The vendors have designed have designed and are comfortable with the design of back to back walls using overlapping strips with aspect ratios as narrow as 0.5. Vendor requests that back to back walls be designed using overlapping strips instead of tying together if the minimum reinforcement length of 70% of wall height can not achieved | After discussion with the structure designer, BOS and Central Office Geotech hereâ€™s the response: The contractor should bid the plans and specifications as they are shown. Specific contractor design issues can be addressed as part of the standard shop drawing review process. | Mike Coleman | 10 | 2022-02-22 10:46 | 2022-03-07 09:46
20220308 | 20220308009 | 9 | 532.5120 Further Follow-Up | There are critical bidding details not shown on the Construction Details pages that are needed. Roadway elevations and top of footing elevations are needed. Height of upright to the lighting units are needed. Length of mast arm shows some of the lengths, but overall length is needed. There is a note to see lighting plan for more information, but I can't find any structure information in the lighting plan to address this. Furthermore, do none of these structures receive structure numbers? Also, why is there no corresponding Section 531 Drilling Shafts bid items or Foundation bid items for the footings to these structures? Thank you in advance for clarifying. | Additional information will be provided on the detail sheets in a forthcoming addendum. | Mike Coleman | 11 | 2022-02-24 10:04 | 2022-02-28 11:04
20220308 | 20220308009 | 9 | PREFAB STEEL TRUSS BRIDGE DELIVERY DATE | POTENTIAL SUPPLIERS HAVE CONCERNS WITH PROPOSED DELIVERY TIME FRAME FOR THIS STRUCTURE STATING IT WILL PROBABLY NOT BE AVAILABLE UNTIL AFTER THE 10/15 INTERIM COMPLETION DATE. CAN REVISIONS BE MADE TO THE CONTRACT TIME FRAME TO ACCOMMODATE FOR THIS? | The project should be bid based on the current specifications. | Jill Fehrman | 12 | 2022-02-25 15:07 | 2022-03-04 16:02
20220308 | 20220308009 | 9 | Monotube Cantilever Type II (structure) | Original plan and addendum does not provide Pole Heights or Arm lengths which are critical for manufacturer to be able to provide a price quote.If this information cannot be provided, will the DOT consider providing the structures for contractor install? | Additional information will be provided on the detail sheets in a forthcoming addendum. | Mike Coleman | 13 | 2022-02-28 09:07 | 2022-02-28 13:36
20220308 | 20220308009 | 9 | Trenchless Contractor Qualifications | Would the Department be willing to modify the requirements to either 1) min drive length of previous projects to 500 feet or 2) pipe diameter of previous projects to 48 inches diameter? This would open up the pool for potential bidders to provide a more competitive bid. | We are acceptable with the modified requirements and will update the special provision in a forthcoming addendum. | Mike Coleman | 14 | 2022-03-01 00:14 | 2022-03-02 06:39
20220308 | 20220308009 | 9 | HOBAS open cut | Hobas is specified under Trenchless requiring min stiffness 140 for jacking. HOBAS also fabricates pipe for open cut and is requesting to be included as an option for all 96" piping as follows: Trenchless Min stiffness min stiffness 140 Direct Bury Min stiffness 46 | The items should be bid as presented in the project plans and specifications. | Mike Coleman | 15 | 2022-03-01 09:41 | 2022-03-02 18:25
20220308 | 20220308009 | 9 | Steel Truss Mesh Panel Finish | Note on sheet 572 includes protective screening as painted green along with the truss and railing, however other areas denote mesh panel screening on the bridge to be stainless steel. Please advise the required finish for the mesh panel screening that will be attached to the steel truss bridge. | The stainless steel protective screening is to receive a painted finish as stated on the plans. | Mike Coleman | 16 | 2022-03-02 09:49 | 2022-03-03 09:40
20220308 | 20220308009 | 9 | Railing Steel Ped. Ornamental - Artwork | Please provide the full artwork file for the railing steel pedestrian ornamental. | The project bid should be based on the details in the plan. The artwork file will be provided to the awarded contractor. | Jill Fehrman | 17 | 2022-03-03 07:03 | 2022-03-04 12:01
20220308 | 20220308009 | 9 | Railing Steel Ped. Ornamental - Pickets | The section thru railing points has key notes 6A and 11 pointing at the traditional picket location. Note 6A calls for the traditional 1" x 1" picket, while note 11 calls for the 1" steel plate. Could the entire picket just be cut from 1" plate instead of building up shapes as detailed in Note 11. The biggest issue will be galvanizing and paint finish. The silicon and phosphorus in the weld metal will cause a thicker coating of zinc at the built-up locations. Additionally, unless providing full-pen welds, there will be an air gap which if the weld isn't fully sealed or if cracks develop in the future it will cause rust bleeding. | The entire picket may be cut from 1â€ plates. | Jill Fehrman | 18 | 2022-03-03 07:07 | 2022-03-04 11:53
20220308 | 20220308009 | 9 | Storm Sewer Trench Backfill | Does the Department intend to base the storm sewer trench backfill on the WisDOT Standard Specifications or on the City of Madison Standard details? |  |  | 19 | 2022-03-03 11:30
20220308 | 20220308009 | 9 | Storm Structures | City of Madison requires that all storm structures to be bid as cast-in place with pre-cast possibly being approved post-bid. For structures that are listed as round with a diameter sizing, may this be bid as a square cast-in place structure with the same inside dimension? | Yes, round storm sewer structures may be bid as square however, other underground utilities will need to be reviewed to determine potential conflicts from the larger structure. | Mike Coleman | 20 | 2022-03-03 19:04 | 2022-03-07 09:40
20220308 | 20220308010 | 10 | HMA 4LT Pavement, Asphaltic Surface, Incentive HMA Density | Looking through the plan set typical proposed sections it states that the Bench Bump Outs are going to be Asphaltic Surface but the multiuse path and Adams Street is 4LT Pavement that is under the QMP Spec. Wouldn't it better if all the mix fall under the Asphaltic Surface due to the type of paving on the path? The Incentive HMA Density should also be eliminated as well because the due to the type of paving it shouldn't fall under the density because there could be an issue when compacting the mix to cause structural damage to the new retaining wall being installed next to the path. | An addendum will be issued to eliminate items 460.2000 Incentive Density HMA Pavement and 460.5224 HMA Pavement 4LT 58-28 S. Quantities under 460.5224 HMA Pavement 4LT 58-28 S will be moved to the 465.0105 Asphaltic Surface item. | Mike Coleman | 1 | 2022-02-18 15:38 | 2022-02-25 09:13
20220308 | 20220308010 | 10 | Hand Railing & Hand Railing Anchors | On Sheet #6 on the first typical from STA 141+10 - 143+20 it shows the hand railing going through the asphalt. Is the intent to have an anchor and hand put up before the asphalt is laid and pave around the hand rail? Or is the intent to install the hand rail after the asphalt is laid? | I would defer to this as a contractorâ€™s means and methods to provide a final product that meets plans and specs. The contractor is required to pour concrete bases for the railing support. It is by the contractors means and methods to either pave first and then cut out the asphalt areas to pour the bases or to pour all the concrete bases and then pave around them. They should reference the construction detail on page 9 as well for installation of the concrete bases. | Mike Coleman | 2 | 2022-02-25 14:49 | 2022-02-28 11:47
20220308 | 20220308010 | 10 | Hand Railing & Hand Railing Anchors STA 141+10 - 143+20 | On Sheet #6 the first shows the hand railing going through the asphalt. Is the intent to install the hand railing or hand railing anchors before the asphalt is laid down or is the intent to install the hand railing after the asphalt is laid down? If the hand railing is install after the asphalt is laid down would there be an anchor put in then have to be paved around? | I would defer to this as a contractorâ€™s means and methods to provide a final product that meets plans and specs. The contractor is required to pour concrete bases for the railing support. It is by the contractors means and methods to either pave first and then cut out the asphalt areas to pour the bases or to pour all the concrete bases and then pave around them. They should reference the construction detail on page 9 as well for installation of the concrete bases. | Mike Coleman | 3 | 2022-02-25 14:59 | 2022-02-28 11:46
20220308 | 20220308013 | 13 | BACKPLATES | Number 56. traffic signal faces. In the specs states the backplates shall be a reflective yellow. The traffic signal plan does not show any of the signal heads with reflective backplates. Can you please confirm if the backplates should have reflective yellow tape, and if so should it be 2 inch tape? | The backplates will not be reflective, an addendum will be issued accordingly. | Mike Coleman | 1 | 2022-02-17 14:49 | 2022-02-22 11:30
20220308 | 20220308013 | 13 | Can the design schedule be provided? |  | The design schedule can be found at the following location: https://wisdot.box.com/s/4g6l8tlwx4ti6so8j34vkmej3qbl14vw or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-03-05 12:20 | 2022-03-07 10:24
20220308 | 20220308013 | 13 | Extending morning opening hours for nighttime work. | Can the morning opening hours be extended to later than 5:30am? The shopping center doesn't open until after mid-morning and the businesses are largely offices generally without huge volumes of traffic and little volume unit after 7:00am. | Bid per the special provisions. | Mike Coleman | 3 | 2022-03-05 13:19 | 2022-03-07 11:43
20220308 | 20220308014 | 14 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 1 | 2022-02-11 11:56 | 2022-02-14 13:45
20220308 | 20220308014 | 14 | Traffic Signal Controller | We were unable to locate in the specials/specs or in the plans for this project what traffic signal controller will be used in the cabinet. Can you please confirm what traffic signal controller will be used? | Per the Special Provisions article Transport and Install Traffic Signal Cabinet, Item SPV.0060.18. â€œMilwaukee County will program the controller and provide at traffic signal turn-on.â€ The traffic signal controller will most likely be an Econolite. | Mike Coleman | 2 | 2022-02-15 12:31 | 2022-02-16 06:52
20220308 | 20220308014 | 14 | Can the soils report be provided? |  | The geotechnical report can be found at the following location: https://wisdot.box.com/s/ws6j8og6k50t052iupi52kcpxfdcrsyn or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-02-26 15:53 | 2022-02-28 12:09
20220308 | 20220308014 | 14 | DOT Site | Could contractors utilize the Northwest corner of the intersection of 94 and Rawson for crushing concrete from the Rawson project for the Rawson project? We have inquired about this property before, and we were told it was for DOT project use â€“ we just donâ€™t remember who in the SE region we got that information from. | WisDOT cannot commit to use of the site in question at this time. The successful bidder may make a proposal through the construction engineer if they wish to use the site. WisDOT makes no guarantee that the site will be ultimately available for use by the successful bidder. | Mike Coleman | 4 | 2022-03-01 16:52 | 2022-03-07 14:01
20220308 | 20220308015 | 15 | SPV.0090 Special 12 Watermain DI CL 53 12" | With current supply chain lead times on DI pipe, will the City allow for C900 DR18 to be utilized on this project? | The City will allow the C900. | Mike Coleman | 1 | 2022-03-03 08:25 | 2022-03-07 13:19
20220308 | 20220308017 | 17 | Can the Soil Report please be provided? |  | A soils report was not done for the project due to the nature of the work. | Mike Coleman | 1 | 2022-02-26 15:31 | 2022-02-28 11:33
20220308 | 20220308017 | 17 | Can the Design Schedule be provided? |  | The design schedule can be found at the following location: https://wisdot.box.com/s/6fz45l4nmj8ppnvzwjc5zka9dzvdxl6e or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-02-26 15:52 | 2022-02-28 11:39
20220308 | 20220308018 | 18 | Underwater Pier Construction | Please advise if it is acceptable to pour the new piers underwater. | It is acceptable to place the pier concrete underwater since the observed water elevation noted on bridge drawing 1 of 13 is less than 5-ft above the bottom of the pier concrete elevation. | Mike Coleman | 1 | 2022-03-02 15:34 | 2022-03-03 08:57
20220308 | 20220308020 | 20 | MANHOLE 70A 8 FT DIAMETER | ON PLAN SHEET 34 MANHOLE 70A 8 FT DIAMETER LOOKS TO HAVE A SUMP. IF A SUMP IS NEEDED PLEASE ADVISE THE DEPTH OF SUMP REQUIRED. | Sump shall have a 2â€™ depth. An addendum will be issued to correct the miscellaneous quantities table. | Mike Coleman | 1 | 2022-02-23 07:39 | 2022-02-24 08:39
20220308 | 20220308020 | 20 | does the steel run entire length of the curb & gutter? |  | As noted on the construction detail on page 6, longitudinal drilled tie bars are only required at the match points between existing and proposed curb and gutter. All other tie bars shall be installed per the standard detail drawing for concrete curb and gutter. | Mike Coleman | 2 | 2022-03-02 10:07 | 2022-03-03 09:33
20220308 | 20220308021 | 21 | Pavement Markings | Good morning, On plan sheet 115, there is a note (*) that the quantity of 4" epoxy includes a second application to be applied after the rumble strip operation. This is typical of projects like this. However, the first application is usually a temporary epoxy bid item rather than the regular 4" item due to the fact that it is to be placed on the same day as paving prior to the rumble strip operation. Can you clarify if the markings that are to be placed prior to the rumble strips are to be placed daily after paving as would be the case for a temporary or same day item or if they are to be placed 1 time as would be the case under a regular epoxy item? Will an addendum be issued to address this matter? Thank you. | We included temporary raised pavement markers in lieu of temporary or same day pavement marking. Standard Spec 646.3.1.1 (6) says pavement marking must be applied within 7 days of mainline paving. The intent was apply mainline pavement marking once and then re-apply in locations if centerline rumble strips if rumbles were not installed prior to pavement marking needing to be applied. Standard Spec 646..3.1.1 (6) â€œ) If the roadway is open to traffic use temporary raised pavement markers or apply temporary same day marking. Apply permanent marking within 7 days of completing mainline paving. If the roadway is closed during construction, apply permanent marking before opening to traffic.â€ | Mike Coleman | 1 | 2022-02-22 10:21 | 2022-02-22 13:21
20220308 | 20220308021 | 21 | Asphaltic Surface Driveways & Field Entrance VS 4 MT 58-28 | On sheet 10 the butt joint detail for asphaltic driveways states "asphaltic driveways shall be paid for as HMA TYPE 4 MT 58-28S" however there is also an asphaltic surface driveways and field entrances pay item. Can you please clarify the difference between one driveway that may be paid under 4 MT vs one driveway that may be paid under asphaltic surface driveways & field entrances Thanks, | The intent is to pay for all the driveways with butt joins as HMA TYPE 4 MT 58-28S and pay for the 5 driveways identified on the Plan Detail Sheets as â€œPave Entrance to Right of Wayâ€ with Asphaltic Surface Driveways & Field Entrances. The approximate locations of those driveways are: â€¢ Sta. 115+50 LT â€¢ Sta. 150 LT â€¢ Sta. 283 LT â€¢ Sta. 283 RT â€¢ Sta. 323 LT | Mike Coleman | 2 | 2022-03-02 16:42 | 2022-03-03 11:38
20220308 | 20220308022 | 22 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 1 | 2022-02-11 11:57 | 2022-02-14 13:48
20220308 | 20220308022 | 22 | Geotechnical Report | Can the geotechnical report be posted? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/erxwby74ruhm8llddbetnu6m9w1efwa5 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-02-14 13:49 | 2022-02-14 13:54
20220308 | 20220308022 | 22 | Removing Structure Over Waterway 91+69 | Can more information be provided on the existing Concrete Box Culvert @ Sta 91+69 that is called out to be removed? Possibly an original construction plan or as-built. | The existing box culvert structure at Sta. 91+69 does not have a known structural number and as-built plans are not available. The attached construction detail was included as part of a previous private development project to the south of the roadway. This information has not been verified. Bidders are encouraged to investigate the existing structure in person. You can find a detail of the structure at the following location: https://wisdot.box.com/s/erxwby74ruhm8llddbetnu6m9w1efwa5 or can be accessed on the HCCI March bid letting page under Supplamental Information. | Mike Coleman | 3 | 2022-02-23 13:55 | 2022-02-24 14:15
20220308 | 20220308022 | 22 | Railroad Flagging | In the special provisions for the Soo Line Railroad Company (CP) it states that 50% of flagging costs will be reimbursed by the department under the "Railroad Flagging Reimbursement" item. However, the special provision item for the Union Pacific Railroad Company does not have the same provision. Will 100% of the flagging costs associated with the Union Pacific Railroad Company be the responsibility of the contractor? | Railroad flagging reimbursement is intended to be used for the Soo Line Railroad Company (CP) as that is anticipated to take longer than 14 days. Flagging for work at the Union Pacific Railroad crossing is anticipated to be much shorter in duration due to less work being performed at this crossing. The contractor is responsible for 100% of the flagging costs at the Union Pacific Railroad. | Mike Coleman | 4 | 2022-02-24 10:13 | 2022-02-28 12:19
20220308 | 20220308022 | 22 | Excavation in fill sections | Provided there appears to be enough suitable existing topsoil obtained from proposed cut sections to cover future slopes, will all excavation of unsuitable materials in proposed fill sections, below proposed subgrade and within the roadway foundation (i.e. existing ditches) be measured and paid as common excavation prior to placing fill per standard spec and does this area need to be backfilled with breaker run? Can suitable fill material be used in this area? The plans do not appear be accounting for the all the potential excavation volumes of this area based on stationing listed in construction details for EBS and backfilling language listed in earthwork table adds further confusion as to where breaker backfill should be used given there are large fill areas that will likely additional excavation of unsuitable material prior to fill placement. Please clarify | Excavation on the project will be paid for either by Excavation Common (205.0100) or Excavation Marsh (205.0400), as appropriate and as noted on the plans. The Standard Specifications are to be followed for calculating payment of excavation and salvaged topsoil quantities. Breaker Run is to be used in EBS areas as shown on the construction details. Suitable fill material can be used outside of Breaker Run or Backfill Granular Grade 2 areas. Refer to the Marsh Excavation construction detail for an example. The plans correctly account for all excavation and fill material per the standard specifications. | Mike Coleman | 5 | 2022-03-05 15:15 | 2022-03-07 11:44
20220308 | 20220308022 | 22 | Erosion Mat III B | There are no approved products on the PAL for E-Mat III B. Proposal 51 had this question and the bid item was eliminated. Please provide clarification on this bid item on this project. |  |  | 6 | 2022-03-07 08:41
20220308 | 20220308026 | 26 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) Min/max cover heights are less than 15 feet for Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPCS? | Contractors will NOT be permitted to use Class IIIA and/or IIIB culvert pipes in lieu of the sole specified CPCS because of the lack of cover. Per FDM 13-1 Table 15.2, plastic pipe requires a minimum 2 feet of cover to top of subgrade. When taking into account the driveway pavement sections, the culvert pipes specified to be corrugated steel were utilized because the cover was less than 2 feet to top of subgrade. | Mike Coleman | 1 | 2022-02-11 11:58 | 2022-02-14 14:24
20220308 | 20220308026 | 26 | Asphaltic Surface | Can the Asphalt required for the pipe patches, subgrade fix, and the curb and gutter patches changed to an asphaltic surface item requiring MT mixes? This work would happen prior to the paving on the mainline and outside of the main PWL testing. | An addendum will be issued to include Asphaltic Surface for pipe patches, subgrade fix, and the curb and gutter patches. The addendum will adjust quantity for item 465.0110 Asphaltic Surface Patching and adjust quantity for item 460.6224 HMA Pavement 4MT 58-28S. | Mike Coleman | 2 | 2022-02-22 10:56 | 2022-02-23 11:26
20220308 | 20220308026 | 26 | CIR Time Frame | Would the Department consider removing the 96 hour restriction between milling and CIR from the project special provision found on page 4. Replacing this special with one from a similar job last month that stated â€˜A milled surface open to through traffic shall not remain in place for longer than 7 days. Provide an even cross sectional profile of the roadway at the end of each dayâ€™s milling.â€™ This project would be difficult to build as a mill and fill for the following reasons: 1. Once milling is complete, the milled surface is inspected for yielding areas and if any yielding areas are discover the â€œBase Repair for CIR Layerâ€ must be completed prior to CIR. Time must be allotted to complete this base repair. 3. If the CIR operation is required by the 96 hour restriction to match up daily it will add significantly to the costs to the operations due to production inefficiencies. Not only will the project take longer to build but the number of construction joints required | The Department will modify the 96 hour restriction in the project special provisions by an addendum. | Mike Coleman | 3 | 2022-02-25 11:31 | 2022-03-03 08:54
20220308 | 20220308026 | 26 | Guardrail | The guardrail is required to be removed and replace within 72 hours. During the grading portion of the project the guardrail will have to be removed and replaced due to the undercut at these areas prior to the Cold-In-Place Recycling and paving operations. During the CIR and paving operations the new guardrail would have to be in place and may not have the correct elevation after the final lift is placed. Would the Department either consider adding 614.0400 Adjusting Steel Beam Guardrail or allowing the guardrail to be taken down during the grading phase and placed after the CIR and paving operations are completed which would exceed 72 hours? Lastly, if the guardrail is in place during the CIR the equipment that is required to accomplish the CIR cannot mill to the face of the guardrail. Is it allowable to have the CIR as close to the guardrail as it possible and pave the remaining over the aggregate surface? | The guardrail requirements timeframe will be removed and SS 104.6.1.2.4 will be modified by addendum. An item for adjusting the guardrail will not be added to the contract, the new guardrail should be set to the anticipated finished pavement height. Any final adjustments needed would be incidental to the guardrail item. Guardrail is not anticipated to be in place during CIR, CIR limits should not change at guardrail. | Mike Coleman | 4 | 2022-02-25 11:32 | 2022-03-03 10:46
20220308 | 20220308026 | 26 | Aggregate shoulder in CIR | It appears in the Quantities that the milling is being paid at the 15â€™ lane width throughout the project. After the milling and prior to the CIR on the south end of the project is being widened 2 feet on each side. After the milling is the remaining base aggregate on the shoulder above the milled surface anticipated to be incorporated in the CIR?. If this in not the case cn an item be added to remove this material prior to the CIR footprint of 17â€™. | The remaining base aggregate on the shoulder above the milled surface is anticipated to be incorporated in the CIR. | Mike Coleman | 5 | 2022-02-25 11:38 | 2022-03-03 08:54
20220308 | 20220308026 | 26 | Timeframe | In order to allow more latitude on job completion, would the Department consider changing the completion date to November 1st with an interim completion date for HMA of Friday, October 14th. | The Department will not be changing the completion date for the project. | Mike Coleman | 6 | 2022-02-25 11:39 | 2022-03-03 08:55
20220308 | 20220308026 | 26 | Pilot Car | The standard requirement for a pilot car is 2 miles according to the flagger handbook. Could the specials be amended to this standard? | The special provisions will be amended by an addendum to conform to the flagger handbook. | Mike Coleman | 7 | 2022-02-25 11:40 | 2022-03-03 08:55
20220308 | 20220308026 | 26 | Type 5 Aluminum Poles | Suppliers for Type 5 Aluminum Poles are informing contractors that once Type 5 Aluminum Poles are ordered they are at least 4-6 months out when approved for manufacture. With the August completion date for the Roundabout would the DOT either extend the opening date or allow the RAB to be opened prior to the lights being constructed. | The Department will not be changing the interim completion date for the project of August 9th. An addendum will be issued to further clarify the roundabout lighting requirements. | Mike Coleman | 8 | 2022-02-28 11:21 | 2022-03-03 10:51
20220308 | 20220308027 | 27 | Aggregate Shoulders | The typical section shows 'Existing 3 1/2" base aggregate dense 3/4-inch'for shoulders. How does the department intend to pay for this scope of work? | The existing 3 ï¿½-inch base aggregate dense ï¿½-inch shoulder work is included with Preparation of Foundation for Asphaltic Shoulders, Item 211.0400 that includes excavating and shaping existing aggregate shoulders, using excavated material to shape remaining aggregate shoulders, and disposing of surplus or unsuitable material. | Mike Coleman | 1 | 2022-02-21 12:51 | 2022-02-22 11:33
20220308 | 20220308028 | 28 | Density Requirement | Will the density requirement be getting thrown out for the lower layer over the rubbilize as the typical section shows a thickness of 1.5" - 2.95" for crown correction. THe minimum thickness for a 12.5mm mix is 1.75" per the spec. | An error was found in the typical section that affected the paving layer thicknesses. An addenda is being created to correct the typical section. The change will result in all layer thicknesses meeting requirements in the standard specifications. Density requirements will not be waived. | Mike Coleman | 1 | 2022-02-23 17:30 | 2022-02-28 10:59
20220308 | 20220308028 | 28 | Centerline Joint | During Stage 4 and 5 when the inside lane gets milled down and 2 lifts of asphalt placed to open traffic, what will be the expectation for the centerline, which will be uneven, when traffic is opened on it Saturday evening through Monday. | A vertical differnce of less than 2â€ is permitted per standard specification. Should this occur on this project it shall be signed accordingly per SDD 15D39 (drop-off signing). In the addenda that is being produced for this project, we are adding the SDD. | Mike Coleman | 2 | 2022-02-23 17:36 | 2022-02-28 11:55
20220308 | 20220308028 | 28 | Stages 9&10 | Will the department consider Stages 9&10 to take place inbetween memorial day and July 4th to get the continuous closures done prior to July | An addendum will be issued to include SPV language updates to answer this question and modify when Stages 9 & 10 are to be completed. After further review, the Region has made the decision to require this work to be completed before the July 4th restrictions. | Mike Coleman | 3 | 2022-02-23 17:39 | 2022-02-28 11:50
20220308 | 20220308029 | 29 | Typical section | Sheet 6, is the intent to pave the 10' outside shoulder in two lifts, Lower 1 being 8' wide and 1.75'' thick and the upper layer at 10' wide and 1.75" thick? | There was a shading error on the typical section. The intent is to mill 1.75â€ of the 10â€™ shoulder off and replace it with 1.75â€ of new HMA. An addendum will be issued to address this correction of the typical section. The addenda will also correct some minor traffic control quantities that needed to be updated. | Mike Coleman | 1 | 2022-02-22 13:01 | 2022-02-28 11:44
20220308 | 20220308030 | 30 | Miscellaneous Quantities Milling Missing | The milling quantities are not noted in the miscellaneous quantities. Can this information be provided? Sheet 31 and Sheet 34 "erosion control quantities" appear to be duplicated. | An addendum will be issued to add the missing plan sheet and delete the duplicate plan sheet | Mike Coleman | 1 | 2022-02-16 09:55 | 2022-02-21 07:08
20220308 | 20220308030 | 30 | Project Start Date | Would the department allow the project to be started earlier if the contractor could complete the project by the Iola Car Show dates? | There are additional commitments that were made during the design process that need to be followed through with. The timeframe for the contract work will remain as advertised. | Jill Fehrman | 2 | 2022-03-03 08:14 | 2022-03-04 11:52
20220308 | 20220308033 | 33 | Design Schedule | Could you please provide the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/xjqwk94a4m39naobzkzjbt3ilhp7plsz or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-02-17 09:36 | 2022-02-24 08:37
20220308 | 20220308033 | 33 | Closure Lengths | Article 4 of the special provisions indicates that the maximum lane closure lengths allowed with a flagging operation â€œwill be two city blocks in the city of Princeton and one mile elsewhere.â€ For the scope of work for constructing a PWL HMA Pavement and QMP HMA Pavement, with the typical paving train consisting of a mill, cleanup equipment, trucks, paver, transfer machine, rollers, and density techs, these maximum lengths are not constructible. Will the department change the special provisions to allow the contractor to follow the standard lengths allowed by specification, and SDD 15C12-07 (2 miles)? | This will be addressed via addendum. | Mike Coleman | 2 | 2022-02-28 13:24 | 2022-03-02 18:30
20220308 | 20220308033 | 33 | End of Work Week Paving | Article 3 of the special provisions instructs the contractor to â€œpave lanes carrying through traffic by the end of the work week.â€ Would the department consider revising this to allow traffic to run on a milled surface for up to 96 hours? This would allow the contractor to be more efficient. | This will be addressed via addendum. | Mike Coleman | 3 | 2022-02-28 13:25 | 2022-03-02 18:31
20220308 | 20220308033 | 33 | Base Aggregate | In Misc. Quantity Plan sheet 80 the stone for sidewalk is listed under Item #305.0120 (1 1/4" Stone) In Misc. Quantity Plan sheet 84 the stone for sidewalk is listed under Item #305.0110 (3/4" Stone) Please Clarify | The base aggregate from sidewalk should have been placed in the ï¿½â€ column to match the sidewalk table. I will prepare an addendum (#2) to correct the MQ table and revise the total base aggregate quantities on the proposal. | Mike Coleman | 4 | 2022-03-01 11:32 | 2022-03-02 18:28
20220308 | 20220308034 | 34 | Temporary Pavement Markings | Good morning, On plan sheet 115, it appears there is temporary epoxy markings included on the surface for sections 646+11-667+42 & 908+00-1210+89. What is the plan for temporary epoxy markings on the surface in sections 807+00-864+35 & 1210+89-1287+12? Will an addendum be added to include temporary epoxy markings for those sections? Thank you. | The section noted from stations 807+00-864+35 & 1210+89-1287+12 are located in an urban area and will not require centerline rumble strips. Therefore, no temporary epoxy is necessary. The top line of the table (Station 646+11-667+42) is labeled incorrectly. It should read STA 646+11-STA 807+00. The quantities as shown are correct. An addendum noting this will be prepared. | Mike Coleman | 1 | 2022-02-21 08:47 | 2022-02-21 11:42
20220308 | 20220308034 | 34 | Project Schedule | Will the department please provide the preliminary schedule used in the project design and development for review? | The design schedule can be found at the following location: https://wisdot.box.com/s/pr8x9oakayhcb6r3di53b8ezzbs1zh4j or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-02-22 11:39 | 2022-02-23 10:55
20220308 | 20220308034 | 34 | Lane Closure Lengths with Flagging | Article 4 of the special provisions indicates that the maximum lane closure lengths allowed with a flagging operation â€œwill be two city blocks in the urbanized areas of Lake Tomahawk and Woodruff and one mile elsewhere.â€ For the scope of work for constructing a PWL HMA Pavement, with the typical paving train consisting of a mill, cleanup equipment, trucks, paver, transfer machine, rollers, density techs, and core rig for the PWL Core Pilot Project, these maximum lane closure lengths are not constructible. Will the department clarify what scope of work is restricted to these maximum closure lengths, or change the special provisions to allow the contractor to follow the standard closure lengths allowed by specification, and SDD 15C12-07? | The flagging limits of two city blocks will be removed and replaced by â€œthe contractor will cease or alter work operations if traffic delays become longer than 15 minutes. If the contractor fails to comply with this special provision within a timely manner the project engineer shall suspend work operations in accordance to Subsection 108.6 until the contractor complies with the 15-minute delay period. If the contractor continues operations, Subsection 105.3.2.3 (Unauthorized Work) may be enforced for any work completed during that time, no additional compensation or additional time will be allowed due to such suspension of operationsâ€. An addendum will be issued. | Mike Coleman | 3 | 2022-02-24 20:11 | 2022-02-28 11:51
20220308 | 20220308034 | 34 | End of Workweek Restriction | Article 3 of the special provisions instructs the contractor to â€œpave lanes carrying through traffic by the end of the work week.â€ Would the department consider revising this to allow traffic to run on a milled surface for up to 96 hours? This would allow the contractor to be more efficient. | The special provisions will be updated to allow traffic on a milled surface for up to 96 hours. An addendum will be issued. | Mike Coleman | 4 | 2022-02-24 20:13 | 2022-02-28 11:52
20220308 | 20220308034 | 34 | Distance between lane closures | Would the department consider eliminating the language from Article 4 that states â€œA second lane closure may occur if it is located more than two miles from the first operationâ€? | The distance between lane closures restriction will be changed from two miles to one mile between additional lane closures. An addendum will be issued. | Mike Coleman | 5 | 2022-02-24 20:14 | 2022-02-28 11:52
20220308 | 20220308034 | 34 | Asphalt at Storm Sewer | The Misc. Quantities tables for both items of Asphaltic Surface, item 465.0105, and Asphaltic Surface Patching, item 465.0110, show quantities for asphalt pavement for the storm sewer, however there are no details which would indicate the depth, width, or location for the quantities shown. Can the department clarify how the quantities for each respective item shall be used? Are the quantities doubled up, or will both items be utilized for patching over the new/repaired storm sewer facilities? | The quantity for asphalt repairs at Storm sewer trenches was assigned to both items in error. The item is intended to be asphaltic surface. This will be addressed as part of an upcoming addendum. | Mike Coleman | 6 | 2022-02-28 08:08 | 2022-03-02 06:45
20220308 | 20220308034 | 34 | reconstruct inlets | As all inlets are currently under snow or filled with snow, can a more detailed explanation be given of what work is required at each location for reconstruction of inlets? Such as number of pipes to be mudded around, extent of riser repair and depth, and what structure repair entails? | The expectation is that adjusting rings are replaced where riser repair is called for in the plan under the adjusting inlets or reconstructing inlets bid item. Reconstruction work in addition to this is described in the Repair column of the tables on the storm Sewer Plans ,whether mudding existing pipe connections or other structure repair, which may include tuckpointing of the brick structures or repairing the top of the structure. | Mike Coleman | 7 | 2022-03-03 15:05 | 2022-03-07 09:11
20220308 | 20220308035 | 35 | Asphaltic Surface Temporary | Could the department supply a detail section for the asphalt surface temporary, item # 465.0125? | The department is anticipating the work area be paved with temporary asphalt prior to opening to traffic, but prior to removing the temporary pipe. When the temporary pipe is removed, the asphalt would be removed and repaved. The quantity in the plan reflects the estimated amount for the whole work area. | Mike Coleman | 1 | 2022-02-25 12:40 | 2022-03-02 06:48
20220308 | 20220308035 | 35 | Flagging Operation | Article 4 of the special provisions for flagging operation states â€œlimit flagging operation to 0.6 miles (3,100â€™).â€ For the scope of work for constructing a PWL HMA Pavement, with the typical paving train consisting of a mill, cleanup equipment, trucks, paver, transfer machine, rollers, and density techs, this maximum length is not constructable. Will the department change the special provisions to allow the contractor to follow the standard lengths allowed by specification, and SDD 15C12-07 (2 miles)? | An addendum will be issued to increase the flagging operation length to 2 miles. | Mike Coleman | 2 | 2022-02-25 12:41 | 2022-03-01 12:25
20220308 | 20220308035 | 35 | Curb Locations | Can you verify the location of Item #601.0588 36" Type TBT & Item #SPV. 0090.02 Special Curb. The construction detail on plan sheet 7 & the Misc. quantities on plan sheet 13 may not have the correct location or are not identified correctly. | An addendum will be issued to update the construction detail station ranges. Quantities will not change. | Mike Coleman | 3 | 2022-03-01 08:52 | 2022-03-02 18:22
20220308 | 20220308036 | 36 | Structure B-43-63 | Are there Plan Sheets for the Endwall Layout, Earthwork Calculations, and Soil Boring Available for this structure similar to what was provided for C-43-23? Are there also additional quantities for B-43-63 Endwalls that are not included in the Schedule of Items? | The endwalls for B-43-63 should follow SDD 8f10 Concrete Masonry Endwalls for Culvert Pipe and Pipe Arch, with the modifications shown in the construction details (namely to shrink up the distance between the pipes to 1.23â€™, and about reinforcement between the pipes). The item for this is 504.0900 Concrete Masonry Endwalls (CY). Then thereâ€™s also the construction staking item for the pipes (650.6000). In the MQs, earthwork table, Division 2 shows the Scott Creek location. The transition cut for B-43-63 is listed. There are exact locations for the inverts of the pipes (STA, offset, elevation). Typically just SDD 8f10 is shown, not any further layout. A soil boring plan sheet was not prepared for structure B-43-63. The geotechnical report can be found at the following location: https://wisdot.box.com/s/ziu9f42r80z78ag74bskq7iu3qzq19ki or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-02-10 10:55 | 2022-02-14 14:21
20220308 | 20220308036 | 36 | Flowable Fill | To what line and grade is flowable fill to be installed? There is not a bottom elevation shown on the plan. | The 157 CY of flowable fill was estimated assuming a trench that is 6â€ below bottom of pipe (Standard Spec 520.3.2.1(5)), and a trench width of 3â€™ on the outsides of the pipes. The intent of the detail is for the flowable fill to go up to the center of the pipe on the outsides, and top of pipes between the pipes. | Mike Coleman | 3 | 2022-02-16 10:16 | 2022-02-22 11:29
20220308 | 20220308036 | 36 | Temporary pavement markings | Good morning, This project has temporary paint on the surface prior to rumble strips being placed. Similar projects would normally have temporary epoxy on the surface prior to the rumble strips due to the fact that epoxy is not to be placed over paint and rumble strips do not fully remove the temporary markings placed prior to the rumble strips. Will an addendum be added to include a temporary epoxy item? Thank you. | The temporary paint item will be replaced with a temporary tape item via addendum. | Mike Coleman | 4 | 2022-02-21 07:23 | 2022-02-23 14:12
20220308 | 20220308036 | 36 | Please Clarify Language Regarding Paving Lanes by end of Workweek | Can the Department clarify the intent of the statement in Article 4 that states: â€œPave lanes carrying through traffic by the end of the work weekâ€? For the pipe replacements at Julia Creek, Pine Creek, and Scott Creek, the work is allowed to be constructed with a full closure of STH 32; this seems impractical to require travel lanes to be paved by the end of the workweek during full closures. If the lanes carrying through traffic must be paved by the end of the workweek following the allowable closure for these 3 locations, or if the other 4 pipe culvert replacement locations are not allowed to have unattended gravel driving surface over the weekend, it would be helpful to modify the language of the Special Provisions to that end. | Any pipe location open to the travelling public (NOT detoured) needs to be paved prior to the start of the weekend. | Mike Coleman | 5 | 2022-02-24 20:17 | 2022-02-28 06:42
20220308 | 20220308036 | 36 | What is the purpose for the Asphaltic Surface Temporary item? | The Misc. Quantities table on Sheet 16 shows Asphaltic Surface Temporary Quantities in equivalent amounts as the HMA Pavement Quantities for the culvert replacements at Scott Creek & Julia Creek. Since there is no staging shown that would indicate the location of the Asphaltic Surface Temporary, is it the Departmentâ€™s expectation that the entire area will need to be paved first with temporary asphalt, and then re-excavated, and paved again with the permanent pavement? Can you please clarify the intent for how item 465.0125 shall be used? | The department is anticipating the work area be paved with temporary asphalt prior to opening to traffic, but prior to removing the temporary pipe. When the temporary pipe is removed, the asphalt would be removed and repaved. The quantity in the plan reflects the estimated amount for the whole work area. | Mike Coleman | 6 | 2022-02-24 20:19 | 2022-03-01 07:36
20220308 | 20220308036 | 36 | Where will Asphaltic Flumes be constructed? | The Misc. Quantities table on Sheet 16 shows a quantity of 30 SY for Asphaltic Flumes, item 465.0315, at the Julia Creek culvert location. The plan sheets donâ€™t appear to indicate a flume at this culvert. Can the department please provide clarification, or a detail for the location of this work item? | The location for the asphaltic flume is indicated on a construction detail, sheet 9. | Mike Coleman | 7 | 2022-02-24 20:20 | 2022-02-28 06:14
20220308 | 20220308036 | 36 | Julia Creek | What is the intent with the Temp. Barrier at Julia Creek. There is no detail in the plan. If the work in this are is not complete can it go to a One lane road stop condition like Scott Creek? |  |  | 9 | 2022-03-04 12:34
20220308 | 20220308037 | 37 | DBE/Hauling Excess Shoulder Material/Core timing | In the November 9th bid the Assigned DBE Goal was 3% and in the March 8th bid the DBE Goal is 7%. Why has this changed? In the November 9th bid there was line # 28-305.0504.S (Hauling Excess Shoulder Material) that I do not see bid in the March 8th letting . In the special provision within the March letting item 12 is still shown but no bid line is shown for this work. Will this item be added via addendum? If not how will hauling excess material be paid if needed? Will coring be allowed the next day as in other pilot coring projects or will it need to be completed the day of paving? This will limit the amount we can pave each day if required at the end of each day. | The DBE Goal was inadvertently set at 7%. It will be revised to 3% in an upcoming addendum. Article 12 of the special provisions will be removed in an upcoming addendum. Article 18 shows that cores can be done the next day. | Mike Coleman | 1 | 2022-02-18 13:05 | 2022-03-01 12:23
20220308 | 20220308037 | 37 | Water Membrane HMA | There are currently no materials that meet the special provisions. In the past Mel-Dek was used. Is this material acceptable? | An addendum will be issued to update the specification. | Mike Coleman | 2 | 2022-03-01 11:08 | 2022-03-02 08:55
20220308 | 20220308039 | 39 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | Contractors will NOT be permitted to use Class IIIA and/or IIIB culvert pipes in lieu of the sole specified CPCS because of the lack of cover. Per FDM 13-1 Table 15.2, thermoplastic pipe requires a minimum 2 feet of cover to top of subgrade. | Mike Coleman | 1 | 2022-02-11 12:00 | 2022-02-15 08:40
20220308 | 20220308039 | 39 | Barrier System - Grade/Shape/Finish | Is the column on sheet 68 labeled Common Excavation supposed to be labeled Borrow? The cross sections do not show much for common and but plenty of borrow. | Yes, the column on sheet 68 that shows quantities for bid information only should have been labeled as Borrow and not Excavation Common. | Mike Coleman | 2 | 2022-02-15 15:36 | 2022-02-17 06:32
20220308 | 20220308039 | 39 | Guardrail Removal Schedule | The SPV's note that guardrail must be removed and replaced in the same day. There is a significant amount of grading at this location as well as plenty of guardrail. The face of the guardrail is 8' from the edgeline and the current hinge point is about 12' from the edgeline. Can spec 104.6.1.2.3 apply here? | The requirement to remove and replace the guardrail in the same day will still apply. | Mike Coleman | 3 | 2022-02-15 15:46 | 2022-02-17 06:37
20220308 | 20220308039 | 39 | Guardrail Removal Schedule #2 | The area that the guardrail is to be removed and replaced also calls for asphalt mow strip to be installed. So, given that it is 3K rail, each day the guardrail contractor removes up to 75' of guardrail, grading contractor excavates the shoulder and preps for paving, paving contractor paves the mowstrip, guardrail contractor comes back to drill through the hot asphalt and installs the 75' of guardrail without damaging the asphalt, and makes a temporary connection to the remaining guardrail run. It doesn't seem very cost effective but is that a rough schedule of what we can expect to be required to complete the work? | An addendum will be issued to revise the work restriction. | Mike Coleman | 4 | 2022-02-17 10:29 | 2022-02-22 06:56
20220308 | 20220308039 | 39 | Guardrail Curb Removal | The detail in the plans does not accurately depict the conditions on the project. The plans show the rail curb sitting on top of the existing HMA mat. However, it is buried to the upper rib and in spots completely buried. To remove this, the asphalt in front of the panel will either need to be removed or all of the guardrail including posts will need to be removed to pull that panel out of the road. Does this work require the rail to be reinstalled within 24 hours? What does the void get filled with? Is that incidental to the removals? | An addendum will be issued to revise the work restriction. Saw-cuts are shown in front of rail curb locations. The void gets filled with ï¿½-Inch Base Aggregate Dense. | Mike Coleman | 5 | 2022-02-17 13:59 | 2022-02-22 06:59
20220308 | 20220308039 | 39 | temporary pavement markings | Good morning, being that the lower layer needs to be placed within 96 hours of the milled surface, will temporary paint quantities be added to this project (currently, it appears there are enough for the milled or lower layer, but not both) to accommodate 2 applications of temporary paint? Thank you. | An addendum will be issued to revise the temporary paint quantities. Both the milled asphalt and lower layer of asphalt will receive temporary paint. | Mike Coleman | 6 | 2022-02-19 08:35 | 2022-02-22 06:59
20220308 | 20220308039 | 39 | Asphaltic Curb | The plan details show a detail for asphaltic curb on page 19. In the northwest region we have been able to use the â€œCarlson Curbâ€ to replace the detail in the plans. Will this practice be permitted on this project? | Can you provide the dimensions of the Carlson Curb you are proposing? We can then make a determination if this is acceptable or not. | Mike Coleman | 7 | 2022-02-28 16:07 | 2022-03-02 06:44
20220308 | 20220308039 | 39 | Asphaltic Surface and Driveways | The plans call for 2â€ of milling with a new 3.25â€ pavement section. The road will rise approximately 1.25â€ overall. There are 14 HMA driveways on the project. Due to change in the final elevation, the driveways and road will not match up. Can the department add the Asphaltic Surface Driveway & Field Entrance pay Item? | The elevation difference is addressed by the construction detail "Rural Driveway Intersection Detail" which indicates a butt joint is required at the match point with the existing asphaltic driveways and that the driveway match is to blend back on the entrance far enough to get a smooth profile. However, an addendum will be prepared that removes the driveway tonnage from the item of HMA Pavement 5 MT 58-34 V and replaces it by adding new item Asphaltic Surface Driveways and Field Entrances. | Mike Coleman | 8 | 2022-02-28 16:10 | 2022-03-03 09:44
20220308 | 20220308039 | 39 | Prepare Foundation for Asphaltic Paving | The Prepare Foundation of Asphaltic Paving is missing from the schedule of items. Can this be added via addendum? | An addendum will be prepared to add Item 211.0100 Prepare Foundation for Asphaltic Paving (project). | Mike Coleman | 9 | 2022-02-28 16:11 | 2022-03-03 09:36
20220308 | 20220308039 | 39 | DBE Percentage | Historically 6% DEB participation has been not achievable in the NW region due to the lack of DBE firms willing to quote in the area. Also, due to the nature of the project (Milling & Paving) DBE opportunities for participation will also be limited. Would the department consider lowering the commitment to 3% to be more comparable to other goals in the region? | The DBE goals for proposal 39 were reviewed and the DBE opportunities warrant a 6% goal. | Jill Fehrman | 10 | 2022-03-02 08:10 | 2022-03-02 17:07
20220308 | 20220308044 | 44 | Temporary Markings | Good morning, As it sits, this project does not appear to have any temporary or same day pavement markings for the milled surface (typically temporary paint), the lower layer (typically temporary paint), or the upper layer (typically same day epoxy daily or temporary epoxy if rumbles are to be placed). Will an addendum be issued to add temporary and/or same day markings? Thank you. | An addendum will be prepared to include temporary markings and same day markings. | Mike Coleman | 1 | 2022-02-19 08:11 | 2022-02-21 11:44
20220308 | 20220308044 | 44 | 3/4 Dense Base | During the pulverizing and fine grading/widening process most of the existing shoulder aggregate material will get incorporated into the roadway. The department may want to consider ï¿½â€ base course quantities figured for shouldering along the final mainline surface of the roadway. Currently there is only ï¿½â€ base quantities figured for the aggregate driveways. | The existing shoulder gravel should not be incorporated into the roadway. Per Note 3 on page 5 of the plan the existing shoulder aggregate will be bladed to allow wider pavement and then bladed back to match the new pavement surface. | Mike Coleman | 2 | 2022-02-24 08:02 | 2022-03-01 07:17
20220308 | 20220308044 | 44 | Removing Asphaltic Surface | The existing asphalt driveways will need to be removed on this project. The department may want to consider adding an item for removing asphaltic surface to cover this work. | The item Removing Asphaltic Surface will be added to account for pavement removals at asphaltic driveways impacted by the project. Plan and quantity updates associated with this change will be included in an upcoming addendum. | Mike Coleman | 3 | 2022-02-24 08:06 | 2022-03-01 07:13
20220308 | 20220308044 | 44 | 3/4 Base | Note that there is limited space on the exisitng shoulder to store the amount of salvaged material needed since the pavement is being widened, therefore the material may go down the end slope. We cannot tell because of the snow, but the end slopes likely vary and are greater than the 4:1 shown on the plans in areas. This will add to the potential issue and result in varying shoulder widths/appearance. | This was addressed with question #2. The existing shoulder gravel should not be incorporated into the roadway. Per Note 3 on page 5 of the plan the existing shoulder aggregate will be bladed to allow wider pavement and then bladed back to match the new pavement surface. In regard to the improvement concept, the existing roadway (according to the typicals) has 4â€™ gravel shoulders. The plans call for converting the shoulders to 2â€™ paved, 2â€™ gravel, so theyâ€™re not being inherently widened overall. It makes sense to me to assume that there would be an excess of shoulder aggregate available to do the shoulder shaping since the plans call for removing 2â€™ of aggregate shoulder width (replaced by paved shoulder) and the shoulder aggregate should only have to come up a little over an inch to match the new pavement elevation. | Mike Coleman | 4 | 2022-03-01 08:18 | 2022-03-02 18:27
20220308 | 20220308047 | 47 | Pulverize & Relay Quantity | It appears that the pulverize and relay quantity includes the reconstruction sections of the project as defined by sheet 6 (lower section). Is the intent to pulverize these areas as part of item 325.0100? or will asphalt need to be removed from the project by other means? Thanks | Yes the intent is to have these areas pulverized and the resulting material made available for use as base material in the reconstruction areas. | Mike Coleman | 1 | 2022-02-11 16:03 | 2022-02-16 09:55
20220308 | 20220308047 | 47 | Incentive Air Voids HMA Pavement | Since this is not a PWL project, the â€œIncentive Air Voids HMA Pavementâ€ item does not apply and can be removed. | The Incentive Air Voids HMA Pavement item will be removed via an addendum. | Mike Coleman | 2 | 2022-02-24 08:38 | 2022-02-28 06:13
20220308 | 20220308047 | 47 | Pulverize and Relay | If the pulverized material from the reconstruct sections is to be used as base material for the reconstruct sections per previous Q&A.....1) How will the department pay for salvaging and replacing the pulverized material? 2) How will that affect the quantity of 1 1/4 base? | The pulverize and relay material will be moved via Common Excavation, Item 205.0100, and applied to fill quantity. Base Aggregate Dense 1- ï¿½ Inch, Item 305.0120, quantity does not change. | Jill Fehrman | 3 | 2022-03-03 08:03 | 2022-03-04 12:03
20220308 | 20220308048 | 48 | Solar LED signs | Will you accept an alternate sign other than TAPCO if it meets the specifications? | Designer checked with St. Croix County who will be maintaining the stops signs and the answer is yes, an alternate solar LED stop sign is acceptable if it meets the specifications. An addendum will be issued to clarify the specifications. | Mike Coleman | 1 | 2022-02-01 15:55 | 2022-02-11 10:04
20220308 | 20220308048 | 48 | Planholder list | When will the plan holder list be released? | A pdf is created with the most current plan holders for the letting. The file is updated and posted each Friday after advertisement, as well as; Monday, Wednesday and Monday before the letting | Mike Coleman | 2 | 2022-02-10 10:05 | 2022-02-11 11:55
20220308 | 20220308048 | 48 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) Min/max cover heights are less than 15 feet for Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPCS? | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 3 | 2022-02-11 11:59 | 2022-02-14 13:57
20220308 | 20220308048 | 48 | Plan holder list | There is no link to the plan holders in Bid Express or the DOT website? | Plan Holders are posted every friday, and the monday, wednesday, and friday the week before the letting, and on Monday of letting week. | Mike Coleman | 4 | 2022-02-11 12:20 | 2022-02-14 06:45
20220308 | 20220308049 | 49 | Time Schedule | Due to the short duration of this project, and the restrains on the North and South ends due to bridge closures. We feel that there is not adequate time to build the project area in between the 2 closures without utilizing only the town road for access. Can you please look at some additional time added to the contract. | The required construction items within the bridge closures/replacements were reviewed for schedule of completing critical bid items. An addendum will be issued to provide additional time for the construction of this project and to increase the traffic control quantities. | Mike Coleman | 1 | 2022-03-01 15:36 | 2022-03-02 18:23
20220308 | 20220308051 | 51 | Erosion Mat Class III Type B | There are not any products listed in the PAL for Erosion Mat Class III Type B. | This was addressed as part of addendum 2. | Mike Coleman | 1 | 2022-02-28 12:42 | 2022-03-07 09:47