## qandasearchletting_results
Date: | 2022-04-11
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220412 | 20220412001 | 1 | proposal line number 0002, finishing roadway | Good morning, this item has never been included in a maintenance striping contract. Will the department explain what the expectations of 213.01 (the specification starts with 213.1 on page 119 of the standard specifications book) on this project? Will this item be removed from this project? Thank you. | Finishing Roadway bid item will be removed via addendum. | Mike Coleman | 1 | 2022-04-07 06:58 | 2022-04-07 11:17
20220412 | 20220412002 | 2 | Paving Restrictions | Given the number of operations required (mill, prepare and install shoulder widening, distressed pavement mill/pave and placing HMA binder), Can the window of time between milling and paving be opened up to give contractors more flexibility in scheduling and completing this work? | No, the window of timing between milling and paving cannot be opened up. We are following the recommendation of our Pavement Engineer. This was also confirmed during the PS&E review process when asked by BPD. The reason for the short window is because of the high volume of truck traffic including OSOW trucks. Once milling operations are complete, there will only be 2â€ of existing HMA remaining. The remaining pavement will take a beating if we do not follow the contract. | Mike Coleman | 1 | 2022-03-22 12:19 | 2022-03-23 08:57
20220412 | 20220412003 | 3 | Project Schedule - Completion Date | Will the department please provide the preliminary schedule used in the project design and development for review? In talking with suppliers current material procurement lead times will very likely not allow this project to be completed by the August 27th completion date. Can revisions be made to the contract completion to account for this? | The design schedule and Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/2xjlsog3yx4282ntqi164nirudmb5lr8 or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. Contract completion date will not be changed. | Mike Coleman | 1 | 2022-03-21 15:40 | 2022-03-23 10:41
20220412 | 20220412004 | 4 | Distressed Pavement Milling | What is the minimum width for the Distressed Pavement Milling Item? There is no detail in the plan. | A detail sheet was inadvertently deleted from the plan set that had a detail for the distressed milling. An addendum will be issued to add the detail. | Mike Coleman | 1 | 2022-03-15 15:49 | 2022-03-16 13:11
20220412 | 20220412004 | 4 | Construction Staging & Distressed Milling & Paving Patching | Looking at the construction staging details underneath the Special Provisions it states that there is 48 hours between milling and paving. In the December 2021 letting STH 82 Juneau County was let with construction staging stating 7 days between milling and paving with only 200 Tons worth of distressed pavement patching. Also we are roughly milling off the same thickness on both projects and they have around same A.A.D.T so wouldn't it be better to have the same construction staging as STH 82 in the December 2021 letting to allow adequate time assess 1600 Ton worth of distressed pavement patching? | STH 58 5020-01-60 only has 3.5-inches of existing pavement (over 4-inches mill and relayed asphaltic pavement) which will only leave 1.5-inches after milling. The existing typical sections appear to incorrectly label the mill and relayed pavement base material as HMA. STH 82 5010-06-72 is milling 2.25-inches of the existing 5-inches which will leave 2.75-inches after milling (along with completing a thicker 4-inch overlay). Given this information, the two projects should not be compared for staging purposes, and the department will proceed with the original 48 requirement between milling and paving. | Mike Coleman | 2 | 2022-03-24 16:33 | 2022-03-30 13:12
20220412 | 20220412004 | 4 | Asphaltic Surface | Looking at the quantity of Removing Distressed Pavement Milling there is 13,000 SY in the plan and the quantity of asphaltic surface in the plan only covers 500 tons worth or 4,464 SY. If there is 13,000 SY x 2" of Thickness x 112 lbs/sy-in / 2,000 Tons = 1,460 Tons worth of Asphaltic Surface? So should the quantity of Removing Distressed Pavement Milling be 4,464 SY to cover 500 Ton or 13,000 SY to cover 1,460 Tons? | The Removing Distressed Pavement Milling Quantity of 13,000 SY is correct, and the Asphaltic Surface quantity will be adjusted to 1,500 tons via an upcoming addendum. | Mike Coleman | 3 | 2022-03-25 15:22 | 2022-03-30 13:22
20220412 | 20220412007 | 7 | Migratory Birds | It is unlikely that the contract will be executed prior to the 4/15 bird netting requirement. Would the department look into providing for the netting to be completed prior to 4/15 by DOT or County forces for this project? It would be understood the contractor would be responsible for maintenance of the netting installed by others. | Dane County will be installing the netting by April 1. Item 999.2005.S is included in the plans for maintaining bird deterrent system once the construction contract is authorized. | Mike Coleman | 1 | 2022-03-14 11:55 | 2022-03-16 12:20
20220412 | 20220412008 | 8 | Migratory Birds | It is unlikely that the contract will be executed prior to the 4/15 bird netting requirement. Would the department look into providing for the netting to be completed prior to 4/15 by DOT or County forces for this project? It would be understood the contractor would be responsible for maintenance of the netting installed by others. | â€œthe bird netting special only requires the Contractor to maintain the nets that the County put upâ€ For this contract, the County will do the initial installation and the contractor will take over the maintenance of it once the contract is executed. | Mike Coleman | 1 | 2022-03-14 11:55 | 2022-03-15 14:33
20220412 | 20220412009 | 9 | Migratory Birds | It is unlikely that the contract will be executed prior to the 4/15 bird netting requirement. Would the department look into providing for the netting to be completed prior to 4/15 by DOT or County forces for this project? It would be understood the contractor would be responsible for maintenance of the netting installed by others. | The Department will install netting at the bridge prior to 4/15. The contractor will be required to maintain it, as well as remove it at the appropriate time. | Jill Fehrman | 1 | 2022-03-14 11:56 | 2022-03-18 09:11
20220412 | 20220412009 | 9 | Item 211.0400 Prepare Foundation for Asphaltic Shoulders | Typical sections on Sheet 4 and 5 of the Plan require Prepare Foundation for Asphaltic Shoulders 2â€™ from the existing edge of pavement. Note *** for these areas, states that weeds/deleterious material need to be removed from these limits. 1. Do Weeds/deleterious materials need to be disposed of offsite? Or can this material be wasted onto the foreslopes? 2. Following weed/deleterious material removal, will it be acceptable for material from the pulverize and relay operation be relayed 2â€™ wider than existing pavement in order to Prepare Foundation for Asphaltic Shoulders? Or will new CABC be required to be placed following the removal of weeds/deleterious material to bring shoulders up to match existing HMA elevation? | 1. It is acceptable to waste the material onto the foreslope. 2. It is acceptable that the pulverized material be placed the additional 2â€™ wider than the existing pavement edge to prep shoulders for asphalt. | Jill Fehrman | 2 | 2022-03-14 14:23 | 2022-03-18 09:13
20220412 | 20220412009 | 9 | 5730-00-71 Traffic Control - C-62-314 work | We do not see anything for traffic control in the plans or special provisions for project number 5730-00-71. What is the plan for traffic at the culvert extension C-62-314? This culvert work is outside of the detour route for the 5730-00-80. |  |  | 3 | 2022-04-07 10:23
20220412 | 20220412010 | 10 | DBE Percentage | Given the scope of this project and there being very limited items for subcontractors that typically quote this area that qualify as DBE it is going to be extremely difficult to meet the 4% goal. Would there be any consideration of lowering the DBE percentage for this project to make it more attainable? | OBOEC has reviewed the DBE Goals. The DBE goal of 4% will remain. | Mike Coleman | 1 | 2022-04-04 08:12 | 2022-04-04 11:21
20220412 | 20220412011 | 11 | Migratory Birds | It is unlikely that the contract will be executed prior to the 4/15 bird netting requirement. Would the department look into providing for the netting to be completed prior to 4/15 by DOT or County forces for this project? It would be understood the contractor would be responsible for maintenance of the netting installed by others. | Per the contract documents, if the other options provided will not work, the contractor will need to apply for a depredation permit. The region environmental coordinators determined the permit was a better route, given the tendency for flooding in this river. The netting may cause more harm than good if it gets caught up in the flood waters and depending when it is installed could be a safety hazard to canoe/kayaks. The netting is also difficult to maintain because of the river and the drastic elevations changes. Weâ€™ve used the permit in the past and it works well in these instances. | Mike Coleman | 1 | 2022-03-14 11:57 | 2022-03-16 13:06
20220412 | 20220412011 | 11 | 404 permit | Can the 404 permit be made available for this project. | The 404 permit can be found at the following location: https://wisdot.box.com/s/h3x0jlhhgnvyi15gzfps3g4ekngx2or5 or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-03-28 14:41 | 2022-03-29 08:18
20220412 | 20220412012 | 12 | Contract Time | What is the reason for the late start date of June 8, 2022? | Based on the timing of let and contract execution, starting much sooner that June 8th may not be feasible. The Department will consider waiving this clause if contractors work schedules dictate the need for an earlier start date. | Mike Coleman | 1 | 2022-04-05 11:26 | 2022-04-11 06:24
20220412 | 20220412012 | 12 | DBE Percentage | Given the scope of this project and there being very limited items for subcontractors that typically quote this area that qualify as DBE it is going to be extremely difficult to meet the 5% goal. Would there be any consideration of lowering the DBE percentage for this project to make it more attainable? | OBOEC has reviewed the current DBE Goal. The goal of 5% will remain. | Mike Coleman | 3 | 2022-04-06 08:33 | 2022-04-06 09:17
20220412 | 20220412013 | 13 | Design Schedule | Can the DOT provide their design schedule? | The design schedule and Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/qk1tliseb95ao02iyaqwkqcj2fypdpb3 or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-03-24 17:16 | 2022-03-28 06:59
20220412 | 20220412013 | 13 | Steel Beam Guard | How does the department expect contractors to coordinate beam guard removal, removal of the asphaltic surface/block in the shoulder surrounding the posts, backfill and compact trench with ï¿½â€ base, install new beam guard of a different spec and height, and time these operations appropriately allowing for a junction between existing rail and new rail at the end of a each shift. The state could save substantial cost if the contractors are allowed more time to efficiently complete guardrail replacement. | The contractor is responsible for the schedule and the means and methods to accomplish the work required in the contract. There is not a requirement in the contract to make a temporary connection at the end of each day between the new and old rail. Shoulder closures may remain in the beam guard areas during non-working hours. | Mike Coleman | 2 | 2022-03-24 17:18 | 2022-03-29 07:03
20220412 | 20220412013 | 13 | Lane Closures | Between stations 34+50 and 101+00, lane closures are restricted to 0.5 miles. Is this practical considering most summer paving operations span well over 0.5 miles due to heat related cold roller backups, then subsequent PWL testing behind that? Additionally, for the sake of completing the project as quickly as possible, it would be in the projects best interest to start paving operations on the west limits allowing beam guard operations to take place as soon as possible. This would mean the test strip would be placed on the west end, the test strip by itself would extend beyond the 0.5 miles closure. | An addenda will be submitted revising Article 4. Traffic to the following: Delete the first sentence of the article and replace with the following: Construct STH 33 under traffic with flagging and limit the single lane restriction to a single continuous length not exceeding .75 miles from Station 35+40 to Station 101+00 and 1.5 miles from Station 101+00 to Station 442+89. | Mike Coleman | 3 | 2022-03-24 17:19 | 2022-03-29 07:01
20220412 | 20220412013 | 13 | 72 hour milled surface | Article 3 of the special provisions states that milled travel lanes are to be paved with-in 72 hours. Per the scope of work: milling, shoulder widening, shoulder paving, distressed milling & paving & PWL mainline paving, the contractor requests that the 72 hour be changed to 96 hours. | After further discussion with the traffic and pavement sections the 72 hour restriction will remain. | Mike Coleman | 4 | 2022-04-01 14:38 | 2022-04-05 06:26
20220412 | 20220412013 | 13 | Shoulder Widening | Per the detail on sheet 8 of the plan, is it the intent to have 4 inches of new base aggregate placed below the asphalt prior to paving the lower layer on the shoulder widening? This is not shown in the detail on sheet 12. If so, how does the contractor get paid for removing the existing material? | The intention is to pay for Prepare Foundation for asphaltic shoulders for the area needed to place the new shoulder asphalt. The intention is not to remove all of the material noted in the item Prepare Foundation for Asphaltic Shoulders but to shape and compact this existing material. The contractor needs to remove enough material to place the new asphalt. | Mike Coleman | 5 | 2022-04-01 14:42 | 2022-04-05 06:26
20220412 | 20220412013 | 13 | Completion Date | Would the Department consider changing the completion date to October 17th to allow for more flexibility in overall scheduling? | Due to commitments made during the design phase the completion date will not be changed. | Mike Coleman | 6 | 2022-04-05 13:15 | 2022-04-06 08:18
20220412 | 20220412013 | 13 | Steel Beam Guard Follow-Up | After reviewing the answer to the original guard rail question, is it possible to remove the line in the Specials, "Only remove as much guardrail as can be installed in the same day?" The way the Specials is written is dictating means and methods when guardrail must be re-installed at the end of each day. We feel it will be much more efficient and cost-effective to allow for the removal of at least one side of the road, remove the asphalt that runs through all of the posts on one side, shoulder, and then reinstall that side of guardrail. If drums and "shoulder closed signs" are in place, why is this line needed? | The slopes along this stretch are steep and need to be protected. It is up to the contractor to determine the means and methods to complete the work based on the requirements of the contract. This line will not be removed from the specials. | Mike Coleman | 7 | 2022-04-06 08:25 | 2022-04-11 06:22
20220412 | 20220412015 | 15 | Migratory Birds | It is unlikely that the contract will be executed prior to the 4/15 bird netting requirement. Would the department look into providing for the netting to be completed prior to 4/15 by DOT or County forces for this project? It would be understood the contractor would be responsible for maintenance of the netting installed by others. | La Crosse County will be netting the bridge. Item 999.2005.S is included in the plans for maintaining bird deterrent system once the construction contract is authorized. | Mike Coleman | 1 | 2022-03-14 11:57 | 2022-03-15 15:03
20220412 | 20220412015 | 15 | Item 36 Bar steel reinforcement HS Coated | There is a quantity discrepancy for bid Item 36-Coated rebar. The SOI lists 33,660 LB's but adding up the plan totals comes to 36,620 LB's. It appears the quantities for the abutments were not accounted for in the total. | The correct quantity should be 36,660 lbs for this item. We will prepare an addendum to clarify. | Mike Coleman | 2 | 2022-03-15 10:50 | 2022-03-15 15:02
20220412 | 20220412016 | 16 | Rock Bags - Silt Fence Relief | Why are rock bags for silt fence relief incidental to the silt fence item? There is a standard item for rock bags that has been used for this application. | After further discussion, there will be an addendum issued. Rock bags will no longer be incidental to the silt fence, the standard item will be used. | Mike Coleman | 1 | 2022-03-24 11:11 | 2022-03-28 06:55
20220412 | 20220412017 | 17 | Availability of Pipe Materials | We have been told by all suppliers that the lead time for the ductile watermain pipe will be late November/ early December. With the completion date set for December 13th, not sure how this can be accomplished. In addition to watermain pipe, valve and hydrants are 16 weeks for a lead time. | Extraordinary delays in material deliveries the contractor or their suppliers cannot foresee and forestall resulting from strikes, lockouts, freight embargoes, industry-wide shortages, governmental acts, or sudden disasters. Addendum #01, extended the completion time to May 25, 2023. | Mike Coleman | 1 | 2022-03-15 10:38 | 2022-03-22 07:31
20220412 | 20220412017 | 17 | Geotech Report for Area Near Proposed Temporary Shoring | 1. It appears that the temporary shoring is proposed for the storm sewer vault on Losey Blvd. Please confirm. 2. Is there any geotechnical report or information available near the proposed location for temporary shoring? | 1. Project ID 7575-07-83 includes bid item 511.1100 Temporary Shoring. The intent of this item is for it to be used during the installation of the proposed storm sewer vault and portions of the proposed 36-inch and 48-Inch storm sewer pipe located at STA 152+79.36 (Losey Blvd Intersection). 2. Existing geotechnical information in the location of the temporary shoring is limited. The geotechnical report can be found at the following location: https://wisdot.box.com/s/f25ghe8ms1x49ieb03bgakvftuqd0jcn or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-03-23 11:28 | 2022-03-24 10:54
20220412 | 20220412017 | 17 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | The City of La Crosse is contributing more than 50% of the cost of the storm sewer pipe on this project and per FDM 13-1-17.3.2 they have approved the use of concrete pipe. | Mike Coleman | 3 | 2022-04-05 11:31 | 2022-04-06 12:34
20220412 | 20220412017 | 17 | TRAFFIC SIGNAL CONTROLLER & CABINET | SPECIAL 302. TRAFFIC SIGNAL CONTROLLER & CABINET (EAST AVE & LA CROSSE ST) There is nothing in the specials for this item. There is two other items that should take care of the traffic controllers SPV.0060 --- 307 & 308 Let me know if you need anymore information on this. |  |  | 4 | 2022-04-08 14:37
20220412 | 20220412017 | 17 | Bid Form | The bid form in the plan set does not match the bid form on Bid Express. On the plan set Item 0392 Traffic Signal Controller & Cabinet is not on Bid Express. Does it need to be or is it not needed? | An emergency addendum is being issued to correct the Schedule of Items. The schedule of items in the advertised proposal were incorrect. The items in Bid Express is correct. The addendum will show the correct schedule of items. | Mike Coleman | 5 | 2022-04-11 09:30 | 2022-04-11 11:12
20220412 | 20220412018 | 18 | DBE Goal | Project has a DBE goal of 12%. There aren't any substantial work categories for DBE participation on this project. Would the department consider lowering the DBE goal to something obtainable? | The DBE Office has re-reviewed this goal. The goal will remain at 12%. | Mike Coleman | 1 | 2022-03-10 09:11 | 2022-03-11 09:47
20220412 | 20220412018 | 18 | timing of crack sealing | Is the sealing of the cracks going to be done right after milling is completed and before replacement? | Within Special Provision Sealing Cracks and Joints with Hot-Applied Sealant, Item SPV.0085.0002, the article states the following: Prior to commencing work, complete all pavement repairs that are included in the contract and are adjacent to pavement cracks. Work would include the outside shoulder milling and HMA work, concrete pavement repair and replacement SHES, continuous diamond grinding, concrete pavement, foam jacking bridge approach slabs, signal loops and any other engineer directed pavement repair areas using undistributed quantity locations. We anticipate the sealing to be performed towards the end of the operations prior to final pavement markings. This may be influenced by contractor means and methods or sequence of operations. For instance, work in one segment or direction may be ahead of operations within another segment or direction allowing sealing to proceed per plans, specifications, and at the approval of the engineer in the field. | Mike Coleman | 2 | 2022-03-14 10:25 | 2022-03-14 10:25
20220412 | 20220412018 | 18 | Foam-Jacking, Item SPV.0085.0001 | If saw cutting of the joints is determined to be necessary to perform the foam jacking, will a repair be required to reconnect the concrete pavement approach slabs? | Yes a repair would be required. It is the intent of this project to minimize impacts to the traveling public by not permitting peak hour lane closures and off-peak hour two-lane closures. Please note the following excerpt of the Foam-Jacking specification: Perform work in a manner that avoids pavement blowout, cracking, excessive lifting, uneven pavement, or excessive lateral pressure on adjacent retaining walls. Damage caused by the Contractorâ€™s operation must be repaired to a like condition at no cost to the Department. If the initial injection does not produce desired results, the injection process must be repeated until an acceptable improvement has been attained. For clarity adjacent retaining walls would include bridge abutment and wingwalls. | Jill Fehrman | 3 | 2022-03-14 15:56 | 2022-03-18 10:18
20220412 | 20220412018 | 18 | Drop Off Safety Slope ? | In the proposal it states "No weekday or weekend peak hour lane closures are allowed". Will a safety slope at the edge of the concrete lane be required after the existing 5" asphalt shoulder pavement is removed? Binder pavement placement will not be able to occur same night of milling due to need of proof roll and EBS. Please advise | Per Standard Specifications 104.6.1.2.3, a 3:1 safety slope will be required if the shoulder work cannot be back to a 2-inch or less drop-off by end of the work day. Contractor means and methods should conform to this requirement. | Mike Coleman | 4 | 2022-03-29 18:14 | 2022-04-04 12:14
20220412 | 20220412018 | 18 | High Performance Dowels | Do you want the High Performance Dowels in both the concrete pavement replacement bid item and the concrete pavement HES 8"? | High performance dowel bars are intended for concrete pavement HES 8-inch transverse bars on the NB Off-Ramp to 124th Street corresponding to Standard Specification Section 415 and 505. | Mike Coleman | 5 | 2022-04-05 06:35 | 2022-04-05 06:36
20220412 | 20220412018 | 18 | Proof Roll | Will the department allow a Proof Roll to be done after a safety slope is installed? | Yes. The Department will allow a proof roll to be done after a safety slope is installed. An addendum will be issued. | Mike Coleman | 6 | 2022-04-06 05:31 | 2022-04-06 11:56
20220412 | 20220412018 | 18 | SCM for SHES and HES mixes | Will 501.3.2.2.2(1) be required for SHES and HES items? |  |  | 7 | 2022-04-07 14:55
20220412 | 20220412018 | 18 | Schedule of Operations | Please clarify the Schedule of Operations language. It states â€œDo not move to the next stage until all work in current stage or substage is completedâ€. The use of â€œall workâ€ is very general, please be more specific. Can each major operation work through the project per the staging plan, then the succeeding operation can follow in the same manner? Or does each contractor operation need to assume 12 mobilizations NB and 8 mobilizations SB? |  |  | 8 | 2022-04-08 16:05
20220412 | 20220412018 | 18 | Design schedule and quantites | Please provide a design schedule. |  |  | 9 | 2022-04-08 16:09
20220412 | 20220412020 | 20 | Longitudinal joint | I would like clarification of this statement in the specials, "The longitudinal joint between travel lanes and between travel lanes and shoulders will be required to be echelon" So is this stating that echelon paving is required across both lanes of traffic no cold joints allowed | An addendum will be issued to clarify the language. Consistent with normal direction of travel - pave driving lane, adjacent turn lanes, and shoulders in echelon. In locations of two way left turn lanes, construct HMA pavement with a single cold joint across the full paved roadway width. | Mike Coleman | 1 | 2022-03-24 11:52 | 2022-03-29 08:08
20220412 | 20220412020 | 20 | PUSH BUTTONS - PROPOSAL LINE NUMBER 0242 | The quantity listed on this project for push buttons lists 3 but the plans only show 2. Should a 3rd button be included in the quote and if so, what arrow direction for the sticker sign? | The quantities show push buttons on Signal Base 2, 3, and 8. On sheet 1 of 4 of the signal plansâ€™ push buttons are also shown on SB 2, 3, and 8. See the revision note above the signature block on sheet 1 of 4 also. | Mike Coleman | 2 | 2022-03-29 13:25 | 2022-04-01 10:21
20220412 | 20220412020 | 20 | HMA Shoulders | What is the intent of the un-hatched areas (presumably paved shoulders) roughly from stations 256+61-279+00 and stations 289+00-331+00? Per the typical section these areas are intended to receive 4" removing asphaltic surface milling and 4" HMA pavement, however the hatching in the plan details doesn't indicate this. Please provide clarification on what removal activity is needed (if any) and what the proposed pavement section is. | The hatch pattern did not show up in the plans for the station ranges indicated, however, quantities for 4" removing asphaltic surface milling and 4" HMA pavement for the shoulders are reflected in the miscellaneous quantities and the station/offset notes in the plan detail sheets. | Mike Coleman | 3 | 2022-04-08 10:35 | 2022-04-11 11:20
20220412 | 20220412020 | 20 | DBE GOAL | This project has a DBE goal of 10% There are not any substantial work categories for DBE participation on this project would the department consider lowering the DBE goal to something that is more obtainable? | OBOEC has reviewed the goal. The DBE Goal of 10% will remain. | Mike Coleman | 4 | 2022-04-08 14:47 | 2022-04-11 08:51
20220412 | 20220412021 | 21 | Traffic Signal Controller | We could not find what type of traffic signal controller is being used on this project in the specs or plans. Can you please confirm the controller type? (EPAC/Eagle, Econolite, Etc.) | The controller will be existing Econolites. | Jill Fehrman | 1 | 2022-03-18 08:05 | 2022-03-18 10:22
20220412 | 20220412021 | 21 | CABINET MODIFICATION | Number 21 of the special provisions is listed as Cabinet Modification to furnish load switches and MMU and to install the equipment. Who is to program the MMU, Econolite Controller, and Cabinet modification & should that cost be included in this proposal pay line 0168? | The intent of item 21 of the special provisions is to have the contractor program the malfunction management unit and perform the cabinet modification. The cost for those items should be included. The controller was not mentioned in the specification because it was to be changed by Milwaukee County forces. | Mike Coleman | 2 | 2022-04-05 09:22 | 2022-04-06 06:16
20220412 | 20220412021 | 21 | Restoration of Contaminated Soils areas | Will the pavement be removed and counted in the tonage of the two bid items 10 and 180. What bid items will restore the roadway after excavation the roads. | The tonnage for those two items is only to install the monotube traffic signal bases and associated items. No pavement is being removed. | Mike Coleman | 4 | 2022-04-08 23:40 | 2022-04-11 07:05
20220412 | 20220412023 | 23 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | The culvert repair at 9 locations require a partial repair that must match the existing pipe type and cannot be changed to Class IIIA or Class IIB (nonmetal) culvert pipe. There are 4 concrete culvert locations that require total replacement and 3 of these culverts are within 2 feet of the top of subgrade at one point along the pipe and must be constructed as type IV concrete pipe. The location at STA 263+59 meets the requirements of Class IIIA culverts and will be changed via addendum #1. | Mike Coleman | 1 | 2022-04-05 11:35 | 2022-04-06 09:18
20220412 | 20220412023 | 23 | Start By Date | With this project being re-bid the contractor would request that the original start by date be eliminated. | The start by date will be changed to August 8, 2022 and the item of cold weather paving will be added to the contract. We will be making the changes via addendum | Mike Coleman | 2 | 2022-04-06 08:09 | 2022-04-07 07:51
20220412 | 20220412024 | 24 | Milling Depth | Right now the plan calls out to mill the majority of the 16', 12', & 10' shoulder at 1/2" depth. Will the department consider looking at milling 1.75" or 2" on the length of this project. There is a lot of segregation spots in the current surface lift with patches that are the depth of the surface layer. It would be beneficial to get this layer removed to eliminated reflective cracking coming back from those issues. | Proceed per plan. We raised the grade on this project because we are short on structure. It is a balance between milling out the distresses and trying to provide more structure. We selected SMA on this project for its crack mitigation properties. | Mike Coleman | 1 | 2022-03-18 13:45 | 2022-03-29 08:12
20220412 | 20220412024 | 24 | Traffic control | please explain how the following sentence on page 12 of the proposal is applicable to this project. (Provide a dedicated person or alternate method to guide traffic alongside or near moving operations such as milling, paving, and shouldering) | Since the work will be occurring behind barrels, we will not be requiring a dedicated flagger at the moving operation. In this case, barrels are considered an â€œalternate methodâ€ to a flagger. | Mike Coleman | 2 | 2022-03-24 13:08 | 2022-03-25 07:51
20220412 | 20220412024 | 24 | Temporary Pavement Marking | Hello- Since the lane closures are only allowed Mon-Fri, will the contractor need to apply the Stage 1 yellow/Stage 2 white centerline paint for a short term closure? Can traffic control drums be used in lieu of the edgeline? Also, the Stage 2 temporary paint is applied to final surface and removing it will leave a scar. If temporary markings are to be used on this surface should it be removable tape? | Temporary pavement marking is intended to be used in the merge area for the lane closures only, per standard detail. | Mike Coleman | 3 | 2022-04-04 11:19 | 2022-04-06 08:26
20220412 | 20220412026 | 26 | Traffic Signal Controller | Can you please confirm what traffic signal controller is being used for this intersection? (EPAC/Eagle, Econolite, Etc.) | The traffic signal controller at the West Riverview Expressway and West Grand Avenue intersection is a Siemens m60 controller. | Mike Coleman | 1 | 2022-03-18 08:42 | 2022-03-23 10:50
20220412 | 20220412026 | 26 | Soil Borings | Is there soil boring information available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ap0idpa91mu5ll1osrmzp4ud26m9vrrq or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-04-06 13:18 | 2022-04-07 07:54
20220412 | 20220412027 | 27 | Start Date | The Special Provisions state that work shall start no later than July 7, 2022. What is the reason for this and will the department consider removing this requirement to allow for a later start date? | The reason for the specified start before date is to ensure the project is completed before the Cranberry Harvest season begins. STH 173 is one of the primary haul routes for the seasonâ€™s crop in that area. The design team does not feel adjustments should be made that would permit the project to be completed later in the season. | Mike Coleman | 1 | 2022-03-25 14:49 | 2022-04-01 07:12
20220412 | 20220412029 | 29 | Stage 2 Interim Completion Year | It appears on Page 7 of the Specials under Interim Completion and Liquidated Damages for Stage 2 work the year is incorrect by stating 2022, it should be 2023. Please confirm. | Yes, it should be 2023. This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2022-03-15 08:49 | 2022-03-16 12:15
20220412 | 20220412029 | 29 | Design Conversion factors used (tons/cy) | What are the design conversion factors used (tons/cy) for these item of work: Base Aggregate Dense 3/4" and Base Aggregate Dense 1-1/4"? | A design conversion factor of 2.0 tons/cy was use for both Base Aggregate Dense 3/4" and Base Aggregate Dense 1-1/4". | Mike Coleman | 2 | 2022-03-15 09:04 | 2022-03-16 12:25
20220412 | 20220412029 | 29 | Design Schedule & Soil Geotechnical Report | Please provide the Design Schedule & Soil Geotechnical Report. | The design schedule and Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/7linc9tpw8hejm4ldet8tw9uxwhey2j6 or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2022-03-15 09:07 | 2022-03-16 12:28
20220412 | 20220412029 | 29 | Temporary Mechanically Stabilized Earth Walls | Additional information required to complete design of the Temporary MSE wall: Friction Angle of the Foundation Soils Factored Bearing Resistance of the Foundation Soils Friction Angle and Total Unit Weight of the Retained Soil (Soil behind the Reinforced Zone) | Please see the tables below for the recommended soil parameters at the boring locations. Boring HA-1 (based on water table depth of 5.7 feet) Depth (ft) Soil Type Effective Unit Weight Friction Angle (deg) Cohesion (psf) 0-0.5 Topsoil (remove) --- --- --- 0.5-5.7 SM 115 30 0 5.7-7.5 SM/SP 60 30 0 7.5-8.6 SP 60 34 0 Boring HA-2 (based on water table depth of 7.5 feet) Depth (ft) Soil Type Effective Unit Weight Friction Angle (deg) Cohesion (psf) 0-1 Topsoil (remove) --- --- --- 1-3.5 SM 115 30 0 3.5-7.5 SM/SC/SP 120 30 0 7.5-9.8 SP 60 30 0 9.8-10.5 ML 55 26 0 10.5-11 SP 60 30 0 Boring HA-3 (based on water table depth of 8.1 feet) Depth (ft) Soil Type Effective Unit Weight Friction Angle (deg) Cohesion (psf) 0-0.5 Topsoil (remove) --- --- --- 0.5-1 SM 115 30 0 1-4.5 CL 120 24 500 4.5-8.1 SM/SP 120 32 0 8.1-10 SP 60 34 0 Boring HA-4 (based on water table depth of 7.0 feet) Depth (ft) Soil Type Effective Unit Weight Friction Angle (deg) Cohesion (psf) 0-0.8 Topsoil (remove) --- --- --- 0.8-2.8 SC/SM 120 30 0 2.8-7.0 SP 120 34 0 7.0-9.6 SP 60 34 0 | Mike Coleman | 4 | 2022-03-17 08:47 | 2022-03-24 10:49
20220412 | 20220412029 | 29 | Earthwork Data | The earthwork data on page 607, DIVISION 1 (STA 38+55TR - STA 237+00TR): IH 94 WB TEMP ROAD(STAGE 1B) the totals don't add up. Common, fill and EBS are all not right if you add all the STA numbers up. Also Division C2 IH 94 EB 232+00 - 237+00 Common Excavation of 13 CY seems low compared to the cross section please confirm this is correct. | Sheet 607 - Reviewing the spreadsheets the tables are derived from, it was determined that the sum totals did not extend the full length of the sheet, thus missing several rows in the totaled numbers at the bottom. Corrected totals are shown below Total cut should read 36,062 CY, (from 34,876 CY) Total Fill should read 69,500 CY (from 68,077 CY) Total EBS should read 1,803 CY (from 1,744 CY) Sheet 611 - Division C1 & C2 were reversed and the totals were incorrect. A corrected cut total for EB 2C1 is 655 CY and EB 2C2 is 2,945 CY. Other totals for these two tables on sheet 611 will be corrected in an addendum. | Mike Coleman | 5 | 2022-03-22 09:19 | 2022-03-23 10:48
20220412 | 20220412029 | 29 | 3/4 Base and 1-1/4" Base Quantiies | It appears on plan sheet 253, the 3/4" and 1-1/4" Base quantities don't total the Project Totals, it look likes the Stage 2C Phase 1 and 2 is where the problem is. | As stated in the question #6, the total for Stage 2C was totaled incorrectly for the base aggregate. This total will be corrected in upcoming addendum. | Mike Coleman | 6 | 2022-03-25 16:08 | 2022-03-29 07:10
20220412 | 20220412029 | 29 | Article 21. Select Borrow, Item 208.1100. | Why is Granular Backfill Grade 1 specified for Select Borrow? The Geotech doesn't specify Grade 1, it only suggests using Section 209 Granular Backfill, which should mean either Grade 1 or Grade 2 Granular. Grade 1 Granular is not available in the project area or surrounding areas. Grade #2 should be specified instead of Grade #1, its more available in the area (less expensive) and it will meet the requirements specified by the Geotech report. | Granular Backfill, Grade #2 would also be an acceptable borrow material. Addendum #2 will make this revision, allowing for Grade 1 or Grade 2. | Mike Coleman | 7 | 2022-03-29 08:48 | 2022-03-29 12:28
20220412 | 20220412029 | 29 | Temp MSE Walls Measurement | Section D for Measurement specifies the exposed face from front face ground line to retained grade for pay quantity. In the E Payment section, it states that payment will be based on the line of minimum embedment, which is an additional 1.5' of wall height. Which is correct? Also, is the removal of the wall incidental to the item? That is not discussed in the payment portion of the SPV. Thanks | Section D Measurement is correct. The payment area shall be the exposed face in the plane of the wall from the front face groundline to the retained grade as shown on the construction detail. Removal of the wall is included in the temporary wall wire faced mechanically stabilized earth bid item. | Mike Coleman | 8 | 2022-03-31 07:56 | 2022-04-01 10:22
20220412 | 20220412029 | 29 | 2022 Work to 2023 "Contractor Option" | Would the Department allow (contractor option) the specified Year 1 (2022) work (Stage 1A & 1B - Temporaries) to be constructed in the spring of 2023 with the understanding that all specified Year 2 (2023) work is still required to be completed by the same dates within the specials? This option would have less impact to the traveling public and allow the contactor to move work from the busy 2022 work months (July/August/September) to the spring of 2023 which is less busy. | No. Please bid according to the specified staging. | Mike Coleman | 9 | 2022-04-01 12:31 | 2022-04-04 10:50
20220412 | 20220412030 | 30 | ASP-5 Fuel Cost Adjustment | This is no ASP-5 Fuel Cost Adjustment included within the proposal and there is more than 100,000 cy of excavation. | ASP-5 will be added via an upcoming addendum. | Mike Coleman | 1 | 2022-03-10 09:06 | 2022-03-16 06:52
20220412 | 20220412030 | 30 | Topsoil vs Salvaged Topsoil | Why is the bid item Topsoil used on this project and not Salvaged Topsoil, which is available within this project area? | We anticipate some of the topsoil may be salvaged, but new material may also be required within the project limits. The department will issue an addenda providing a split between Salvaged Topsoil item (stages 1, 2, 3) and the Topsoil item (stage 4 and undistributed amount). | Mike Coleman | 2 | 2022-03-10 09:13 | 2022-03-16 12:21
20220412 | 20220412030 | 30 | Special Provision # 20 Temporary Emergency Pullouts | This special states that payment is for aggregate base course, signs, removing as required, and for providing and placing topsoil, fertilizer, seed, and mulch. Why are all these items incidental to this item and not paid for by there respective bid items already in the contract? Please change this. All the other special provisions for this project state the department will pay separately for finishing and erosion control items (#25, #28). | â€¢ Bid these per the standard detail and special provision. The anticipated values of quantities are shown in the MQ table on Sheet 177 for ease of developing your bid cost. The anticipated locations of the pullouts are shown on the traffic control plans. | Mike Coleman | 3 | 2022-03-14 16:20 | 2022-03-16 12:18
20220412 | 20220412030 | 30 | Design conversion factors used (tons/cy) | What are the design conversion factors used (tons/cy) for these item of work: Base Aggregate Dense 3/4" and Base Aggregate Dense 1-1/4"? | The design team used the following conversions for estimating purposes: BAD 3/4": 2.10 Tons/CY BAD 1 1/4": 2.00 Tons/CY This is consistent with the ranges allowed per FDM 19-5, Table 3.1. | Mike Coleman | 4 | 2022-03-15 09:04 | 2022-03-16 06:54
20220412 | 20220412030 | 30 | Design Schedule & Soil Geotechnical Report | Please provide the Design Schedule & Soil Geotechnical Report. | The design schedule and Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/88z7fza4pcphofxxsxle43fp9yce8xim or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 5 | 2022-03-15 09:06 | 2022-03-16 06:58
20220412 | 20220412030 | 30 | Abandoning Wells | What is the depth and size (diameter) of each well to be abandoned? | â€¢ These are anticipated to be standard monitoring wells for groundwater sampling based on surface observations. â€¢ The monitoring wells are anticipated to be 60 to 70-feet deep based on historic investigations completed by others. â€¢ The diameter is not known by WisDOT | Mike Coleman | 6 | 2022-03-25 11:59 | 2022-03-29 07:11
20220412 | 20220412030 | 30 | Earthwork Summary Note #4 | Note #4 says "SALVAGED/UNUSABLE PAVEMENT MATERIAL IS THE EXISTING CONCRETE AND ASPHALT PAVEMENT VOLUME, NOT AVAILABLE FOR FILL (MATERIAL TO BE WASTED)." Why must this material be wasted? If processed per the standard specifications this material can be used in embankments and other aggregate items. Can this note be removed or altered to allow the contractor to use this material as needed per the standard specifications to allow for the cheapest bid to the Department. | The note is intended to let you know that salvaged/unusable pavement material (part of cut) was not used to balance fills per WisDOT standard practice for the earthwork summary. If the contractor desires to recycle pavement materials following standard specifications, they can do so. The intent of the note is to not preclude recycling. | Mike Coleman | 7 | 2022-03-29 16:25 | 2022-03-30 12:39
20220412 | 20220412030 | 30 | Earthwork Summary Note #9 | Note #9 says, "EBS MATERIAL IN DIVISION 2 TO BE WASTED, DO NOT INCORPORATE EBS INTO FILLS." If this EBS material can be processed/dried/etcs to meet the requirements within the standard specifications, why does this material need to be wasted? Please change this note to allow this for the lowest bid possible. | We anticipate little opportunity to incorporate the EBS (shown Division 1, not Division 2 per note 9) into the project fills in Divisions 2 to 6 based on the cross sections for the pavement replacement. If the material is found to be acceptable by the engineer once it is excavated, there can be further discussion in the field. Bid the project as shown. | Mike Coleman | 8 | 2022-03-29 16:30 | 2022-03-30 12:39
20220412 | 20220412030 | 30 | Special Provision # 13 - Northern WI Veterans Memorial Cemetery | The above referenced special provision states the following. "No work will occur outside the right-of-way adjacent to the cemetery." "Do not use the adjacent right-of-way outside the slope intercepts shown on the plan for staging of personnel, equipment and/or supplies, borrow, or waste disposal." The second paragraph in the special provision ONLY pertains to the right of way adjacent to the cemetery, correct? Obviously, there is right of way that will be needed to be used to build the project (staging area, etc.) that is outside the slope intercept of the project. This will be allowed? | The second paragraph in the special provision applies to the right of way adjacent to the cemetery. The use of the remainder of the project right of way is covered under standard spec 106.4 Storing and Handling Materials. | Mike Coleman | 9 | 2022-03-30 16:44 | 2022-04-01 07:12
20220412 | 20220412030 | 30 | Culvert & Storm Sewer Pipe Cross Drain Detail (page 13) | Please confirm that if it is a storm sewer cross drain pipe DOT will want the entire trench up to subgrade, including the transition cut backfilled with sand? (as stated in 608.2.2.3) If this is true then a foundation backfill item should be added to account for a quantity of backfill needed for the transition cut. Or would DOT only want foundation backfill for storm sewer cross drain pipe to 1 ft above the pipe as if it was a culvert pipe (520) item? | Per the Culvert & Storm Sewer Pipe Cross Drain Detail (page 13), the foundation backfill for storm sewer cross drain pipe should be taken to 1 ft above the storm sewer cross drain pipe as if it was a culvert pipe (520) item. | Mike Coleman | 10 | 2022-03-31 13:52 | 2022-04-04 06:26
20220412 | 20220412030 | 30 | 2022 Work to 2023 "Contractor Option" | Would the Department allow (contractor option) the specified Year 1 (2022) work (Stage 1B - Crossovers) to be constructed in the spring of 2023 with the understanding that all specified Year 2 (2023) work is still required to be completed by the same dates within the specials? This option would have less impact to the traveling public and allow the contactor to move work from the busy 2022 work months (July/August/September) to the spring of 2023 which is less busy. | At this time, the Department is not planning to change the proposal in the current advertisement. | Mike Coleman | 11 | 2022-04-01 12:32 | 2022-04-05 12:16
20220412 | 20220412030 | 30 | 1 1/4" Base Aggregate Bid Quantity | Please look at your 1 1/4" base aggregate bid quantity. In doing a quick takeoff of stage 2(nb) and stage 3(sb) mainline 1 1/4" base quantities it seems like the quantity shown for stage 2 (49296 T) mainline 1 1/4" and stage 3 (46841 T) mainline 1 1/4" includes the entire quantity for mainline to be re-done, including the mainline to be completed during stage 4A & 4B. The bid quantity of base aggregate 1 1/4" may be doubled up for the portion of mainline at CTH B to be done in stage 4, since the base aggregate 1 1/4" is listed in the summary for stage 4 work. | We have reviewed the 1 1/4" Base Aggregate calculations and the quantities as shown are correct, there are no double calculations. In the miscellaneous quantities, the MAINLINE rows in Stage 2 and 3 include the left turn lanes and over widening (Stage 2 only) quantities which are 12â€ in depth. | Mike Coleman | 12 | 2022-04-04 15:08 | 2022-04-05 10:28
20220412 | 20220412031 | 31 | Migratory Birds | It is unlikely that the contract will be executed prior to the bird netting requirement. Would the department look into providing for the netting to be completed prior to 4/15 by DOT or County forces for this project? It would be understood the contractor would be responsible for maintenance of the netting installed by others. | The county will be installing netting on the structures. An addendum will be issued such that contractor is only responsible for maintenance. | Mike Coleman | 1 | 2022-03-14 11:59 | 2022-03-29 08:45
20220412 | 20220412031 | 31 | Precast Wingwall Quantities | Sheet 63 of the plan calls out precast wings on the inlet and outlet sides of structure B-61-289, whereas the estimated quantity calls out â€œPrecast Concrete Wingwalls B-61-289: 1 Eachâ€. Does this quantity include all four precast wings? | The quantity includes all four precast wings. The special provision for this bid item â€œPrecast Concrete Wingwalls B-61-0289â€ indicates under section D Measurement that the department will measure Precast Concrete Wingwalls (Structure #), as a single complete unit of work for each structure, acceptably completed. Each unit shall consist of all the wingwalls required for one box culvert. | Mike Coleman | 2 | 2022-03-26 08:33 | 2022-03-29 13:48
20220412 | 20220412032 | 32 | Migratory Birds | It is unlikely that the contract will be executed prior to the 4/15 bird netting requirement. Would the department look into providing for the netting to be completed prior to 4/15 by DOT or County forces for this project? It would be understood the contractor would be responsible for maintenance of the netting installed by others. | Jackson County will be netting the bridge for the town. Item 999.2005.S is included in the plans for maintaining bird deterrent system once the construction contract is authorized. | Mike Coleman | 1 | 2022-03-14 11:59 | 2022-03-15 15:04
20220412 | 20220412033 | 33 | Adjusting Guardrail | Please review your line 52 for adjusting steel plate beam guard quantities. Most of this quantity states that it is for adjusting EAT's. Per the Standard Spec, this bid item will not address the changes needed in the EAT's. The subsequent bid items for "replacing posts and blocks" and "replacing rail and hardware" don't cover proprietary items found in EAT's either. | The 2022 Standard Spec does not restrict adjusting guardrail for EAT areas. The item and quantity of Adjusting Steel Plate Beam Guard in intended for guardrail locations shown in plans including the end treatments. If the required height adjustments to an existing EAT would cause component of the guardrail system to become unserviceable, then replacement of such component could be measured and paid for under Replacing Material items included in the contract, as the Engineer designates. | Mike Coleman | 1 | 2022-04-06 08:48 | 2022-04-07 07:36
20220412 | 20220412033 | 33 | Traffic Control | On page 3 of the special provisions it states that "only one flagging operation at a time can be performed within the project limits". Is this going to be upheld? This will force us into a mill and fill scenario driving up costs rather than utilizing the 72 hours that are also present in the special provisions. | The Contract does allow for additional flagging operations to occur with approval by Engineer. The 72-hour requirement needs to remain as this is, due to concern of the remaining pavement surface following milling. This was discussed throughout design and during Central Office Review. | Mike Coleman | 2 | 2022-04-06 12:26 | 2022-04-07 07:50
20220412 | 20220412035 | 35 | 15' Culverts | There are two mainline culvert pipe locations that are showing 15" diameter culvert pipe replacements. These two locations currently have an existing plastic pipe inserted within a metal culvert. Should these culverts be increased in diameter to meet design recommendations in Chapter 13 Drainage of Facilities Development Manual? Chapter 13-15-5.3.1 (Design Criteria) states the following: 5.3.1 Minimum Pipe Size In accordance with Department of Transportation practice, the minimum size of pipe for culvert cross drains shall be 24 inches, except that on multi-lane highways in fill of 10 feet or more, the minimum size shall be 30 inches. | A review of the current design standards for perpetuation projects (FDM 13-1-30) has a section dedicated to â€œCriteria for â€œIn-Kindâ€ Replacement (30.3.2.2). The STH 64 culvert replacements at the locations questioned meet all 15 criteria for replacement in-kind. No clear signs or evidence of undersizing have been observed from our field review and WisDOT has no reports of a known drainage issue at these locations. In addition, both locations with 15â€ diameter culvert pipe replacements have shallow cover (1.28â€™ and 1.45â€™). It would not be recommended to upsize these culverts without lowering the proposed inverts, which would result in modifications to the existing drainage ditch system along STH 64. This type of improvement would not fit current WisDOT perpetuation standards. | Mike Coleman | 1 | 2022-04-05 15:17 | 2022-04-11 07:47
20220412 | 20220412036 | 36 | PWL Density | WIll the department consider removing the PWL density for the lower layer and change to QMP. There is approx 5500 tons of lower layer to be paved. After the test strip it leaves 4800 tons. THe project has 2 bridges on it, the road takes a 90 degree turn to Gilman and there are 2 different sets of concrete rumble strips that are staying in place and will have to be paved around. There is little opportunity with all these starts and stops to get the rolling pattern going nice and consistent before the next stop and is evident that it will be very problematic at 1.5" let alone 1.25" and a 58-34V oil. This, along with past problems of gauges not reading consistently on the thin lift, are going to be an extreme challenge and hopefully can be reconsidered for QMP. | PWL will be kept in the project. Please bid per plans and specifications. See table 460-3 of the standard. Note 5 was added with the latest specifications when using # 5 mixes on lower layer, with minumum thickness. | Mike Coleman | 1 | 2022-03-19 11:55 | 2022-03-23 06:18
20220412 | 20220412036 | 36 | AS Patching | Given the quantity of AS Patching in the plan (750), one would be safe to assume the DOT is anticipating quite a bit of work will need to be done after milling to prepare patches and patch before paving? | Yes, we assume a lot of work will be required to prepare patches. | Mike Coleman | 2 | 2022-03-20 08:30 | 2022-03-23 06:19
20220412 | 20220412036 | 36 | PWL Tons @ Rumble Strips | Would the department consider removing the PWL Density on the tons of HMA that are between the rumble Strips and treating them like intersection tons. There are 2 sets of concrete rumble strips coming into 2 different stop signs. Each set will have 3 segements that will be 2-3 loads of HMA per lift. taking off and coming into each one is going to take alot of time, no different than paving an intersection. | The rumble strips will be removed to partial depth to match the milling and new asphalt rumble strips will be added. An addendum will be issued for the change. | Mike Coleman | 3 | 2022-03-28 09:28 | 2022-03-30 10:09
20220412 | 20220412036 | 36 | Temporary markings on milled surface | Good morning, seeing as the milled surface can be left 72 hours before paving, what is your plan for temporary pavement markings on the milled surface? Thank you. | Temporary marking will be applied to the milled surface. The additional quantity will be added in the addendum for question #3. | Mike Coleman | 4 | 2022-03-29 06:50 | 2022-03-30 10:09
20220412 | 20220412036 | 36 | Guardrail | The guardrail at the 2 pipe installations calls for portions to be adjusted, portions to be removed/replaced, and portions to be removed/reset. It appears that some of those quantities may overlap each other, specifically sta 253+70 - 254+80 LT. Won't most of the guardrail have to be removed at these 2 locations in order to complete the excavation for the culvert pipe transitions which extend out to the subgrade shoulder point? It also appears that a temporary lane shift could be required to complete the installations given the depth of the excavations. This would also cause a conflict with guardrail that is to remain in place. If the guardrail is removed/reset do the slopes have to be built to current standards for reinstallation of the existing guardrail or does the guardrail have to be changed to a different type to accommodate the steepness of the slopes since the cross sections show little to no slope work being done in some of the locations? | The intent is to remove and reinstall minimal guardrail for the replacement of the two culvert pipes. In the areas of removing and reinstalling guardrail, the shoulders would be restored to existing condition and match into the new pipes. The exception is the one terminal that is being upgraded which will match current standards. For the quantities that overlap, if the guardrail is not removed and reinstalled, it will need to be adjusted to meet current standards. | Mike Coleman | 5 | 2022-04-01 07:07 | 2022-04-05 10:29
20220412 | 20220412037 | 37 | Traffic Signal Controller | Can you please confirm what traffic signal controller is being used? (EPAC/Eagle, Econolite, Etc.) | The City of Milwaukee is using Econolite Cobalt TS2 Type 1 controllers. | Jill Fehrman | 1 | 2022-03-18 10:31 | 2022-03-18 17:03
20220412 | 20220412037 | 37 | Temp Shoring at Pier | Should there be an item for temp shoring to allow for removal of the existing pier and construction of the new pier? It does not appear that there is sufficient room in the closed work area to allow for open cut? | The maximum depth of excavation for removal of existing pier footings and construction of new footings is approximately 10.5ft. The existing and finished pier footings are 10 ft wide. With 36 ft of median/shoulder removal and replacement, excavation slopes will not exceed 1:1. The structure designer believes this is adequate working room and no additional payment will be made for shoring should the contractor chooses to use shoring. | Mike Coleman | 2 | 2022-03-31 11:37 | 2022-04-05 08:09
20220412 | 20220412038 | 38 | Winter Suspension & Construction Staging | In the Special Provisions underneath construction staging (Stage 1 Construction) it states that "The following work may be constructed in stage 1, 2, or 3 as long as the lane closure length and spacing requirements noted in the Traffic section are met." Stage 1 & 2 have to be completed prior to the winter shutdown in 2022 so shouldn't that statement be removed? | This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2022-03-24 17:29 | 2022-03-30 12:05
20220412 | 20220412038 | 38 | Project Design Schedule | Can a design schedule be provided? | The design schedule and Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/zn7ac51vtd9behet2onx8u7evffjrkmy or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-03-24 17:31 | 2022-03-28 10:31
20220412 | 20220412038 | 38 | Centerline Over-mill | At the centerline over-mill into the adjacent lane can the can the 3-foot area be milled at the slope of the adjacent lane? For example, when the passing lane is milled at the lane cross slope the 3-foot area of the driving lane would be milled at the passing lane cross slope. | In order to evaluate the centerline joint and crack repairs needed, as well as the Dowel Bar Slot and Dowel Bar Spall Repairs needed, existing asphalt needs to be removed. The plans currently have the following note within the â€œTraffic Control Stage 1 Typical Sections- Mill and Overlayâ€ sheets: WITHIN THE DRIVING LANES, ALL MILLING SHALL EXPOSE THE TOP OF THE EXISTING CONCRETE SURFACE PRIOR TO PAVING THE FINISHED LOWER LAYER. Therefore, both lanes need to be milled at the slope of the existing concrete in their respective lanes. No Addendum is needed, as the plans address this question. | Mike Coleman | 3 | 2022-03-24 17:31 | 2022-03-28 13:24
20220412 | 20220412038 | 38 | Traffic Lane Closures | Will the department consider eliminating the statement that lane closures are not allowed Northbound from 12:01 PM to 11:59 PM on Fridays between June 23, 2022 and September 5, 2022 and Southbound from 9:01 AM to 11:59 PM to allow the contractor fully schedule their forces and work full weeks? | During the design process, a substantial amount of time was devoted to evaluating traffic conditions vs. contractor operations. The plans and special provisions balance traffic congestion and safety vs. contractor operations. No changes will be made to the lane closure restrictions. | Mike Coleman | 4 | 2022-03-24 17:32 | 2022-03-30 10:05
20220412 | 20220412038 | 38 | Milled Surface | Why won't the department allow traffic to run on a milled surface? The Contractor is responsible for maintenance and the contract has an Asphaltic Surface Patching Item? | Travel lanes for I-39 traffic will not be allowed to run on a milled surface. Milling will remove all of the existing asphalt and expose the existing concrete surface to allow field determinations and repairs of centerline joint, centerline cracks, and dowel bar slots. There will be no changes to the special provisions related to traffic running on a milled surface. | Mike Coleman | 5 | 2022-03-24 17:35 | 2022-03-30 12:06
20220412 | 20220412038 | 38 | HMA Pavement Timing | Why is the department specifying that the traffic is not allowed to travel on the binder for no more than 3 weeks? | During the design process, a substantial amount of time was devoted to evaluating how long traffic could run on the binder layer. The special provisions balance allowing the contractor to maximize their construction efforts and ensuring the binder does not deteriorate with anticipated traffic loadings. No changes will be made to the binder layer restriction. | Mike Coleman | 6 | 2022-03-24 17:37 | 2022-03-30 06:25
20220412 | 20220412038 | 38 | Outside Shoulder Pavement Thickness | Looking at the Proposed Typical Cross Section it shows that the Outside Shoulder is only getting one 1.75" surface lift and in the Traffic Control Details for Stage #1 is states that the outside shoulders are getting two lifts of 4LT. So shouldn't the outside shoulder pavement be milled at 3.5" and paved at 3.5" like it states on the Traffic Control in order to meet the intent is to have the roadway lower lift match with the same elevation by the end of the week. If the intent is to only pave 1.75" surface lift then there will be an issue with the lanes not being matched up to the same elevation by the end of the week. | This will be addressed in an upcoming addendum. | Mike Coleman | 7 | 2022-03-29 10:01 | 2022-03-30 12:07
20220412 | 20220412038 | 38 | Is there a good reason why the stage 3 Ramp work can't be performed in 2022. | Normally on divided highway projects, we do the ramp work and ramp asphalt paving with the mainline work. I believe it generally provides for a better-quality project and would shorten the overall project completion time and be less of an inconvenience to the public. Can Stage 3 work be performed in 2022 and can it be done with other stages of the project shortening the over-all completion of the project? |  |  | 8 | 2022-04-09 13:20
20220412 | 20220412039 | 39 | Alignment Data | Can the department provide the alignment detail showing the northing and easting for the end station of the alignment for USH 8? Or could an alignment file be made available to the bidders? | Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One in Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 1 | 2022-03-11 13:32 | 2022-03-15 11:37
20220412 | 20220412039 | 39 | Follow up to Question #1 - Available File-types are not Usable | Can the department please provide the northing & easting for the end station of the USH 8 alignment? Prior to submitting question #1, the Contractor Data Package was downloaded and reviewed, and the file types provided which likely contain the requested information, are not usable without additional software capabilities (i.e. XML & DWG files). The only file type within the CDP that is readable with standard software is the .CSV format, which only provides the superelevation details, but not the corresponding northing and easting locations for the alignment. The Alignment Details in the plans were also reviewed, and the northing and easting for the ending station of the alignment was not provided. Contractor is requesting the northing and easting for the end of the alignment, east of curve 13. | The alignment file can be found at the following location: https://wisdot.box.com/s/dg889fuu429uf85u9dip72cjujxsx0kf or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-03-15 12:49 | 2022-03-16 07:02
20220412 | 20220412039 | 39 | Traffic Control for Culvert Work | What is the departmentâ€™s intent for maintenance of traffic during construction at structure C-43-918? Will bid items for temporary precast concrete barrier wall, crash cushions, and temporary traffic signals be added to control traffic and provide a workspace for construction? | The intent was for wing wall replacement of C-43-918 to be completed utilizing a full shoulder closure while work was occurring with additional flagging on USH 8 as needed during work hours. | Mike Coleman | 3 | 2022-03-29 10:34 | 2022-03-31 07:03
20220412 | 20220412039 | 39 | Project Schedule | Will the department please provide the preliminary schedule used in the project design and development for review? | The design schedule and Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/dg889fuu429uf85u9dip72cjujxsx0kf or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2022-03-29 10:41 | 2022-03-31 07:07
20220412 | 20220412039 | 39 | Weekend Traffic Restriction for Milled Surface | Would the department consider removing the language â€œor by the end of the work weekâ€ from Paragraph 5 of Article 3 in the special provisions? This would allow traffic to run on a milled surface for up to a maximum of 96 hours regardless of the day of the week, and would allow the contractor to be more efficient with the milling & paving operations. | After discussions with the Region, the language in the specifications will be modified to remove the weekend restrictions. However, the timetable for traffic on any milled surface will be reduced to 72-hours. | Mike Coleman | 5 | 2022-03-29 16:33 | 2022-04-04 10:48
20220412 | 20220412039 | 39 | Box Culvert Temp. Stream Diversion | In the general notes section on the structure plans it states, "see roadway plans for temporary stream diversion details", we are not finding anything in the plan set for details. Did the temp. diversion detail sheet get left out? | No temporary diversion channel details were developed. Contractor has flexibility to determine means and methods for the temporary diversion of water for this project. | Mike Coleman | 6 | 2022-04-01 13:51 | 2022-04-04 10:49
20220412 | 20220412039 | 39 | Temporary Diversion Chanel | Is the intent of the Temporary Diversion Chanel to be in the form of a temporary culvert through the roadway, or through the existing box culvert? | The intent of the temporary diversion channel was to keep water flow through the existing box culvert. | Mike Coleman | 7 | 2022-04-08 11:00 | 2022-04-11 07:06
20220412 | 20220412039 | 39 | 625.0100 Topsoil | In the miscellaneous quantities there a quantity of 7960 sy of Topsoil called out as undistributed. That is more the 50% of the pay item. Can some indication be provided on where this quantity is planned on being used, or can the quantity be adjusted to be more in line with the locations of disturbance as shown on the plans? | The undistributed restoration quantities include some areas at the culvert pipe transitions outside of the erosion mat areas. | Mike Coleman | 8 | 2022-04-08 11:49 | 2022-04-11 08:49
20220412 | 20220412040 | 40 | DBE Goal | This project was bid in December with a DBE goal of 3%, now the project goal has increased to 4%. Can we maintain the 3% goal? | This has been reviewed by OBOEC. The goal will remain at 4%. | Mike Coleman | 1 | 2022-03-25 20:04 | 2022-03-28 10:36
20220412 | 20220412040 | 40 | Milling and Paving Restriction | This project was bid in December without any restrictions on when paving had to be completed after milling. This time a restriction requiring paving to be completed within 96 hours of milling was added. It does not appear anything changed from the original plan which would require additional restrictions? | The restrictions were required in the pavement design report but were missed in the first letting, then added for the current letting. The original restrictions in the pavement design report were more restrictive than included in this contract and were reduced to balance the risk to the DOT and production for the contractor. | Mike Coleman | 2 | 2022-03-25 20:16 | 2022-03-28 10:35
20220412 | 20220412041 | 41 | Milled Surface | The proposal calls for through traffic lanes to be paved by the end of the work week and also prohibits a milled surface during Special Events, which includes weekend ball tournaments throughout June and July. Will the department consider allowing a milled surface over the weekend to accommodate continuous construction activities, and therefore, eliminate additional mobilizations/phases to complete the work? | An addendum will be issued to change the current end of week requirement to a milled surface open to through traffic shall not remain in place for longer than 72 hours unless adverse weather prevents placement of the asphalt layer. | Jill Fehrman | 1 | 2022-03-16 12:06 | 2022-03-18 16:57