## qandasearchletting_results
Date: | 2022-05-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220510 | 20220510001 | 1 | Vertical Clearance Elevation over I-94 | What is the minimum clearance elevation to be maintained over EB and WB I-94? |  |  | 1 | 2022-05-05 08:39
20220510 | 20220510002 | 2 | 649.0760 Temp RPM's | The quantities for item 649.0760 appears to be overstated. Typical spacing between these is 25', but going off of the listed quantities these would need to be spaced at 6' to use that many in the lane shift tapers. Please advise if this quantity is overstated or if the contractor should plan on installing every 6'. Thanks | The spacing of the Temporary Marking Raised Pavement Marker shall be 25 feet. An addendum will be issued to correct the quantity. | Mike Coleman | 1 | 2022-04-27 16:18 | 2022-05-02 09:29
20220510 | 20220510003 | 3 | designers schedule | can we have the designers schedule please. | The design schedule can be found at the following location: https://wisdot.box.com/s/mgqknzs8k7w4vlismb5rkedcseqnl0n3 or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-04-12 07:35 | 2022-04-12 10:37
20220510 | 20220510003 | 3 | Traffic control | Is there any way we can get a 1 page traffic control plan per stage / like the project over view plan accept being traffic control | An addendum will be issued to add a traffic control sheet | Mike Coleman | 2 | 2022-04-14 16:01 | 2022-04-18 08:38
20220510 | 20220510003 | 3 | Traffic and Hours of Operation. | Can the hours of lane closures be provided the interstate highway portion of the project? | The lane closure hours for IH39 are listed in Table 1 and Table 2 of the Traffic section in the special provisions. Table 1 is for the Summer and Table 2 is for the Spring and Fall | Mike Coleman | 3 | 2022-04-23 12:44 | 2022-04-26 06:47
20220510 | 20220510003 | 3 | No Time Extensions - Old Language - Remove | The below language should be removed based on discussions with the Department during association meetings for transferring to much risk to the contractor. Page 3 of the Specials. The department will not grant time extensions to the interim completion dates specified above for the following: 1. Severe weather as specified in standard spec 108.10.2.2. 2. Labor disputes that are not industry wide. 3. Delays in material deliveries. | With having the incentive/disincentive for Interim completion of work wording in the contract, we felt the time extension language was appropriate. Originally the no time extension language was intended for only the incentive/disincentive portion of the contract, but we didnâ€™t specify this in the specials. The interim completion dates Outside of Stage 2 and Stage 4 should not be affected by the no time extension clause. An addendum will be issued specifying incentive/disincentive with the time extension clause. | Mike Coleman | 4 | 2022-04-25 13:42 | 2022-04-27 11:52
20220510 | 20220510003 | 3 | CAD Files | Can CAD files be made available with existing and proposed surfaces in one of the following formats (LandXML, .Dwg or .DGN) | Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One is Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 5 | 2022-04-27 07:49 | 2022-04-27 08:00
20220510 | 20220510003 | 3 | Answer to Question #4 - No Time Extensions | Would the DOT consider only applying these No Time Extensions to the Incentive Part of the Interim Completion Dates and not the Disincentive. These No Time Extensions (Weather, Labor & Material Delays) are not controllable by the Contractor, so why should the contractor get penalized for them? Please consider only applying them to the incentive. | Please see addendum no. 3 issued April 28, 2022. | Jill Fehrman | 6 | 2022-04-28 11:27 | 2022-05-09 12:32
20220510 | 20220510003 | 3 | Bid item 142 Temporary Shoring | Would the Department provide the reasoning for the Temporary Shoring that is being called for along both sides of STH 60 under the existing bridges? | During the timeframe STH 60 is lowered to subgrade, the bottom of the pier foundation could be exposed. BOS felt it was necessary to stabilize the material next to the piers with Temporary Shoring. | Jill Fehrman | 7 | 2022-05-05 11:44 | 2022-05-06 11:37
20220510 | 20220510003 | 3 | Concrete Approach Slab | The plan details for 1012-01-74 identify CPAS areas but there is no bid item or quantity for Concrete Approach Slabs. Please clarify | An upcoming addendum will be issued to add the Item Concrete Approach Slabs to the proposal. | Jill Fehrman | 8 | 2022-05-05 14:59 | 2022-05-06 11:42
20220510 | 20220510003 | 3 | common Ex. Waste | Will the waste excavation be able to be wasted on the R/W ? | WisDOT anticipates future work in this area. The contractor will not be allowed to waste excavation material within the R/W. | Jill Fehrman | 9 | 2022-05-05 15:44 | 2022-05-06 11:33
20220510 | 20220510004 | 4 | Pickup Sweeping | Will the contractor be required to Pickup Sweep or Vacuum Sweep the residuals from the milling operations? See Special Provisions Page 5, 8. Environmental Protection, paragraph 4. On rural highway the residuals from the milling operations have traditionally been broomed to the shoulder. | SWR Maintenance has confirmed that the residuals from millings can be broomed to the shoulder. | Mike Coleman | 1 | 2022-04-14 13:16 | 2022-04-19 11:20
20220510 | 20220510004 | 4 | Special Provision #4 & #5 | Special provisions 4 and 5 seem to be pretty restrictive for a rural mill and overlay project. Is this based on traffic counts? And will the department consider removing? | An addendum will be issued to revise. | Mike Coleman | 2 | 2022-04-19 09:42 | 2022-04-20 07:52
20220510 | 20220510004 | 4 | Night Time operations | Is the night time work restriction because of traffic count? Would the department consider allowing day time work with shorter work zones? Thanks | The department will not allow daytime work with shorter work zones for this project due to the traffic volumes on this highway. | Jill Fehrman | 3 | 2022-05-02 12:59 | 2022-05-09 12:35
20220510 | 20220510005 | 5 | Turbidity Barrier Data | For calculating the t-barrier height, what is the known streambed elevation? Also, given the data that the observed water level was 776.60 ft and the Q2 is 784.39 ft, plus difference between observed water and streambed elevations, it appears that the t-barrier height needed will make this application non-functional in the event of any significant rise in water level. Will the department consider removing the t-barrier bid item and increasing the cofferdam area or adding a temporary shoring bid item? | After reviewing the bidderâ€™s original question below, Iâ€™m wondering if they are inquiring about turbidity barrier at the piers vs. the abutments (they donâ€™t specify turbidity barrier at the abutments). Either way, from BOSâ€™s perspective, cofferdams should be used at the piers, and turbidity barrier should still be feasible at both abutments based on the bottom of abutment elevations in relation to the observed water elevation and the Q2 water elevation. Based on our streambed cross-sections, we anticipated that turbidity barriers could be placed in front of the abutments above the observed water elevation out of the water which would still allow room for construction of the abutments behind the turbidity barrier. Additionally, FDM 10-45 states that turbidity barrier can be installed up to 8 feet tall and can be used for flows up to 5 ft/sec (the estimated Q2 flow for B-28-192 is ~1.9 ft/sec and we donâ€™t anticipate that the turbidity barrier would exceed 8 feet tall for this project). | Mike Coleman | 1 | 2022-04-25 09:11 | 2022-04-28 10:03
20220510 | 20220510005 | 5 | Schedule & 404 Permit | Could the Department please provide the designers schedule and the Corp 404 permit? | The design schedule and 404 permit can be found at the following location: https://wisdot.box.com/s/wmi17cof64hprp2izk3r74l17p8uo51e or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-04-27 14:07 | 2022-04-28 10:02
20220510 | 20220510005 | 5 | Seismic Monitoring/Pre- & Post Construction Surveys | Considering the close proximity to existing residences to the proposed structure, could bid items be added to account for seismic monitoring during construction operations along with pre and post construction surveys? | Based on the proximity of the existing residences and the proposed structure, the Department has deemed vibration monitoring during construction operations to be unnecessary. The Contractor may elect to perform vibration monitoring to meet Section 107 of the Standard Specification at no cost to the Department. | Jill Fehrman | 3 | 2022-05-05 09:27 | 2022-05-09 10:49
20220510 | 20220510007 | 7 | Bid Items | Good morning, Could you please explain the inclusion of line items #0016, Field office type B, #0036, Construction staking resurfacing, & #0038, Construction staking supplemental control? For such a short project with operations that will, in essence, be completed in 20 days or less, it would seem that having the expense of a field office on a project such as this would be a cost that could be avoided. In looking at the staking items, this project, as far as I can tell, does not involve any resurfacing or other work that would require either of the items included. Will an addendum be issued to remove these items? Thank you. | The field office is being included to proved field staff a location to coordinate with contractors, staff and completed project documentation. item #0036, Construction Staking Resurfacing Reference and item #0038, Construction Staking Supplemental Control are needed to provide stationing to accurately mark and reference work. | Jill Fehrman | 1 | 2022-05-03 07:50 | 2022-05-09 12:08
20220510 | 20220510008 | 8 | Quantities | Are the provided quantities for Base Aggregate 3/4" and Water accurate? | After reviewing the estimate and quantities, there was a mistake with the Base Aggregate Dense 3/4-Inch and the Water quantities. Below are the revised quantity estimates for the corresponding items. Base Aggregate Dense 3/4-Inch: 4,554 Tons Water: 248 MGAL An Addenda will be submitted to adjust these quantities. | Mike Coleman | 1 | 2022-04-25 11:40 | 2022-04-26 06:56
20220510 | 20220510009 | 9 | R-66-62 | There are no bid items to capture all of the work associated with the R-66-62 wall. Per the Standard Spec, roadside retaining walls should have specific bid items to pay for all aspects of completing the wall. Is it to be assumed that any removals, excavation, backfill, and restoration are incidental to the Concrete Barrier Type S56C item, or will the Department add items to capture these divisions of work? | Quantities for Common Excavation are shown on page 26 of the plan. | Jill Fehrman | 1 | 2022-05-04 09:34 | 2022-05-09 12:58
20220510 | 20220510010 | 10 | Plan/ Spec Discrepancies | The specials calls out the replacement of C-64-90 in the scope of work and the plan calls out in the estimated quantities 156 cy of Concrete Masonry Culvert, but the plan does not show that work. | An addendum will be issued to add the C-64-90 plan set to 1320-22-70, delete C-64-8 from 1320-22-70, and add C-64-8 to the 3180-00-77 plan set. The full size plan sheets can be found at the following location: https://wisdot.box.com/s/dug33lhtg6kwih4dbhzwo9lodia7ccc6 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-04-13 16:49 | 2022-04-21 09:15
20220510 | 20220510010 | 10 | Erosion Control Filter Bag | Please review the Specials Material and Construction section and compare it to the construction detail on page 7 of the plan. If the detail is what is needed, the Specials Material and Construction language doesn't match the detail. We're assuming a Type R or Type HR fabric or similar is needed. | Dewatering bag should be used for the settling basin application. | Mike Coleman | 2 | 2022-04-25 10:05 | 2022-04-29 10:35
20220510 | 20220510011 | 11 | SPV.0045.01 Portable Speed Trailer | What is the intended use for the Portable Speed Trailer? Typically these devices are not used on road closures. If this is to be used on the project, how many devices are needed and where are they to be placed? Thanks | The portable speed trailer is meant to be used on the detour route as needed based on complaints received for speeding vehicles on the detour route. Only one device is expected to be needed at a time. The location it will be placed is dependent on the location(s) of the complaints. | Mike Coleman | 1 | 2022-04-26 18:39 | 2022-04-27 07:31
20220510 | 20220510011 | 11 | Topsoil and Salvaged Topsoil | Section 4 of of Article 21 of the Special Provisions indicate specific requirements for the pH, organic matter, clay, silt, and sand/Gravel composition of the required topsoil. The required compositions are very rarely naturally occurring and this spec will require the manufacture and import of topsoil which will substantially increase the cost. Is this spec necessary for a primarily rural roundabout project in which the existing vegetation is already thriving with the native material? | Please see addendum no. 1 issued May 5, 2022. | Jill Fehrman | 2 | 2022-04-29 08:28 | 2022-05-09 12:34
20220510 | 20220510011 | 11 | Soil borings | Does the DOT have Soil borings that can be made available to the contractor for this project? | The link has been updated to link to the correct folder. The Soils Report can be found at the following location: https://wisdot.box.com/s/8vi2le2l7mrk8jlds1kdwxdtb5oedz5u or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-04-29 09:33 | 2022-05-02 10:28
20220510 | 20220510011 | 11 | Schedule | Would the state consider allowing the start date to be moved back towards a notice to proceed of closer to a 8-1-22 start, to allow contractors to catch up on the there current work load considering the wet spring and the delays due to materials. This later start could offer contractors the ability to offer more competitive bids. | The contract includes an anticipated start date of July 5, 2022, unless otherwise approved by the engineer. The Department expectation is that start notice will be issued to preclude risk of late season construction impacts, following review and acceptance of contractor schedule. | Jill Fehrman | 4 | 2022-05-05 09:36 | 2022-05-05 16:30
20220510 | 20220510012 | 12 | Bridge Traffic Control | Sheet 27 outlines how to address drop off and hazard protection. With proposed bridge joint replacement creating a drop off hazard through the bridge deck, typically to meet safety standards temporary precast barrier is utilized. Staging plans do not appear to allow for space to utilize temporary precast barrier and creates a situation that hazard or new concrete can be kept protected. Additionally, notes state not to store materials or equipment within 8â€™ of traveled way but stage 1 is not wide enough to achieve this across the bridge decks (i.e. once joints are out or for painting equipment). Please advise if temp concrete barrier can be added to the traffic control at bridge staging. |  |  | 1 | 2022-05-03 14:47
20220510 | 20220510012 | 12 | AT&T Contact | Article 7 states that an AT&T MH will be required to be adjusted. No contact information is provided for AT&T. Please provided contact information and location of AT&T adjustment. It can not be determined if this adjustment is located in an area that will be under a long term lane closure or under a nightly closure. | The AT&T contact can be found on the general notes sheet (page 2) of the plan set. | Jill Fehrman | 2 | 2022-05-03 14:48 | 2022-05-04 15:36
20220510 | 20220510012 | 12 | Design Schedule | Please provide design schedule for anticipated work to show how DOT anticipated/calculated working days for interim completion dates. It does not seem feasible to complete proposed structure work, especially structure painting, close to prescribed working days. | The design schedule for this project can be found in the Supplemental information file at the following link: https://wisdot.box.com/s/f41zqqpw1vlfgymevej7fcf3b2s9blvu The supplemental information for this proposal may also be accessed directly from the May Bid Letting page. | Jill Fehrman | 3 | 2022-05-03 14:50 | 2022-05-04 15:47
20220510 | 20220510012 | 12 | Menomonee River Pkwy Traffic | Traffic control will be required on Menomonee River Pkwy to perform expansion joint replacement. Please allow for shoulder closures or similar. |  |  | 4 | 2022-05-03 14:54
20220510 | 20220510015 | 15 | RPL Requirement | The closest point of the RR ROW to any work on this project is approximately 275'. Is railroad protective liability insurance coverage required? If yes, can the Department please provide an explanation as to why it is required? | Due to proximity of traffic control to railroad crossing DOT #692245A, railroad insurance is required on the project. | Jill Fehrman | 1 | 2022-05-03 15:00 | 2022-05-04 16:17
20220510 | 20220510015 | 15 | Intermediate Parapet - Reinforcing Steel | Can the rebar for the intermediate parapet (the one in the middle of the deck) be drilled in and epoxied after the deck pour? If not can bar couplers be used to avoid having rebar sticking up vertically out of the deck? This would allow for a more efficient and cost effective single deck pour resulting in better over quality. | An alternative detail for drilled/epoxied anchors has been utilized in the past. A pdf of the detail has been placed The design schedule can be found at the following location: https://wisdot.box.com/s/8xuy8n2zd527gw26ptl30lfbx7d8cmd2 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Jill Fehrman | 2 | 2022-05-04 22:34 | 2022-05-09 12:52
20220510 | 20220510016 | 16 | Repainting Decorative Railing | The repainting decorative railing bid item is 9EA and is shown as 3EA at the west abutment, east abutment and superstructure. Is it the Departments intent to remove the entire length of the railing on the bridge from all 3 parapets and have it repainted and then reinstalled? Also who is going to determine which sections need repair and how many repairs are there on the railing? | Question 1: As indicated on SPV.0060.02 â€œrepainting decorative Steel Railingâ€, description, the intent is to remove, clean , repaint and reinstall all railings (9EA). Question 2: As indicated on SPV.0060.01 â€œdecorative Railing repairâ€, description, the damaged section (s) to be repaired shall be identified and approved for repair by the project engineer in the field. One 11-foot section was identified for a repair during the initial field survey. | Jill Fehrman | 1 | 2022-05-04 18:28 | 2022-05-05 16:25
20220510 | 20220510016 | 16 | Parapet Removal | Please advise where the removal of the existing parapet is paid under for the SE corner of the bridge. | Partial removal of existing parapet at SE corner of the bridge is incidental to bid item 502.01 â€œConcrete Masonry Bridgesâ€ | Jill Fehrman | 2 | 2022-05-04 18:54 | 2022-05-05 16:26
20220510 | 20220510017 | 17 | ASPHALTIC SURFACE PATCHING | Is the removal for the asphaltic surface patching paid under the main milling item "removing asphaltic surface milling"? Typically I have seen this done under a separate pay item; i.e. removing distressed pavement or asphaltic base patching; and just wanted to clarify the intent. Thanks, Dom |  |  | 1 | 2022-04-21 13:15
20220510 | 20220510017 | 17 | SPV.0090.01 Straw Wattles | The Materials section of this SPV states, 'Furnish straw wattles meetin the requirements of the PAL listing.' When using this website, 'https://wisconsindot.gov/Documents/doing-bus/eng-consultants/cnslt-rsrces/tools/pal/pal.pdf', we can't find a listing for straw wattles. Is the intent of plan to use '628.7504 Temporary Ditch Checks' that are filled with straw only or is there a site that lists these requirements? | Yes when utilizing the Wisconsin Erosion Control Product Acceptability List (PAL), look under Temporary Ditch Checks â€“ Bid Item 628.7504. There are 20 approved items. This is the list: American Excelsior Curlex 12 inch Sediment Log American Excelsior Curlex 20 inch Sediment Log American Excelsior AEC Premier 12 inch Wattle American Excelsior AEC Premier 20 inch Wattle American Excelsior Curlex Bloc American Excelsior Curlex Bloc HD Eroâ€Guard EG Straw Log12 Erosion Control Blanket.com Stenlog 12 Erosion Tech Nature Log Excelsior WTL10 ( 12") Erosion Tech Nature Log Excelsior WTL13 (20") Erosion Tech Nature Log WTL8 (12" straw) Erosion Tech Nature Log WTL9 (20" straw) Filtrexx Ditch Chexx Ro Lanka Bioâ€D Silt Check Tensar North American Green Sedimax â€ SW12 Triangular Silt Dike Triangular Silt Dike Western Excelsior EXCEL Straw Log 12" Western Excelsior EXCEL Straw Log 18" Western Excelsior EXCEL Straw Log 20" Western Excelsior Aspen Xcel Excelsior Log Any of these items whether it is a sediment log, a wattle, a Nature Log (excelsior or straw), straw log or excelsior log can be used as long as it does not need entrenchment for installation. This item will be paid for by the linear foot acceptably installed. | Mike Coleman | 2 | 2022-04-25 15:02 | 2022-04-27 06:00
20220510 | 20220510018 | 18 | Cleaning Culvert Pipes | Are you able to provide the pipe sizes and lengths of pipe for this quantity of culvert pipe cleanings? | The pipe lengths can be scaled on the plan, and for most of the cleaning culvert pipe locations the size/material is shown in the existing topo on the plan detail sheets. As-built plans can be found at the following location: https://wisdot.box.com/s/sz1g8lvvgi6ufcdvzi6ag9wolodzo3en or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-04-25 15:46 | 2022-04-27 12:00
20220510 | 20220510018 | 18 | Lane Closure Language | The staging for this project shows long-term lane closures to be setup, including a significant amount of temporary pavement markings to be applied in these lane closures. However, in the Traffic article of the Special Provisions there is a line that states: "If no work is taking place within a closed lane segment for 48-hours, except for the curing of concrete, remove the lane closure as directed by the engineer." Can this line be removed from the Special Provisions, or should the contractor plan on opening up lane closures over the weekend if there isn't concrete curing? | Please bid the project as shown in the plans, with wood posts and to be completed by 11/4/22 as stated in the contract documents. | Jill Fehrman | 2 | 2022-05-04 09:05 | 2022-05-09 11:12
20220510 | 20220510021 | 21 | Quantities | Can the Department confirm the quantities provided for Base Aggregate Dense 3/4" and Water? | Thereâ€™s an error for both quantities. An addendum will be issued. | Mike Coleman | 1 | 2022-04-19 13:20 | 2022-04-20 12:38
20220510 | 20220510021 | 21 | Schedule | Could the department provide the design schedule for this project? | An updated design schedule has been provided. The design schedule can be found at the following location: https://wisdot.box.com/s/rkr6j27t5mr8mxrdf6l6njvjug3p4h0m or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-04-26 14:10 | 2022-04-28 06:35
20220510 | 20220510021 | 21 | 643.1205.S Basic Queue System | The Miscellaneous Quantities table for item 643.1205.S shows (6) Flashing Beacon Signs used in each direction. Are these meant to be placed on the right shoulder, one placed each mile for 6 miles; or are they meant to be placed as three pairs on both shoulders? Thanks | It should be 3 per direction for a total of 6. Follow SDD 15D12-09d for guidance. | Mike Coleman | 3 | 2022-04-29 16:11 | 2022-05-02 10:37
20220510 | 20220510021 | 21 | 643.1205.S Basic Queue System | Will item 643.1205.S Basic Traffic Queue Warning System be placed in a single, stationary location for the duration of the project (at the project limits)? Or will it need to be moved in conjunction with the location of the lane closure each day? | It is required to be moved in conjunction with wherever the initial lane closure taper is for each direction of travel on I-41. Otherwise the system will not work appropriately as the sensors and FMS trailers wonâ€™t be picking up the queues starting at the lane closure point. With this being 6.8 miles in length, the basic QWS will need to move locations at least twice throughout the project, as there is a 5 mile lane closure length restriction in place as well. | Mike Coleman | 4 | 2022-04-29 16:13 | 2022-05-02 09:32
20220510 | 20220510021 | 21 | Temporary Pavement Markings | Should item 649.0105 Temporary Marking Line Paint 4-Inch be added to this project for temporary markings placed on the milled surfaces? Typically this item has been used on similar projects for markings on milled surfaces. Thanks | Misspoke on the previous response. A region SPV will NOT be include as we do not have type 2 or CL rumbles. Temp paint should be used for applications prior to final epoxy. | Mike Coleman | 5 | 2022-04-29 16:16 | 2022-05-02 10:40
20220510 | 20220510021 | 21 | Cable Barrier | In talking to cable barrier suppliers, there is an industry wide shortage on wire cable. Cable barrier lead time is sometime in 2023. How will the department handle this shortage in regards to completion date, liquidated damages, and allowance for an extraordinary delay? | The department has been in contact with industry and is not aware of any conditions that would meet Standard Specification 108.10.2. Liquidated damages will be assessed per contract and any efforts to mitigate the liquidated damages will be the responsibility of the contractor. Please bid accordingly. | Jill Fehrman | 6 | 2022-05-04 10:12 | 2022-05-05 14:21
20220510 | 20220510021 | 21 | Restoration |  |  |  | 7 | 2022-05-04 10:13
20220510 | 20220510021 | 21 | Restoration | Project shows 11,333 SY of Salvaged Topsoil with 207,293 SY of Erosion Mat. Please clarify intent and confirm quantities. | The quantity error will be corrected in an addendum. | Jill Fehrman | 8 | 2022-05-04 10:20 | 2022-05-05 13:58
20220510 | 20220510021 | 21 | Milled Surface Open to Traffic | Per the specials on sheet 5 under milled surfaces open to traffic, would the department re-look at the scope of work for the four lane highway and revise the language to fit the scope of work? | An upcoming addenda will address this issue. | Jill Fehrman | 9 | 2022-05-04 15:37 | 2022-05-05 14:03
20220510 | 20220510022 | 22 | Specials #4 , Traffic | The specials under traffic state that the maximum length of the work zone is 500 feet. Contractorâ€™s scope is milling rumbles and clean up with a pick up broom in a mobile train that travels upward of one mile per hour, as such will the department change this to be a one mile length closure to allow for mobile train, the safety of the crews and the traveling public. | An addenda will be issued to modify the special provision to state that the maximum allowable length of the work zone is 1 mile. | Mike Coleman | 1 | 2022-05-02 13:23 | 2022-05-04 06:01
20220510 | 20220510024 | 24 | Asphaltic Surface for Pipe Patching | With the pipe patching occurring prior to mainline paving could the patching under the 3 MT and 4 MT items be put under an Asphaltic Surface Bid Item with the requirement that the mix used be an MT? | An addendum will be issued to include Asphaltic Surface requiring MT mix for pipe patches. | Mike Coleman | 1 | 2022-04-19 15:00 | 2022-04-21 09:17
20220510 | 20220510024 | 24 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | An addendum will be issued for pipe material concern. | Mike Coleman | 2 | 2022-04-21 11:10 | 2022-04-27 06:30
20220510 | 20220510024 | 24 | 100+00-210+97 surface pavement markings | Good morning, If I am reading this correctly, based on plan sheet 50, your plan is to have temporary epoxy markings on the surface prior to the rumble strips being installed but no temporary or same day markings for the surface where there are not going to be rumble strips. Typically, if that is the case, there would be a same day epoxy item for the area (100+00-210+97) that does not get rumble strips. While there are regular epoxy (not same day) markings figured, there will be, with the items available, a gap between upper layer surfacing and final marking installation where there will be no markings on the surface in the area that does not get rumble strips. Will an addendum be issued to add a same day bid item to cover this 2.1 mile area? Thank you. | An addendum will be issued for pavement marking same day. | Mike Coleman | 3 | 2022-04-26 07:00 | 2022-04-27 07:32
20220510 | 20220510024 | 24 | Design Schedule | Could the department post the schedule developed during the design? | The design schedule can be found at the following location: https://wisdot.box.com/s/jbeind8n5ixhtxhz0thtdc236840rykq or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2022-04-26 08:56 | 2022-04-27 07:08
20220510 | 20220510024 | 24 | Even Cross Section Profile | Under the "milling and overlay" section of the special provisions it says an even cross section profile is required at the end of each day. If the contractor utilizes a notched wedge to eliminate the vertical longitudinal joint while paving as required by the standard specification would they be required to sit back and match up lanes each day? | An addendum will be issued to address this issue. | Jill Fehrman | 5 | 2022-05-02 19:23 | 2022-05-04 16:00
20220510 | 20220510024 | 24 | Flagging Operations | The specials only allow for one 2 mile flagging operation at a time on STH 147. It seems unfeasible to construct a 10+ mile project in the given working days with only being allowed one closure at a time. Would the department consider allowing multiple closures if an adequate gap was provided between them? | An addendum will be issued to address this issue. | Jill Fehrman | 6 | 2022-05-02 19:35 | 2022-05-04 16:04
20220510 | 20220510024 | 24 | Base Patching Asphaltic | Would the department consider changing the 16 TN of Base Patching Asphaltic to Asphalt Surface. The base patching item requires an uncommon 25 MM aggregate size which is usually not needed or wanted. | An addendum will be issued to address this issue. | Jill Fehrman | 7 | 2022-05-02 19:44 | 2022-05-04 16:06
20220510 | 20220510024 | 24 | Project Working Days/ Completion Date | With the need to start the box culvert July 5th, would the department consider adding 15 working days to provide more flexibility to complete milling and paving operations after the box culvert and pipe work is finished. | Due to local commitments and traffic volumes late in the year the contract schedule cannot be modified. | Jill Fehrman | 8 | 2022-05-04 15:53 | 2022-05-05 15:07
20220510 | 20220510026 | 26 | PWL mix | In the PWL mix table it has the lower layer for the 2' widening, which is a 4MT, under incentive air voids HMA. This should be considered to be changed to QMP testing as to run a 750 test strip will take all day to get out as this would be the first paving operation with the 4MT and there wont be a chance to do a test strip prior to this. There is also a possiblity this asphalt would come from a different location than the rest of the PWL 4MT if the schedule and timing calls for it. | An addendum will be issued to correct this. | Mike Coleman | 1 | 2022-04-27 17:31 | 2022-04-29 10:31
20220510 | 20220510026 | 26 | R / R Insurance | Where does this project conflict with the rail road? Why is there R /R insurance required? | The railroad insurance is required due to the width restriction signing that will need to be placed near the intersection of STH 97 and STH 13. See page 87 of the plan. | Mike Coleman | 2 | 2022-05-02 11:21 | 2022-05-03 07:24
20220510 | 20220510026 | 26 | Concrete Masonry Bridge Quantity | Please double check the quantity for Concrete, Masonry Bridge item. Bid quantity seems high. Provide breakdown if found to be correct (abutments and superstructure). | A recheck of the concrete masonry bridges quantity indicates that the estimated quantity is high. Per Standard Specification 502.4.2(1) The department will measure the Concrete Masonry Bridges bid items by the cubic yard acceptably completed. | Jill Fehrman | 3 | 2022-05-05 14:05 | 2022-05-09 10:58
20220510 | 20220510026 | 26 | Concrete Masonry Bridge Quantity | Will an addendum be issued to correct the quantity? |  |  | 4 | 2022-05-09 11:22
20220510 | 20220510027 | 27 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and/or IV? | An addendum has been issued to address this. | Mike Coleman | 1 | 2022-04-21 11:15 | 2022-05-04 05:55
20220510 | 20220510027 | 27 | Typical Sections | The typical sections call out 4 inches of asphalt pavement on the shoulders. Can the department clarify the lift thicknesses and HMA type for the shoulders? | Match the shoulders with the top two lift thicknesses and mixes of the adjacent driving lane for STH 34. Match the shoulders with the mainline for CTH DB/Old 51 as well. Shoulders 4.25-inches of HMA (2-inch 4 HT 58-28 H over 2.25-inch 3 HT 58-28 S) An addendum will be issued to clarify | Mike Coleman | 2 | 2022-04-21 12:54 | 2022-04-25 11:57
20220510 | 20220510027 | 27 | Asphalt Quantity | Can the department verify the HMA quantities for the project? It appears that the HMA quantities are missing for station 8+50NB-10+00NB are missing. | The quantity is correct as provided however the stationing wasnâ€™t updated in the summary. An addendum will be issued to correct this. | Mike Coleman | 3 | 2022-04-21 12:59 | 2022-04-25 11:54
20220510 | 20220510028 | 28 | Specials #12 | The miscellaneous quantities on pages 16 & 17 shows undistributed quantities of 900 CY of Excavation (cut) under Earthworks and 1,120 ton of Breaker Run both for Yielding Subgrade Area. With those items being included should #12 in the Specials Preparing Foundation for Asphaltic Paving be Removed. | The item Prepare Foundation for Asphaltic Paving is needed on this project to restore, correct, or strengthen the pavement foundation to a condition suitable for construction. Subsection 211.5, â€œPaymentâ€ section of the Prepare Foundation for Asphaltic Paving item notes: (4) The department will pay separately for the following work under the pertinent contract bid items, or absent the pertinent items, as extra work: - Excavating and backfilling areas of yielding or unstable materials. The intention of the special provision is to direct the contractor to use 10:1 slopes in areas of yielding or unstable materials to minimize frost movement and avoid trapping water. | Mike Coleman | 1 | 2022-05-02 10:40 | 2022-05-03 07:25
20220510 | 20220510028 | 28 | 1 1/4 Base Aggregate Dense Quantity | The typical section on Sheet 4 for stations 170+69-187+86 calls for 12" of Base Aggregate Dense 1 1/4" under the proposed shoulder widening. The base course tabulation on Sheet 17 does include any quantity of 1 1/4" in this area. Will the Department please clarify? | An upcoming addendum will address this issue. | Jill Fehrman | 2 | 2022-05-04 19:57 | 2022-05-06 07:45
20220510 | 20220510030 | 30 | Design Schedule & Soil Geotechnical Report | Please provide the Design Schedule & Soil Geotechnical Report. | A soils report was not completed for this job. Soil boring for the cable barrier are included in the plan. The design schedule can be found at the following location: https://wisdot.box.com/s/6deglws79szdpl9umxs2f9j3eo874lk2 or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-04-18 11:56 | 2022-04-20 07:30
20220510 | 20220510030 | 30 | Design Conversion factors used (tons/cy) | What are the design conversion factors used (tons/cy) for these item of work: Backfill Granular Grade 2 and Base Aggregate Dense 3/4" and Base Aggregate Dense 1-1/4"? | Backfill Granular Grade 2 = 1.4 ton/cy Base Aggregate Dense ï¿½â€ = 2.0 ton/cy Base Aggregate Dense 1-1/4â€ = 2.0 ton/cy | Mike Coleman | 2 | 2022-04-18 12:02 | 2022-04-20 07:35
20220510 | 20220510030 | 30 | 1-1/4" Base Course Under Shoulders | Currently the Finished Typical Sections on Mainline designate 3/4" Base Course under the Asphalt Shoulders, can 1-1/4" Base Course be use instead like most other projects in the State? | Per standard spec 305.2.2.1 (2): Unless the plans or specifications specify otherwise: 1. Use 1 1/4-Inch in base course layers. Always use 1 1/4-inch in the top 4 inches of base. The contractor may substitute 3-inch for 1 1/4-inch in lower base zones including material underlying the shoulder. 2. Use 3/4-inch in shoulders. Always use 3/4-inch to match the thickness of the paved shoulder in the unpaved portion of the shoulder and on exposed shoulder foreslopes. The contractor may substitute 1 1/4-inch for 3/4-inch elsewhere in shoulders and shoulder foreslopes. If using 1 1/4-inch, limit the allowable reclaimed asphalt content to 50 percent or less. | Mike Coleman | 3 | 2022-04-18 13:37 | 2022-04-20 07:26
20220510 | 20220510030 | 30 | design schedule | could the design schedule for proposal 330 please be provided. | The design schedule can be found at the following location: https://wisdot.box.com/s/6deglws79szdpl9umxs2f9j3eo874lk2 or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2022-04-18 16:32 | 2022-04-20 07:31
20220510 | 20220510030 | 30 | Answer to Question #3 - 1-1/4" Base Course Under Shoulders | The plans show 3/4" Base Aggregate under the Asphalt Shoulder. So according to the previous answer to question #3, the contractor must use 3/4" Base under the Asphalt Shoulder because the plan shows that, correct? No 1-1/4" Base will be allowed under the Asphalt Shoulder? If this is the case, why? All other projects in the area use 1-1/4" Base under the shoulders and the plans always specify 1-1/4" under the Asphalt Shoulders. | An addendum will be issued to correct the typical sections. | Mike Coleman | 5 | 2022-04-20 16:20 | 2022-04-25 11:50
20220510 | 20220510030 | 30 | Earthwork Summary vs Earthwork Data Sheet | There are numerous variances between the Earthwork Summary vs the Earthwork Data Sheets, please confirm which one is correct. Also the plan is missing Earthwork Data sheets for 231+52 - 239+00 IH 94 EB EXISTING, 6+52 - 28+64 SOUTHWEST LOOP and 73+50 - 84+00 IH 94 EB EXISTING,RT. | The earthwork summary is correct and missing sheets will be added in an upcoming addendum. | Mike Coleman | 6 | 2022-04-22 15:30 | 2022-04-29 10:36
20220510 | 20220510030 | 30 | Removing Concrete Pavement | It appears Removing Concrete Pavement quantities on STH 312 are 9 times higher than they should be. | Removing Concrete Pavement on STH 312 was not converted from S.F. to SY. An addendum will be issued. | Mike Coleman | 7 | 2022-04-25 17:14 | 2022-04-27 06:31
20220510 | 20220510030 | 30 | REMOVING CONCRETE SURFACE PARTIAL DEPTH | What is the average depth of the REMOVING CONCRETE SURFACE PARTIAL DEPTH pay item? | The average depth of Removing Concrete Surface Partial Depth is 3.5 inches, which is the depth of the asphalt milling. An additional detail will be added in an upcoming addenda. | Mike Coleman | 8 | 2022-04-26 09:20 | 2022-04-29 10:33
20220510 | 20220510030 | 30 | schedule | the design schedule seems overly aggressive to the point it is unreasonable. production rates of excavation at 9000 cy/day, Base course at 7000 ton/day for starters. this might work out on a reconstruct that can be accomplished with off road haul equipment, multiple spreads and short hauls but certainly not this type of work. also the design schedule shows 40 WD to complete stage 2, with these inflated productions, yet the contract is only allowing 42 calendar days. Stage 3 work shows 48 WD starting March 1st yet the contract states work can start no sooner than March 28th which allows 58 days at best. if we have a spring next year anything close to this year it is unbuildable in the timeframes allowed. it would be great if someone could please review/clarify the logic with these interim dates as there are significant LD's, $50,000 / CD, associated with the interim completion dates on this project. | The schedule is not contractual. Production rates are an estimate as they are controlled by the contractors means and methods. The prosecution and progress provides the time frame and work needed to be done. The addendum will include a revised prosecution and progress. 2023 interim damages are $10,000. | Mike Coleman | 9 | 2022-04-26 14:49 | 2022-05-04 05:59
20220510 | 20220510030 | 30 | Stage 2 & Stage 3 Interim Complete Dates | Instead of the Interim Completion Date language for Stage 2 & 3 stating all work for those respective Stages must be done by those major traffic weekends, can they state that all work must be completed to safety allow 2-Lanes of traffic in each direction for those weekends and all remaining work can be completed under allowable lane closures during the timeframes stated in the traffic section? | This will be addressed in an upcoming addendum. The prosecution and progress will be modified to require the concrete pavement and base agg shoulders to be completed, at a minimum, so that all four lanes of Interstate traffic can be safely opened to traffic by the Interim Completion Date. | Mike Coleman | 10 | 2022-04-27 09:10 | 2022-04-29 10:15
20220510 | 20220510030 | 30 | Answer to Question #6 - Earthwork Summary vs Data Sheets | If the Earthwork Summary is correct then please correct these earthwork Data sheets. 1. -25+08 - -24+92 IH 94 EB EXISTING - 15 CY Summary vs 421 CY Data 2. 29+92 - 30+08 IH 94 EB EXISTING - 17 CY Summary vs 451 CY Data 3. 49+00 - 66+00 IH 94 WB EXISTING - 1,310 CY Summary vs 1,071 CY Data 4. 49+00 - 196+00 IH 94 EB EXISTING - 59,250 CY Summary vs 52,570 CY Data 5. 16+25 - 23+25 SOUTHEAST RAMP - 1,720 CY Summary vs 2,902 Cy Data 6. 16+00 20+00 SW RAMP EASTBOUND - 550 CY Summary vs 318 CY Data 7. 60+41 - 68+65 SW RAMP - STAGE 3A SW'S3A' - 1,400 CY Summary vs 1,197 CY Data 8. 0+50 - 16+00 SW RAMP EASTBOUND - 2,250 CY Summary vs 510 CY Data 9. 61+50 - 71+00 SE RAMP - STAGE 2A SE'S2A' - 300 CY Summary vs 1,074 CY Data 10. 73+50 - 84+00 IH 94 EB EXISTING, RT - 1,000 CY Summary vs 654 CY Data | The earthwork summary sheets are correct. Updated earthwork data sheets will be provided at the Pre-Construction Meeting. | Jill Fehrman | 11 | 2022-04-29 11:43 | 2022-05-09 11:48
20220510 | 20220510030 | 30 | Answer to Question #8 - Removing Concrete Surface Partial Depth is 3.5 inches | So according to the existing typical sections within the Removing Concrete Surface Partial Depth work areas, there is a 6-8" Asphalt overlay on top of the concrete pavement. The new proposed section is Mill 3.5" off of Asphalt (under the Milling Asphalt Item) and repave, so how is the Removing Concrete Surface Partial Depth Item 3.5" into the concrete also? There is still another 2.5-5.5" of asphalt on top of the concrete, How does that come off? And 3.5" of milling in concrete seems like a lot and more than likely the mill will hit steel causing damage to the mill. Are the existing topicals wrong? Is the work area wrong? Is the Concrete Surface Partial Depth Item needed. Please clarify this. | In the mill and pave section, the existing pavement, in the concrete repair areas, will be removed under the Concrete Pavement Repair Non-Doweled Special item. This item compensates for removing the pavement in the repair area and replacing it with concrete to match the surface of the existing asphalt pavement. Then when the pavement is milled, prior to paving, it will be asphalt milled in the asphalt pavement areas and paid as Removing Concrete Surface Partial Depth in these concrete repair areas. There will be a detail and bid items included in an upcoming addendum. | Mike Coleman | 12 | 2022-04-29 13:21 | 2022-05-03 07:26
20220510 | 20220510030 | 30 | Sign Supports Structural Steel HS | Could the department please provide the information table for the Sign Supports Structural Steel HS? It is normally located in the Misc quantities section and i am not finding it. | Item will be added to the Misc. Quantities in an addendum. | Mike Coleman | 13 | 2022-05-03 08:50 | 2022-05-04 06:00
20220510 | 20220510030 | 30 | Stages 2 and 3 Lane Closures | What is the intent of 120 total lane closures in Stages 2 and 3? Traffic will already be in bi-directional configurations in these stages, so additional lanes can't be taken in this time. Does the department intend on paying a Lane Closure item for each calendar day that traffic is in the bi-directional setup? The overall item quantity is 204, so this possibly inflates the item by almost 60%. Thanks | This will be addressed in an upcoming addendum. | Jill Fehrman | 14 | 2022-05-03 11:26 | 2022-05-04 16:11
20220510 | 20220510030 | 30 | Paved Shoulder Width | Within the Concrete Patching Section of this job 194+00 to 304+00 the drawing on page 14 shows a bold pavement layer at 6' with a note of paved shoulder 4' and the quantities description within the location column on Page 288 call out for 4' shoulder - Please confirm which width the department wants. | This will be addressed in an upcoming addendum. | Jill Fehrman | 15 | 2022-05-04 07:18 | 2022-05-04 16:13
20220510 | 20220510030 | 30 | 4MT Quantity | On page 291 of the plans within the Hma 4MT 58-34S table there seems to be some busts in quantities. The second and forth line show the same quantity for the driving lane and passing lane tons. Also the quantity within stations 304+27 to 347+43 shown as 26,28,25,28 tons are off I believe by 2600 plus tons. Please confirm this. | An upcoming addendum will address this issue. | Jill Fehrman | 16 | 2022-05-04 07:27 | 2022-05-05 13:36
20220510 | 20220510030 | 30 | 3HT 58-34S Quantities | On Page 292 the table for the 3HT 58-34S from Station 304.. to 346.. the quantities are way overstate I believe by 2300 plus tons. Please confirm. | An upcoming addendum will address this issue. | Jill Fehrman | 17 | 2022-05-04 07:31 | 2022-05-05 13:36
20220510 | 20220510030 | 30 | 4HT 58-34V Quantities | On page 292 within the table for 4HT 58-34V the quantities for the 304.. to 346.. show shoulder upper layer. I believe per detail on Page 10 that this shoulder is showed using a 4MT 58-34S 10 foot wide. Please confirm if this quantity should be removed. | The 4HT 58-34V quantities are for the median shoulder. The 4MT 58-34S is for the outside shoulder. | Jill Fehrman | 18 | 2022-05-04 07:37 | 2022-05-04 17:26
20220510 | 20220510030 | 30 | Cold Weather Paving - Time Frames for work completion | Wtih the time frames of post 9/6/2022 and Pre 5/25/2023 the department may want to consider a cold weather paving item. The work required to be completed prior to 5/25 2023 will be very difficult if we have a spring like the one we are currently having. Would the department consider moving this deadline for work within 2023. | An upcoming addendum will address this issue. | Jill Fehrman | 19 | 2022-05-04 07:43 | 2022-05-05 13:37
20220510 | 20220510030 | 30 | Bored and Jacked Storm Sewer | I am not seeing a pipe profile for the upstream half of proposed storm sewer 162+30 - 36inch, or a profile at all for proposed storm sewer 131+25 - 36inch. | An upcoming addendum will address this issue. | Jill Fehrman | 20 | 2022-05-04 09:33 | 2022-05-05 13:37
20220510 | 20220510030 | 30 | Bored and Jacked Storm Sewer 131+25 | Misc quantities on sheet 329 says the Special 02. Bore and Jack Storm Sewer Class III 36inch at station 131+25EB is 136 LF. On the plan and profile sheet 355 is lists this pipe as being 155 LF. Please advise if this jack and bore should be 136' or 155'. The pipe as the same station but WB is also listed and shown to be 155 LF. | The pipe length is 136 LF. | Jill Fehrman | 21 | 2022-05-04 09:37 | 2022-05-05 13:34
20220510 | 20220510030 | 30 | Asphaltic Surface Temporary | Please confirm the WDOT Asphaltic Surface Temporary Staging Time frames. On plan Sheets 293 the temp staging calls out for 2A/2B - I do not believe this represents the special provisions Stage 2 but should be considered Stage one requiring this work to be completed prior to 9/6/22 correct? The staging work shown for the asphaltic surface temporary in Stage 3A/B/C on 293 of the plans should be completed with stage 2A/2B when possible prior to 9/6/22 or after the October 18,2022 date correct? Stage 3 will require us to tie temporary asphalt into the new concrete slab thus this work will be very late in the year after October 18th 2022. With work needed to be completed for the temp after this date the 10/9/22 winter suspension will need to be moved correct? | Please refer to Addendum #1 for the revised Prosecution and Progress for staging. Temporary widenings and crossovers need to be constructed to complete stage work. | Jill Fehrman | 22 | 2022-05-05 06:46 | 2022-05-06 11:13
20220510 | 20220510030 | 30 | Structures S-18-121 and 122 | Where and what are sign structures S-18-121 and 122? Are those different names for the two temporary structures 0001 and 0002? Does the removal items just pay for removing the pads that need to be built for the placement of the footing blocks? | Structures S-18-121 and 122 were replaced with the temporary Structures 0001 and 0002. Addendum #3 will remove Sign Structures S-18-121 and 122. | Jill Fehrman | 23 | 2022-05-05 06:49 | 2022-05-06 11:11
20220510 | 20220510030 | 30 | Paving adjacent to New Concrete Slab/Asphaltic Surface Temp | Will the final 3MT/4MT paved shoulders be installed next to the new concrete slab or will the Asphaltic Surface Temp Pavement be installed next to the new slab in areas where the crossovers/tie in's for the staging are required. This area is shown within the hatched areas on sheets 131 and 132? Depending the answer this will determine the timing of having to either remove temp and placing finished shoulders or removing the temp that would butt up against the finished shoulders. | It is anticipated that the Asphaltic Surface Temp Pavement will be placed next to the new slab in areas where the crossovers/tie in's are required for staging. | Jill Fehrman | 24 | 2022-05-05 06:54 | 2022-05-09 11:50
20220510 | 20220510030 | 30 | Required Del Date for Temp Overhead Sign Structures | Our supplier is concerned about the ability to produce the two (2) temporary overhead signs structures in time. Are you able to provide the estimated date that these two (2) sign structures will be needed? | The temporary overhead sign structures will be needed by Labor Day 2022. | Jill Fehrman | 25 | 2022-05-05 12:37 | 2022-05-05 15:20
20220510 | 20220510030 | 30 | QMP Testing and Incentive Density | The plan shows all testing besides the HT Mix will be completed by department. I do not believe with only the HT mixes available for incentive will there be anyway to reach the $28,000 listed in the Quantities for incentive Density. Can you let me know how is is determined? |  |  | 26 | 2022-05-05 19:53
20220510 | 20220510030 | 30 | Earthwork Summary vs Earthwork Data Sheets | Addendum #1 added some Earthwork Data Sheets that don't match the Earthwork Summary just like the ones mentioned in Question #11 (which is not answered) 1. 73+50 - 84+00 IH 94 EB EXISTING, RT - 1,000 CY Summary vs 654 CY Data 2. 6+52 - 28+64 SOUTHWEST LOOP 4500 - 4,500 CY Summary vs 3,699 CY Data | The earthwork summary sheets are correct. Updated earthwork data sheets will be provided at the Pre-Construction Meeting. | Jill Fehrman | 27 | 2022-05-06 10:07 | 2022-05-09 11:48
20220510 | 20220510030 | 30 | 4MT - Shoulders | The shoulders on the concrete replacement section show a 3" lift of 4MT. The max upper layer thickness per 460 I believe is 2.5". Please confirm that 3" will be allowed. |  |  | 29 | 2022-05-06 11:45
20220510 | 20220510031 | 31 | Structure Plans | The structure plans seem to have been omitted from the plan set found on the Bid Letting Information Page. | This will be addressed in an upcoming addendum. | Jill Fehrman | 1 | 2022-05-04 14:31 | 2022-05-04 16:16
20220510 | 20220510036 | 36 | Shaping Shoulders | Shaping Shoulders item should be added to blade, shape and compact the existing shoulder aggregate, maintain drainage and incorporate the existing material into the new shoulder. | The Shaping Shoulders bid item will be added via addenda to the contract. | Mike Coleman | 1 | 2022-05-01 12:21 | 2022-05-02 10:36
20220510 | 20220510036 | 36 | Milling and Paving Time Restriction | Can the time restriction between milling and paving the first lift be removed or extended to 7-10 calendar days for scheduling efficiencies related to other work and test strip time? | The language in the â€œSTH 48 Millingâ€ section in the prosecution and progress will be revised via addenda. The timeframe will be extended to 10 calendar days. | Mike Coleman | 2 | 2022-05-01 12:23 | 2022-05-02 10:38
20220510 | 20220510036 | 36 | Shoulder Closure Restriction | Can the restriction on the shoulder closure at CTH V be removed or extended to 15 or more days? It would not seem closing the shoulder would not affect traffic for this short distance? Depending on the intent, cure time for the curb and gutter does not leave much time to complete the other work. | The language in the â€œCTH V Turn Laneâ€ section of the prosecution and progress will be revised via addenda. The timeframe allowed for CTH V turn lane shoulder closure will be extended to 21 calendar days. | Mike Coleman | 3 | 2022-05-01 12:27 | 2022-05-02 10:38
20220510 | 20220510036 | 36 | HMA Incentive Unit Price | Incentive items for Density, Air Voids and Longitudinal Joints should have unit prices of $1.00 in the bid proposal. The unit price is blank and fillable. Line numbers 142, 144 and 146. | A unit price of $1.00 for the DOL bid items on proposal lines 142, 144, & 146 via addenda. | Mike Coleman | 4 | 2022-05-01 12:28 | 2022-05-02 10:38
20220510 | 20220510036 | 36 | CTH V Lower HMA Layer | The CTH V intersection should be constructed before completing the mainline milling and paving. It would be best if the lower layer of asphalt would also be able to be placed before milling and paving the mainline. The PWL spec requires a test strip to be completed for volumetrics prior to placing more 5MT mix than what is allowed for the test strip. Could the lower layer only for the CTH V intersection and turn lane be placed as Asphaltic Surface with the requirement that the mix design meets a 5MT? If the 58-34V Asphalt Cement is required for the lower layer that could be required as well. | The preferred order of work operations would be the construction of the CTH V turn lane prior to milling and paving the mainline. The required HMA material of the lowest 2â€ of the turn lane can be paid for as â€œAsphaltic Surfaceâ€ to avoid complicating the mainline mill/paving operations and logical sequence of operations. Quantities will be adjusted for bid items 465.0105 & 460.6645 via addenda. The requirement of the lowest layer meeting the requirements of 5MT 58-34V will be noted in the miscellaneous quantities table. | Mike Coleman | 5 | 2022-05-01 12:31 | 2022-05-02 10:39
20220510 | 20220510038 | 38 | Temporary markings on surface layer | Good morning, Plan sheet 19 includes temporary paint quantities for the binder (lower) layer of asphalt after paving each day and also includes regular epoxy quantities for the upper layer. Typical projects would include same day epoxy quantities for the upper daily rather than regular epoxy quantities to be applied after all paving is completed. Will an addendum be issued to change the regular epoxy items to same day epoxy or does the department have another plan for guiding traffic through the project after paving is completed daily? Thank you. | Same Day Epoxy will be added via addendum. | Mike Coleman | 1 | 2022-04-27 08:37 | 2022-05-03 07:31
20220510 | 20220510039 | 39 | Can the design schedule be provided? |  | The design schedule can be found at the following location: https://wisdot.box.com/s/mmhoesu7ex9enquhlcjdg3nlb32l4t1m or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-04-07 07:36 | 2022-04-13 13:50
20220510 | 20220510039 | 39 | Prep Foundation for Asphaltic Shoulders | With the Prep Foundation for Asphaltic Shoulders on the project and according to the typicals we will be milling through all the asphalt because there is only 3" of existing HMA on the shoulders and then place 3.5" of HMA for the new shoulders. We have paved some shoulders on that same corridor here earlier SPN 1016-01-64 and that stated there was 3" of existing asphalt and when the contractor removed the material there was 5" plus of existing HMA. If there is 5" of mix are we going to just mill 3.5" out and place 3.5" of HMA? IF that is the case would the Prep Foundation for Asphaltic Shoulders be eliminated? This project also doesn't have an item for tack coat so if there is a milled surface left the tack item would need to be added. | Please bid as shown in the plans and specs. | Mike Coleman | 2 | 2022-04-28 11:29 | 2022-04-29 10:27
20220510 | 20220510039 | 39 | Existing Asphalt Shoulder Thickness & Proposed Typical Sections | Looking at the existing typicals it states that there is 3" of existing HMA paved with base underneath. We have paved shoulders on a project earlier this year SPN 1016-01-64 which is on the same corridor and that project also stated there was 3" of existing HMA on the shoulders, but when the contractor removed the existing HMA they discovered there was 5" of HMA. So would the plan be to remove the entire 5" of existing shoulder and place 5" of new HMA or would we remove 5" HMA and place 3.5" as spelled out on the proposed typicals? | Please bid as shown in the plans and specs. | Mike Coleman | 3 | 2022-04-28 11:35 | 2022-04-29 10:28
20220510 | 20220510039 | 39 | On Ramp Gore Areas | Is the plan to do the mill and repave the ramp gore areas as well or will those be skipped? There is nothing that states those would be done in the plan and there is no traffic control detail for the ramps being closed to do that work if those are intended to be done. | The ramp and gore areas will be not be done as part of this project. | Mike Coleman | 4 | 2022-04-28 11:44 | 2022-04-29 10:37
20220510 | 20220510039 | 39 | Asphalt Next to or Under Beam Guard | Being that this project has several stretches of beam guard along it and none are getting removed or adjusted throughout the project. What is the plan for the asphalt next to or underneath the beam guard? Would it be safe to say that the intent is to get as close as we can to the beam guard with the mill and the pave leave the rest or is it excepted to be removed completely and repaved? | The intent is to mill and pave as close to the beam guard as possible. | Mike Coleman | 5 | 2022-04-28 11:50 | 2022-04-29 10:29
20220510 | 20220510039 | 39 | Project Schedule | There have been some concerns voiced concerning the schedule on this project. Would the department consider allowing a Mid March or April 1 start in 2023? | The Department has reviewed the schedule and will remain with a completion date of November 4, 2022. | Jill Fehrman | 6 | 2022-05-02 17:44 | 2022-05-04 16:19
20220510 | 20220510039 | 39 | Woven Wire Fence | Would the Department allow installation of fence to be completed in the spring of 2023, it has been very difficult almost impossible to get a wood post supplier to even reach back out to the contractor on if they will have the amount of posts needed for this project? With the short time frame allotted for this project i feel there will be supply issues that would push the completion of the fence into the spring of 2023. | Please bid the project as shown in the plans with wood posts and to be completed by 11/4/22 as stated in the contract documents. | Jill Fehrman | 7 | 2022-05-04 11:07 | 2022-05-09 12:10
20220510 | 20220510039 | 39 | Fence post | Since wood post are in very short supply would the DOT accept an option of steel post for item 616.0100? | Please bid the project as shown in the plans with wood posts and to be completed by 11/4/22 as stated in the contract documents. | Jill Fehrman | 8 | 2022-05-04 16:10 | 2022-05-09 12:11
20220510 | 20220510040 | 40 | Temporary Epoxy | Good morning, on page 2 of 29 it states "install temporary marking line epoxy 4-inch yellow (yellow centerlines) on milled surface layer on the same day as milling operation, before the conclusion of each workday..." and "install temporary marking line epoxy 4-inch (yellow centerlines) to the paving joint on the HMA surface course before the conclusion of each workday...". It appears that there are only enough quantities to place this item on the surface course prior to the rumbles being placed. Can you please confirm the department's intentions? Will an addendum be issued to add additional quantities to this item? Thank you. | The plan set has a quantity error on this item. The plan set includes quantity for one application of the Temporary Marking Line Epoxy 4-Inch when two applications are called for in the special provisions. An addendum is being prepared to correct the error. | Mike Coleman | 1 | 2022-04-27 10:14 | 2022-04-27 12:02
20220510 | 20220510040 | 40 | I90/94 Closure | As stated in the proposal, USH 12 is an alternate route for I90/94. If the situation arises and we have to cease all operations within 15 minutes, will the Department cover material costs that will ultimately have to be wasted? Further, 15 minutes to stop all paving operations is not very practical without leaving the road in disarray and likely more dangerous - could this be extended? The contractor inevitably takes on significant risk with these guidelines. | The language is consistent with language employed when addressing construction operations on alternate routes for the Interstate system traffic. The time cannot be extended. | Jill Fehrman | 2 | 2022-05-03 18:09 | 2022-05-09 12:16
20220510 | 20220510040 | 40 | Prep Found For Asph Shoulders | Can the Department check their quantity of prep foundation for asphaltic shoulders - it looks to correspond with only one side of the project. |  |  | 3 | 2022-05-06 09:36
20220510 | 20220510041 | 41 | Removing & Installing Guardrail | There seems to be conflicting issues with the Removal/Installation notes for the guardrail. It is impossible to remove guardrail, complete the earthwork, HMA mow strip/shoulders, and properly install the minimum amount of guardrail on the same day. Was the last paragraph of the notes inserted by accident? If not please expand on how you expect this to be completed all on the same day. | All the guardrail does not need removed, graded and the minimum 150â€™ replaced the same day. If all the guardrail is removed in one day the slope can be delineated with drums as required in standard spec 104.6.1.2.3 and the special provisions. The intent of the minimum 150â€™ beam guard upstream is to protect a blunt end if removal or installation of the guardrail is not completed in one day. | Jill Fehrman | 1 | 2022-05-03 15:08 | 2022-05-05 14:45
20220510 | 20220510042 | 42 | US-10/45 Peak Hours | Do the peak hours listed in the Special Provisions only apply to the section where US-10 and US-45 run concurrent? | Yes, the USH 10 / USH 45 Peak Hours defined in the Traffic article only apply to the section where USH 10 and USH 45 run concurrent. | Mike Coleman | 1 | 2022-04-14 16:12 | 2022-04-18 08:35
20220510 | 20220510044 | 44 | Traffic control closures | In the special provision it states the project needs to start by 7/7. All lane closures must be down sundays from 7/1 - 9/5, afterwards they may be able to stay up over the weekends. The first 2 stages of the project are to lower the profile of the Interstate under 5 overpasses. WHen this was bid in January, we were able to start right away and had weekend closures til 7/1. Having to now take them down every weekend for this removal work will dramatically take more time. Would the department have any leeway in allowing a set amount of weekend closures from 7/1-9/5 to get these removals done in a timely fashion to help with project schedule? | The region will submit an addendum allowing all-day Sunday single-lane closures for pavement replacement at the overpasses. | Mike Coleman | 1 | 2022-05-03 13:08 | 2022-05-04 06:56
20220510 | 20220510045 | 45 | Asphaltic Surface Timing at Culvert Pipes | Article 3 of the special provisions, paragraph 4 says: "Pave the USH 45 lanes and paved shoulders at culvert locations within 48 hours of completion of the culvert installation." Paragraph 6 of the same article says: "Upon completion of each culvert pipe installation, patch travel lanes with asphaltic surface and ensure roadway elevations between adjacent travel lanes are even prior to reopening USH 45 to traffic." Are these two statements conflicting? Or what is the intent with the timeframe allowed to pave the asphaltic surface after completion of the culvert pipe? | The intent is to pave the culvert replacement locations within 48 hours of completion of the culvert installation, unless it falls within a weekend. An addendum will be addressed to clarify the language in the Prosecution and Progress. | Mike Coleman | 1 | 2022-04-26 12:04 | 2022-04-27 09:14
20220510 | 20220510046 | 46 | cross pipe clarification | The new cross pipe installed at STA 119+97 states on plan sheet 58 that joint ties are to be used. Is the designer's intent to use RCCP then or is there another option? Please clarify. | The number of joint ties listed in the MQ table were provided for information only if the contractor decided to use concrete pipe. The contractor may use any material they desire as long as it meets the requirements for bid item 520.3430 Culvert Pipe Class III-A Non-Metal 30-Inch. | Jill Fehrman | 1 | 2022-05-05 13:44 | 2022-05-05 16:31