## qandasearchletting_results
Date: | 2022-06-13
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220614 | 20220614003 | 3 | Replacing Guardrail Rail And Hardware | Can you provide the as-built for the WI-106/Curtis Mill Rd/Rock River Road intersection? Also, do you know which specific panels of the guardrail have been determined to be replaced? The guardrail here is radius rail at the intersection. We'd like to know what material will need to be ordered for replacing and what the radius of the existing rail is. | An as-built plan sheet can be found at the following location: https://wisdot.box.com/s/jq03dihaycewtalnbzilcxy8chohzfob or can be accessed on the HCCI June bid letting page under Supplemental Information. The As-Built sheet from Project ID: 3576-07-71 (2008) is indicating the SW radius is 54â€™, and the NW radius is 39â€™. With regard to the specific panels to be replaced, the engineer in the field will verify existing guardrail height prior to adjusting steel plate beam guard, and final adjustment height is to be determined by the engineer in the field, as indicated in the Existing Beam Guard Adjustment Table in the Construction Details of the plan. The measurements found in the table were taken at/near the mid-point of each existing radius. | Mike Coleman | 1 | 2022-05-13 09:05 | 2022-05-17 06:28
20220614 | 20220614005 | 5 | T-Barrier Sequence | Can you confirm if the anticipated timeframe for the t-barrier is after the stream realignment is completed? | Turbidity barrier is shown in stage 1A installed prior to the abutment and channel realignment being started. Turbidity barrier is shown in stage 1B installed prior to water being diverted into new channel and prior to west abutment construction. Coordination with contractor operations will be required and as directed by the engineer in the field. | Mike Coleman | 1 | 2022-05-13 09:20 | 2022-05-16 13:04
20220614 | 20220614005 | 5 | MGS Thrie Beam Transition | We are concerned that the NW corner MGS Thrie Beam Transition won't be able to follow the curve of the road without a bid item for radius thrie beam. If needed, and without this sort of bid item, the thrie beam may encroach on the lane width in this area. Please confirm that the standard bid item will be able to maintain lane width. | Item 614.2500 MGS Thrie Beam Transition is shown in the plans as curved matching road edge line at 153ft radius. Contractor shall bid accordingly using the bid item provided or as required. | Mike Coleman | 2 | 2022-05-13 09:24 | 2022-05-16 13:05
20220614 | 20220614006 | 6 | Storm Sewer Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) As there is a sizable amount of sole specified Class III storm sewer, could you please provide clarification as to the special situation that warranted that sole specification? SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | Based on depth of cover, location, or site specific conditions, the selection of pipe materials was based on the policies described in FDM 13-1-17. Notes 7 and 8 of the General Drainage Notes at the start of the storm sewer plans note where cover is measured for concrete and plastic pipe. There are locations throughout the project where there is 2â€™ of cover to the bottom of the base course but not to the bottom of the select crushed material. In those locations Class III pipe was specified because there is not sufficient cover to use plastic pipe and meet the backfill requirements for plastic pipe to avoid pipe deflection from construction loading. | Mike Coleman | 1 | 2022-05-16 14:08 | 2022-05-17 13:44
20220614 | 20220614008 | 8 | schedule | Contractor is requesting a copy of the DOT's preliminary schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/f8zfygl0kov6jx8d91y3e6hx4upr1rq9 or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2022-05-16 14:18 | 2022-05-17 07:54
20220614 | 20220614008 | 8 | culvert at 463+77 | IS this work to done under a full freeway closure per the traffic control plan on plan sheet 35? Does all the work required including the 15" asphalt patch have to be done in the 15 hour window? Can the southbound crossing be done at the same time? The specials talk about NB this year but never says anything about SB. The lane closures never talk about a full highway closure they only talk about the 3 days for the closure time of the ramps at Brown Road. I guess I little more guidance on how this work is supposed to happen would be great. Place placing 15" of HOT mix asphalt has its own issues when given a short duration to complete the work. Please advise. | The intent is to remove and replace the culvert below USH 41 northbound and southbound under a freeway closure with USH 41 traffic routed up the Brown Road interchange ramps as shown in the traffic control plans and discussed in the special provisions (Prosecution & Progress article under Additional Work and the Traffic Control article). The pavement would need to be patched prior to reopening USH 41 to traffic, however the full length of the patch as shown in the applicable construction detail would not need to be completed during the same closure window as the culvert removal and replacement. The intent is to have the entire culvert replaced during the 2022 construction season as discussed in the Prosecution and Progress, however it is anticipated that the entire culvert replacement will not be completed during a single 15 hour window so USH 41 northbound and southbound do not need to be closed concurrently depending on the contractorâ€™s operation. The USH 41 southbound exit ramp closure at Brown Road is intended for the frost heave repair on that ramp and independent of the culvert replacement work. | Jill Fehrman | 2 | 2022-05-19 15:56 | 2022-05-20 17:28
20220614 | 20220614011 | 11 | Project Schedule | This project is set up to be a 55 working day contract to be completed in the 2022 construction season. Would the department consider allowing the project to be completed in 2023 with a notice to proceed issued no later than April 10, 2023? | The department will not allow the project to be constructed in 2023. All work must be completed during the 2022 construction season. An addendum will be issued to add cold weather paving. | Jill Fehrman | 1 | 2022-05-20 11:00 | 2022-05-26 07:19
20220614 | 20220614012 | 12 | Project Schedule | This project has an October 14, 2022 completion date. Would the department consider allowing the culvert pipe work to be completed by August 26, 2022 per the special provisions, and the remaining work to be completed by May 27, 2023? | â€¢ The department will revise the completion date to May 26, 2023 (not May 27 as requested in contractorâ€™s question). o A holiday restriction will be added to the contract for Memorial Day in 2023 (noon Friday May 26, 2023 to 6:00 AM Tuesday, May 30, 2023). â€¢ The interim completion date for the culvert pipe work will remain the same (August 26, 2022). â€¢ An addendum will be submitted for the revision. | Mike Coleman | 1 | 2022-05-20 11:15 | 2022-05-24 06:35
20220614 | 20220614013 | 13 | SPV.0060.03 Watermain Offset Work | What is the size of the existing watermain that will need to be offset? | The crossing in the vicinity of Station 121+50 is described as 8â€ PVC C900 watermain pipe, and the crossing near Sta 124+10 is described as 10â€ PE DR11. This information originated from Scott Valliere of the LDF Tribe Utility Department in an email dated April 17, 2020. | Mike Coleman | 1 | 2022-05-23 07:19 | 2022-05-23 09:58
20220614 | 20220614017 | 17 | B-35-157 Geotechnical Report | Can a copy of the geotechnical report for bridge B-35-157 please be provided? | The Geotech reports for B-35-157 and B-35-167 can be found at the following location: https://wisdot.box.com/s/sxhkmsjhwl4e84pn7scto84q98uew549 or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-05-12 08:42 | 2022-05-16 08:28
20220614 | 20220614017 | 17 | Instream disturbance | Item #3 in the special provisions indicates that no instream disturbance is allowed between Sept. 19th and May 15th, does this mean that the box culvert must be completed and the temporary diversion of Scott Creek removed and restored by 9-19? Similarly, do both abutments and all riprap at Little Somo River need to be done by 9-19? | At Scott Creek the box culvert must be completed and stream banks restored prior to November 3. The temporary culvert need not be fully removed by this date as long as it is isolated from the stream. At Little Somo River in stream work will not be allowed until after May 15, 2023. An addendum will be issued with these updates. | Jill Fehrman | 2 | 2022-05-17 08:24 | 2022-05-20 17:47
20220614 | 20220614017 | 17 | Scott Creek Box Culvert Temp AS | The Traffic Control Staging plans, Sheets 12-15, for the Scott Creek Box Culvert Replacement note that the hashed temporary asphalt areas are to be 4 inch while the typical on sheet 12 notes 5 inches. Will the department please clarify the correct thickness? | The correct thickness is 5â€ as shown on the sections on sheets 8 and 12. The depth shown in the legend for the hatched areas is incorrect. | Mike Coleman | 3 | 2022-05-21 08:14 | 2022-05-24 06:42
20220614 | 20220614017 | 17 | Little Somo Bridge Asphalt Quantities | The stationing on the typical section on sheet 4 of the Little Somo Bridge plans do not match stationing in the Butt Joint Removal and the Asphaltic Surface tabulations on sheet 24. The Asphaltic Surface Tabulation also calls out 325 tons for the Temp Road and 875 tons for mainline. I am estimating roughly 550 tons for the mainline and 325 tons on the temp road for a total of 875 tons. It seems that the temp road tonnage might be doubled. Will the department please clarify as to whether the temp road should be AS Temporary as well as verify the quantities for the Little Somo Bridge project? | The stationing on the proposed typical begins at 984+30 (not 982+75) and ends at 989+74 (not 991+50). The stationing in the miscellaneous quantities for asphaltic surface should be 983+70 â€“ 990+34. The temporary road will be paid as Asphaltic Surface. The quantity for mainline was rechecked and confirmed to be correct. It includes the wedging required for the proposed profile (see note on proposed typical section and detail on Sheet 8). An addendum will be issued to correct this. | Mike Coleman | 4 | 2022-05-21 08:26 | 2022-05-24 07:09
20220614 | 20220614018 | 18 | L-55-11 & L-55-12 Foundation Details, Drilling Shaft 48-inch quantity | 1. Can structure plans/foundation details be provided for the High Mast L-55-11 & L-55-12 structures? 2. What item(s) is the 30LF of Drilling Shaft 48-Inch bid item for? | 1. The foundation details for the high mast lighting will be added in an upcoming addendum. 2. The 30 LF of Drilling Shaft 48-Inch are for the high mast lighting foundations as noted on the foundation details. The foundation details have been added via addendum. A full size copy of the plan sheet can be found at the following location: https://wisdot.box.com/s/kqclhgurkd7fuenlvo0jafmh6agx9110 or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-05-12 09:58 | 2022-05-16 08:18
20220614 | 20220614018 | 18 | Abandoning Well | What is the depth of the well to be abandoned? | The existing well has a depth of 180â€™. The DNR well report is being provided for reference and can be found at the following link: https://wisdot.box.com/s/kqclhgurkd7fuenlvo0jafmh6agx9110 The information can also be accessed from the June Bid Letting page under Supplemental Information - Questions and Answers. | Jill Fehrman | 2 | 2022-05-12 16:09 | 2022-05-19 17:21
20220614 | 20220614018 | 18 | Salvaged Topsoil | There doesn't seem to be a quantity for salvaged topsoil for the IH 94 temp median lane work for stages 2 & 4. Please revise quantity. | The revised quantity and plan sheets will be provided with an upcoming addendum. | Mike Coleman | 3 | 2022-05-13 09:34 | 2022-05-17 09:24
20220614 | 20220614018 | 18 | Asbestos Report | Can the asbestos report be posted? | The asbestos report can be found at the following location: https://wisdot.box.com/s/kqclhgurkd7fuenlvo0jafmh6agx9110 or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 4 | 2022-05-16 13:07 | 2022-05-16 13:13
20220614 | 20220614018 | 18 | L-55-11/12 Geotechnical Report | The plan sheet issued in addendum one for structures L-55-11/12 notes in the drilled shaft elevation "casing is anticipated to be needed per the geotech report." Can a copy of the referenced geotechnical report please be provided? | The Geotechnical report for this project can be found at the following location: https://wisdot.box.com/s/kqclhgurkd7fuenlvo0jafmh6agx9110 or by using the link to the Supplemental QA Information found on the June Bid Letting page. | Jill Fehrman | 5 | 2022-05-18 16:14 | 2022-05-20 17:44
20220614 | 20220614018 | 18 | 532.4500, High Mast 100-FT (structure) Lowering Devices & Fixtures | Could you please provide the system weight, and EPA of the lowering device and the fixtures for Structure L-55-11 and L-55-12. | The information requested can be found on the Wisconsin DOT Approved Products List under the specified bid item: https://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/tools/prods/659.aspx. | Mike Coleman | 6 | 2022-05-20 08:14 | 2022-05-23 10:22
20220614 | 20220614007 | 7 | Temporary pavement markings on milled surface | With the milled surface able to be left for 72 hours, what is the departments plan for temporary markings on the milled surface? There appears to be temporary on the surface prior to rumbles and same day post rumbles, but nothing for the milled surface. Will an addendum be issued to address the temporary markings on the milled surface? | An addendum will be issued to add Temporary Marking Line Paint 4-inch. | Mike Coleman | 1 | 2022-05-24 11:52 | 2022-05-25 13:45
20220614 | 20220614009 | 9 | SURFACE PREP AND COATING | Does the whole arch require surface preparation and coating? | As noted on sheet 2 of 4 of the structure plans, the exterior of the upper arches requires full paint removal and replacement as part of the â€œStructure Repainting Recycled Abrasive B-5-158-10â€ bid item. This includes the entire arch extending down to the top of the tie girder. | Jill Fehrman | 1 | 2022-05-25 14:43 | 2022-05-26 07:20
20220614 | 20220614007 | 7 | Full Depth Asphaltic Surface Repair | In order to improve ride quality, will the department allow full depth asphaltic surface repair to be completed prior to milling operations? | After further discussion with the WisDOT construction PM, we will NOT allow asphaltic surface repair prior to milling operations. Build per the contract. | Mike Coleman | 2 | 2022-05-25 15:20 | 2022-05-31 10:04
20220614 | 20220614006 | 6 | Modular Block in R-30-71 | Where is this 50 sf of modular block going? Page 844 shows section C-C is modular block. Page 843, in section c-c, shows vertical rustication grooves, which isn't possible in a modular block wall that we know of. Pages 846 thru 850 show the elveation and footing view of each wall section, and they all appear to be concrete. | The existing modular block wall from station 0+00 to station 0+07.52 will need to be removed, salvaged, and reinstalled as needed to construct the cast-in-place concrete retaining wall portion of the wall at the 90 degree corner. See Sheet 1 of 12 for the plan and elevation of the modular block wall. See Sheet 2 of 12 for Section C-C, coping detail, and soil parameters and wall external & overall stability evaluation tables for the modular block wall. The vertical rustication grooves on the cast-in-place concrete retaining walls are referenced in Section A-A & Section B-B on Sheet 2 of 12. The note references a vertical rustication grooves detail on Sheet 3 of 12 of the plans. | Mike Coleman | 2 | 2022-05-27 11:15 | 2022-06-01 12:20
20220614 | 20220614006 | 6 | Slotted Drain Questions | I am not seeing any detail for the slotted drain in the plans. Will Wisconsin require gasket material for the band joints? It lists them as 8â€ in a description on the Estimate of qty page? But is on 15â€ pipe? I also would need to know if they require a capped end on the highest invert end? And how the outlet breaks down with the elbow degree involved and pipe lengths. | I am not seeing any detail for the slotted drain in the plans. The slotted drain is to be constructed per SDD 8D13 â€œSlotted Corrugated Metal Pipe Surface Drainsâ€ so additional details are not necessary. Will Wisconsin require gasket material for the band joints? Band joints provided should meet the article in the special provisions for 521.2005.S.01. The special provision article does not specifically mention band joints but section 520.3.3(7) of the standard specs says â€œMake field joints by joining the metal pipe sections together with a band bolted firmly in place.â€ There is no reference to whether a gasket material is required or not. It lists them as 8â€ in a description on the Estimate of qty page? But is on 15â€ pipe? The slotted vane drain will be 8â€. There is a 15â€ storm sewer pipe below the vane drain that conveys the water in the STH 50 median ditch from one side of the crossover to the other. The 8â€ vane drain will terminate into this 15â€ pipe at the downstream end. I also would need to know if they require a capped end on the highest invert end? Section C of the Special Provision article requires the upper end of the slotted vane drain to be plugged. Section E identifies that the plug is including in the unit price for the slotted vane drain. And how the outlet breaks down with the elbow degree involved and pipe lengths. The connection between the end of the vane drain and the 15â€ storm sewer pipe is to be determined by the contractor. It is anticipated that it will be similar to SDD 8D13 Slotted Drain Installation Type B except that the pipe will terminate into the pipe with a blind connection rather than terminating into an inlet. | Mike Coleman | 3 | 2022-05-27 11:28 | 2022-06-01 07:32
20220614 | 20220614018 | 18 | Casing for High Mast Foundations | Will this be allowed to remain in place if using galvanized CMP? | Per BOS: The CMP casing may, or may not, be left in place depending on the contractorâ€™s means and methods for drilling the shaft and placing the casing. | Mike Coleman | 7 | 2022-05-31 05:44 | 2022-06-01 08:42
20220614 | 20220614018 | 18 | General Questions | 1. Lighting Protection and Grounding: a. There is a bid item Lighting Protection and Grounding SPV 0060.105. It this item related to the tower? b. In the bid item Communication Tower, it also includes lighting protection and grounding system. 2. Who is providing the LP tank? 3. Were there any soil borings at the tower locations? 4. The communication racks are provided by others. Who is installing them? Who is responsible for hooking them up? | 1. Lighting and Grounding: a. This bid item is not related to the tower. It is related to/for the high mast lighting on the project. b. The spec section included within the Communication Tower bid item (SPV.0060.300) covers the requirements for the tower site grounding system. That is â€œ33-79-00 Tower Grounding and Lightning Protectionâ€ pages 694-698. 2. The LP tank is part of (SPV.0060.106 Emergency Generator Communications Tower) pages 604-607. The tank is to be bought by the contractor and turned over to DOT as part of the project and filled with fuel (see pages 605-606). 3. Not specifically. See page 700 â€œTower Foundationâ€ for soil design parameters to use for tower foundation design. This references the Geotech report. The Geotech report was provided in response to question #5 in Bid Express. 4. Racks will be provided and installed by others (DOT/DSP technicians). DOT/DSP technicians are responsible for hooking them up. | Mike Coleman | 8 | 2022-05-31 09:23 | 2022-05-31 09:27
20220614 | 20220614006 | 6 | Request for Geotechnical Data | Please provide the geotechnical reports available for this project area. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/h2hjdbseufkukc73npb64oi7v2le0o0o or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 4 | 2022-05-31 09:51 | 2022-06-01 07:30
20220614 | 20220614018 | 18 | CAD File | Are there any CAD files available for estimating | Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One is Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 9 | 2022-05-31 22:08 | 2022-06-01 07:38
20220614 | 20220614018 | 18 | More general questions | A few more questions; 1. You have a bid item for two (2) Special 001. Trash Receptacles and also have the same in the building section under 12 93 00 Site Furnishings 2. I do not see any signage for non-smoking or firearms, etc. 3. The last two we provided 4â€™ bridges for the inspection pits | 1. Revisions to the trash receptacles and cigarette snuffers will be included in an upcoming addendum. 2. 12 generic signs are included on sheet A414 Page #200 of the set and they are also included in the specification section 10 14 16 Page#272-274. The generic signage is meant to cover the no smoking/firearms along with any additional signage the DOT would like to have around the building that includes text and a symbol/pictogram on a typical 7â€x7â€ sign. Past facilities have varied on the number of each that were included. 3. We have detail 4/A207 Page #183 for the inspection pit bridge planks and we call out a quantity of 2 on 1/A204 Page 180. We will clarify this better and reference our detail in an upcoming addendum. | Mike Coleman | 10 | 2022-06-01 07:45 | 2022-06-02 05:26
20220614 | 20220614006 | 6 | Line Item 0286 - 4' chain link fence | Good morning, In reviewing the plan sheets, it does not appear that there is a miscellaneous quantity sheet or a plan sheet that outlines the 4' chain link fence item. Can you please elaborate more on that item in terms of what it entails, etc.? Thank you. | The Fence Chain Link 4-FT miscellaneous quantity can be found in sheet 1 of 12 of Structure R-30-71 (CAT 0020), sheet 1 of 12 of Structure R-30-70 (CAT 0030), and sheet 1 of 5 of Structure R-30-73 (CAT 0040). There are no Fence Chain Link 4-FT quantities for Category 0010. | Mike Coleman | 5 | 2022-06-01 09:18 | 2022-06-01 12:22
20220614 | 20220614018 | 18 | SPV - Red Granite Chips | Does the DOT have approved "Red Ruby" granite sources that this material can be bid from? | The DOT does not have an approved source for the material. The material is commercially available at most landscaping retailers. | Mike Coleman | 11 | 2022-06-01 10:24 | 2022-06-02 11:11
20220614 | 20220614018 | 18 | SPV Base Aggregate Dense 3/4" washed | The spec included in the SPV is impossible to produce (can not have just 0%...must have a range). For 240 tons, can the spec meet 501 size No. 1 (3/4") concrete stone that is produced normally in the area to save some costs on making a specialty size material. | The gradation listed in the SPV will be revised in an upcoming addendum to match the gradation listed in 501 for the No.1 concrete stone. | Mike Coleman | 12 | 2022-06-01 10:31 | 2022-06-02 05:28
20220614 | 20220614003 | 3 | LONGITUDINAL JOINT | Is it the department's intention for us to leave a 2" vertical standing joint on the longitudinal joint in-between milling and paving operations? | Yes, it is anticipated that a 2â€ vertical standing joint will be left in place between milling and paving operations. Please do take note however, that the Special Provisions state â€œOnce a section of roadway has been milled, pave the section within 72 hours or prior to the weekend, whichever occurs sooner.â€ So no 2â€ vertical standing joints should be left in place for more than 72 hours or over weekends. | Mike Coleman | 2 | 2022-06-01 14:37 | 2022-06-02 11:16
20220614 | 20220614018 | 18 | Concrete Barrier Type S32 | The dimensions of the concrete pad that the concrete barrier wall is sitting on are different dimensions than shown in the SDD 14B32. Is it the intent to pay for this as incidental to the barrier wall as the concrete pad for the barrier or are you intending to pay for it as concrete pavement? Please advise. | The intent is for the concrete pad to be incidental to the barrier wall. A revised plan sheet noting this will be provided in an upcoming addendum. | Mike Coleman | 13 | 2022-06-01 14:56 | 2022-06-02 11:13
20220614 | 20220614018 | 18 | USH 12 Virtual Weigh Station Location | Where is any excavation work that would be needed captured for the work on USH 12 for the Virtual Weigh Station. Although minor I don't see anything for pavement removal or common excavation, let alone any quantities for base aggregate, HMA pavement, etc. Please advise. | There is no grading work anticipated for the Virtual Weigh Station. All other items mentioned are considered incidentals necessary to complete the contracted work as mentioned in section E Payment. | Mike Coleman | 14 | 2022-06-01 15:03 | 2022-06-02 11:15
20220614 | 20220614014 | 14 | Project Start/Completion | This project is setup to be completed during the 2022 construction season. The Notice to Proceed will be issued such that work shall start no later than July 20, 2022, unless approved by the engineer. Would the department consider allowing the concrete patching to be completed in the fall of 2022 as the weather allows, suspend time and complete the project in spring of 2023? Would the department allow a later notice to proceed? | The intent of the contract is to complete the project in the 2022 season while avoiding late season paving. An addendum will be issued to add Cold Weather Paving and Cold Weather Marking. | Mike Coleman | 1 | 2022-06-01 19:24 | 2022-06-03 06:00
20220614 | 20220614014 | 14 | Asphatic Surface Patching | It appears an item for asphaltic surface patching should be added for the prep of foundation area 1031+00 - 1119+38 NB, possibly the culvert replacement at Harround Rd and other locations as needed. | The Department will plan to do an addenda to add the item 465.0110, Asphaltic Surface Patching to the project. | Mike Coleman | 2 | 2022-06-01 19:27 | 2022-06-06 08:23
20220614 | 20220614015 | 15 | Project Completion | This project is to be completed in the 2022 construction season. Would the department consider allowing the option to complete the project this season or spring of 2023? | The project should be completed in the 2022 construction season as required by the contract documents. | Mike Coleman | 1 | 2022-06-01 19:33 | 2022-06-08 08:34
20220614 | 20220614015 | 15 | Match Milling and Paving Edges. | Under Prosecution and Progress it states â€œMatch milling and paving edges of adjacent lanes prior to completing work at the end of each day.â€ This project is specified as a mill & fill. We are removing 2.25â€ and putting back 1.75â€ lower layer leaving 0.5â€ difference. Will the 0.5â€ difference be allowed with uneven lane signs? | An addendum will be issued to remove this restriction as the standard spec drop off language will cover it. | Mike Coleman | 2 | 2022-06-01 19:41 | 2022-06-08 08:34
20220614 | 20220614015 | 15 | Intersection Restriction | Under Prosecution and Progress it states â€œPlace the surface layer of asphalt pavement on sideroads within seven calendar days after the surface layer of asphalt pavement is placed on STH 27 adjacent to the sideroad. Would the department allow the mainline surface layer paving to be completed on the entire project prior to requiring intersections to be paved? | An addendum will be issued to remove this restriction. | Mike Coleman | 3 | 2022-06-02 07:39 | 2022-06-08 08:33
20220614 | 20220614015 | 15 | One Mile Restriction | Under Traffic it states, â€œLane Closures shall be limited to one mile in length at all times.â€ This is not reasonable for a mill and fill situation. AADT on this road is only 1,100. As always, we will limit the lane closure length to the minimum distance possible. | An addendum will be issued to revise the restriction to 2 miles. | Mike Coleman | 4 | 2022-06-02 07:40 | 2022-06-08 08:31
20220614 | 20220614015 | 15 | MTV | Typically the material transfer vehicle item would be included in a project like this for the mainline suface layer. In case it was missed, it is not included in the proposal. | An addendum will be issued to add the item. | Mike Coleman | 5 | 2022-06-02 07:52 | 2022-06-08 08:30
20220614 | 20220614018 | 18 | Concrete Items | 1. Can you please check the Coloring Concrete WisDOT Red quantity? The quantity listed seems to be about half of what is needed. 2. Can you please clarify if the Concrete Pavement in the Scale Approach Pavement Reinforcement area is paid separately? | 1. The revised quantity will be provided in an upcoming addendum. 2. Yes the Concrete Pavement 11-Inch and Scale Approach Pavement Reinforcement are separate items being paid for in that area. | Mike Coleman | 15 | 2022-06-03 06:05 | 2022-06-03 06:06
20220614 | 20220614003 | 3 | ECHELON PAVING REQUIREMENTS | Are side streets and driveways required to be paved in Echelon with the mainline? | It is not expected that side roads and asphalt driveways be paved concurrently with the mainline (i.e. it is acceptable to pave mainline first and come back and get side roads and driveways). It is expected that side roads will be signed properly and home owners or business owners notified in the interim. Additionally, the Special Provisions requirement that states â€œonce a section of roadway has been milled, pave the section within 72 hours or prior to the weekend, whichever occurs sooner,â€ is still applicable. | Mike Coleman | 3 | 2022-06-03 13:00 | 2022-06-08 14:17
20220614 | 20220614018 | 18 | Excavation Work at SWEF | Was there a soil study completed to check for any potential of petroleum contaminated soil at the weigh station? If so can any correspondence be provided as soon as possible. | The Phase 1 Hazardous Materials Assessment report can be found at the following location: https://wisdot.box.com/s/kqclhgurkd7fuenlvo0jafmh6agx9110 or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 16 | 2022-06-06 10:25 | 2022-06-06 12:51
20220614 | 20220614008 | 8 | Start by date. | Contractor is requesting removal of the start-by date. | Due to the project being multi-year with NB US 41 being completed in the 2022 construction season and SB US 41 being completed in 2023 construction season, the contract will be revised from a working day to a completion date contract via an addendum and the start-by date will be removed. The addendum will also include an interim completion date for the NB US 41 work that needs to be completed in 2022. | Mike Coleman | 3 | 2022-06-06 15:36 | 2022-06-08 06:22
20220614 | 20220614018 | 18 | Substitution Request / WisDOT SWEF Facility | Good afternoon, We were invited to bid the acoustical ceilings for this project and would like to submit a substitution request. Sheet A902, Section 095100 Acoustical Ceilings, ACT-1 calls for Armstrong â€œor equalâ€ Fine Fissured 1732. We would like to submit an equal product for approval: USGâ€™s Radar 2220. The proposed item is equal to the specified, from an alternate manufacturer, for cost competitive bidding. Below are links to a product comparison and data sheet for your viewing. Thank you for your consideration! Product Comparison: file:///H:/Documents/ACT%20Comparison%20WisDOT.html Data Sheet: file:///C:/Users/libbiefroehle/Downloads/usg-radar-climaplus-ceiling-panels-data-SC2127%20(3).pdf |  |  | 17 | 2022-06-06 15:56
20220614 | 20220614018 | 18 | Subcontractors | Can you provide a list of subcontractor's on previous SWEF projects? | A list of subcontractorâ€™s used on previous SWEF projects can be found at the following location: https://wisdot.box.com/s/kqclhgurkd7fuenlvo0jafmh6agx9110 or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 18 | 2022-06-07 07:31 | 2022-06-07 07:36
20220614 | 20220614006 | 6 | CAD Files | Can you supply the CAD files for this project? | Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One is Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 6 | 2022-06-07 08:32 | 2022-06-08 06:27
20220614 | 20220614008 | 8 | Line 0050 Base Patching Asphaltic | Would the district consider using 4HT in lieu of a Grade 2 mix for the item of Base Patching Asphaltic? | The Base Patching Asphaltic item will require the mix to be a type LT or MT to ensure proper gradation and compaction is used for the base patch locations. | Mike Coleman | 4 | 2022-06-07 11:05 | 2022-06-08 14:17
20220614 | 20220614009 | 9 | Rope Lighitng | THe department has specifiied a 500 LF long Rope Lighitng, can you provide the manufacturer that supplies rope lighting in this length? The longest we can find is around 150LF. An yinsight on this would be appreciated. | An emergency addendum was issued to removes AQLIGHTING as an approved supplier. Updated the plan sheet notes on page 66 and 77. | Mike Coleman | 2 | 2022-06-08 08:30 | 2022-06-13 10:41
20220614 | 20220614009 | 9 | Dimensions | There are absolutely no dimension on the sheets showing the sections of the bridge, the project is not broken out into quantities it is Lump Sum. Can dimension be provided so a proper and accurate pricing cna be provided? Lump Sum is hard enough to get a fair price, with no dimesnions it is next to impossible. | The As-Built plans can be found at the following location: https://wisdot.box.com/s/dylnnm0dbn7xbpmb7tam3u8vhjh2k3gp or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 3 | 2022-06-08 08:32 | 2022-06-08 14:16
20220614 | 20220614015 | 15 | Incentive Density Lognitudinal Joints | Just noticed the price in the proposal for the Longitudinal Joint incentive is $0.40. We think it should be $1.00 for the bid item? Payment is $0.40/LF in the spec for full incentive, but not normally how it is shown in the proposal. | An addendum will be issued to correct this. | Mike Coleman | 6 | 2022-06-08 09:10 | 2022-06-09 11:39
20220614 | 20220614018 | 18 | Plumbing and HVAC Plans | It was discovered thereâ€™s a drawing scale discrepancy for the plubing and HVAC plans. The given scale of 3/16â€ = 1â€ scale given on mechanical drawings appears to be incorrect after cross referencing architectural plans. According to the architectural plans, the building length from east to west scales 114â€™ which matches given dimension on drawing. Using the 3/16â€ = 1â€™ scale as noted on the mechanical drawings the building length scales 57â€™. Please confirm. In the event there is a scaling issue, we will need to re-estimate the plumbing and HVAC portion of this project. There may not be enough time by bid date. |  |  | 19 | 2022-06-08 11:55
20220614 | 20220614010 | 10 | Triple 60" Culvert STA 662 | While placing triple run of 60" CPRC at Sta 662, could contractor have hard closure including night time for 2-3 days while work is being performed? | Any hard closure at night would need the approval of local emergency responders and engineer during construction. | Mike Coleman | 1 | 2022-06-08 12:46 | 2022-06-09 12:52
20220614 | 20220614018 | 18 | 4MT Quanity | On page 478 the 4MT quantity seem to be proportionally off from the 3MT based on the standard 5" of pavement cross section. Please confirm these quantities. | The revised quantity will be provided in an upcoming addendum. | Mike Coleman | 20 | 2022-06-08 12:54 | 2022-06-09 07:09
20220614 | 20220614010 | 10 | Bridge Approach HMA Paving | If the bridge is completed this fall the approaches will have to be paved prior to completing a test strip. Would the department change this quantity of 4 LT to Asphaltic Surface? | At this time, 4 LT will remain. | Mike Coleman | 2 | 2022-06-08 15:28 | 2022-06-09 12:53
20220614 | 20220614010 | 10 | Roadway Closures? | Why were the allowable closure days reduced so much from the original bid? In Segment 1 is the intention to complete the remaining culverts not called out in the specials after the roadway is open to through traffic under flagging operations? | : The intention is to replace the deep culvert pipes (those listed in the specials) during the hard closure. With the change in paving schedules, the detour was reduced to 14 days. | Mike Coleman | 3 | 2022-06-08 15:45 | 2022-06-09 13:15
20220614 | 20220614010 | 10 | Design Schedule | Could the department provide the updated design construction schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/hilmby5dz9lxbp714vrszs1f2gckpgxd or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2022-06-08 15:46 | 2022-06-09 13:21
20220614 | 20220614018 | 18 | USH 12 Virtual Weigh Station | It appears that the scale paving on USH 12 is already paved, what was the intent for installing loops for the scale work? | The scale paving was completed under a separate WisDOT project last year. As stated in section 2.2 Loop Detectors of the spec, if the Contractor will be deploying loop detectors as a part of their system, â€œâ€¦the appropriate PCC section of roadway will be removed, loops will be installed, and the appropriate PCC section will be replaced. This removal/replacement of the PCC and associated activities such as sawing shall be incidental to the Virtual Weigh Station bid item. â€œ | Mike Coleman | 21 | 2022-06-09 06:19 | 2022-06-09 12:51
20220614 | 20220614018 | 18 | Removing Asphalt Milling Item | Please clarify that the bid item removing asphaltic surface millings on this job. The cross section does not show milling and shows full depth pavement 5" in these sections on page 11. This will change the 4MT quantity as asked in previous question. | The Removing Asphaltic Surface Milling is being utilized during Stage 1 of Traffic Control to mill the outside shoulder to remove the rumble strip (shown on page 352). The shoulder will then be repaved with 1â€ of 4 MT 58-34S. The typical section is being updated to reflect this in an upcoming addendum. | Mike Coleman | 22 | 2022-06-09 11:46 | 2022-06-09 13:18
20220614 | 20220614013 | 13 | Bore and Jack Pipe Material | 1. Would it be acceptable to use 30" Reinforced Concrete Pipe Class IV jacking pipe without a casing in lieu of the IPS carrier pipe with steel casing? 2. Neither HDPE pipe or concrete pipe is readily available. When it takes longer than the allowed 30 working day time period to get the pipe, will the project time be stopped until the material has been obtained? |  |  | 2 | 2022-06-09 14:56
20220614 | 20220614006 | 6 | 643.0500 Flexible Tubular Marker quantities | The quantities for Flexible Tubular Marker posts/bases appears to be overstated. Stage 2A shows 703 EA, and then Stage 2B shows an additional 712 EA. Was the 703 installed in 2A accidentally re-counted in Stage 2B? I don't see where another 712 could be installed in this stage. Should the 2B qty be 9? Same for stage 4. 4A installs 205 ea, 4B installs 191 ea; but then 4C installs 705 more? It looks like 4C should add 309 ea for a total installed of 705. These potential repeated quantities are 44% of the total bid quantity. Please review and advise. Thanks |  |  | 7 | 2022-06-10 10:55
20220614 | 20220614014 | 14 | Requirement to start prior to prior to July 20, 2022. | Under Prosecution and Progress its states that work shall start no later than July 20, 2022. We also see Addendum 2 which is helpful. Will starting before July 20, 2022 requirement be eliminated or relaxed? It seems very challenging to get an award, contract, precon, etc. and work started by July 20, 2022 and to be held responsible to start prior to July 20, 2022. This seems very challenging and not conducive to best pricing. A start in August is more realistic. |  |  | 3 | 2022-06-11 10:48