## qandasearchletting_results
Date: | 2023-01-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230110 | 20230110002 | 2 | Adding and asphalt shoulder repair item. | Will WisDOT add an asphalt repair item for repairing asphalt shoulders damaged by traffic and/or other contractor operations like will occur when concrete replacements are performed? | At this time the Region does not see a need for an asphalt repair item. | Mike Coleman | 1 | 2022-12-11 13:28 | 2022-12-15 09:12
20230110 | 20230110003 | 3 | centerline joint milling | May the fines from the 2 foot centerline joint milling be swept onto the existing gravel shoulders? Or will pickup sweeping be required? | The contractor must dispose of all milling material outside of the project limits. An addenda will be forthcoming. | Mike Coleman | 1 | 2022-12-16 15:16 | 2022-12-27 09:23
20230110 | 20230110007 | 7 | OH Lines | Even with the proposed relocation of the OH power and communication lines proposed in the special provisions, OSHA clearances do not appear to be met for crane use. The new structure layout will be within 10' of the OH utilities. Will these lines be de-energized at all during construction, or will extra ordinary efforts be necessary for pile driving and other crane work near the OH lines? | The subject overhead utility lines can be temporarily relocated if requested by the contractor during construction. The special provisions will be updated via addendum. | Mike Coleman | 1 | 2022-12-20 10:06 | 2023-01-03 07:10
20230110 | 20230110010 | 10 | CIR/Shaping Shoulders | Typically, Existing asphalt is 15 feet wide, CIR Layer is to be placed 17 feet wide, a 2â€™ change in width. Why is shaping shoulders defined as 3 foot wide removal, when 2 feet of removal is sufficient to place 17 feet of CIR? Concerned about relaying CIR material with an un-confined edge. Potential is high for having density and/or loss of section on the outside edge if material is not laterally supported. Please advise. | There has been no issues with the unconfined edge overall on the CIR we have constructed in Wisconsin. This is consistent with SPV language highlighted below which requires the removal of shoulder material to reduce any contamination of the CIR Layer with shoulder aggregate. This also provides a good working platform for operations to provide a consistent cross section. This language should remain in the specification. | Mike Coleman | 1 | 2022-12-16 10:44 | 2022-12-20 06:54
20230110 | 20230110010 | 10 | CIR Specifications | Can the special provisions for Item 327.1000.S be updated to the latest revision? Section C.7.3 Surfacing Paragraphs (4) & (5) have been updated/eliminated on other projects. | An addendum will be issued to revise section C.7.3 Surfacing. | Mike Coleman | 2 | 2022-12-16 11:22 | 2022-12-20 06:56
20230110 | 20230110010 | 10 | Prepare Foundation for Asphaltic Shoulders | Can the 3 feet of shoulder material be bladed out and incorporated into the new CABC shoulder? Or is the intent to remove and haul 3 feet of existing shoulder materials to be wasted off site? | Per standard spec 211.3.6 reuse of the shoulder material is allowed if it meets the requirements of standard spec 305. The contractor would need to ensure that the material bladed to the side to be reused would still meet all requirements for base aggregate dense ï¿½ inch or 1 ï¿½ inch under standard spec 305. If not, the material would not be allowed to be reused. If existing shoulder material bladed off meets the requirements for base aggregate dense ï¿½ inch or 1 ï¿½ inch under standard spec 305, the material would be considered for use in the lower 4.5 inches of the proposed aggregate shoulders as article 16 of the special provisions allows only aggregate classified as crushed stone for Dense 3/4-Inch when used in the top 3 inches of the unpaved portion of the shoulder or for unpaved driveways and field entrances. | Mike Coleman | 3 | 2022-12-20 08:50 | 2022-12-22 09:46
20230110 | 20230110012 | 12 | Structure Plans | Can you please direct me to the plans for the (1) 532.5130 Monotube Cantilever Type III (structure) S-67-981. | Structure plans (S-67-981) are in the as-let plans on the bidding webpage. As mentioned, they are on 194-195 within the 1300-09-71 page numbering system. | Mike Coleman | 1 | 2022-12-19 20:11 | 2022-12-21 06:56
20230110 | 20230110013 | 13 | Item 390.0203 Base Patching Asphalt | I do not see a detail for Item 390.0203 Base Patching Asphalt. Are we to assume 6" removal and replacement? | Depth of asphalt pavement is unknown. 6â€ removal and replacement at the direction of the Engineer is a reasonable assumption. | Mike Coleman | 1 | 2022-12-16 10:33 | 2022-12-28 08:30
20230110 | 20230110019 | 19 | Earthwork | Can the Department please provide the soil borings for this project and the earthwork tables in excel format? | The soil borings and earthwork tables in excel can be found at the following location: https://wisdot.box.com/s/pb0xlbpp0tzxxia81bikez4f4od3slmq or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-12-19 15:09 | 2022-12-21 06:44
20230110 | 20230110023 | 23 | Drainage Fabricated Items | Questions for Project #23 on the 1-10-2023 Letting. The anti-seep collar shows to be aluminum? Is that supped to be aluminized coated like the pipe? Also is there a better print for the stop log risers? The detail for the center of the large riser shows something behind the two channels that are back to back, but it is not labeled as to what it is. | â€¢ Anti-seep collar should be aluminum â€¢ Riser detail in plan is the standard NRCS detail. The component behind the two back-to -back channels is an angle brace per note 3. | Mike Coleman | 1 | 2022-12-13 15:48 | 2022-12-15 09:09
20230110 | 20230110029 | 29 | CIR specifications | Can the special provisions for Item 327.1000.S be updated to the latest revision? Section C.7.3 Surfacing Paragraphs (4) & (5) have been updated/eliminated on other projects. | An addendum will be issued to update the language. | Mike Coleman | 1 | 2022-12-16 11:28 | 2022-12-22 09:45
20230110 | 20230110029 | 29 | CTY WW roundabout | Per sheet 13, CTH WW/K roundabout detail sheet, there is a roundabout to be built by others. Is there information on when this will be built? Impact to traffic patterns or who is building this? | This project is a Local County project. The County will be bidding this project on January 16, 2023 to a contractor. Advertisements for this project will begin in late December. The current timeline for construction of WW and the roundabout is planned from June 1, 2023 to September 1, 2023. | Mike Coleman | 2 | 2022-12-20 09:48 | 2022-12-21 13:44
20230110 | 20230110031 | 31 | Subsurface Information | Is there any subsurface information available for this project? Any borings done for the sign structure foundations? | The only subsurface investigation completed was for the sign structures. The Geotech report can be found at the following location: https://wisdot.box.com/s/7p16f6ujhw5sj6qdot55eswhyyx08tc2 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-12-14 14:31 | 2022-12-19 12:56
20230110 | 20230110032 | 32 | 1550-04-76; 60th Ave Intersection Mix Type | The department may want to consider changing the surface lift mix type from Asphaltic Surface to Asphaltic Surface Intersections for 60th Ave. This will line up with the other intersection surface mix type from project 1550-02-76. This will also address the mix meeting a 4MT 58-34S mix type from SPV #27. | An addendum will be issued to address this. | Mike Coleman | 1 | 2022-12-15 16:27 | 2022-12-19 12:58
20230110 | 20230110032 | 32 | 5MT & 4MT Quantities | When looking at the miscellaneous quantities on Sheet 31 the 5MT 58-34V and 4MT 58-34V quantities might be interchanged. The 4MT 58-34V item is the thicker lift which would typically result in more tons. | We have the lower layer 4MT and the upper layer 5MT quantities flipped around on the MQ sheet. We will issue an addenda on for this error. | Mike Coleman | 2 | 2022-12-15 16:52 | 2022-12-21 13:43
20230110 | 20230110035 | 35 | Prep Foundation for HMA | What does this item cover? How is the asphalt removal and excavation of existing base for 5" HMA being paid on Seacrist Lane? | Per standard spec 211.3.5.1â€¦. Prepare aggregate base, existing asphaltic pavement or surfacing, or concrete base and pavement foundations for asphaltic surfacing sufficiently ahead of prime-coating or surfacing to allow uninterrupted placement. Remove material that may adversely affect bond before surfacing. Areas of removal for Secrist Ln were included within the common excavation quantities for STH 37. | Mike Coleman | 1 | 2022-12-19 15:28 | 2022-12-21 06:53
20230110 | 20230110035 | 35 | Fish restrictions conflict with construction schedule & asphalt placement | Hi, this project indicates that the project must start by 4/10/23. However, with an in-stream restriction from 3/15-5/15, the project will need to start much earlier (mid-February?) to construct the bypass, temp structure, remove the existing structure, build the pier, and place the new riprap. Asphaltic surface for the temporary roadway will not be available at that time of year. We respectfully request that the fish restrictions be waived in this instance to allow something closer to a late March start (preferred), or eliminate the asphaltic surface on the bypass (not desirable at that time of year)? There currently are no fish in the trickle of water there now. | An earlier start requiring waiving the timing restrictions for in-stream work should not be necessary as all temporary bypass, temporary structure work and removal of existing structure can occur mid-May to avoid the May 15th restriction timeframe. The Notice to Proceed of April 10th was included to allow contractor time to perform necessary Clearing activities as well as Bird Deterrent System installation prior to those timeframe restrictions. | Mike Coleman | 2 | 2022-12-19 17:15 | 2022-12-21 06:54
20230110 | 20230110035 | 35 | Low Chord elevation for the temporary structure | Is there a low chord elevation for the temporary structure that should be specified? | Temporary structure information (Q5, HW5, area opening) was provided on sheet 23, Plan & Profile Temporary Bypass. The low chord should be at or just above the HW5 elevation. | Mike Coleman | 3 | 2022-12-20 06:59 | 2022-12-21 06:58
20230110 | 20230110035 | 35 | Pier conflicts with erosion control, channel of waterway | Hi, The erosion control plan (page 7 of the .pdf plan file) shows the new, fully encased pier crossing the channel of the waterway from bank to bank, completely obstructing the flow of any water (the old pier is in the same place, but it was an open bent). This bridge is virtually a dry run, but some provision should be made for future runoff. Should a stream relocation item be added to the contract, with drawing to illustrate how the intended future flow of water is to be channeled? | Stream relocation will not be added at this time. | Mike Coleman | 4 | 2022-12-20 07:19 | 2022-12-22 09:43
20230110 | 20230110007 | 7 | Construction Schedule | This contract has a completion time of 40 working days. Given the minimum concrete curing times required per WisDOT standard specifications, we have concerns that this amount of time may not be achievable. The amount of curing days required for a slab span bridge with an overhanging concrete sidewalk and concrete parapets is substantial. Coupled with concrete approach slabs, the amount of time spent on curing will take up a large portion of the construction schedule. Has WisDOT considered this in the contract schedule requirements, or will extra-ordinary efforts and/or HES concrete be required for this project? | An addenda is being prepared to increase the number of working days. | Mike Coleman | 2 | 2022-12-20 10:15 | 2022-12-29 09:27
20230110 | 20230110036 | 36 | Railroad Flagging | There is no standard special provision included on this project for railroad flagging on structure B-27-169. The railroad is less than 100' from the project site. In the past, projects within this distance of railroad tracks have included standard special provisions for railroad flagging. Will the department be including a provision for railroad flagging on this project, or is railroad flagging not required on this contract? | It was anticipated that there would not be a need for a flagger for more than 2 weeks including if a crane could foul the track. | Mike Coleman | 1 | 2022-12-20 10:33 | 2023-01-03 06:52
20230110 | 20230110023 | 23 | Stop Log Water Structure | Are the soil borings available for the area of Stop Log Water Control Structure? | No soil boring available for the area of Stop Log Water Control Structure. | Mike Coleman | 2 | 2022-12-20 15:13 | 2022-12-21 08:02
20230110 | 20230110006 | 6 | R/W Plat | Is there a R\W Plat for this project? | The full-size R/W Plat can be found at the following location: https://wisdot.box.com/s/wk94qzqhikk1f90msbp9zbo3vfhfmn9x or can be accessed on the HCCI January bid letting page under Supplemental Information. An addendum will be issued to add the R/W Plat to the plans. | Mike Coleman | 1 | 2022-12-21 08:39 | 2022-12-21 13:45
20230110 | 20230110023 | 23 | Joint Ties | Do all concrete culvert joints get joint ties on this project? | Concrete culvert joint tie requirements would follow Standard specification section 520.3.3(5). | Mike Coleman | 3 | 2022-12-21 09:52 | 2022-12-21 11:03
20230110 | 20230110033 | 33 | Concrete Culvert Joint Ties | Do all concrete culvert pipe joints get joint ties on this project? | I can find no reference in the plans or special provisions for pipe joint ties. (In some areas (Lake Superior basin red clay soils) of the NWR we do require every joint to be tied) This project is not in that area. Therefore, pipe ties shall be as specified in the standard specs. (last three joints on both ends of pipe). | Mike Coleman | 1 | 2022-12-21 09:54 | 2022-12-22 09:51
20230110 | 20230110017 | 17 | Soil Borings | Are any soil boring logs available? | The soils report can be found at the following location: https://wisdot.box.com/s/y2zn8gb7bva08ztf4ruz0kyxi27k539m or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-12-21 13:51 | 2022-12-28 08:29
20230110 | 20230110016 | 16 | Base Patching | The base patching quantity appears in the milling item and also in SPV.0180.01 Base Patching item. Could you clarify which item the base patching falls under? | Base patching falls under SPV.0180.01 Base Patching and includes the 3â€ additional milling required as per the specifications. The quantity of milling for base patching under 204.0125 Removing Asphaltic Surface Milling should be removed. The quantity plan sheet will be updated as part of Addendum #1. | Mike Coleman | 1 | 2022-12-21 15:09 | 2022-12-30 06:03
20230110 | 20230110016 | 16 | Milling | It appears the milling quantity is overstated. I believe the 3' shoulder milling is figured at a 3" depth rather then the 1" average the plan shows. Could you please confirm? | The quantity for 204.0125 Removing Asphaltic Surface Milling was overstated. The correct milling depths are shown in the plans at 3â€ mainline and 1â€ shoulder. The revised quantity should be 20,108 TONS, which includes the removal of the Base Patching Milling as that work is covered under SPV.0180.01 Base Patching. The quantity plan sheet will be updated as part of Addendum #1. | Mike Coleman | 2 | 2022-12-21 15:17 | 2022-12-30 06:03
20230110 | 20230110035 | 35 | Common Ex Quantities | In reference to the answer to the prior question about common ex quantities for Seacrist Ln, the cross sections do not show any cut on Seacrist Lane. The subcut stops at 12' from centerline. The misc quantities show 278 TN of BAD 1 1/4" getting placed for Seacrist Ln. Typically, shaping is incidental to base so it is unclear what the prep foundation item is for if virgin base is being placed. Also, the earthwork summary shows 231 CY of Common Ex from station 545+50 to 547+75 yet there is 259 CY of Unusable Pavement Material in that area? Can we confirm the common ex quantities are correct? Thanks | Common Excavation quantities are incorrect and an Addendum will be issued to update these. | Mike Coleman | 5 | 2022-12-22 09:34 | 2022-12-27 09:21
20230110 | 20230110036 | 36 | Coordination with Other Projects | Is WisDOT aware that Hwy 95 will be the haul route for the resurfacing project on WI 121, Alma Center to Northfield, October #9? The detour route will add 20 miles, one way, to the hauls for that project. | Yes we are aware of this. | Mike Coleman | 2 | 2022-12-22 09:46 | 2023-01-03 06:53
20230110 | 20230110009 | 9 | 656.0201 Electrical Service Meter Breaker | This item only has one option and it currently has a lead time of 80 weeks. There are no alternates available. How should this be bid with an item that cannot be manufactured until long after the project deadline? | The project team has communicated with Alliant Energy who will supply the power for the project. Alliant Energy is aware of the lead times and recommended keeping the item as-is noting that the lead times, while long, are not usually as long as stated. Alliant Energy mentioned if the specified meter is not available within the construction time frame, they will work with the contractor to determine a safe and acceptable alternative that they will be willing to connect into. | Mike Coleman | 1 | 2022-12-22 09:52 | 2022-12-28 07:44
20230110 | 20230110004 | 4 | Temporary Pedestrian Detours | Where it is proposed that pedestrian traffic is to be detoured only 4.25' in front of the work area, is there an alternative to this detour plan. 4.25' is not enough space for construction equipment. | Due to the existing width of the roadway, and the need for two 11â€™ lanes to maintain traffic, 4.25â€™ in front of the work area is all that can be accommodated on STH 73. If additional room is needed, a lane would need to be closed and a flagging operation would be required to maintain traffic. After the ramp is constructed, the temporary accommodations would need to be put back in the configuration shown in the plans to maintain 2 lanes of traffic during cure time. | Mike Coleman | 1 | 2022-12-27 10:30 | 2022-12-29 09:29
20230110 | 20230110036 | 36 | Bar Steel HS coated Item 54 | The bid quantity for Item 54 coated rebar appears to be short by 880 LBs. The bid quantity is listed as 77,240 LB but adding quantities listed for the 2 bridges the quantity should be 78,120 LB | That is correct. An addendum will be issued to update the quantity. | Mike Coleman | 3 | 2022-12-27 10:59 | 2023-01-03 07:08
20230110 | 20230110015 | 15 | Geotechnical Report | Can the Department provide the Geotechnical Report for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/hgw9fmlkqxom2o7qed8wp8kdxfthauom or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2022-12-27 13:02 | 2022-12-29 09:33
20230110 | 20230110017 | 17 | Clearing and Grubbing Schedule- Staging | How would stage one and stage two be cleared if no tree clearing is allowed between April 1 and October 31. Is this work to be done outside of stage / outside the work zone area? All done by April 1? | CTH D is staged, but is closed to through traffic through the duration of construction. All clearing on the project will occur in Stage 1 prior to April 1st to comply with the Northern Long Eared Bat endangered species requirement. | Mike Coleman | 2 | 2022-12-27 13:12 | 2022-12-29 09:35
20230110 | 20230110038 | 38 | Project schedule | Would the department please provide the anticipated schedule for this project? It appears with the work required, in stages, for the traffic control, project tie ins, temporary shoring, structural approaches, etc., there is not enough time allowed with the 60 working days allocated. would the department consider increasing the working days to reflect the amount of work required? | The design schedule can be found at the following location: https://wisdot.box.com/s/h21h21uppk82eod84evor3kbsxgsjysw or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. An addendum was issued on 1/4 to change the working days from 60 working days to 67 working days. | Mike Coleman | 1 | 2022-12-28 07:46 | 2023-01-03 07:01
20230110 | 20230110019 | 19 | Project Design Schedule | Can the department provide the design construction schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/pb0xlbpp0tzxxia81bikez4f4od3slmq or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2022-12-28 11:13 | 2022-12-30 05:59
20230110 | 20230110002 | 2 | Work Restrictions | Are there going to be work restrictions for April and May or can the Contractor work during the day in April and May. The Special Provisions do not contain work restrictions for April and May. | An addendum will be sent out with the work restrictions for April and May. | Mike Coleman | 2 | 2022-12-28 11:44 | 2022-12-30 06:04
20230110 | 20230110019 | 19 | Earthwork | Earthwork - On the Typical Proposed Section for the pulverize and relay portions of the project, the department has shown areas on the 4:1 being filled with base aggregate dense 1-1/4" and areas on the 3:1 Topsoil seed, fertilizer & Mulch/EMAT. In the earthwork tables it has a combined 6,281CY of fill needed for the pulverize and relay Sections of the road. Can the department clarify that the fill quantity given in the earthwork tables for the pulverize and relay sections of the road has the base aggregate dense 1-1/4" for the 4:1 slope deducted from the fill needed that is shown in the earthwork table? | Yes, the 1 ï¿½â€ area has been removed from the fill quantity included in the earthwork tables. | Mike Coleman | 3 | 2022-12-29 09:33 | 2022-12-30 06:00
20230110 | 20230110025 | 25 | Excavation for base | How is the excavation for the new sidewalk grade and material removed for the placement of base paid for? Can an excavation item be added to cover this work? | Foundation excavation and preparation for the new sidewalk grade and material removed for the placement of base is incidental to the Concrete Curb and Gutter and Concrete Sidewalk bid items under 601.5 (3) and 602.5.2 (1), respectively, included in the project. An excavation item will not be added to the contract for this work. | Mike Coleman | 1 | 2022-12-29 09:47 | 2023-01-04 06:24
20230110 | 20230110015 | 15 | RRFB System Quantities | Can you clarify the number of Rectangular Rapid Flashing Beacon (RRFB) systems that are included with this job? According to the Proposal and Plan qtys (Line 290 and 292), there is only 1 complete RRFB system (1 on each side of the road). However, the plans shows that there are 2 complete systems; 1 at station 565 (which is the listed on the proposal/plan qty), and 1 at station 585. | Only one complete Rectangular Rapid Flashing Beacon (RRFB) system (one on each side of STH 67) is included in this project. RRFB location shown on plan sheet 71 is correct. Stations shown on Miscellaneous Quantity Table (Sheet 99) are not correct, correct stations are: Sta. 584+83 LT and Sta. 584+93 RT. | Mike Coleman | 2 | 2022-12-29 13:40 | 2023-01-03 07:10
20230110 | 20230110037 | 37 | Temporary Shoring | How will the temporary shoring be measured and paid for per the bid item specification? As shown in the plans, it appears it is being utilized as a cofferdam, not soil retention? | The measurement shown in the current plans is from the ground line on the active water side to the top elevations noted on the plan. Note, the system developed was to accommodate temporary waterway diversion inside the R/W and was not placed on the structure plans per coordination with BOS. I donâ€™t disagree it sort of looks like a cofferdam but also has retaining components to we could work inside the R/W. We plan to issue an addendum so there is no confusion in the field on how to pay for this. | Mike Coleman | 1 | 2022-12-29 14:08 | 2023-01-04 06:22
20230110 | 20230110031 | 31 | Joint Sealing | Would concrete pavement joint seal be added to this project? It meets the requirements. | No, concrete pavement joint sealing is not intended to be added to the project. The concrete pavement operations should follow the standard specifications. | Mike Coleman | 2 | 2022-12-31 16:20 | 2023-01-04 14:32
20230110 | 20230110031 | 31 | Bypass Road Construction | Will flaggers be needed/allowed to get material in to build the bypass road in Stage 1? Will borrow be needed to build the bypass road? | Yes flaggers will be allowed to construct the bypass road in Stage 1 in accordance with the DOT standards. It is anticipated that the excavation in the northwest quadrant of the STH 65/70th Avenue intersection will provide enough earthwork that borrow will not be needed. | Mike Coleman | 3 | 2023-01-03 08:17 | 2023-01-05 15:36
20230110 | 20230110043 | 43 | Waterway Markers | Sheet 78 of the plans shows waterway marker placement but no bid item exists to pay for these markers. Please advise if the waterway markers will be paid for under a bid item or what item they are considered incidental to? | Per Standard Spec 107.19, the contractor is required to provide temporary lights, waterway markers, other devices, or combination thereof as the governmental authority specifies. All expenses the contractor incurs to maintain navigation are incidental to the contract cost. | Mike Coleman | 1 | 2023-01-03 08:27 | 2023-01-04 14:12
20230110 | 20230110038 | 38 | Answer to question 1 | Could you review the answer to question #1? | An addendum has been issued to change the contract completion time from 60 working days to 67 working days. | Mike Coleman | 2 | 2023-01-03 08:41 | 2023-01-04 14:15
20230110 | 20230110002 | 2 | New Lisbon On & Off Ramp Paving | Looking through the plan it states that there are 4 ramp shoulders - (2 on & 2 off ramp shoulders) that need to be paved and the only way to do this work safely the ramps needs to be closed. There is nothing shown in the traffic control details where the on & off ramps are going to be closed. We did a similar operation last year at the CTH HH on and off ramps and we did the ramp work spread out over 2 nights only shutting down 1 on & off ramp each night and it seemed to still allow traffic to flow and not cause any issues. Would DOT be open to allowing the closure of the on & off ramps for 2 nights? | We are only paving the shoulders through the gore at the New Lisbon ramps so the Region feels that this work can be completed under traffic. | Mike Coleman | 3 | 2023-01-03 09:05 | 2023-01-04 11:35
20230110 | 20230110003 | 3 | HMA Paving | Given the type of work and potential staging of the paving would QMP HMA specification be a better option than the PWL specification? There may be economic value paving from multiple sites with QMP as well. | Asphalt paving requirements shall be bid as specified, including the PWL specification. | Mike Coleman | 2 | 2023-01-03 09:13 | 2023-01-06 11:42
20230110 | 20230110006 | 6 | Soil Borings C-22-14 | Are there any soil borings near C-22-14 which we could look at in regard to required shoring designs? | No borings were taken near C-22-14. | Mike Coleman | 2 | 2023-01-03 09:51 | 2023-01-05 06:14
20230110 | 20230110038 | 38 | Days | As others have asked, would the department consider increasing the working days to reflect the amount of work required? There does not seem to be nearly enough time to complete this staged slab span work. 90 days would traditionally be allocated for a project of this size and scope without extraordinary equipment and forces. | An addendum has been issued to change the contract completion time from 60 working days to 67 working days. | Mike Coleman | 3 | 2023-01-03 10:12 | 2023-01-04 14:15
20230110 | 20230110033 | 33 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | We do not anticipate changes. Please bid as shown in the plans. | Mike Coleman | 2 | 2023-01-03 10:56 | 2023-01-04 11:32
20230110 | 20230110006 | 6 | Storm Sewer Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | We do not anticipate changes. Please bid as shown in the plans. | Mike Coleman | 3 | 2023-01-03 11:11 | 2023-01-04 11:32
20230110 | 20230110012 | 12 | Storm Sewer and Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers and culverts shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges - Culvert installations at ADT of 20k or less Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | We do not anticipate changes. Please bid as shown in the plans. | Mike Coleman | 2 | 2023-01-03 11:16 | 2023-01-04 11:33
20230110 | 20230110017 | 17 | Storm Sewer Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and/or IV? | We do not anticipate changes. Please bid as shown in the plans. | Mike Coleman | 3 | 2023-01-03 11:22 | 2023-01-04 11:33
20230110 | 20230110034 | 34 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | We do not anticipate changes. Please bid as shown in the plans. | Mike Coleman | 1 | 2023-01-03 11:27 | 2023-01-04 11:33
20230110 | 20230110002 | 2 | HMA Pavement from STA 1170+50A - 1171+50A | Looking through the plan the typical say the HMA will be 4HT with V-Oil and the MQ's show 4SMA V-Oil. Just trying to get clarification on which type of mix it will be exactly? | The MQ sheet will be revised by an addendum. The correct item is listed in the proposal and rest of the plan. | Mike Coleman | 4 | 2023-01-03 11:34 | 2023-01-05 06:12
20230110 | 20230110023 | 23 | Asphaltic surface | The construction details for the culvert crossings on STH 54 show no definition of mix type or depth. Could this be provided and be changed to asphaltic surface, as these will be done prior to any test strip being done? On STH 76, HMA has quantity for both 3 LT and Asphaltic Surface in the culvert crossing areas. Can this be changed to all asphaltic surface? | An addendum will be issued to provide clarification at culvert crossings patches. | Mike Coleman | 4 | 2023-01-03 14:16 | 2023-01-04 14:31
20230110 | 20230110002 | 2 | Que Warning System | The state put the standard QWS schematic in the spec but they don't call it out in the bid items or the traffic control summary? Any idea if there is an anticipation of the QWS being used? | The Basic Traffic Queue Warning System will be utilized for this project and the plans and special provisions will be revised to clarify this by addendum. | Mike Coleman | 5 | 2023-01-03 14:26 | 2023-01-05 06:12
20230110 | 20230110037 | 37 | Traffic Control | Once the detour is up for 48, can we hard close the area overnight for the work area for the culvert. | Once the detour is in place, continuous/hard STH 48 closures may remain overnight at a maximum of two culvert replacement locations at one time as outlined in the special provisions. | Mike Coleman | 2 | 2023-01-03 15:34 | 2023-01-04 10:16
20230110 | 20230110012 | 12 | Soil Borings | Can you please provide soil borings for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/f5ml96zh200mwsrn5yt8alzka5ewcodp or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-01-03 15:37 | 2023-01-04 10:32
20230110 | 20230110012 | 12 | Grade 2 Granular Backfill | In the earthwork table, there is a note that Marsh excavation can be filled with material other than Grade 2 ,specifically onsite material. Can the undistributed amount ( 8,518) which coincides with the undistributed EBS excavation, be filled with onsite material as well? According to the Quantity tables only roughly 400 tons(earmarked for EBS per cross sections) of the 17,000 Ton of Grade 2 would be needed. | Per the Geotechnical Report, which was included for response #3, - Grade 2 Granular should be used for Marsh Excavation fill and be backfilled to at least 2 feet above the existing ground surface with Grade 2 granular backfill. See additional Construction Detail in plan. - Pit Run should be used for all EBS locations. An addendum will be issued to correct this. | Mike Coleman | 4 | 2023-01-03 15:43 | 2023-01-04 10:56
20230110 | 20230110019 | 19 | Temporary Shoring to Support Northern Existing Culvert Pipe | Please clarify how the Contractor is to support the northern existing 84" culvert pipe used to temporarily divert the stream? Is sheeting that may be needed to support the pipe incidental to the SPV bid item? There is currently no mention of sheeting or shoring for the pipe in the payment section of the SPV item. Thank you. | Any required support for the 84â€ diversion culvert due to excavation for structure C-36-251 is incidental to item 206.2001 as detailed in Standard Spec 206.5.2(2). SPV Temporary Drainage at Culvert is not an applicable bid item for support of the temporary drainage culvert as it relates to structure excavation means and methods. | Mike Coleman | 4 | 2023-01-03 15:51 | 2023-01-05 15:13
20230110 | 20230110002 | 2 | Asphalt Shoulder Repair | The existing asphalt shoulders are in very poor condition, and we believe the asphalt shoulders will require repair prior to opening to traffic each morning. Please if the asphalt repair of the existing shoulders will be incidental or paid for. | At this time the Region does not see a need for an asphalt repair item. | Mike Coleman | 6 | 2023-01-03 17:08 | 2023-01-04 10:12
20230110 | 20230110002 | 2 | Working Days. | Will working days be charged Monday through Thursday night only unless the Contractor works Sunday night? Will a working day be charged even if the Contractor does not work Sunday night? | Due to the work restrictions, the Region would consider Sunday night, Monday night, Tuesday night, Wednesday night, and Thursday night as the normal 5 day work week. | Mike Coleman | 7 | 2023-01-03 17:10 | 2023-01-04 10:14
20230110 | 20230110016 | 16 | Water | Will a bid item for water be added to the contract? | The Bid Item 624.0100 Water will be added to the contract for a quantity of 78 MGAL. This update will be included in Addendum #2. | Mike Coleman | 3 | 2023-01-04 07:09 | 2023-01-04 11:03
20230110 | 20230110043 | 43 | Traffic Control Lane Closures | The SPVs allow lane closures on local roads and on the interstate but no bid items are included for lane closures. Please advise if lane closures are incidental or if bid items will be added. | All lane closures will be incidental to the traffic control item | Mike Coleman | 2 | 2023-01-04 08:12 | 2023-01-06 11:49
20230110 | 20230110034 | 34 | Phase Completion | Can you clarify what work needs to be complete in each phase before moving to the next? For example do all lifts of asphalt need to be completed in phase 1A before moving to phase 1B? | For each phase the underground work, curb & gutter, and asphaltic pavement shall be complete prior to moving to the next stage/phase. Work outside of the curb & gutter does not need to be 100% complete prior to moving to the next stage. | Mike Coleman | 2 | 2023-01-04 08:38 | 2023-01-04 14:17
20230110 | 20230110034 | 34 | Crack and Damage Survey | For the Property at 403 S. Main Street, do you need a Survey on the entire school or just the area of the building directly parallel to STH 13? | The crack and damage survey for the property at 403 S. Main Street (Mellen High School) does not need to include the entire building. The survey should just be conducted for the portion of the building directly parallel to STH 13. | Mike Coleman | 3 | 2023-01-04 08:38 | 2023-01-04 14:21
20230110 | 20230110034 | 34 | Soil Borings | Are there soil borings available? | There were soil borings taken for the retaining wall and bridge structures for this project. The boring info for these structures are included with the structure plans. There were also soil borings taken on the roadway within Mellen. The Geotech reports can be found at the following location: https://wisdot.box.com/s/20odv3judy9bcy7l5zy2cupajygfkrky or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 4 | 2023-01-04 08:44 | 2023-01-04 14:29
20230110 | 20230110034 | 34 | 3MT Quantity | On our takeoff of quantities the 3MT seems light by what we think may be the lower lift on the Parking lanes? | The 3MT quantity seems to check out. This quantity is broken into 2 categories, the 0010 (WisDOT roadway) and 0030 (City of Mellen). The 0030 quantity only covers 8â€™ for the Cityâ€™s parking lane. The remaining width is covered by the main 0010 ID. Also, just for clarity, the parking area thickness is 4.25â€ and the mainline thickness is 6.5â€. | Mike Coleman | 5 | 2023-01-04 10:29 | 2023-01-04 14:31
20230110 | 20230110017 | 17 | Sanitary MH Castings | Item #252 (Adjusting Sanitary Manholes) specifies that new Sanitary MH castings/lids be provided. Can you provide more information on the specific casting that is required? | The description in the specifications calls for reusing the existing casting for Adjusting Sanitary Manholes. This is correct for the project. The basis of payment is incorrect and should be as follows: Payment is full compensation for adjusting the manhole to finish grade; for salvaging existing casting; for furnishing and installing Internal/External seal; and for reinstalling existing casting. An addendum will be issued to correct this. | Mike Coleman | 4 | 2023-01-04 11:33 | 2023-01-04 14:13
20230110 | 20230110017 | 17 | Typical Trench Detail Under Pavements | Page 11 of the plan shows a detail drawing for "Typical Trench Detail Under Pavements". Is this detail for both the culvert pipes and storm sewers that cross beneath the roadways? | The â€œTypical Trench Detail Under Pavementsâ€ on page 11 of the plans is specific to Sanitary Sewer 6-Inch lateral construction at Sta. 191+97, RT. | Mike Coleman | 5 | 2023-01-04 12:01 | 2023-01-05 15:39
20230110 | 20230110026 | 26 | Water | Will a bid item for water be added to the contract? | No, the water item will not be included on this project. Per the Standard Specifications, section 624.5.3, if the contract does not include the bid item Water, then furnishing and applying water is incidental to the other items of work. | Mike Coleman | 2 | 2023-01-04 12:16 | 2023-01-05 15:38
20230110 | 20230110019 | 19 | Cad Files | Are surfaces available for take offs? | No files are available for this project. Contractor Data Packets are not required for Local Program projects. | Mike Coleman | 5 | 2023-01-04 14:14 | 2023-01-05 06:50
20230110 | 20230110036 | 36 | RR Flagging Follow-Up | Even though railroad flagging may only be necessary for a limited amount of time, a cost for the flagging needs to be incorporated into our bid. This is given in the contract documents on all jobs requiring any amount of flagging. How much will the railroad flagging cost per day for this project? Contractors need to have this information in order to properly estimate the flagging costs incurred during construction. | The Spec book says comply with the railroad rules and regulations. It is up to the contractor to find out costs for flagging. Contractor can contact railroad flagging contact in the Special Provisions for the most current costs. | Mike Coleman | 4 | 2023-01-04 14:21 | 2023-01-05 16:49
20230110 | 20230110016 | 16 | Asphaltic Driveways | There is no asphaltic surface driveways and field entrances item on the job. Will one be added per addendum? | An asphaltic surface driveways and field entrances item will not be added to the contract. The payment of work for the paved driveways will be under items as called out in the â€œDriveways and Field Entrancesâ€ and â€œButt Joint Paved Drivewaysâ€ details on page 10 of the plan set. | Mike Coleman | 4 | 2023-01-04 14:48 | 2023-01-06 08:46
20230110 | 20230110019 | 19 | Box Culvert Area | In the box culvert area, there is no section of gravel or Breaker shown for the roadway. Please clarify the section that should be bid. | In the area where the road is removed for the box culvert construction, the typical section will consist of 4â€ of HMA Pavement (1 ï¿½â€ â€“ 4LT 58-28 S & 2 ï¿½â€ â€“ 3LT 58-28 S), 13â€ of Base Aggregate Dense 1 ï¿½â€ and 24â€ Breaker Run, matching the proposed typical section included in the plans for the reconstruction areas. The breaker run should be transitioned from 0â€-24â€ in 25â€™. The aggregates will be paid for as placed per the contract. | Mike Coleman | 6 | 2023-01-04 15:47 | 2023-01-05 15:27
20230110 | 20230110007 | 7 | Construction staking | plan has the item construction staking pipe, which should be construction staking storm sewer 2 | Per specification 650.3.6, staking for appurtenant inlets and catch basins are included under the construction staking pipe culvert bid item. We do not anticipate making any changes, please bid as shown in the plan. | Mike Coleman | 3 | 2023-01-05 08:25 | 2023-01-09 09:57
20230110 | 20230110019 | 19 | Tack on Pulverized Surface | There is a note in the miscellaneous quantities (sheet 34) that states to "Tack pulverized material prior to placing lower layer of HMA pavement". The contractor requests that this requirement be removed. | Please bid tack coat quantity and MQ note as shown in the plans. | Mike Coleman | 7 | 2023-01-05 09:03 | 2023-01-06 09:00
20230110 | 20230110013 | 13 | clearing and grubbing | There are 3 stations of undistributed clearing and grubbing. There is a note in the specials about the clearing from lots 3 and 4 going to the property owner. Obviously the designer knowns where lot 3 and 4 are so why is that stationing not listed ?? How do you expect any contractor to bid on clearing and grubbing by the station without having any idea where the work is? There could be 2 trees or 50 trees. The trees could be under high line wires or other places that make the work difficult. If there is going to be a id item, it should be by the inch diameter | The stations in question are as follows: 21+00 â€“ 22+00 58+00 â€“ 59+00 115+00 â€“ 116+00 (Parcel 3 & 4) | Mike Coleman | 2 | 2023-01-05 09:35 | 2023-01-09 12:06
20230110 | 20230110029 | 29 | HMA | The current design on the plan calls for a single 2" lift of HMA going over the CIR. With the CIR process it is very difficult and not possible in most applications to run slope in the CIR process as you are putting down the same amount of material that you are picking up in the process. Even though the plan calls for 5" being milled and 4" being put back, depending on the current cross slopes the CIR thickness will be constantly varying. This being said, there are currently 1400 tons in the plan for wedging, would the DOT consider dropping the lift thickness to 1.5" and adding more tons to the project to put down a leveling layer before the surface? ALso, with the current design of one lift being placed the thickness of the surface will be variable, which will not be conducive for doing PWL Density on the project. | It is understood that the CIR may have variances after placement, and it was estimated 1400 additional tons would be needed for wedging. If during construction it is determined more wedge material is needed to ensure the planned cross slopes and profile, that would need to be added via a quantity overrun on wedging and directed in the field. The final 2â€ surface should be maintained. The final course should be maintained at 2â€ and any variances to be corrected with the wedging course. | Mike Coleman | 3 | 2023-01-05 10:04 | 2023-01-06 08:55
20230110 | 20230110004 | 4 | Proposal Schedule of Items - Page 6 Missing | In the proposal schedule of items page 6 is missing. Can an addendum be provided to include the full 7 pages of the proposal schedule of items. | The list of items can be found on pages 69 â€“ 71 of the plans and can also be found in Bid Express. We will not be issuing an addendum at this time. | Mike Coleman | 2 | 2023-01-05 10:07 | 2023-01-05 17:09
20230110 | 20230110041 | 41 | Closure Date to Install S-66-401 | Need to request a delivery date for the span or an anticipated Closure Date for the #41 Project. As there are multiple sub-projects under #41, I need to know which one the span will be erected on. One of the docs that you sent over had the USH-45 sub-project highlighted. That has a 90 calendar day, post closure date, before Liquidated Damages kick in. The Overall Completion date for the entire #41 project is 10/31/2023. That does not leave much time to get drawings approved/returned and have the structure fabricated/delivered. | The 90-day closure window is specific to the USH 45 closure for work on ID 1100-43-70. Work on the sign bridge is under ID 3700-43-70 and may occur during any time of the contract so long as it meets the closure windows specified in the Traffic section and occurs before the overall contract completion date. There are Lane Rental Fees associated with the Full Freeway closure for erecting the overhead truss and DMS. | Mike Coleman | 1 | 2023-01-05 10:15 | 2023-01-06 12:28
20230110 | 20230110041 | 41 | B-66-37 Structural Steel for bearing stiffeners | In reference to the structural steel bid item 168 which covers the installation of the stiffener plates at the abutment bearings on B-66-37. Will a CWI be required for inspecting the welds for the new stiffeners to the existing girder ends? | Yes, the stiffener plate field welds are required to be inspected by a CWI. | Mike Coleman | 2 | 2023-01-05 10:37 | 2023-01-06 11:47
20230110 | 20230110026 | 26 | Cattle pass steps | According the SDD 8 F 3-3 it states " Bid as Concrete Steps By the Square Foot" I don't see a line item for Concrete steps, is it incidental to the masonry end walls? | No steps are required for this cattle pass. | Mike Coleman | 5 | 2023-01-05 10:56 | 2023-01-10 10:24
20230110 | 20230110034 | 34 | Retaining Wall Shoring | Does the DOT have any insight on the backfill material/existing boulders present on the backside of the retaining wall that is to be replaced? It appears that there are larger boulders the entire length of the retaining wall that would make driving shoring impractical. | We do not have any insights on the backfill material that was used on the existing structure. There were no soil borings taken behind the wall. The boring logs for the new structure are included in the plan. These were taken near the front face of the wall. There are exposed rocks on the slope behind the wall. It is unknown if these are boulders or exposed shallow bedrock Temporary shoring is designed by the contractor and does not necessarily need to be temporary sheet piling. Depending on what is encountered during excavation, there may be other types or means of shoring that could be used. | Mike Coleman | 6 | 2023-01-05 11:45 | 2023-01-09 10:05
20230110 | 20230110025 | 25 | PWL | In order to build this project to plan staging, and to maintain the flow of cross traffic, and also to pave around structures on this urban job, would the DOT consider eliminating the PWL spec on this project. | The Department will not remove the PWL requirements from the project. | Mike Coleman | 3 | 2023-01-05 11:50 | 2023-01-06 11:51
20230110 | 20230110038 | 38 | Days Are Still Too Few | This job has two stage slab span with parapets and structural approach slabs. Clearly need much more than 67 days. 90 is appropriate, 80 is maybe doable with expedited forces. Parapet work cannot proceed until after deck curing on each stage. This delays structure work for at least 14 days! Comparable Jobs average 90 days. 1175-19-70 was a similar sized job with 100 days allowed and was a beam bridge which allows parapet work to proceed immediately after deck pours. 1430-01-79 was a similar sized job with 80 days allowed, but expedited forces needed to work weekends to meet this deadline. 7070-06-61 was a similar sized job with 60 days allowed, but as a REDECK had 4 less substructures to construct and as a beam bridge allowed parapet work to proceed immediately after deck pours. | An emergency addendum has been issued to revise the contract completion time to 75 working days. | Mike Coleman | 4 | 2023-01-05 12:59 | 2023-01-09 09:59
20230110 | 20230110010 | 10 | CIR Base Repair vs. Undistributed EBS | How will the engineer determine whether to use the undistributed EBS quantity (12,087 CY) or the Base Repair for CIR Layer item outside of the specified station ranges for EBS (562+60-576+80, 656+00-669+20, 682+40-710+12)? | An emergency addendum has been issued to remove the undistributed EBS quantity and the base aggregate, asphaltic surface and breaker run quantitites associated with it. | Mike Coleman | 4 | 2023-01-05 13:45 | 2023-01-09 10:01
20230110 | 20230110010 | 10 | Pipe Crossings | On sheet 12, the construction detail for the cross sectional view of the culvert pipe says to use "trench or native" backfill. The cost of each material varies significantly. Should contractors figure trench or native backfill? | An emergency addendum was issued to remove â€œor nativeâ€ from the backfill note in the legend to clarify the type of material required. | Mike Coleman | 5 | 2023-01-05 14:05 | 2023-01-09 10:02
20230110 | 20230110029 | 29 | CIR Milling Width | It appears that there are several extra wide area/turn lanes that are to get incorporated into the CIR. This will result in several set backs for the CIR train. In addition, the varying widths may result in trouble matching centerline height. Would the DOT consider allowing one uniform width to be milled throughout the project? | The contractor should bid as shown in the plans. | Mike Coleman | 4 | 2023-01-05 15:31 | 2023-01-06 10:33
20230110 | 20230110002 | 2 | Project Design Schedule | Would DOT be willing to share the link for the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/acfphimiyznukklqh4m55944v9148jl2 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 8 | 2023-01-05 17:17 | 2023-01-09 10:13
20230110 | 20230110002 | 2 | Number of Dowel Bars in the Contraction Joints | Will 11 bar or 13 bar units be required in the contraction Joints in the Concrete Replacements? Please note, there are only 8 bars at the construction joints and 13 bars in the aggregate interlocked contraction joints seems like over kill and a waste. | Number of bars required will follow the Standard Detail 13C09-16b located in the plans. | Mike Coleman | 9 | 2023-01-06 07:02 | 2023-01-06 11:22
20230110 | 20230110002 | 2 | Design Schedule | Can the Design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/acfphimiyznukklqh4m55944v9148jl2 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 10 | 2023-01-06 07:03 | 2023-01-09 10:13
20230110 | 20230110036 | 36 | RE: Railroad Flagging Follow-Up | To be clear on RR flagging requirements: Is DOT dictating that the contractor use less than 70' of boom in our crane(s) during construction of the B-27-0169 structure outside of a (less than two week window) during pile driving and demolition operations? | See standard spec 107.17 and article 9 of the special provisions. | Mike Coleman | 5 | 2023-01-06 10:12 | 2023-01-06 11:42
20230110 | 20230110023 | 23 | Grade 2 Granular Backfill Item | Please confirm what the grade 2 granular backfill item on the earthwork summary table is for? | The grade 2 granular backfill will be used to backfill the frost heave grading transition on the bridge approaches shown on the plan and profile sheet. | Mike Coleman | 5 | 2023-01-06 10:39 | 2023-01-09 09:53
20230110 | 20230110038 | 38 | 67 WD's | The addendum added only 7 WD's to the contract which is still insufficient to complete this work. This project should be a minimum of 90 WD's. Will the department consider adding additional time? | An emergency addendum has been issued to revise the contract completion time to 75 working days. | Mike Coleman | 5 | 2023-01-06 10:45 | 2023-01-09 09:59
20230110 | 20230110021 | 21 | Clearing and Grubbing | The plans show 6 trees to be removed as part of items 201.0105 Clearing and 201.0205 Grubbing. The special provisions state that Brown County Highway Dept. will complete the resurfacing of CTH MM in the summer of 2023 with a tentative completion date on May 11, 2023. Section 3. of the special provisions state that the work associated with this contract must be completed within 14 days following the completion of the Asphalt pavement. Finally, the contract completion date is September 1, 2023. Section 3 of the special provisions then state within the Northern Long-Eared Bat paragraph, "no tree clearing is allowed between April 1 and October 31, both dates inclusive." Given the completion date, anticipated schedule for paving operations, and 14 day completion following paving; how does the department anticipate the clearing and grubbing items to occur outside of the April 1 to October 31 window as noted in the special provisions? | Section 3 of the special provisions state that select pavement marking/rumble strip items need to be complete within 14 days after asphalt paving by others. Other items need to be completed prior to the completion date or as the contract requires. It is expected that the contractor will complete tree clearing in March under a conditional notice to proceed. | Mike Coleman | 1 | 2023-01-06 10:56 | 2023-01-09 10:04
20230110 | 20230110041 | 41 | Existing Framing Plans | Can the existing steel framing plans be made available for the bridges to be cleaned and coated? | I am assuming that this question pertains to structures B-66-30/31/32/33/34/35/102/103, is that correct? All of these structures are to be cleaned and painted as part of the 1100-43-70 contract. All of the existing structure as-built plans are available to contractors on HSIS. If the bidder does not yet have an HSIS account, they can self-register for a WisDOT web access management system (WAMS) account, and then they will receive access to existing structure plans via HSIS. (Follow this link https://on.wisconsin.gov/WAMS/home and click on the â€œRegister for a Wisconsin User ID link). | Mike Coleman | 3 | 2023-01-06 18:48 | 2023-01-10 07:11