## qandasearchletting_results
Date: | 2023-02-13
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230214 | 20230214003 | 3 | MGS Thrie Beam | Is there a layout detail for installing 9 LF, 20 LF, and 22 LF of this bid item? Standard drawings show 39.4 LF per installation. | The existing thrie beam will remain in place. An upcoming addendum will address the beam guard quantities. | Jill Fehrman | 1 | 2023-01-12 10:16 | 2023-01-17 16:53
20230214 | 20230214003 | 3 | Exclusion Fencing | The Prosecution and Progress section under Eastern Massasauga rattlesnake state "properly trenched-in silt fence with turn-around ends." The Exclusion Fencing SPV Description states "Silt Fence." The construction detail on page 13 of the plan appears to represent standard silt fence. However, the Materials section is stating woven wire fence, non-woven fabric, and steel posts. Would the Department consider simply using "properly trenched-in silt fence" with posts on the construction side for this bid item? | The materials of the SPV will be revised to exclude metal posts and wire fabric and the construction will be revised to allow for materials to be installed as specified in section 628 (silt fence), however all time restrictions, inspections, maintenance, etc. included in the SPV will remain. An upcoming addendum will be issued to address these revisions. | Jill Fehrman | 2 | 2023-01-12 10:30 | 2023-01-17 16:55
20230214 | 20230214004 | 4 | Erosion Mat Quantities | The MQs shat 7,158 SY of erosion mat IA and 5,785 SY of Urban IB. However, the Barrier System Grade/Shape/Finish item show 7,670 SY of erosion mat IA as incidental to the bid item and numerous plan sheets show the Urban IB in Barrier System G/S/F areas. Have the pay quantities been doubled up? How much erosion mat will be measured and paid for under the erosion mat bid items? | The quantities for erosion mat listed in the Guardrail Summary table were incorrect. The quantities for erosion mat listed in the Erosion Control summary table included the erosion mat quantities that should have been listed in the Guardrail Summary table. The Barrier System Grade/Shape/Finish bid item information will be updated to reflect the proper items and quantities. The quantities for the erosion mat bid items will be updated to remove the beam guard erosion mat quantities. The Landscaping bid items will also be updated to match the proper quantities. The updates and changes discussed above will be submitted in an addendum. | Mike Coleman | 1 | 2023-01-12 10:50 | 2023-01-19 08:29
20230214 | 20230214004 | 4 | Design Schedule | Will the department please provide the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/u6zs9fku2qd47eyjv3b2kg6etzjsxx6b or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-01-18 08:56 | 2023-01-19 09:49
20230214 | 20230214005 | 5 | DISTRESSED PAVEMENT MILLING / ASPHALTIC SURFACE | Is the patching back of the Asphalt for the Distressed pavement milling paid under Asphaltic surface Temporary or is the Asphaltic surface patching item just missing? Thanks, | We will be adding asphaltic surface to the contract. | Mike Coleman | 1 | 2023-01-11 12:45 | 2023-01-12 13:49
20230214 | 20230214007 | 7 | Replacing Guardrail Posts and Blocks | Numerous plan sheets are stating that this bid item is to be used for posts 1 and 2 of existing EAT's on the project. However, FDM 11-45, Section 30.5.2.3, specifically prohibits this bid item being used for this purpose. Will this be changed by addendum? | An upcoming addendum will address this issue. | Jill Fehrman | 1 | 2023-01-12 11:21 | 2023-01-17 16:43
20230214 | 20230214007 | 7 | Stainless flashing detail | Hi, we have strong reservations about the new stainless steel flashing detail. Multiple suppliers have to us that they can't bend flashing in such an intricate manner, which means a custom extrusion or machining a custom drip edge out of solid material. If it could be bent in that shape, the screws would deform it due to the return bends towards the concrete. The flashing would not be able to be overlapped due to the bottom 3/4"x3/4" box detail, and we believe it would catch and retain water and ice. Is there a pre-made extrusion or rolled product that you used as a guide for this profile? if so, can you provide more information? Would the Department consider the use of it's existing flashing detail? | No changes will be made. This type of flashing was requested by the Bureau of Structures and is a new standard flashing. | Mike Coleman | 2 | 2023-01-13 17:08 | 2023-01-20 06:00
20230214 | 20230214011 | 11 | Vegetated Porous Pavement | Is there a product WisDOT has in mind for this item? | The project specification may be met by many products available. Two examples of these products are listed below. Geoblock 5150, manufactured by Presto Geosystems 670 N Perkins Street PO Box 2399 Appleton, WI 54912 (800) 548-3424 VersiGrid H/D 2.0, manufactured by VersiGrid 4020 Rocky Mountain Road Bonner, MT 59823 (406) 552-4918 | Mike Coleman | 1 | 2023-01-16 12:30 | 2023-01-24 08:00
20230214 | 20230214015 | 15 | Design Schedule | Could you please provide a link to the DOT design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/1447wusibkod5npcb7tjcomcj764skae Or click on Supplemental QA Documents link on the February Bid Letting webpage and access the proposal folder. | Jill Fehrman | 1 | 2023-01-12 07:11 | 2023-01-17 17:06
20230214 | 20230214015 | 15 | System Ramp Closures | For EB traffic, nighttime hours, single lane of traffic, what is the westernmost station where traffic can be fully moved to 1 lane without having to close either system ramp? | An upcoming addendum will include a plan detail sheet to clarify the traffic control. | Jill Fehrman | 2 | 2023-01-12 07:15 | 2023-01-17 16:51
20230214 | 20230214015 | 15 | Design Schedule Logic | The design schedule assumes 3,600 tons per night for milling and paving. Apparently, the design schedule logic did not account for an 8-hour closure window and a 6.5 hour or shorter production window for milling, cleaning, tacking, curing, paving and striping. Given that the PWL spec will restrict the contractor to 1 asphalt plant, this production rate is not even physically possible. Please take a second look at the schedule. Perhaps a pre-bid meeting would be worthwhile. | The design team looked into this concern, and also met with the construction team to discuss. First off, the design team did review the time chart and noticed a correction needed for the HMA pavement production rate. The 3,600 was reduced to 2,800. This should help a bit with the concern below. The corrected time chart can be found at the following location: https://wisdot.box.com/s/1447wusibkod5npcb7tjcomcj764skae With the revision above, the consensus is that the schedule is tight but doableâ€¦with production rates similar to the adjacent freeway overlay from 2018 (very similar size and scope), and other recent larger projects here in the region. | Mike Coleman | 3 | 2023-01-18 09:51 | 2023-01-24 08:07
20230214 | 20230214018 | 18 | Completion date | With no asphalt on the project, we would the Department consider moving the 10/15 completion date to 11/1 or 11/15? With the large number of projects bidding with early fish restriction dates, the extra flexibility would be appreciated by the contracting community. | The bridge owner (Town of Washburn) is agreeable to pushing back the completion date. An addendum will be prepared. | Mike Coleman | 1 | 2023-01-13 17:18 | 2023-01-19 08:27
20230214 | 20230214026 | 26 | Radar Detection | Wavetronix radar has been specified as the vehicle detection for this project. The City of Kenosha also uses Econolite Evo radar for vehicle detection. Would it be possible for us to bid the Econolite Evo as an approved equal? | No, the Econolite Evo will not be allowed for this project. The vehicle detection specified in the special provisions should be used. | Mike Coleman | 1 | 2023-01-16 12:45 | 2023-01-19 08:14
20230214 | 20230214035 | 35 | CIR Specifications | Can the special provisions for Item 327.1000.S be updated to the latest revision? Section C.7.3 Surfacing Paragraphs (4) & (5) have been updated/eliminated on other projects. | We will issue an addendum updating this to the new special provision for Item 327.1000.s. | Mike Coleman | 1 | 2023-01-17 10:34 | 2023-01-19 08:30
20230214 | 20230214036 | 36 | Heavy Riprap requirements at Station 286 and 496 | Plan sheets 9 and 10 include notes that indicate Heavy Riprap and HR fabric will be required. There does not seem to be any bid items or quantities for these items at these locations. Could bid items be provided? | An addendum will be issued to address the missing items. | Mike Coleman | 1 | 2023-01-18 09:13 | 2023-01-20 05:58
20230214 | 20230214037 | 37 | Turbidity Barrier Concern | The Q2 elevation and velocity are above the standard guidance for using turbidity barrier on the project. The Q2 elevation is almost 17 feet high, requiring 21-foot turbidity barrier on the south side. Also, the Q2 velocity is stated to be 5.1 fps. Will the Department be willing to require sheeting for at least the south side of the river on this project if not both sides? | The use of turbidity barrier where water flow exceeds 5 ft/s was considered during design. The 5.1 ft/s modeled average can vary significantly across the stream cross section. The turbidity barrier is located close to the stream bank where velocities are lower than the modeled average velocity and the use of turbidity barrier was therefore considered acceptable. | Mike Coleman | 1 | 2023-01-17 08:03 | 2023-01-23 06:31
20230214 | 20230214038 | 38 | CIR Specifications | Can the special provisions for Item 327.1000.S be updated to the latest revision? Section C.7.3 Surfacing Paragraphs (4) & (5) have been updated/eliminated on other projects. | We received a revised STSP with some recent industry changes that were agreed to. We will do an addendum to provide the current industry standard and eliminate the paragraphs in question. | Mike Coleman | 1 | 2023-01-17 10:35 | 2023-01-19 08:17
20230214 | 20230214044 | 44 | CIR Specifications | Can the special provisions for Item 327.1000.S be updated to the latest revision? Section C.7.3 Surfacing Paragraphs (4) & (5) have been updated/eliminated on other projects. | An addendum will be issued to update the language. | Mike Coleman | 1 | 2023-01-17 10:35 | 2023-01-23 06:26
20230214 | 20230214049 | 49 | Staging | Looking for some clarification of the staging for the project from STA 195+00 to 221+50? | Article 4 Traffic and plan pages 111 â€“ 138 (specifically page 124, 127, 130) explain staging at the Main Street/STH 35 Intersection between STA 195+00 to STA 221+50. | Mike Coleman | 1 | 2023-01-16 09:23 | 2023-01-19 08:26
20230214 | 20230214038 | 38 | Design Schedule | Can the Department please provide the preliminary design schedule used for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/gbumecza9nr46xe8dlj0wuo2r8qjwtha or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-01-18 10:48 | 2023-01-20 05:55
20230214 | 20230214031 | 31 | Concrete Cure Time for Methacrylate Sealant | Will the minimum 21 day cure time for concrete in the joint repair areas be waived for placement of the Methacrylate Sealer for this project in order to meet the 90 calendar day schedule? | The minimum 21 day cure time for concrete in the joint repair areas will NOT be waived for placement of the Methacrylate Sealer for this project. The application of the Methacrylate Flood Seal isnâ€™t required to be completed in the 90 calendar days allowed for the long-term single lane closures. | Mike Coleman | 1 | 2023-01-18 11:53 | 2023-01-23 06:24
20230214 | 20230214038 | 38 | Contract Time | Based on scope of work (12 pipe culverts, 2 stages for approach slab & pavement replacement with asphalt patching at the Brule River, removing asphaltic surface milling, CIR with moistures needed before paving, paved lower layer shoulder widenings, HMA Pavement, shouldering, striping & landscaping), Contractor believes the 12 Calendar Day detour, and the overall 35 Working Days allowed are insufficient to construct the project. Would the Department consider allowing 18 Working Days for the detour, and overall contract time at a minimum of 45 Working Days? | â€¢ The detour is lengthy and the 12 days has been selected to reduce road user impacts while also accommodating the work at reasonable rates. â€¢ The only work to be completed under the 12 day detour are the culvert replacements are which generally shallow. â€¢ All other work including patching, approach slabs, etc. can be completed during the detour, but are not required to be completed under the detour. â€¢ The schedule is reasonable for the work operations required. â€¢ Bid the project at 35 days working days. | Mike Coleman | 3 | 2023-01-18 14:50 | 2023-01-23 06:29
20230214 | 20230214015 | 15 | SPV.0060.801, SPV.0060.804 AND SPV.0060.805 | IS THERE A DETAIL DRAWING OR DIMENTIONS AVAILABLE FOR THE INLET COVER 27-M BID ITEM SPV.0060.801? CAN PRECAST FLAT TOPS BE USED FOR CAPPING THE ITEMS IN PV.0060.804 AND SPV.0060.805? | The detail for Inlet Covers Type 27-M is found on Sheet 177. Precast flat top slabs may be used for items SPV.0060.804 and SPV.0060.805, as long as they conform to the details on Sheet 175. | Mike Coleman | 4 | 2023-01-18 15:04 | 2023-01-23 06:27
20230214 | 20230214035 | 35 | Culvert Extension Shoring | What is the Department's intention regarding any temporary shoring necessary in order to perform the culvert extensions? It appears that shoring may be needed in several locations as to not undermine the roadway due to the proximity of the work to the existing pavement. The plan does not call for any temporary shoring at the culvert extension locations and the plan does not state that any necessary shoring is incidental to other items. | In lieu of shoring, the department will add temporary traffic signals for C-35-1959 and C-35-1961 and associated items allowing for closing one lane and maintaining a single lane of traffic. The department will also add concrete barrier precast temporary for C-35-1960 and associated items for allowing the closing of the shoulder. The changes will be submitted in an addendum. | Mike Coleman | 2 | 2023-01-18 17:09 | 2023-01-25 09:17
20230214 | 20230214051 | 51 | PWL #1 | Due to the condition of the exiting road, the variability of the road, vertical alignment, horizontal alignment, underlying soil conditions and other variables specific to this project would the department consider using the QMP Density specification instead of PWL Density on this project? | The department is including an addendum to include the Distressed Pavement Relief â€“ Ride and Distressed Pavement Relief â€“ Density to account for the condition of the existing roadway. | Mike Coleman | 1 | 2023-01-18 21:03 | 2023-01-25 09:25
20230214 | 20230214051 | 51 | PWL #2 | Sheet 35 shows that all lifts in the reconstruct areas are required to be PWL Air Voids and PWL Density. While the overall tonnage on the lower lift is large enough for the test strip tonnages, the tonnage is split between three separate sections. Each section is under the 750 ton required and will not allow enough room to get a proper rolling pattern established or consistent run at the plant. Will the lower lift be changed to QMP or Asphaltic Surface? The second lift of the reconstruct areas is also required to be paved ahead of time before opening the areas up to traffic (per SPV #4, paragraph 2). Similar to the first lift there will not be enough tonnage to establish a test strip. Will these areas be switched to QMP as well or something else? | An addendum will be issued to adjust the HMA Layer over crushed aggregate in the reconstruction sections to Acceptance testing by the Department, eligible for density incentive. We will add item 460.2000. | Mike Coleman | 2 | 2023-01-18 21:05 | 2023-01-25 09:25
20230214 | 20230214051 | 51 | PWL #3 | The upper layer of paving constitutes 1.75â€ paving over 4.25â€ of new pavement in the reconstruct areas, 1.75â€ paving over 2â€ of new pavement/milled surface in the rehab areas, and 2â€ paving over milled surfaces in other areas. Due to all of the different underlying conditions and pavement thickness throughout the upper layer how many density test strips will be required? The reconstruct areas again will not have the tonnage to complete a full density test strip. By this time a volumetric test strip will have been completed so that is not an issue. | We will remove the test strip over base aggregate via an addendum. | Mike Coleman | 3 | 2023-01-18 21:06 | 2023-01-25 09:25
20230214 | 20230214051 | 51 | HMA Shoulders | A note on sheet 4 in the plans state to always pave 2â€™ for the new shoulder. Many areas on this project do not have much more than a 2 foot existing gravel shoulder. Per 450.3.2.11 the safety edge is required which requires additional paving width to construct the taper. Will the safety edge be excluded for constructability issues or will the asphalt shoulder be narrowed as needed to allow room for the safety edge? | The 2â€™ shoulder and safety edge are both required. Additional Base Aggregate was included for areas where the existing shoulder may not be wide enough to account for both. The tie in point is anticipated to be the existing subgrade shoulder point. | Mike Coleman | 4 | 2023-01-18 21:07 | 2023-01-25 09:26
20230214 | 20230214051 | 51 | HMA Shoulder Density | Due to the existing shoulder material, underlying soils, widths, vertical alignment and horizontal alignment of this road density on the HMA shoulders will likely be marginal at best and pose increased risk. The plan states a 2â€™ widening over gravel on an existing 2â€™-4â€™ shoulder, essentially leaving little to no gravel shoulder left to support the unconfined edge and keep the HMA from pushing out under the compaction of the rollers. We ask the department to consider ordinary compaction per 450.3.2.6.2 for the HMA shoulders on this project. | Discussions with Central Office resulted in the inclusion of Acceptance Testing by the Department for the shoulder areas following standard nuclear density testing procedures. | Mike Coleman | 5 | 2023-01-18 21:08 | 2023-01-25 09:28
20230214 | 20230214051 | 51 | Prosecution & Progress - Milling | In SPV 3, paragraph 6 it states that the lower layer of HMA pavement shall be placed on milled surfaces within 72 hours. What about the areas that are only getting milled 2â€ and an upper layer of 2â€? Will the restriction be waived in these areas so that all milling and the entire lower layer can be completed prior to starting the upper layer or will the mill have to mobilize back for these sections prior to the upper layer paving to meet the 72 hour requirement? | Rehab (3.75â€ overlay) consists of 2-inch lower layer HMA with 1.75â€ upper layer HMA. Rehab (2.00â€ overlay) consists of 2-inch upper layer HMA. We anticipate that the 2-inch HMA layer will be placed continuously, regardless of whether it is serving as a lower layer or upper layer (same test strip as noted in MQ). The 1.75-inch HMA layer would be constructed after this 2-inch lower layer, using butt joints on the surface 1.75-inch lift to match into the 2-inch upper layer rehab (2.00â€) sections. The 10 day/72 hour requirement would apply to all milled sections. The quantity of butt joints will be modified via addendum to include these joints. | Mike Coleman | 6 | 2023-01-18 21:10 | 2023-01-25 09:36
20230214 | 20230214051 | 51 | Shaping Shoulders | On Sheet 34, the Shaping Shoulders item only accounts for the stations within the reconstruct areas. Based on the rehab typicals on sheet 4 the quantity should be increased to cover the entire project or another item needs to be added for shaping the shoulders to widen the pavement. | This work is covered under the item Prepare Foundation for Asphaltic Paving. The Shaping Shoulders item is only in the areas of the 2 inch mill and 2 inch pave sections. | Mike Coleman | 7 | 2023-01-18 21:11 | 2023-01-25 09:45
20230214 | 20230214051 | 51 | Misc Repairs - HMA Quantities | On Sheet 34, Asphaltic Surface shows 500 ton under misc. repairs and Asphaltic Surface Patching shows 100 ton under misc. repairs. There is also 50 ton under minor repairs which is for ramping, potholes, and pop-outs. Can you clarify what the misc. repairs are for and which will be paid under Asphaltic Surface and which will be paid under Asphaltic Surface Patching? | The work for the additional 500 tons of Asphaltic Surface is for wedging and leveling, spot lane failures, and edge repairs in larger areas under the assumption that a paving machine would be required. The 100 tons of Asphaltic Surface Patching is for smaller pop outs, ramping, and other repairs in smaller areas under the assumption that these will be hand placed. | Mike Coleman | 8 | 2023-01-18 21:12 | 2023-01-25 09:46
20230214 | 20230214051 | 51 | MTV | There is no item for a Material Transfer Vehicle. Typically this is required for the surface lift. | An Addendum will be issued to include the use of a Material Transfer Vehicle. This will be required for all surface lifts (Reconstruction 1.75â€ upper layer, Rehab 1.75â€ upper layer, and Rehab 2â€ upper layer. | Mike Coleman | 9 | 2023-01-18 21:13 | 2023-01-25 09:46
20230214 | 20230214051 | 51 | Asphalt Driveways | Sheet 6 of the plan shows Removing Asphaltic Surface for private entrances. It does not appear the quantity is accounted for in the miscellaneous quantities on sheet 32. Another option that could be considered is adding Removing Asphaltic Surface Butt Joints quantity to mill and overlay the driveways. | Will include additional quantity for removing asphaltic surface for these areas in the addendum. | Mike Coleman | 10 | 2023-01-18 21:14 | 2023-01-25 09:47
20230214 | 20230214051 | 51 | Temp Paint | On Sheet 40 there is 137,280 LF of Temporary Marking Line Paint 4-inch for centerline on the surface lift prior to rumble strips. Should this quantity be switched to Temporary Marking Line Epoxy 4-inch? | We agree that since this project is not an SMA, the upper layer (pre-rumble) should be changed to Epoxy. This will be included in the addendum with a note to match the same dimensions for permanent epoxy dimensions. | Mike Coleman | 11 | 2023-01-18 21:15 | 2023-01-25 09:48
20230214 | 20230214051 | 51 | PCMS | Due to the horizontal and vertical alignment of this project there are numerous blind spots and concerns related to flagging operations, site distance and safety. Could PCMS boards be added to the project to warn motorists on days flagging operations are occurring? | A PCMS is not required per the standard detail drawing. Additional safety measures can always be proposed and/or implemented by the contractor during construction. It is anticipated that flagging work will be completed while through traffic is detoured. | Mike Coleman | 12 | 2023-01-18 21:17 | 2023-01-25 09:48
20230214 | 20230214051 | 51 | Lane Width | When milling and paving an 11 foot lane with is required to be maintained which is possible if using the existing 2 foot gravel shoulder. This road does not have good shoulder slopes and poor conditions exist in locations on the shoulder edges. When paving the first lane a notched wedge joint is required which puts the paving operation 1 foot into the existing lane plus the equipment needed for automatics. Temp paint is also typically offset to accommodate the paving joint- which may not be possible due to the existing lane widths. The department may consider posting a restricted lane width during milling and paving operations for safety. Breakup of the lower HMA layer over the gravel shoulder may also be a concern when paving the upper layer(s). | It is anticipated that the work requiring flagging will be completed while the road is closed to through traffic. The department normally doesnâ€™t post width restrictions on roadways closed to through traffic. We would consider posting additional lane width restriction signing outside of the full road closure timeframe. | Mike Coleman | 13 | 2023-01-18 21:23 | 2023-01-25 09:50
20230214 | 20230214035 | 35 | Temporary Shroing | Was temporary shoring considered for the box culvert barrel extensions? Tie in points are in close proximity to the existing beam guard. | In lieu of shoring, the department will add temporary traffic signals for C-35-1959 and C-35-1961 and associated items allowing for closing one lane and maintaining a single lane of traffic. The department will also add concrete barrier precast temporary for C-35-1960 and associated items for allowing the closing of the shoulder. The changes will be submitted in an addendum. | Mike Coleman | 3 | 2023-01-19 08:27 | 2023-01-25 09:17
20230214 | 20230214031 | 31 | Gawk Screen | Is this Gawk Screen a proprietary item? I have checked with manufacturers and suppliers and not one has the gawk screen that is to the WISDOT specifications shown and none have a crash testing certification for it. Will the state allow an alternative item such as glare screen? | The Gawk Screen Item is not intended to be a proprietary item. The material needs does not require crash testing certification. Alternative Glare screen will not be allowed. | Mike Coleman | 2 | 2023-01-19 14:34 | 2023-01-25 11:13
20230214 | 20230214038 | 38 | 96 hour Window | In the special provision #3 Prosecution and Progress it states that once the CIR is complete the HMA needs to be placed within 96 hours. In the special provisions the CIR specification states the HMA Paving is not to start until the moisture content is 2.5% or below (Section C.7.1). The question is when does the clock start for the 96 hours, once the CIR is laid and compacted or once the moisture content is reduced to 2.5%. | An addendum will be issued to remove the 96 hour requirement in the prosecution and progress. The contractor will need to follow the 10 day requirement per the CIR special provision. | Mike Coleman | 4 | 2023-01-19 15:19 | 2023-01-25 10:46
20230214 | 20230214038 | 38 | CIR Construction | In the note box on sheet 5 of the plans it states that â€œAlternate Methods and Depths of Milling maybe utilized by the contractor if approved by the engineerâ€. Would milling 2.5â€ at centerline at a 2% in the tangent sections and CIR 4â€ at Centerline at a 2% (4â€) in the tangent sections be an approved method? This is exactly the same process that is being done in all the curves on this project. | The intent of the suggested milling depths in the table is to provide the contractor an option to remove the necessary volume of existing asphaltic pavement and remove shoulder aggregate material that should not be mixed into the CIR material. It is anticipated that a uniform milling depth may not result in the required CIR depth across the variable widths proposed along the project. Alternate methods will be approved if the contractor can demonstrate the CIR specification can be met and that the finished product will match the proposed typical section as shown in the plans with the following requirements: â€¢ Finished CIR depth and width â€¢ The finished edge of pavement surface does not result in a raise over the existing conditions. The existing side slopes do not allow for any profile raise. | Mike Coleman | 5 | 2023-01-20 10:12 | 2023-01-24 09:35
20230214 | 20230214038 | 38 | Prepare Foundation for Asphaltic Shoulders | In reference to the Item â€œ Preparation Foundation for Asphaltic Shouldersâ€ can the project be constructed by using the existing CABC that is below the existing HMA Shoulder Widening in the CIR mixture? If not, is the design intent to core out 4â€ by ~ 2â€™ onto the outside shoulder to be used to build the finished CABC Shoulder? If the existing cored out material is used to build the finished shoulder and there is not room for all the material on the shoulder would the excess be allowed on the foreslope? | â€¢ The existing base aggregate below the existing HMA Shoulder Widening should not be mixed into the CIR process per the CIR specification. â€¢ The intent of the suggested variable milling depth table is to utilize the milling operation to remove the existing aggregate material volume under the existing HMA Shoulder Widening that is not needed for the CIR process. The contractor may choose to remove the existing paved shoulder and the underlying aggregate with another method if they propose to change the milling approach. The item Prepare Foundation for Asphaltic Shoulders is intended for the preparation/shaping of aggregate foundation after existing shoulder removal and shaping of the finished aggregate material on the unpaved portion of the shoulders. â€¢ Use of the hauling excess material item is not anticipated with the current proposal. Disposal of excess material is incidental to preparation items per 211.3.6. â€¢ Excess material will not be allowed to be wasted on the fore slopes since existing side slopes are steep and ditch capacities are small. | Mike Coleman | 6 | 2023-01-20 10:13 | 2023-01-24 09:37
20230214 | 20230214037 | 37 | Schedule | Please provide the estimated schedule for completing this structure in 50 working days. 50 working days does not seem sufficient for this structure. | The design schedule can be found at the following location: https://wisdot.box.com/s/1p0mxskydn646ab5crwukousm35cdg2f or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. The region design and construction personnel looked at similar projects and schedule concerns were non-existent. The region feels 50 working days is sufficient. | Mike Coleman | 2 | 2023-01-20 16:41 | 2023-01-23 10:18
20230214 | 20230214038 | 38 | Design Schedule Follow-Up | The design schedule posted in the link provided in the previous question is a schedule for STH 60 in Dodge County. Can the department please provide the correct design schedule for proposal #38, for STH 55 in Forest County? | You are correct. I posted the wrong project schedule. I have posted the correct one now. The design schedule can be found at the following location: https://wisdot.box.com/s/gbumecza9nr46xe8dlj0wuo2r8qjwtha or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2023-01-23 08:38 | 2023-01-23 10:08
20230214 | 20230214017 | 17 | Damage inspection report | Can the damage inspection report listed under the general notes on sheet 2 of the plan for B-40-360 be made available? | The damage inspection report can be found at the following location: https://wisdot.box.com/s/oaigwhenkzpq2zx9y49y1moesubljata or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-01-23 13:42 | 2023-01-24 09:41
20230214 | 20230214003 | 3 | Pavement Markings | Good morning, What is the plan for pavement markings during paving on the surface layer? It appears there is temporary for the milled surface and a regular epoxy (centerline) for the upper layer which is not required to be placed same day. Should the regular epoxy item be changed to a same day item? Will an addendum be issued? Thank you. | The final epoxy centerline will be revised to the same day item. An addendum will be forthcoming to address this. | Mike Coleman | 3 | 2023-01-24 07:42 | 2023-01-27 09:08
20230214 | 20230214019 | 19 | 8-1/2 Pavement | Where is the 8 1/2 pavement. That is Pav 4 in the legend. | The 8-1/2â€ concrete pavement is for the raised concrete crosswalks. The minor sideroads have the raised concrete crosswalks (107th St, 106th St, 105th St, 103rd St, 102nd St, 101st St and 100th St) . The areas are indicated on the plan details as PAV4. The construction detail for the raised concrete crosswalks is shown on p11. | Mike Coleman | 1 | 2023-01-24 09:24 | 2023-01-24 11:25
20230214 | 20230214009 | 9 | 3. Prosecution and Progress - work shall start no later than 4-3-23 | Per special provision article 3. Prosecution and Progress - work shall start no later than 4-3-23, unless otherwise approved by the engineer. This is a 90 working day contract which is about 5 months of work - working 5 days a week with weather accounted for (less than 4.5 months if working 6 days a week), so if the work starts in early April the work will be completed by Early September leaving 2.5 months on the normal construction season available. Will the engineer approve a later start date if the contractor can show all work being completed within the 2023 construction season, like early June after the Memorial Weekend? This will give the contractor the opportunity to preform grading activities in the summer months vs the spring months which will lower costs by being more productive with less delay because of poor weather, which will lead to less EBS and Backfill ($$). By allowing this flexible start time, the bidding contractors will be able submit more competitive bids. | There is a second project, on CTH M, that is scheduled for that season. Extensive coordination between the two project teams and the local municipalities was completed to minimize the overlap of the two projects and minimize impacts to the traveling public in this area. Start work no later than 4-3-23 will remain. | Mike Coleman | 1 | 2023-01-24 09:34 | 2023-01-24 13:39
20230214 | 20230214010 | 10 | Shoulder Paving 7062-02-73 | For STA 128+60 to STA 881+89, what is the desired finished HMA shoulder dimension in this area? Dimension arrows are unclear on the typical sections (sheet 5), not sure if 3.5 foot or 4 foot shoulder is shown? Plan notes on sheet 16 & Sheet 40 (Start and stop annotations) indicate a 3 foot paved shoulder. Please advise. Thanks | For STA 128+60 to 881+89, the finished HMA shoulder dimension shall be 3 ï¿½â€™. Refer to typical section note ï¿½ for clarification of ï¿½â€™ dimension. Plan notes on sheets 16 and 40 (start/stop annotations) should correspond to typical section dimensions: mill ï¿½â€™, pave 3 ï¿½â€™. An addendum will be issued containing revised plan sheets. | Mike Coleman | 1 | 2023-01-24 10:47 | 2023-01-27 07:16
20230214 | 20230214010 | 10 | Centerline Joint Milling 7062-02-73 | Will the contractor be allowed to broom fines from the centerline milling operation out to the shoulder and deposit them on the CABC shoulder? Or will it be required that this material is picked up and hauled off the project? | Per 2023 Standard Spec 204.3.2.2.2(1), the contractor is permitted to incorporate suitable material into the work. Fines from milling operations shall not be placed on finished shoulders. | Mike Coleman | 2 | 2023-01-24 10:48 | 2023-01-27 07:22
20230214 | 20230214038 | 38 | Prosecution & Progress | Article 3 of the Special Provisions states, â€œMaintain the CIR surface with daily or regular maintenance and rolling and pave lanes carrying through traffic within 96 hours.â€ This language makes the project non-constructible; the curing process for the CIR layer often takes 3-4 days to achieve proper moistures, and would inherently force the contractor beyond the 96 hours allowed to cover the CIR layer with HMA. Other CIR projects in the state have moved to allowing 10 days to pave the HMA over the CIR layer, after the curing process. Would the Department please revise the special provisions to match the timeframes allowed in standard CIR contracts, and revisit extending the allowable contract time to allow for adequate curing time between the CIR process and the paving process? | An addendum will be issued to remove the 96 hour requirement in the prosecution and progress. The contractor will need to follow the 10 day requirement per the CIR special provision. | Mike Coleman | 8 | 2023-01-24 14:34 | 2023-01-25 10:47
20230214 | 20230214038 | 38 | Shoulder Aggregate Material | Please clarify the intent for the aggregate material below the existing 2-inch asphaltic pavement shoulders. The note on Sheet 5, infers that a portion of this material is intended to be removed under the Rem. Asph. Surf. Milling item, with a portion of it remaining to be incorporated into the CIR layer, per: â€œSuggested milling depths provided in the table below are intended to remove excess volume of existing asphaltic pavement and underlying shoulder aggregate material not needed during the CIR processâ€¦â€. Removal of this volume of material is beyond the scope of the Milling item, 204.0120. Previous answers contradict the typical section notes indicating that in some areas, aggregate course will need to be incorporated into the CIR layer. Is the designerâ€™s intent to excavate and remove this aggregate from site, or re-use it as shoulder aggregate under 211.0400, or incorporate into the CIR layer? The existing road may not be wide enough to store this aggregate during construction. | Aggregate will only be incorporated in the CIR layer if it is encountered within the originally constructed 11â€™ paved lanes. This will only occur in locations where the combined milling depth and CIR depth are deeper than existing asphaltic pavement. The coring and GPR data are included in the plans for review of potential locations. The contractor should not incorporate the shoulder aggregate into the CIR per the CIR specification. The existing shoulder widths and side slopes will likely prohibit the permanent placement of surplus material excavated under item 211.0400 (Prepare Foundation for Asphaltic Shoulders). Removal surplus material disposal will be incidental to item 211.0400 per standard spec 211.3.6. An addendum will be issued to address these clarifications. | Mike Coleman | 9 | 2023-01-24 15:06 | 2023-01-26 07:27
20230214 | 20230214038 | 38 | Roadway Width Changes | The proposed typical sections indicate pavement width changes which can create ride quality issues with a CIR layer. The existing typical section indicates a typical pavement surface extending 13-ft each side of centerline from STA 0+83 to 287+35. However, the proposed typical shows narrowing the pavement width from 13-ft to 12-ft right of centerline from STA 212+75 to 287+35, and also shows widening to 14-ft left and right of centerline from STA 60+50 to 82+50. Would the department consider revising the plans to maintain a constant width CIR layer at 13-ft each side of centerline from STA 0+83 to 287+35 (this is typical in CIR projects)? Constructability and ride quality issues could be mitigated with this change. | â€¢ The finished typical section is not narrowing the existing paved roadway in any location. â€¢ The note and symbol on the existing typical section indicates â€œno paved shoulder from STA 212+00 - STA 287+35â€. Within that station range the existing paved width (at the surface) is a total of 24â€™ wide which also matches the proposed width. â€¢ The existing paved roadway widths are dictating most changes in CIR width shown in the plans. The finished roadway width will match the existing paved width except at select locations shown in the plan. â€¢ The variations in CIR widths will be removed at the guardrail locations and a short segment through Alvin (approximately 440â€™) to allow for a more uniform CIR through these areas. An addendum will be issued to address these changes. â€¢ The other variations in CIR width will remain since they are required to meet project needs. â€¢ If ride quality is a concern, the leveling layer could be used to reduce those issues at the remaining CIR width change locations. | Mike Coleman | 10 | 2023-01-24 15:08 | 2023-01-26 07:28
20230214 | 20230214038 | 38 | Typical Section Constructability | The proposed typical section is not constructible. The proposed typical section with variable mill depths laterally will result in variable depth CIR, which will likely yield inconsistent compaction across the mat. Contractor recommends eliminating the laterally variable milling depths (beveled from 0â€ at centerline to the variable 4â€ to 5.5â€ at 11â€™ Lt or Rt), and instead profile milling each lane to a depth of 2.5â€ at a target 2% slope (as has been done in previous CIR jobs), followed by a consistent-depth CIR layer at the proposed final slope (as has done in previous CIR jobs), upon which the leveling layer and final HMA surface can be paved. | The intent of the suggested milling depths in the table is to provide the contractor an option to remove the necessary volume of existing asphaltic pavement and retain the required volume to complete the CIR layer. It is anticipated that a uniform milling depth may not result in the required CIR depth across the variable widths proposed along the project. If an alternative milling is proposed with a uniform 2% milled cross slope, it is anticipated the milling depth may range from 2" to 2 3/4" depending on the finished width of CIR layer. Alternate methods will be approved if the contractor can demonstrate the CIR specification can be met and that the finished product will match the proposed typical section as shown in the plans with the following requirements: â€¢ Finished CIR depth and width â€¢ The finished edge of pavement surface does not result in a raise over the existing conditions. The existing side slopes do not allow for any profile raise. | Mike Coleman | 11 | 2023-01-24 15:11 | 2023-01-26 07:29
20230214 | 20230214038 | 38 | Date Constraints for Start of Work | Would the Department consider removing the date constraints of July 17th for the start of the Detour, and/or the Start-by date of July 31st, to allow the contractor(s) more flexibility throughout the construction season? | The detour cannot be implemented prior to July 17 due to a Michigan DOT project along the detour route. An addenda will be issued to remove the July 31 date. However, please recall the CIR specification has a September 15 and temperature requirements that will dictate some project operations. | Mike Coleman | 12 | 2023-01-24 15:15 | 2023-01-26 07:25
20230214 | 20230214035 | 35 | CIR Depth | The CIR on this project is specified to be â€œFull Depthâ€ and relayed to 2% cross slope. Core data provided shows up to 2.75 inches in variation of thickness in the existing asphalt, even with the outliers excluded from the average. Milling during the CIR process to the full depth of the asphalt will create several constructability issues, to name a few: 1. non-uniform depth of cut will lead to poor ride quality, with a single lift HMA overlay following the CIR this will be a large issue 2. It is likely that existing pavement thickness varies from one side of centerline to the other, which will lead to a centerline miss-match as CIR is performed one lane at a time. 3. Some of the existing pavement depths are greater than what can be processed with a CIR train in a single pass of the equipment. Given these issues, can the CIR on this project be changed to a uniform milling depth of 4 inches across the 15 foot lane? | CIR depth will be changed to 3â€ on all three projects. Revised typical sections and quantities will provided in an addendum. | Mike Coleman | 4 | 2023-01-24 15:33 | 2023-01-30 08:27
20230214 | 20230214035 | 35 | Paving Fabric in CIR | For STA 480+82 to STA 505+82 can the CIR depth be reduced to avoid encountering the waterproof membrane, which is sitting directly on the concrete pavement? For STA 505+82 to STA 530+82 at what depth is the existing waterproof membrane? Is it possible to avoid milling into this membrane by reducing CIR depth? | At STA 480+82 â€“ 505+82, the CIR depth will be reduced to 3-inches to avoid disturbing the waterproof membrane sitting on the concrete pavement. At STA 505+82 â€“ 530+82, the asphalt will be milled 1 3/4 inches and resurfaced with 4-inches of HMA. Revised typical sections and miscellaneous quantities will be provided through an addendum. | Mike Coleman | 5 | 2023-01-24 15:34 | 2023-01-30 08:16
20230214 | 20230214009 | 9 | Soil Borings | Are there any soil borings available within the project limits? | The soils report can be found at the following location: https://wisdot.box.com/s/11t8gorpvj5argidifr12xl8o7xhew93 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-01-25 13:53 | 2023-01-30 08:25
20230214 | 20230214010 | 10 | Cold Weather Pavement Markings | Good afternoon. In looking at the cold weather pavement marking bid item, typically this item would be removed and replaced in the spring once weather allows. In this case, with the center line having rumbles, it is impossible to remove the entire cold weather marking, even with a water blaster, without compromising the integrity of the road. What is the department's expectations with this item(if it is deemed necessary) in terms of removal? Would just the marking on the surface need to be removed? Thank you. |  |  | 3 | 2023-01-25 16:28
20230214 | 20230214015 | 15 | Egress and Ingress | The plans allow for daytime work in stage two. To complete the work in the short duration allowed around 500 truckloads of material will need to be exported or imported each day. This will significantly affect traffic. Please confirm that safe access will be allowed during daytime hours for up to 500 truckloads of material. | Yes, access will be allowed during daytime hours. Ingress/egress details and and associated information can be found in the planset on pages 68 and 79 and in the special provisions, article 74. | Mike Coleman | 5 | 2023-01-25 18:42 | 2023-02-02 07:16
20230214 | 20230214015 | 15 | ASPHALT SURFACE COURSE STAGE TWO | To construct the permanent wall, the asphalt surface will need to be installed. There is a note that states asphalt sawing for light base installation is incidental to the light base. Is the intent to install asphalt prior to the transitions and light bases being installed? If so will the department be paying for the asphalt and common excavation under the contract bid items? | The intent is that concrete transitions, bases, anchors, etc., would be constructed first. Both asphalt layers would then be placed to match. And then, the standard barriers would be poured on top of the surface layer of asphalt. If the contractors means and methods vary from this approach, extra asphalt, sawing, and/or common excavation, would not be paid for. | Mike Coleman | 6 | 2023-01-25 18:51 | 2023-02-02 16:05
20230214 | 20230214015 | 15 | Schedule Logic | You referred to the 2018 project as "similar". Are you aware that that project bid 13 weeks earlier and started 7 weeks earlier? That project allowed for 20 weeks from start thru stage 2 rather than 13 weeks. That project allowed for 2 lanes of traffic SB for the entire 20 weeks. That project allowed for single lane closures from 7PM until 9:30PM. That project had only 2/3 the pavement quantity in thru stage 2. The scope may be similar but the design schedule certainly is not. | We discussed internally again with the construction team. Though the schedule is tight, we feel it is still manageable. During design we did extend the allowable closure hours to better match recent freeway projects. We donâ€™t anticipate any revisions being made to schedule and closure hours (other than the updated time chart shared previously) prior to the Let. | Mike Coleman | 7 | 2023-01-26 07:47 | 2023-01-30 08:28
20230214 | 20230214015 | 15 | Relocate Sign Bridges | Can you provide and/or direct me to the as-builts for the sign structures to be moved: S-40-410, S-40-413, S-40-801, S-40-869, and S-40-870? We haven't been able to locate them on the Structures Website. Specifically, we need the hardware and anchor bolt sizes that need to be replaced. | The sign bridge as-built plans can be found at the following location: https://wisdot.box.com/s/1447wusibkod5npcb7tjcomcj764skae or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 8 | 2023-01-26 09:07 | 2023-01-31 07:00
20230214 | 20230214016 | 16 | Pavement Markings | Good morning, With the requirement to have temporary pavement marking at the end of every working day when milling or paving removes or covers the existing centerline pavement marking, it appears you have enough temporary paint for the lower layer but do not have an item that provides for same day marking on the upper layer. There is a regular epoxy item but not a same day epoxy item. Will an addendum be issued to change the centerline markings on the surface to same day epoxy rather than the regular epoxy item? Thank you. | I have reviewed the question and discussed with the LPA â€“ Eau Claire County. To address this question, it was agreed that the temporary pavement marking should be removed from the plans and specs. The requirement for marking to be completed at the end of every day should be removed. Regular epoxy should be all that is required. An addendum will be issued. | Mike Coleman | 1 | 2023-01-26 09:58 | 2023-01-30 08:30
20230214 | 20230214004 | 4 | Stabilized Base Reclamation SPV.0180.01- Gradation Requirement | This project requires all existing asphalt is milled off of the roadway, leaving base course behind (either virgin CABC or reprocessed asphaltic base). The Base Reclamation process will use a pulverizer to mix asphalt emulsion into this existing granular base. A pulverizer is not capable of sizing an existing granular material, the sizing action of a pulverizer is dependent on the cutting action of teeth on the drum into an existing layer of pavement. Since the contractor has no ability to know what the exact sizing of the existing granular materials are on this project, can the B.2 requirement for 100% passing the 2â€ sieve be removed? | The specification will not be changed. This requirement does not apply to existing base aggregate. The specification only applies to RAP material and pulverized/processed remaining pavement. | Mike Coleman | 3 | 2023-01-26 10:46 | 2023-02-03 06:26
20230214 | 20230214004 | 4 | SPV.0195 Asphalt Stabilizing Agent Quantity | It appears the Asphalt Stabilizing Agent quantity is vastly overstated. Plans and specs require either 5.5% emulsion (virgin CABC areas) or 4.0% emulsion (reprocessed asphaltic base sections). Based on take offs the plan oil quantity of 4,442 Tons provides for an average application rate of 7.2% emulsion over the project. Is this a calculation error? If not, what is the intent of the extra emulsion? | An additional undistributed quantity was originally included to account for the tonnage with water weight included. Based on further discussion with industry experts familiar with this base stabilization operation, additional weight for water in the emulsion is typically not included with the reported emulsion tonnage. The undistributed quantity of Asphalt Stabilizing Agent will be removed in an upcoming addendum to reflect this direction. | Mike Coleman | 4 | 2023-01-26 10:47 | 2023-02-03 06:26
20230214 | 20230214004 | 4 | Base Stabilization/Milling Traffic Restrictions | Being this project is closed to traffic & detoured can the restrictions for milling and base stabilization within the same lane and same day be removed? Placing three operations into a single work zone (milling, base repair for Stabilized base reclamation layer & Stabilized Base reclamation) will hinder production of all operations. The design schedule for the project does not show milling, base repair and stabilized base reclamation occurring 100% concurrently. | Base stabilization timing requirements will be relaxed to have to take place within 48 hours of the milling operation. Special provision language updates will be issued in an upcoming addendum. | Mike Coleman | 5 | 2023-01-26 10:48 | 2023-02-03 06:29
20230214 | 20230214004 | 4 | Base Repair for Stabilized Base Reclamation | Prosecution & Progress under base stabilization and paving operations states: the engineer may waive same day requirements for base repair and stabilized base reclamation, and in doing so, the contractor then assumes responsibility for the integrity of the base material until stabilization is complete. Since the contractor has no control over the amount of base repair required or the condition of the existing base course, wouldnâ€™t it be better to allow local traffic a window of time on the existing base course to expose areas needing base repair prior to performing the stabilized base reclamation (in that case DOT saves the expense of having to purchase & install emulsion in areas that will likely fail, as The stabilized base reclamation process will not cure or limit failures from poor subbase materials)? | The Department will be responsible for any weak spots discovered in a proof roll immediately following milling operations. The contractor would be responsible for any damaged areas caused by their equipment thereafter. Special provision language updates will be issued in an upcoming addendum. | Mike Coleman | 6 | 2023-01-26 10:49 | 2023-02-03 06:30
20230214 | 20230214012 | 12 | B-11-175 Abutment Concrete Qty | The abutments for the B-11-175 structure are almost identical in size but the estimated qty table shows that the south abutment is 70.1CY whereas the north abutment is 56.0CY. Please advise if the north abutment concrete volume is correct. | Concrete quantities for the pier and north abutment were inadvertently flipped in the table. An addendum is being prepared to clarify. Total concrete quantity does not change. | Mike Coleman | 1 | 2023-01-26 13:33 | 2023-01-30 08:29
20230214 | 20230214035 | 35 | Temporary Water Diversion | What is the Department's intention regarding the water diversion at structure C-35-1960? The other two structures receiving extensions have a pay item for the temporary water diversion but the 1960 structure does not. | This culvert appears to be dry most of the time and should not need water diversion. | Mike Coleman | 6 | 2023-01-26 14:13 | 2023-01-30 08:14
20230214 | 20230214004 | 4 | Prosecution and Progress | Page 2 of the specials under prosecution and progress, 1st paragraph under Base Stabilization & Paving Operations states: â€œIf same day base stabilization requirement is waived for base repair for stabilized base reclamation layer, the contractor is responsible for the integrity of the base material until the stabilization operation is completedâ€â€™ This makes the project difficult to bid because of unforeseen conditions and contractor requests this portion be removed from the specials. | The Department will be responsible for any weak spots discovered in a proof roll immediately following milling operations. The contractor would be responsible for any damaged areas caused by their equipment thereafter. Special provision language updates will be issued in an upcoming addendum. | Mike Coleman | 7 | 2023-01-27 08:23 | 2023-02-03 06:31
20230214 | 20230214015 | 15 | Temp lighting | There is currently no inventory of type 4 60 foot wood poles, in fact they are no longer produced. The lead time on type 2 60 foot wood poles is 18 weeks. The accelerated schedule does not account for the 18 week lead time or the 4 weeks required to install the temp lighting. Please redesign the temp lighting plan to allow for shorter poles or add an item to the contract for temporary light plants by the day. | The Department is not aware of a material issue with regards to the poles. | Mike Coleman | 9 | 2023-01-27 11:08 | 2023-02-07 08:39
20230214 | 20230214023 | 23 | Structure Painting Scope | Please clearly define the scope of the structural steel repainting. Per the Special provisions, there is 50,100 SF of surface to be painted, the 16th note in General Notes on sheet 5 of 47 of the bridge plans indicates that "All existing steel shall be sandblasted and painted", the second to last item listed in the Proposed Improvements note on sheet 5 of 47 calls for painting of bents 1-8. 50,100 sf is certainly not close to the entire bridge steel surface area so more detail is needed. | Response to question #1 for the Holton Ph1 bridge project: -Paint all structural steel at bents 1-8 below the main girder beam seat elevations at each respective bent. -Paint all top girder/stringer flanges located within the defined limits of the expansion joint replacement locations. -See plan sheets 1-3 for painting locations of bents 1-8 and expansion joints 1-10. Note- All steel above the main girder beam seat elevations will be painted in a future phase. | Mike Coleman | 1 | 2023-01-27 13:42 | 2023-02-01 06:53
20230214 | 20230214035 | 35 | AFAD | Can the contractor use AFAD(Automated Flagger Assistance Device) for work on this project where temporary traffic signals are not designated? The plan contains a SDD showing the appropriate traffic control needed. | The contractor is allowed to use an Automated Flagger Assistance Device (AFAD) provided the device is on the Approved Products List (APL) and SDD 15D12b Traffic Control, Lane Closure with Automated Flagger Assistance Device is followed. | Mike Coleman | 7 | 2023-01-27 14:20 | 2023-01-30 13:41
20230214 | 20230214038 | 38 | AFAD | Can the contractor use AFAD(Automated Flagger Assistance Device) for work on this project where temporary traffic signals are not designated? The plan contains a SDD showing the appropriate traffic control needed. | AFADs are allowed for use on state highways if they follow SDD 15D12 - 09b and if the device is on the approved products list. | Mike Coleman | 13 | 2023-01-27 14:38 | 2023-01-30 12:10
20230214 | 20230214039 | 39 | AFAD | Can the contractor use AFAD(Automated Flagger Assistance Device) for work on this project where temporary traffic signals are not designated? The plan contains a SDD showing the appropriate traffic control needed. | The contractor is allowed to use an Automated Flagger Assistance Device (AFAD) provided the device is on the Approved Products List (APL) and SDD 15D12b Traffic Control, Lane Closure with Automated Flagger Assistance Device is followed. | Mike Coleman | 1 | 2023-01-27 14:40 | 2023-01-30 13:42
20230214 | 20230214040 | 40 | AFAD | Can the contractor use AFAD(Automated Flagger Assistance Device) for work on this project where temporary traffic signals are not designated? The plan contains a SDD showing the appropriate traffic control needed. | The contractor is allowed to use an Automated Flagger Assistance Device (AFAD) provided the device is on the Approved Products List (APL) and SDD 15C12b Traffic Control, Lane Closure with Automated Flagger Assistance Device is followed. An addendum is being issued to add the SDD to the plans. | Mike Coleman | 1 | 2023-01-27 14:41 | 2023-01-30 13:43
20230214 | 20230214015 | 15 | Drainage Tables in Excel Format | Can the drainage tables on pages 419 to 429 & 1079 to 1088 be provided in excel format? | The excel files can be found at the following location: https://wisdot.box.com/s/1447wusibkod5npcb7tjcomcj764skae or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 10 | 2023-01-27 15:28 | 2023-02-01 06:51
20230214 | 20230214024 | 24 | Pavement Markings | Good afternoon, it appears there is a temporary paint item and associated quantities for the lower layer and a regular epoxy item for the upper layer. Should the regular epoxy item be switched to a same day epoxy item so that it will be installed the same day as the upper layer of asphalt? Will an addendum be issued to change this item? Thank you. | The regular epoxy will not be switched to same day epoxy. Additional items and quantity for Temporary Marking Raised Pavement Markers Type II, Traffic Control Drums, and Traffic Control Signs will be added to the plan through an addendum for temporary delineation between final surface paving and permanent pavement marking. | Mike Coleman | 1 | 2023-01-27 15:34 | 2023-02-01 07:01
20230214 | 20230214038 | 38 | Survey | AT this time, is there a survey of the project completed with elevations and cross slopes and if so can the contractor please be permitted to see the survey? | The contractor data packets posted at the following link contain all of the survey data and surfaces. The contractor should review this data and if this does not resolve the question, please submit a follow up question. https://wisdot.box.com/v/Supplemental-Info-20230214 | Mike Coleman | 14 | 2023-01-30 10:24 | 2023-01-31 06:56
20230214 | 20230214015 | 15 | Temp Shoring for water main at R-40-716/717 | The temp shoring at R-40-716 & R-40-717 is for the existing water main running along the east side of the structures. We cannot find an information on the elevations of the waterman as it goes past the structure. Without it there is no way to determine what shoring design may be needed. Can you provide elevations of this watermain where shoring will be required? | Water main as-builts from the City of Milwaukee can be found at the following location: https://wisdot.box.com/s/1447wusibkod5npcb7tjcomcj764skae or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 11 | 2023-01-30 13:38 | 2023-02-01 08:19
20230214 | 20230214023 | 23 | Existing Structure Design Info | Please provide any available information for design of the existing structure. | Scans of the existing structure design information can be found at the following location: https://wisdot.box.com/s/c2vi50we4smh07dzbz3litwao0mpmesv or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-01-30 16:19 | 2023-02-01 06:59
20230214 | 20230214022 | 22 | Stamping Colored Concrete | Is the concrete for the item Stamping Colored Concrete paid for in the item Concrete Sidewalk 5-Inch? The quantity might be off if this is the case. Usually the Stamping Colored Concrete item only covers the additional cost for color and stamping of the concrete unless the item is a SPV item. | We will be preparing an addendum to add the quantity of Concrete Sidewalk 5-inch needed for the stamped and colored concrete. | Mike Coleman | 1 | 2023-01-31 13:59 | 2023-02-02 07:15
20230214 | 20230214036 | 36 | Salvage Beam Guard | Would the department consider adding a salvage beam guard item into the project? With having to remove the beam guard for grading and curb and gutter work this would be a separate operation and completed before milling & paving of asphalt would be on so the correct heights wouldn't be known to install the new beam guard. | No. The department will not be adding a salvage beam guard item to the project. Per the special provisions the contractor will have 10 calendar days to install the new beam guard after removing the existing. | Mike Coleman | 2 | 2023-01-31 16:35 | 2023-02-02 07:21
20230214 | 20230214019 | 19 | 643.5000 Traffic Control | Item 643.5000 Traffic Control has been omitted from the plan quantities. Can this item be added on? Thanks | An addendum will be issued to add the item. | Mike Coleman | 2 | 2023-01-31 19:05 | 2023-02-02 06:53
20230214 | 20230214045 | 45 | Prosecution and Progress - Start Restriction | The Notice to Proceed is required such that work shall start no later than June 5th, 2023. Can the contractor be allowed to start anytime so that the project is completed during the 2023 construction season? | The statement â€œThe Notice to Proceed will be issued such that work shall start no later than June 5, 2023, unless otherwise approved by the engineer.â€ will be removed. An addendum will be published within the next 1-2 days to address this change. It is important to note that due to WDNR requirements on fish spawning, any instream disturbance at the culverts located at Sta. 60+50, 308+00, and 315+15 cannot occur until after June 1. | Mike Coleman | 1 | 2023-01-31 19:54 | 2023-02-02 16:04
20230214 | 20230214045 | 45 | Thin and Varying Pavement Thickness | Under Prosecution and progress it states, Due to the thin and varying thickness of the existing pavement, pave the lower layer within 48 hours of milling. Is it reasonable to expect the contractor to get consistent density test results as required by the PWL specification when the existing pavement is thin, variable and has limited ability to hold traffic? | Question has been discussed with WisDOT pavement engineers. The PWL and joint density requirements will remain. Between the remaining existing pavement and thick supporting base and subbase, it should be adequate to allow contractor to compact upon to reach required densities. | Mike Coleman | 2 | 2023-01-31 19:57 | 2023-02-03 14:20
20230214 | 20230214045 | 45 | Paving Plan | While 48 hours is allowed between milling and paving the lower layer it appears plan sheets 15, 16 and 17 are showing a mill and fill operation? | Plan sheet 15,16, and 17 are to be removed from the letting plan set. An addendum will be issued. | Mike Coleman | 3 | 2023-01-31 19:58 | 2023-02-03 14:21
20230214 | 20230214045 | 45 | Pavement Thickness & Type | The department may want to consider increasing the upper layer to 1.75 inches (increasing total pavement thickness to 3.5 inches) and changing the mix to a 4MT for the entire project. This would help with the pavement structure and thin/variable pavement with minimal cost difference. Changing only the lower layer to a 4MT is also an option, however this does not allow for the needed tonnage on the upper layer (5MT) for the PWL specification. | The two layers of 5MT is an acceptable practice. Keeping the PWL is the best practice and provides the department the opportunity for a quality pavement. PWL is supported by our FHWA partners and should be employed whenever possible. | Mike Coleman | 4 | 2023-01-31 20:00 | 2023-02-03 14:22
20230214 | 20230214045 | 45 | Asphaltic Surface Temp | Why is a 4MT 58-34S material required for the asphaltic surface temp item? Should this be for the asphaltic surface item instead? | Article #18 (Asphaltic Surface Temporary) will be removed from the special provisions for this project. An addendum will be issued within the next several days. | Mike Coleman | 5 | 2023-01-31 20:01 | 2023-02-03 14:22
20230214 | 20230214045 | 45 | Asphaltic Surface Driveways and Field Entrances | The department may want to add the Asphaltic Surface Driveways and Field Entrances item for driveways instead of lumping it in with the asphaltic surface. Especially if specifying a specific mix and AC type for the Asphaltic Surface. | Article #18 (Asphaltic Surface Temporary) will be removed from the special provisions for this project. An addendum will be issued within the next several days. | Mike Coleman | 6 | 2023-01-31 20:02 | 2023-02-03 14:24
20230214 | 20230214045 | 45 | Misc Repairs | On Sheet 49, Asphaltic Surface shows 1000 ton under misc. repairs and Asphaltic Surface Patching shows 300 ton under misc. repairs. Can you clarify what the misc. repairs are for and which will be paid under Asphaltic Surface and which will be paid under Asphaltic Surface Patching? | The intention of these pay items is to account for unforeseen repairs that may be required and/or â€œsoft spotsâ€ uncovered during the pavement milling operations. This may include miscellaneous repairs, wedging, breakthroughs, etc. The Asphaltic Surface item is intended to cover larger areas of repair and the Asphaltic Surface Patching item is intended to cover small pop outs, potholes, and repairs that can generally be completed with minimal workforce or equipment. | Mike Coleman | 7 | 2023-01-31 20:03 | 2023-02-03 14:25
20230214 | 20230214035 | 35 | Quantities | The quantities for line items 650.45, 650.50, and 650.992 on project 1580-30-70 do not seem to make sense, will there be an addendum addressing this? | The quantities for the three staking items were corrected. Revisions will be included in an addendum. | Mike Coleman | 8 | 2023-02-01 09:28 | 2023-02-07 08:38
20230214 | 20230214009 | 9 | Design Conversion Factors (tons/cy) | What are the design conversion factors used (tons/cy) for these item of work: Base Aggregate Dense 3/4", Base Aggregate Dense 1-1/4" and Select Crushed Material? | Conversion factor for Base Aggregate Dense 3/4" and Base Aggregate Dense 1-1/4â€ is 1.85 tons/cy. Conversion factor for Select Crushed Material is 1.75 tons/cy. | Mike Coleman | 3 | 2023-02-01 12:03 | 2023-02-02 15:51
20230214 | 20230214015 | 15 | SPV 10 Available Documents | Per SPV Article 10, can you provide information/documents as outlined for both project ID's. | The requested files can be found at the following location: https://wisdot.box.com/s/1447wusibkod5npcb7tjcomcj764skaeor can be accessed on the HCCI February bid letting page under Supplemental Information. Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One is Contractor Data Packages, and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 12 | 2023-02-01 16:07 | 2023-02-02 16:01
20230214 | 20230214015 | 15 | Bridge Painting Color | B-40-196/197 - sheet 692 and 696 state bridge painting to match existing color. There appears to be multiple existing colors. Please provide more detail on intended scope of work. | B-40-196/197 should use Federal Standard Color No. 25240 or as approved and directed by the Engineer. | Mike Coleman | 13 | 2023-02-01 16:12 | 2023-02-06 07:49
20230214 | 20230214034 | 34 | Traffic control | During Stage 1, will the DOT allow the closure of Krautkramer Lane between River road and Sth 107, this will dictate mobilization costs. Thank you | The Department considered the request but will not allow the closure of Krautkramer Lane between River Road and STH 107. This request was discussed with the village of Marathon City, but due to additional traffic impacts anticipated by rerouting the County Concrete trucks to the other local streets the village was opposed to the proposed closure. A closure of Krautkramer was also not discussed during the public involvement process. | Mike Coleman | 1 | 2023-02-02 07:47 | 2023-02-03 14:30
20230214 | 20230214052 | 52 | Railroad Flagging | The railroad tracks run parallel with the road approximately 40' from the edge of the bridge. There is no flagging or flagging reimbursement language included within the Special Provisions. Is WisDOT's intent to no longer reimburse railroad flagging? | WisDOT will not be reimburse flagging costs on this project. The contractor will need to coordinate with the railroad per article 7 of the Special Provisions and Standard Specification 107.17. | Mike Coleman | 1 | 2023-02-02 09:55 | 2023-02-06 08:19
20230214 | 20230214036 | 36 | Project Schedule | In the Specials it says end walls at station 286+80 and 496+50 need to be completed by June 1st to avoid impacts on northern long eared bats, would the DOT consider a netting as a deterrent to give contractor more flexibility in the project schedule also prior to June 1st historically project would encounter the most water at pipe and end wall locations. | Netting for Northern Long Ear Bats is not an option on this project. | Mike Coleman | 3 | 2023-02-02 11:28 | 2023-02-07 08:36
20230214 | 20230214022 | 22 | SPV - base aggregate | What is engineering logic and rational into not allowing the use of reclaimed and recycled asphalt, reprocessed materials, and blended materials in base layers when WisDOT has been promoting the use of recycled materials for decades to lower overall project costs and help lower greenhouse emissions? This seems to be contradictory to why the specification was written and the departmentâ€™s stance on carbon emissions. Is the department trying to set a new precedence in which locals can deviate from standard specifications whenever they want? | Waukesha County has found that use of the selected and specified material provides for the best base material through out the county. | Mike Coleman | 2 | 2023-02-02 13:49 | 2023-02-03 14:36
20230214 | 20230214019 | 19 | Sanitary manhole backfill requirements | Per the Specials 104 and 105; Sanitary Manhole excavation are to be backfilled with slurry backfill. The plan sheets (133-136) call for granular backfill. Please confirm which is correct. | The Sanitary Manholes are to be backfilled with granular backfill. An addendum will be submitted to revise the backfill requirements in the special provisions. The plans will remain unchanged. | Mike Coleman | 3 | 2023-02-03 07:58 | 2023-02-07 08:41
20230214 | 20230214022 | 22 | Common Excavation - Undistributed EBS | There is 26,800 CY of Undistributed EBS shown in the miscellaneous quantities which is 33% of the total for the project. Would the department consider a haul off EBS item for the 26,800 CY of undistributed EBS? | The EBS is paid for as Excavation Common which includes hauling and disposal of unsuitable material. Contractor should account for this in their unit price. A separate haul off item will not be provided. | Mike Coleman | 3 | 2023-02-03 09:45 | 2023-02-06 07:50
20230214 | 20230214045 | 45 | Structure Staking | A construction staking item appears to be needed for Structure B-55-290. | The item quantity of Construction Staking Pipe Culverts (650.6000) is increased by 3 each. The updated total for this bid item is now 9 each. An Addendum will be posted next week with updated plan sheet. | Mike Coleman | 8 | 2023-02-03 12:13 | 2023-02-06 07:48
20230214 | 20230214052 | 52 | Item 0144 SPV.0090 Flashing | What is the Flashing detail for this project? | The Stainless Steel Flashing bid item is being eliminated. An addenda will be issued. | Mike Coleman | 2 | 2023-02-03 12:30 | 2023-02-08 11:50
20230214 | 20230214037 | 37 | Item 0040 Type M Railing | In the general notes for the M railing details, it says the railing is painted. Please provide the color of paint needed for the railing. | The intent was not to paint the railing. An addendum will be issued to remove the general note. | Mike Coleman | 4 | 2023-02-03 12:36 | 2023-02-07 08:40
20230214 | 20230214031 | 31 | Modular expansion joints | It is our understanding that the first phase of modular expansion joints is needed on site August 1 and the second phase is needed mid-September. We cannot meet this schedule. Can an extension to the completion date be granted, say by two months? | The department has reviewed modular expansion joints schedule requirements and will be adjusting the contract time in an addendum. | Mike Coleman | 3 | 2023-02-03 13:40 | 2023-02-08 06:38
20230214 | 20230214004 | 4 | Culvert Pipe Class Specifications | I need a list of what gauge and corrugation will be required for items 58-72. It is not noted anywhere I can find in the plan sheets. | The following is a list of the required gauge and corrugations for the Corrugated Steel options under the general Culvert Pipe Class III and IV items per FDM 13-1 Attachment 25.2: Item 520.3148 â€“ Culvert Pipe Class III 48-Inch: 0.109â€ Gauge, 2â€ x 2/3â€ Corrugations Item 520.3160 â€“ Culvert Pipe Class III 60-Inch: 0.138â€ Gauge, 2â€ x 2/3â€ Corrugations Item 520.3324 â€“ Culvert Pipe Class III-A 24-Inch: 0.064â€ Gauge, 2â€ x 2/3â€ Corrugations Item 520.3330 â€“ Culvert Pipe Class III-A 30-Inch: 0.079â€ Gauge, 2â€ x 2/3â€ Corrugations Item 520.3336 â€“ Culvert Pipe Class III-A 36-Inch: 0.079â€ Gauge, 2â€ x 2/3â€ Corrugations Item 520.3524 â€“ Culvert Pipe Class III-B 24-Inch: 0.064â€ Gauge, 2â€ x 2/3â€ Corrugations Item 520.4130 â€“ Culvert Pipe Class IV 30-Inch: 0.079â€ Gauge, 2â€ x 2/3â€ Corrugations Item 520.4136 â€“ Culvert Pipe Class IV 36-Inch: 0.079â€ Gauge, 2â€ x 2/3â€ Corrugations | Mike Coleman | 8 | 2023-02-03 14:27 | 2023-02-06 07:45
20230214 | 20230214015 | 15 | Base Patching Special Provision | This project has a special provision for Base Patching Concrete SHES Special, Item SPV.0180.001. The only difference in the wording from the standard specification is under the payment section there is no mention of incidental tie bars and dowel bars. What is the intent of the special provision for base patching on this project? | There are two types of base patching used on this project. The base patching for the freeway ramps and crossroads should follow the standard item. The mainline freeway should use the special item that does not require tie bars or dowel bars since that pavement has been previously rubblized. See the construction detail on page 45. | Mike Coleman | 14 | 2023-02-03 15:58 | 2023-02-07 08:37
20230214 | 20230214030 | 30 | 30 ID#4677-10-71 | Item SPV.0060 Speical 05. RADIO COMMUNICATION SYSTEM SPECIAL CTH OO & FRENCH RD Question: Max distance for Radio comm cable is 330ft w/o additional equipment (ethernet extender) Qty is listed at 336â€™ does that include distance up the pole to the radio? | The Quantity of 336 LF includes a significant amount of cable slack (extra 10â€™ in each pull box plus an additional 10% added to the total distance) and includes the full distance from the signal base up the monotube assembly to the end of the horizontal signal arm. The actual distance from the cabinet to the radio mounting location will be less than 300â€™ and a repeater will not be needed. It is anticipated the radio can be installed at the top of the vertical signal pole. | Mike Coleman | 1 | 2023-02-04 14:38 | 2023-02-06 08:19
20230214 | 20230214002 | 2 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/ohxahkv1oa0ze8tyzlo52p6qb89u4msu or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-02-05 14:13 | 2023-02-06 08:18
20230214 | 20230214015 | 15 | Departments response to question 6 | In reference to the department's response on question 6. Is it the departments intention to place the standard concrete barrier on top of HMA pavement? If so, is it assumed there will be no concrete barrier pad required in these areas? The concrete barrier pad shown in the SDD is in fact HMA pavement according to the department response and the concrete barrier pad is only then required in areas of transitions, bases, anchors, etc..? | Yes, the standard concrete barrier should be placed on top of the HMA pavement. This is outlined in the fourth general note on page 3 of the plans. No concrete pad will be required in these areas. Concrete bases will be required as part of the non-standard barriers including transitions, bases, anchors, etc. | Jill Fehrman | 15 | 2023-02-06 08:55 | 2023-02-09 07:35
20230214 | 20230214035 | 35 | PWL Density Question | Would the department consider waiving PWL density testing from STA 743+00 to 777+00 and STA 505+82 â€“ 530+82? Both segments are shorter than the length needed to complete a test strip. | Bid the number of the test strips that are in the plan. | Mike Coleman | 9 | 2023-02-06 12:23 | 2023-02-08 11:51
20230214 | 20230214031 | 31 | Bid Item 657.0545 Monotube Arm 45 -ft | WE have been informed that the lead time on this arms could be as long as 48 weeks, We have broughtthis issue up before, this is ging to be areal issue. What if the electrical contracotr cannot get the 45 FT Monotube arm by the completion date the Prime Contractor has chosen? WISDOT should order these type of items ahead of time and supply them so as to not cause issues, or have the projects let earlier to avoid this. An electrical subcontractor should nit be held accountable for supply chain issues. | The department has reviewed monotube lead times with statewide suppliers and believes there is adequate time in the schedule. | Mike Coleman | 4 | 2023-02-06 14:19 | 2023-02-08 06:40
20230214 | 20230214030 | 30 | Bid Item 653.0201 Electric Service Meter Breaker Pedestal | Lead times are 48-52 weeks for meter pedestals, how is the department going to handle this if the product cannot be installed before the completion date? | An addendum will be issued to address the contract completion time | Jill Fehrman | 2 | 2023-02-06 14:25 | 2023-02-09 07:41
20230214 | 20230214029 | 29 | Electrical items lead times | Lead times for these and other poles and related items can be as long as 48 weeks, suppliers arent even giving lead times with most quotes. Thsi is a working day contract, if the Prime contractor decides to start the project early in the construction season the electrical items may not be available. How is the department going to handle this? | An addendum will be issued to address the contract completion time. | Jill Fehrman | 1 | 2023-02-06 14:32 | 2023-02-09 07:44
20230214 | 20230214004 | 4 | Asphalt Stabilizing Agent Quantity | It appears the Asphalt Stabilizing Agent quantity is vastly overstated. Plans and specs require either 5.5% emulsion (virgin CABC areas) or 4.0% emulsion (reprocessed asphaltic base sections). Based on take offs the plan oil quantity of 4,442 Tons provides for an average application rate of 7.2% emulsion over the project. Is this a calculation error? If not, what is the intent of the extra emulsion? | An additional undistributed quantity was originally included to account for the tonnage with water weight included. Based on further discussion with industry experts familiar with this base stabilization operation, additional weight for water in the emulsion is typically not included with the reported emulsion tonnage. The undistributed quantity of Asphalt Stabilizing Agent will be removed in an upcoming addendum to reflect this direction. | Mike Coleman | 9 | 2023-02-06 15:24 | 2023-02-08 06:10
20230214 | 20230214004 | 4 | Base Stabilization/Milling Traffic Restrictions | Being this project is closed to traffic & detoured can the restrictions for milling and base stabilization within the same lane and same day be removed? Placing three operations into a single work zone (milling, base repair for Stabilized base reclamation layer & Stabilized Base reclamation) will hinder production of all operations. The design schedule for the project does not show milling, base repair and stabilized base reclamation occurring 100% concurrently. | Base stabilization timing requirements will be relaxed to have to take place within 48 hours of the milling operation. Special provision language updates will be issued in an upcoming addendum. | Mike Coleman | 10 | 2023-02-06 15:24 | 2023-02-08 06:10
20230214 | 20230214023 | 23 | Fabrication Class | What fabrication classification is required for the structural steel on this project? Will a WDOT approved fabricator for Primary Bridge Members be mandated? | : An approved fabricator from the Steel Bridge Primary Members APL will be required. The fabricator must be approved for product 1 (unspliced rolled sections) on the APL. | Jill Fehrman | 3 | 2023-02-06 15:47 | 2023-02-09 08:34
20230214 | 20230214012 | 12 | Bird Deterrent | The project special provisions state the existing structure has deterrent that was installed by Columbia County. A site visit does not show and deterrent installed. Could an update be provided? | The County is aware of their netting commitment and will place the bird netting prior to April 15th of this year. | Jill Fehrman | 2 | 2023-02-06 17:32 | 2023-02-10 14:28
20230214 | 20230214032 | 32 | Item 0048, 513.2001 Railing Pipe | Please provide the railing detail for Item 0048, 513.2001 Railing Pipe LF 40.000 on Project 32. | An addendum will be issued to include a construction detail of the railing pipe. | Mike Coleman | 1 | 2023-02-07 08:26 | 2023-02-07 12:46
20230214 | 20230214052 | 52 | 4LT versus Asphaltic Surface | Would the department consider changing the 4LT to Asphaltic Surface with the small quantities with this job? There is 50 or less tons of each mix type. | The department will proceed with the HMA Pavement bid items as advertised. | Jill Fehrman | 3 | 2023-02-07 08:28 | 2023-02-09 07:29
20230214 | 20230214009 | 9 | Rubblized Concrete Layer | Can the Department provide any information on the rubblized concrete layer? Does it have steel mesh in it? Is there any data on the rough sizing of the concrete? | Based on the asbuilt (2004) when the concrete was rubblized we do not have the information on the rough sizing of the concrete or the presence of steel mesh. Although during the time period the concrete pavement was placed (1960â€™s) it was common for concrete pavement to include wire mesh. | Jill Fehrman | 4 | 2023-02-07 10:30 | 2023-02-09 08:44
20230214 | 20230214015 | 15 | 643.1200.S Traffic Queue System | Can the Department clarify how many devices will be needed for each QWS setup? SDD shows (6) PCMS and (3) PTS per setup; however with a complex Interstate interchange at each end of the project I would assume that these systems would be utilized on multiple roadways, but there isn't a plan sheet that shows exactly what is needed. Similar projects (N. leg Zoo) explicitly stated what devices were needed and where they were to be placed. I could see a scenario where there are up to (9) PCMS on SB-41/NB-43 and (12) on NB-41/SB-43. The number of devices will greatly influence the bid cost for this item, and assigning a quantity of (1) per direction leaves a lot of room for interpretation. Thanks | Assume 6 PCMS and 3 PTS per setup. | Mike Coleman | 16 | 2023-02-07 12:14 | 2023-02-13 08:13
20230214 | 20230214016 | 16 | Contract Schedule - Working Days | Could we see how the 35 working days was derived? With the amount of grading that is required for the 10:1 excavations at the pipes, we don't believe 35 working days would be sufficient without additional forces to be working at multiple locations at the same time. | The design schedule can be found at the following location: https://wisdot.box.com/s/8svd12t9t3nyrtzr7yk5yr1m5rckedbt or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-02-07 12:40 | 2023-02-08 06:52
20230214 | 20230214047 | 47 | Storm Sewer Staking | It appears that the storm sewer staking quantity is much higher than the actual number of storm sewer structures that are in the plan. | We looked into this and the quantity was incorrect in the MQ table. An addendum will be issued. | Mike Coleman | 1 | 2023-02-07 13:03 | 2023-02-08 11:52
20230214 | 20230214015 | 15 | epoxy crack seal clarification | Please clarify the difference between item 214 509.9020.S Epoxy Crack Sealing and item 216 509.9025.S Epoxy Injection Crack Repair. | The primary difference is that Epoxy Crack Sealing does not require pressurized injection of the epoxy into the crack, but rather surface sealing like a caulk. Epoxy Injection Crack Repair does require pressurized injection of the epoxy into the crack including use of vent ports to ensure crack penetration. | Jill Fehrman | 17 | 2023-02-07 15:09 | 2023-02-09 07:28
20230214 | 20230214019 | 19 | Watermain restraint requirement | The plans and SP 88 call out for all watermain joints to be restrained. it is not customary to restrain straight runs of pipe. Is Cert-Lok C900 pipe acceptable? If not, each joint on the PVC watermain will require a mechanical restraint coupler. | All water main pipe joints are required to be restrained. Internal restraints (i.e. Rieberlok or equal) or external restraints (Certa-Lok C900 pipe or equal) would both acceptable. Mechanical / Bolt-on couplers are not allowed. Addendum will be issued to clarify the requirements in the special provision. | Jill Fehrman | 4 | 2023-02-07 15:23 | 2023-02-09 08:33
20230214 | 20230214020 | 20 | Missing Plan Sheets | Can you provide the remainder of the plan and profile plan sheets. It appears there are some missing. | Plan & profile sheets were only provide on CTH Y where a profile adjustment is required to smooth out the profile and reduce the hump in the center of the intersection for the new higher speed through movement. Plan and Profile sheets were not provided on CTH NN as this is a mill/overlay with cross slope adjustments. Information on the pavement surface are available on the pavement grades sheets and the cross sections. | Mike Coleman | 1 | 2023-02-07 18:27 | 2023-02-08 11:50
20230214 | 20230214045 | 45 | Cleaning Culvert Pipes | The cleaning culvert pipe item appears to include the culverts that require lining. Will those be paid as cleaning pipe or is it incidental to the culvert lining items? |  |  | 9 | 2023-02-08 09:56
20230214 | 20230214035 | 35 | Shattered Concrete | under the 1580-30-71/72 project, the existing typical shows 7" shattered concrete pavement, the specials do not reference this to be put back in that matter. Will the concrete need to be shattered in the base paving? Can the concrete be poured back in one pour? (Including the 7-inch shattered and the 8-inch paving) or will it require two pours? How will the shattered concrete layer be paid for? | The concrete is replaced at the culvert pipes (see Culvert Pipe Detail on sheet 12 of the 70 plan and sheet 9 of the 71 project). The layer of shattered concrete is being replaced with 7â€ BAD and the 8â€ of concrete is being replaced with 8â€ base patching SHES. The new base patching SHES will not be shattered. | Jill Fehrman | 10 | 2023-02-08 12:03 | 2023-02-09 14:33
20230214 | 20230214023 | 23 | Teflon Plates at Expansion Joints | There are teflon plates at expansion joints shown in the plans to be replaced, work to remove and replace the plates is not incidental to any of the current bid items. Please advise if replacement of the plates will be required and what items will be used to pay for this work. | Teflon plate locations are shown in the plan set on sheets 10-13 at expansion locations. Teflon plates on the top of the stringers are too be replaced where exposed for expansion joint work. The item Teflon pad is listed as a Non-Bid item in the estimate of quantities table shown on sheet 5. Existing Teflon plates at the underside of stringer locations shown in the plan set (sheets 10-13) are to remain. | Jill Fehrman | 4 | 2023-02-08 12:58 | 2023-02-09 15:40
20230214 | 20230214011 | 11 | Convert Manhole to Valve Box | The existing gate valves in these 4 manholes are butterfly valves per City of Onalaska, shall the butterfly valve adaptor be used in this situation? |  |  | 2 | 2023-02-08 13:44
20230214 | 20230214011 | 11 | Water Main Fittings | Specs detail all water main fittings shall have a fusion bonded epoxy coating, is this accurate? As City of Onalaska spec does not include this. |  |  | 3 | 2023-02-08 13:48
20230214 | 20230214015 | 15 | Slotted Drain | In light of the approval of contractors to use corrosion resistant non-metal pipe under 520, would the DOT permit contractors to install DuraSlot (Slotted drain with modified AASHTO M294 HDPE Pipe) for the bid item 521.2005.S? For more information and specifications on DuraSlot, see https://assets.ads-pipe.com/m/11a70b2903fcbd3/original/Duraslot-Pipe-Specification.pdf |  |  | 18 | 2023-02-08 13:57
20230214 | 20230214045 | 45 | Utilities | The special provisions state that St Croix Electric has an OH line that crosses the eastern endwalls of proposed structure B-55-290 with "No conflicts anticipated". With the size/weight of the proposed pipe and apron endwalls being installed at that location we feel that conflicts should be anticipated. Is it possible to de-energize the lines or tip the poles out enough to safely set the pipe/endwalls? | Per workplan from St. Croix Electric, they would be willing to cover up (shield) the overhead line between Sta. 225+50 and Sta. 227+75 if needed. Coordinate with St. Croix Electric to make arrangements for covering the overhead line. | Mike Coleman | 10 | 2023-02-08 14:52 | 2023-02-13 07:53
20230214 | 20230214031 | 31 | Bid Item 657.0545 Monotube Arm 45 -ft | The department has stated that the suppliers they checked with aroundthe state said lead times should not be an issue. Ca nthe department provide the list of suplliers that stated this? The suppliers we checked with state the opposite. | The department does not have a standard list for arms only but the standard list for monotube poles can be found in the following link: https://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/tools/prods/657-0300.aspx | Jill Fehrman | 5 | 2023-02-09 07:33 | 2023-02-09 15:45
20230214 | 20230214039 | 39 | Class III-A Non-Metal vs Class III-B Non-Metal | I am not seeing a Class III-B in the proposal documents, but on sheet 52 STA 196+29 and sheet 56 STA 336+66 there is some 36" pipe Class III-B non metal pipe. Was this pipe missed in the estimated quantities? Phone Ext is 66049. Thanks, Jesse Hurt | Bid the pipe that is in the estimated quantities and Miscellaneous Quantities for those location. | Mike Coleman | 2 | 2023-02-09 10:18 | 2023-02-13 08:01
20230214 | 20230214037 | 37 | 2-year flood elevation | Is the 2-year flood elevation listed in the erosion control accurate? The 2-year flood elevation is listed at 1125.47' and the elevation of the pier seat is 1124.45'. | The Q2 elevation shown on the plans is accurate. | Jill Fehrman | 5 | 2023-02-09 10:34 | 2023-02-10 15:00
20230214 | 20230214005 | 5 | Common ex & landscape | Are we to expect that common excavation and landscaping are incidental to the sidewalk item, there is quite a bit of them both | Yes, the excavation is incidental to the Concrete Sidewalk bid Item. It is small quantities for each curb ramp. As for landscaping, there is grass seed, fertilizer, and erosion mat items. Any decorative plants, woodchips, edging etc. that conflicts with the sidewalk construction and slope grading is to be removed and have fertilizer and grass seed put back down. Landscaping items were discussed with property owners as part of the departmentâ€™s real estate negotiations. Decorative landscaping restoration will be the responsibility of the property owner as they have been compensated for that. | Jill Fehrman | 2 | 2023-02-09 11:13 | 2023-02-10 14:40
20230214 | 20230214038 | 38 | Shoulder Aggregate Quantities | Based on the answers to questions 6 & 9, it is understood that the designer intends that the base aggregate below the existing paved shoulder is not to be incorporated into the CIR layer, and that this material shall be removed from site and disposed of, incidental to preparation items under 211.3.6. The department acknowledged that existing shoulder width will likely prohibit placement of surplus material on shoulders due to narrow shoulders and steep side slopes. Given these conditions, the aggregate below the paved shoulder will not be available for incorporation into the final aggregate shoulder, and the plan quantity of 300 Ton for ï¿½-inch base aggregate dense appears to be insufficient for shouldering the project. The contractor is responsible for shaping the remaining aggregate shoulder under 211.0400, but if remaining material is insufficient to meet the proposed typical sections, will the department pay for additional quantity under item 305.0110 to complete the shouldering? | An addendum will be issued to adjust the anticipated quantity. | Jill Fehrman | 15 | 2023-02-09 11:16 | 2023-02-10 15:01
20230214 | 20230214004 | 4 | Stabilized Base Reclamation & Base Repair for Stabilized Base Reclamation Layer | In the event that the stabilized base reclamation layer fails due to failure of underlying soils after the injection of emulsified asphalt: Who is responsible for this repair? What will be the method of repair? Will the repaired areas require re-injection of asphalt emulsion? |  |  | 11 | 2023-02-09 11:45
20230214 | 20230214004 | 4 | Stage 1 PWL | With the staging, and stage 1 being mostly an intersection, there may not be room for a representative test strip. Would the department allow stage one tons to be QMP? | The Department will maintain the PWL requirements for the work done in Stage 1. Per the Stage 1 description in the Traffic article of the special provisions, work during this stage may also include milling and base stabilization elsewhere on the project beyond the immediate STH 60/STH 67 intersection area. This may include the section of STH 60 adjacent to the intersection to the distance necessary to complete the representative test strip. | Jill Fehrman | 12 | 2023-02-09 14:09 | 2023-02-10 14:58
20230214 | 20230214030 | 30 | PROSECUTION AND PROGRESS | #3 PROSECUTION AND PROGRESS LAST PARAGRAPH "INTERIM COMPLETION". CAN YOU ELABORATE/EXPLAIN THIS PARAGRAPH? DOES ALL WORK ON THE "OO" WEST END MEDIAN NEED TO BE COMPLETED OVER A WEEKEND? | Work on the west end of the CTH OO median at the STH 441 Northbound Ramps needs to be completed within the weekend timeframe specified (6:00 PM Friday to 6:00 AM the following Monday) to the extent of allowing the existing northbound left and left/thru lanes to operate without restrictions or lane closures outside of the noted timeframe for the remainder of the project. | Jill Fehrman | 3 | 2023-02-09 16:14 | 2023-02-10 15:02
20230214 | 20230214045 | 45 | Apron End Walls for 72"x113" HE CL4 Pipe | Precast Apron End Walls cannot be spaced 3' apart as specified in the plans. The maximum outside dimension of the Precast Apron End Wall of this size is 17' wide. The short side is 12' wide. Can the spacing between the runs be more than 3' to accommodate the apron endwalls or should it be cast-in Place? |  |  | 11 | 2023-02-10 10:42
20230214 | 20230214045 | 45 | Joint Specification for 72"x113" HE RCP CL4 | Can you confirm that a mortar joint that meets ASTM C990 is acceptable in lieu of ASTM C443? |  |  | 12 | 2023-02-10 10:44
20230214 | 20230214046 | 46 | U Beam Details | The plans have one cross section showing voids in the beams, but they are not called out anywhere else on the plans. How can I find out if they will be solid or will need voids? |  |  | 1 | 2023-02-10 11:26
20230214 | 20230214045 | 45 | 72"x113" RCP HE CLASS IV | Sheet 114 of the project plans call for a minimum cover of 1' of backfill structure type B from the top of the pipe to the subgrade. As per the fill height tables under the WisDOT Facility Design Manual Section 13 Drainage Practice Attachment 25.9, the minimum cover required for a CLIII and CLIV RCP is 1'. (https://wisconsindot.gov/rdwy/fdm/fd-13-01-att.pdf#fd13-1a25.9). Is a CLIII acceptable in lieu of a CLIV 72"x113" RCP HE? |  |  | 13 | 2023-02-10 12:55
20230214 | 20230214045 | 45 | 72x113 RC apron endwalls SP 20 line item 0180 | Is there a detail for the 72x113 RC Apron Endwall? The SDD for aprons contained in the plan set does not detail that size or shape. Please provide so that it can be bid accordingly. Thank you. |  |  | 14 | 2023-02-10 16:16
20230214 | 20230214021 | 21 | Grubbing | Is removal of the trees downed by others, incidental to the grubbing item? |  |  | 1 | 2023-02-13 09:42
20230214 | 20230214012 | 12 | Grubbing | Is removal of the trees downed by others, incidental to the grubbing item? |  |  | 3 | 2023-02-13 09:44
20230214 | 20230214020 | 20 | Grubbing | Is removal of the trees downed by others, incidental to the grubbing item? |  |  | 2 | 2023-02-13 09:45
20230214 | 20230214019 | 19 | 20230214019 | SPV47 FLA 28-FOOT ALUMINUM LIGHT POLE SPECIAL 35 It seems to me like they are using some of the 657 stuff with the Special pole. They are mounting a LED roadway fixture on these called out in the SPV. SPV pole flagpole canâ€™t quote without: need locations and length of banner arms on this to design wall required. Banner size would be good to have too. |  |  | 5 | 2023-02-13 11:15
20230214 | 20230214045 | 45 | 72"x113" AEWs | Can WIDOT provide a detail for the Apron Endwalls for Culvert Pipe RCHE 72x113-Inch? |  |  | 15 | 2023-02-13 11:18