## qandasearchletting_results
Date: | 2023-05-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230509 | 20230509003 | 3 | Construction staking | There is a slope staking quantity but no cross sections. There is no item for electrical staking. Could you please clarify? | An Addenda will be issued. Slope staking will be removed, and electrical staking will be added. | Mike Coleman | 1 | 2023-05-01 13:15 | 2023-05-03 10:59
20230509 | 20230509004 | 4 | Footing for S-67-613 | Will the footing for this re-installation be based on the current footing or a new style footing for this structure? Is there a detail for what footing is anticipated? | The re-installation will be on a footing matching the existing footing. Page 23 of the plan has details for the base. The contractor will need to verify the existing bolt pattern so that the new base has the correct bolt pattern. | Mike Coleman | 1 | 2023-05-05 08:12 | 2023-05-08 07:39
20230509 | 20230509005 | 5 | 643.0900 Traffic Control Signs | Miscellaneous Quantity table for Traffic Control Signs appears to be overstated. WB 794 shows 80 days x 14 ea, which should total 1,120 days; but the total shown for this line is 12,800 days. The same error is on the EB 794 line; 65 days x 9 ea, which should be 585 days; but the total is again shown as 12,800 days. This item is overstated by 23,895 days not counting the Undistributed days. Can this quantity be revised? Thanks | The items will be addressed via addendum. | Mike Coleman | 1 | 2023-04-26 15:48 | 2023-05-01 10:24
20230509 | 20230509008 | 8 | Misc Quantities Earth work calculations | Can the earth work quantity table be adjusted / Addressed on sheet 102 of the plan set. The quantities shown are not adding up in in their totals. I believe there might be several typos / emissions. Can this be reviewed and adjusted? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2023-05-01 17:36 | 2023-05-03 06:18
20230509 | 20230509010 | 10 | Plans and Specs | Pay items 66 & 68 are for 3 LT and 4 LT respectively which matches the mix types on pages 2 of the plans and match the tonnages shown in the table shown on sheet 550 of the plans for the frontage road HMA but the plans call out for 3 MT and 4 MT. What mix type is to be used for the frontage road binder/surface? | The Frontage Road shall be paved with 3MT and 4MT mix types. An addendum will be issued to clarify the requirements. | Mike Coleman | 1 | 2023-04-24 14:42 | 2023-04-26 11:33
20230509 | 20230509010 | 10 | Acceptance Criteria for HMA | There does not appear to be an Acceptance Criteria Table for HMA provided in the planset. Can one be provided to show the QMP/PWL density breakdowns? | The HMA PWL Incentive Density Eligibility Table shown on page 500 of the plans will be revised through an addendum to clarify QMP/PWL breakdowns. | Mike Coleman | 2 | 2023-04-25 08:15 | 2023-04-26 11:34
20230509 | 20230509010 | 10 | manhole and inlet adjustments | Would the Department entertain making pavement replacement NOT incidental to the adjusting and reconstructing manhole and inlet items? | The Department will not make an adjustment to bid items, please bid according to the plan as shown. | Mike Coleman | 3 | 2023-04-26 14:36 | 2023-05-01 10:33
20230509 | 20230509010 | 10 | SPV006033 & 34 Spread footing | Is there a detail for these spread footings? | Yes, please see page 683 for S-67-1489-001 and page 684 for S-67-1489-002. The MQ table (page 539) and the traffic signal plans (page 268) show that item SPV.0060.33 is for structure S-67-1489-02 and item SPV.0060.34 is for structure S-67-1489-01. | Mike Coleman | 4 | 2023-05-04 11:16 | 2023-05-05 06:38
20230509 | 20230509010 | 10 | Can the design schedule be provided? | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/9tmjfgylzagwd6rt9p004blho2t7vyh0 or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 5 | 2023-05-08 05:22 | 2023-05-08 08:32
20230509 | 20230509010 | 10 | Quantity Base Patching. | It appears the designer figured there would be around 1000 syds of Base Patching and SHES Base Patching according to the Miscellaneous quantity sheets. The Department then added roughly 6400 syds of undistributed quantity. There is obviously a very large increase in cost if the quantity is 1000 syds vs nearly 8000 syds spread over the area of the entire 370,000 syd of milling and asphalt paving. Can the Department provide some type of assurance the quantities for these two items will be approximately what the bid quantity is? |  |  | 6 | 2023-05-08 10:07
20230509 | 20230509011 | 11 | HAULING EXCESS SHOULDER MATERIAL & FINISHING ROADWAY/SHAPING SHOULDERS | Greetings, Two questions: 1.) On page 12 of the Proposal you state under the "Hauling Excess Shoulder Material" special provision that the engineer will direct us to move excess materials to areas of deficiency. Where exactly are these areas and how much material per location will there be. 2.) On page 7 of the plan the "typical sections - proposed" sheet you show a detail for "proposed typical section shoulder milling detail". In the detail you show "regrade shoulder under finishing roadway item". Should this actually say regrade shoulder under shaping shoulders item? | 1. Hauling excess shoulder material will be called out to replace the borrow item. An addendum will be issued to clarify. 2. The note â€œregrade shoulder under finishing roadway itemâ€ was an error. Regrading the shoulder will be part of the Preparation of Foundation for Asphaltic Shoulders or Shaping Shoulders depending on the location. An addendum will be issued to clarify. | Mike Coleman | 1 | 2023-04-26 11:00 | 2023-05-02 05:41
20230509 | 20230509011 | 11 | Asphaltic Surface Patching | There is 1,194 tons of Asphaltic Surface Patching in the contract and there is no item for removing the existing pavement. Can the Department add an item for distressed milling or equivalent to the contract? | See addendum #01. | Mike Coleman | 2 | 2023-05-02 14:20 | 2023-05-03 07:33
20230509 | 20230509011 | 11 | ASPHALTIC SURFACE PATCHING | On sheet 10 of the plan set the detail references "asphaltic repair" however the only item in the pay items is "asphaltic surface patching". What is your intention for paying for the milling out of the areas that will require asphaltic surface patching? | see addendum #01 | Mike Coleman | 3 | 2023-05-02 17:16 | 2023-05-03 07:34
20230509 | 20230509012 | 12 | Culvert Bid Items | Would the department be opposed to issuing an addendum to allow for Class IIIA or Class IIIB culvert bid items to â€œClass III-A and Class III-B items â€¦ to introduce potential project cost reductions into the competitive bid process by allowing the contractor to select from multiple material options for pipes sized up to 36 inchesâ€ (FDM 13 â€“ 15.2 par. 3) | The proposed culverts do not meet the conditions required in FDM 13-1-15 in terms of size of culvert, shape of culvert or do not have the required two feet of subgrade cover. No addenda related to pipe materials will be issued. | Mike Coleman | 1 | 2023-04-20 16:11 | 2023-04-25 10:28
20230509 | 20230509012 | 12 | Excavation & Cross Sections at C-51-10 | Please provide roadway cross section at C-51-10 and please clarify how pavement removal, subgrade removal and any backfill under the subgrade between the culvert top and the pavement will be paid via bid items. | The removal of the material on top of box C-51-10 to complete the repairs will be paid as part of bid item â€˜Excavation for Structures Culverts C-51-10â€™, which also includes additional excavation needed for structure repairs. The saw cutting of the pavement would be paid separately. The replacement of the material over the box will be completed per the details in the plan â€“ see page 298 for the â€˜Box Culvert Backfill Detailâ€™, and page 13 for the â€˜C-51-10 Pavement Replacement Detailâ€™. Materials used to replace the pavement over the repaired structure will be paid per the contract items noted in the detail on page 13. | Mike Coleman | 2 | 2023-05-04 14:48 | 2023-05-05 09:33
20230509 | 20230509013 | 13 | storm sewer items | Would the Department be opposed to issuing an addendum to allow for Class IIIA or Class IIIB storm sewer bid items in lieu of the sole specified Class III RCP items â€œto introduce potential project cost reductions into the competitive bid process by allowing the contractor to select from multiple material options for pipes sized up to 36 inchesâ€ (FDM 13 â€“ 15.2 par. 3) | Proposed project 2340-00-79 has one small segment of storm sewer in the shoulder. Per FDM requirements cover conditions do not allow the use of Class IIIA or B materials for this segment of storm sewer. Proposed project 2698-03-70 replaces the storms sewer laterals to match proposed curb line. Per FDM requirements on cover conditions and FDM designer discretion on material consistency / short runs, Class IIIA or B materials will not be allowed for these segments of storm sewer. | Mike Coleman | 1 | 2023-04-25 16:12 | 2023-04-27 07:44
20230509 | 20230509013 | 13 | 17. Notice to Contractor â€“ Material Stockpile | "Material stockpiles on STH 20 or CTH ES west of the I-43 SB ramps is not allowed unless the engineer approves otherwise in writing." Can you please define a stockpile? More detail, 1' high topsoil berm, load of pipe, dump truck load? This is very restrictive and will greatly increase the cost and the amount of time on this project. This language should be removed. | An addendum will be issued to clarify. | Mike Coleman | 2 | 2023-05-01 09:33 | 2023-05-03 08:26
20230509 | 20230509013 | 13 | Excel Spreadsheet Data | Can the Excel Spreadsheet be provide for the Earthwork Summary, Earthwork Data Sheets, Storm Sewer Structures, Storm Sewer Pipe and Culvert Pipe? | The requested excel files can be found at the following location: https://wisdot.box.com/s/ri9ue1f18l9unldbkgaw8y58zpor981j or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-05-02 12:39 | 2023-05-03 11:04
20230509 | 20230509013 | 13 | 3. Prosecution and Progress. - Operations | Page 6 of 106 under Operations paragraph #2, "Within 96 hours of removing the existing pavement structure and base course from any location along the roadway, construct that portion of the roadway by cutting / filling the final subgrade, placing breaker run and the first lift of base course. and then 48 hours for forecasted rain" This language needs to be removed. This is not possible, this contract also has storm sewer and water main work that has to happen after the pavement is removed and before Breaker Run can be placed and hopefully is doesn't rain in East Troy for the next 2 years. Also it appears that this project will not allow the pavements to be recycled on this project because 96 hours is not enough time from removal to placement. This is unrealistic language and needs to be removed. | An addendum has been issued to remove the existing pavement structure from the second paragraph under the section titled Operations. | Mike Coleman | 4 | 2023-05-02 13:10 | 2023-05-05 06:35
20230509 | 20230509013 | 13 | 41. Topsoil and Salvaged Topsoil | Per this language, "Ensure that for the upper 2 inches, 100 percent of the material passes a one-inch sieve and at least 90 percent passes the No. 10 sieve.", it appears both Salvaged Topsoil and imported Topsoil must be screened for the top 2"? Or will the DOT accept the use of a Harley Rake to process the placed topsoil inplace that mostly meets the one-inch sieve requirement? If not it appears the existing topsoil must be stockpiled somewhere, which has to be approved by the engineer, where on the project will this be allowed? Will the contractor be allowed to use the Southeast Gore area of IH-43 & STH 20 for stockpile area and staging area? There are some trees that need to be cleared, will WisDOT REC approve those to be cleared for Stage 1 construction? | The department does not specify the means and methods used. Material must meet the requirements specified in the special provision. Stockpiles, as answered in question #2, will be revised in an upcoming addendum. | Mike Coleman | 5 | 2023-05-02 13:57 | 2023-05-03 11:13
20230509 | 20230509013 | 13 | 71. 8-inch Gate Valve & 12-inch Butterfly Valve - " milling, asphalt, HMA pavement" | For the bid items 8-inch Gate Valves and 12-inch Butterfly valves, the special provisions state: "Payment is full compensation for milling existing pavement,...asphalt base patching, and HMA pavement...and restoring the site." There are (5 each) 8'inch Gate Valves and (9 each) 12-inch Butterfly Valves. A vast majority of this work is in reconstruct locations. The 8" Water Main, Edwards Street special provision has similar language. An Edwards Street Utility Trench Detail is given in the plan. Can more detail be given as to where the milling existing pavement is expected to occur? Also, other than the utility trench in Edwards Street, where is the asphalt patching and HMA pavement intended for? These costs are incidental to the three mentioned water main items. There is currently no way to accurately estimate costs for this work. | Milling, asphalt patching, and HMA pavement are intend for use on Edwards Street outside of the reconstruction limits. | Mike Coleman | 6 | 2023-05-04 13:11 | 2023-05-08 09:52
20230509 | 20230509014 | 14 | Base Patching | 1. Is base patching to be performed under flagged traffic or under a closed lane? 2. Per the note on page 12 it appears the asphalt for base patching will be paid under item #46 Asphaltic Surface. If so, what is item #32 for? Are these in conflict? Will we be requited to use 1" aggregate (25mm binder) for the base patching per spec 315.2?? Will this work be performed prior to the 4" milling? | 1. Base Patching Asphaltic will need to be completed under flagging operations during the hours of 8am -3:00pm (Monday â€“ Friday) specified in the special provisions. 2. Addendum #1 will be issued to resolve this issue. Item 465.0105 Asphaltic Surface will be removed from the project and the asphaltic material for the base patching will be the material specified under item 390.0203 Base Patching Asphaltic. The base patching will need to take place prior to milling the pavement during stages 1 and 2A. Locations of patching will be marked out by the engineer. | Mike Coleman | 1 | 2023-04-18 12:34 | 2023-04-18 13:17
20230509 | 20230509014 | 14 | Asphalt Base Patching/Removing Concrete Pavement | Is the 260 SY of the item Removing Concrete Pavement the 260 SY of concrete removals needed for the Asphaltic Base Patching item? | The intent is to use the 260 SY for the patching item. | Mike Coleman | 2 | 2023-05-04 16:03 | 2023-05-05 09:37
20230509 | 20230509015 | 15 | Federal Aviation Administration Coordination | We are wondering why there is a FAA coordination requirement on this project? If required, a 90 day notice is not feasible for a project that will have to start in 60 days or less. Listed on page 4 of 60 |  |  | 1 | 2023-05-04 12:02
20230509 | 20230509016 | 16 | Typical Section Milling | Sheet 9 of the plan shows the binder at what looks to be 11' @ a 2% cross slope and the surface lift is a 12' @ 2% cross slope with a 5' 4% shoulder slope. Was the intent for the binder to be 12' @ a 2%? The reason for this question is the shoulder milling will be extremely difficult and costly as shown in the plan to mill ~1' @ a 2% and 5' @ a 4%. It may also create reflective cracking at 11' in the surface. | The binder was not intended to be 12 feet at 2 percent, the typical section is correct as shown. Because there is 22 feet (11 feet per side) of a 5-inch asphaltic pavement structure under the mainline, a 3.5-inch milling and paving operation can be used without compromising the underlying existing pavement. Between the 11 and 12-foot offset, the existing pavement structure is only 4.5-inches and, if milled to a 3.5-inch depth, would leave only 1-inch of existing pavement to remain. Extending the binder at a 2 percent cross slope to the full 12-foot width would potentially compromise the underlying 1-inch pavement structure and may increase the likelihood of unforeseen repairs and quantity overruns if the 1-inch of remaining pavement is disturbed or fails. Itâ€™s understood that additional milling passes may be needed to accommodate the proposed typical section. | Mike Coleman | 1 | 2023-05-02 16:41 | 2023-05-04 06:04
20230509 | 20230509016 | 16 | Staging at where STH 120 Crosses I 43 | There are 4 stages for the work between STA 520+83 and STA 557+07. Can the contractor propose alternate staging and try to overlap the stages? | An alternate staging plan can be proposed, but ultimately must adhere to the Traffic and Prosecution and Progress sections of the special provisions, particularly regarding where local and full access should be maintained for STH 120, Honey Creek Road, and the IH-43 interchange ramps. The maximum length of time that closures are permitted, outlined in the Prosecution and Progress article, must be followed and a final staging plan must be approved by WisDOT. | Mike Coleman | 2 | 2023-05-08 07:03 | 2023-05-08 09:19
20230509 | 20230509016 | 16 | Can the Design Schedule be provided? | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/xkb2snm86d1y5acpf33btq3s3g44tqpx or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-05-08 07:04 | 2023-05-08 09:05
20230509 | 20230509017 | 17 | Item # 22 Abandoning Well | Does the Department have any additional information on this well. An ID number, depth, any pumping hardware in it? | The Department does not have additional information regarding the well. | Mike Coleman | 1 | 2023-05-03 12:11 | 2023-05-05 06:38
20230509 | 20230509018 | 18 | Asphaltic Seal Applied to Underseal Coated Areas | In the specials #23, page 36, section C, paragraph (2) the last bullet point states â€œ Dilute the material at a ratio of 1:1 before application at place of manufacture.â€ Would the Department allow for the ratio to be greater than 1:1 for the material? | The material is being diluted to avoid bleeding that can occur when too much asphalt binder is used in the underseals. The dilution of the material at a ratio of 1:1 or a lower application rate of the 85/15 ratio will be allowed to avoid a bleeding issue. | Mike Coleman | 1 | 2023-04-26 15:03 | 2023-05-02 09:33
20230509 | 20230509018 | 18 | Asphaltic Pavement Underseal | In the specials #23, page 36, section C, paragraph (3) states Pave HMA Pavement overlay within 48 hours on pavement underseals applied after September 1.â€ Would the Department consider changing this to 96 hours? Within the P&P Section under milling and paving Operations we have 96 hours to cover up the milled surface with either asphaltic surface layer or asphaltic underseal, while also providing an even cross section profile of the roadway each day of milling. To construct this within the current time restrictions would be difficult due to the milling, widening, underlayment, and paving being in such a tight area. This would increase the hazards to the public as well as the contractor. There would also be increased costs due to additional mobilizations to meet the set requirements. | The Department finds it acceptable to allow 96 hours to pave HMA pavement overlay on pavement underseals applied after September 1. An addendum will be issued. | Mike Coleman | 2 | 2023-04-26 15:05 | 2023-05-02 09:34
20230509 | 20230509018 | 18 | Schedule | Would the Department provide their construction schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/ax7umccuoxr5xhdvgjh2l5cuhu5xzq9h or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-04-26 15:06 | 2023-05-01 10:30
20230509 | 20230509018 | 18 | Barrier System Grading & Shaping Item | Can an item, 614.0010 Barrier System Grading Shaping Finishing, be added for the 17 MGS guardrail Terminal EATs included in this project. | Item is not required on ID 1491-23-71 and ID 9560-06-71 as no widening beyond the existing subgrade shoulder point is required to complete the work. Minor shoulder shaping is depicted on cross sections and paid under the base aggregate dense ï¿½-inch item. All grading and shaping required on ID 9560-06-72 is illustrated on cross sections and volumes are included on earthwork detail sheets. This work is being paid under contract earthwork and finishing items. | Mike Coleman | 4 | 2023-05-02 13:27 | 2023-05-03 06:20
20230509 | 20230509019 | 19 | Railroad Movements | Article 13 indicates thee are 45 through trains and several switch movements daily through the project. If this is correct, there would be on average, one train movement every half hour every day. Is this accurate or has there been a typo? | Yes, Article 13 stating there are 45 train movements daily is accurate. | Mike Coleman | 1 | 2023-04-25 10:15 | 2023-04-26 07:31
20230509 | 20230509019 | 19 | Schedule | Is the design schedule available for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/cfw4d0hv1at1i75w7nxclankrnax8bze or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-05-02 08:59 | 2023-05-02 10:45
20230509 | 20230509019 | 19 | Watermain | SPV Article 5 states that the existing 10â€ watermain is buried under the streambed and runs through both of the existing bridge abutments. The water main will be capped and either be filled with slurry or pressure grouted. What is the depth of this watermain at proposed substructure units? | The utility map from the City of Fond du Lac at this crossing can be found at the following location: https://wisdot.box.com/s/cfw4d0hv1at1i75w7nxclankrnax8bze or can be accessed on the HCCI May bid letting page under Supplemental Information. Based on the generic elevations provided in this detail along with the existing structure plans and the project survey data, the approximate elevation of the top of the watermain would be 738.71 at the east abutment, 737.38 at the west abutment, and 737.64 at the pier. | Mike Coleman | 3 | 2023-05-02 08:59 | 2023-05-02 10:51
20230509 | 20230509019 | 19 | Train Traffic | Following up on question 1, with approximately 1 train every half hour and the contractor typically being shut down 15-20 minutes prior to a trainâ€™s arrival, how does the department expect the contractor to build the job with these short windows? | WisDOT built 3 much more complex track carrying structures on this line just South of here with the same amount of train traffic. It takes close coordination with the railroad and the railroad flaggers. Much of the work can be done without stopping if you are more than 25 feet from the RR. Certain equipment like cranes will need to stop working. Note about 15 of the trains are just a single helper locomotive coming northbound that disconnects from the southbound trains after assisting to get up Byron Hill South of Fond du Lac. Also note that setting the crane east of the bridge and arranging with the RR to meet their requirements, much of the work can in theory be done without a RR flagman. | Mike Coleman | 4 | 2023-05-02 09:00 | 2023-05-03 08:43
20230509 | 20230509019 | 19 | West Abutment Temporary Bracing | SPV Article 37 states that temporary bracing will be required to support the west abutment at locations where the abutment is located within the railroad shoring requirement limits for WCL. The contract documents do not provide the design capacity of the existing west abutment, which is needed to determine the bracing requirements. Will the department provide this information? | No, the department will not be providing this information. The existing structure plans are available on the DOTâ€™s HSI site. | Mike Coleman | 5 | 2023-05-02 09:00 | 2023-05-02 13:09
20230509 | 20230509019 | 19 | Construction Vibrations | In reference to SPV Article 34 and SPV Article 35, which requires visually inspecting and recording all ground surface and structure conditions within 200 feet of vibration activities. Has anyone inspected the existing buildings prior to their ongoing renovation? As renovation continues through bridge construction, how will changes to building be documented? | No inspections have been completed for the existing buildings prior to their ongoing renovation. Follow the requirements in the Special Provisions for these bid items for monitoring during construction. | Mike Coleman | 8 | 2023-05-02 09:01 | 2023-05-02 13:08
20230509 | 20230509019 | 19 | Staining | Structure plan sheet 17 shows the limits of concrete staining multi-color. This limit is below the water line based on the observed water elevation provided in the plan. SPV Article 28 states the concrete stain shall be applied when the temperature of the concrete surface is 45 ï¿½ F or higher and after 28 days of cure. Will the department waive this requirement, or will we be required to keep our cofferdams in place for 28 days after placing abutment concrete? | Due to proposed construction schedule changes that occurred late in the design stage, the decision has been made to hold the limits of Architectural Surface Treatment and Concrete Staining Multi-Color to 6â€ above the water line. Use the observed water elevation shown on the plans as a starting reference point for bidding. | Mike Coleman | 9 | 2023-05-02 09:01 | 2023-05-02 13:11
20230509 | 20230509019 | 19 | Cut Stone Boulders | Do outcropping stones meet the standards for the cut-stone boulder item or do they need to be completely flat on all sides to meet the specifications? | The cut-stone boulders do not need to be completely flat on all sides. Acceptable cut-stones boulders should meet the material, size, and placement requirements as detailed in the plans and the item Special Provision. Examples of cut-stone boulders can be found at the following location: https://wisdot.box.com/s/3yrgc8b8lzybfkl2utgej7680250vsys or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 10 | 2023-05-05 09:32 | 2023-05-05 11:20
20230509 | 20230509021 | 21 | SPV item for Screened Breaker Run - Specification? | Can you tell us what the City of Marshfield's Standard Specification for screened breaker run is that is referenced in the specials? If different than the WisDOT 312 Select Crushed, could it be an option for this SPV item? | An addendum will be issued to add a special provision that adds a link to the City of Marshfield's standard specification. | Mike Coleman | 1 | 2023-05-01 14:11 | 2023-05-02 09:31
20230509 | 20230509022 | 22 | Full Containment of bottom flange painting | Will entire length of bottom flange of exterior girders need to be fully contained or is hand tool cleaning acceptable for these areas and full containment of end 5' only? | Full containment only of the end 5â€™ is required; the remaining length between each 5â€™ end zone may be cleaned using power tools in accordance with SSPC SP 15. | Mike Coleman | 1 | 2023-05-04 14:36 | 2023-05-05 07:48
20230509 | 20230509023 | 23 | Item 614,2610 MGS Guardrail Terminal EAT | In the AASHTOWare Projects bid for the project, this item has a fixed unit price of $3750.00/EACH. Why is this? Typically fixed unit prices are only used for incentives and OJT payments. | An emergency addendum has been issued to correct this. | Mike Coleman | 1 | 2023-05-05 10:12 | 2023-05-05 11:21
20230509 | 20230509023 | 23 | Backfill Granular Grade 1 | Why is Backfill Granular Grade 1 being used to backfill the EBS topsoil in Stage 1 crossover construction? It seems that Borrow (or Select Borrow) would be a more appropriate item to put in the bottom of the crossover. With no drainage allowed for in this layer (trapped in the median) it seems that Backfill Granular Grade 1 would promote water to get trapped under the crossovers? | The layer is anticipated to drain due to longitudinal grade and/or no water encountered during investigations during design. The Region prefers to use the Backfill Granular Grade 1. Bid the project as shown. | Mike Coleman | 2 | 2023-05-05 10:23 | 2023-05-08 07:41
20230509 | 20230509024 | 24 | Existing Girder Condition | Due to the disrepair and condition of the prestressed beams has the department considered replacement of the prestressed girders? | The existing bridge is timber and being completely replaced. | Mike Coleman | 1 | 2023-05-05 20:01 | 2023-05-08 08:28
20230509 | 20230509025 | 25 | Temporary markings. | It appears this project should have a temporary pavement marking, epoxy bid item added so that the center line is delineated daily after paving. Will the department be issuing an addendum to add this item? Thank you. |  |  | 1 | 2023-04-28 06:44
20230509 | 20230509025 | 25 | Mudjacking Approaches | Is the intent to raise the existing approaches or to fill the voids under the approach? The Special Provision describes drilling holes and filling voids and not raising. | The intent is to fill the voids, not raise. | Mike Coleman | 2 | 2023-05-04 09:13 | 2023-05-04 09:38
20230509 | 20230509028 | 28 | Clearing | It appears that others have completed the clearing for the project. However, it does appear that there are several trees that could potentially be in conflict with construction activities, specifically with the grading and storm sewer on the west side of the structure. Will these trees be removed prior to construction? | All trees envisioned needing to be cleared have been taken down. Other trees will need to remain in place. | Mike Coleman | 1 | 2023-05-03 09:51 | 2023-05-04 06:05
20230509 | 20230509028 | 28 | Removing Storm Sewer | There appears to be some sort of concrete structure or vault sitting directly above the existing storm sewer in the NW quadrant adjacent to the abutment of the existing bridge. What are the expectations for the final product in that quadrant? Is the concrete vault to be removed as well? | Existing concrete vault will be removed as part of the project. | Mike Coleman | 2 | 2023-05-03 09:59 | 2023-05-04 06:05
20230509 | 20230509028 | 28 | Existing Landscaping | The property owner in the NW quadrant has a variety of landscaping along the driveway, ditch, and backslope. What is happening with the existing landscaping and does any of it need to be replaced? | Landscaping in this area will not be replaced as part of the project | Mike Coleman | 3 | 2023-05-03 10:08 | 2023-05-04 06:05
20230509 | 20230509028 | 28 | Existing Girder Condition | Due to the disrepair and condition of the prestressed beams has the department considered replacement of the prestressed girders? | With most of the deterioration at the girder ends and the proposed encapsulation in the concrete abutment diaphragms, it was determined that the girders could remain. | Mike Coleman | 4 | 2023-05-08 08:39 | 2023-05-08 09:16
20230509 | 20230509030 | 30 | Bid Item - 0328 SPV.0165 Special 01. Fiber Wrap Reinforced Non-Structural | Please provide a Special Provision for this bid item | An addendum will be issued to add the special provision. | Mike Coleman | 1 | 2023-04-10 14:59 | 2023-04-12 05:50
20230509 | 20230509030 | 30 | Anchored Barrier | The Temporary Barrier on Structure B-67-152 requires it to be anchored in stage 1. Should a bid item be created for anchoring the Temporary Barrier? | Yes, a bid item for anchoring the Temporary Barrier will be part of the forthcoming addendum. | Mike Coleman | 2 | 2023-04-19 11:55 | 2023-04-25 10:26
20230509 | 20230509030 | 30 | Temporary Sheet Piling | Plan sheets 39, 40 and 41, as well as Article 11 of the Special Provisions discuss the use of Temporary Sheet Piling at the abutment (shoreline) locations for Structures B-67-377,378 and 379. How is this paid for? Could a bid item be created for this requirement? | Bid item 512.1000 Piling Steel Sheet Temporary is already part of the project. | Mike Coleman | 3 | 2023-04-19 11:58 | 2023-04-25 10:26
20230509 | 20230509030 | 30 | Bird Deterrent System | In regards to Structure B-67-152, since we are past April 15th, did the Department engaged the county yo install the bird deterrent system on this structure or will the schedule require the contractor to wait until after August to begin work? | The contractor will have to wait until after August 31st, if there are active nests present. | Mike Coleman | 4 | 2023-04-19 12:15 | 2023-04-25 10:26
20230509 | 20230509030 | 30 | Northern Long Eared Bat Restriction @ B-67-0377 | The project site for structure B-67-0377 has 4 stations of clearing & grubbing. Is it the intent that work at this site cannot start until after 10/31/2023? | Yes, that is correct. | Mike Coleman | 5 | 2023-04-20 11:01 | 2023-04-25 10:25
20230509 | 20230509030 | 30 | Distressed Pavement Replacement | Please review the Asphaltic Surface quantity for the "Distressed Pavement" replacement. Bid item only has a total of 18 tons for 11,380 sy. | There is an error in the calculation of the asphaltic surface, as mentioned. An addendum will be issued to address the quantity revision. | Mike Coleman | 6 | 2023-04-21 11:08 | 2023-04-24 08:54
20230509 | 20230509030 | 30 | 3. Prosecution and Progress - Construction Staging | In the section listed as Constuction Staging - USH 18 General Project Construction. Construct Structure B-67-377 and approaches and Construct Structures B-67-378 and B-67-389 {supposed to read B-67-379 I assume) are separate bullet points. Does that mean that structure B-67-377 and approaches are to be constructed first and be completed before B-67-378 & 379 are built concurrently? With the number of date restrictions, Fish Spawning, NLEB tree clearing, Migratory bird restrictions and Utility movement (complete mid November 2023) can the Department supply a copy of their preliminary schedule to show when they were anticipating these structures would be built? | Based on the amount of work, probable work days, and date restrictions, it is anticipated that two of the bridges will need to be worked on concurrently in order to meet the completion date. However, which structures and the order can be adjusted/determined by the contractor. The design schedule can be found at the following location: https://wisdot.box.com/s/2orzzhkwb1h2b20g79bi7tkzy7i8ioeb or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2023-04-25 13:35 | 2023-05-08 10:04