## qandasearchletting_results
Date: | 2023-10-16
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20231017 | 20231017001 | 1 | Parking & Storing | SPV Article 8 states: "Do not park or store any vehicle, piece of equipment, or construction materials on the right-of-way, unless otherwise specified in the traffic control article or without approval of the engineer." Will the engineer approve vehicles, equipment, and/or construction materials being parked or stored on the right-of-way within the 16' work area behind the concrete barrier temporary precast? | Parking or storing of vehicles, equipment, and/or construction materials that is completely behind the temporary concrete barrier would be allowed. However, per the plan detail, nothing will be allowed within 4â€™ of the back of the barrier. | Mike Coleman | 1 | 2023-10-02 09:21 | 2023-10-02 12:32
20231017 | 20231017001 | 1 | Field Office | Is a field office necessary given the project duration is less than two weeks? | Yes, a field office is required. | Mike Coleman | 2 | 2023-10-02 10:02 | 2023-10-02 11:38
20231017 | 20231017001 | 1 | Barrier Pad | Does the concrete barrier pad need to be removed and replaced or just the wall? | The concrete barrier pad does not need to be removed or replaced. | Mike Coleman | 3 | 2023-10-02 10:32 | 2023-10-02 11:44
20231017 | 20231017001 | 1 | Adhesive Anchor Depth | Is note 810 on SDD 14B32-10h indicating the embedment depth of the adhesive anchors is 3'? Maximum shear and tension strengths for adhesive anchors are achieved at significantly lower embedment depths (12" +/-). 3' embedment depth is excessive, assuming that what note 810 is indicating. | The 3â€™ embedment depth has been confirmed to be correct. | Mike Coleman | 4 | 2023-10-02 10:42 | 2023-10-02 12:33
20231017 | 20231017001 | 1 | Time frame for setting up and removing traffic control | Are there any time requirements, such as night time work, for setting up and taking down traffic control items? | Based on existing traffic volumes, the set-up and takedown of traffic control items should avoid the hours from 7:00-8:00 AM and from 3:00-6:00 PM. An addendum will be forthcoming to address this item. | Mike Coleman | 5 | 2023-10-09 08:42 | 2023-10-09 11:15