## qandasearchletting_results
Date: | 2024-01-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20240109 | 20240109003 | 3 | Cofferdam Gas Main Conflict | Now that an item for cofferdams has been added to the contract, has the Department coordinated with Madison Gas & Electric for additional gas main relocation work as the recently added cofferdam will be in conflict with the existing gas main? | An addendum will be issued to address the conflict in the utilities article. | Mike Coleman | 2 | 2024-01-03 14:34 | 2024-01-04 16:25
20240109 | 20240109003 | 3 | Turbidity Barrier | The stated velocities of the water in the plan are 5.8 fps. FDM 10-10-45.3 recommends against turbidity barrier at velocities over 5 fps. The 5.8 fps in the plan also doesn't account for the reduced stream width once the turbidity barrier is in place, likely increasing velocities further. Will the Department consider other BMP's for stream diversion? | Due to the water velocities, we will be removing the turbidity barrier bid item and adding the bid item 206.5001 Cofferdams (B-13-0871) for stream diversion. An addendum will be issued for this change. | Mike Coleman | 1 | 2023-12-14 10:01 | 2023-12-18 13:04
20240109 | 20240109005 | 5 | Geotechnical Data | Can you provide any geotechnical data for this project area? | The soils report and hazmat report can be found at the following location: https://wisdot.box.com/s/y7rpyuxycpyhx5pg7y7pys6bquqoepsr or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-01-04 07:23 | 2024-01-04 15:37
20240109 | 20240109005 | 5 | EBS Backfill | On the Earthwork Summary is says EBS is to be backfilled with Select Crushed Material and in review of the Select Crushed Summary it only shows 400 tons of undistributed quantity which is not enough to backfill 2,155 CY of EBS. It appears more Select Crushed Material should be added. Please confirm. | The quantity of Select Crushed Material for backfilling EBS areas is included in the â€œmainâ€ quantity for each stage. As part of an upcoming addendum, this quantity will be separated for clarification. | Mike Coleman | 1 | 2023-12-21 08:40 | 2023-12-22 11:42
20240109 | 20240109006 | 6 | Common Excavation | Page 19 of plan set shows 619 Cy common but 731 Cy waste. Is the table missing information? If not, can you explain more in depth the table details. | If I understand this question correctly, 619 CY of excavation is what we calculated using the average end area procedure. The â€œWasteâ€ table in the plan is a running total, not a line summary. (Which is the â€œMass Ordinateâ€ column in the table.) I believe the person asking the question double counted the first line in the â€œWasteâ€ column to arrive at 731 CY of waste. 619 CY of Excavation is what the MisQs states, which matches the Estimate of Quantities. | Mike Coleman | 1 | 2024-01-02 15:03 | 2024-01-03 12:55
20240109 | 20240109007 | 7 | Work restriction Hours | Does this project have any work restriction hours due to hwy 16 lane closures for the outside and inside lanes, similar to past projects in the area? | As long as the lane configurations stated in the Traffic special provision are maintained, the Department does not anticipate the need for any additional time restrictions on work hours. Work operations between 10:00 PM and 6:00 AM will require Engineerâ€™s written approval according to Standard Specification 107.8. | Mike Coleman | 7 | 2024-01-04 13:56 | 2024-01-05 10:01
20240109 | 20240109007 | 7 | Asphalt Sidewalk | PB5 is in existing asphalt sidewalk this will need to be cut and removed to find the exiting conduit and install the Pull box. Will this be paid for by the items? | If removing asphaltic surface and sawing asphalt are required, the department does not consider this incidental. If needed, the items will be added during construction. Replacement of sidewalk will utilize the Asphaltic Surface item already present in the proposal. | Mike Coleman | 4 | 2024-01-04 11:13 | 2024-01-05 10:04
20240109 | 20240109007 | 7 | County M Road Closure | Traffic Control Stage 2, County M North/South Closed (plan sheets 18-21) - these pages show a road closure on County M, and the details reference: "WORK ON COUNTY M TO BE COMPLETED USING ROAD CLOSED (DETOUR) OPERATIONS. SEE SDD "BARRICADES AND SIGNS FOR VARIOUS CLOSURES"" 1. Is a Detour required for these short-term closures? 2. The above referenced SDD is not included in the plan set 3. If a detour is needed, please issue a plan sheet for approved detour route and/or appropriate SDD sheet. | 1. No signed detour will be utilized, as local roads facilities would be utilized. Road Closure Signs and Barricades would be installed. 2. The following SDD should be included: 15C02-09A BARRICADES AND SIGNS FOR MAINLINE CLOSURES 15C02-09B BARRICADES AND SIGNS FOR VARIOUS CLOSURES 15C02-09C DETOUR SIGNING FOR MAINLINE CLOSURES An addendum will be issued to add these SDD's | Mike Coleman | 2 | 2023-12-20 10:11 | 2023-12-22 11:53
20240109 | 20240109007 | 7 | Staging | We would also like to bore to the median as well to pick up the light pole on the East side of the intersection. We would need to have a the left turn lane closed. Just making sure that this will be okay under the plan closures | As long as a though/right lane and a dedicated left turn lane are provided, the Department can allow for flexibility on which lane is closed at a time (such as using the outside lane as the through/right and the inside lane as the left turn lane such as in Stage 2). If the left turn lane would be returned to use traffic prior to removal of the remainder of the existing left turn lane pavement, the Department would require a temporary pavement surface (HMA or concrete) for traffic to operate on; this would be considered incidental to the work. | Mike Coleman | 5 | 2024-01-04 11:15 | 2024-01-05 10:03
20240109 | 20240109008 | 8 | Concrete Base Patching | Can any of the concrete base patching be done during daytime hours under the permanent lane closure? | As per â€œFreeway and Ramp Work Restrictionsâ€ under the â€Prosecution and Progressâ€ Article in special provisions, there will be no daytime permanent lane closure hours. | Mike Coleman | 8 | 2024-01-02 09:56 | 2024-01-03 12:59
20240109 | 20240109008 | 8 | Extending Closure Times.en | Can the closure and opening times be extended. Can Northbound closures start earlier at night when volumes are not as high entering Milwaukee and can opening times lengthened in the south bound direction when traffic leaving Milwaukee is not as heavy. Every minute helps on nighttime projects and even a half hour increase in time we can work is helpful. | Nighttime closure and opening times must be followed as described in the special provisions under Article Number 3 â€œProsecution and Progressâ€. | Mike Coleman | 6 | 2023-12-23 11:43 | 2023-12-28 08:25
20240109 | 20240109008 | 8 | Can the design schedule be provided?? | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/8xnqem9ccydx8m8eo7i27g71e8rtmndn or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-12-13 07:26 | 2023-12-13 09:44
20240109 | 20240109008 | 8 | 90A Native Pollinator Seed | Can you tell us if the seeding area is about 1.5 acres or is it around 10 acres? The specs arenâ€™t clear if the cover crop should be factored into your application rate but we can figure it out if you know the total area to be seeded. | The designated area for receiving the 90A seeding mix and seeding nurse crop is approximately 5.3 acres, which are shown in the Erosion Control Plans. The 90A seeds should be sown at a rate of 0.245 pounds per 1000 square feet, as specified in the special provisions. The cover crop (nurse crop) consists of various seed combinations listed in the table provided in the special provisions under Article 67 (Native Pollinator Seeding Mixture No. 90A), depending on the timing of installation. Application rate for the cover crop must follow the guidelines outlined in that table. | Mike Coleman | 7 | 2023-12-29 09:46 | 2024-01-03 07:06
20240109 | 20240109008 | 8 | Topsoil | Note #5 on the FTMS Plan overview states topsoil and restoration is incidental to the FTMS items, but the erosion control plan and topsoil quantity for NB I-43 appear to include the restoration in the topsoil item. Should the 20,218 sy of topsoil for category 1,000 IH 43 (NB) be removed from the topsoil item? | Restoration items at the locations where FTMS is constructed are not intended to be incidental to FTMS items. As outlined in the erosion control plans and miscellaneous quantities, these items should be considered as separate payable items. Please disregard note #5, as it should not be taken into consideration within this context. | Mike Coleman | 9 | 2024-01-02 14:13 | 2024-01-04 15:39
20240109 | 20240109008 | 8 | Cleaning Culvert Pipes | The note on the EC pages states to clean all existing culvert pipe ends. How is this being paid? For instance, sheets 91/92 shows EW3 being paid for cleaning on NB lanes. The pipe goes to a median structure, and there is a pipe extending out of this median structure to the NW to EW35 on SB lanes. The MQ's do not list the pipe ending at EW35 being cleaned, though. So, in this instance, how does the endwall EW35 cleaning get paid? There are numerous other instances similar to this throughout the plan, including EW37-EW42, and others. | Cleaning existing culvert pipe ends is to be paid under item 520.8700 Cleaning Culvert Pipes. The Cleaning Culvert Pipes quantity is incorrect and an addendum will be prepared to address this. | Mike Coleman | 2 | 2023-12-14 11:03 | 2023-12-18 11:39
20240109 | 20240109008 | 8 | Emulsified Asphalt | The notes in the MQ's on page 252 state to place emulsified asphalt along existing guardrail. The plan doesn't include bid item 614.0397 for emulsified asphalt, only 614.0396 for asphalt mow strip. Is the intent of the plan to place asphalt mow strip around existing guardrail? | The incorrect bid item is listed for the mow strip. The intent is to use bid item 614.0397 Guardrail Mow Strip Emulsified Asphalt. An addendum will be prepared to address this incorrect item. | Mike Coleman | 3 | 2023-12-14 11:16 | 2023-12-18 11:39
20240109 | 20240109008 | 8 | Fence Woven Wire 6-foot | The SDD doesn't show a fence height of 6-foot. We are unaware of fencing meeting DOT specifications that is manufactured with a 6-foot height. Additionally, the standard fence posts won't be embedded sufficiently for a 6-foot fence. Please advise if this is a typo or if some other detail is to be used for bidding and installation. | The incorrect bid item is listed for the fencing. The intent is to use bid item 616.0206 Fence Chain Link 6-FT. An addendum will be prepared to address this incorrect item. | Mike Coleman | 5 | 2023-12-19 08:44 | 2023-12-21 09:14
20240109 | 20240109008 | 8 | Replacing Guardrail Items | There is at least one guardrail EAT listed using bid items 614.0950 and 614.0951. FDM 11-45 Sections 30.5.2.2 and 30.5.2.3 both state to not use these bid items for EAT's. In light of that, please provide more detail as to which posts in the EAT and which panels in the EAT need replacement. Also, the note on page 81 of the plans states to replace the EAT reflective panel. Is this the plastic marker post or a steel panel in the EAT? | The intent of items 614.0950 and 614.0951 are not to be used within the EAT system. The note on page 81 refers to the reflective sheeting on the EAT system which is under item 816.0953 Replacing EAT Reflective Panel. | Mike Coleman | 4 | 2023-12-14 11:42 | 2023-12-18 11:40
20240109 | 20240109009 | 9 | Stone Veneer Seat Wall Planters "Precast Concrete Signage panel and Pin- Mounted Letters" | In the special provisions it lists under the description " This special provision describes furnishing and installing exterior stone wall veneer, limestone wall coping, and metal flashing; furnish and install concrete footing wall, steel reinforcing, base aggregate, rigid insulation, 4" PVC drain pipe, filter fabric, and drainage aggregate, furnish and install precast concrete signage panels and pin-mounted letters." There is no detail or reference in the plans or specifications on the "precast concrete signage panel and pin-mounted letters". Is this to be included with the Seat wall Planters or is this to be omitted? If to be included can a detail and specification please be provided. | The wording â€œfurnish and install precast concrete signage panel and pin-mounted lettersâ€ can be deleted from the description for the Stone Veneer Seat Wall Planters article. | Mike Coleman | 1 | 2024-01-05 13:56 | 2024-01-08 14:44
20240109 | 20240109010 | 10 | Can the Design Schedule Be Provided? | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/xtu7nafs3xjhik4h6wpqd5k78gvaaf2e or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-12-30 15:42 | 2024-01-03 07:11
20240109 | 20240109010 | 10 | Asphalt patching for loops | Sheets 17-25 show various 5" patching for conduit loops and new curbs. The legend indicates that this patching is to be paid under HMA items. Will this patching be paid under 3MT/4MT or under on the asphaltic surface patching item? Thank you | The areas are paid for based on the layer thicknesses specified in the general notes for 5â€ HMA pavement and those areas are accounted for in the MQs for 3MT and 4MT, not as part of the asphalt patching item. | Mike Coleman | 3 | 2024-01-03 10:49 | 2024-01-04 08:17
20240109 | 20240109010 | 10 | Dowel Bars and Tie Bars | The quantities for the Dowel Bars and Tie Bars seem high and appear to need to be adjusted. | We had some bad math/formulas in that spreadsheet. An addendum will be issued to correct this. | Mike Coleman | 2 | 2023-12-31 09:43 | 2024-01-03 07:13
20240109 | 20240109011 | 11 | Project Schedule | The contract time appears very aggressive to meet the 45 WD contract. Can the project schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/q797xc2rlurqo32syxx1e67fuuoskg8q or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-01-03 09:56 | 2024-01-04 08:15
20240109 | 20240109011 | 11 | Structure 523 | This has 30" pipe running through it. The size needs to be a 60" INL with a 24"x30" opening in the cover with no adjustment due to the shallow design. Can we expect a change? | Revised storm sewer plan sheets and quantities will be provided in Addendum #1. | Mike Coleman | 1 | 2023-12-22 11:02 | 2023-12-26 09:31
20240109 | 20240109012 | 12 | Structure discreptancy | 4.0 is labelled in misc. as a 48" plan and profile shows it as a endwall 4.1 is labelled in misc as a 2x3 plan and profile shows it as a 48" This results as one less 2x3 in the plan. Can we expect a addendum. | 1. The MQ sheet shows it as both a 15â€ AEW and a 4â€™ MH. The 15â€ AEW is correct. 2. Due to the SS pipe angle the 4â€™ MH is correct. The 2x3 inlet was the original design and was inadvertently left in the MQ table. The 4â€™ MH was inadvertently placed in the line above for Structure 4.0. 3. The Storm Sewer Plan and Profile sheet is correct. The MQ sheet will be updated as soon as possible to move the 4â€™ MH item from Structure 4.0 to Structure 4.1. At the same time the 2x3 Inlet on Structure 4.1 will be removed. Item #611.3230 total will be 9. | Mike Coleman | 1 | 2023-12-22 14:23 | 2023-12-27 09:37
20240109 | 20240109012 | 12 | Soil Borings | Are soil borings available? | Soil boring information for ID 2310-13-71 is available. An addendum will be forthcoming to add that information to the 2310-13-71 plan set. | Mike Coleman | 2 | 2023-12-27 13:32 | 2023-12-29 10:07
20240109 | 20240109012 | 12 | Concrete Base Course | It shows on sheet 5 of the 2310-13-71 roundabout plans that the road has a layer of "concrete base course" in the existing typical plans. Is this referring to concrete pavement or crushed concrete base course? | Based on available As-Built information, existing concrete base course may be present in the existing pavement layers as shown in the plan typical sections. Addendum #3 is being processed ASAP to add Item 204.0100 Removing Concrete Pavement for the reconstruction of the intersection of Eagle Drive/STH 60. | Mike Coleman | 5 | 2024-01-03 12:52 | 2024-01-04 15:41
20240109 | 20240109012 | 12 | Curb Ramp, Grading, Shaping, and Finishing | The plan has several references to Curb Ramp, Grading, Shaping, and Finishing, but there is not a bid item. Will the work for the curb ramp be paid under the standard bid items or will a bid item need to be added? | Standard bid items are being used for this project. The notes referenced on the Plan Detail Sheets were inadvertently left in and should be ignored. | Mike Coleman | 3 | 2023-12-28 07:13 | 2023-12-29 10:07
20240109 | 20240109012 | 12 | 643.3960 6" Mask Out Tape | What is the intent for item 643.3960 Temporary Marking Removable Mask Out Tape 6-Inch? The item is shown on the Misc. Qty table on sheet 198, however it is not shown on the Traffic Control plan sheets. This item would not be typically used as shown in Stage 2A/2B as it would be installed on pavement that is being replaced, so a standard Pavement Marking Removal item could be used. Also, it is shown to be used on Stage 3 which is new pavement, so there wouldn't be any existing pavement markings to be covered. Thanks | The pay item in question was removed from the Traffic Control/Staging Plans as it was determined to not needed. However, it was inadvertently left in the MQ table. An addendum will be issued to remove the item. | Mike Coleman | 4 | 2024-01-02 09:09 | 2024-01-03 12:58
20240109 | 20240109012 | 12 | Railroad flaggers | Will the Railroad be providing Railroad flaggers for the work being done on this DOT project at their cost? or does the cost of Railroad flaggers need to be paid by the Contractor of the DOT project? | Refer to the Special Provision Articles Article 4, indicates Contractor is to provide flaggers when needed. Article 9, indicates what work is being done by the WSOR Railroad at no cost to the contractor. Article 15, indicates Contractor is to coordinate with the WSOR Railroad for any additional traffic control requirements. Based on the articles, the understanding is that the Contractor is to provide the flaggers at the railroad when required. However, Contractor is to coordinate it with the WSOR Railroad as there may be other requirements. With Railroads there is the potential that railroad flaggers be WSOR personnel or have WSOR personnel on site while contractor provided railroad flaggers are there. | Mike Coleman | 6 | 2024-01-04 15:32 | 2024-01-05 10:06
20240109 | 20240109013 | 13 | Can the design schedule be provided? | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/yvt6pmm66c542wmhrklvmi8fifrniz7x or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-12-30 15:44 | 2024-01-04 08:05
20240109 | 20240109013 | 13 | Base Patching Quantity. | The Base Patching Quantity seems high, or the dowel bar and sawing quantities seem low. | We found an error, the base patching formulas, were not correct. An addendum will be issued. | Mike Coleman | 2 | 2023-12-31 13:52 | 2024-01-04 08:08
20240109 | 20240109014 | 14 | Plugged unit prices | There are multiple items with unit prices already plugged - items 2, 6, 48-62, 206-208, 212-216, 224-226. Can you please explain why these items are pre-plugged? | An addendum was issued to correct this. | Mike Coleman | 2 | 2023-12-20 11:43 | 2024-01-04 15:45
20240109 | 20240109014 | 14 | Seed No. 70 | There is a note on the lower right corner of page 30 of the plan referencing using 70 seed. There is no quantity for this. Is this note an error or how is this being paid? | An addendum will be issued to correct the seed number error in the plan note and we have a request to add turbidity barrier item from the region construction PM. | Mike Coleman | 1 | 2023-12-14 14:34 | 2023-12-21 09:00
20240109 | 20240109015 | 15 | Temporary Bus Stop, Item SPV.0060.46. - payment for temp asphalt | For temporary bus stops in item 364, will any asphaltic surface temporary tonnage be paid under item 40? Or, is all asphalt incidental to this item? | The unit price for each temporary bus stop includes the furnishing and removing of the temporary asphalt. This is noted in the last sentence of the Temporary Bust Stop spec. The asphalt used for the temporary bus stops will not be paid under item 40 as referenced in the question. | Mike Coleman | 2 | 2024-01-03 10:53 | 2024-01-04 08:22
20240109 | 20240109015 | 15 | CUC Trench Pavement Removal | In the removal plan set it is shown to have the concrete pavement removed for the CUC Trench installation. Is this trench area quantified included, in the Removing Concrete pavement quantity in the estimate of quantities? There is nothing identifying this in the misc. qty tables. Or is it called out in the special provisions under the CUC items. | The pavement removals are shown in the Miscellaneous Quantities under Stage 2, Sta. 23+75 - 37+60, median; and Stage 3, Sta. 47+60 - 51+55, Rt | Mike Coleman | 1 | 2023-12-28 09:02 | 2024-01-03 07:16
20240109 | 20240109017 | 17 | Special 02. Rectangular Rapid Flashing Beacon (RRFB) System | For line item 274, Special 02. Rectangular Rapid Flashing Beacon (RRFB) System, should the quantity be 2 EACH instead of 1 EACH,1 set for each 13' aluminum pole? | For line item 274, Special 02. Rectangular Rapid Flashing Beacon (RRFB) System - Station 47+75 LR/RT, the quantity of 1 EACH is correct. This item includes furnishing and installing the fully operational RRFB system at this location (both the Left and Right locations) except for the items noted in B.2.11 that are paid separately. | Mike Coleman | 2 | 2024-01-04 07:41 | 2024-01-04 15:46
20240109 | 20240109017 | 17 | Special 03. Temporary Water Diversion Station 41+00 To 44+00 | For Special 03. Temporary Water Diversion Station 41+00 To 44+00; There appears to be trees that will be in conflict with constructing this water diversion. Should there be clearing and grubbing items added for this section of the project? | The Village of Bellevue is responsible for clearing and grubbing between Oct 31 and April 1. This is stated in the Special Provisions, Article 3. Prosecution and Progress, Northern Long-eared Bat. | Mike Coleman | 3 | 2024-01-04 09:36 | 2024-01-04 16:30
20240109 | 20240109017 | 17 | Temp Water Diversion 41+00 - 44+00 | The same question with the pipe at station 49+00 applies to the ditch. This seems to add an extraordinary amount of work. With the TRM in the new ditch area being built so close to the existing ditch and the slope towards the road already failing would bypass pumping be allowed for the ditch area as well. | WDNR will not allow by-pass pumping for the stream relocation due to expected duration to construct stream/sideslope/historical issues with flashing and ease of constructing channel alongside existing channel. | Mike Coleman | 4 | 2024-01-05 08:27 | 2024-01-08 06:55
20240109 | 20240109017 | 17 | Temporary Diversion Station 49+00 | The special provision appears to not allow by-pass pumping. Since the existing culvert is partially in conflict with the proposed new culvert and the special provision also tells us to maintain flows it would appear that a diversion channel or pipe is the only viable option to divert the flow. Because of the depths involved this adds a considerable amount of work to divert flows and install the new work. Is the statement about no by-passing correct? | Department will modify article 24 to allow bypass pumping for up to 48 hours (continuous) for the culvert pipe replacement at 49+00. Bypass pumping will not be allowed for stream relocation 41+00 to 44+00. | Mike Coleman | 1 | 2024-01-03 12:36 | 2024-01-04 08:22
20240109 | 20240109020 | 20 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/4y81ja21pyotbmdv7nyauon5tf8yivd9 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2024-01-04 07:02 | 2024-01-05 10:10
20240109 | 20240109020 | 20 | Centerline Repair | Can we rely on the width of the center line repair shown in the plan sheets? The standard detail shows the centerline is 2 foot wide and the plans are showing centerline to be up to 6 foot wide in many areas. We would normally rely on the plans, but want to clarify. The costs a lot more to prepare and pour a 2-foot-wide centerline repair per square yard versus a 6-foot-wide centerline repair shown in the plan sheets per square yard. | Addendum #1 provides a construction detail and special provision detailing that longitudinal joint repairs are to intended to be 2-feet in width. The â€˜Plan Details â€“ Pavementâ€™ sheets in Addendum #1 depict a hatching on longitudinal joints that is not to scale but wide enough for visibility/clarity in the plan view. The legend on those sheets also references the 2-foot width bid item for longitudinal joints. | Mike Coleman | 5 | 2024-01-05 07:28 | 2024-01-08 07:01
20240109 | 20240109020 | 20 | Excess shoulder material | How would the department like to handle the excess shoulder material that will be remaining after grading out the shoulder in preparation for HMA shoulder paving. This material has good likelihood to be chunky. | Based on the integrity of the existing shoulder pavement, how low the existing shoulder is in comparison to the final shoulder elevation, the overall shoulder width to the shoulder point, and the requirements of standard spec section 325, it is anticipated that the pulverized material will be able to be graded out appropriately and covered with a small layer of Base Aggregate Dense ï¿½-Inch. | Mike Coleman | 3 | 2024-01-03 14:56 | 2024-01-08 07:00
20240109 | 20240109020 | 20 | Grade, Shape, Finish Seed | The seed mix for the grade, shape, finish guardrail items on page 123 didn't get stated. What seed mix is anticipated for these? | Seeding Mixture No. 20 is intended for use with that item. An addendum will be prepared so the miscellaneous quantities sheet shows that clearly. | Mike Coleman | 2 | 2023-12-14 15:56 | 2023-12-18 05:56
20240109 | 20240109020 | 20 | QMP | Will the full class 1 QMP apply to the concrete pavement being replaced starting at station 805+75 that goes for 380 feet and is being bid as concrete pavement as result of its length or will the QMP for ancillary concrete apply? Also, does a concrete paver have to be used or can placement methods allowed for concrete replacements be used given the location is being diamond ground? | QMP would follow Standard Spec 715 for Concrete Pavement QMP. The concrete pavement is to be placed with a paver. Quantity for diamond grinding was not included for this segment. | Mike Coleman | 7 | 2024-01-07 10:28 | 2024-01-08 11:18
20240109 | 20240109020 | 20 | Can a Centerline Repair Item be added? | WisDOT Projects with centerline repair work have had a centerline repair item. 2-foot centerline repair is very different from concrete repairs and replacements and should not be blended. The costs are very different. Please provide a centerline repair item with specifications like WisDOT has used on other projects with centerline repair. | An addendum will be submitted to differentiate between the typical concrete repair areas and those along longitudinal joints. | Mike Coleman | 1 | 2023-12-07 06:34 | 2023-12-15 05:41
20240109 | 20240109022 | 22 | Storm Sewer Joint Ties | Under special provisions item 14, it calls out to provide joint ties at all joints of infall and outfall pipes. To clarify, does this mean all 319' of concrete storm sewer has to have joint ties? Or, just so far out, or in, to each structure? | According to WisDOT Standard Specification 608 Storm Sewer, Section 608.3.3 Laying Pipe (5); Provide joint ties on concrete storm sewer system infall and outfall pipes. Tie the last 3 pipe joints or, if using apron endwalls, the endwall joint and the next 2 pipe joints. | Mike Coleman | 1 | 2024-01-05 09:54 | 2024-01-08 06:56
20240109 | 20240109023 | 23 | Cranberry Creek Landfill | The phone number given in the specifications for the landfill to haul the Creosote contaminated material is not correct. It goes to a robo call center selling medical devices. I tried Google and about 6 different numbers I found on there, all of which go unanswered with no voicemail, or have a recording that says it is no longer a working number. Please provide a phone number for the vendor so we can get pricing of disposal to put in our bid. | We were able to track down the correct contact information for the landfill (see below highlighted). Land Fill Name: Waste Management Cranberry Creek Landfill Location/Address: 2510 Engle Road, Wisconsin Rapids WI 54495 Contact Information: Lisa Gaupp (920) 205-5633 | Mike Coleman | 1 | 2023-12-29 12:26 | 2024-01-03 07:05
20240109 | 20240109025 | 25 | Non-Nuclear Density Gauge | Due to the burden of regulations involving transporting a nuclear gauge across state lines, we have been utilizing a TransTech PQI-380 non-nuclear asphalt density gauge for several years with no problems. All of the other states we have worked in have accepted this method of testing asphalt density. We would like to respectfully request the non-nuclear option for this project. | Currently WisDOT does not use non-nuclear gauges for acceptance, however, 108.8 of the standard specification discusses substituting equipment, methods, and materials. | Mike Coleman | 1 | 2024-01-04 11:56 | 2024-01-08 11:13
20240109 | 20240109025 | 25 | Same Day paint | Due to the heat from the hot in-place process, the paint applied to centerline will be burned off when the opposite late is processed. Will the second application of paint be a pay item? | If it is determined by the engineer that there needs to be a reapplication of pavement marking, the department will pay for as an overrun. | Mike Coleman | 2 | 2024-01-04 15:11 | 2024-01-08 11:18
20240109 | 20240109028 | 28 | Video detection system | Video detection spec lists shall be Iteris. Would Econolite Vision be accepted as an equal alternative for this project? | Econolite Vision would not be considered an equal alterative. | Mike Coleman | 1 | 2023-12-20 08:07 | 2023-12-22 11:40