## qandasearchletting_results
Date: | 2024-04-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20240409 | 20240409001 | 1 | Schedule of Items | The schedule of items at the back of the special provisions does not match the Items in Bid Express or the .ebsx file in aashtoware. There is more than a handful of that do not match the proposal line number or description or approximate units. What is correct? | An addendum will be issued to add the correct SOI. | Mike Coleman | 1 | 2024-03-06 16:52 | 2024-03-13 07:36
20240409 | 20240409001 | 1 | Soil Boring Report | Are soil boring reports available for this project? | The soils reports can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-03-08 06:34 | 2024-03-13 08:06
20240409 | 20240409001 | 1 | Design Schedule | Please provide the design schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2024-03-12 08:34 | 2024-03-13 07:59
20240409 | 20240409001 | 1 | Removing Concrete Pavement | It seems to be that the removing concrete pavement quantity is incorrect. We believe that some of the areas seem to be calculated using the entire pavement width, including the asphalt shoulders and not just the area of concrete underneath the asphalt pavements. | Much of the shoulder area within the project does include concrete pavement. As is noted in the existing typical sections, the shoulders are a combination of 6â€ non-reinforced concrete pavement or 5â€ asphaltic pavement, which was then overlaid with asphalt as part of the most recent rehabilitation completed in 2017. The previous project plans didnâ€™t provide specific locations where concrete shoulder areas were patched/repaired with asphalt. The concrete removal quantity was estimated based on information available and we believe it is reflective of the current conditions. | Mike Coleman | 4 | 2024-03-12 16:35 | 2024-03-14 08:34
20240409 | 20240409001 | 1 | Marsh Backfill Quantity | In the earthwork summary how was the expanded marsh backfill quantity (13065 CY) calculated? It looks like the reduced marsh in fill quantity was used, which doesnâ€™t seem correct. Secondly, the marsh backfill is stated be backfilled with select crushed material. Please provide the calculations showing how the quantity of 28010 tons of marsh backfill (select crushed material) was derived. Lastly, in the past preliminary plan earthwork summary it stated the expanded marsh backfill is to be filled with cut material. Given this projects soil characteristics are for the most part granular in nature why couldnâ€™t suitable cut material and / or rock excavation be used to backfill the marsh excavation, using a select borrow spec as past projects have used? | 1. The reduced marsh is not in this calculation. The marsh excavation is broken into two portions. The first portion will be filled with cut material while the second portion will be filled with select crushed material. The quantity questioned is the sum of the marsh excavation that will be backfilled with select crushed material multiplied by the factor of 1.50 shown. 2. The only column in the EW Summary table that has a unit of â€˜tonsâ€™ is the Select Crushed Material. All others are in cubic yards. The FDM conversion factor of 1.9 Tons/CY was used to convert the cubic yard quantities to tons. The quantity noted takes the expanded marsh backfill select crushed material, adds the expanded fill select crushed material, then multiplies by the FDM conversion factor. In equation form: (13,065+1,675)*1.9 = 28,006, rounded to 28,010. 3. Having good material to get out of the water and muck, and a stable working platform, is critical in the marsh excavation area. To accomplish that, it was determined select crushed would be specified. Depending on material that has been excavated from within the project, or is being excavated from within the project when the marsh excavation is occurring, the quantity of select crushed could be reduced. The final determination would be made by the construction engineer. | Mike Coleman | 5 | 2024-03-12 16:52 | 2024-03-14 08:46
20240409 | 20240409001 | 1 | Undistributed EBS & Select Crushed Material | The plan shows a substantial amount of undistributed EBS and EBS backfill (Select Crushed Material). Putting these quantities of EBS and Select Crushed Material into the bid items inflates these items considerably. There is no reason to have these unreasonable undistributed amounts in this bid given surrounding soil properties. The undistributed EBS inflates the common excavation by +/- 10%, while the undistributed select crushed material inflates that item by +/- 30%. Please adjust both the undisturbed quantities of EBS and Select Crushed Material from this project, as right now these items are too big of a risk to properly bid. This is very important to get the most competitive low bid for the department as well as the taxpayers. Lastly, in the past preliminary plan earthwork summary it stated the expanded EBS backfill is to be filled with cut material. Given this projects soil characteristics are for the most part granular in nature why couldnâ€™t cut material be used to backfill the EBS excavation? | 1. While rock and granular soils are present within the project limits, other materials are present as well, including marsh/wetlands. In addition, portions of reconstructed roadways will be over existing ditches and some over-excavation/EBS is expected. But based on discussion with the SW Region Soils Engineer, the EBS percentage will be reduced to 5% as part of an addendum. 2. Having good material to get out of the water and muck, and a stable working platform, is critical in the marsh excavation area. To accomplish that, it was determined select crushed would be specified. Depending on material that has been excavated from within the project, or is being excavated from within the project when the marsh excavation is occurring, the quantity of select crushed could be reduced. The final determination would be made by the construction engineer. (This is the same response as previously provided to part 3 of question #5.) | Mike Coleman | 6 | 2024-03-12 17:05 | 2024-03-14 13:51
20240409 | 20240409001 | 1 | Causeway Detail | Can the department provide the design surface used in developing the Temporary Access? | The design surfaces associated with the temporary causeways can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. The surfaces are for information only and not for bidding purposes. The layouts were developed to determine if reasonable access was possible to construct the new bridges and to create a conservative estimate for environmental footprint impacts. To be as conservative as possible, the designers didnâ€™t consider all environmental restrictions in the layouts, but the contractor will need to. | Mike Coleman | 7 | 2024-03-13 07:36 | 2024-03-19 07:14
20240409 | 20240409001 | 1 | 404 Permit | Please provide the approved 404 permit for the project. | The 404 Permit information can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 8 | 2024-03-13 11:40 | 2024-03-14 08:27
20240409 | 20240409001 | 1 | Structure Bid Items | 123 - Median 2 missing and not accounted for is it intended to added this structure? 203 per bid items is a 48" Diameter, but as drawing in plan it should in fact be a 60". | Drainage structure 123 was omitted in the MQ tables and will be added. In addition, endwall 124 and storm sewer pipe run 123 â€“ 124 will be corrected in the MQ table to the correct 30â€ size. Drainage structure 203 will be corrected to the correct 5-ft diameter manhole in the MQ tables. | Mike Coleman | 9 | 2024-03-18 12:22 | 2024-03-20 07:55
20240409 | 20240409001 | 1 | Drilled Shaft Casing Requirement | Please confirm that the use of full-depth permanent casing is required for all drilled shaft excavation per SPV.0060.30 and SPV.0060.12. Please also confirm that excavation below the tip of the full-depth temporary casing will not be permitted at any time, even under a drilling support fluid. Finally, is there any required depth in which the casing must be left-in-place or is the use of a temporary left-in-place casing up to the means and methods of the contractor. | 1. We assume there is a minor typo in the submitted question, and it was asking to confirm that TEMPORARY casing is required. Permanent casing is not permitted. Full length temporary casing is required for all drilled shaft installations per the special provisions. 2. Correct â€“ Excavation below the tip of the full-depth temporary casing will not be permitted at any time, even under a drilling support fluid. 3. Per the response to part 1 of the question, the use of permanent casing is not permitted. The contractor shall submit a temporary casing removal plan per the drilled shaft special provisions. | Mike Coleman | 10 | 2024-03-19 09:14 | 2024-03-25 08:47
20240409 | 20240409001 | 1 | Drilled Shaft Oscillator Use | Please confirm that an oscillator is required to install the specific full-depth temporary casing per SPV.0060.30 and SPV.0060.12. | Yes, an oscillator/rotator is required to install the full-depth temporary casing per the special provisions. | Mike Coleman | 11 | 2024-03-19 09:15 | 2024-03-20 07:59
20240409 | 20240409001 | 1 | Planting Schedule for Living Snow Fence | In regards to the bare root shrub plantings for living snow fence, plan indicates they need to be planted in Stage 1 after other construction operations are finished. This would put the planting around the month of August which is not ideal timeframe for planting bare root stock. Would moving planting to fall timeframe such as October be acceptable? | Note 10 on the Planting Detail sheets will be revised to state: â€˜Install plantings prior to June 1st of calendar year 2026 during stage 4. Temporary Snow Fence shall be installed in the fall of 2024 during stage 1 or 2.â€™ | Mike Coleman | 12 | 2024-03-19 10:02 | 2024-03-21 12:48
20240409 | 20240409001 | 1 | Tremie Size | Per SPV.0060.30 & SPV.0090.12, subsection C.3.10.4, will a tremie size smaller than 10-inches in diameter be allowed for a pressurized tremie placement of drilled shaft concrete? | Yes, a pressurized tremie placement system is acceptable. The minimum requirements of a pressurized system include: â€¢ Minimum pressurized tremie pipe diameter of 4 inches. â€¢ Steel tremie line within the shaft that has one-way flap valve (or other means to seal the end as the tremie is lowered to the bottom of the shaft). â€¢ Use a grout mix at the start of the pour. These minimum requirements will be incorporated into the special provisions as an addendum. | Mike Coleman | 13 | 2024-03-19 10:07 | 2024-03-25 09:15
20240409 | 20240409001 | 1 | Drilled Shaft Concrete Placement Time | Per SPV.0060.30 & SPV.0090.12, subsection C.3.10.2, please consider extending the window for both concrete placement after excavation and also concrete placement following inspection and approval. Following excavation completion, a robust cleaning process will be required to meet shaft bottom cleanliness requirements. Additionally, cleanliness testing and acceptance by SID can be a time consuming process. Please consider extending the window from excavation completion to time of placement from 24 hours to 48 hours. From the time testing is completed and accepted to the time concrete placement can begin will require longer than 3 hours. Following inspection and testing of the shaft for cleanliness, the contractor will have to set the rebar cage, potentially splice the rebar cage, and build and set the tremie into the shaft. This process will likely take longer than 3 hours on average. Please consider extending this specific window from 3 hours to 8 hours. | 1. The department will accept extending the timing between excavation completion and beginning of concrete placement to a maximum of 48 hours. 2. The department will accept a maximum time between final inspection and concrete placement of 8 hours provided that the demonstration shaft construction shows that excessive sediment accumulation does not occur at 8 hours after final inspection. The contractorâ€™s means and methods, and proposed installation plan shall demonstrate the process to be used to ensure clean shaft base(s). Demonstrating an adequately clean base may require additional time to complete the demonstration shaft process. The contractor shall ensure a clean bottom of drilled shaft for all production shafts, in addition to the demonstration shaft(s), as it is critical to the performance of the drilled shafts. | Mike Coleman | 14 | 2024-03-19 10:16 | 2024-03-21 12:41
20240409 | 20240409001 | 1 | Hydraulic Analyses | Please provide the hydraulic analyses required by the 404 permit for all stages of temporary access for Wisconsin River Structure Construction and Demolition. | The WisDOT completed hydraulic model, and a single page PDF displaying results, can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. The results are for information only and not for bidding purposes. The hydraulic analysis assumed all temporary river accesses were in place simultaneously. In addition, the analysis assumed the entire backwater area was impeded by the temporary river accesses. Per special provision article 94, Section C.1, contractors will need to â€˜â€¦ use construction methods that result in minimal disruption to the existing flow of water such as equalizer pipes, temporary bridges, or other means available.â€™ | Mike Coleman | 15 | 2024-03-19 11:58 | 2024-03-25 08:21
20240409 | 20240409001 | 1 | Causeway Elevation | What is the permitted top of causeway elevation? Is the permitted top of causeway elevation constant through the main river channel, over the island, and through the backwater channel areas? | There is no permitted top of causeway elevation. The contractor can use a single elevation for all causeways, or the elevation could vary between causeways or within a single causeway. The contractor will need to complete a hydraulic analysis for whatever elevation or elevations are selected. | Mike Coleman | 16 | 2024-03-19 12:00 | 2024-03-21 08:14
20240409 | 20240409001 | 1 | Cofferdam Elevation | What is the permitted top of cofferdam elevation? Is the permitted top of cofferdam elevation constant through the main river channel, over the island, and through the backwater channel areas? | There is no permitted top of cofferdam elevation, and the Department does not require a minimum top of cofferdam elevation. Itâ€™s the contractorâ€™s responsibility to determine top of cofferdam elevations, which may be the same for all cofferdams or vary between cofferdams. | Mike Coleman | 17 | 2024-03-19 12:01 | 2024-03-20 13:49
20240409 | 20240409001 | 1 | Existing/Proposed Structure Scour | Is scour due the permitted causeway and cofferdams expected at any of the existing or proposed substructure? If so, what piers are expected to be affected and to what extent? Is scour protection required at any potentially affected piers? | Scour may occur, but the extent and locations are dependent upon what each contractor proposes for temporary river access layouts. To monitor scour during construction, the SPV/bid item of â€˜Underwater Scour Monitoringâ€™ is included in the contract. No scour protection is included in the contract. | Mike Coleman | 18 | 2024-03-19 12:05 | 2024-03-25 08:41
20240409 | 20240409001 | 1 | Insurable Properties | What insurable properties were identified by the hydraulic analyses as potentially affected by the permitted causeway and cofferdams? At what flow are these properties affected? | The hydraulic modeling completed assumed a top of temporary river access at the 2-yr elevation. Refer to the response to Question #15 for additional assumptions made for the temporary river access hydraulic modeling. The hydraulic analysis evaluated potential impacts for the 100-yr flow event. Based on a cursory review of LiDAR information and FEMA mapping, as many as 17 insurable structures were identified as being potentially impacted by the temporary river access. | Mike Coleman | 19 | 2024-03-19 12:08 | 2024-03-25 08:32
20240409 | 20240409001 | 1 | Box Culvert Extension | As presented we would not be able to provide precast box culvert. Would the DOT be willing to complete in a single phase so we can present a twin cell precast box culvert. | A 2-cell precast box extension of C-11-11 is not feasible as the work must be staged to accommodate the water flowing through the structure. If the extension of the culvert by means of precast elements canâ€™t be provided in stages, then the box extension will need to be completed as cast-in-place. | Mike Coleman | 20 | 2024-03-19 13:21 | 2024-03-21 12:30
20240409 | 20240409001 | 1 | Temporary River Access | In the precon meeting somebody asked the question if other materials could be used in the river besides riprap for the temporary river access. In article 94 of the specials, it calls out Riprap specifically. In the meeting it sounded like other materials may be accepted if it was not salvaged or recycled materials. Could you please elaborate on what types of materials would be acceptable for building temporary access? | Materials to be used for temporary river access should be provided per the current requirements of article 94. Contractors may propose alternative materials through Standard Spec section 100 for the Departmentâ€™s review and acceptance/rejection. | Mike Coleman | 22 | 2024-03-19 13:39 | 2024-03-26 13:11
20240409 | 20240409001 | 1 | Parcel Acquisition - Parcels 1, 3, 21, 22, 23, and 24 | If ROW acquistions are not complete by July 1st and this delays start of contractors access into the listed parcels to be acquired, what is the anticipated timeframe that needs to be accounted for that contractors need to be aware of prior to bid? Or is July 1st the date that parcels are expected to be acquired? If the DOT does not acquire the parcels by July 1st, what relief will be granted to the contractor? | Parcels 1, 3, 21, 22, and 23 have been acquired and can be accessed whenever the project starts. Parcel 24 is not yet acquired, and the July 1st date would still apply. The â€˜Work Zone Restrictions â€“ Parcel Acquisitionâ€™ paragraph will be revised with Addendum 2 to remove references to parcels 1, 3, 21, 22, and 23. | Mike Coleman | 23 | 2024-03-19 16:26 | 2024-03-21 08:15
20240409 | 20240409001 | 1 | In Stream Disturbance Definition | SPV 22 - Definitions - Per this section work inside a "dry" cofferdam is not considered in-stream disturbance. Typcially, work inside any cofferdam, whether wet or dry, is considered a closed environment and would not be in-stream disturbance. Please change this language to remove the "dry" wording. | The definition for â€˜In-stream disturbance/work or in-water disturbance/workâ€™ will be revised as part of Addendum No. 3. | Mike Coleman | 24 | 2024-03-19 16:31 | 2024-04-04 06:48
20240409 | 20240409001 | 1 | Utility Relocates | Can the Dept provide an update on utility relocations work and anticipated dates for all utility relocates to be complete? | From a 3/8/24 request to the utilities, the status of relocation work is: â€¢ AT&T Legacy â€“ All relocation work completed. â€¢ Alliant (electric) â€“ Relocation work on CTH U is complete. Relocation on/near CTH V should be completed by the end of March. Once the CTH V area is complete, they work with state patrol to have the overhead lines at CTH V and St Lawrence Bluff Road dropped. Work that will remain is de-energizing the DOT services on CTH U, CTH V and St Lawrence Bluff Road that serve FTMS facilities. These will be taken out of service during construction. â€¢ Brightspeed â€“ They have started their relocations but have work remaining along the interstate that still need to be completed. Relocations will be completed prior to construction. â€¢ Frontier â€“ No response received. They are only abandoning facilities, and no new installations are planned. â€¢ Madison Gas & Electric (gas) â€“ No conflict based on ULO completed earlier in month. Addendum #2 will include revised language that the utility will need to install a rock shield wrap during culvert installation. â€¢ Spectrum â€“ They had not yet started relocations but estimate to be completed by the middle of April. â€¢ TDS Metrocom â€“ TDS had underground construction completed. However, they were still using the old fiber lines until a fiber cut-over can be completed, which is estimated to occur by the end of March. | Mike Coleman | 25 | 2024-03-19 16:32 | 2024-03-21 12:39
20240409 | 20240409001 | 1 | Mussel Relocation | Will the department consider beginning the relocation efforts for the remaining mussels prior to July 2024? Is the contractor to assume this work will not be complete until the end of July 2024? | Language in the first paragraph of the â€˜State and Federal Listed Fresh Water Mussel Relocationâ€™ section of the Prosecution and Progress article will be updated as part of Addendum #2 to clarify that mussel relocation work will be completed by June 30, 2024. | Mike Coleman | 26 | 2024-03-19 16:33 | 2024-03-26 07:43
20240409 | 20240409001 | 1 | Hydraulic Analysis | As discussed in the pre-bid meeting this morning, please provide the hydraulic analysis for contractor review. | The WisDOT completed hydraulic model, and a single page PDF displaying results, can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. The results are for information only and not for bidding purposes. The hydraulic analysis assumed all temporary river accesses were in place simultaneously. In addition, the analysis assumed the entire backwater area was impeded by the temporary river accesses. Per special provision article 94, Section C.1, contractors will need to â€˜â€¦ use construction methods that result in minimal disruption to the existing flow of water such as equalizer pipes, temporary bridges, or other means available.â€™ | Mike Coleman | 27 | 2024-03-19 16:36 | 2024-03-25 08:25
20240409 | 20240409001 | 1 | Storm Sewer Rock Excavation | Rock excavation is shown in the cross sections for the storm sewer pipe from Sta 1149+00 - 1154+00 WB but the plan does not include a bid item for Storm Sewer Rock Excavation. Please add a bid item. | All rock excavation required for the project had been captured under the Excavation Rock bid item, 205.0200. Item 608.0005 (Storm Sewer Rock Excavation) will be added to the project for the portion of rock excavation required for storm sewer. The Excavation Rock item will be reduced by the same quantity. | Mike Coleman | 28 | 2024-03-20 08:10 | 2024-03-20 13:32
20240409 | 20240409001 | 1 | Blasting for pier demolition | Please confirm that blasting for underwater pier demolition will not be allowed as prohibited by SPV article 20. | Based on proximity of the new WB bridge to the old bridges, blasting for underwater pier demolition will not be permitted. | Mike Coleman | 29 | 2024-03-20 14:27 | 2024-03-22 10:17
20240409 | 20240409001 | 1 | ATC Lines and Secant Wall | Can the approximate elevations of the power lines in vicinity the secant wall (R-11-48) area be provided? Also is it possible to get a outage of the powerlines if necessary to facilitate the secant wall drilling if OSHA required clearances cannot be maintained? If an outage is possible, how long can the outage last, how long before an additional outage is possible and what is the advanced notice requirements? | Survey data associated with the ATC power lines can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. The survey data is for information only and not for bidding purposes. The file includes specific dates and weather conditions associated with data collected for each span. The power lines will be higher or lower depending on the time of year and weather conditions. Per article 19 of the special provisions, coordination with ATC for any outages is the responsibility of the contractor. The design team did complete some initial outreach with ATC, who indicated temporary line shutdowns may be possible. Please use the contact information included in article 19 to determine answers to other questions asked regarding outages. | Mike Coleman | 30 | 2024-03-20 15:38 | 2024-03-22 10:12
20240409 | 20240409001 | 1 | Causeway and Cofferdam Elevations | What were the top of causeway and cofferdam elevations assumed in the hydraulic analysis required by the 404 permit? | There are no permitted/required elevations in the 404 permit tied to the top of causeways and top of cofferdams. Contractors can propose elevations for each based on their means and methods and acceptable levels of risk associated with possible higher water events during construction. The contractor will need to complete a hydraulic analysis for whatever elevation or elevations are selected. | Mike Coleman | 31 | 2024-03-21 08:17 | 2024-03-21 13:55
20240409 | 20240409001 | 1 | Schedule of Living Snow Fence Installation | The current schedule for the Living Snow Fence shows installation to be in Stage 1 which begins June 3rd. These plants will not be available then and is outside the typical planting window which ends June 1st. Should the contractor assume this task would take place in the spring of 2025 which is the next available planting window? | See response to question #12. Note 10 on the Planting Detail sheets will be revised to state: â€˜Install plantings prior to June 1st of calendar year 2026 during stage 4. Temporary Snow Fence shall be installed in the fall of 2024 during stage 1 or 2.â€™ Planting installation in spring of 2025 is not desirable as all EB & WB traffic will be shifted into the EB lanes and there wonâ€™t be any room for the contractor to work along the outside shoulder of the roadway. In the spring of 2026, the EB lanes will be under construction and the planting contractor can work safely within the closed area. | Mike Coleman | 32 | 2024-03-21 10:56 | 2024-03-21 13:09
20240409 | 20240409001 | 1 | Temporary Access | The detail of the potential work roads as shown on sheet 39 of the plans are very good concepts. We would like confirmation that these roads can be reconfigured to meet the needs of cofferdam installation, drilled shaft installation and prestressed beam setting. | As noted, the information provided on plan sheet 39 is for information only. The layouts depicted were developed to determine if reasonable access was possible to construct the new bridges and to create a conservative estimate for environmental footprint impacts. They are considered conceptual, and contractors are expected to develop their own layouts to fit with means and methods being proposed, while also adhering to the environmental restrictions in the contract. | Mike Coleman | 33 | 2024-03-21 14:15 | 2024-03-25 09:24
20240409 | 20240409001 | 1 | 404 Permit - Barge Spud | The 404 Permit indicates the spuds used to moor the barges would be 20 inch H-pile. We would like to confirm that larger spuds can be utilized. | The language within the 404 permit regarding 20â€ spuds is only an estimate of the size a contractor may use. The 20â€ size was considered a standard size for estimating impacts within the river. The contractor would be allowed to use spuds larger than 20â€ to anchor barges. | Mike Coleman | 34 | 2024-03-21 14:17 | 2024-03-26 08:49
20240409 | 20240409001 | 1 | Temporary Access | The work roads have a 50 foot top width on the main access area and 40 foot top width on the finger access areas. Can these widths be modified (increased) to accommodate the potential equipment needed for cofferdam installation, drilled shaft installation and prestressed beam setting? | The information provided on plan sheet 39 is for information only. The layouts depicted, including widths, were developed to determine if reasonable access was possible to construct the new bridges and to create a conservative estimate for environmental footprint impacts. They are considered conceptual, and contractors are expected to develop their own layouts to fit with means and methods being proposed, while also adhering to the environmental restrictions in the contract. | Mike Coleman | 35 | 2024-03-21 14:18 | 2024-03-25 09:25
20240409 | 20240409001 | 1 | In-stream Restriction | Moving equipment barges, material barges and tugs during the in-stream restrictions time period would not be considered an in-stream disturbance. Can this be confirmed? | The definition for â€˜In-stream disturbance/work or in-water disturbance/workâ€™ will be revised as part of Addendum No. 3. | Mike Coleman | 36 | 2024-03-21 14:19 | 2024-04-04 06:49
20240409 | 20240409001 | 1 | Dredging | Please confirm that dredging of the Wisconsin River would be allowed, if needed. If allowed, would there be any restrictions. | Dredging of the Wisconsin River may be possible. A definitive answer is not possible without knowing the details of where dredging is proposed to occur and to what extent. If dredging were to be pursued, the DOT and DNR would need details of the proposed operation. Information needed would include a dredging plan that adequately addresses instream sediment transport, dewatering, and disposal of materials. Operations would need to comply with all other contractor provisions and environmental restrictions. BMPâ€™s would need to be employed during dredging operations to minimize additional sediment transport downstream. Dewatering discharges would need to be as clear or clearer than the receiving water. Dredged materials may not be disposed or stockpiled in waterways or wetlands. | Mike Coleman | 37 | 2024-03-21 14:20 | 2024-03-26 13:08
20240409 | 20240409001 | 1 | Hydrology Study | Would the department make the hydrology study available to the contractor for review? | The WisDOT completed hydraulic model, and a single page PDF displaying results, can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. The results are for information only and not for bidding purposes. The hydraulic analysis assumed all temporary river accesses were in place simultaneously. In addition, the analysis assumed the entire backwater area was impeded by the temporary river accesses. Per special provision article 94, Section C.1, contractors will need to â€˜â€¦ use construction methods that result in minimal disruption to the existing flow of water such as equalizer pipes, temporary bridges, or other means available.â€™ | Mike Coleman | 38 | 2024-03-21 14:22 | 2024-03-25 09:22
20240409 | 20240409001 | 1 | Hydrology Study | Based on the DOT hydrology study, what is the top of the work road/ temporary access elevation to be used? The plan indicates 2 feet above the waterline but does not indicated what water elevation to use. | As part of Addendum #2, plan sheet 39 will be updated to note an elevation of 780.50 was used for the top of the temporary river access. A note is also being added to state the elevation is not permitted or required. See response to Question 16 for additional information. | Mike Coleman | 39 | 2024-03-21 14:23 | 2024-03-25 09:26
20240409 | 20240409001 | 1 | In-stream Restrictions | During removal of the lower portions of B-11-22/23, if cofferdams are used to encompass the piers, can the removal continue to remove these lower portions during the restriction phases of 3/1 - 6/1 and 6/1 - 7/31? | The definition for â€˜In-stream disturbance/work or in-water disturbance/workâ€™ will be revised as part of Addendum No. 3. | Mike Coleman | 40 | 2024-03-21 14:25 | 2024-04-05 10:24
20240409 | 20240409001 | 1 | Substructure Removal | It was discussed, at the pre-bid meeting, to remove the existing piers for B-11-22/23 to the streambed. It was also acknowledged that the river is constantly shifting. Could the Department provide elevations for each pier to be removed? | It is the Departmentâ€™s expectation that standard spec 203.3.2.1 be followed for the existing pier removals. Piers in the waterway are to be removed down to the natural stream bed at the time of removals. Piers out of the waterway should be removed a minimum of 2â€™ below natural or finished ground line. | Mike Coleman | 41 | 2024-03-21 14:34 | 2024-03-25 09:34
20240409 | 20240409001 | 1 | Concrete Masonry Seal | Will QMP testing be required for the Concrete Masonry Seal? | Yes, QMP testing will be required for the Concrete Masonry Seal per the Standard Specification requirements. | Mike Coleman | 42 | 2024-03-21 14:34 | 2024-03-25 09:20
20240409 | 20240409001 | 1 | Tremie Placing Concrete for Drilled Shafts | Please add the following to C.3.10.5: When placing concrete underwater, including when water in a shaft excavation exceeds 3 inches in depth, the Contractor shall place the concrete by pressure feed using a concrete pump, with a watertight tube having a minimum diameter of 4 inches. The discharge end of the tube on the concrete pump shall include a device to seal out water while the tube is first filled with concrete. Alternatively, the Contractor may use a plug that is inserted at the hopper of the concrete pump and travels through the tremie to keep the concrete separated from the water and slurry. Concrete placement by gravity feed is not allowed. Throughout the underwater concrete placement operation, the discharge end of the tube shall remain submerged in the concrete at least 5 feet and the tube shall always contain enough concrete to prevent water from entering. The concrete placement shall be continuous until the work is completed, resulting in a seamless, uniform shaft. | Yes, a pressurized tremie placement system is acceptable. The minimum requirements of a pressurized system include: â€¢ Minimum pressurized tremie pipe diameter of 4 inches. â€¢ Steel tremie line within the shaft that has one-way flap valve (or other means to seal the end as the tremie is lowered to the bottom of the shaft). â€¢ Use a grout mix at the start of the pour. These minimum requirements will be incorporated into the special provisions as an addendum. | Mike Coleman | 43 | 2024-03-21 15:03 | 2024-03-25 09:20
20240409 | 20240409001 | 1 | Drilled Shaft Soil Conditions | B-11-183 and B-11-184 have drilled shafts that extend below the deepest soil borings at each pier. What are bidders to assume the soil conditions are below the lowest borings at each shaft locations? | Supplemental geotechnical information will be collected in the construction phase borings that are part of the contractorâ€™s scope for the project. See Special Provision article 118 for additional information. | Mike Coleman | 44 | 2024-03-21 15:04 | 2024-03-25 09:16
20240409 | 20240409001 | 1 | Springs and Artesians | On sheets 38 (Construction Detail â€“ WI River Restrictions Overview) and 39 (Temporary Access/Barge Access Overview) of the project drawings springs were observed adjacent to the drilled shafts in several locations. After review of the geotechnical report for B-11-183 and B-11-184 no piezometer readings were shown. Does the State anticipate artesian conditions causing the hydrostatic water elevation being above the river elevation? If so, what elevation is to be assumed? | Groundwater conditions are summarized in the â€™Geotechnical Exploration and Bridge Foundation Evaluation Reportâ€™ for bridges B-11-183 & B-11-184, which were made available in response to Question #2. The completed borings did not encounter artesian conditions. Supplemental geotechnical information will be collected in the construction phase borings that are part of the contractorâ€™s scope for the project. See Special Provision article 118 for additional information. | Mike Coleman | 45 | 2024-03-21 15:07 | 2024-03-25 09:18
20240409 | 20240409001 | 1 | Concrete Pavement 12-inch Special SPV | In the SPV item SPV.0180.01 under the Materials (B) section, note (2) for the Concrete Pavement 12-inch Special it states "Use clean, hard, durable non-quartzite coarse aggregates". Can the DOT explain why quartzite aggregates can not be used? Quartzite aggregates have been used on many DOT projects over the years in this area with no known issues as it would be a viable option for this project. Would the DOT revise this SPV to allow quartzite coarse aggregates for this project? | The special provision wonâ€™t be revised. Pavement buckling has been observed on Portland cement concrete (PCC) pavements near the project area that have used quartzite in the coarse aggregate source. This has been attributed to the difference in the coefficient of thermal expansion (CTE) between the quartzite aggregate and the concrete pavement. Restricting the use of quartzite coarse aggregate will reduce the chance of future pavement buckling. | Mike Coleman | 46 | 2024-03-21 16:45 | 2024-03-25 12:22
20240409 | 20240409001 | 1 | Pier 12 Rock Elevations | The special 'Cofferdams B-11-184 Pier 12, Item SPV.0060.24' has a note that reads, See "Pier 12 Details" sheet of the B-11-184 structure plans for approximate top of rock elevations at the pier 12 seal corners. I don't see any reference to the rock elevations at the seal corners on the plans. Please provide these details so a cofferdam can be designed, and the quantity of rock excavation required can be determined or advise where in the plans this is detailed. | The reference in article 88 to the â€˜Pier 12 Detailsâ€™ sheet of the bridge plan will be removed as part of Addendum #2. The rock depths at this pier location are variable. The design was done with the knowledge that setting the bottom of seal elevation at 762.50â€™ will provide the 2â€™-0â€ minimum key into the rock thatâ€™s called for in the plans. The exact elevations of the rock at the corners of the seal are unknown. Generally speaking, the rock is assumed to be at 775â€™ on the south side of the seal and at 765â€™ on the north side of the seal. | Mike Coleman | 47 | 2024-03-22 11:35 | 2024-03-26 13:06
20240409 | 20240409001 | 1 | Drilled Shaft Rock Sockets | The geotechnical report for the river bridge references that all shafts, "...will need to extend (socket) into bedrock, likely a depth of at least 1.5 x the shaft diameter..." The plans, however, only reference bearing on top of rock. Will rocket sockets be required for all shafts? If so, please add a bid item for "drilled shafts - rock sockets" for the length of anticipated socket drilling for each shaft. | The final length of drilled shafts will be determined in the field based on construction phase geotechnical borings. The contractor will be required to perform the borings. The Department will determine and provide final drilled shaft length based on those borings. Rock sockets into material discernably harder than the majority of the drilled shaft length arenâ€™t expected to be required. | Mike Coleman | 48 | 2024-03-22 14:23 | 2024-03-26 07:44
20240409 | 20240409001 | 1 | Drilled Shaft Bottom Cleanliness Testing Device | Will a DID (Ding Inspection Device) be allowed for drilled shaft bottom cleanliness inspection instead of a SID or SQUID? Product info can be found at the link below: https://www.dmy-inc.com/did.php | The contractor shall plan to inspect for drilled shaft bottom cleanliness using the SID/SQUID as the contract currently calls for. As is the case for all projects, contractors may propose alternative methods, materials, and processes through Standard Spec section 100 for the Departmentâ€™s review and acceptance/rejection. | Mike Coleman | 49 | 2024-03-22 14:26 | 2024-03-26 07:45
20240409 | 20240409001 | 1 | Thermal Integrity Profiler (TIP) Testing | SPV.0060.11 and SPV.0060.12 references ASTM D7949 which is currently under revision and not available. Please consider eliminating TIP testing from project as the ASTM standard is not available at the current time. | The Department acknowledges that ASTM D7949 has not been reapproved as of the date of this letting. However, there are no technical issues with the existing ASTM D7949 specification (which remains available for download) and thus, this project will move forward requiring it as stated in the project specifications. | Mike Coleman | 50 | 2024-03-22 14:43 | 2024-03-26 07:46
20240409 | 20240409001 | 1 | Construction Phase Borings for Drilled Shafts | We understand that supplemental geotechnical information will be collected via the construction phase borings as part of the contractor's scope for the project. According to Special Provision article 118, the construction phase borings are to extend below the deepest soil borings presented in the Geotechnical Exploration and Bridge Foundation Report. Please advise that if any of the supplemental construction phase borings present geotechnical information that is materially different than the geotechnical information presented in the Geotechnical Exploration and Bridge Foundation Report that the Contractor may be provided the opportunity to evaluate and recover subsequential cost and schedule impacts related to any materially different geotechnical information. | The information contained in the contract documents shall be used as the basis for bidding. Following the construction phase supplemental borings completion, a final determination of drilled shaft length will be made by the department. If the actual work required differs from the information contained in the contract documents, the contractor will have the right to utilize the process outlined in standard spec 104.2 to revise the contract and ask for additional compensation/time. | Mike Coleman | 51 | 2024-03-25 11:11 | 2024-03-28 09:08
20240409 | 20240409001 | 1 | bearing plate details B-11-185 | There is a note on one end of the 54w beam stating that there is a beveled anchor plate however, there are no details. Could you please confirm if there is a bearing plate, and if so, provide the details. | The note regarding the beveled anchor plate on the girder detail sheet of structure B-11-185 was inadvertently included. The beveled anchor plate is not needed and there is no â€˜Bearing Detailsâ€™ sheet to reference. The plan sheet will be updated to remove the note as part of an addendum. | Mike Coleman | 52 | 2024-03-26 14:50 | 2024-04-01 09:49
20240409 | 20240409001 | 1 | Use of SONITEC CSL Tubes for Drilled Shafts | Will SONITEC CSL tubes be allowed in lieu of schedule 40 steel pipe? SONITEC tubes provide a safer installation process for workers when installing and splicing CSL tubes. Product information can be found at the link below. https://www.foundationtechnologies.com/files/documents/Sonitec-Product-Sheet--Domestic.pdf | SONITEC CSL tubes will not be allowed in lieu of schedule 40 steel pipe for CSL testing in the drilled shafts for this project. If the contractor and a SONITEC supplier would like to prove this systemâ€™s efficacy for use on future projects, SONITEC CSL tubes may be used in addition to the schedule 40 steel pipe as shown on this project in limited locations to be accepted by the engineer and at no cost to the Department. | Mike Coleman | 53 | 2024-03-27 09:18 | 2024-04-02 12:48
20240409 | 20240409001 | 1 | Earthwork | Please provide the Earthwork Data in excel format. | The earthwork data in excel format can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 54 | 2024-03-28 07:45 | 2024-03-28 10:33
20240409 | 20240409001 | 1 | Lagging Thickness | Please clarify thickness of lagging for R-11-048. SPV for timber lagging has minimum 3" thickness and plan set has minimum 6" thickness | The plan information is correct at 6â€. The language in article 120 will be corrected as part of an upcoming addendum. | Mike Coleman | 55 | 2024-03-29 14:22 | 2024-04-01 11:37
20240409 | 20240409001 | 1 | Agency coordination | Is the army corps 404 permit the only coordination required among regulatory agencies with jurisdiction over Lake Wisconsin and the Wisconsin River for the causeway shown in the plan and as modified by the contractor? | In addition to the US Army Corps of Engineers, the Wisconsin DNR, and Alliant Energy on behalf of the Federal Energy Regulatory Commission (FERC) will need to be consulted/coordinated with when determining the layouts for temporary river access. See special provision article #23 for information regarding FERC coordination. Wisconsin DNR coordination is through the normal Cooperative Agreement process. | Mike Coleman | 56 | 2024-03-29 15:10 | 2024-04-01 09:51
20240409 | 20240409001 | 1 | Rigid Inclusions | Based on the typical section for Rigid Inclusion Ground Improvement, the pay limits only apply to the flat area of Load Transfer Platform. However, the plan view area appears to include the sloped portion of the necessary excavation to build the LTP and install the columns. Please review limits and clarify. | The typical section views are correct. The plan view will be updated as part of Addendum #3. The revised quantity requiring ground improvement is estimated to be 41,575 SF. The miscellaneous quantity sheet will be updated to reflect this new amount. | Mike Coleman | 57 | 2024-04-01 08:35 | 2024-04-02 12:44
20240409 | 20240409001 | 1 | Rigid Inclusions | As the Rigid Inclusion Ground Improvement is a design-build item, can the design-builder elect to start production work at its own risk prior to completion of the load test program? | No. In accordance with subsections C.3 and C.4 of article 127 (Ground Improvement Rigid Inclusion Systems), complete verification load tests on a minimum of three non-production rigid inclusions prior to beginning production rigid inclusion installation. | Mike Coleman | 58 | 2024-04-01 08:36 | 2024-04-01 12:14
20240409 | 20240409001 | 1 | Rigid Inclusions | Can the frequency of Pile Integrity Tests be reduced from 20% of the elements to 5% (which is more typical)? | Pile Integrity Testing (PIT) frequency will remain at 20%. Rigid inclusion ground improvement is a new technology for WisDOT, and the testing frequency is within the typical range suggested in GEC 8. | Mike Coleman | 59 | 2024-04-01 08:37 | 2024-04-01 10:28
20240409 | 20240409001 | 1 | Construction Staking Electrical Items | There is currently no bid item 652.8501 Construction Staking Electrical Installations, please advise if this bid item will be added by addendum? | The bid item is not required. The only electrical related items pertain to ITS installations, which do not require precise locations for this project. If there are any questions about locations of ITS facilities, Dean Beekman would either address them in the field or stake them out himself. His contact information is included in article 99 of the special provisions. | Mike Coleman | 60 | 2024-04-01 10:47 | 2024-04-02 12:47
20240409 | 20240409001 | 1 | Sign Structure D11-10P Foundations | Please confirm the D11-10P permanent sign foundations behind R-11-44 and R-11-46 exert no load on the MSE walls and that the sign foundations extend below the proposed leveling pad of the MSE retaining walls. | Per the Permanent Signing Plan and miscellaneous quantities, the D11-10P signs being installed near retaining walls R-11-44 & R-11-46 are Type II signs on wooden posts and not Type 1 signs with concrete footings. The sign locations can be adjusted, both laterally and longitudinally, to avoid having any impacts on the MSE walls. | Mike Coleman | 61 | 2024-04-01 12:24 | 2024-04-02 12:45
20240409 | 20240409001 | 1 | Slotted Drain | What type installation connection will be required for the slotted drain? Type A shows a short length of pipe, type B shows elbows. | Elbow type connections should be assumed for all connections. But connection types will need to be verified by actual field conditions encountered. | Mike Coleman | 62 | 2024-04-01 13:11 | 2024-04-03 08:46
20240409 | 20240409001 | 1 | Hydraulic Sizing Report | Please provide the Hydraulic Sizing Report that goes along with the Hydraulic Analysis. | The WisDOT completed hydraulic sizing report can be found at the following location: https://wisdot.box.com/s/boh5m1tmev2m86zzl9obxpjdgu5yevjy or can be accessed on the HCCI April bid letting page under Supplemental Information. The results are for information only and not for bidding purposes. | Mike Coleman | 63 | 2024-04-01 14:11 | 2024-04-03 06:39
20240409 | 20240409001 | 1 | Trial Drilled Shaft Foundation | Do all trial drilled shafts for structure B-11-183 have to be completed prior to starting production shafts, or does only the trial drilled shaft at a specific pier need to be completed prior to starting production shafts at the same pier? For structure B-11-184? | For B-11-183, the trial shaft at Pier 2 shall be successfully completed before starting the production shafts at Piers 2 through 5, the trial shaft at Pier 6 shall be successfully completed before starting the production shafts at Piers 6 through 9, and the trial shaft at Pier 10 shall be successfully completed before starting the production shafts at Piers 10 and 11. For B-11-184, the single trial shaft at pier 2 shall be successfully completed before starting the production of any of the B-11-184 production shafts. | Mike Coleman | 64 | 2024-04-01 14:56 | 2024-04-03 06:40
20240409 | 20240409001 | 1 | R-11-048 Soldier Pile Batter | If soldier piles are set at a batter of 1/4"per foot some piles will exceed the 3ft shaft diameter, and others will have limited clearance. Please clarify minimum clearance from edge of footing shaft, and concrete footing diameter. | The requirement for 1/4â€ of batter per 1â€™-0â€ of wall height has been eliminated. In reviewing this matter, changes were also made to the cantilever soldier pile elevation data in Unit 3. Plan sheets conveying these changes will be included in Addendum No. 3. | Mike Coleman | 65 | 2024-04-01 16:20 | 2024-04-04 06:47
20240409 | 20240409001 | 1 | Drilling Contractor Qualifications | In lieu of the requirement in Section A.1 Qualifications of the Contractor; A.1.1 Drilling Contractor Qualification Submittal The drilling contractor performing the work described in this special provision must have drilled shaft foundation project(s) successfully completed similar to those that the plans show using equipment meeting the requirements in Section B.2 within the last five years. Submit . . . Could it be replaced with: The drilling contractor performing the work described in this special provision must have drilled shaft foundation project(s) successfully completed similar to those that the plans show using equipment meeting the requirements in Section B.2. Submit . . . There are drilling subcontractors who have completed projects with 5â€™, 6â€™, 7â€™, 8â€™, 9â€™ and 10â€™ diameter shafts up to depths of approximately 120 feet within the last five years and provide the owner additional competitive bids. | The requirement of contractors having performed similar drilled shaft work using similar equipment within the last 5 years will not be revised. | Mike Coleman | 66 | 2024-04-02 17:02 | 2024-04-03 12:52
20240409 | 20240409001 | 1 | Aggregate Base Items | What conversion factors were used for Base Aggregate Dense 3/4", Base Aggregate Dense 1 1/4" and Select Crushed from CY to TONS? | The designers used the following conversions: Base Aggregate Dense 3/4" = 2.0 to 2.1 Tons/CY; Base Aggregate Dense 1 1/4" = 2.0 Tons/CY; Select Crushed = 1.9 Tons/CY. | Mike Coleman | 67 | 2024-04-02 17:07 | 2024-04-03 08:36
20240409 | 20240409001 | 1 | B-11-183 and B-11-184 elastomeric bearing sole plate coating | What is the required coating over the A588/A709 50W sole plates that are being field welded to embedded girder anchor plates? | The elastomeric bearing steel top plates shall be painted in accordance with section 506.2.8.1 of the standard specifications. Additional notes will be added to the elastomeric bearing sheets for B-11-183 and B-11-184 as part of an addendum. | Mike Coleman | 68 | 2024-04-03 10:07 | 2024-04-03 15:34
20240409 | 20240409001 | 1 | Ground Improvement Rigid Inclusion System | On sheet 41 of the plans a construction detail is given to construct this system. This detail shows a "1:1 (Typ)" slope coming down off the edge of the existing asphalt shoulder. It is most likely that this 1:1 slope will not meet OSHA requirements. This slope will most likely need to be built at a 1.5:1 slope to meet OSHA requirements. Will reduction of the LTP/Rigid Inclusion System overall SF area of improvement to meet OSHA requirements be acceptable? The other options are to provide additional Temporary Shoring (already a bid item) or to remove some/all of the existing asphalt shoulder and replace with Asphaltic Surface Temporary (already a bid item) and aggregate base items in order to achieve an OSHA compliant slope to construct the LTP/Rigid Inclusion System to the limits shown in the plan and future addendum. Temporary shoring and asphalt removal/replacement are not required in the bid item for Ground Improvement Rigid Inclusion System per the details and specifications. | The Ground Improvement Rigid Inclusion System is to be contractor designed and tested by following the information in article 127 of the project specs. The details included in the plans are additional information on how the system may be constructed within the area depicted. Depending on a contractorâ€™s means and methods, some modifications to the details may be required. | Mike Coleman | 69 | 2024-04-03 10:50 | 2024-04-08 07:17
20240409 | 20240409001 | 1 | Ground Improvement Rigid Inclusion System - Notes | On page 41 of the plans, a note in the bottom states "Remove 12-Inches of the Load Transfer Platform and restore to existing conditions once the temporary widening is not required". The specifications for the Ground Improvement Rigid Inclusion require the installation of this system but not the removal. It looks like the earthwork quantities include the removal of this widening in Stage 3 to get this widening back to existing conditions but do not incorporate the excavation needed to remove the top 12-Inches of the LTP. It does not seem like this removal should be required as this is a basic inslope in the final condition and the LTP will be left under an embankment. Please remove this note from the plans or increase the Common Excavation to perform this removal. | The double asterisk note will remain on the plan sheet but will be modified to the following: â€˜After temporary widening is no longer required, remove sufficient thickness of the Load Transfer Platform, if required, so a minimum of 6â€ of topsoil can be placed for reestablishing median vegetation and drainage. Removal, if required, would be paid as Common Excavation.â€™ | Mike Coleman | 70 | 2024-04-03 11:02 | 2024-04-04 06:47
20240409 | 20240409001 | 1 | Existing Concrete Pavement | Does the Department know if the existing concrete pavement is doweled or continually reinforced? | Multiple types of existing concrete pavement are likely to be encountered based on available as-builts. The original 4-lane pavement was listed as â€˜Reinforced Concrete Pavementâ€™ and likely includes steel fabric or mesh. More recent concrete pavement is likely doweled. | Mike Coleman | 71 | 2024-04-03 11:41 | 2024-04-04 06:45
20240409 | 20240409001 | 1 | Stone Causeway Between Piers 3 & 6 | Can stone causeway be used as a means of access between piers 3 & 6 if causeway design contains sufficient waterway openings to allow necessary flows to remain and deemed acceptable upon result of the hydrology study? | Per language included in article 94 of the project specifications, placement of riprap material for use as temporary access between piers 3 and 6 on both new bridges is not allowed. | Mike Coleman | 72 | 2024-04-03 15:24 | 2024-04-05 09:59
20240409 | 20240409001 | 1 | Living Snow Fence Plant Material | What is the minimum acceptable height for the shrubs on the living snow fence? | Seedling stock which is typically 1-2 year bare root stock that is 15â€-24â€ tall. | Mike Coleman | 73 | 2024-04-03 15:57 | 2024-04-05 09:58
20240409 | 20240409001 | 1 | Living Snow Fence Plant Material | Are single cane plants acceptable for the living snow fence or do the plants need to comply with the minimum cane requirements according to the American Standard for Nursery Stock (ANSI)? | Acceptable plants for the living snow fence are listed on page 178 of the plan. | Mike Coleman | 74 | 2024-04-03 15:59 | 2024-04-05 09:59
20240409 | 20240409001 | 1 | Soldier Pile Supplier | Do the soldier pile supplier/fabricators need to be on the pre-approved products list for primary members or Fabricated Bridge Components list. | The Department will accept soldier pile steel fabrications supplied by approved fabricators from both the â€œPrimary Membersâ€ list and the â€œFabricated Bridge Componentsâ€ list. Please note that Standard Specifications for 506 Steel Bridges apply and require that all welding conform to AWS D1.5, as referenced in â€œ506.3.19 Weldingâ€. | Mike Coleman | 75 | 2024-04-05 10:33 | 2024-04-08 07:18
20240409 | 20240409001 | 1 | Causeway access between piers 3 and 6 | The response to question 72 is contradictory to the response provided in the prebid meeting on 3/19/2024. Requiring barge access or constructing a temporary structure present significant unnecessary safety risks to the contractor, the existing piers and the power lines east of the bridge. Please revise the response to question 72 to allow causeway access between piers 3 and 6 with acceptable hydrologic survey results. | Shifting temporary river access to be partially or completely between new piers 3 and 6 may be possible. However, it cannot be stated with certainty that such a shift will be acceptable prior to the Department receiving and reviewing documents. The temporary river access layouts in the plan were used to estimate environmental impacts and complete preliminary hydraulic modeling. Contractors are likely to make some adjustments to the layouts to fit their individual means and methods for constructing the new bridges. Any changes of what is currently permitted will require the contractor (working in conjunction with WisDNR & WisDOT) to submit a request for an amended 404 permit. In addition, any temporary river access utilized for the project will need to maintain an opening within the main river channel (see plan page 38) to allow for aquatic organism passage as well as sufficient depth for all expected navigational traffic. The â€˜openingâ€™ cannot be achieved solely by means of equalizer pipes. The exact layout of temporary river access, including an acceptable opening, would need to adhere to all conditions/requirements outlined in section B.2 (Deliverables) of article 94 of the project special provisions. Those requirements are included as part of the response to the question: â€˜For any temporary access constructed within the banks of the Wisconsin River, prepare and submit hydraulic calculations and report increase in velocities and potential for erosion for the restricted waterway detailing the effect on river flows for Q2, Q5, and Q100 flood events. Use intermittent openings in the temporary access to allow for continued river flow without causing excessive downstream scouring. Include the location and size of temporary access and openings in the calculations. Calculations shall be signed and sealed by a professional engineer licensed in the state of Wisconsin. The engineer and WDNR will complete a review of the hydraulic calculations within 10 days of submittal. Do not construct any temporary access until the engineer and WDNR approve the hydraulic calculations. Causeway design, layout, openings, widths, and elevations must avoid any increase to the base flood elevation (BFE) on insurable structures. Any increase to the BFE that impacts an insurable structure will require contractor notification of all impacted property owners, the affected County Zoning Department, and additional FEMA coordination.â€™ | Mike Coleman | 76 | 2024-04-05 16:59 | 2024-04-08 12:53
20240409 | 20240409002 | 2 | 643.0800 Traffic Control Arrow Boards | Please review the quantity listed for Traffic Control Arrow Boards. The Misc. Qty table on plan sheet 26 shows a quantity of (1) for every line item listed in the Traffic Control table. Should this be (1) for (40) days on the Westbound lane closure and (1) for (35) days on the Eastbound lane closure? Thanks | The quantity should be 75 days total, (1) for (40) days on the Westbound lane closure and (1) for (35) days on the Eastbound lane closure. An addendum will be issued to clarify the miscellaneous quantity plan sheet and the project quantities. | Mike Coleman | 1 | 2024-03-22 14:23 | 2024-03-26 07:45
20240409 | 20240409002 | 2 | Installing and Maintaining Bird Deterrent System | There is an item for installing and maintaining bird deterrent system for both structures in this contract. Being this project is bid in April and migratory birds/ swallow dates of 4/15 - 8/31 will the county/ local municipality be installing the bird deterrent system? |  |  | 2 | 2024-03-28 16:55
20240409 | 20240409002 | 2 | Removing rivets Item 54 quantity | Does the quantity of 93 Each for this item include removing the existing top batten plate on sheet 9 and the existing top lacing shown on sheet 11 for the batten plate replacement work? The plan states that these can be removed if necessary for installation of the new batten plates. The total quantity for the removing rivets bid item does not work out if these are not included. There appear to be 65 rivets for the work at all other locations, and then 16 for the optional removal at Span 8 NT L14 and 12 at Span 8 ST L11. | The optional removal rivets are included with the plan quantity. Payment will be based on the actual number of rivets removed. | Mike Coleman | 3 | 2024-04-03 11:44 | 2024-04-05 10:04
20240409 | 20240409003 | 3 | Soil Borings | Are soil borings available? | The soils reports can be found at the following location: https://wisdot.box.com/s/vfv6c1m1psoy2j3zjue4nz03wg1tzycx or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-03-15 14:54 | 2024-03-19 07:11
20240409 | 20240409003 | 3 | Cross Drains | A detail for Cross Drain Installation is provided in the Construction Details for both plans, please clarify which cross drains will be subject to this detail. Will the excavation of the 10:1 slope be paid as common excavation at all locations? Will the Granular Backfill Grade 2 be paid separately or will it be incidental to the pipe installation? If paid separately, an additional bid item will need to be added. | All cross drains, including non-drainage pipes, under CTH O are required to follow the construction details. Install side road and driveway culvert pipes per Standard Specifications unless directed to utilize construction details as determined by the engineer. An addendum will be issued to clarify bid items and pay limits for the Cross Drain Installation detail. | Mike Coleman | 2 | 2024-03-25 15:08 | 2024-04-02 07:29
20240409 | 20240409003 | 3 | Earthwork | Can the Earthwork Data plan pages be provided in excel format? | The Earthwork Data Sheets can be found at the following location: https://wisdot.box.com/s/vfv6c1m1psoy2j3zjue4nz03wg1tzycx or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-03-26 08:15 | 2024-03-26 13:29
20240409 | 20240409003 | 3 | Breaker Run | Breaker Run is provided as a CY item. Please review and verify the bid quantity. | Breaker Run Quantity is a CY item. The bid item quantity for it should be 185 cy. This can be revised in an addendum. | Mike Coleman | 4 | 2024-03-26 10:51 | 2024-03-28 05:36
20240409 | 20240409003 | 3 | Rock Excavation | Where is Rock Excavation anticipated? It is not shown in the Earthwork Data or the cross sections. Will the Department allow the Rock Excavation to be processed into Base Aggregates and utilized on the project? | The soil reports were submitted earlier and are located : The soils reports can be found at the following location: https://wisdot.box.com/s/vfv6c1m1psoy2j3zjue4nz03wg1tzycx or can be accessed on the HCCI April bid letting page under Supplemental Information. Any virgin base aggregate placed on the project must follow Standard Spec 106.3.4.2.2 for source approval (this testing can take up to a month or longer to complete) and then additionally follow the specifications in Standard Spec 301 and Standard Spec 305. | Mike Coleman | 5 | 2024-03-26 12:52 | 2024-03-28 08:23
20240409 | 20240409003 | 3 | Construction/Completion Date of 2025? | Is the Proposal correct that this will be a 2025 construction project or is supposed to be a 2024 construction since it is being bid in April of 2024. | The Proposal is correct that this will be a 2025 construction project. It is being bid in April of 2024. Per Special Provisions 3. Prosecution and Progress, tree clearing may occur in 2024, but all other construction is to occur in 2025. | Mike Coleman | 6 | 2024-04-01 13:35 | 2024-04-02 07:30
20240409 | 20240409003 | 3 | Station 63+04 Ends | Are cross drain bars and sloped ends required on station 63+04? the note shows cross drain as on 643+45 and 647+75 where sloped ends and cross drainage bars are required. | Cross Drain bars added to one end, the other end is behind beamguard. Also added cross drain bars at pipes at 622+40 Items will be added in an addendum. | Mike Coleman | 7 | 2024-04-01 16:01 | 2024-04-03 12:51
20240409 | 20240409004 | 4 | Soil Borings | Are soil borings available? | The soils reports can be found at the following location: https://wisdot.box.com/s/0shaz13aqx7b0cislfmgx9khn1xp3t2n or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-03-15 14:55 | 2024-03-19 07:09
20240409 | 20240409005 | 5 | Bird Netting | Will the local municipality install the bird netting? | Yes, Columbia County installed netting on the structure 2/21/2024. | Mike Coleman | 1 | 2024-03-21 08:30 | 2024-03-21 12:38
20240409 | 20240409006 | 6 | Photometric Evaluation | In section "B.1.2 Photometric Evaluation" it states the Photometric layout files will be available from the DOT. We would like to request those files; please advise when and how those will issued. Thank you- |  |  | 1 | 2024-04-08 16:29
20240409 | 20240409007 | 7 | S-67-420 | We can't seem to find the drawings for S-67-420. Can you please provide them? | An addendum will be issued to add ALL the Sign structures | Mike Coleman | 1 | 2024-03-18 16:18 | 2024-03-22 10:00
20240409 | 20240409007 | 7 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/zdttee1niqleow14vhp3i5udeece2zna or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-03-22 13:39 | 2024-03-25 12:19
20240409 | 20240409007 | 7 | Strapping C-67-1570 | The strapping detail for structure C-67-1570 shows two straps per wing on wings 3 and 4. The bid quantity is two, should it be four each? | Per Item SPV.0060.010 Strapping C-67-1570 in the Special Provisions, the measurement section states, â€œThe department will measure Strapping C-67-1570 as each wing for the repair work, acceptably completed.â€ There are two wings with strapping, therefore the quantity of 2 EACH is correct. | Mike Coleman | 3 | 2024-03-26 16:35 | 2024-03-27 12:35
20240409 | 20240409007 | 7 | Reset Existing Bearings SPV.0060.103 | What is intended to be done for this bid item? Are we to cut the bearings loose, reposition and weld them back into place or just jack the girders and attempt to reposition the laminated bearing pads? It is unlikely that the rubber in the bearings will return to plum after they are jacked off of the abutment. | Cutting the bearings loose by removing the weld is not intended with this item. The bearings are anticipated to return to mostly plumb once the load is lifted, and in some cases, force may need to be applied to achieve a plumb position. | Mike Coleman | 4 | 2024-04-02 11:08 | 2024-04-03 15:23
20240409 | 20240409007 | 7 | Backfill Slurry | Due to the small amount of backfill slurry that will be needed each night, most suppliers are unwilling to quote at night for this material in such small volumes. Can the Department either allow for more time for the cross culvert installation or specify a different backfill material (ie clear stone etc)? | The Backfill Slurry bid item will be updated to Backfill Granular Grade 1 for the cross culvert installation with an Addendum. | Mike Coleman | 5 | 2024-04-03 07:56 | 2024-04-05 10:00
20240409 | 20240409007 | 7 | Cross Culverts | Will the Department be paying for Temporary Asphalt in the culvert pipe patches? By the time closures are set, the patches are sawed, culvert is installed/backfilled, there will not be enough time for the the HES base patching to get strength prior to opening to traffic. | The Detail for Installation of Culvert Pipes will be updated to show Temporary Asphalt for the culvert patch with an Addendum. The culvert locations will still require Base Patching Concrete SHES to replace the temporary asphalt, but work can be done under single lane closures. | Mike Coleman | 6 | 2024-04-03 08:04 | 2024-04-05 10:01
20240409 | 20240409007 | 7 | S-67-420 Follow-Up | Is the 'Foundation Two-Shaft' quantity of 1 correct for this structure or should there be a quantity of 2? | The quantity will be updated to 2 in an Addendum. | Mike Coleman | 7 | 2024-04-03 08:40 | 2024-04-05 10:02
20240409 | 20240409007 | 7 | Micromilling | 1. Due to the schedule constraints, is this item necessary? Prospective bidders will need to be milling and paving sections of IH 94 shortly after the base patching is completed to finish the IH 94 work by 10/27. Therefore, the base patches will be subject to live traffic for short time periods. 2. If the micromilling is deemed necessary, can the Department remove the section 420 from SPV 130 so that Diamond Grinding is not bid per the specifications? Conventional milling equipment is capable of temporary ride fixes, much more available, and is far less expensive. | 1. The micromilling bid item is included as an option to get a smooth riding surface if base patches are subject to live traffic before special events. If the paving can be completed without having to run traffic on base patches, that is an acceptable approach. 2. The micromilling bid item shall be bid per the specification requirements. Conventional milling does not provide the desired surface roughness for opening to traffic. | Mike Coleman | 8 | 2024-04-04 11:00 | 2024-04-05 10:03
20240409 | 20240409007 | 7 | HFST | The High Friction Surface Treatment requires a 30 day cure time on the pavement. Will there be a specific stage for the HFST? It's not clear when that is to occur and how the traffic control will be handled. | The High Friction Surface Treatment (HFST) traffic control and stage is identified on the Traffic Control Miscellaneous Quantities page (page 337). Additional language in the Special Provisions Prosecution and Progress article states â€œThe high friction surface treatment will require the contractor to pave those areas completely to allow time for cure and favorable temperatures to apply the final HFST. The contractor is expected to account for this in their schedule.â€ | Mike Coleman | 10 | 2024-04-05 13:10 | 2024-04-08 09:01
20240409 | 20240409008 | 8 | 6" Epoxy Quantity | Please review the quantities for the 6" Epoxy markings on this project, as the plan and proposal have conflicting quantities. Proposal shows: 646.2040 Marking Line Grooved Wet Ref Epoxy 6-Inch 25,683 LF Plan Misc. Qty shows: 646.2020 Marking Line Epoxy 6-Inch 12,890 LF 646.2040 Marking Line Grooved Wet Ref Epoxy 6-Inch 12,793 LF Please advise which is correct. |  |  | 1 | 2024-04-01 10:44
20240409 | 20240409009 | 9 | Design Schedule | Could you please provide a design schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/owwyoi3o3djftkhlcvaw2pxssv6i3rfv or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-03-15 12:51 | 2024-03-19 06:48
20240409 | 20240409009 | 9 | Pavement Marking | There is not a Same Day Epoxy item for the surface layer of pavement. Does the Department intend to have Grooved Wet Reflective Centerline? | No, the centerline will be epoxy pavement marking, nor grooved wet reflective. An addendum will be issued to remove the 646.2020 Marking Line Epoxy 6-Inch item and replace with the 646.4720 Marking Line Same Day Epoxy 6-Inch. | Mike Coleman | 2 | 2024-03-19 16:31 | 2024-03-21 08:12
20240409 | 20240409009 | 9 | Pavement Marking | There is not any quantity for Temporary Marking Line Paint Edge lines. Will this be paid under the Temporary Marking Line Paint item? | No, temporary edge line markings is not intended to be used on this project. | Mike Coleman | 3 | 2024-03-20 07:58 | 2024-03-21 08:14
20240409 | 20240409010 | 10 | consturction schedule | Contractor is requesting a copy of the DOT's initial construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/18fojqw11xrz6hjvrij1nz3afgo7ceqm or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-03-20 14:24 | 2024-03-25 12:20
20240409 | 20240409012 | 12 | Soil Borings | Are soil borings available? | Soil borings are not available for this project. | Mike Coleman | 1 | 2024-03-15 14:56 | 2024-03-19 06:50
20240409 | 20240409012 | 12 | Bid Items and Sign Details | While reviewing the plan set we noticed a couple of possible omission's. -Missing Bid Item for Type I Covering Signs- -Missing Sign Detail for Fixed Message Signs- | Item 643.0910 (Traffic Control Covering Signs Type 1) was inadvertently omitted from the bid package. In addition, the quantity of Item 643.0920 (Traffic Control Covering Signs Type 2) has been revised. An addendum will be prepared for this update. | Mike Coleman | 2 | 2024-03-22 09:16 | 2024-03-25 09:25
20240409 | 20240409016 | 16 | Traffic Control Quantities | It doesn't appear that there are enough lane closures and/or ramp closures for bid items to cover the 30 days post construction of each area to provide the seed watering and sod watering bid items. Will the department add an additional quantity of 10 lane closures and ramp closures to each site for this work to be accomplished? | The design team reviewed the question and determined additional traffic control quantities are warranted for Sites 1, 3, 4, and 5 as described below. The proposed quantity of 10 closures per site is reasonable. An addendum will be issued. Site 1 â€“ Same shoulder closure will be used as used for construction. Quantities will be added for additional days. Site 2 â€“ Nothing additional needed. All watering can be done from fence gate access. Site 3 â€“ Full traffic control needed for this site. Quantities will be added for additional days including lane closure. Site 4 â€“ Shoulder closure on Watertown Plank Rd and ramp signage needed. Quantities will be added for additional days. Site 5 â€“ Shoulder closure and ramp signage needed. Quantities will be added for additional days. Site 6 â€“ Nothing additional needed. There is very little traffic/activity in this area. Water truck should be able to access site over curb without any additional traffic control. | Mike Coleman | 1 | 2024-03-25 09:10 | 2024-04-01 07:42
20240409 | 20240409016 | 16 | Traffic Control | Will we be allowed night time ramp closures for sites #3,4,5 to do the main regrading? This would make the work much easier to do and complete more quickly? | No nighttime ramp closures will be allowed for Sites 3, 4, and 5. | Mike Coleman | 2 | 2024-04-04 14:47 | 2024-04-05 13:46
20240409 | 20240409016 | 16 | Schedule - Traffic Control | Stage 2-Site 2 has the most work of all the pond areas but only shows 2 days of traffic control, I dont think the work can be completed in this time frame. Can additional days be added to this stage. 2 days detour and 4 days staging? | Most of the work at Site 2 can be accessed and completed by entering the fence gate on 100th Street. This access point will not require any traffic control. The traffic control (including ramp closures and detour routes) will be necessary to place the base aggregate dense with the asphaltic material binder behind the barrier walls. It is assumed that the material will be brought in from the freeway side and dumped over the top of the barrier. | Mike Coleman | 3 | 2024-04-04 14:54 | 2024-04-05 13:46
20240409 | 20240409016 | 16 | Site 2 Access | Can Site 2 be accessed for all of the work from South 100th St thru the access gate? Is there a reason this access can not be used for this work for the riprap and regrading? | Yes, most of the work at Site 2 can be accessed and completed by entering the fence gate on 100th Street. This access point can be used for the riprap and regrading. | Mike Coleman | 4 | 2024-04-04 14:56 | 2024-04-05 13:47
20240409 | 20240409016 | 16 | Flexmat | Can you show the exact location of the flexmat in site 2, I do not see it on the plan sheets? | The Flexamat location is shown on page 14 of the plans at Site 2E. This is on the NW side of the pond. It is the â€œemptyâ€ shape as shown on the erosion control legend on page 12. | Mike Coleman | 5 | 2024-04-04 15:00 | 2024-04-05 13:47
20240409 | 20240409016 | 16 | Traffic Control | Site 4 shows access is by crossing I41 SB Off Ramp. Is there any restrictions on crossing in this location during the day? | There are no crossing restrictions at the bottom of the loop ramp at Site 4. The specs discuss this area in the Traffic article under â€œEquipment Crossingâ€. It states that extreme caution should be used when crossing the ramp. It also requires that measures be taken to minimize vehicular and equipment crossings at this location. | Mike Coleman | 6 | 2024-04-04 15:03 | 2024-04-05 13:47
20240409 | 20240409016 | 16 | Site 2 Night time | The plan shows the work at site 2 as night time, if we can access from South 100th St can this be done during the day? | Most of the work at Site 2 can be done during the daytime. The night time work is specifically for hauling in the base aggregate dense material to the site. Bringing in the base aggregate dense from the freeway side over the barrier walls should allow for easier and more efficient operations. The steep slopes within this site would make bringing the aggregate in off of 100th Street difficult. Also, ground disturbance needs to be minimized and will not be allowed outside of the work zones shown in the plans. | Mike Coleman | 7 | 2024-04-04 15:05 | 2024-04-05 13:47