## qandasearchletting_results
Date: | 2024-05-14
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20240514 | 20240514001 | 1 | 1589+17 - 1592+67 Slotted Vane Drane | As shown in the typical sections from STA 1589+17 to 1592+67, contractors are to pave up to the edge of the slotted vane drane (presumably 3&quot;). In most cases a 1x3 is put on top of the vane to prevent HMA from entering the pipe. In this case it will have to be larger board or protective device due to the HMA being ~3&quot; above the top of the vane. Is this incidental to paving? Also if the Department plans to use this for a future crossover, there is a high likelihood traffic using this crossover in the future will cause the unconfined edge of the HMA to fail at the vane. Has the Department looked if there are any products available to put a &quot;riser&quot; on the vane to help prevent this future failure? If such product exists, please add an item via addendum. | The department will not be using this crossover in the future and therefore the slotted drain does not need to be raised or adjusted vertically. It is the contractorâ€™s responsibility to prevent HMA from entering the pipe and is incidental to paving. | Mike Coleman | 1 | 2024-04-30 09:22 | 2024-04-30 10:57
20240514 | 20240514001 | 1 | Temporary Barrier Wall | In the staging plans, contractors will have to move the wall off of NB/WB onto EB/SB in order to pave on NB/WB from STA ~1582+31-1592+67. This will have to happen again when paving EB/SB. This will create more &acirc;&#128;&#156;mini-stages&acirc;&#128;&#157; in each direction as the existing wall is pinned and removal is not something that can be removed, placed, milled, and paved in each direction in the timeframes. On sheet 25 it shows the various sections (A-A, B-B, C-C, D-D, &amp; E-E). Would the Department entertain changing the plans and leaving the wall and milling a butt joint as shown in section D-D for the entire length of the temporary wall? This would reduce costs on the project by eliminating the need for crash cushions, moving the pinned wall multiple times over multiple different nights, moving the wall back at the end of the project, reduce the HMA quantities slightly, and increase production on the paving/milling operations. | We cannot mill a butt joint for the entire length of the temporary wall due to the steepness of the existing shoulder. Creating a butt joint steepens the shoulder by 2.4% to 2.8% which would make some shoulders steeper than the maximum allowable shoulder slope. | Mike Coleman | 3 | 2024-05-06 13:19 | 2024-05-07 11:46
20240514 | 20240514001 | 1 | Prosecution and Progress | Is the below paragraph necessary? It contradicts Lane Rental Fee Assessment &quot;The Contractor will not incur a lane rental fee assessment for closing lanes during the allowable lane closures times&quot; and may add inadvertent costs to the project. Work Restrictions&#58; A maximum of 20 days of single lane closures will be allowed to complete non HMA paving work. Assessments per the Lane Rental Fee Assessment article will be charged for lane closures outside the allowed time periods, or for additional days. |  |  | 2 | 2024-04-30 09:57
20240514 | 20240514001 | 1 | Temporary Barrier Block | Please clarify that there should be no Item for Concrete Barrier Temp Precast Delivered (603.8000) and that all block for this project will be shifted-multiple times (and then left in place at the end of project). If this is not the case a pay item needs to be added or clarification needs to be provided as to what is to be included in the Item for Conc Barr Temp Prec Inst. Please also clarify or include more information of the current barrier block on site that is to be shifted. Is all of this barrier block currently pinned? Will it need to be unpinned and re-pinned multiple times for stage shifts? | There will be Concrete Barrier Temporary Precast in place when the project begins, and it will be pinned. The Concrete Barrier Temporary Precast will need to be pinned in its final location. No Concrete Barrier Temporary Precast Delivered item will be required. Concrete Barrier Temporary Precast Installed item and temporary locations are shown in the plan. | Mike Coleman | 4 | 2024-05-06 17:04 | 2024-05-07 11:47
20240514 | 20240514001 | 1 | 643.1500 Radar Trailers & SPV.0045 Digital Speed Reduction System | Please confirm that both items 643.1500 Speed Radar Trailer and SPV.0045 DSRS are to be used at the same time. Typically we have seen one or the other used, not both on the same project. This could be slightly confusing/overwhelming to the traveling public as there could be up to (6) Radar Trailers and (12) Digital Speed Limit Trailers used within a 3.5 mile stretch of roadway. Thanks | An addendum will be provided to eliminate item 643.1500 Traffic Control Speed Radar Trailer. | Mike Coleman | 6 | 2024-05-07 08:49 | 2024-05-08 09:59
20240514 | 20240514001 | 1 | Item 136 - Special 01. Removing Barrier Wall Lip (SPV.0060) | Please provide more clarity on this Item. Does this have to do with removing 55 EA pieces of Temporary Barrier block that is LIP (Left in Place) near Inlet or Vein Drain locations or is this to sawcut and break a concrete &quot;lip&quot;/edge from permanent cast in place Concrete Barrier? | The item Removing Barrier Wall Lip is to remove a portion of the permanent concrete barrier that interferes with the placement of steel adjustment rings at existing inlets. See the construction detail on Page 19 of the plans. | Mike Coleman | 5 | 2024-05-06 17:08 | 2024-05-07 11:47
20240514 | 20240514001 | 1 | Lane Closure Timeframes | Would the Department entertain extending the lane closure timeframes by 2 hours to significantly reduce project costs and overall construction timeframes on the SB/EB direction? | No, the lane closure timeframes will not be extened. | Mike Coleman | 7 | 2024-05-09 14:48 | 2024-05-10 08:48
20240514 | 20240514002 | 2 | WI DOT Sparta Rest Area Roller Shade Question | (Roller Shades) The Miscellaneous Schedule on Page A1-50 calls for WT-1 Manual Roller Shades, but then lists Profile&#58; Roller 20. Roller 20 is a Lutron motorized shade. Could you please confirm that we are to supply + install manual shades? I am not seeing any other mentions of motorization except for the &quot;Roller 20&quot; note. | Roller shades should be manual. Lutron Contract roller shades should be listed in lieu of Lutron Roller 20. Miscellaneous Schedule will be updated in the upcoming project addendum. | Mike Coleman | 18 | 2024-05-06 13:32 | 2024-05-08 07:47
20240514 | 20240514002 | 2 | Addendum 1 plans | Are the plans for Addendum 1 to scale? | As part of the addendum process, the included plan sheets are reprinted from their original 11â€x17â€ size to 8.5â€x11â€, so the sheets would not be to scale with what is listed on the sheets at that size. | Mike Coleman | 27 | 2024-05-08 15:21 | 2024-05-09 10:36
20240514 | 20240514002 | 2 | Getoechnical Report | Can you post the Geotechnical Report? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/dq18rd54chqojxffi1a635pps4cd70rg or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 11 | 2024-04-23 13:44 | 2024-04-23 13:47
20240514 | 20240514002 | 2 | light pole bases | Do all light pole bases need to be cast in place or can they be precast bases? | All light pole bases must be cast in place per WisDOT standard spec 654. | Mike Coleman | 19 | 2024-05-06 14:18 | 2024-05-07 11:50
20240514 | 20240514002 | 2 | Exterior Finish Schedule | Exterior Finish Schedule calls for a UC-6 roof panel, spec calls for UC-4 which are we to use? Not seeing anything in the specs regarding snowbar or the composite metal panels- are we to go off the Exterior Finish Schedule? | UC-4 panels should be used. Refer to Accessories 07 41 13 Metal Roof Panels for snow retention or snow bars. Provide system equivalent to system shown on the drawings. Composite metal panels additional spec section will be included in the upcoming project addendum. | Mike Coleman | 24 | 2024-05-07 09:22 | 2024-05-08 07:51
20240514 | 20240514002 | 2 | Site Furnishings Conflicting Information | For article 28, Part 2 Products, 2.2 Site Furnishings, Section A.3 states to surface mount unless otherwise noted. Both types of picnic tables and the benches state to use the in-ground mounting option. The SDD calls for a surface mount to thickened sidewalk concrete. Which style is needed? Also, the model numbers for both types of picnic table and the benches are for a galvanized finished product. The material listed below that states to use Powder Coated Black. Which finish is needed? | The articles will be revised for clarity with an upcoming addendum. | Mike Coleman | 12 | 2024-04-25 11:37 | 2024-04-29 09:46
20240514 | 20240514002 | 2 | Water Source Heat Pump Approved Manufacturers | For spec section 23 81 28 - Water to Air Heat pumps and spec section 23 81 49 - Ground source unitary heat pumps can Climatemaster be added to the list of approved bidders? | Climatemaster manufactures products that meet the project specifications. Climatemaster will be added to the list of approved manufacturers in an upcoming addendum. | Mike Coleman | 1 | 2024-04-11 08:51 | 2024-04-16 08:16
20240514 | 20240514002 | 2 | Water Well | From my research there is only one well, that has been reported twice, that currently serves the Sparta Rest Stop. It was drilled in 1966, and produces 56 GPM. It has a 12in bore hole with an 8in hung liner, that starts at 47ft deep. Can someone verify this, and update the spec to request a 12in pitless adapter? I can not find any specs for water line placement, to the well, or what size drop pipe, or service lines are being requested. Are these all being reused? Does the well need to be rehabilitated to provide 86GPM? | â€œFrom my research there is only one well, that has been reported twice, that currently serves the Sparta Rest Stop. It was drilled in 1966, and produces 56 GPM. It has a 12in bore hole with an 8in hung liner, that starts at 47ft deep.â€ â€¢ Your research is correct. The information you provided can be found in the Well Construction Report for existing well number JB123. The report can be viewed on the WDNR website. However, well JB123 will NOT be used for the new Rest Area facility. As shown on Plan Sheet 303 for project 1071-07-79 (Miscellaneous Quantities) and Standard Specification 204.0265, Abandoning Wells, the existing well will be ABANDONED using WDNR code-compliant procedures. â€œCan someone verify this, and update the spec to request a 12in pitless adapter?â€ â€¢ Two Pitless adapters are called for on Sheet 303 of the plans (Miscellaneous Quantities), and Special Provision SPV.0060, Pitless Adapter in the Specifications. â€œI can not find any specs for water line placement, to the well, or what size drop pipe, or service lines are being requested.â€ â€¢ Two new wells shall be constructed at Stations 1185+34 RA and 1191+62 RA as shown on Sheets 39 (Utility Plans -Water) and 303 (Miscellaneous Quantities) of the Plans and throughout Specifications pages 604-613. Plan Sheet 39 also shows the locations of the 3-inch water lines that run from the two wells to the Rest Area building and the 1-inch water line that runs from the Rest Area Building to the Maintenance Building. See Specification for Water Lines on page 613 for other requirements (min. depth 7.5-feet). â€¢ Please note that this is an 86 GPM constant pressure system with variable speed pumps and well system controls that alternate the draw on the two wells on a daily basis. Please see the specifications for other requirements. â€œAre these all being reused? â€œDoes the well need to be rehabilitated to provide 86GPM?â€ â€¢ No. The existing well will be ABANDONED. The new 2-well system shall provide 86 GPM. | Mike Coleman | 26 | 2024-05-08 13:40 | 2024-05-13 06:33
20240514 | 20240514002 | 2 | Generac Power Systems as approved equal | Good afternoon. I am submitting a request that Generac Power Systems be added to the list of acceptable manufactures for the standby generator and automatic transfer switch for this project. If this is not attainable, will Generac Power Systems be considered an &quot;equal&quot; manufacture? Wolter Inc has done several projects with WIDOT with no issues in the past. Thank you for your time! Dustin Blackburn Sales Account Manager 262-525-8011 dustin.blackburn@wolterinc.com | Generac Power Systems is an acceptable manufacturer. They will be added to the project specifications in the upcoming project addendum. | Mike Coleman | 16 | 2024-05-01 16:09 | 2024-05-08 07:46
20240514 | 20240514002 | 2 | Substitutions for trees? | Good morning, Would the project manager accept the substitutions of Celtis occidentalis &#39;Chicagoland&#39; for straight Celtis occidentalis? Additionally, would the project manager accept the substitution of Quercus alba to Quercus imbricaria Shingle Oak or Quercus palustris &#39;PWJR08&#39; Pacific Brilliance Oak or Qercus bicolor Swamp White Oak? Please let me know. Thanks. | Please bid as shown on the plans and in the specs. The winning bidder may propose alternatives to those products that are listed in the project documents to the construction team. They will work with the architectural team to determine if it is an approved equal or not. | Mike Coleman | 30 | 2024-05-10 05:13 | 2024-05-10 09:32
20240514 | 20240514002 | 2 | Tree Species | I see there are 25 2.5" caliper trees requested for this bid. What are the desired species and quantities for the trees requested? I cannot find this information in the specs. | The specific tree species and quantities are listed on the Site Restoration plan sheets (page 56-59). The MQ table in the plans will be updated with an upcoming addendum to list the different tree types separately. | Mike Coleman | 5 | 2024-04-17 08:13 | 2024-04-18 08:30
20240514 | 20240514002 | 2 | Bid Bond | If prime bidders are submitting their bid online and have an annual bond with the DOT is the $100,000 bid guarantee listed in the advertisement for bid also required to be submitted on form DT1303 1/2006 - Proposal Bid Bond Form? | If the bidder has an annual bid bond, which they should in order to bid online, they do not have to submit a proposal bid bond. | Mike Coleman | 31 | 2024-05-10 08:19 | 2024-05-10 10:23
20240514 | 20240514002 | 2 | Communications Conduit / Raceway | Is an underground conduit(s) required to accommodate low voltage communications, camera and security cables between the rest area building and the the maintenance shed? If so, What is the size and number of conduits required? | We need (1) 2 inch conduit from the main building to the maintenance shed. This will be addressed in upcoming Addendum 02. | Mike Coleman | 13 | 2024-04-30 08:44 | 2024-05-07 06:34
20240514 | 20240514002 | 2 | Controls | Plan calls out for TAC Andover. 1.12 under spec 23 09 24 DDC Control for HVAC In past the Department has allow others of equal to be used and this has been done on other rest areas and government buildings. Can this be changed to allow others to be approved upon Department approval? | Please see the response to Question #25 for additional acceptable manufacturers. | Mike Coleman | 28 | 2024-05-09 07:41 | 2024-05-09 10:35
20240514 | 20240514002 | 2 | Controls | Plan calls out for TAC Andover. 1.12 under spec 23 09 24 DDC Control for HVAC Question #25 states a list of approved controls In past the Department has allow others of equal to be used and this has been done on other rest areas and government buildings. Can ABB controls also be approved? | The design team has determined that ABB Controls would be an approved manufacturer. The winning bidder may propose different manufacturers than those that are listed in the project special provisions to the construction team. They will work with the architectural team to determine if they are an approved equal or not. | Mike Coleman | 29 | 2024-05-09 11:00 | 2024-05-10 06:24
20240514 | 20240514002 | 2 | Site Electrical - well pump electrical circuitry is missing from the spec and drawings. | Please provide electrical circuitry for the well pump including phase, voltage, and panel board breaker? | This information will be provided in an upcoming addendum. | Mike Coleman | 3 | 2024-04-15 14:47 | 2024-04-22 08:14
20240514 | 20240514002 | 2 | Site Electrical - Sewer Ejector pump electrial circuitry is missing from ths spec and drawings. | Please provide electrical circuity for the the sewer ejector pump including phase, voltage, amperage and panel board breaker? | This information will be provided in an upcoming addendum. | Mike Coleman | 2 | 2024-04-15 14:43 | 2024-04-22 08:29
20240514 | 20240514002 | 2 | Spec Divsion 28 - Electronic Safety and Security | Please provide the spec section for Division 28 Electronic Safety and Security? | This information will be provided in an upcoming addendum. | Mike Coleman | 4 | 2024-04-15 14:50 | 2024-04-22 08:29
20240514 | 20240514002 | 2 | Camera Pole Disconnect | Reviewing the panel schedules from the Rest area building i am not seeing a breaker for the camera pole disconnect. Where is the camera pole disconnect being power from? | The breaker for the exterior FTMS cameras is to be located in the lighting cabinet as noted on page 258 and 266 of the let plans. | Mike Coleman | 23 | 2024-05-07 09:08 | 2024-05-08 07:45
20240514 | 20240514002 | 2 | door and wall portection | section 10 28 00 specifies door and wall protection however non is shown on drawings - confirm location / quantity. | Spec section 10 28 00 covers the wall guards (WG-1) under the hand dryers as indicated on the schedule. Door Hardware has protective plates included in section 2.10. and sets call out kick plates as applicable. | Mike Coleman | 21 | 2024-05-07 07:34 | 2024-05-08 07:50
20240514 | 20240514002 | 2 | window shades | section 12 24 00 specifies material types for window shades however none are listed or shown on drawings. confirm location / quantity of required window shades. | Window shades are listed on the Miscellaneous Schedule, manual window shades are in the offices. Contract roller shades by Lutron in lieu of Lutron Roller 20. Miscellaneous Schedule will be updated in the upcoming project addendum. | Mike Coleman | 22 | 2024-05-07 07:40 | 2024-05-08 07:50
20240514 | 20240514002 | 2 | Section 07 41 13 Metal Roof Panels | Section specs for holcim elevate UC-4 metal roof panel system. can we propose the UC-3 system in lieu of UC-4 system thank you | A UC-3 roof panel system will not be accepted in lieu of UC-4 roof panel system. | Mike Coleman | 15 | 2024-05-01 08:48 | 2024-05-07 07:01
20240514 | 20240514002 | 2 | Xcel X-former pad - Clarifaction who provided and installs? | See - Electrical Service, Sparta Rest Area, Item SPV.0060.19 C Construction states that the utility provides and installs the transformer pad. See - Electrical Plan Sheet E2-00, Note 46 calls for the contractor to provide concrete mounting pad per utility requirements? Please clarify who furnishes and installs the concrete pad for the Xcel Utility transformer? | Transformer pad will be provided and installed by utility. Contractor will be responsible for grading and gravel preparation for pad. Keynote #46 will be removed from sheet E2-00. Update will be included with an upcoming addendum. | Mike Coleman | 10 | 2024-04-22 11:37 | 2024-04-29 07:04
20240514 | 20240514002 | 2 | Rammed Aggregate piers | Soils report calls for two foundation options; #1 Excavate unsuitable soils or #2 Rammed Aggregate piers. However on the sheet notes of S1-11 page 126 it states all foundations are to be supported by rammed aggregate piers. please confirm that option#1 per the soils report listing foundation over excavation as acceptable. | Both options were assessed by the design team. The contractor should bid rammed aggregate piers, as called out in drawings. | Mike Coleman | 20 | 2024-05-07 07:31 | 2024-05-08 07:49
20240514 | 20240514002 | 2 | Door Hardware - Cylinders and Keying | Spec item 087100.10-2.4A.1a states to match existing cylinders, field verify. Can you please provide clarification on what cylinders would be acceptable. thank you | The door hardware spec sections have been revised and replaced. These will be included in the upcoming project addendum. | Mike Coleman | 17 | 2024-05-02 14:05 | 2024-05-09 07:23
20240514 | 20240514002 | 2 | Telephone conduit & Mounting Board | Spec Section 26 00 10 - Basic Electrical Requirements Line H states: Include a Telephone service conduit, where shown on the plans and plywood mounting board in the equipment room painted white. Telephone conduit - Please specify the size and the location of the conduit run? Mounting board - Please specify the size? | Please refer to sheet E2-11B for location and size for the telephone board (keynote #15). Refer to keynote #8 for conduit stub requirements for telephone/internet service. Telephone/internet service point and cabling by others. | Mike Coleman | 9 | 2024-04-19 16:32 | 2024-04-29 07:05
20240514 | 20240514002 | 2 | Xcel Electrical service Charges | Spec section 26 00 10 Basic Electrical requirements line 1.3 E. sates that the electrical contractor shall include all utility company charges in the bid. Electrical service, Sparta Rest Area, Item SPV.0060.19 B Materials states: The electric utility company (Xcel Energy) charges will be paid for separately by the department. Please clarify if Xcel Energy Charges need to be included in the bid? | All costs for the extension of the new service will be paid for by the department. The contractor will be responsible for any costs associated with temporary electricity during construction. | Mike Coleman | 8 | 2024-04-19 16:22 | 2024-04-24 07:39
20240514 | 20240514002 | 2 | Electrical Service, Sparta Rest Area, Item SPV.0060.19 | Special SPV,0060.19 calls for the EC to provide two 5-inch conduits from the transformer location to the CT cabinet. This note conflicts with the electrical riser diagram E4-11 shown on page 201. The plan note on riser calls for the installation of (2) parallel runs of 4-500 MCM (AL) in 3" conduits between the Xcel pad mount X-former and the wall mounted CTY cabinet on the exterior of the rest area building. Please clarify the the conduit and conductor requirements between the Xcel pad mount transformer and the building mounted Ct cabinet on the exterior wall of the rest are4a building? | The riser diagram on sheet E4-11 will be updated to reference special SPV.0060.19 for conduit and wire requirements. This will be updated with an upcoming addendum. | Mike Coleman | 7 | 2024-04-19 16:07 | 2024-04-29 07:06
20240514 | 20240514002 | 2 | HVAC Controls | The specs indicate TAC Andover is the only acceptable controls system manufacturer. A bidding mechanical contractor has informed us that this manufacturer is no longer in business as it was bought out by Schneider Electric. Can you please provide a list of other approved manufacturers? thank you | Other acceptable manufacturers for DDC equipment would be as follows: 1. Delta Controls. 2. Honeywell International, Inc. 3. Johnson Controls, Inc. 4. Schneider Electric. 5. Siemens AG, Building Technologies Division. These be included in the upcoming project addendum. | Mike Coleman | 25 | 2024-05-08 12:10 | 2024-05-09 07:23
20240514 | 20240514002 | 2 | Electrical Service Meter | There is a qty for Electrical service meter breaker pedestal location 01 but it does appear to me that they plan to feed it out of the Building MDP Service. Site electrical and Interior building are conflicting. | That item will be removed and associated updates will be included with an upcoming addendum. | Mike Coleman | 6 | 2024-04-19 11:44 | 2024-04-24 07:39
20240514 | 20240514002 | 2 | LP Fuel System | What bid item is the LP fuel system supposed to be included in? There doesn&#39;t appear to be a bid item for this. | The LP system cost is included in the item SPV.0060.14, Rest Area Building Electrical, noted under section 33 50 00. | Mike Coleman | 32 | 2024-05-13 14:17 | 2024-05-14 09:00
20240514 | 20240514002 | 2 | Communications, Camera and Security cabling / wiring to Maintenance Shed | Will communication, camera and security cabling be required between the rest area building and the maintenance shed? | We need (1) 2 inch conduit from the main building to the maintenance shed. This will be addressed in upcoming Addendum 02. | Mike Coleman | 14 | 2024-04-30 08:47 | 2024-05-07 06:36
20240514 | 20240514005 | 5 | SOI | The schedule of items does not match the plan quantities. Please update | We are looking into the situation. an addendum will be issued to correct any discrepancies. | Mike Coleman | 1 | 2024-04-29 11:51 | 2024-04-30 09:20
20240514 | 20240514007 | 7 | Base Aggregate | Can the existing base aggregate be recycled? If it is used for base aggregate will the Department pay for borrow to replace the recycled existing base fill volume? | No, Standard Spec 301.2.4.2 Aggregate Classifications; provide aggregate conforming to one of the following classifications based on weight percentages. So according to this the existing base aggregate would have to be reprocessed or blended prior to being reused. | Mike Coleman | 4 | 2024-05-07 10:00 | 2024-05-09 07:25
20240514 | 20240514007 | 7 | Question 4. | If the existing base and asphalt pavement is reprocessed and reused on the project as aggregate base, will the department pay to replace this volume with borrow? | No, the department will not pay for borrow to replace the volume of the existing base aggregate and asphalt pavement according to the following: According to Standard Spec 104.8 Rights in the Use of Materials Found on the Project (1) â€œThe department will not charge the contractor for the materials found within the above described excavation limits and so used. Replace, at no expense to the department, with other acceptable material all of the excavation materials so removed and used for embankments, backfills, approaches, or otherwise.â€ According to CMM Section 231.3 Materials Found Outside Excavation Limits: The contractor may request that the engineer allow them to test that material. If no concerns with using this material are found and/or addressed the project engineer will document a Contract Modification Justification and change order for an adjustment in the unit price of the item of work. | Mike Coleman | 6 | 2024-05-11 16:26 | 2024-05-13 09:11
20240514 | 20240514007 | 7 | Removing Asphalt Surface | There is a bid item for Removing Asphalt Surface with at quantity of 3,250 SY&#39;s. The areas called out are 500 lf in the NB/SB direction and 550 lf in the EB/WB direction. Per Standard Specifications&#58; Under the Removing Asphaltic Surface bid item, remove all types of asphaltic pavement or surfacing not supported on rigid bases or not underlain by proposed excavation. Also, remove asphaltic overlays of existing concrete pavements, bases, or bridge decks designated to remain in place. What is the reason for this work/bid item? | According to Standard Spec 205.3.2(5) â€œCompletely remove pavement, asphaltic surface, and rigid base from within the roadbed slopes and underlying proposed embankments to a depth of 2 feet or more below the finished grade line, or to the depth the plans shows.â€ This bid item and quantity is for the removal of the existing roadway asphaltic surface that is below the bottom of proposed subgrade and will not be removed and paid for by common excavation. | Mike Coleman | 5 | 2024-05-07 13:35 | 2024-05-09 07:22
20240514 | 20240514007 | 7 | Temporary Culvert | What size and length will the temporary culvert need to be for line # 270 Special 04 | According to the Special Provision Temporary Water Diversion, C-51-89, Item SPV.0060.04 a temporary culvert is one of three methods allowed for a temporary water diversion of the East Branch Dover Ditch. Details of the contractorâ€™s method selected, including the length and size of a temporary culvert if that method is selected, shall be detailed in the contractorâ€™s ECIP for approval by the engineer using a Q2 = 46 cfs as stated in the special provision. | Mike Coleman | 1 | 2024-04-23 15:07 | 2024-04-24 08:38
20240514 | 20240514007 | 7 | Can the Soils Report be provided? |  | Only geotechnical work for the project was for structure C-51-0039. The geotechnical report can be found at the following location: https://wisdot.box.com/s/nxyyl8nyiz5bg1jw9cid3bcgnzb99ycl or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-05-07 09:58 | 2024-05-09 07:21
20240514 | 20240514007 | 7 | Can the Design Schedule be provided? |  | The design schedule can be found at the following location: https://wisdot.box.com/s/nxyyl8nyiz5bg1jw9cid3bcgnzb99ycl or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2024-05-07 09:58 | 2024-05-09 07:20
20240514 | 20240514011 | 11 | Pre-Boring | 550.0020 Pre-Boring Rock or Consolidated Materials 550.4 Measurement - Pre-Boring is paid by the LF measured from the footing base to the depth the plans show, or engineer directs. Why is this proposal only paying for the 3 FT cored into rock? 3&#39; x 12 bore hole = plan quantity 36 LF We feel Plan Quantity should probably be closer to 180 LF. | This item was reviewed and additional quantity is anticipated. The anticipated total quantity is 145 LF. An addendum is being drafted. | Mike Coleman | 4 | 2024-05-09 09:37 | 2024-05-09 14:06
20240514 | 20240514011 | 11 | Temporary Structure | Is 1 1/4 inch base agg dense an allowable driving surface on the deck of the temp structure? | It may be allowable if the temporary structure ensured the aggregate would not enter the waterway. This would need to be approved through the temporary structure approval process as stated within the standard specifications. | Mike Coleman | 3 | 2024-05-03 11:25 | 2024-05-06 08:25
20240514 | 20240514011 | 11 | Temporary Structure | Is base agg dense an allowable driving surface on the deck of the temp structure? |  |  | 1 | 2024-04-23 10:48
20240514 | 20240514011 | 11 | Temp Bridge | Plan documents show a temporary bridge length of 30&#39; based on the temporary abutment stationing. However, current site conditions indicate that a temporary bridge would have to be significantly longer to clear the river. Can the Department please confirm the required temporary bridge length at the location indicated in the plans? | The anticipated 30 foot temporary structure was sized from topographic survey and hydraulic need. The structure is not anticipated to be from top of bank to top of bank, but placed within the sloped banks to minimize length with aggregate being installed behind the abutment up to the proposed grade. | Mike Coleman | 5 | 2024-05-09 10:08 | 2024-05-09 11:54
20240514 | 20240514011 | 11 | Qty's for 12" CMP | Stations 1+26 and 2+38 show 24&#39; lengths in the plans. Sheet 21 shows them as 12&#39; and 66&#39; on the culvert table? What lengths are correct? | The miscellaneous quantities on Page 21 are correct. The plan and profile sheet page 25 will be updated to match the MQs on addendum 1. | Mike Coleman | 2 | 2024-04-30 09:43 | 2024-05-01 10:27
20240514 | 20240514011 | 11 | Temporary Structure | What is the minimum roadway clear width as measured between the inside faces of the concrete barriers at right angles to the centerline? | The clear width between barriers shall be 14 LF. | Mike Coleman | 6 | 2024-05-09 12:46 | 2024-05-09 14:06
20240514 | 20240514012 | 12 | Pedestrian Railing on B-64-205 | Are the original drawings available for the existing Pedestrian Railing on B-64-205 that is to be removed and reset? | Drawings for the existing railings are not on record and are therefore unavailable. | Mike Coleman | 1 | 2024-04-24 14:26 | 2024-04-29 10:13
20240514 | 20240514012 | 12 | Quantities: Concrete Masonry Bridges and Architectural Surface Treatment | The plan quantities for Concrete Masonry Bridges and Architectural Surface Treatment on B-67-205 &amp; B-67-248 appear to be significantly off. Can the plan quantities for these items be verified and/or will these items be paid at plan quantity? | Plan quantities have been verified. There are no significant differences, with variation only a result of standard rounding within 1% or less of computed values. Items will be paid at the item unit price. | Mike Coleman | 2 | 2024-04-29 09:10 | 2024-05-06 07:31
20240514 | 20240514012 | 12 | Schedule Duration | The specifications require that the cofferdams remain in place until the staining is complete for the architectural surface treatment on the bridge wings. Considering a 28 day cure period requirement on concrete for the application of any stain along with the staging on the project, the time required to complete the work does not fit within the contract time allotted. Can the department clarify if time will be suspended for concrete curing when the curing becomes the critical path activity on the schedule and no other work can occur? | Stage 1A and 1B are intended to permit wingwall repairs at all quadrants early in construction in consideration of cure time and staining. Work is anticipated to proceed to Stage 1 for superstructure repairs on EB and to Stage 2 for superstructure repairs on WB inside while concrete cures with no time suspension. Full cure is anticipated to be reached early in Stage 2, at which point the contractor may return to a Stage 1A traffic configuration on EB to complete wings 1 and 4 if necessary. When Stage 3 is reached for WB outside work, wings 2 and 3 will be fully cured and may be stained and cofferdams removed. Note a 1A configuration cannot be used concurrently with Stage 3 due to pedestrian connectivity. | Mike Coleman | 3 | 2024-04-29 09:32 | 2024-04-30 10:56
20240514 | 20240514013 | 13 | Span Drive Machinery Refurbishment | 1) Speed reducers are defined in general terms, but specifics such as input speed, horsepower, reduction ratio, double/triple reduction, and output torque are not defined. These items are critical to a gearbox manufacturer when it comes to building a gearbox for quoting accurately. - Page 118 of 228 in the specs, para. C.6.3.1 states &acirc;&#128;&#156;Provide gear boxes with the ratings shown on the Plans.&acirc;&#128;&#157; Plans do not provide ratings. Please provide. 2) Machinery and motor brakes &acirc;&#128;&#147; only detail provided is 19&acirc;&#128;&#157; diameter brake wheel&#58; need to know required torque capacity - Page 123 of 228, para. C6.4.1 states &acirc;&#128;&#156;If no torque is shown in the Plans, the brake shall produce a torque equal to or up to 10 percent greater than the maximum torque of the existing brake. Where required in the Plans, brakes shall be AISE rated. Thruster and drum sizes are to be rated for the torque requirements specified in the Plans and components shall meet the following&#58;&acirc;&#128;&brvbar;&acirc;&#128;&#157; Plans do not provide this information. Please provide | 1) Primary Reducers shall be: Quadruple reduction differential, input speed to be 1170 rpm, Input 80HP Total, Reduction 288:1, Output Shaft Torque Rating of 105 ft*kips, 2) See question 22: Motor Brakes: 8" Diameter Wheel, Max Torque Rating 155 ft*lbs., Factory Set Torque Rating 110 ft*lbs. Machinery Brakes: 10" Wheel, Max Torque Rating 220 ft*lbs. or 260 ft*lbs depending on thruster used; verify with manufacturer , Factory Set Torque Rating 150 ft*lbs | Mike Coleman | 17 | 2024-05-03 13:45 | 2024-05-07 06:58
20240514 | 20240514013 | 13 | Submarine Cables | 15. Regarding the Submarine Cable specification paragraph C.1, which references table 4-7 for Sheath thicknesses, could the owner kindly verify if those thicknesses align with the details specified in the drawing labeled E39? 16. The Submarine Cable specification calls for flame-resistant binder tape over conductors. Considering the cable will be submerged, I&#39;d like to confirm whether it&#39;s necessary for the binder tape to be made of a flame-resistant material. | 15. All submarine cables layout have been coordinated with the cable manufacturer for compliance to specification section SPV.0060.016. 16. Corrugated binder tape is typically provided by submarine cable manufacturers with flame resistance & moisture resistance features to cover all applications. The use of a non-resistance can be considered at the time of shop drawing review. | Mike Coleman | 3 | 2024-05-01 07:37 | 2024-05-06 07:33
20240514 | 20240514013 | 13 | Span Drive Motors | 17. The specifications call out AC motors/drives while sheet E2 of E83 calls out DC motors. Confirm that these are AC motors. What RPM are the motors to be? The specs are not clear on this. | AC motors are required. They shall be 1200rpm (1170rpm synchronous speed). | Mike Coleman | 4 | 2024-05-01 07:41 | 2024-05-06 07:36
20240514 | 20240514013 | 13 | Laptop Software | 18. What software do the laptop needs to have? Spec page 175/375 | Two laptops to be provided. See response to Question #6. | Mike Coleman | 5 | 2024-05-01 07:42 | 2024-05-06 07:38
20240514 | 20240514013 | 13 | Remote Control Systems | 19. Please clarify the intent on the remote control system. Are we making any programming changes at Wells Street or only in the remote desk at Knapp? a. For the Knapp Street remote console, what is the intent with 2 PLC&acirc;&#128;&#153;s in the rack. In a ControlLogix system, only one PLC can control an IO card. If we have the console IO controlled from one PLC, what is the purpose of the 2nd? b. Will the HMI in the remote control desk at Knapp be replaced? We believe the current Panelview is communicating DH+ to the SLC-500 PLC that is there and the new PLC would communicate via Ethernet. We recommend the Panelview Replacement in this project. Please confirm. | 19. The specifications require two laptops. 1. One dedicated to Cherry St. which will be used by the contractor to help program the PLC, and configure the CCTV system. Hence the contractor is to install a copy of the PLC program and CCTV system. Please see sheet E51. 2. The second laptop is to be used to interface with the existing CCTV system at Knapp St. Hence, this Laptop is to house the CCTV program needed to cofigure the system. Refer to sheet E52. 19.a. Sheet E56, the existing remote console back plate is shown for "Existing" and "Modified". The existing PLC is to be removed and the modified shows the new PLC. 19.b. Per Panel View manufacturers data, "The PanelView terminal is initially set to DHCP with BootP support (Dynamic Host Configuration Protocol) enabled. If your network has a DHCP/BootP server, you can connect the PanelView terminal to the EtherNet/IP network and the DHCP/BootP server will automatically establish an IP address." Please refer to Rockwell Automation Publication 2711-IN036J-EN-P - November 2009. | Mike Coleman | 6 | 2024-05-01 07:45 | 2024-05-06 07:35
20240514 | 20240514013 | 13 | Center Lock Assembly | Center lock assembly actuator on sheet M11 note 5 calls out a ball screw. Can an Acme screw be used instead? These are most commonly used on bridges, less susceptible to failure due to contamination, less expensive, etc. | ACME screw is acceptable. | Mike Coleman | 18 | 2024-05-03 13:46 | 2024-05-07 06:58
20240514 | 20240514013 | 13 | Span Drive Motors | Does this bridge require a &acirc;&#128;&#156;snow and Ice&acirc;&#128;&#157; mode like other bridges in the area? It is not present here. | For times that ice and snow load require both motors at the same time. The motor drive selector switch shall be set to "Both". | Mike Coleman | 9 | 2024-05-01 07:47 | 2024-05-06 07:39
20240514 | 20240514013 | 13 | Cherry Street Control System | In the Cherry Street Control system, what is the reason for DeviceNet communication? Can these racks be connected via Ethernet? The hot-standby ControlLogix PLC&acirc;&#128;&#153;s should synchronized via a 1756-RM2 module and fiber cable. These are not shown in the plans. Please confirm this direction | The contractor can propose an Ethernet based communication between I/O racks and PLC during the submittal process. | Mike Coleman | 7 | 2024-05-01 07:46 | 2024-05-06 07:38
20240514 | 20240514013 | 13 | S3 & S4 Shaft Drilling | Long shafts cannot be gun drilled with center hole. Please confirm S3 and S4 shafts without 20% holes will be acceptable. | S3 & S4 shafts will need to be drilled. | Mike Coleman | 12 | 2024-05-01 11:16 | 2024-05-07 06:42
20240514 | 20240514013 | 13 | Machinery Weldment Anchors | Machinery weldment details on sheets M7, M8 and M9 do not specify anchor hole diameters or anchor bolt details. How are the weldments attached to the machinery floor (anchor type, size, embedment)? | Machinery Support Weldments shall be secured to machinery room floor with 1-1/2" dia. SS Adhesive Anchors, Embedded to 11.5" min. depth. Anchors shall comply with WisDOT St. Sp. 502.4112. | Mike Coleman | 25 | 2024-05-08 12:33 | 2024-05-13 06:36
20240514 | 20240514013 | 13 | Buy America | Please clarify exactly which components do not have to meet Buy America. Partial list of items to consider&#58; Reducers, Machinery &amp; Motor brakes, Couplings, bearings, motors, encoders. Many of these items are only manufactured outside of the United States or come at a significantly higher price to meet BUY America standard. | All components identified in Question #11 for proposal 20240514013 (Reducers, Machinery &amp; Motor brakes, Couplings, bearings, motors, encoders) must adhere to WisDOT's Buy America provision. Perspective bidders are responsible to review and understand CMM 228.5 to become familiar with Buy America requirements, and must account for any BA requirements when selecting materials for inclusion in their bids. | Mike Coleman | 11 | 2024-05-01 11:14 | 2024-05-07 06:38
20240514 | 20240514013 | 13 | Bridge Machinery B.9 | Please clarify paragraph B.9, on page 20 of 228, where it states that machinery base supports and brackets are to be galvanized AND painted&#58; &acirc;&#128;&#156;Hot-dip galvanize and paint with the approved two-coat paint system all machinery supports and brackets after fabrication.&acirc;&#128;&#157; | Supports shall be Hot-dipped galvanize and paint per specification. | Mike Coleman | 21 | 2024-05-03 14:07 | 2024-05-07 07:00
20240514 | 20240514013 | 13 | Motor and Machinery Brakes | Please define the brake sizes (diameter), maximum torque rating and factory set torque ratings. | Motor Brakes: 8" Diameter Wheel, Max Torque Rating 155 ft*lbs, Factory Set Torque Rating 110 ft*lbs Machinery Brakes: 10" Wheel, Max Torque Rating 220 ft*lbs or 260 ft*lbs depending on thruster used; verify with manufacturer , Factory Set Torque Rating 150 ft*lbs | Mike Coleman | 22 | 2024-05-06 07:29 | 2024-05-06 07:40
20240514 | 20240514013 | 13 | Manpower Pl Exclusion Zone | Please provide additional clarification on the barge exclusion zone in the Northwest quadrant at Manpower Pl. Horizontal limits and what can and cannot be done in the area would be helpful. At a minimum we are requesting barges be allowed in this area without spudding. | The response will be that they can park a barge within the area without spudding or river bed disturbance. | Mike Coleman | 15 | 2024-05-02 14:20 | 2024-05-06 13:38
20240514 | 20240514013 | 13 | Design Schedule | Please provide the design schedule for the project. | The design schedule can be found at the following location: https://wisdot.box.com/s/4buywrke2isy6mwx3x6ao9wkol12jk3i or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-04-15 12:45 | 2024-04-17 06:42
20240514 | 20240514013 | 13 | Grid Deck | Please see Sheet S09 of S71 of the Contract Plans, also noted as Sheet 65. &acirc;&#128;&cent; Typical Connection Plate Detail on the left side of the page shows a 6&acirc;&#128;&#157; x 3/8&acirc;&#128;&#157; bolt down plate fitted between the steel grid main bars. This is carried through on Section A-A, B-B, C-C and D-D above. Also note Typical Interior Panel Joint on the right hand side of the page that shows a 3/8&acirc;&#128;&#157; x 7&acirc;&#128;&#157; bolt down plate that runs continuous below the grid. Note that this will elevate the grid by the thickness of the bolt down plate. The project should choose one of these details and eliminate the other. We suggest the continuous plate detail. &acirc;&#128;&cent; Note the pipe sleeve shown on the Plan Pipe Sleeve &amp; Bolt Down Plate detail. This is not shown on the Typical Connection Plate Detail shown on the left. Pipe sleeves are expensive and may only offer marginal assistance with installation. Consider removing the pipe sleeves from the plans. &acirc;&#128;&cent; Typical Interior Panel Joint detail shows a 2 &frac12;&acirc;&#128;&#157; x &frac14;&acirc;&#128;&#157; cross bar. The specifications call out a 2&acirc;&#128;&#157; x &frac14;&acirc;&#128;&#157; cross bar. We suggest the 2 &frac12;&acirc;&#128;&#157; cross bar. &acirc;&#128;&cent; Half-Filled Steel Grid at Transverse Splice shows a bolted connection between panels. Typical Interior Panel Joint shows side trim on both panels and an open gap. We recommend the bolted connection. Please see Sheet S08 of S71 of the Contract Plans, also noted as Sheet 64. &acirc;&#128;&cent; The drawings indicate a 4way type grid. Note 1 calls out &acirc;&#128;&#156;Welded 5-inch 4-way w diagonal elements.&acirc;&#128;&#157; The project specifications indicate 5&acirc;&#128;&#157;RB6.2 with &acirc;&#128;&#156;ribless&acirc;&#128;&#157; main bars. We suggest the diagonal type floor. &acirc;&#128;&cent; Note 1 calls out the minimum section properties for the steel grid bridge decking. Grid Deck properties (with 50% of Diagonal bars &acirc;&#128;&#147; no mention of supps). From sheet 64&#58; Stop = 4.65in3/ft Sbot = 4.64in3&acirc;&#128;&#153;ft 5&acirc;&#128;&#157;-4 way offers&#58; Stop = 3.63 Sbot = 4.21 5&acirc;&#128;&#157;RB6.2 offers&#58; Stop = 3.89 Sbot = 5.12 We suggest the plans be revised to reflect the 5&acirc;&#128;&#157;-4 Way Properties Stop = 3.63 Sbot = 4.21 The specifications call out .2% copper bearing steel for the grid flooring. Our current material supply may not allow that, and we would like to have this requirement removed. | Sheet S09 of S71: 1. Provide 6" x 3/8" bolt down plate as shown on Typical Connection Plate Detail and Sections A-A thru D-D. 3/8" x 7" plate is inadvertently shown on the Typical Interior Panel Joint Detail. Use 6" x 3/8" plate for Typical Interior Panel Joint as shown on the Typical Connection Plate Detail. 2. Pipe sleeve detail is provided for the ease of installation and removal of deck grating system. If Contractor choses to eliminate the pipe sleeve and/or provide a better detail, then it could be included with the shop drawings for Department's review and approval. Acceptance of such detail shall be at the discretion of the Department. 3. Provide 2 1/2 " x 1/4" cross bar as shown on the Typical Interior Panel Detail on Sheet S09 (Sheet 65). 2" x 1/4" cross bar is inadvertently called out on the specifications. 4. Alternate joint detail could be included with the shop drawings for the Department's review and approval. Acceptance of such detail shall be at the discretion of the Department. Sheet S08 of S71 1. Provide Welded 5-inch 4-way w/ diagonal elements as per Note 1 on Sheet S08 (Sheet 64) with main bars spaced at 7.5" as shown on Sheet S09 (Sheet 65). 6" main bar spacing is inadvertently called out on the specification instead of 7.5" spacing. 2. Any request to change the section modulus shown on plans shall be submitted with shop drawings for Department's review and approval. Acceptance of such detail shall be at the discretion of the Department. 3. Material shall meet the requirements of the Special Provision. Any request to use an alternate material shall be submitted to the Department for review and approval. Acceptance of such request shall be at the discretion of the Department. | Mike Coleman | 26 | 2024-05-09 06:50 | 2024-05-13 06:35
20240514 | 20240514013 | 13 | Bearing Refurbishment | Rehab of bearings involves installation of new bushings. Diameters are not provided. Please provide. | Bore Diameters provided on Drawing M5. Further, Contractor shall measure shafts individually to verify existing shaft diameters. | Mike Coleman | 19 | 2024-05-03 13:58 | 2024-05-07 06:59
20240514 | 20240514013 | 13 | Traffic Gates | Sheet E40 shows illustrations of two different gate operators (the ones marked &quot;1A &amp; 1B&quot; correlate to FedTransit Type ST-70/B&amp;B VW-7 whereas the one marked &quot;2&quot; corresponds to FedTransit Type ST-40/B&amp;B VW-4&quot;. The specifications (SPV.0060.031) match the ST-40/VW-4 operator, please confirm this is what is required. | Gate operator shall be as per SPV.0060.31. | Mike Coleman | 24 | 2024-05-07 08:11 | 2024-05-08 07:52
20240514 | 20240514013 | 13 | Span Drive machinery Refurbishment | SPV57.C.6.1 - - Tooth Contact. If existing bushings and/or gears are worn this spec may not be achievable without hand grinding. Any grinding would affect backlash in the system. Would this be considered extra work? - Backlash - Backlash is not adjustable between B3 and B5 and therefore P2/G2 will have to remain as it is currently which may or may not meet AGMA tolerances. How would backlash that is out of tolerance be handled? | All bearing bushings are being replaced. Contractor shall take note of existing Tooth Contact and Backlash. After replacing bearing bushings all care shall be taken to get tooth contact and backlash back to existing conditions, if not better. Grinding will be permissible, but only to a very minor extent. Removal of more than a few thousands of an inch per tooth shall require the approval of the Engineer. | Mike Coleman | 14 | 2024-05-01 11:40 | 2024-05-07 06:56
20240514 | 20240514013 | 13 | Reducer Specs | We can not find the specifications for the new gear box , we need the ratio , service factor , torque , etc. The specifications refer to the plans, but we can not find the information in the plans. | Primary Reducers shall be: Quadruple reduction differential, input speed to be 1170 rpm, Input 80HP Total, Reduction 288:1, Output Shaft Torque Rating of 105 ft*kips | Mike Coleman | 10 | 2024-05-01 10:47 | 2024-05-07 06:37
20240514 | 20240514013 | 13 | Span Drive and Motors | What are the horsepower requirements for these motors? | 40HP at 1170 RPM Synchronous Speed | Mike Coleman | 16 | 2024-05-03 13:37 | 2024-05-07 06:57
20240514 | 20240514013 | 13 | Shaft Diameters | What are the shaft diameters of shafts S3, S4 and S5? | Shafts to be 8" diameter. | Mike Coleman | 20 | 2024-05-03 13:59 | 2024-05-07 06:59
20240514 | 20240514013 | 13 | Span Drive Motor Operation | What is the intent with running both motors on leaf? Each 40Hp motor should be able to generate the torque needed independently. Drawings do not show wiring for Master/Slave configuration, but there is a switch on the desk for selecting both motors. | Each motor can run the bridge on its own, except for Condition C (Ice and Wind). During those times both motors lift the bridge. Under Condition A, the motors alternate between each one another. | Mike Coleman | 8 | 2024-05-01 07:46 | 2024-05-06 07:40
20240514 | 20240514013 | 13 | Droop Cable System | While reviewing the drawings it appears that there are no droop cables called out in the conduit schedule or in the details. May we get clarification and specifications on droop cable system installation for transitioning from the fixed structure to the moveable span? | A portion of cables 22PF, 26CF, 22PN, 30PN, 26CN, 36CN, 37CN, and 38CN as called for in the conduit schedule will need to run thru droop cables. | Mike Coleman | 23 | 2024-05-06 14:14 | 2024-05-08 07:52
20240514 | 20240514013 | 13 | Guard Material Spec. | Will 316 stainless be acceptable for all new manufactured guards? | Yes, 316 Stainless Steel is acceptable. | Mike Coleman | 13 | 2024-05-01 11:17 | 2024-05-07 06:55
20240514 | 20240514013 | 13 | Bridge House Site Walk | Will the State allow for a pre-bid bridge house site walk? The logistics for the work detailed inside of the bridge houses including the safe removal and replacement of the drive machinery components cannot be completely and comprehensively planned without first seeing the bridge houses in person. Please advise on when a site walk can be scheduled. | Contractors can call Karen Forlenza at 414-708-6552 to arrange a site visit. | Mike Coleman | 2 | 2024-04-15 12:53 | 2024-05-07 07:42
20240514 | 20240514014 | 14 | Cofferdam | Under the Removing Structure Minimal Debris item in the special provisions, it is stated that &quot;Removal of the existing structure shall be performed in stages under dry conditions using sandbags or other non-erodible materials to divert water away from the removal area&quot;. What is the intention of this statement? Turbidity barrier is shown for protection of the substructure units, and pouring concrete underwater is also stated to be allowable. Is the department requesting a cofferdam that would allow for &quot;dry conditions&quot; during removals? If so, a cofferdam bid item should be added to the contract. If not, please explain the intent of the verbiage in section 13 of the special provisions. |  |  | 1 | 2024-04-30 16:26
20240514 | 20240514016 | 16 | Salt Storage Building Questions | 1. Plan view of the salt storage building shows a 12' high divider wall behind the man door. With the angle of repose of salt, location of the doors and height of the partition wall, this detail will causes far more problems and cost than benefit. I have seen one or two other WisDOT projects bid with this detail, but it has always been eliminated after award. If the owner wants to keep salt away from the man door, they usually place a barrier block in this location after building construction is complete. The detail as provided is a concern for design, construction, and paving. 2. SPV.0060.01 G.1.e. Since this will be a salt storage building, 80 pcf is typically used for the salt load. 80 pcf would be consistent with every other WisDOT or County building constructed in the past. 100 pcf can be facilitated, but will add unnecessary cost. Suggest changing to 80 pcf if the building will be used for salt storage. | Question 1 response: 12-foot high divider wall behind the main wall is to remain as shown in the plans. Question 2 response: A unit weight of 80 pounds per cubic foot for the salt is acceptable for the design load. An addendum to the special provisions will be provided. | Mike Coleman | 1 | 2024-04-12 13:29 | 2024-04-16 07:10
20240514 | 20240514016 | 16 | Completion | Approved manufactures for the salt shed materials are stating there will be a lead time of approximately 24 weeks from time of order. This would result in asphalt and concrete work being done in 2025 and could result in parts or all of the building being completed in 2025. Will the department allow for work to be completed in 2025? | Yes, work will be allowed to be completed in 2025. An addendum to the special provisions will be provided. | Mike Coleman | 6 | 2024-05-01 08:33 | 2024-05-06 07:23
20240514 | 20240514016 | 16 | Fox Valley & Lake Superior Railroad | Article 9 of the Special Provisions discusses Railroad Insurance and Coordination. It appears that the property line is 65 feet from the center of the tracks. Can the Department give further explanation to the need for this provision. | Railroad Insurance is needed per the exclusion in the Contractors General Liability Insurance that specifically excludes â€œONâ€ or â€within 50â€™â€ of RR ROW. Project is 15â€™ from the RR ROW assuming 50â€™ RR ROW from track. | Mike Coleman | 7 | 2024-05-06 14:44 | 2024-05-07 11:39
20240514 | 20240514016 | 16 | Construction Schedule | Can the Department provide their schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/gm9l11ydurha9dc4d0hpbxisfkf26wfv or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2024-04-24 12:01 | 2024-04-25 07:26
20240514 | 20240514016 | 16 | Soil Borings | Can you please provide soil borings? | The soils report can be found at the following location: https://wisdot.box.com/s/gm9l11ydurha9dc4d0hpbxisfkf26wfv or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-04-19 14:24 | 2024-04-22 10:33
20240514 | 20240514016 | 16 | Engineered Soils | Please remove the requirement of at least 97% Mineral SiO2 Sand and that substitutions such as calcium carbonated sand or dolomitic sand will not be allowed. SiO2 Sand is extremely difficult to source and is not industry standard. Industry standard typically uses a concrete / torpedo sand, which does have "SiO2 Sand" but not at the min. 97% requirement. When referencing WIDNR spec 1004 it also aligns with industry standard concerning sand requirements. | Substitutions for the use of Si02 , such as calcium carbonated sand or dolomitic sand may also be used. Manufactured sand or stone dust will not be allowed. An addendum to the special provisions will be provided. | Mike Coleman | 3 | 2024-04-22 10:01 | 2024-04-24 08:37
20240514 | 20240514016 | 16 | Engineered Soils #2 | Remove the requirement stating &quot;Provide sand consisting of mineral sand that is at least 97% SiO2&quot; in the special provision. The DNR spec you are referencing clearly states &quot;The preferred sand component consists mostly of SiO2&quot;. As stated in previous questions industry standard sand used for these mixes will NOT meet the 97% minimum requirement. | 97% SiO2 requirement has been removed and replaced with the preferred sand component should come from a naturally occurring pit or borrow source and consist primarily of (>50%) Si02. An addendum to the special provisions will be provided. | Mike Coleman | 5 | 2024-04-25 11:33 | 2024-04-29 08:19
20240514 | 20240514017 | 17 | Base Repair for CIR Layer | Can the department clarify when this item will be used? In the past this item was only used for yielding areas of milled surface prior to the CIR operation and would only require placing millings back. The last paragraph of section C in the special provisions for this item (15.) seems to imply that this item will be used once paving operations have begun? Will this item be used to fix yielding areas after the CIR process has been completed and if so will the department require asphalt surface to be placed? | The Base repair for CIR is to be used on the 310 CIR work, after the milling of the existing asphalt, and before CIR operations. The intent is to not use this item after CIR operations have been done. | Mike Coleman | 6 | 2024-05-06 08:52 | 2024-05-09 10:39
20240514 | 20240514017 | 17 | Project Construction Schedule | Can the department provide the design construction schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/umepjfvb7is0qx0ywedpyr46se6px37m or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-05-03 08:26 | 2024-05-07 11:41
20240514 | 20240514017 | 17 | 96 HR Milled Surface | Does the 96 HR milled surface requirement in the special provisions only apply to the 4 lane section under IH 43 and the roundabouts where the plan only calls for milling and asphalt paving? Other projects in the region have not had restrictions or have had longer time frames on CIR projects to allow the milling to get out ahead of the CIR operation. | The 96 hr Milled surface requirement does not apply to the sections of work done by CIR operation. | Mike Coleman | 4 | 2024-05-06 08:28 | 2024-05-08 09:57
20240514 | 20240514017 | 17 | 72 HR Even Cross Sectional Profile | In the special provisions it states for paved surfaces provide an even cross-sectional profile of the roadway within 72 hours of paving the adjacent lane. Will this be required if the contractor utilizes a notched wedge center line joint? | The 72 hr restriction will not be required if the contractor utilizes a notched wedge centerline joint. | Mike Coleman | 5 | 2024-05-06 08:31 | 2024-05-08 09:59
20240514 | 20240514017 | 17 | 4337-23-71 Typical Existing Sections | Is there a typical existing section for the station ranges 196+35-260+54, 274+51-306+11, 320+86-505+37? | Yes the cross sections were mistakenly left off plan an addendum will be coming with additional information. | Mike Coleman | 2 | 2024-05-03 08:43 | 2024-05-07 11:42
20240514 | 20240514017 | 17 | Pilot Car | The traffic section of the special provisions state the two-lane undivided sections of highway can be closed to 1 lane through the use of flagging operations and a pilot car. Will the pilot car only be required for the CIR operations as typical on past projects or will it be required for all flagging operations (i.e. Milling, Paving, Shouldering, Rumble Strips)? | The intent is to have the Pilot car for the CIR operations only, where the paving and milling operations are spread out over a long distance. Not required for normal other operations. | Mike Coleman | 3 | 2024-05-03 09:08 | 2024-05-07 11:44
20240514 | 20240514018 | 18 | 96-Hour Mill and Pave | Per page 16 of the plans, contractor is required to mill the roadway prior to Asphaltic Surface Patching and Concrete Base Pathing operations. Based on the work that needs to be completed (milling, Asphalt Patching &amp; Concrete Base Patching), contractor is requesting that the 96-hour rule be removed as this would not be constructable. | The Milled Surface restriction is not intended to be applied to areas with base patching. The Milled Surface restriction will not apply to closed roadways, an addendum will be issued to modify the Milled Surface restriction. | Mike Coleman | 1 | 2024-04-26 08:31 | 2024-04-29 09:45
20240514 | 20240514020 | 20 | Temporary Epoxy or Temporary Paint | Hello - the bid item for this project shows 643.3170 Temporary Marking Line Epoxy 6-Inch, but the Misc. Qty table on plan sheet 59 has this listed as Temporary Marking Line Paint 6-Inch. Please clarify if this item is Epoxy or Paint. Thanks | The MQ table is correct it should be paint for the temporary markings not epoxy. An addendum will be issued. | Mike Coleman | 1 | 2024-05-03 10:55 | 2024-05-06 13:23
20240514 | 20240514021 | 21 | Excavation and Subgrade Improvement 1.25 CABC | The area of subgrade improvement can not be dug out backfilled and paved with 7 inches in one day, will the contractor be paid for the 1.25 Inch Base material needed for the temporary base aggregate patch? Does the qty in the plan include enough material for the Base Aggregate patch that will be needed? |  |  | 1 | 2024-05-08 15:23
20240514 | 20240514022 | 22 | US 10 Traffic Management | How does the Department plan to handle the traffic exiting on and off at the US 10 Interchange? The plans or specifications do not make any reference as to how this traffic will be handled. | All traffic on the US 10 interchange ramps needs to be maintained at all times. No adjustments to any of the signal timings are anticipated. | Mike Coleman | 2 | 2024-05-09 12:33 | 2024-05-10 06:22
20240514 | 20240514022 | 22 | Milling & Repaving | Would the department allow the Contractor to mill and repave mainline 12&acirc;&#128;&#153; and 3&acirc;&#128;&#153; shoulder at a 2% cross slope in lieu of the 4% (3&acirc;&#128;&#153; shoulder) as outlined in the plan cross sections? | WisDOT expects the roadway & shoulders to be milled/paved at the slopes shown on the plan cross sections. | Mike Coleman | 1 | 2024-05-09 12:32 | 2024-05-10 06:22
20240514 | 20240514024 | 24 | Geotechnical report | Are there soil borings for this job that can be passed onto the contractor? | No soil borings were collected for the project. | Mike Coleman | 2 | 2024-05-03 10:14 | 2024-05-06 13:29
20240514 | 20240514024 | 24 | Doweled Pavement | Is the pavement on this contract intended to be doweled. There is no indication on the typical sections and do doweled concrete pavement SDD included in the plan. | â€¢ All existing and proposed concrete pavement is doweled. | Mike Coleman | 3 | 2024-05-10 14:45 | 2024-05-13 08:27
20240514 | 20240514024 | 24 | Waste in ROW | There is a lot of ROW to work with at this intersection, possibly in preparation for a future interchange. Can the contractor waste the material in the ROW, which would stockpile the material for future construction and savings? | Please review and follow 205.3.12 of the standard specifications. | Mike Coleman | 1 | 2024-04-18 11:18 | 2024-04-22 08:30
20240514 | 20240514025 | 25 | Traffic allowed on Milled surfaces | Will traffic be allowed on milled surfaces after existing polymer overlay is removed if temporary lines are installed. | Yes, traffic will be allowed to drive on milled surface. The project was designed with that consideration. | Mike Coleman | 1 | 2024-05-09 11:25 | 2024-05-13 08:34
20240514 | 20240514026 | 26 | Adjusting Cable Barrier | Can the Department clarify if any cable barrier terminal ends are being replaced according to this SPV bid item? | If any of the required supporting documents in the Adjusting Cable Barrier Type 1 bid item require replacing the cable barrier terminal ends, then replacing the cable barrier terminal ends is incidental to the Adjusting Cable Barrier Type 1 bid item. | Mike Coleman | 1 | 2024-04-26 14:51 | 2024-04-29 09:45
20240514 | 20240514026 | 26 | Beam Guard | Can the department look at adding a salvage rail or adjusting rail item to the project. Essentially all of the grading work for the job is underneath and behind all of the rail being replaced. All this work will need to take place before paving starts and the rail must come out for grading operations and get put back in. It never works out to put up new rail before paving has been done and hit the tolerance for height for new rail on pavement. It all will need to get adjusted after the fact or we could salvage and put back the existing and put in the new after paving, with the salvage rail special provision item that&#39;s been used in these applications before. Thank you | We anticipate that there is enough information in the plans to determine the correct height of the guardrail. Please bid the project per the plan and special provisions. Note in the finished typical sections that the IH 39 NB and SB 10-foot outside paved shoulder is not being milled and overlaid with this project. The prosecution and progress article requires guardrail to be installed within 10 calendar days of removal of existing guardrail. | Mike Coleman | 3 | 2024-04-29 18:18 | 2024-05-06 07:30
20240514 | 20240514026 | 26 | Storm sewer work at STA 1291 - 1292 SB | Is it the department&#39;s intention to get the removals, storm sewer tie-in, and new storm sewer installation completed during night work? Will this need to be paved back in nightly, so it is open by 6&#58;00 am? Am I reading the lane closures correctly (form STA 1270 to end of project 1508+90)&#58; the SB lane can be closed at 6&#58;00 p.m. but the ramp at USH 10/66 West can&#39;t be closed until 8&#58;00 pm for night work? | A portion of the IH 39 SB parallel off ramp to USH 10 EB/STH 66 WB could be closed reducing the parallel ramp length adjacent to IH 39 SB while keeping the ramp open to traffic to complete the storm sewer and guardrail work at this location. If an IH 39 SB lane or ramp closure is needed, the lane and ramp closure will follow the restrictions in the Prosecution and Progress article of the special provisions. | Mike Coleman | 4 | 2024-05-03 17:16 | 2024-05-06 13:31
20240514 | 20240514026 | 26 | Temporary Marking | Is the intent to have Temporary Edge lines installed at the end of each week? | Temporary edgelines do not need to be installed prior to opening all lanes to IH 39 traffic each weekend. The intent is to install temporary edgelines prior to switching stages. Temporary or permanent edgeline is required during times listed in the Holiday and Special Event Work Restriction article of the special provisions. Refer to page 101 of the plan for details on drum placement when edgeline is not present and both lanes are open to traffic. | Mike Coleman | 6 | 2024-05-06 11:42 | 2024-05-07 11:49
20240514 | 20240514026 | 26 | Lane Shift | It&#39;s a little unclear in the plan, but the lane shift that happens in the NB direction starting just north of Hwy 10 for the acceleration lane construction stays up all week?As it&#39;s north of STA 1270 where everything else is night work only. Also assuming this would need to come down for the weekend? | The prosecution and progress article provides permitted lane closures times from station 1270+00 to 1508+90 and states â€œLane closures and lane shifts as shown in the project plan to construct the IH 39 NB parallel on ramp from USH 10 are allowed to remain in place outside the listed timesâ€. The traffic control for the parallel on ramp construction is shown in the project plans and does not need to be installed and removed daily. | Mike Coleman | 2 | 2024-04-29 18:14 | 2024-05-01 07:24
20240514 | 20240514026 | 26 | Busn 51 Ramps | Would the department consider closing the business 51 ramps for 2 days in each direction to perform the milling, paving, shouldering with restriction of having these done before school starts up. | The IH 39 NB on ramp from BUS 51 NB has two lanes for the majority of its length. A single lane closure could be installed on the IH 39 NB on ramp without outside of the ramp closure restrictions that keeps the ramp open to traffic when a ramp closure is not allowed. The work on the other ramps at the BUS 51 interchange (Northpoint) will follow the restrictions in the Prosecution and Progress article of the special provisions. Additionally, the Prosecution and Progress article of the special provisions allows traffic to operate on a milled surface for up to 96 hours. | Mike Coleman | 5 | 2024-05-04 06:32 | 2024-05-06 13:30
20240514 | 20240514027 | 27 | Schedule | Does the DOT have a construction schedule that was used for design that is available for Contractors to look at? | The design schedule can be found at the following location: https://wisdot.box.com/s/m27nad5onq38a1ji6npl0drvpck3dkb8 or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-05-01 11:55 | 2024-05-08 07:42
20240514 | 20240514028 | 28 | Mobilizations Erosion Control and Emergency EC | What work is anticipated to be performed under these bid items? The project has no other EC items that we can find. | These items are not needed because there are no other erosion control items in the project. The SPV item for Temporary Construction Access B-24-0019 would have these items incidental to that item if they were needed. An addenda will be submitted. | Mike Coleman | 1 | 2024-04-26 15:00 | 2024-05-01 07:23
20240514 | 20240514030 | 30 | Permanent Sheet Piling Paint Confirmation | Question 1 asked about painting the permanent sheets. The department&#39;s response stated that the sheets do not need to be painted. However, standard spec 512 indicates that permanent steel sheeting must be painted. Please indicate the department&#39;s requirement for painting the permanent sheets on this project. | Plan sheet 61 indicates the â€œChannel and connections are to be painted in accordance with pile spec. and after installation paint shall be touched up to the satisfaction of the engineer.â€ The intent was for the MC18X42.7 channel and channel connections to be painted. No other members require painting. | Mike Coleman | 2 | 2024-05-09 10:57 | 2024-05-10 06:21
20240514 | 20240514030 | 30 | Permanent Sheet Pile | The structure plan details that the channel cap and connections will be painted. Will the Permanent steel sheeting also need to be painted? | The exposed wall, consisting of permanent steel sheeting, will not need to be painted. | Mike Coleman | 1 | 2024-05-02 17:54 | 2024-05-08 07:35
20240514 | 20240514031 | 31 | Pedestrian Accommodations | I do not see a detailed map showing relevant streets, locations, etc for the Pedestrian Detours you are requesting for B-17-0130 and B-61-0118 in the plan. Will you be providing that? | A detailed map will be provided to construction staff to layout the pedestrian detours. | Mike Coleman | 1 | 2024-05-05 14:23 | 2024-05-08 09:58
20240514 | 20240514031 | 31 | Traffic Control- Temporary Traffic Signals | Will WISDOT permit the use of temporary traffic signals in lieu of flaggers for bridge locations that require a flagging closure? | Temporary signals are acceptable in lieu of flaggers where practical. Flagging is incidental to this contract and temporary signals are used then that method would also be incidental. The contractor is responsible for timings and is subject to approval by the engineer. Closures are not to remain in place when work is not being completed on the structures. | Mike Coleman | 3 | 2024-05-08 10:06 | 2024-05-08 11:27
20240514 | 20240514031 | 31 | Contract Time | Will WISDOT reconsider contract completion deadline to complete the scope of work for this contract. After, reviewing the bridge locations and the scope of work and being unable to commence operations due to migratory bird season and inability to prevent nesting now that the season has already begun, I believe the amount of time given is inefficient with this size project. | Multiple bridge painting operations were assumed to be completed simultaneously. B-47-33, B-17-847, B-10-158, and B-06-885 are currently netted, completed by the counties. Contract completion time will not be altered. Contractor is to verify with construction staff that migratory bird nests are not presented before beginning work. | Mike Coleman | 2 | 2024-05-08 09:15 | 2024-05-08 11:51
20240514 | 20240514034 | 34 | Soil Borings | Are soil borings available? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/2veok2456qujeo5jm2fc3mitwv5prt07 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-05-03 10:31 | 2024-05-07 11:36
20240514 | 20240514034 | 34 | Traffic Staging | SPV 4 &acirc;&#128;&#147; Traffic, Stage 5, Construction states to &acirc;&#128;&#156;place final HMA surface under flagging operations&acirc;&#128;&#157;. Under flagging, with a short distance to the east, traffic could quickly get backed up to STH 35/65 while rotating traffic through the roundabout. To assist in the safety of the travelling public and our workers and to provide reduced joints and a higher quality finish of the surface, would the department consider a closure of the roundabout/E. Cascade Ave for an 8 hour period to complete the surface and any necessary testing? If no closure is allowed, can the staging be adjusted to place the upper lift along with the lower lift in the earlier stages? | City Response: We would be comfortable with an 8-hour closure for paving with the restriction that it not occur during UWRF move-in and the City receives a one-week notice prior to closure. | Mike Coleman | 1 | 2024-04-29 17:27 | 2024-05-07 11:38
20240514 | 20240514035 | 35 | Construction Timing | Can a contractor start work prior to July 1st on the rural sections of County E west of the Village of Mason? | I spoke with Bob Anderson (Bayfield County Highway Commissioner) about this issue and he said yes the contractor may start work prior to July 1st west and north of Mason. The Town Board didnâ€™t want the road thru Mason and from 63 to Mason on CTH E to be disturbed prior to or during Mason Days. | Mike Coleman | 1 | 2024-04-25 07:41 | 2024-04-25 13:27
20240514 | 20240514037 | 37 | Detour and Traffic Control requirements if must be finished in 2025 | If project doesn&#39;t finish in 2024 does the road open to traffic? In 2025 does the Detour need to be reinstalled or is only Road Work ahead signage need to be installed? | The roadway will be open to traffic over Winter of 2024. The County will allow the roadway to be completed in 2025 under flagging operations. | Mike Coleman | 3 | 2024-05-08 16:01 | 2024-05-13 09:27
20240514 | 20240514037 | 37 | Pavement History | Is there any core/boring data available for the project? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/fz65gg2p9zf3saz6ho2qvxpff3y4knv0 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-04-16 08:13 | 2024-04-19 10:16
20240514 | 20240514037 | 37 | Item 54 | Plans show 76&#39; and Estimate of qty&#39;s shows 72&#39;for 72&quot; Aluminized Pipe. Also will 12ga 5x1 be acceptable for this pipe? | The pipe length shown in the plan of 76â€™ is the estimated length of pipe. The pipe will need to meet the standard specification requirements. | Mike Coleman | 2 | 2024-05-01 09:29 | 2024-05-06 07:32
20240514 | 20240514038 | 38 | Poor condition of Span 3 Prestressed Girders | The north end of span 3 prestressed girders at the existing joint appear to be in poor condition. Would the department consider and addendum to remove and replace these girders? | Replacement of the span 3 girders is not necessary. The concrete girders were inspected prior to plan development. The concrete surface repair bid item can be used to repair the girder ends and these girders will be encased in a concrete diaphragm at the north abutment. | Mike Coleman | 1 | 2024-05-07 09:36 | 2024-05-09 13:43
20240514 | 20240514039 | 39 | Soil Borings | Are soil borings available? | The soil borings can be found at the following location: https://wisdot.box.com/s/p2xcupiyvwm4jdsyi6dwxso7w46gnc0h or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-05-03 10:32 | 2024-05-06 13:27
20240514 | 20240514041 | 41 | Haul Route | Will contractors be able to haul construction materials through Hwy 13 in Washburn exceeding the 20Ton gross limit? | The local detour route through Washburn is posted at 20 Tons. There will not be an exemption to this weight limit for hauling construction materials and contractors shall plan on using the truck detour route. | Mike Coleman | 1 | 2024-05-06 16:56 | 2024-05-07 11:48
20240514 | 20240514042 | 42 | Structure Plan Sheets | Plan sheets showing structure repairs appear to be missing. | The structure sheets will be added by addendum. | Mike Coleman | 1 | 2024-04-12 09:46 | 2024-04-17 07:12
20240514 | 20240514042 | 42 | Asbestos Abatement | Please confirm the only asbestos to be abated on the structure is the caulk at the wingwall and abutment joints. | The asbestos report can be found at the following location: https://wisdot.box.com/s/cbvl7n98wcyz9zm4eox3yb7dilwj9uoi or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-04-29 08:58 | 2024-04-30 09:33