## qandasearchletting_results
Date: | 2024-07-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20240709 | 20240709001 | 1 | Concrete Barrier Precast Left In Place, Item SPV.0090.01 | Please confirm that the precast barrier block has to have been cast within the last 6 months per spec. Due to the large inventory of barrier block in the state of Wisconsin not much if any block has been cast in the past 5 years. If this is the case the unit price will be more than double and longer lead times might apply. | An addendum will be prepared to change the manufactured date of the Concrete Barrier Precast Left In Place from within 6 months to within 6 years. | Mike Coleman | 1 | 2024-06-19 13:32 | 2024-06-26 07:27
20240709 | 20240709002 | 2 | Bill of Bars - Rebar Quantity | Bill of Bars&quot; total is 3,472 lbs. more than the &quot;Proposal Schedule of Items&quot; weight. It&#39;s all in Structure B-15-30. It appears that the parapets may not be included in the schedule of items. Can this be clarified? | Yes. This discrepancy will be corrected in an upcoming addendum. | Mike Coleman | 1 | 2024-06-17 16:48 | 2024-06-18 08:40
20240709 | 20240709002 | 2 | Box Culvert | Can a precast box culvert spec be included for this project? | A precast concrete box culvert may be provided for structure C-15-46 per the 10th note listed under the General Notes on page number 218 of the plan. The â€œspecâ€ shall follow the standard specifications and the precast details in the Chapter 36 standards of the current Wisc DOT Bridge Manual. | Mike Coleman | 2 | 2024-06-26 07:12 | 2024-06-26 10:24
20240709 | 20240709002 | 2 | Design Schedule | Please provide the design schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/iycpb8cv8l3bqhz7ydu0fu4i5pxbin96 or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2024-06-26 07:49 | 2024-06-26 10:19
20240709 | 20240709003 | 3 | Box Culvert | Can a precast box culvert spec be included for this project? | No, the precast option is not allowed for this structure due to the low fill [B.M. 36.12] and the size of the box [ASTM C1577] | Mike Coleman | 1 | 2024-06-26 07:12 | 2024-07-01 07:37
20240709 | 20240709003 | 3 | Soil Borings | If available, could you provide the soil borings for this project? | All soil borings completed for these projects are in the plan, at Structure C-44-134. | Mike Coleman | 5 | 2024-07-02 18:19 | 2024-07-03 09:07
20240709 | 20240709003 | 3 | Pipe Patch HMA | Page 79 of the Misc. Quantities of 6230-16-71 shows pipe patch and curb fill locations as 3 MT, 4 MT and Asphaltic Surface. Should these areas be considered asphaltic Surface as they are done in 2024? Otherwise, what is the testing requirements? | Patching in areas of concrete curb and gutter and pipe replacements is intended to use the Asphaltic Surface item. An addendum will be issued to revise the quantities accordingly. | Mike Coleman | 2 | 2024-07-01 17:44 | 2024-07-05 06:36
20240709 | 20240709003 | 3 | Flagging Queues | The specials on page 8 state that the max lane closure allowed is a 2-mile accumulative lane closure. This job is 8.04 miles and in order for the contractor to be efficient and cost effective, the following lane closures will be needed. Milling lane closure will be about 1 ï¿½ miles. This is to allow for Milling mainline, widening of the shoulders, distressed milling, all trucking needed to perform the work, Coring for Density, flagging queue and flaggers. The paving train will need a minimum of 1 mile to 1.5 miles. This is to accommodate the paving train which consists of trucks, transfer machine, paver, breakdown roller, rubber tire roller, cold roller, density techs, flagger queues and flaggers. There could be a couple of other closures needed on any given day for the other scopes to perform their work. Could the Department please remove this restriction from the specials? | The concerns of combined operation limits not to exceed 2 miles lane closure on WIS 47 when the detour is not in place is needed due to volume of traffic on WIS 47. The concerns of combined operation limits not to exceed 2 miles lane closure on WIS 54 when the detour is in place is needed due to length of detour combined with flagging delays. To clarify the combined operation limits not to exceed 2 miles lane closure on WIS 54 does not apply when the WIS 54 detour is not in place. | Mike Coleman | 3 | 2024-07-02 11:30 | 2024-07-03 10:54
20240709 | 20240709003 | 3 | Permanent Sheet Piling | Will the Permanent Sheet Piling need to be painted? | Permanent Sheet Piling does NOT need to be painted. | Mike Coleman | 4 | 2024-07-02 18:10 | 2024-07-03 13:28
20240709 | 20240709004 | 4 | SPV.0045.01 Digital Speed Reduction System | Hello - please review the quantity table on plan page 135 regarding the Digital Speed Reduction System. The measurement for this item is per system, per day, but the Misc. Qty table shows multiple days/systems measured per project ID. This quantity is doubled or quadrupled depending on the stage. For example, 1020-07-79 Stage 2 is 144 days long, but the quantity for this item is 576 Days, indicating that there are (4) separate systems. This same quantity is repeated on 1020-07-81 Stage 2 with another (4) systems, for a total of (8) DSRS systems in Stage 2. Please review this quantity table. It looks like the total quantity should be 1,180 days | The Digital Speed Reduction System item will be paid each day the system is in use per Project ID. If multiple projects utilize the system, the item will be paid on each of the Project IDs using the system on that day. | Mike Coleman | 4 | 2024-07-05 14:18 | 2024-07-09 07:49
20240709 | 20240709004 | 4 | Geotechnical Report | Please provide a copy of the Geotechnical Report. | The geotechnical reports can be found at the following location: https://wisdot.box.com/s/qvll2ep0n60fxfw4zlx2v2q6fdvhj165 or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-06-26 10:24 | 2024-07-01 07:35
20240709 | 20240709004 | 4 | Asphaltic Surface Temporary | The specification calls out a 4HT 58-34V for these two lifts for asphaltic surface temporary. Would the department consider a 3HT with a lower grade oil for both lifts or the bottom lift? | Special provision article 18 is will be deleted via addendum. | Mike Coleman | 3 | 2024-07-01 09:42 | 2024-07-03 06:27
20240709 | 20240709004 | 4 | HMA Pavement | The typical sections for I-94 show a full depth 11.25 inch HMA constructed with all 4HT 58-34V. The department may want to consider a 3HT mix and needed asphalt cement type for the bottom layers of this pavement structure to help with overall structure and cost. On sheet 2 in the plans there is a chart under the General Notes that lists &acirc;&#128;&#156;19.0 MM&acirc;&#128;&#157; under the Nominal Maximum Size Gradation column for the lower two layers. | An addendum is being issued to revise the HMA aggregate sizes. | Mike Coleman | 2 | 2024-06-28 10:11 | 2024-07-03 06:23
20240709 | 20240709005 | 5 | Response to Question 4 | Based on the response to Question 4 and soil borings provided, the excavations shown in the current plans (1&#58;1 and 0.5&#58;1) will not be OSHA compliant as it is most likely the excavation will be in Class C soils which will require a 1.5&#58;1 slope. If your excavation limits are set based on environmental/utility/other constraints, temporary shoring will be required to perform the designed excavations. Please confirm that the temporary shoring required will be paid as extra work. Temporary shoring is not incidental to the bid items required in the contract (Common Excavation, Backfill Granular, Base Aggregate Open Graded) to construct the plan design and should not be considered the responsibility of the contractor to &quot;perform the work in the plan while still remaining OSHA compliant&quot;. The contractor did not design the excavation staging and limits on the project. | After discussion with the region design team, they feel confident in the design as provided. Please bid accordingly. | Mike Coleman | 5 | 2024-07-09 09:37 | 2024-07-09 10:40
20240709 | 20240709005 | 5 | Steel Sheet Piling Painting Requirements | Can the requirements for the painting system to be applied to the steel sheet piling for structure R-16-010 be provided? The only requirements listed states the top coat color but the painting system is not called out. | Specification details for painting permanent steel sheet piling are covered under 512.3.3. Under section 512.3.3, it refers to sections 550.3.11.3, 517, and the approved products list (APL) for further details. | Mike Coleman | 3 | 2024-07-02 09:32 | 2024-07-03 06:19
20240709 | 20240709005 | 5 | Sheeting Specs | Plan sheets 279 and 280 list differing section modulus specifications for the permanent sheeting. Please identify which spec is to be used. Thank you. | The minimum section modulus needed is 31 in^3/ft, shown on the Steel Sheet Pile Retaining Wall sheet and in footnote 3 of the â€˜Wall External & Overall Stability Evaluationâ€™ table on the Wall Data & Quantities sheet. | Mike Coleman | 1 | 2024-06-26 09:13 | 2024-06-26 11:01
20240709 | 20240709005 | 5 | Staged for Little Pokegama Excavation (Cross Section Sheets 308-320) | The cross sections referenced for the staged excavation show slopes of 0.5&#58;1 and 1&#58;1. Will WIDOT be providing an engineered drawing that verifies the current soils conditions will allow for these steep slopes? Do the current plans cover this requirement when dealing with OSHA? As this excavation will be considered a trench excavation with workers in the bottom of the trench to place fabric/underdrain/stone, an engineered statement/classification will be required to meet OSHA standards and allow workers in this trench. If such a statement will not be provided by WIDOT, it is most likely the existing soils will be classified as at Type C soil with a maximum slope of 1.5&#58;1. This will require more excavation/backfill and most likely utility relocations in order to provide an OSHA compliant slope. Will WIDOT pay for these additional costs? | Due to environmental, utility and other project constraints the excavation limits are set. The soil borings can be found at the following location: https://wisdot.box.com/s/fpie6vo66x9jjqcof6t5dqplluv7oe7t or can be accessed on the HCCI July bid letting page under Supplemental Information. Please bid excavation and backfilling accordingly to perform the work in the plan while still remaining OSHA compliant. | Mike Coleman | 4 | 2024-07-08 19:09 | 2024-07-09 09:11
20240709 | 20240709005 | 5 | Little Pokegama Excavation Mix Type | The typical section for the Little Pokegama Excavation on sheet 7 specifies 7 inches of 5MT 58-34V mix. The department may want to consider changing this to a 4MT 58-28S or 58-34S for the paving that will occur in 2024 for better structure and pricing. This area will be milled and overlayed with the 5MT58-34V in 2025. | Per discussion with the NW region pavement engineer, a change to the 4MT 58-34S mix will be made to the 7 inches of HMA that will be paved at station 96+40 â€“ 100+00 in 2024. An addendum will be issued. | Mike Coleman | 2 | 2024-06-28 09:14 | 2024-07-02 08:57