## qandasearchletting_results
Date | 2024-11-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20241112 | 20241112001 | 1 | Transformer Bases | The current lead time for item 657.0225, transformer bases, is 30 months. How does the project plan to handle this and other long lead time parts that will be unattainable before the project deadline? | WisDOT does not recognize a shortage in transformer bases at this time. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. | Mike Coleman | 1 | 2024-11-05 13:11 | 2024-11-06 17:38
20241112 | 20241112001 | 1 | Design Schedule & Geotech Report | Can you provide the design schedule and geotechnical report? |  |  | 2 | 2024-11-05 17:20
20241112 | 20241112002 | 2 | Milling/HMA Paving Restrictions | Per the special provisions the lower layer must be placed within 48 hours of milling. With the distressed milling/asphalt surface, 48 hours will be very difficult/costly. Can the Department extend this timeframe to at least 84 hours? | The existing typical shows 4â€-4.5â€ of asphalt and we feel most of the asphalt will be totally removed and distressed milling will be minimal. Our concern is having the subgrade open to truck hauling or the elements for longer than needed. We are staying with 48hrs. | Mike Coleman | 1 | 2024-10-14 10:11 | 2024-10-15 12:30
20241112 | 20241112002 | 2 | Milling/HMA Paving Restrictions #2 | Paragraph #6 in the Prosecution and Progress States&#58; â€œThe lower layer of HMA pavement shall be placed within 48 hours of milling to minimize damage to the underlying pavement......â€ This paragraph leads to multiple questions&#58; 1. Can the Department provide locations of the distressed milling? With only a 48 hour window, contractors need to have a plan for paving. 2. What are the parameters the engineer will use to determine if the contractor is required to drop everything and place the lower lift on the same day as milling? Will there be a minimum tonnage or size considered for mobilizing on a day that contractor&#39;s are not paving on site? 3. What specifications will the engineer be following to determine if the contractor is using â€œavoidable operational procedures and haul truck management? | 1. No. The exact locations are unknown. 2. We will remove this sentence â€œIf underlying pavement or subbase shows signs of distress due to construction activities, the field engineer may instruct the contractor to place the lower layer of HMA pavement the day of milling. 3. We will remove â€œIf underlying pavement is damaged due to avoidable operational procedures, i.e., excessive loading, haul truck management, etc., as determined by the field engineer, it will be the contractorâ€™s responsibility to fix underlying areas.â€ We feel that if the pavement is damaged during construction this can be handle by language in the spec book. | Mike Coleman | 2 | 2024-10-22 11:33 | 2024-10-28 08:01
20241112 | 20241112002 | 2 | Fisheries/Stream Work | Per the Prosecution and Progress, does the box culvert work (2 EA) and pipe crossing (1 EA) apply to this special provision or will prospective bridge contractors be able to start prior to June 15th? It appears these area are more of farm/runoff ditches than waterways as they are dry or drier during certain times of the year. | A screenshot from the original DNR correspondence can be found at the following location: https://wisdot.box.com/s/u5e4ri4ioswklflvw0nmmud195014khj or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-10-22 14:11 | 2024-10-28 08:05
20241112 | 20241112002 | 2 | Dewatering | Would a temporary water diversion be allowed in lieu of the pumping/dewatering details shown in the plans? | When we started looking at constructing the box culvert we determined the water flow was low enough that pumping would be enough. Seemed like a temporary diversion channel was unnecessary. Pumping also gave the contractor the opportunity to access the box culverts from the north and south. We are not against the diversion channel. There is no temporary limited easement to accommodate the channel. Utilities or Environmental have not been looked at. This would be the responsibility of the contractor. No updates to the plan will be made for this. | Mike Coleman | 4 | 2024-11-05 06:29 | 2024-11-06 17:40
20241112 | 20241112002 | 2 | Milling Quantity | Can the Department recheck the SYs of milling in the plan? It appears to be underrunning by ~10-12%. | Quantities were recomputed. Plan quantity is 122,050 SY. Revised quantity is 103,950 SY. An addendum will be issued. | Mike Coleman | 5 | 2024-11-05 15:55 | 2024-11-07 09:33
20241112 | 20241112002 | 2 | Notice to Proceed | Would the department be willing to change the Notice to Proceed date from June 10th to a later date in the summer, possibly August 1st? | June 10th was picked based on not getting into cold weather paving. We see no reason to change the Notice to Proceed date. | Mike Coleman | 6 | 2024-11-06 16:38 | 2024-11-07 09:35
20241112 | 20241112003 | 3 | Geotech Report | Can the Department provide the geotechnical report for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/kud5dt6zn16odhjn2t22b6rzj4hzw2br or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-14 12:46 | 2024-10-15 07:23
20241112 | 20241112003 | 3 | Watermain | Can the Department provide maps of the existing watermain in the area of this project? | The maps can be found at the following location: https://wisdot.box.com/s/kud5dt6zn16odhjn2t22b6rzj4hzw2br or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-10-17 12:13 | 2024-10-21 10:00
20241112 | 20241112003 | 3 | City Specifications | Can the Department provide the City of Watertown specifications for watermain? | The design team got together and confirmed that all watermain work listed in the plans conform to the WisDOT standard specs for sewer/water/backfill as well as the spec book. City specifications were not used or referenced with this project. | Mike Coleman | 3 | 2024-10-17 12:54 | 2024-10-21 10:06
20241112 | 20241112003 | 3 | Adjusting Sanitary Sewer Manholes | Per the Special Provisions for adjusting sanitary manholes, the contractor may have to dig all the way to the bottom of the manhole, by pass pump, or may not depending on what the Department/City want. IE this bid unit could be between $500/EA-$10,000/EA depending on what the engineer deems necessary in the field. Could the Department/City inspect the 4 MHs in the contract and see exactly what is needed for the 4 MHs so that Contractors could bid accordingly? |  |  | 4 | 2024-10-21 07:26
20241112 | 20241112003 | 3 | Contaminated Groudwater | This special provision describes pumping ground water into the sanitary sewer or hauling off site. With the Department&#39;s previous testing results, will contractor&#39;s be allowed to pump into the sanitary sewer or not? There is a large difference in cost between being able to pump into the sanitary sewer vs. hauling off-site and this specification does not clarify whether the City will accept the groundwater. |  |  | 5 | 2024-11-05 16:18
20241112 | 20241112003 | 3 | Design Schedule | Can you provide the design schedule? |  |  | 6 | 2024-11-05 17:13
20241112 | 20241112005 | 5 | HMA Density Acceptance | What will the density target be for the lower layer of asphalt since there will be differing underlying material? Targets are different whether paving on base or paved surface. | An addendum will be processed to accommodate the varying underlying surfaces for the lower lift of HMA pavement. Cores will be used as a means of density acceptance for the lower lift of HMA pavement. The addendum will reflect decreasing the quantities associated with the bid items 460.0110.S HMA Percent Within Limits (PWL) Test Strip Density, 460.2005 Incentive Density PWL HMA Pavement, 460.007 Incentive Density HMA Pavement Longitudinal Joints, and 460.2010 Incentive Air Voids HMA Pavement so that those items only apply to the upper layer. Special Provision language and bid items associated with providing for density acceptancy and incentive of the lower layer via cores will be added. | Mike Coleman | 1 | 2024-11-04 15:04 | 2024-11-06 13:37
20241112 | 20241112007 | 7 | Geotechnical Report | Can the Geotechnical Report be made available for this project? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/y4thwfu9gqcuw0whr9ouj4hb6n3gbmi9 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-17 08:47 | 2024-10-21 10:34
20241112 | 20241112007 | 7 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/y4thwfu9gqcuw0whr9ouj4hb6n3gbmi9 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-10-17 08:57 | 2024-10-17 13:08
20241112 | 20241112007 | 7 | Earthwork & Pipe Tabulations | Can the excel versions of the earthwork tabulations and pipe MQ&#39;s be provided? | The excel spreadsheets can be found at the following location: https://wisdot.box.com/s/y4thwfu9gqcuw0whr9ouj4hb6n3gbmi9 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-10-24 08:18 | 2024-10-28 06:44
20241112 | 20241112007 | 7 | Marsh Excavation | For B-12-916, the marsh excavation details show placing the Geotextile Type SAS at an elevation roughly 6-ft below groundwater. Will the contractor be required to dewater before placing this item? If so, how will the dewatering be paid? | Geotextile Type SAS shall be installed per standard specification 645.3.1.2. If groundwater is encountered, dewatering will be required to ensure geotextile is correctly installed and would be incidental to the Excavation for Structures bid item. | Mike Coleman | 4 | 2024-10-25 16:00 | 2024-10-29 07:01
20241112 | 20241112007 | 7 | Sod On Shoulders- Mill & Relay | The existing shoulders on the project are currently heavily vegetated with sod for a majority of the project length. We assume it cannot be incorporated into the mill and relay material and in most cases if it was rolled out by a grader it would end up either down the foreslope or filling the ditch. Is this sod to be removed from the project? If so, what pay item is being used for this? | An addenda will be issued to clarify the general notes page. Non-conforming material cannot be incorporated into the mill and relay operation. Excess material that cannot be placed on the foreslope shall be removed under item 211.0101 Prepare Foundation for Asphaltic Paving. Payment is incidental to this item under spec 211.3.6. | Mike Coleman | 5 | 2024-10-30 16:34 | 2024-10-31 10:45
20241112 | 20241112007 | 7 | Mill & Relay- Profile Drop | Notes on typical sections state&#58; â€œMill &amp; Relay Profile to be 1â€ - 2â€ below existing profile. Maintain existing slopes as best as practical.â€ Where is the excess material expected to go to create the drop in profile? The existing shoulders are not low enough to accept this material. Will the existing shoulder need to have a trench excavated to make room for excess material to lower the profile? If so, what pay item is used for this work? If the mill and relay mills 11â€™ x 4â€ and a 1â€ profile drop is required then 2â€™ x 5.5â€ of existing shoulder material will need to be removed on the outside edge of the lane to make room for the 6.7 TON/STA of millings generated by lowering the profile 1â€. | The proposed width is wider than the existing width to add paved shoulders. The decrease in profile is from spreading the mill and relayed material wider as shown in the typical sections. Milling material is not to be removed unless required by contractor operations. The intent of the note is to correct the normal crown and supers to be in line with current design standards as best as practical and not increase shoulder or side slopes beyond the 2.5:1 max slope. Proposed width of mill & relay are wider than existing pavement widths. Excess material that cannot be placed on the foreslope shall be removed under item 211.0101 Prepare Foundation for Asphaltic Paving. Payment is incidental to this item under spec 211.3.6. | Mike Coleman | 6 | 2024-10-30 16:35 | 2024-10-31 10:46
20241112 | 20241112007 | 7 | Superelevations | Is the superelevations to be marked out by the engineer or under the construction staking items. And if it is to be done under construction staking is the State supplying super tables for the transisions. | 5780-03-61 Super elevation transitions and tables will be supplied by project engineer during construction. Staking per 650.8000. 5780-03-81 Super elevation transitions and tables are listed in the project plan, see construction details. Staking per item 650.8000. | Mike Coleman | 7 | 2024-10-31 07:28 | 2024-11-01 06:50
20241112 | 20241112008 | 8 | Geotechnical Reports | Can the Geotechnical Report be made available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ik47x3gm9jxda2mqzoj9ij44ipzu249b or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-17 08:48 | 2024-10-17 13:42
20241112 | 20241112008 | 8 | Design Schedule | Can the Design Schedule be provided? |  |  | 2 | 2024-10-17 08:58
20241112 | 20241112008 | 8 | Earthwork & Pipe Tabulations | Can the excel versions of the earthwork tabulations and pipe MQ&#39;s be provided? | The excel spreadsheets can be found at the following location: https://wisdot.box.com/s/ik47x3gm9jxda2mqzoj9ij44ipzu249b or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-10-24 08:18 | 2024-10-28 06:46
20241112 | 20241112008 | 8 | Sod on Shoulders- Mill & Relay | The existing shoulders on the project are currently heavily vegetated with sod for a majority of the project length. We assume it cannot be incorporated into the mill and relay material and in most cases if it was rolled out by a grader it would end up either down the foreslope or filling the ditch. Is this sod to be removed from the project? If so, what pay item is being used for this? | An addenda will be issued to clarify the general notes page. Non-conforming material cannot be incorporated into the mill and relay operation. Excess material that cannot be placed on the foreslope shall be removed under item 211.0101 Prepare Foundation for Asphaltic Paving. Payment is incidental to this item under spec 211.3.6. | Mike Coleman | 4 | 2024-10-30 16:37 | 2024-10-31 10:47
20241112 | 20241112008 | 8 | Mill & Relay - Profile Drop | Notes on typical sections state&#58; â€œMill &amp; Relay Profile to be 1â€ - 2â€ below existing profile. Maintain existing slopes as best as practical.â€ Where is the excess material expected to go to create the drop in profile? The existing shoulders are not low enough to accept this material. Will the existing shoulder need to have a trench excavated to make room for excess material to lower the profile? If so, what pay item is used for this work? If the mill and relay mills 11â€™ x 4â€ and a 1â€ profile drop is required then 2â€™ x 5.5â€ of existing shoulder material will need to be removed on the outside edge of the lane to make room for the 6.7 TON/STA of millings generated by lowering the profile 1â€. | The proposed width is wider than the existing width to add paved shoulders. The decrease in profile is from spreading the mill and relayed material wider as shown in the typical sections. Milling material is not to be removed unless required by contractor operations. The intent of the note is to correct the normal crown and supers to be in line with current design standards as best as practical and not increase shoulder or side slopes beyond the 2.5:1 max slope. Proposed width of mill & relay are wider than existing pavement widths. Excess material that cannot be placed on the foreslope shall be removed under item 211.0101 Prepare Foundation for Asphaltic Paving. Payment is incidental to this item under spec 211.3.6. | Mike Coleman | 5 | 2024-10-30 16:39 | 2024-10-31 10:47
20241112 | 20241112008 | 8 | Supers | Is the superelevations to be marked out by the engineer or under the construction staking items. And if it is to be done under construction staking is the State supplying super tables for the transisions. | Super elevation transitions and tables are listed in the project plan, see alignment details. Staking per item 650.8000. | Mike Coleman | 6 | 2024-10-31 07:29 | 2024-11-01 06:49
20241112 | 20241112009 | 9 | Typicals - Plan Details | The finished typical sections, Cross sections do not match the plan details? What are we supposed to use to bid project? | The plans were reviewed by the department and designer, please bid on the provided plans accordingly. | Mike Coleman | 1 | 2024-10-15 09:32 | 2024-10-22 06:48
20241112 | 20241112009 | 9 | Geotechnical Report | Can the Geotechnical Report be made available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/xy8wkfre4hb93jhscv7cko85y1rsr5pp or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-10-17 08:50 | 2024-10-17 11:54
20241112 | 20241112009 | 9 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/xy8wkfre4hb93jhscv7cko85y1rsr5pp or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2024-10-17 08:59 | 2024-10-17 13:41
20241112 | 20241112009 | 9 | Soldier Pile Suppliers - Approval | Since the soldier piles are paid for under bid item 506.0605 Structural Steel HS, will suppliers be required to be on the APL list &quot;Approved Fabricators, Steel Bridge Primary Members&quot; Product key category 1 or higher? Or will Piling suppliers (DBE &amp; Non) which not on the APL be acceptable? | Soldier pile wall fabricators are allowed to come from Fabricated Bridge Component APL lists or from the Steel Bridge Primary Members APL. Soldier piles and tiebacks anchors are considered primary members, and the welding requirements are covered in section 506 of the Standard Specifications. | Mike Coleman | 4 | 2024-10-21 10:54 | 2024-10-30 06:48
20241112 | 20241112009 | 9 | Select Crushed Quantity | The total Select Crushed quantity listed in the MQs (28,463 ton) and schedule of items does not take into account the quantity required for EBS BF. Please revise. | See page 185, Miscellaneous Quantities, Aggregate Summary Table, there is 3,888 TONs of undistributed Select Crushed Material and in the â€œRemarksâ€ it states â€œEBSâ€. The 3,888 TONs is based on the grand total of EBS Excavation multiplied by a factor of 1.8. You can find the EBS Excavation grand total from the Common Excavation Table on 184. | Mike Coleman | 5 | 2024-10-21 16:02 | 2024-10-23 08:26
20241112 | 20241112009 | 9 | Soldier Pile Corners | Please provide a detail for lagging support between posts 3&amp;4, 28&amp;29, and 32&amp;33. No piles are drawn at these points, and existing detail has no lagging support shown | An addendum is being prepared that will provide more plan information on the lagging supports between posts at the corners of the soldier pile wall. | Mike Coleman | 6 | 2024-10-25 13:03 | 2024-10-31 10:35
20241112 | 20241112009 | 9 | Soldier Pile Wall Access | Will soldier pile driller have any access to backside of wall, or is all access to come from roadway? | All access is to come from the roadway side of the retaining wall. There is an area of temporary limited easement behind the wall to allow room to work. | Mike Coleman | 7 | 2024-10-29 14:41 | 2024-10-30 17:48
20241112 | 20241112009 | 9 | Soldier Pile Wall TLE Limits & Constructability | The structural plans for the soldier pile wall do not show the PLE and TLE limits. How much room is between the back flange of the soldier pile wall and the TLE? From a constructability standpoint there should be a temporary shoring item added to the estimate of quantities to allow for demolition of the wall, thus creating a suitable and safe drilling bench to install the vertical H-Piles from the roadside. | The TLE limits very throughout the wall extents. Linework associated with project edgelines and right-of-way limits (including TLE) was included in the published Construction Data Packet. The narrowest point between the back flange and the edge of the TLE is approximately 6â€™ at Pile 33, but is wider elsewhere with some stretches as wide as 16â€™. Shoring for the structure is addressed under item 206.3001, Excavation for Structures Retaining Walls R-13-0373. Please refer to Standard Specification 206.3.7(2) and 206.5.2(2) for further details. | Mike Coleman | 8 | 2024-10-31 14:55 | 2024-11-05 07:53
20241112 | 20241112009 | 9 | Solider Pile Wall - House Foundation | Will details be provided regarding the residential structure foundations behind the soldier pile wall? | Details pertaining to the residential structure foundation have not been made available to the design team and will not be provided. | Mike Coleman | 9 | 2024-10-31 15:46 | 2024-11-05 07:55
20241112 | 20241112009 | 9 | Solider Pile Wall - Temporary Shoring | Will temporary shoring bid item be added for this structure or is all shoring for this wall incidental to Excavation for Structures? | Shoring for the structure is addressed under item 206.3001, Excavation for Structures Retaining Walls R-13-0373. Please refer to Standard Specification 206.3.7(2) and 206.5.2(2) for further details. | Mike Coleman | 10 | 2024-10-31 15:47 | 2024-11-05 07:55
20241112 | 20241112009 | 9 | Existing Masonry Retaining Wall As-Builts | Will as-builts be provided for the existing retaining wall that is to be removed? Going along with the note shown on Sheet 2, please confirm the wall is to remain in place until it crosses the face of the new wall between soldier piles 28 and 29? | As builts for the existing retaining wall were sought throughout the design process in coordination with the City of Stoughton, but none were found. Thus, as-builts for the existing retaining wall will not be provided because they donâ€™t appear to exist. The intention is for the existing retaining wall to remain in place from the Sta. 1+99 wall corner to end of wall, limited to where it crosses the face of the new wall as noted. The remainder of the existing wall is to be removed concurrently with lagging placement in cut sections of new wall | Mike Coleman | 11 | 2024-10-31 15:49 | 2024-11-06 17:48
20241112 | 20241112009 | 9 | Geotech Report for R-13-373 | Please provide the geotech report for R-13-373. The borings for this retaining wall performed by Gestra on 5/19/22 are not part of the uploaded geotech report; it is mainline borings only. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/xy8wkfre4hb93jhscv7cko85y1rsr5pp or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 12 | 2024-11-04 13:00 | 2024-11-07 14:19
20241112 | 20241112009 | 9 | Transformer Bases | The current lead time for item 657.0225, transformer bases, is 30 months. How does the project plan to handle this and other long lead time parts that will be unattainable before the project deadline? | WisDOT does not recognize a shortage in transformer bases at this time. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. | Mike Coleman | 13 | 2024-11-05 13:12 | 2024-11-06 17:37
20241112 | 20241112009 | 9 | Soldier Pile Wall | From Post 28 to 38, Construction with big equipment will be required to build this portion of the wall. Per the plan details there is no reconstruction of the &quot;Melton&quot; parking lot. Will the Department be paying contract units for any partial reconstruction of the &quot;Melton&quot; property? | The parking lot area within the temporary limited easement would be contractual eligible for payment to restore the parking lot. Any area of the parking lot outside of the temporary limited easement disturbed by construction activity would be the responsibility of the contractor to restore at their own cost. | Mike Coleman | 14 | 2024-11-07 10:17 | 2024-11-11 08:25
20241112 | 20241112009 | 9 | Soldier Pile Wall - Geotechnical Borings | The borings provided in the Geotechnical Report by Gestra, dated 5/19/22, do not extend to the design tip elevation of the soldier piles. Is there any geotechnical information available below EL 847.20 at the location of the retaining wall? For soldier pile excavations that exceed the termination depth of the applicable boring, is the Contractor expected to assume a continuation of the subsurface material classification, properties and strength based on the last known information shown in the borings? | First page of the Geotech Summary R-13-373, Sand below elev. 877 is called out. There isnâ€™t additional geotechnical information available below what is shown in the boring logs. The contractor is expected to assume a continuation of the subsurface material classification, properties, and strength based on the information provided by the geotechnical summary. | Mike Coleman | 15 | 2024-11-11 10:50 | 2024-11-12 08:47
20241112 | 20241112010 | 10 | Geotechnical Report | Can the Geotechnical Report be made available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/2qdbfieuwfqnumj79qwohroydtzois04 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-17 08:51 | 2024-10-17 12:05
20241112 | 20241112010 | 10 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/2qdbfieuwfqnumj79qwohroydtzois04 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-10-17 08:59 | 2024-10-17 13:34
20241112 | 20241112010 | 10 | Bar steel reinf. quantities, Items 134, 136 | The quantities listed for the plain and coated rebar across the four bridges, B-386/387/388/899 do not appear to add up to the quantities listed in the proposal. Item 134&#58; proposal lists 30,250 LB, structures total =28,780 LB Item 136&#58; proposal lists 260,560 LB, structures total = 258,290 LB | For Structure B-13-899, the total quantities also include what is needed for the retaining wall (R-13-386) in the NW quadrant. The bridge and the retaining wall are in the same category. â€¢ The coated bar in the retaining wall is 2,270 LB (258,290 + 2,270 = 260,560) â€¢ The regular bar in the retaining wall is 1,470 LB (28,870 + 1,470 = 30,250) Refer to the R-13-386 plan sheets for the additional bar quantities. Once the additional quantity is factored in, the totals will match the structure sheets and the proposal. | Mike Coleman | 3 | 2024-10-21 16:40 | 2024-10-23 08:22
20241112 | 20241112010 | 10 | Structure Plan | Believe the structure plans for B-13-899 &amp; R-13-386 is missing in plan. | Structure B-13-899 plan set is in the plans shown on sheets 543 â€“ 585. There was no bookmark created. Structure R-13-386 is missing in the plan set. An addendum will be issued to add R-13-386. | Mike Coleman | 4 | 2024-10-23 11:18 | 2024-10-24 08:15
20241112 | 20241112010 | 10 | Item # 640 - Concrete Supports | There are two separate locations shown that concrete supports are needed for the block retaining wall but only 1 EACH is shown in the miscellaneous quantities. Please update the bid quantity to 4. | An addendum will be issued with the updated quantity. | Mike Coleman | 5 | 2024-10-30 08:04 | 2024-11-05 07:56
20241112 | 20241112010 | 10 | Utility Line Opening | Consider adding an ULO item with a small undistributed quantity to this project. | An addendum will be issued that will add the ULO bid item to the project. | Mike Coleman | 6 | 2024-10-30 08:07 | 2024-11-05 09:48
20241112 | 20241112010 | 10 | Barrier Wall Delineation | Can a detail be provided for the Barrier Wall Delineation item? SPV.0060.02. | A detail is not needed. The special provision for the Barrier Wall Delineation item is clear about size, placement, and mounting. | Mike Coleman | 7 | 2024-11-01 14:34 | 2024-11-06 17:41
20241112 | 20241112010 | 10 | Temporary Shoring | Are there required displacement limits on the railroad at the location of the temporary shoring. Is any survey monitoring to be required. If so, how will it be paid? | Displacement limits and survey are not required at the temporary shoring location by the railroad. | Mike Coleman | 8 | 2024-11-04 06:35 | 2024-11-06 17:44
20241112 | 20241112010 | 10 | Debris Containment | Is the contractor to be required to have debris containment for all spans during removal of existing B-13-60, even with traffic closed and roadway and path below to receive new pavement, or is the debris containment meant only for the span over the railroad? | Debris containment is intended for over the railroad. | Mike Coleman | 9 | 2024-11-04 06:39 | 2024-11-06 17:45
20241112 | 20241112010 | 10 | Transformer Bases | The current lead time for item 657.0225, transformer bases, is 30 months. How does the project plan to handle this and other long lead time parts that will be unattainable before the project deadline? | WisDOT does not recognize a shortage in transformer bases at this time. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. | Mike Coleman | 11 | 2024-11-05 13:12 | 2024-11-06 17:37
20241112 | 20241112010 | 10 | Earthwork | Please provide the Earthwork Data tables in excel format. | The Earthwork Data tables in excel format can be found in the Contractor Data Packet (CDP). | Mike Coleman | 12 | 2024-11-05 14:34 | 2024-11-11 08:26
20241112 | 20241112010 | 10 | B-13-899 Superstructure CY | Please confirm 492.9 CY for superstructure quantity. Was the parapet CY forgotten in this number? | The parapet CY has been reviewed and was not forgotten in this number. 492.9 CY is the correct quantity for the superstructure concrete. | Mike Coleman | 13 | 2024-11-05 15:34 | 2024-11-11 08:30
20241112 | 20241112010 | 10 | Taylor Road Traffic Control Plan - Girder Erection | Special Provisions and traffic control plans state Taylor Road will be closed in stage 2a and then Siggelkow Rd will be closed with Taylor Road open for the remainder of stage 2. In order to set girders over Taylor Road, Taylor Road will need to be closed and probably during a timeframe Siggelkow Rd is also closed in order to get the project completed on time. What will be the requirement for traffic control on Taylor Road (full closures, flagging, etc) and what time of day will this work be allowed to take place? | The Department has made a commitment to the Village of McFarland that Taylor Road and Siggelkow Road will never be closed to traffic at the same time during construction. If the contractor requests to close Siggelkow Road sooner, flagging operations along Taylor Road with a single lane open would be acceptable during daytime operations. Then Taylor Road must remain open to traffic outside daytime operations. | Mike Coleman | 14 | 2024-11-07 13:35 | 2024-11-11 10:46
20241112 | 20241112010 | 10 | Temporary Shoring (structure) R-13-375/376/378 | The Wall External &amp; Overall Stability Evaluations tables for these 3 retaining walls have minimum length of reinforcements between 14 and 16.5 feet. The temporary shoring layout for these 3 walls is approximately 9-10 feet behind the front face of the retaining wall. The temporary shoring as shown in the plans will not allow for the minimum length of reinforcement for these walls. The temporary shoring should be moved back to account for the required reinforcement lengths, which will make the shoring much taller (more SF) and may require specialized tie back systems versus standard cantilever shoring systems. | Temporary shoring locations shown on the plans are not labeled as an exact location. As included in the general notes, drawings are not intended to be scaled. Temporary shoring quantities shown are intended to account for additional height due to offset and back slope of fill behind the walls. | Mike Coleman | 15 | 2024-11-07 16:59 | 2024-11-12 08:41
20241112 | 20241112010 | 10 | B-13-899 Excavating for Pier 2 within Railroad ROW | In the past we have seen that you can not excavate within 15&#39; of the C/L of the railroad tracks without permission or a permit from the railroad. Proposed Pier 2 edge of footer is approximately 13.5&#39; to C/L of track. Even with a temporary shoring system there will be excavating technically within 15&#39; of C/L. Please confirm permits or approvals have been received. | From the Railroad Special Provisions 3. Provide an obstruction-free work zone adjacent to a track extending 12 feet or more horizontally on both sides of the track centerline. Keep this work zone free of construction debris. 4. Unless the railroad's chief engineering officer approves otherwise in writing, maintain minimum clearances from falsework, forms, shoring, and other temporary fixed objects as follows: 4.1 Provide 12 feet, plus 1.5 inches per degree of track curvature, measured horizontally from the track centerline. | Mike Coleman | 16 | 2024-11-08 11:08 | 2024-11-12 08:42
20241112 | 20241112010 | 10 | Excavation for Structures Retaining Walls (structure) R-13-377 & R-13-1378 | There is currently nothing in the plans to pay for the excavation to construct these retaining walls. Please provide Excavation for Structures items for these two retaining walls. Structures R-13-375 &amp; 376 currently have quantities of Common Excavation to pay for the excavation for these two retaining walls. Please provide the appropriate Excavation for Structures Retaining Walls (structure) to pay for the excavation required to construct these two retaining walls. | R-13-374 (WNW): Excavation Common is calculated to front face of retaining wall. Excavation required for the MSE wall, reinforcement straps, and backfill structure zone is incidental to the Wall Modular Block MSE item. The additional excavation/grading required beyond the limits of the MSE wall, reinforcement straps, and backfill structure zone is paid for under Excavation for Structures Retaining Walls. R-13-375 (WNE): Excavation Common is calculated to front face of retaining wall. Excavation Below Subgrade (EBS), as shown on the structure plan sheets, is quantified as Excavation Common (Cat. 0050). All excavation beyond the front face of retaining wall, excluding the EBS, is incidental to the Wall Modular Block MSE item. R-13-376 (ESW): Excavation Common is calculated to front face of retaining wall. EBS, as shown on the structure plan sheets, is quantified as Excavation Common (Cat. 0060). All excavation beyond the front face of retaining wall, excluding the EBS, is incidental to the Wall Modular Block MSE item. R-13-377 (ENE): Excavation Common is calculated to front face of retaining wall. All excavation beyond the front face of retaining wall is incidental to the Wall Modular Block MSE item. R-13-378 (ESE): Excavation Common is calculated to front face of retaining wall. All excavation beyond the front face of retaining wall is incidental to the Wall Modular Block MSE item. R-13-386: All excavation required for the retaining wall is classified under Excavation for Structures Retaining Walls. | Mike Coleman | 17 | 2024-11-10 15:45 | 2024-11-12 08:44
20241112 | 20241112011 | 11 | 415.0100 Concrete Pavement 10" | Is it ok if this is poured by hand with a truss screed? | Please reference standard specification 415.3.6 Placing Concrete. The intent is to use slip-form placement wherever practicable. | Mike Coleman | 1 | 2024-10-16 10:51 | 2024-10-21 10:17
20241112 | 20241112011 | 11 | 415.0100 Concrete Pavement 10" Work Area | Traffic control details on sheet eleven do not provide enough working area between new pavement and existing roadway. Typically, a minimum of four feet of space is required between edge of new pavement and existing pavement for machine installation. A minimum of three feet of space is required between edge of new pavement and existing for hand placement. Please advise if working area can be increased. |  |  | 2 | 2024-11-06 14:10
20241112 | 20241112012 | 12 | Guardrail Timing | The staging of the plan is in conflict with SS 614.3.1(1). Please confirm that this project is waiving this requirement. | The department will not waive SS 614.3.1(1). The engineer will approve modifications to the staging plan to meet the standard spec in accordance with Schedule of Operations section in the special provisions. | Mike Coleman | 1 | 2024-11-04 09:08 | 2024-11-08 11:12
20241112 | 20241112013 | 13 | Pier Construction | Special Provision 12 states that concrete poured under water is allowable. It further reads that all displaced water from the pier pour must be treated prior to discharge back into the river. In order to fully capture displaced water from the pier pour for treatment, a cofferdam would be required. At a minimum, turbidity barrier could be attempted, but may not be ideal in moving current. Neither a cofferdam nor turbidity barrier at the pier is shown in the plans or quantities. Would the Department entertain adding either of these options, as this is what would be necessary in order to fulfill the requirements of Special Provision 12? | Turbidity Barrier will be added to the plans. An addendum will be submitted with changes to the plans, quantities and estimate. | Mike Coleman | 1 | 2024-10-10 14:35 | 2024-10-14 10:21
20241112 | 20241112013 | 13 | Turbidity Barrier and Sheeting | The plans show a Q2 of 8 feet of water and a velocity of 5.95 ft/sec. With the further restriction of the stream by turbidity barrier or sheeting that will only increase these numbers, is it possible to use a temporary sheeting bid item for this project instead of turbidity barrier? | Temporary sheeting was not considered a viable option due to the shallow depth of bedrock in the streambed. | Mike Coleman | 2 | 2024-10-21 13:00 | 2024-10-22 06:46
20241112 | 20241112014 | 14 | Excavation Common | It appears the excavation common quantity for areas that are to be sub-graded (ie pipe trenches, patch areas, etc) is missing. Can the Department revise the excavation common qty to reflect the actual quantities that will be performed? | An addendum will be issued to revise the common excavation quantity to include excavation to bottom of subgrade for areas of full depth pavement replacement. Payment for excavation and backfill below bottom of subgrade for water main, storm sewer, and sanitary sewer is included in those items of work. | Mike Coleman | 1 | 2024-11-05 10:24 | 2024-11-05 14:45
20241112 | 20241112014 | 14 | Transformer Bases | The current lead time for item 657.0225, transformer bases, is 30 months. How does the project plan to handle this and other long lead time parts that will be unattainable before the project deadline? | WisDOT does not recognize a shortage in transformer bases at this time. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. | Mike Coleman | 2 | 2024-11-05 13:13 | 2024-11-06 17:30
20241112 | 20241112014 | 14 | Traffic Control Plans & HMA Pavement | Per the traffic control staging shown on Sheet 187 pavement will be placed to the center of the roadway. Per the striping/lane configuration there will be a new center turn lane, will pavement joints follow striping/lane configuration or traffic control plans? Does traffic control staging need to be adjusted? | The intent is to follow the traffic control staging typical sections (12-foot lane widths/pavement joints). | Mike Coleman | 3 | 2024-11-06 15:08 | 2024-11-07 09:40
20241112 | 20241112014 | 14 | HMA Pavement | The plans and/or special provisions do not specifically say if HMA Pavement will need to be placed prior to reopening intersections after its respective closure or in other asphalt patching areas. Please provide some detail on if base aggregate can be used to maintain pedestrian and vehicle traffic and if so, how long can it remain in place until asphalt paving should occur. | The â€Pedestrian Accessâ€ section of the Traffic article outlines requirements for pedestrian access. Surfaces accommodating pedestrian access need to be ADA compliant. Prior to reopening intersections after their respective closures, it will be required to place the lower lift of asphalt. The second closure allowed at sideroads for â€œfinal paving operationsâ€ is intended for placing the upper layer of asphalt. | Mike Coleman | 4 | 2024-11-07 08:49 | 2024-11-11 06:25
20241112 | 20241112015 | 15 | Geotechnical Report | Can the Geotechnical Report be made available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/g9gb7akx6ix67cgv2f1att7ttbnwfmbz or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-17 08:52 | 2024-10-17 13:26
20241112 | 20241112015 | 15 | Sewer Manhole SAN 2 | Will sanitary sewer manhole SAN 2 require an outside drop for the 8&quot; sewer? | Based on City spec 600 and Sanitary Sewer Details sheet â€œDetails of Drop Manhole for 30â€ Pipe or Smallerâ€ an outside drop would be required at SAN MH 2 location and is incidental to Sanitary Manhole 4-FT Diameter item. | Mike Coleman | 2 | 2024-10-31 15:54 | 2024-11-04 16:17
20241112 | 20241112015 | 15 | 8" water service | Will the 8&quot; water service and 8&quot; watermain pipe be incidental to the 12&quot; watermain? | There is no 8â€ watermain in contract and we are only connecting to existing 8â€ services. Any work including necessary fittings would be incidental to the applicable watermain item based on the Article 35 of the specials. | Mike Coleman | 3 | 2024-10-31 15:57 | 2024-11-04 16:16
20241112 | 20241112015 | 15 | Storm Sewer Gaskets | Are waterstop gaskets approved for connecting PVC storm sewer to the structure? | Per special provisions article 33, City specification 205 and 220, a watertight gasket is required at all pipe connections. | Mike Coleman | 4 | 2024-10-31 16:00 | 2024-11-04 16:17
20241112 | 20241112015 | 15 | Water services | Will the water services be reinstated for 1630 Losey, 1710 Losey, and at STA 34+90 for 2300 Green Bay? | The address 1630 Losey has its water service provided from Losey Blvd. No work required. The address 1712 Losey does not require a water service. The address 2300 Green Bay & 1710 Losey has its water service from the proposed 6-inch watermain. | Mike Coleman | 5 | 2024-11-01 14:57 | 2024-11-04 16:18
20241112 | 20241112015 | 15 | 8" Sewer Main | Bid item 194 is for 652 LF of 8&quot; PVC sewer. I can only find 40 LF at SAN 2 on the plan, is this a typo? | The item quantity should be 40 LF. An addendum will be prepared showing correct totals. | Mike Coleman | 6 | 2024-11-01 16:38 | 2024-11-04 16:15
20241112 | 20241112015 | 15 | Schedule and Work Duration | Could the Department share the design schedule? Based on what we are seeing, this work is not feasible in the timeframe per the Proposal. |  |  | 7 | 2024-11-11 14:27
20241112 | 20241112016 | 16 | Install Guardrail | Should there be an item for installation of salvaged guardrail or is that incidental to the salvage? Also, more footage may need to be salvaged to fit a 53&#39; temporary anchor on the existing guardrail. | Installation of salvaged guardrail is included in the Salvaged Rail bid item. See Article 15. Salvaged Rail, Item 614.0920 of the Special Provisions. The intent is to install the EAT terminal to the existing guardrail (posts 1 - 3 in the SDD), not a full EAT system. The limits of the removal shown on Sheet 7 of the plans allows for the 12.5 feet required for the EAT terminal. | Mike Coleman | 1 | 2024-10-28 06:11 | 2024-10-28 11:36
20241112 | 20241112016 | 16 | Safety fence item? | Good afternoon, with this project being located in a residential neighborhood with small children and a playground across the street, would the Department please consider adding a safety fence item, at least around the bridge construction area? | The roadway is barricaded off and closed for the construction of the bridge. There is no active sidewalk or crosswalk at this location. The contractor may elect to provide any additional protection they deem necessary to protect their worksite. | Mike Coleman | 2 | 2024-11-01 16:54 | 2024-11-05 09:50
20241112 | 20241112016 | 16 | East approach asphalt limits | Can the sawcut for the east side of the structure be moved to station 11+75 to allow room for construction activities? As drawn, the plan leaves 7&#39; of crane clearance to the sawcut after the abutment is properly excavated (assuming 30&#39; length &amp; swing radius). There is no place for the crane to move and allow excavator access without moving outside of project limits. Please note that the entire bridge will have to be built from one side, which will require a larger crane. | The allowable 50-ft roadway approach is a WisDOT standard. The roadway will be closed an additional 80-ft beyond the roadway sawcut providing additional working room for the contractor. | Mike Coleman | 3 | 2024-11-01 17:17 | 2024-11-05 09:51
20241112 | 20241112016 | 16 | Removal of existing 3 cell culvert | The existing structure is a 3 cell box culvert, with poured end walls. Currently the floor of the box is silted in on 2 cells (both dry) and cutoff walls extend across the length of the culvert, according to as-builts. Specifications would dictate that the contractor can leave structures 2&#39; below grade. Will this apply to the box culvert floor that is covered in fill? Can the cutoff walls below the culvert be left? | The entire floor of the existing box culvert shall be removed. The cutoff walls shall be removed to 2-ft below the natural streambed elevation. | Mike Coleman | 4 | 2024-11-01 17:36 | 2024-11-05 09:52
20241112 | 20241112017 | 17 | Borings - Geotechnical | Are there borings available for this project? | 13 borings logs from 1989 are located at the link below. The original pavement of this roadway is from 1941 and the roadway received one mill/overlay (1991) since then for which these borings were taken. The Geotechnical Reports can also be found at the following location: https://wisdot.box.com/s/1a5dtcaod4751hh2mia36rvrir8z1v0c or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-24 10:43 | 2024-10-30 06:47
20241112 | 20241112017 | 17 | Design Ton/CY Factors | What conversion factor (Ton/CY) was used for 3/4&quot; Base Aggregate, 1-1/4&quot; Base Aggregate and Breaker Run for this project? | 1.85 conversion factor (CY to Ton) was used for Base Aggregate Dense 3/4-Inch, 1 1/4-Inch, and breaker run. | Mike Coleman | 2 | 2024-10-24 10:50 | 2024-10-24 13:51
20241112 | 20241112017 | 17 | Existing 8" Reinforced Pavement | How is the existing 8&quot; Reinforced Pavement reinforced? Wire mesh or continuously reinforced with rebar? | The as-builts can be found at the following location: https://wisdot.box.com/s/1a5dtcaod4751hh2mia36rvrir8z1v0c or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-10-24 10:54 | 2024-10-28 06:37
20241112 | 20241112017 | 17 | Begin Work | When would work begin on this project? | Per the construction time chart, we assumed April 1, 2025. If weather permits and contractor is able to, they could start prior to that date. | Mike Coleman | 4 | 2024-10-24 12:12 | 2024-10-28 06:28
20241112 | 20241112017 | 17 | Transformer Base Breakaway Lead Times | How will the DOT be handling the nationwide shortage and 30 month lead time on the Traffic Bases? These bases only have one manufacturer and I have included some information below that came direct in a letter from the Akron Foundry Company&#58; &quot;There is a high demand for our Akron Foundry product line. The 30-month lead time has been unavoidable on our Traffic Bases.&quot; | WisDOT does not recognize a shortage in transformer bases at this time. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. | Mike Coleman | 5 | 2024-10-24 12:37 | 2024-10-30 07:16
20241112 | 20241112017 | 17 | CAD Files | Can you provide digital CAD files for this project? | Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One in Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 6 | 2024-11-05 08:49 | 2024-11-05 10:03
20241112 | 20241112017 | 17 | Traffic Control Stage 4 | What is the designers intent for traffic control in stage 4? Stage 1,2 and 3 have been detailed appropriately, however, a single page (250) was provided for stage 4. While I understand the road will be closed to through traffic, as noted in the special provisions on page 9 of 57, there must be some minimum standard of traffic control that is to be expected to assist and accommodate the local traffic. Additionally, without a minimum standard of design provided, is it safe to assume that the traffic control quantities represented in the MQâ€™s have adequately captured the need of the devices in stage 4? | The designerâ€™s intent is to completely close the Stage 4 Puetz Road intersection work area for construction without maintaining local access after implementing the detour route for STH 100. This stage is to be done either before or after the pavement replacement work to the east begins or is completed. The construction Project Manager is supportive of this method. Every property outside or within the construction limit has alternative access. The driveway at Station 50+85 ï¿½B, LT does not need local access during construction as the building is no longer there. Traffic control devises shown on Standard Detail Drawings listed on page 250 are anticipated to be adequate for traffic control in this stage in addition to the proposed detour. Traffic control devices shown on applicable Standard Detail Drawings are included in the Miscellaneous Quantity table. | Mike Coleman | 7 | 2024-11-05 17:00 | 2024-11-06 17:59
20241112 | 20241112017 | 17 | Concrete Surface Repair | If shotcrete is used for the surface repair, will a certified nozzleman be required? | Shotcrete would first have to be approved for use. If WisDOT is okay with it, then yes we suggest a certified nozzleman be required. | Mike Coleman | 8 | 2024-11-07 08:57 | 2024-11-12 08:43
20241112 | 20241112018 | 18 | Sheet 4 - Saddle Inlet Detail -33" dimension for a Type H-S Casting (24x36) | Sheet 4 - Saddle Inlet Detail shows a 33&quot; dimension for a Type H-S Casting (24x36). Please confirm if the proposal should include 33&quot; RCP pipe or 24x36 precast riser as the saddle. Thank you, | An addendum will be issued to update the construction detail for clarity. | Mike Coleman | 1 | 2024-10-10 09:43 | 2024-10-16 10:16
20241112 | 20241112018 | 18 | Joint ties required for 87"x136" C3 pipes | Are joint ties required for any / all joints of the 87&quot;x136&quot; HE pipe runs? Thanks | As currently represented in the plans and specifications, no joint ties would be required. The standard spec does not require joint ties when masonry endwalls are used (520.3.3(5)). | Mike Coleman | 2 | 2024-10-10 11:54 | 2024-10-14 08:44
20241112 | 20241112018 | 18 | Temporary Water Diversion Plan | The project plans and provisions indicate a Temporary Diversion Plan is required to be submitted with the ECIP. As witnessed on other projects with diversion channels, the design of the diversion was held to being capable of diverting the Q2 stream flows. Will the Temporary Diversion Plan in this contract be held to a Q2 water design to ensure the channel can carry all stream flows during the construction period? | See SPV.0060.03, Section C Construction, 5th paragraph, which indicates Q2 of 180 cfs. | Mike Coleman | 3 | 2024-10-29 14:09 | 2024-10-31 10:36
20241112 | 20241112018 | 18 | Additional Headwall Details | Please provide additional section view details for the proposed headwall on the inlet and outlet sides. There are no details for the upper header and lower header currently. | The current detail provided is a modified version of WisDOT SDD 8F10, Concrete Masonry Endwalls for Culvert Pipes. On the WisDOTâ€™s version of 8F10 there are no details for the upper header and lower header currently. The detail provided in our version should be enough to build the structure. Any additional viewpoints will not provide additional information. If there is something specific in question, please clarify. | Mike Coleman | 4 | 2024-11-05 11:15 | 2024-11-06 17:20
20241112 | 20241112018 | 18 | Design Schedule & Geotech Report | Can the geotechnical report and design schedule be provded? | The design schedule and Geotech Report can be found at the following location: https://wisdot.box.com/s/nhtlk240pne1zz9kbebp8uy7poqalpps or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 5 | 2024-11-05 17:43 | 2024-11-06 17:28
20241112 | 20241112018 | 18 | Structural Grout | Ready mix suppliers are not able to provide a ready mix non shrink grout. Due to the large quantity of structural grout required (105CY) is it acceptable to substitute this material with a standard ready mix grout? |  |  | 6 | 2024-11-11 17:05
20241112 | 20241112019 | 19 | Special Culvert HE Items | For item 0384, 0386, &amp; 0386, what is the intent of requiring a PE stamp for a pipe that is readily available? | Items 0384, 0386, and 0388, while readily available, are non-standard class IV pipe sizes. The PE stamp is required for the design of the pipe itself. An Addendum will be issued to clarify. | Mike Coleman | 1 | 2024-10-16 13:28 | 2024-10-17 12:22
20241112 | 20241112019 | 19 | Watering Seed and Sod | I can&#39;t tell from the plan, but does the schedule allow for 30 days of access to the completed side for watering the seeded or sodded areas before placing steady traffic on that side of the road? If not, what was determined as a solution for caring for thousands of square yards of sod while it is under constant traffic? | It is not recommended to delay a traffic staging switch for 30 days just for watering seed/sod. The contractor should determine the best sequencing and timing of all operations, including restoration, that meets the contract requirements as well as determine appropriate means and methods to accomplish the work. | Mike Coleman | 2 | 2024-10-21 14:56 | 2024-10-23 06:40
20241112 | 20241112019 | 19 | Borings - Geotechnical | Are there borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/0vgfva0pntbxfxq6ug9qpw27ekcu34l8 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-10-24 10:41 | 2024-10-28 06:34
20241112 | 20241112019 | 19 | Design Ton/CY Factors | What conversion factor (Ton/CY) was used for 3/4&quot; Base Aggregate, 1-1/4&quot; Base Aggregate and Breaker Run for this project? | Conversion factors assumed in the plans are: 3/4" Base Aggregate = 2.1 TON/CY 1-1/4" Base Aggregate = 2.3 TON/CY Breaker Run = 1.9 TON/CY | Mike Coleman | 4 | 2024-10-24 10:50 | 2024-10-28 06:39
20241112 | 20241112019 | 19 | Temporary Shoring B-67-401 | It appears there is a potential conflict with the temporary shoring shown between stages for B-67-401 &amp; the sanitary sewer as shown on Sheet 65. Was this conflict reviewed? Also, can the depth and size of the sanitary sewer be provided? | Temporary shoring locations shown on the plans are approximate and may be adjusted to fit field conditions. There is adequate space to shift the temp shoring and still accommodate traffic. The existing sanitary sewer at Sta. 104+50, 3â€™ LT is a 16â€ pipe, approximately 11-ft deep. Exact utility locations should be verified in the field. | Mike Coleman | 5 | 2024-11-04 06:41 | 2024-11-05 11:41
20241112 | 20241112019 | 19 | Breaker Run | Is the 234 ton of Breaker Run in the estimated quantities for B-67-401 included in the quantity for the Breaker Run bid item? | The 234 tons of Breaker Run shown in the B-67-401 miscellaneous quantities are not included in the Estimate of Quantities. An addendum will be issued | Mike Coleman | 6 | 2024-11-05 09:09 | 2024-11-06 06:07
20241112 | 20241112019 | 19 | DBE.bin File | We do not have access to the DBE.bin file for this project, which does not allow us to fill in the DBE section on the AASHTOware portal. Please provide. Thank you. | Please download the dbe.bin file from the letting/attachments portion of Bid Express. Select the letting then select the attachments. Download the dbe.bin file and save in the same folder on your computer that the proposal you are bidding on is located. If you have further questions, you can contact the bid let team at 608-266-1631. | Mike Coleman | 7 | 2024-11-08 12:24 | 2024-11-08 13:38
20241112 | 20241112020 | 20 | 513.4056 Railing Tubular Type H | Would steel railing be an acceptable alternate to the aluminum called out? Considering the the lack of availability for aluminum railing of this type and the small quantity required, availability may be problematic as new tooling may be required to produce. Pricing of steel will also be considerably more favorable for the owner. | Steel tubular railing conforming to departmentâ€™s Bridge Manual standard drawing is acceptable in lieu of aluminum tubular railing. The contractor has the option to select either steel railing or aluminum railing, both are acceptable. | Mike Coleman | 1 | 2024-11-05 10:24 | 2024-11-06 06:12
20241112 | 20241112021 | 21 | Start Date of Project | Do we know a date when the project will begin? | The contract does not require or restrict a specific start date. The time chart estimated 3/17/25 as a start date. The contract does include a 7/31/25 contract completion time and includes a 137 calendar days interim completion to close US 12. | Mike Coleman | 1 | 2024-10-10 08:34 | 2024-10-11 10:04
20241112 | 20241112021 | 21 | Culvert Pipe Backfill | Per the detail on sheet 22, the culvert pipe is to be backfilled with Trench Backfill from 1&#39; above the pipe to subgrade. Per section 520, trench backfill is roadway cut. Is it the Department&#39;s intent to use the native material, or should this be changed to a manufactured backfill (Grade 2 etc.)? | Use trench backfill per standard specification 520.2.5.3. | Mike Coleman | 2 | 2024-10-25 05:23 | 2024-10-30 06:51
20241112 | 20241112021 | 21 | Article 31 Concerning Guardrail Timing | Please consider deleting this article. It appears this will be a closed roadway and this isn&#39;t needed. Additionally, with the SS 614.3.1(1) in place, the milling and paving must occur before guardrail replacement. This leads to the repetitive train of guardrail removal, finished shoulders, and guardrail installation for each section of guardrail, all occurring late in the project. This article will severely limit the daily production and increase costs for both guardrail and shouldering, while simultaneously increasing risk. | Revisions to Article 31 will be included in an addendum. | Mike Coleman | 3 | 2024-11-05 09:40 | 2024-11-07 09:24
20241112 | 20241112021 | 21 | R-64-017 Designer | Do you have stamped shop drawings from the original project for this wall? We can&#39;t find a supplier that has an approved beveled face cap or a cap that is 8 inches tall. Additionally, with the information provided about this wall, we can&#39;t find an engineer that is able to provide a wall design or shop drawings for an existing wall that is only getting caps replaced, which aren&#39;t a structural component to the wall to begin with. | Shop drawings from the original project for this wall are not available. An addendum was issued to allow the use of two 4â€ wall caps as well as one 8â€ wall cap. | Mike Coleman | 4 | 2024-11-05 09:48 | 2024-11-11 08:23
20241112 | 20241112023 | 23 | Turbidity Barrier | Do you have the Q2 values for the anticipated high water values in order to calculate the turbidity barrier size? | The Q2 value used to calculate the turbidity barrier size is 613.45'. | Mike Coleman | 1 | 2024-10-22 11:09 | 2024-10-23 10:33
20241112 | 20241112023 | 23 | Construction Staking Structures | There is no bid item for staking structures. This will be needed to replace the deck. | The bid item 650.6501 Construction Staking Structure Layout will be added via addendum. | Mike Coleman | 2 | 2024-11-04 15:46 | 2024-11-05 09:54
20241112 | 20241112023 | 23 | Thickness of deck overlay. | HSI does not have asbuilts and only notes that there is an existing HMA overlay. How thick is the HMA overlay? | There are no As Builts for the HMA Overlay performed in 2010. The thickness is unknown. | Mike Coleman | 3 | 2024-11-04 15:48 | 2024-11-05 09:53
20241112 | 20241112024 | 24 | Traffic Control | Per the Traffic Control specifications, all operations require flagging. While concrete is curing day/night, do flaggers need to be present when no other operations are on-going or is the intent to only flag while contractors are performing work? | The intent is to flag when the contractor is performing work on site. During such time as curing, the contractor shall use traffic control devices such as temporary stop signs to direct traffic around the construction site. | Mike Coleman | 1 | 2024-10-14 13:07 | 2024-10-15 09:07
20241112 | 20241112024 | 24 | Design Schedule & Geotechnical Report | Can the design schedule and geotechnical report be provided? | The design schedule and Geotech Report can be found at the following location: https://wisdot.box.com/s/txbmdw62thc4vp450kefmtmztm4dqocg or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-11-05 17:44 | 2024-11-06 17:12
20241112 | 20241112025 | 25 | Removing Guardrail | Article 16 in the Specials is almost verbatim the standard spec for 614.0920 Salvaged Rail and 614.0925 Salvaged End Terminals. Can the use of standard bid items be used to replace the Removing Guardrail Special Article? | The removing guardrail bid item was amended in the special provisions to include end treatments, posts, hardware and railing are to be removed and salvaged for Washington County pick up. No removed guardrail, end treatment, posts, or hardware shall be used on the project. | Mike Coleman | 1 | 2024-10-22 12:52 | 2024-10-24 06:32
20241112 | 20241112025 | 25 | Piling through existing substructure | Why is this bridge designed for the new piling to go through all of the existing substructure units? This adds significant cost to the project when it appears there is room to adjust the pier locations. | The bridge superstructure depth was a significant factor in the design. A slab superstructure was the only type that would prevent the low chord from being lowered within the main portion of the channel. To avoid impacting the existing piers, the proposed structure would need either longer end spans or to be configured as a four-span bridge. Based on the total bridge length, BOS required a balanced span configuration, resulting in a main span length of 70 feet, which positioned the proposed piers within 2 feet of the existing ones. If a four-span configuration were chosen, additional piers would need to be constructed within the water, increasing costs. Moreover, the Wisconsin Department of Natural Resources (WDNR) preferred not to reduce the main span of the bridge. Additionally, the existing footings are not supported on piles, so driving new piles was not a concern. | Mike Coleman | 2 | 2024-11-01 14:50 | 2024-11-04 16:05
20241112 | 20241112025 | 25 | Removing Structure B-66-944 | In B-66-147 structure plans, the notes states, â€œExisting structure B-66-944â€¦ The Entire Structure is to be removedâ€ &amp; â€œDuring removal of the existing bridge substructure, remove all footing concrete that is conflict with the proposed piling at piers &amp; abutmentsâ€. Based on the first note, it appears that all the substructures must be fully removed. Based on the second note, it appears that there may be allowance for only removal of substructures in conflict with proposed piling. What is the removal intent for substructures? | The intent is to fully remove the pier footings. While only a portion of the existing pier footings are in conflict with the proposed piles, the DNR requested that the entire pier footings be removed. Regarding the abutments, the intent is to remove the portion of abutment footings that are in conflict with the proposed piles per standard spec 203.3.1(1). All other portions of the abutments are to be removed to an elevation at least 2 feet below finished ground line per 203.3.2.2.1(2). | Mike Coleman | 3 | 2024-11-04 06:52 | 2024-11-06 06:13
20241112 | 20241112025 | 25 | B-66-147 Abutments | Removal of existing abutment footings (in conflict with proposed piling) will require excavation at depths near 13-ft below proposed abutment footings &amp; nearly 9-ft below observed water. The structure plan notes say â€œCofferdams are intended for removal of existing pier footingsâ€. Assuming abutments will also require cofferdams to complete excavation through water, how will the abutment cofferdam be paid? Additionally, the notes say â€œExcavation below abutmentâ€¦ requires engineer approvalâ€ â€“ this seems unnecessary given the plans require excavation below proposed footing to remove existing footing. Would the same breaker run be required at the abutment to fill in the over-excavated area? | The intent is to fully remove the pier footings. While only a portion of the existing pier footings conflict with the proposed piles, the DNR requested that the entire pier footings be removed. Given the depth of the excavation within the river, cofferdams were anticipated to be used at the piers. Regarding the abutments, the intent is to remove the portion of abutment footings that conflict with the proposed piles per standard spec 203.3.1(1). All other portions of the abutments are to be removed to an elevation at least 2 feet below finished ground line per standard spec 203.3.2.2.1(2). The bid item Excavation for Structures Bridges includes excavation to the depth as required to allow for removal of the portion of the existing abutment footing that conflicts with proposed abutment piles. The General Note â€œExcavation below abutmentâ€¦requires engineer approvalâ€ is a standard WisDOT BOS design note. The design did not anticipate cofferdams for removal of the existing abutments, but that does not preclude the use of cofferdams at abutments as a means of construction. Cofferdams are measured by each bridge structure and should be bid accordingly. Breaker run is not required for backfill at abutments. Reuse of excavated material after removal of the portion of the existing footing that conflicts with proposed piles is permitted per standard spec 206. In lieu of reusing excavated material, the contractor may substitute a granular material as approved by the engineer. Backfilling and compacting the space excavated and not occupied by the new structure is included in the bid item Excavation for Structures Bridges. | Mike Coleman | 4 | 2024-11-04 06:59 | 2024-11-06 06:15
20241112 | 20241112025 | 25 | Removing Structure | The general notes state that the entire structure is to be removed. The notes also state that all footing concrete in conflict with piling are to be removed. Can you verify that the intent is to remove the entire structure to within 2&#39; below finished grade and any additional portion in conflict with new piling/substructure. | The intent is to fully remove the pier footings. While only a portion of the existing pier footings are in conflict with the proposed piles, the DNR requested that the entire pier footings be removed. Regarding the abutments, the intent is to remove the portion of abutment footings that are in conflict with the proposed piles per standard spec 203.3.1(1). All other portions of the abutments are to be removed to an elevation at least 2 feet below finished ground line per 203.3.2.2.1(2). | Mike Coleman | 5 | 2024-11-04 14:13 | 2024-11-06 06:16
20241112 | 20241112025 | 25 | Completion Date | Please extend the completion date for this project by two months. The four month time frame to complete this project seems unnecessarily short for a county road. |  |  | 6 | 2024-11-11 09:38
20241112 | 20241112026 | 26 | Data Pack | The datum provided is very jumbled, with peaks and valleys through the entire surface provided. Can someone look at it to see if an accurate datum surface is available? | Updated surface file and cad drawing can be found at the following location: https://wisdot.box.com/s/hh5pjmhop5u9cmdz5hvrbzeiokvo7lu1 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-28 10:15 | 2024-10-30 06:49
20241112 | 20241112026 | 26 | Datum | The datum provided has curb and gutter and finished pavement info on the subgrade. There are points on the model which are 2-5 ft down from where subgrade should be. Could someone please review the datum provided and make corrections. The &quot;jumps&quot; are not just the reconstruct vs pvmt replacement areas. |  |  | 2 | 2024-10-30 09:05
20241112 | 20241112026 | 26 | Aggregate Conversion Factors | What are the conversion factors that were used for the 1.25 Inch ; Select Crushed; 3/4 Inch aggregates? Also was the Select Crushed expanded before determining the qty. on the Aggregates table? I see that the EBS qty will be. | The following conversion factors were used: Base Aggregate Dense 3/4-Inch = 2.1 (Tons/CY) Base Aggregate Dense 1 1/4-Inch = 2.0 (Tons/CY) Select Crushed Material = 1.9 (Tons/CY) Select Crushed quantities were not expanded. EBS was expanded as noted in the earthwork miscellaneous quantities table. | Mike Coleman | 3 | 2024-11-04 08:43 | 2024-11-05 11:40
20241112 | 20241112027 | 27 | EBS C-44-153 | For structure C-44-153, the notes state the approximate limits of EBS under the new structure. The notes also indicate that all cost for EBS is to be included in the excavation for structures pay item. Will the Department follow spec 205.5.2.3 for any quantity overruns in regard to the planned approximate EBS limits? | Additional excavation will be paid for extra work as described in Section 206 of the Standard Spec. | Mike Coleman | 1 | 2024-10-14 13:11 | 2024-10-21 10:15
20241112 | 20241112027 | 27 | CAD Files | Can you please provide CAD files for both overpasses? |  |  | 2 | 2024-10-18 10:01
20241112 | 20241112027 | 27 | Town Roads | Are the contractors responsible for maintaining Holland and Vanderbroek Roads as those are the only access roads to the project? Is Evergreen Drive an acceptable road to haul on? Can we utilize Pogrant Road? |  |  | 3 | 2024-10-18 10:04
20241112 | 20241112028 | 28 | Geotechnical Report | Is there a geotechnical report available for this project? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/3pkn2mfgg4yieiyc4iinfspuj8mnv2j1 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-18 13:25 | 2024-10-21 13:19
20241112 | 20241112028 | 28 | Schedule | The specifications state that Contract 1225-10-72 will have the site prep completed by May 30, 2025. Is there a schedule that can be shared showing the current status of the work associated with contract 1225-10-72? | The design schedule can be found at the following location: https://wisdot.box.com/s/3pkn2mfgg4yieiyc4iinfspuj8mnv2j1 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-10-18 13:26 | 2024-10-21 13:31
20241112 | 20241112028 | 28 | Sheet 162 Ground Level Lighting Plan | On Sheet 162 Ground Level Lighting Plan, Area B the lighting and some of the devices appear to be showing twice. Itâ€™s hard to tell if some of the wall devices are accidently shown twice or if there are actually two devices in the area. Could we get an updated drawing clearing this up? | Sheet 162 did have a plotting issue where fixtures were shown twice. The sheet has been updated and will be processed in an addendum. | Mike Coleman | 3 | 2024-10-18 13:27 | 2024-10-23 07:14
20241112 | 20241112028 | 28 | Lighting Schedule | On Sheets 161 and 162, there is a fixture type L2W shown. There is nothing in the lighting schedule Sheets 172-174 listing this fixture type. Can you add the L2W fixture type to the schedule? | An addendum will be provided to update the light designation as L3R on sheets 161-162. The schedules do not require an update. L3R is included in the lighting schedule. | Mike Coleman | 4 | 2024-10-18 13:29 | 2024-10-23 06:47
20241112 | 20241112028 | 28 | Northern Long-eared Bat | Regarding the Northern Long-eared Bat (page 3 of 622)&#58; The opening paragraph says that â€œ[i]f an individual bat or active roost is encountered during the construction operations, stop work, and notify the engineer and the WisDot Regional Environmental Coordinator (REC).â€ What is the standard protocol? Does all work cease until the bat is out of harms way or REC shows up? If construction operations are delayed waiting on the REC, how does this effect the scheduling? Will time be â€œgiven backâ€ to the general contractor? For example, if construction is shut down for ï¿½ day, will ï¿½ day be added to the intermediate and/or final completion dates? Will there be some sort of training to crews and staff on site to help identify a Northern Long-eared Bat versus other species? If so, when will this occur? | An additional inspection for the NLEB was recently conducted and found no presence of the species within the rest area buildings. With no presence of the species from two inspections, it is considered a very low risk that a bat would be present when demolition of the buildings occurs. If the NLEB is present, US Fish and Wildlife allows as many as five NLEB to be disturbed after coordination with the WisDOT engineer and REC. Demolition work must cease to allow the species of bat to be determined and additional coordination will be required for removal/displacement of the bats. Training for contractor staff will not be provided. The WisDOT construction engineer will coordinate with the contractor to determine the duration of the work disruption. The duration of the disruption will be negotiated as a change of work schedule relative to each construction contract and will extend the associated interim and project completion dates. WisDOT will be responsible for any bat identification. | Mike Coleman | 5 | 2024-10-23 13:38 | 2024-10-29 06:47
20241112 | 20241112028 | 28 | SECTION 03 45 00 2.8, B ARCHITECTURAL PRECAST CONCRETE (APC) | Please confirm 2.8, B. Pointing Grout information (as well as APC designation on sheet A520) indicating â€œPointing Grout â€“ Concave Tooledâ€ brick joints. It is assumed that this is not a manual operation required at all brick joints but rather a detailed description of the brick joint profile required through the use of the brick formliner as described in 2.13, C. Bond Pattern. | As this language is noted in the Architectural Precast Concrete spec, yes, the appearance of concaved tooled joints will occur with the precasting operation and is not a manual operation. | Mike Coleman | 6 | 2024-10-24 10:36 | 2024-10-30 07:13
20241112 | 20241112028 | 28 | SECTION 03 45 00 2.17, D., 3. ARCHITECTURAL PRECAST CONCRETE (APC) | Please confirm 2.17, D., 3. Interior (back of panel) finish texture of the precast panels. Is the light sandblast texture required for paint and tile bond? Would a standard troweled finish be acceptable? | Surfaces with a tile finish must be sandblasted for tile bond per the tile surface preparation requirements. Surfaces with a paint finish can be sandblasted or other uniform finishes may be applied. | Mike Coleman | 7 | 2024-10-24 10:37 | 2024-10-30 07:15
20241112 | 20241112028 | 28 | TA-11 Adult Changing Specs | Some accessories on the plan are not in the spec like TA-11 adult changing. Are these to be owner furnished? | The specification for the adult changing table was added through Addendum 1. | Mike Coleman | 8 | 2024-10-25 08:55 | 2024-11-05 14:38
20241112 | 20241112028 | 28 | Well Pumps | Sheet 31 shows 2 well pumps with conduits and wiring going to them. Sheet 171 in the schedules has well pumps #1 and #2 noted as a conduit stubbed out for future. Are these drawings related? If so can you confirm what is the correct way to take off for the wells. | Sheet 31 provides the layout of the electrical to each well and the minimum conductor size based on the required well pumps. This is related to the well pumps listed in the schedule on Sheet 171. The wire is not detailed in the schedule as conductor size may vary depending on the provided pump manufacturerâ€™s requirements. Installation of conduit and wire to the well pumps is included with the Well System Controls. | Mike Coleman | 9 | 2024-10-29 08:10 | 2024-10-30 18:12
20241112 | 20241112028 | 28 | Spec section 26 05 33 Conduits Part 3.1 | Spec section 26 05 33 Conduits Part 3.1 C #4 notes exposed Interior runs below 10â€™ above finished floor must be IMC or RMC unless otherwise indicated. Would Mechanical Room 118 fall under this Spec? Or because there are electrical panels in the room can it be considered an electrical room like what is noted under 3.1D which states exposed EMT maybe used in electrical rooms. | Per 3.1D 2a, EMT is acceptable floor to ceiling in Room 118. | Mike Coleman | 10 | 2024-10-29 08:11 | 2024-10-31 10:34
20241112 | 20241112028 | 28 | Exterior Lighting | Who is to supply the Exterior Lighting Control Panel that is shown on drawing 166? Is there any info on what type of panel this needs to be? | The exterior lighting cabinet is shown for reference as it is provided power from inside the comfort building and location needs to be coordinated for conduit and power feed. The cabinet will be provided and installed under the 1225-10-72 contract. It is not included in this let. | Mike Coleman | 11 | 2024-10-29 08:11 | 2024-10-30 17:53
20241112 | 20241112028 | 28 | Interim Completion and Liquidated Damages | Weâ€™re looking for clarification on the extent of work required to be completed by August 29, 2025. Is it correct that the intent is to have the building and utilities completed to a point where no additional digging is required, allowing site work from contract 1225-10-72 to continue? Is it expected that the buildings are completely enclosed at this point? | The intent of work to be completed by the interim completion date is that the underground utility work associated with ID 1225-10-73 is substantially completed such that any incomplete work does not impeded work under ID 1225-10-72. Excavation may still be required and performed, but it shall not impact operations under ID 1225-10-72. Similarly, with enclosure of the building, there may be additional work remaining on the exterior of the building after the interim completion date. The remaining work shall not impact operations under ID 1225-10-72. Plan sheets 181 and 182 depict a work zone around each comfort building that is assigned under contract 1225-10-73. Coordination will be required with ID 1225-10-72 where the contracts interact. | Mike Coleman | 12 | 2024-11-01 11:13 | 2024-11-04 16:02
20241112 | 20241112028 | 28 | 3 Inch Copper | Is an alternate material allowed to be used in lieu of 3 inch copper for the water service (SPV.0090.01)? 3 inch copper is uncommon for underground utilities. For this reason, they do not make compression couplings for 3 inch copper. Also, soldering copper for underground use is typically prohibited. Could a material such as 4&quot; ductile iron pipe or 4&quot; C-900 PVC pipe be utilized in lieu of 3 inch copper? Note&#58; They do make compression couplings for 2 inch copper if that would meet the demand. | The copper lines were specified for the project based on the standard used at all other rest area facilities around the state. Provide a bid based on the items as shown in the plan and specifications and an alternative product can be reviewed during construction operations assuming bidder is the successful low bidder. | Mike Coleman | 13 | 2024-11-04 12:53 | 2024-11-05 14:34
20241112 | 20241112028 | 28 | Air Separator Verification and Inline Circulator Pump Manufacturer Approval | On the air separator schedule in the mechanical drawings system flow is 150 GPM and 500 GPM for both air separators but the Pipe size is 2&quot;. That is too much flow going through a 2&quot; pipe. So I wanted verification on if the air separator should sized for the flow or the pipe size given. In the spec section 23 21 23 Hydronic Pumps part 2.1 In-Line Circulators B&amp;G is not a listed manufacturer. I wanted to know if B&amp;G would be approved. | Both air separators, AS-01 and AS-02, should be line size, 2â€. Flow through AS-01 is 21.0 GPM and AS-02 is 60.0 GPM. A plan sheet update will be processed through an addendum. B&G is an acceptable hydronic pump manufacturer. | Mike Coleman | 14 | 2024-11-04 16:05 | 2024-11-06 17:54
20241112 | 20241112028 | 28 | Sanitary Sewer - Site | Special provisions for SPV.0090.03/04 under C. Construction say that we are to test each section of sewer per Standard Spec 607.3.5. What specification is this referencing? Current DOT specs do not have a 607 section? | The specification will be updated via addendum to address the change from 607.3.5 to 608.3.5. | Mike Coleman | 15 | 2024-11-05 08:03 | 2024-11-05 14:46
20241112 | 20241112028 | 28 | Sanitary Sewer - Site | The special provisions for SPV 0090.03/04 Sanitary Sewer 6&quot;/8&quot; list a material for the bedding. But under the measurement and payment it says &quot; includes fittings, frost protection and GRANULAR BACKFILL, &quot; My question is what we are backfilling with? According to the special provisions for the water lines we are using native which is why I am confused because they are in somewhat the same areas. | The specification will be updated via addendum to furnish trench backfill material conforming to 209.2 or 520.2.5.2. | Mike Coleman | 16 | 2024-11-05 08:09 | 2024-11-05 14:49
20241112 | 20241112028 | 28 | Exterion Water Lines | Special provision refer to 607.3.5 what spec is this? | The specification will be updated via addendum to address the change from 607.3.5 to 608.3.5. | Mike Coleman | 17 | 2024-11-05 08:10 | 2024-11-05 14:47
20241112 | 20241112028 | 28 | Slab thickness | Drawing S201 (page 109) What is the slab thickness for the interior of the building and the stoop area in front of the overhead door. | The thickness is shown as 6â€ in Detail A2 on sheet 87. | Mike Coleman | 18 | 2024-11-05 12:05 | 2024-11-11 10:01
20241112 | 20241112028 | 28 | Carpet for Offices | Do you have any information on the carpet for the offices? | The specification for CPT1 was inadvertently omitted from the schedule and the specifications. The basis of design product is a carpet tile, â€œKinetex Strata 1826â€ by J+J Flooring. Color: 1848 Feldspar. Pattern: parquet or similar. This will be addressed through a specification update in an addendum. | Mike Coleman | 19 | 2024-11-05 12:09 | 2024-11-06 17:55
20241112 | 20241112028 | 28 | Flooring Interior Finish | Elevation sheets A250 &amp; A253 are calling out T5 and T4. Since these are not on the interior finish legend, shall I just figure with T3? | Tile references using T4 and T5 are replaced with T3. This will be detailed in an addendum. | Mike Coleman | 20 | 2024-11-05 12:11 | 2024-11-06 17:56
20241112 | 20241112028 | 28 | Power for well | Does project 1225-10-73 include getting power to the well and other items or is this solely just the buildings? | Power to the wells is included in Well System Controls, Item SPV.0060.14. Extending power to the pump is included in Well Pump, Item SPV.0060.15. | Mike Coleman | 21 | 2024-11-05 13:57 | 2024-11-06 17:17
20241112 | 20241112028 | 28 | Truss bearing elevations | Please advise where to find the truss bearing elevations for the picnic shelters? | Trusses bear on framing member B1 and B2 that are 9â€™-0â€ above the slab as shown on sheets 9 and 10. | Mike Coleman | 22 | 2024-11-06 08:17 | 2024-11-07 05:50
20241112 | 20241112028 | 28 | Wood Framing Details | Please provide details showing connections for LVL Hips, Ridges and the roof system. | Design of the SIP roofing system is a delegated design item. SIP diaphragm loads are provided in the contract documents; nailing to the framing is developed by the SIP manufacturer and issued as a submittal. Similarly, specific framing connectors are submitted as shop drawings; guidelines for those connectors are provided in the notes and specifications. | Mike Coleman | 23 | 2024-11-06 14:05 | 2024-11-11 06:35
20241112 | 20241112028 | 28 | Wood Framing Details | Please provide detail for â€œVertical Fascia-PT3â€ called out on A412. | Fascia detail is shown on Sheet 86, Detail B2. | Mike Coleman | 24 | 2024-11-06 14:06 | 2024-11-08 11:03
20241112 | 20241112028 | 28 | Wood Framing Details | Main Building â€“ Page 77, 79 â€“ Notes on Drawing Stating â€œ Sloped Roof Soffit Above - PT-4â€. Provide detail for material. | The material is detailed in multiple sections including A1 and B1 on sheet 86 and as described in Section 06 16 43 GYPSUM SHEATHING. | Mike Coleman | 25 | 2024-11-06 14:06 | 2024-11-07 09:27
20241112 | 20241112028 | 28 | Wood Framing Details | Page 10, Eave Details at Picnic Shelters â€“ Does Outside &amp; Inside Corners of Fiber Cement Panels for Ceilings &amp; Beams get 1x3 trim? | Outside and inside corners shall receive trim as needed to cover seams and joints. | Mike Coleman | 26 | 2024-11-06 14:07 | 2024-11-07 05:51
20241112 | 20241112028 | 28 | Spec Section 23 25 13 | Sheet 601 and 132&#58; It appears the entire system is glycol, however Sheet 132 the ground source heat pump schedule calls for water. In spec section 23-25-13 the glycol mix is 40% on page 492 the following page(493) list glycol mix at 50%. Can we have the glycol mix percentage confirmed and if the entire system is to contain glycol? | 40% propylene glycol should be provided for the entire system including the ground loop piping system and the in-floor heating piping system. The specification is modified by addendum. The â€œwaterâ€ reference on Sheet 132 is to the mixture. | Mike Coleman | 27 | 2024-11-06 14:08 | 2024-11-11 06:36
20241112 | 20241112028 | 28 | Lobby 100 Epoxy Terrazzo | The extents of TER1 and TER2 in lobby 100 are unclear based on the pattern shown on sheet I101. Please clarify. | TER1 is the primary application with TER2 as the smaller accent area shown with shading. It is noted on Sheet 102 where the patterns ALIGN to floor plan locations. Additional dimensions are shown on Sheet 71. | Mike Coleman | 28 | 2024-11-06 14:08 | 2024-11-08 06:36
20241112 | 20241112028 | 28 | Grille & Diffuser Schedule | Please provide a schedule for the Grilles and Diffusers. | A grille and diffuser schedule will be provided by addendum. | Mike Coleman | 29 | 2024-11-06 14:13 | 2024-11-11 06:22
20241112 | 20241112028 | 28 | Grilles & Diffusers | There is no Grille and Diffuser schedule in the Mechanical plans. Can one be provided? | A grille and diffuser schedule will be provided by addendum. | Mike Coleman | 30 | 2024-11-06 14:29 | 2024-11-11 06:24
20241112 | 20241112028 | 28 | Wells | Who is responsible for the Fees and the Submittal of the High Capacity Well Permit to the WDNR? This review process can take up to 6 months, at the various review sections of the DNR. Who is responsible for pump removal &amp; abandonment the two existing wells at the sites? There is not a line item for this, and that work will need to be completed. Item 0018 Well Screen. The wells are bedrock formation wells and are cased through the unconsolidated materials. A well screen does not apply to the four new wells. Should we disregard that line item? Based on my calculations of the grout (item 0020), the amount is lower than what will be required to fill 580â€™ of annular space for the four 12â€ diameter holes with 8â€ casing. I recommend 280 total bags (255cu/ft) of neat cement grout, which includes 30% loss in the formation of any fractures encountered. Maybe I missed it, but did not see a listing in the Davis Bacon Wage Determination for a â€œWell Driller/Pump Installerâ€ In the past there were listings similar to&#58; WELL DRILLER.....................$ 16.52 3.70 Please provide a listing or confirm a rate. |  |  | 31 | 2024-11-07 08:53
20241112 | 20241112028 | 28 | WD-1 | lease verify that drywall furring grid is fine at all GWB-1 locations as there appears to be some cross section discrepancies that show steel stud framing. Please verify whether or not the furring grid will be acceptable be installed at the areas that call out WD-1 panel finish If furring grid is not acceptable for WD-1 locations please verify an acceptable stud size and gauge for framing as we do not have structural or engineered drawings. Please verify that GWB-2 finish on the exterior soffits of the building is correct. Not sure how you would finish and paint Densglass to hold up outside. | 1. A drywall furring grid is acceptable for interior gypsum board ceilings. Note that penetrations of the SIP above must be sealed to prevent vapor drive. 2. The wood panel system base product as a proprietary suspension system. Supplier should provide shop drawings with member sizes. 3. Section 06 16 43 was omitted soffit board in error. Exposed exterior gypsum board to be finished should be exterior gypsum soffit board. The following will replace A. in 2.2 MATERIALS via addendum: A. Exterior Gypsum Soffit Board: 1. ASTM C1396/C1396M with manufacturerâ€™s standard edges. 2. Type X, 5/8â€ thick. 3. Taper long edges. 4. Joint sealant: use setting-type taping compound and setting-type, sandable compound. 5. Base Product: a. â€˜Exterior Soffit Wallboardâ€™ by American Gypsum Company. | Mike Coleman | 32 | 2024-11-07 09:37 | 2024-11-11 06:29
20241112 | 20241112028 | 28 | Plumbing Fixtures WDF-1 and S-1 | Regarding plumbing fixtures WDF-1 and S-1&#58; they show a WDF-1 in the custodial closets and a S-1 in the break area. However, I am not seeing a WDF-1 or S-1 called out on the fixture schedule. Please clarify. | The fixtures have been added to the schedule. This is detailed in an addendum. | Mike Coleman | 33 | 2024-11-07 13:58 | 2024-11-11 06:36
20241112 | 20241112028 | 28 | Tile T1 and T2 | Virginia Tile, the distributor for the (T1 &amp; T2) Laminam panels do not have the panel size that was specified. They can only get the 1 M x 3M size. Is the 1M x 3M size acceptable? | The following sizes and thicknesses are acceptable. Sheet 100 will be updated via addendum. T1 Bianco Size: 1620 x 3240 mm, thickness 5mm T2 Terracotta Size: 1000 x 3000 mm, thickness 3mm | Mike Coleman | 34 | 2024-11-08 06:12 | 2024-11-11 06:28
20241112 | 20241112028 | 28 | Well Permit | Who is responsible for the cost associated with the High Capacity Well Permit? | The Contractor applies on behalf of the state is responsible for submittal and fee. DNR said the contractor should do it, not the designer. | Mike Coleman | 35 | 2024-11-11 07:03 | 2024-11-11 10:02
20241112 | 20241112029 | 29 | Soil Borings | There is a table in the plan with information for soil borings location, but information of the material in the borings is missing. Can that be provided? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ym2oer55btiioq6jttwgrw37gb6wc5a4 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-23 16:00 | 2024-10-28 06:32
20241112 | 20241112029 | 29 | Select Borrow Alternative | Will Select Crushed Material be allowed as an acceptable alternative for Select Borrow, Proposal Item #20? | An addendum will be issued to allow material substitutions under the Select Borrow item. | Mike Coleman | 2 | 2024-10-28 14:50 | 2024-10-30 18:49
20241112 | 20241112029 | 29 | Maintain 15' access Road | Will the department require a safety edge/slope next to traffic when maintaining a 15 foot wide access road as stated in the special provisions? Parts of Hwy Z are being lowered a good amount and will be difficult to maintain a 15 foot wide access road with a safety edge. | Standard spec 104.6.1.2.3 should be followed for drop off protection adjacent to the access road. | Mike Coleman | 3 | 2024-11-05 11:05 | 2024-11-06 06:11
20241112 | 20241112030 | 30 | Temporary Shoring | What train loading will be required for the temporary shoring at 81+88? Does the railroad have any requirements regarding allowable displacements? If survey of the existing track is required prior to temporary shoring, how will the movement monitoring be paid? | The Notice to Contractor â€“ Wisconsin Central LTD (CN) Application for Utility Occupancy special provision article references the CN Southern Region Utility Crossing/Encroachment Application Packet which may be viewed at https://www.cn.ca/-/media/files/delivering-responsibly/safety/utility-installation/utility-crossing-encroachment-application-packet.pdf. The application packet identifies the requirements for the utility occupancy, including loading requirements for shoring. Requirements of the railroad, including but not limited to allowable displacements and potential monitoring of the tracks, are anticipated to be identified as conditions of the final utility occupancy permit. The Contractor shall bear all costs for complying with these requirements as identified within the Notice to Contractor â€“ Wisconsin Central LTD (CN) Application for Utility Occupancy special provision article. | Mike Coleman | 1 | 2024-11-05 06:30 | 2024-11-06 17:49
20241112 | 20241112031 | 31 | Storm Sewer Removals | Does the DOT have storm sewer as-builts that shows the pipe sizes on it. Trying to figure out the storm removals and it is extremely difficult to determine what size is where, whether or not the various sizes are in common trench with the new installation. The misc quantity sheet only helps so much. The breakdowns given cover such a total footage over a fairly large station length. Thanks | We do not have storm sewer as-builts. We used Neenah GIS and survey information to determine the existing storm sewer sizes. Remove SS pipe is shown on the storm sewer sheets with a hatch pattern. This visually shows where the removal and new are located and when they overlap. The removal pipe sizes are shown in the miscellaneous table. | Mike Coleman | 1 | 2024-11-04 17:05 | 2024-11-05 11:42
20241112 | 20241112032 | 32 | schedule | Could the proposed schedule be provided for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/39mkj99pojjom3tw6cxetiqapltnnnqm or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-10-24 21:42 | 2024-10-28 11:53
20241112 | 20241112032 | 32 | Schedule | The schedule provided shows the Temporary Shoring going in in the beginning of May. There is not instream disturbance allowed before June 16th. This doesn&#39;t seem to corelate to the special provisions. If that work wouldn&#39;t start until June 16th this would push the project back at least 1 month. Please clarify. | The intent is for the temporary shoring to be located on the shore just outside of the stream, it is to ensure that the excavation for the abutments (~2.5â€™) does not cause any disturbance to the stream. The temporary shoring should remain in place after project completion so as not to cause stream disturbance as well. | Mike Coleman | 2 | 2024-10-28 12:40 | 2024-10-30 06:50
20241112 | 20241112032 | 32 | Utility Work Plan | Please provide the utility work plan for OH utilities along the Mullet River Path including detailed information regarding the location of known discontinued, relocated, or removed utility facilities. | The utility work plans can be found at the following location: https://wisdot.box.com/s/39mkj99pojjom3tw6cxetiqapltnnnqm or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-11-04 14:53 | 2024-11-11 06:33
20241112 | 20241112032 | 32 | Geotechnical Report | Can the geotechnical report be provded? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/39mkj99pojjom3tw6cxetiqapltnnnqm or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 4 | 2024-11-05 17:45 | 2024-11-07 12:43
20241112 | 20241112032 | 32 | Mullet River MSE wall backfill | Looking into the fill quantity for the area where the walls are, it seems like the area where the MSE wall backfill has also been included in the fill quantity. Could this be verified? | We have confirmed that the MSE wall backfill has not been included in the fill quantity. | Mike Coleman | 5 | 2024-11-06 14:22 | 2024-11-07 09:41
20241112 | 20241112032 | 32 | Timber Railing | Would the department accept Red Pine with the same treatment process in the specifications for the wood used on the timber railing item? | The contractor should prepare their bids based on the wood species called out in standard spec. 507.2.2. No modification will be made to the bid item. | Mike Coleman | 6 | 2024-11-07 08:18 | 2024-11-08 05:55
20241112 | 20241112035 | 35 | Pile points? | Based on prior experience and the layer of sandstone shown in Boring #1, would the Department consider adding pile points to the south abutment? | Pile points will not be added. | Mike Coleman | 1 | 2024-11-03 10:50 | 2024-11-04 16:08
20241112 | 20241112035 | 35 | Railing Tubular Type M bid quantity | According to the drawings plans there are 155 LF (154â€™-8 ï¿½â€) of Tubular Railing Type M. But line 0038 indicates a quantity of 150 LF. Which of these quantities is the correct one? | Yes, this is supposed to be 155 LF. We will issue an addendum. | Mike Coleman | 2 | 2024-11-05 14:09 | 2024-11-06 06:09
20241112 | 20241112035 | 35 | Plan quantities for rebar do not match bill of bars | Hi, The bid quantities for the project include 9,015lbs of plain rebar, but the bill of bars indicates all rebar in the structure is to be coated. Our rebar supplier is finding a different quantity of coated bar than the bid quantity as well. Can these quantities and the bill of bars please be checked for accuracy? | â€¢ We will issue an addendum to correct the discrepancy between the two steel types. Corrected values are as follows: o 505.0400, Bar Steel Reinforcement HS Structures: 3,380 LB o 505.0600, Bar Steel Reinforcement HS Coated Structures: 23,040 LB | Mike Coleman | 3 | 2024-11-08 07:48 | 2024-11-08 13:40
20241112 | 20241112036 | 36 | Borings- Geotechnical | Is there a geotechnical report that the department can provide for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/pxxhoocy00n5538dl9u2cr7r29gss6d1 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-28 09:47 | 2024-10-28 13:08
20241112 | 20241112036 | 36 | CAD Files | Can the department provide the CAD files for this project? | This is a local program project. On local program projects, there is no requirement for contractor data packets. | Mike Coleman | 2 | 2024-10-28 09:48 | 2024-10-28 12:14
20241112 | 20241112036 | 36 | Item 625.01 Topsoil | Will Salvaged Topsoil be acceptable for use under Bid Item 625.01-Topsoil? | Salvaged topsoil is acceptable for bid item 625.0100 provided it meets the required specifications. Additional topsoil will be necessary for areas where salvaging is not feasible. | Mike Coleman | 3 | 2024-11-04 13:45 | 2024-11-05 11:38
20241112 | 20241112037 | 37 | HMA | Would the department consider changing the Asphalt pay item to Asphaltic Surface with a Special Provision stating the lower layer needs to be 2MT 58-28S and the upper layer needs to be 4MT 58-34S? | An addendum will be issued to remove the specific asphalt mixes for the roadway approaches and replace with bid item 465.0105 Asphaltic Surface. Special Provision NCR-465-005 will be added instructing the contractor submit a mix design meeting the requirements for HMA Pavement Type HMA MT. | Mike Coleman | 1 | 2024-10-15 07:28 | 2024-10-16 10:13
20241112 | 20241112037 | 37 | Concrete Masonry Bridges | What is the Concrete Masonry Bridge item being used for? | The Concrete Masonry Bridges item will be removed. The Concrete Masonry Overlay Decks quantity will be increased by 1 CY to account for Full-Depth Deck Repair areas. | Mike Coleman | 2 | 2024-10-18 13:53 | 2024-10-21 13:23
20241112 | 20241112039 | 39 | Geotech Report | Can we obtain a copy of the geotech report for B-37-0475 | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/i72y71r79c6zopa3nzimw68gbs5bzlfe or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-28 17:45 | 2024-10-30 18:43
20241112 | 20241112039 | 39 | Concrete Masonry Bridges | The concrete quantity for pier 3 (B-37-475) appears to be short. Pier 3 shows 35.2 CY it appears the to be closer to 45.2 CY. Can this be reviewed? | Weâ€™ve reviewed the plan and there is indeed a concrete quantity discrepancy for Pier 3. The correct quantity is confirmed as being 45.3 CY (for Pier 3); total quantity for item 502.0100 should be 888 CY. | Mike Coleman | 2 | 2024-11-04 06:24 | 2024-11-06 17:43
20241112 | 20241112040 | 40 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/29m018049gl8een9w32frac09p43host or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-10-14 10:56 | 2024-10-15 07:16
20241112 | 20241112040 | 40 | Temporary Water Diversion | With respect to Temporary Water Diversion Station 198+08, Item SPV.0060.02. Please clarify the following spec language&#58; â€œThe temporary water diversion of Deerskin River at Station 198+08 shall be in place prior to removal of the existing culvert unless the existing culvert is used as part of the temporary water diversion.â€ If the intent of this item is to provide a water diversion prior to removing the existing culvert, how can the diversion be comprised of the existing culvert? Is this permitting the use of the existing culvert to maintain water flow until a one-time release of sediment at the moment the culvert is removed? | Item SPV.0060.02 Temporary Water Diversion Station 198+08 is for providing temporary water diversions for the flows of the Deerskin River during the removal of the 84-inch metal culvert and installation of Structure B-63-31. Release of sediment into Deerskin Creek is not permitted. | Mike Coleman | 2 | 2024-10-25 16:01 | 2024-10-28 11:40
20241112 | 20241112041 | 41 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/ebmiln7pv6bj1rgctdrk9mf8qtubq474 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-10-14 10:57 | 2024-10-15 07:29
20241112 | 20241112041 | 41 | Pulverize and Relay | The miscellaneous quantities show a pulverize and relay quantity in all the reconstruct sections except between stations 323+00 and 325+50, however the typical sections do not show these areas to be pulverized. Are the reconstruction areas intended to be pulverized first prior to excavation? How will the removal of this existing asphalt, pulverized or not, be paid for? | The pulverize and relay quantity described was included because the reconstruction taking place in these regions requires fill over the existing roadway. Pulverizing is desired to break up the asphalt layer therefore allowing the existing material to be used without removal. The asphalt removal between STA 323+00 â€“ STA 325+50 is to be paid as excavation common. | Mike Coleman | 2 | 2024-10-23 12:32 | 2024-10-24 12:21
20241112 | 20241112042 | 42 | Geotech Report | Can we obtain the geotech report for B-37-476 | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/0vt6amc8uxzzn2ao346wy4rq3xmegwj5 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-28 17:46 | 2024-10-30 06:54
20241112 | 20241112042 | 42 | Contract time should be longer | Hi, We do not believe 30 working days is sufficient for this contract. The existing bridge has a concrete slab superstructure &amp; parapets that will need to be largely demolished in place. Both existing concrete abutments have removal limits underwater. and there is pre-boring one one of the abutments. This should be closer to a 45 day contract. | We are open to giving 5 additional days for a total of 35 working days since we think this would help reduce bid costs. Other than in-water work, there are no other restrictions and the roadway is closed. An addendum will be issued. | Mike Coleman | 2 | 2024-11-03 11:14 | 2024-11-04 16:11
20241112 | 20241112042 | 42 | Limits of abutment removal | Hi, can the Department please share what their expectation for existing abutment removal? Without any as-builts, we do not know the depth of the footing below the abutments. This style and vintage of bridge has some relatively shallow footings (2&#39; thick) or very thick (6&#39;thick). Respectfully, if the expectation is that the full footing is to be removed, then a cofferdam item should be added. | The area of the existing abutments is considered streambed. Follow standard spec 203.3.2.2.1. Full abutment removal and use of cofferdams are not anticipated. | Mike Coleman | 3 | 2024-11-03 11:17 | 2024-11-04 16:09
20241112 | 20241112044 | 44 | B-9-309 Btm of Str Elevations | The stated elevations for bottom of abutments and pier footings vary across the structure plans. (example&#58; Pier Footings Btm elevation on sheet 1 states 915.98, sheet 4 states 916.02 and sheets 13 &amp; 14 state 915.77) Please confirm and provide what these elevations shall be at both abutments and pier. | Pier should be EL. 915.77â€™. - It is correct on the pier sheet (13), and incorrect on the General Plan (1) and Subsurface Exploration (4) sheets. West abutment should be EL.935.08. - It is correct on all west abutment sheets (6-8) and the Subsurface Exploration (4) sheet, and incorrect on the General Plan (1) sheet. East abutment should be EL.933.92. - It is correct on all east abutment sheets (9-11) and the Subsurface Exploration (4) sheet, and incorrect on the General Plan (1) sheet. We will update the General Plan (1) and subsurface sheet (4) and provide an addendum to be inserted into the plans. | Mike Coleman | 1 | 2024-10-22 15:56 | 2024-10-24 08:34
20241112 | 20241112044 | 44 | Soil Borings | Are there soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/co2zm6r5etpxchhjbwos28a8srgqx89b or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-10-28 10:34 | 2024-10-30 06:41
20241112 | 20241112044 | 44 | B-9-309, Type H Floor Drain | The quantity being bid is incorrect. | We believe the Type H floor drain item quantity is shown correctly in the quantities on pages 47 and 194 as 1 EACH. The quantity also matches what is shown on the structure plan detail on page 233. | Mike Coleman | 3 | 2024-10-31 08:40 | 2024-11-01 06:48
20241112 | 20241112044 | 44 | Mix Type | Project 8996-01-07 Sheet 11 Calls for the Frontage Road and 171st Street to be AP03 which is 4â€ Upper 1.75â€ 4 HT 58-34H and Lower 2.25â€ 3 HT 58-28H Sheets 19 and 20 show those areaâ€™s as AP01 which is 5.5â€ Upper 2.75â€ 3 HT 58-34H and Lower 2.75â€ 3 HT 58-28H which is a typo because they would not put a 3 HT on surface. |  |  | 4 | 2024-11-05 15:38
20241112 | 20241112045 | 45 | Box Culvert Sizes | Are the sizes of box culverts C-61-62-90 and C-61-38-57 known? | C-61-62-90 â€“ This location has 2 boxes each sized 48â€ H, 54â€ W C-61-38-57 This location has 2 boxes each sized 96â€ H, 108â€ W | Mike Coleman | 1 | 2024-10-17 16:31 | 2024-10-23 08:37
20241112 | 20241112045 | 45 | Structure Adjustments | There are 18 Temp Cover Plates in the quantities shown for Manhole Covers and Inlet Covers. I don&#39;t think these would be needed for the Inlet Covers but plates would be needed for the 13 Sanitary Manhole Covers, if those are required to be adjusted in the same two operation process as the storm manholes. | An addendum will be issued to update the quantities to show 22 temporary cover plates. | Mike Coleman | 2 | 2024-10-28 15:36 | 2024-10-30 07:25
20241112 | 20241112045 | 45 | Box Culvert at Sta 576 | Can you verify the size of the C-61-62-90 box culvert? The answer in the prior question does not seem correct. Thanks | The previous response was taken from the WisDOT provided culvert inventory report so apologies that the information in there was not up to date. After a review of HSI (https://trust.dot.state.wi.us/hsi/HSIController) and the as-builts of this structure, from HSI the size of these double boxes C-61-62-90 are each actually 96â€ height by 108â€ width. | Mike Coleman | 3 | 2024-10-29 05:41 | 2024-10-30 07:17
20241112 | 20241112045 | 45 | 465.0120 Asphaltic Surface Driveways | Please confirm the quantity of bid item #0048 Asphaltic Surface Driveways as it appears this is overstated. | An addendum will be issued to update the quantity. | Mike Coleman | 4 | 2024-11-04 09:46 | 2024-11-06 17:51
20241112 | 20241112046 | 46 | Plan Holder List | DO you know when a plan holder list will be made available? | The plan holders list is updated on the HCCI site every Friday after advertisement. Then on Monday, Wednesday, and Friday the week prior to the letting, and on Monday, the day prior to letting. | Mike Coleman | 1 | 2024-10-15 12:25 | 2024-10-15 12:45
20241112 | 20241112047 | 47 | Crack & Damage Survey | Can you please provide the address&#39;s of the 68 homes/business&#39;s that will require the Crack and Damage survey. | The property ownersâ€™ addresses can be found at the following location: https://wisdot.box.com/s/1nu0n5jo7k7hrn3mn93ydioaazgr582s or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-14 17:03 | 2024-10-15 12:28
20241112 | 20241112047 | 47 | Geotechnical Report | Can the Geotechnical Report be made available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/1nu0n5jo7k7hrn3mn93ydioaazgr582s or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-10-17 08:53 | 2024-10-21 09:09
20241112 | 20241112047 | 47 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/1nu0n5jo7k7hrn3mn93ydioaazgr582s or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2024-10-17 09:00 | 2024-10-21 09:06
20241112 | 20241112047 | 47 | Pedestrian Push Buttons | Pay line 0420 shows quantity of 15, but the signal plans on pages 117-119 &amp; 121-123 show a total of 16. Can you please confirm if all 16 buttons should be supplied, and if not, which button is not to be supplied? | 15 new push buttons are the correct total. The push button on SB15 at the Main Street intersection is an existing push button and is included in the Remove, Salvage, and Reinstall Traffic Signal Standards 13-FT bid item. It is bolded to show that work will be completed with that pole/button, but the button itself is already existing. | Mike Coleman | 4 | 2024-10-21 11:47 | 2024-10-24 06:35
20241112 | 20241112047 | 47 | C&D | Can you clarify if you want the entire building inspected or just the side facing STH 13? &quot;This special provision describes conducting a crack and damage survey of the residence, college, and business buildings located at the building fronts facing STH 13 (Ellis Avenue) from 16th Street to USH 2.&quot; I read it both ways. If only the STH 13 side, how far back into the home is needed? | I read it as inspecting the whole building. Buildings to inspect are those that face STH 13 and are provided by address in the answer to bid question #1. | Mike Coleman | 5 | 2024-10-22 11:09 | 2024-10-24 12:29
20241112 | 20241112047 | 47 | Sacrificial Anodes | Will 3/4&quot; Sacrificial Anode Caps be required on the bolts for buried watermain joints? If so, how many will be required per joint? | The project specifications donâ€™t require sacrificial anodes on the bolts for buried water main, however, they may be added to contract during construction/at a later time and would be required on every other bolt. | Mike Coleman | 6 | 2024-11-06 15:53 | 2024-11-07 14:23
20241112 | 20241112047 | 47 | Polystyrene Insulation | What are the requirements for compressive strength for the polystyrene insulation on this project? | we do not specify a compressive strength requirement, but the material needs to meet AASHTO M230 (without flammability) requirements | Mike Coleman | 7 | 2024-11-06 15:54 | 2024-11-07 14:23
20241112 | 20241112047 | 47 | Item #0508 - Schedule 40 Perforated 6-inch | How much solid SCH80 PVC should be assumed from the inside of the upstream structures to the bends for each rn of perforated 6&quot; SCH40 quoting purposes? | The length of solid SCH80 PVC would be the structure wall thickness plus one to two feet. | Mike Coleman | 8 | 2024-11-06 15:57 | 2024-11-07 14:17
20241112 | 20241112048 | 48 | Soil Borings | Are there soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/bsf9j5j069hszqsfim5mpv5eoc3ae0f7 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-28 10:37 | 2024-10-29 06:59
20241112 | 20241112048 | 48 | Settlement Plate | The settlement plate SPV doesn&#39;t include removal, thus it&#39;s safe to assume this is a permanent structure and must meet Buy America requirements. | WisDOT concurs with this interpretation. As indicated in the Construction and Materials Manual, CMM228.5 - Buy America Provision, documentation is required for products that contain iron and steel, manufactured products, or construction materials, in accordance with 2 CFR Part 184 and 2 CFR Part 200. Please refer to the CMM and the referenced regulations for additional information. | Mike Coleman | 2 | 2024-11-07 10:24 | 2024-11-07 13:41
20241112 | 20241112048 | 48 | Project Completion Timeframe | SPV 3 - Prosecution and Progress requires allowing Station 2050+00 to 2062+00 to remain inactive for 2 months. Will those 2 months be charged towards the working days? | The 2 months to allow for settlement between Station 2050+00 to 2062+00 will be charged towards working days. This was accounted for in the working day calculation and it is anticipated other construction activities shall take place outside of that station range. | Mike Coleman | 3 | 2024-11-07 10:26 | 2024-11-08 07:19
20241112 | 20241112048 | 48 | Settlement Plate & Survey Pin | The Payment description for both of these items state it is compensation to Contractor for monitoring, but the SPV description indicates the engineer will perform all the monitoring. Please clarify. | Engineer is required to monitor settlement plates and survey pins. Contractor is required to protect settlement plates and survey pins. Payment description for both should state â€˜and protecting.â€™ | Mike Coleman | 4 | 2024-11-07 10:28 | 2024-11-08 07:19
20241112 | 20241112049 | 49 | SS 104.6.1.2.4 (2) - Temp Guardrail | Will this road be considered open to all traffic after the bridge/detour work has been completed? The guardrail locations that do not have curb require a shoulder cut. All of the guardrail at these locations will need to be removed to perform this work. Will temporary guardrail need to be installed while the remainder of the project is built under traffic? | An addendum will be prepared to extend the working day detour and require guard rail work to be completed within that timeframe. | Mike Coleman | 1 | 2024-10-10 07:44 | 2024-10-17 06:40
20241112 | 20241112049 | 49 | Guardrail Curb | Should there be an SPV item for removing the guardrail curb? Also, the guardrail curb is partially buried in the asphalt shoulder. Should this be sawcut at the face of the guardrail? Will the asphalt that is beyond the face of rail need to be removed? | An addendum will be prepared to address the buried guard rail. | Mike Coleman | 2 | 2024-10-14 14:31 | 2024-10-17 06:40
20241112 | 20241112049 | 49 | Soil Borings | Are there soil borings available for this project? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/dgpgbvwpe7xrri0oqajwz8sdeknccmxe or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-10-28 10:37 | 2024-10-30 07:32
20241112 | 20241112049 | 49 | Asphaltic Surface | The specifications calls out this item to be 3MT 58-34V on sheet 6 of the plan. Does this lower lift mix need to be a 3MT 58-34V as the upper (3.25&quot;) will be milled off and paved with 5MT 58-34V. | A grade of 4MT 58-34S is the minimum requirement for the asphaltic surface. | Mike Coleman | 4 | 2024-11-04 09:54 | 2024-11-05 14:41
20241112 | 20241112049 | 49 | Asphalt Mow Strip | Are the quantities correct for the asphalt mow strip? Also, is WisDOT looking for the asphalt mow strip or the emulsified asphalt mow strip? | An addendum will be issued. | Mike Coleman | 5 | 2024-11-05 16:07 | 2024-11-06 17:58
20241112 | 20241112050 | 50 | Clarification of payment for excavation under proposed structure | On the front sheet of the bridge plan (60 of 102). There is a note that shows the excavated material (hatched lines) under the new structure &quot;area to excavate included in &quot;Excavation for Structures B-10-397&quot;. If you look at the Earthwork data sheet &amp; the cross sections, it appears that quantity is included in the earthwork balance (Unclassified Excavation) quantity. Please clarify! | Due to the amount of material that needs to be excavated for the new bridge, the intent was to show it in the earthwork table comps while adding a note that this was not used to balance the earthwork. After looking at this closer it appears that note wasnâ€™t added. An addendum will be issued to add the information to the structure plan. | Mike Coleman | 1 | 2024-10-11 12:07 | 2024-10-15 07:26
20241112 | 20241112050 | 50 | Cofferdams | Per standard spec 206.5.2 Excavation for Structures (2) &quot;Payment also includes providing cofferdams, cribs, sheeting, shoring, bracing, pumping, and dewatering except, if the contract contains the applicable bid items, the department will pay separately for this work.&quot; Cofferdams are required as part of the plan, if an earthen cofferdam (no sheet piling) is used at the piers, will this be paid as part of the cofferdam item?â€ | The quantity for the Cofferdams bid item (206.5001) will be updated with a new addendum to have a total of 1 Each. The standard spec calls for cofferdams to be bid on a per-structure basis. Cofferdams are acceptable if they meet the language of standard spec 206.3.3(1), which includes the use of well-point systems in conjunction with excavations/earthen barriers. The updated cofferdam bid item will be paid for per standard spec 206.5.3. | Mike Coleman | 2 | 2024-10-22 09:21 | 2024-10-28 06:40
20241112 | 20241112050 | 50 | Underwater Concrete | Under water inspections are required per the project documents. It is assumed that concrete can be placed under water. If that is so, it is common to see a note similar to &quot;Concrete poured under water will be allowed; pour the concrete conforming to standard spec 502.3.5.3.&quot; Can concrete be placed underwater? | Concrete may be poured under water in accordance with standard spec 502.3.5.3. This is noted in the plans on sheets 61 and 71 â€“ 76. | Mike Coleman | 3 | 2024-10-30 11:16 | 2024-10-31 10:30
20241112 | 20241112050 | 50 | Can the full geotechnical report be provided? | Hi, Is a copy of the full geotech report available? Can we please get a copy? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/j30737bd536xr6raj9zwdi6wqamibk41 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 4 | 2024-11-07 10:46 | 2024-11-11 09:59
20241112 | 20241112051 | 51 | Soil Borings | Are soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/x6tjyy0nuu6x0lehxj88ip01zl2enbd2 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-16 13:31 | 2024-10-17 12:16
20241112 | 20241112051 | 51 | Inlet Type TR Cover | For the Inlet Type TR Cover, is there a separate pipe that this cover ties into or does this cover tie into the storm sewer pipe? If separate pipe, how is that paid for? It appears that the curb will need to be poured prior to the installation of this Inlet Cover so that the drain is set based on the roadway and not that the roadway is set based on the drain. | The Inlet Type TR Cover will tie into a separate pipe that is not part of the storm sewer system shown on page 14 -19 of the plans. This pipe is incidental to the item Inlet Type TR Cover as called out in the special provisions. We will be making updates to the detail as part of an addendum to clarify this in the plan and show how the storm sewer pipe relates to the Inlet Type TR Cover pipe. We did agree that it makes sense to pour the curb first as the intent would be for the grade of the roadway to dictate the grade of the drain and not visa versa. | Mike Coleman | 2 | 2024-10-28 08:07 | 2024-10-28 08:08
20241112 | 20241112052 | 52 | Cofferdam for Painting Pier Piles | Exposed piles in the pier are to be cleaned and painted as part of this project. No cofferdam item is included in the contract for dewatering the pier location. Is the intent to only paint the portion of the piles exposed above water? If not, a cofferdam item would be needed to dewater the pier to stream bottom. | The intent is to only paint the exposed areas of the piles above the water. | Mike Coleman | 1 | 2024-10-30 11:28 | 2024-10-31 10:33
20241112 | 20241112052 | 52 | Debris Capture | Existing plans show debris capture spec. In the departmentâ€™s view, would a debris capture system be allowed which involves parts of the existing slab to be dropped onto a containment system floated on barges or supported on shore prior to being removed? | This would be allowed as long as WisDOT standard specs 107.19 and 203.3.2.2.3.4 are adhered to. | Mike Coleman | 2 | 2024-10-31 11:26 | 2024-11-07 13:43
20241112 | 20241112054 | 54 | Geotech Report | Can we obtain the geotech report for B-60-0158 | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/qnjjbfwa1w826j2yv5srmo98gntq6ooc or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-28 17:47 | 2024-10-30 06:35
20241112 | 20241112054 | 54 | Extending project limits on east side | The erosion control is currently set up in the plan to build the pier from the east side. However, the east project limits are not long enough to accommodate a crane and pre-boring equipment, especially given the need to provide access to the driveway at all times. If the bridge is excavated to plan, and a crane is 30&#39; long, that leaves 7&#39; in which to stage preboring operations and park a crane, which is simply unrealistic. As it stands, there is nowhere to lay down a pile driver within project limits. As al alternative, the staging could be staggered to use the west approach for pre-boring access, and those limits could be extended so we could at least have both units on site at the same time (that does not even bring into play the excavator...). Please consider this constructability issue. Thank you. | The Erosion Control Plan (Sheet 5) gives example staging. As noted on this sheet, â€œEXACT STAGING TO BE DETERMINED BY THE CONTRACTOR.â€ Construction methods shall be outlined in the ECIP. Equipment and materials may be stored outside the Begin/End Project limits as long as they are behind road closure barricades, within the Right-of-Way, and out of wetlands. Road Closure Barricades may be extended past adjacent driveways as long as access to residents is still provided at all times. | Mike Coleman | 2 | 2024-10-31 13:05 | 2024-11-04 05:28
20241112 | 20241112055 | 55 | Concrete Pavement | With the Total length being just over 300 LF and there being only one 12&#39; wide lane slip able the full length will this project still be required to use a slip form paver? With the variable with outside lanes, intersection, and median islands we see the slip form spec limiting our abilities to expedite the paving process. | The department typically holds to this 300â€™ specifications but in this case taking into account the size of the project and the transitions into the intersections slip form paving will not be required on this project. | Mike Coleman | 1 | 2024-11-05 14:40 | 2024-11-06 06:10
20241112 | 20241112055 | 55 | Paving,Milling,Crack Patching, Asphaltic Surface Patching Scheduling | It states that we cannot open traffic after milling until lower layer has been placed. On sheet 6 it is stated that prior to placing lower lift cleaning all joints/Patching PCC is required and paid for as Prepare foundation for asphaltic paving bid item. Blowing and cleaning cracks depending on the extent of this based on exposed PCC can take a substantial amount of time. On page 58 â€“ 60 is also shows a hatched area for anticipated work under asphaltic surface or asphaltic surface patching items. How is the removal of this material being paid prior to paving? This will need to be done after milling and prior to paving which doesnâ€™t seem possible if we must complete this work all prior to lower lift on the same day. Is it anticipated that half the road will remain closed for multiple days under traffic control? I believe that we will need to open the roadway onto the milled surface in order to complete this job. Milling and Prep one day and paving the next. | 1. The hatched areas called out as anticipated to require the asphaltic patching items in the plans are shown for information only, with the intent being that the existing pavement in the hatched areas is more distressed and may require some patching after the mill. Any removals in these areas due to distress would fall under the appropriate Prepare Foundation item as noted in spec, at the direction of the engineer in the field. 2. The intent is to work on small enough areas each day that it would be possible to mill, prepare, and pave the lower layer of HMA in one day. This is due to the minimal amount of asphalt that would remain in some areas after the milling, so the restriction of not opening lanes to traffic until the lower layer of HMA has been paved will remain. To provide more time during lane closures for milling, an addendum will be submitted today to revise the restriction on maintaining all existing lanes of traffic during non-working hours to say â€œIn locations with one existing through lane in each direction, maintain existing lanes of traffic during non-working hours. In locations with multiple through lanes, maintain at least one through lane in each direction at all times, except for the road closure. Each single lane closure for milling operations will be allowed to remain in place for a maximum of two consecutive calendar days.â€. In areas with only two lanes, the lower layer would still need to be completed the same day under flagging. | Mike Coleman | 2 | 2024-11-07 07:30 | 2024-11-08 11:58
20241112 | 20241112056 | 56 | HMA | Would the department consider changing the mix type to Asphaltic Surface. Also, would the department consider looking at an asphalt structure of&#58; 2.25&quot; 3MT 58-34S / 2.25&quot; 3MT 58-34S / 2&quot; 4MT 58-34S. This could be designated in the Typical sections and also written in the special provisions that the Asphaltic Surface item would need to be these mixes and oils for the respected lifts. | An addendum will be issued to add asphaltic surface with the minimum grade of 4MT58-34S. | Mike Coleman | 1 | 2024-10-15 07:23 | 2024-10-16 10:15
20241112 | 20241112056 | 56 | Soil Borings | Are there soil borings available for this project? | Soil boring information is available for each structure location within the structure plan sheets. They can be found on sheet 56 and 62 of the advertised plan set. | Mike Coleman | 2 | 2024-10-28 10:39 | 2024-10-31 06:07
20241112 | 20241112056 | 56 | Clearing | SPV Article 3 states that no tree clearing is allowed from April 1 to October 31. SPV article states that instream disturbance restrictions are from March 1 to June 15. The plan includes 96 SY of Clearing. When does the department anticipate clearing to occur? If before April 1, will working days be assessed? | Once clearing operations are completed by March 31, working day assessments may be suspended. | Mike Coleman | 3 | 2024-11-02 07:36 | 2024-11-04 16:07
20241112 | 20241112057 | 57 | Can the bird netting item be eliminated? | Hi, The existing structure is a pair of CMPs with no evidence of swallow nesting in any of the inspection reports or during our site inspection prior to bid. Swallows don&#39;t typically nest in steel culverts. Can this item please be eliminated from the contract? | Through additional coordination with the WisDOT REC, it was determined that the bird netting item can be removed. An addendum will be issued. | Mike Coleman | 1 | 2024-10-30 15:39 | 2024-11-04 16:04
20241112 | 20241112057 | 57 | Turbidity Barrier | During the removal of the existing structure, is the intention of the turbidity barrier to dam off the stream? With the amount of water flowing through there, that doesn&#39;t seem like it would be a possible option or the right application for turbidity barrier. | Turbidity barrier installation is being modified. A clarification will be issued by addendum. | Mike Coleman | 2 | 2024-10-31 18:05 | 2024-11-05 14:31
20241112 | 20241112058 | 58 | Geotech Report | Can we obtain the geotech report for B-60-159 and B-60-160 | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/af1prrieklsov1zi6guagk7n77bd53uh or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-10-28 17:48 | 2024-10-30 07:28