## qandasearchletting_results
Date | 2024-12-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20241210 | 20241210001 | 1 | Same Day Epoxy | Is the intent of this item to replace the skips removed with concrete replacement after every shift, or are the skips to be replaced at the conclusion of the Stage? | The same day epoxy bid item is intended to be used on an as needed basis during overnight patching operations. If a patch or patches completed during a single night remove one or two lane skips, the skips may not need to be replaced. But if a patch is longer or there are several patches in a row and multiple skips are impacted, they would need to be replaced before fully opening the lanes to traffic. The need for the same day epoxy would be determined by knowing the extent that concrete repairs to be completed in a night would impact the existing lane skips. | Mike Coleman | 1 | 2024-11-19 14:23 | 2024-11-25 08:05
20241210 | 20241210001 | 1 | Shoulder Dropoff | Per the typical sections, the shoulders get 3&quot; of binder and 2&quot; of surface. Will the Department allow a 2&quot; dropoff until surface is paved or is the intent for Contractor&#39;s to pave &quot;hot-on-hot&quot; by the end of each shift to eliminate dropoffs? | The department does not intend for the contractor to pave hot on hot but does expect both layers to be paved before moving to the other shoulder as laid out in stage 4 and stage 5. The 2-inch drop off is within the allowable threshold per standard spec 104.6.1.2.3 and the shoulder closure should remain in place to delineate the drop off as well. | Mike Coleman | 2 | 2024-11-20 09:35 | 2024-11-25 08:15
20241210 | 20241210001 | 1 | Guardrail Mow Strip Emulsified Asphalt | In the construction details regarding guardrail layout, it appears that most all locations of new guardrail are supposed to receive the emulsified asphalt. However, the MQs only state stations 18+49 to 20+13 to receive the material. This leads to 2 questions&#58; Which of these areas of the plan are correct? and Is there a detail for anticipated limits of the emulsified asphalt? Article 19 regarding this issue leads us to believe that emulsified asphalt is intending to be used on existing shoulders in areas where new shoulder material will not be getting placed. | The total quantity of Guardrail Mow Strip Emulsified Asphalt needed for the project was inadvertently listed at a single location instead of being distributed over all locations. There is no change in quantity. The MQ plan sheet will be updated with an addendum to properly distribute the quantity, and a note will be added indicating each area is based on the length of rail to be installed multiplied by 4 feet and then converted to square yards. | Mike Coleman | 3 | 2024-11-21 10:01 | 2024-12-02 06:34
20241210 | 20241210001 | 1 | Barrier System Grade Shape Finish | Is it possible to get the chart that states For Information Only regarding the materials and quantities needed that are associated with this bid item? | The MQ plan sheet will be updated with an addendum to include the â€˜for information onlyâ€™ quantities associated with the five locations where the item of Barrier System Grading, Shaping and Finishing is required. | Mike Coleman | 4 | 2024-11-21 10:13 | 2024-12-02 06:35
20241210 | 20241210001 | 1 | Staging | Can Stage 2 work be performed at the same time as stage 1 or Stage 3 work? | Overlap of concrete repair/replacement work shown in stages 1 thru 3 of the plan is possible as long as any other requirements noted in the special provisions are met. Stages 4 & 5 for asphalt shoulder replacement cannot be completed until concrete repairs have been completed on the adjoining lanes. | Mike Coleman | 5 | 2024-12-02 06:57 | 2024-12-02 11:43
20241210 | 20241210001 | 1 | Tie Bars | Are there more Tie Bars being bid than will be used? If the quantity is overstated, should it be adjusted? | The quantity of tie bars in the bid documents is a best estimate of what may be needed to complete the project. The quantity includes some assumptions as the actual locations of concrete patches and concrete repair is likely to differ somewhat from whatâ€™s depicted in the advertised plans. | Mike Coleman | 6 | 2024-12-02 07:53 | 2024-12-04 06:12
20241210 | 20241210001 | 1 | Traffic Control required for pavement removals | Will pavement removal work be allowed in the single lane closure timeframe, or do removals need to be done after the multiple lane closure is in place? Can work be done tight to traffic in the single lane closure or does it need to be done behind the drums? | The type of work and method of operation will dictate what activities or operations can be completed with single lane closures versus multiple lane closures. All work is expected to be completed in a manner that does not create issues for traffic in lanes that remain open to traffic, and the contractor would not be allowed to partially encroach work operations into lanes that remain open to traffic. | Mike Coleman | 7 | 2024-12-06 11:26 | 2024-12-09 09:06
20241210 | 20241210003 | 3 | Geotech Report | Please provide the full geotech report for this project. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/lx57foqs2h4q8dweunx1ixvupg60tp8p or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-11-18 10:41 | 2024-11-19 05:32
20241210 | 20241210004 | 4 | Railing Tubular Type M | CMM Specification 232.4 states that railing should be measured to the nearest full unit. Should this bid item be 195 LF. | The design team agrees that the quantity should have been rounded, but no change will be required at this time. | Mike Coleman | 1 | 2024-11-21 16:54 | 2024-11-26 11:58
20241210 | 20241210005 | 5 | Steel Thrie Beam | Should this item be Steel Thrie Beam Structure Approach? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2024-11-15 11:07 | 2024-11-19 05:34
20241210 | 20241210005 | 5 | Guardrail Constructability | With the typical sections requiring most of the pavement elevation to rise by 1.5 inches, and SS 614.3.1(1) requiring final shoulders before installing guardrail, what is the anticipated sequence of operations for this staged project? Can PWL pavement be done is multiple guardrail areas so that final shoulders can be installed before guardrail? | It is up to the contractor to determine their order of operations that meets the requirements of the standard specifications. If there are questions on specific locations in the plans, we can investigate further. | Mike Coleman | 2 | 2024-11-21 11:32 | 2024-11-25 11:40
20241210 | 20241210006 | 6 | Geotech Report | Please provide the full geotech report for this project. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/qbv4edwcq2isflswrbwh5vgqhcl7pps6 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-11-18 10:32 | 2024-11-19 05:26
20241210 | 20241210006 | 6 | Utility Line Opening (ULO) | Plans and special provisions call for a Utility Line Opening (ULO), however there is no ULO bid item included in the contract. Please advise. | An addendum will be issued to add the item | Mike Coleman | 2 | 2024-12-05 07:48 | 2024-12-06 07:27
20241210 | 20241210007 | 7 | Geotech Report | Please provide the full geotech report for this project. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/jvgs5h7itbt43ytj235g24ra21gklivp or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-11-18 10:43 | 2024-11-19 05:29
20241210 | 20241210007 | 7 | Construction Schedule | Can the engineers construction schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/jvgs5h7itbt43ytj235g24ra21gklivp or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-11-19 10:03 | 2024-11-19 13:42
20241210 | 20241210007 | 7 | Structure Construction | How are the bridge structures to be complete with the instream restrictions and Blanchard Cricket Frog timeout dates? The schedule show bridges being constructed during the instream restriction dates. | Work within the Branch of the Galena River at Station 10+75 will be allowed during the fish spawning window (March 1st â€“ June 15th) as long as the baseflow is pumped per the specials. Additionally, this work must be completed within the Cricket Frog window (April 9th â€“ May 19th). Please refer to the special provisions for more information about the in-stream and Blanchard Cricket Frog time-out dates. | Mike Coleman | 3 | 2024-11-19 14:15 | 2024-11-25 08:03
20241210 | 20241210007 | 7 | Site Mowing | Article 19 lists SPV.0060.01 Site Mowing. I don&#39;t see it in the schedule of items. Is this item needed and missing or not needed? | An addendum will be issued to add the item. | Mike Coleman | 4 | 2024-11-21 11:51 | 2024-11-25 13:32
20241210 | 20241210008 | 8 | Shop Bent Guardrail | Please review the guardrail installations in this plan. There are numerous areas that the plan calls for shop bent guardrail. I believe most of this would fall under a missing bid item, 614.2350 MGS Guardrail Short Radius. In addition to that, for example, on page 39 of the plan, it states to shop bend a type 2 panel on an 18-foot radius. I don&#39;t believe that is an approved option for a type 2. Is it possible to change the quantities to account for the required locations of MGS short radius to meet the standard detail for guardrail installations? | The Class A and MGS short radius terminals did not fit within the existing right-of-way. A MGS Guardrail 3 installation with a small radius and a type 2 end terminal was approved by the PDS Chief and BPD Design Standards and Oversight Chief on October 20, 2023. The contractor should incorporate the cost of bending the rail shown in the plan under the 614.2300 MGS Guardrail bid item. | Mike Coleman | 1 | 2024-11-11 10:16 | 2024-11-18 06:33
20241210 | 20241210009 | 9 | Geotechnical Report | Can the Geotechnical Report for this project be provided? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/1wz6nqc0l4963a6rp17y1klgte2hzdpq or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-11-25 09:48 | 2024-11-26 06:39
20241210 | 20241210009 | 9 | Undistributed Quantity - Removal of the Safety Wedge | Looking at the Misc Q&#39;s it shows in the Removing Asphaltic Surface under the Milling SY&#39;s the removal of safety wedge is undistributed. So does that mean if the contractor uses a notched wedge it has to be milled out prior to paving the adjacent lane? If this the case than it would be going against the overall purpose of the notched wedge being used? | The undistributed quantity for the removal of the safety wedge is not needed. An addendum will be issued. | Mike Coleman | 2 | 2024-12-02 15:22 | 2024-12-04 09:03
20241210 | 20241210009 | 9 | Item #38 - Prepare Foundation for Asphalt Shoulders Quantity | Looking at the quantity for the prepare foundation for asphalt shoulders doesn&#39;t seem like there is any quantity figure for all the mainline in the rural section to widened that from 15&#39; lane to 17&#39; lanes. If the intent that is shown in the proposed typical sections wider than the existing typical sections from STA 681+34 - 694+18 and 708+95 - 818+04 then the quantity of prepare foundation for asphalt shoulders should be around 121 STA. | The Prepare Foundation for Asphalt Shoulders quantity should be at 125 STA for the shoulder widening. An addendum will be issued. | Mike Coleman | 3 | 2024-12-02 15:59 | 2024-12-04 09:04
20241210 | 20241210009 | 9 | Existing Aggregate Source and HMA on Mill and Overlay Section | Would DOT be willing to reveal the existing aggregate source/mix design used to pave on STH 21 in the mill &amp; overlay section of the project in the past? | The 1994 mix design can be found at the following location: https://wisdot.box.com/s/1wz6nqc0l4963a6rp17y1klgte2hzdpq or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 4 | 2024-12-03 14:46 | 2024-12-04 08:20
20241210 | 20241210009 | 9 | HES 9" | Is the 2,200sy of HES part of the 13,500sy total or an additional amount of the total? | The 2200 SY of HES is an additional amount of the total. | Mike Coleman | 5 | 2024-12-04 11:22 | 2024-12-05 06:08
20241210 | 20241210009 | 9 | Paint / tape quantities in stage 3 | In the misc. quantities (pg 271) it shows a temp paint quantity of 3,376LF of yellow and 1,288LF of white in stage 3. On the plan for stage 3 (pg 186) it shows temp tape. Should this be temp tape in stage 3? |  |  | 6 | 2024-12-06 10:33
20241210 | 20241210010 | 10 | Moving Signs Type I | Should this bid item actually be 638.2102 Moving Signs Type II? | Correct. All references to Signs Type I should be revised to be Signs Type II. An addendum will be issued. | Mike Coleman | 1 | 2024-11-21 16:00 | 2024-11-25 11:09
20241210 | 20241210010 | 10 | Geotechnical Report | Can the Geotechnical Report for this project be provided? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/f8u2bp03ryo1msnuvr660yfsylgp3etf or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-11-25 09:49 | 2024-11-25 13:12
20241210 | 20241210011 | 11 | Pavement Marking | The proposal reads that all 6&quot; and 10&quot; is grooved wet reflective. The plan 2160-07-73 has the 6&quot; and 10&quot; as surface applied in the misc quantities, is it all to be grooved wet reflective? | We will change the marking to Marking Line Grooved Wet Ref Epoxy 6-Inch and Marking Line Grooved Wet Ref Epoxy 10-Inch and issue and addendum reflecting the change. | Mike Coleman | 1 | 2024-11-13 15:25 | 2024-11-19 10:14
20241210 | 20241210011 | 11 | Transformer Base Breakaway Lead Times | How will the DOT be handling the nationwide shortage and 30-month lead time on the Traffic Bases? These bases only have one manufacturer and I have included some information below that came direct in a letter from Akron Foundry Company&#58; &quot;There is a high demand for our Akron Foundry product line. The 30-month lead time has been unavoidable on our Traffic Bases.&quot; Also, would you recommend contractors include LD&#39;s in with their bids as the DOT has said in the past few exact questions they are not recognizing this as a Nationwide shortage? | WisDOT does not recognize a shortage in transformer bases at this time. WisDOT acknowledges extended material lead times for the bid item {657.0200 - 0299 Transformer Bases Breakaway (size)}. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. Any temporary or permanent contractor proposed solutions, due to material lead times, are the responsibility of the contractor. | Mike Coleman | 2 | 2024-11-15 13:48 | 2024-12-05 06:03
20241210 | 20241210011 | 11 | PWL Table - Intersections | PWL is restrictive to 1 mix design per material type. Given that much of the intersection paving is required to be completed during night-time hours, is it possible to classify this material differently so that it can be supplied by a different plant than the day-time material? | The department would like to avoid multiple acceptance types unless necessary and feels that this situation does not warrant multiple acceptance types. | Mike Coleman | 3 | 2024-11-20 11:32 | 2024-11-27 06:00
20241210 | 20241210011 | 11 | reconstructing manholes monolithic shim | plan sheet 235 shows a 5&#39;x5&#39;base patch for both adjusting and reconstructing manholes. a minumum of 6&#39;x6&#39; is necessary to effectively reconstruct manholes. can the dimension and pay items be increased accordingly to accommodate a minumum of 6&#39;x6&#39; for reconstructs? | An addendum was issued to adjust the size of the patch to 6 x 6. | Mike Coleman | 4 | 2024-11-20 14:15 | 2024-12-04 12:15
20241210 | 20241210011 | 11 | Night Traffic Control Set up and Take Down | The project calls out that the 41/43/894 ramps and the major intersections are required to be completed at night. Is the lump sum Traffic Control item inclusive of all costs for nightly set up and take down? | Correct, this work will be incidental to item 643.5000 along with any other costs associated with traffic control that are not already included with the other traffic control bid items. | Mike Coleman | 5 | 2024-11-22 11:04 | 2024-11-25 11:16
20241210 | 20241210011 | 11 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/bl0mcft1julsi5ha6u1mt16wbgf5u34c or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2024-11-23 14:10 | 2024-11-25 11:13
20241210 | 20241210011 | 11 | Base Patch Removal | Do we have to drill and lift out the base patch? If so, with the extra cut for relief can we chisel out the relief area so that we can lift out the main section? | We do not have a preference on the means and methods to remove the base patch as long as the patch is removed without damaging the remaining pavement and the contractor follows standard spec 390. | Mike Coleman | 7 | 2024-11-25 14:18 | 2024-11-26 11:57
20241210 | 20241210011 | 11 | Curb Ramps | Should their be a shaping and grading item for the curb ramps if we have to cut the grade down to meet the ADA specs? | Shaping and grading for the curb ramps will be incidental to the sidewalk bid item. Standard spec 602.5.2 mentions that payment for the concrete sidewalk bid item is full compensation for foundation excavation, preparation, and backfill if there is no adjacent roadway excavation taking place. | Mike Coleman | 8 | 2024-11-25 14:19 | 2024-11-27 05:57
20241210 | 20241210011 | 11 | Major intersection Side Rd. Off Peak Closures | Once per stage and one intersection at a time, would daytime off peak (9am-2pm) cross road traffic closures be allowed. Based on your answer to question 3 this would equate to a considerable cost savings as some asphalt plants are not legally allowed to produce asphalt at night due to city ordinances. | Daytime off peak closures at major intersections will be allowed with advanced coordination (10 days prior to the closure) with Milwaukee County Transit System (MCTS) if a bus route goes through the intersection. Do not close consecutive cross streets. | Mike Coleman | 9 | 2024-12-03 14:06 | 2024-12-04 08:19
20241210 | 20241210011 | 11 | 614.0805 Crash Cushions Permanent Low Maintenance | Can a drawing be provided that shows exact dimensions of the hazard that will be protected by each Crash Cushion? The manufacturer cannot provide their connection/transition design without knowing these dimensions. The existing guardrails that are protected by Sand Barrel Arrays are various widths, and some hazards L/R are not of equal lengths. Standard crash cushion width protection is 30&quot; wide, if the hazard is wider an additional transition assembly will be required which will extend the overall length of the system. Typically a SPV item for Wide Bay Crash Cushion would be used to account for the wider protection width. Would Sand Barrel Arrays be a more appropriate application? |  |  | 10 | 2024-12-03 14:31
20241210 | 20241210011 | 11 | Cleaning Parapets. 509.9050.S | Cleaning Parapets. 509.9050.S requires blast cleaning of the inside face and top surface of the concrete parapet however there is tubular steel railing with screening currently in place on top the parapet. In order to properly blast clean the top surface and not damage the rail coating, the railing should be removed. Should there be an item added to remove and replace the railing or is the intent not to blast clean the top of parapet as depicted on sheet 6 of 11 for B-40-164? | We will update the language in an addendum to only require water cleaning of the top of the parapet, no blast cleaning of top. If the contractor were to elect to remove the railing, it would be incidental to this item. There will be no quantity changes required for this addendum. | Mike Coleman | 11 | 2024-12-04 06:59 | 2024-12-04 11:39
20241210 | 20241210011 | 11 | Existing Pavement Reinforcement | Does the existing 8-inch concrete pavement contain steel mesh? Does it contain dowel bars? | The existing concrete pavement information can be found at the following location: https://wisdot.box.com/s/bl0mcft1julsi5ha6u1mt16wbgf5u34c or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 12 | 2024-12-07 09:09 | 2024-12-09 10:32
20241210 | 20241210011 | 11 | schedule | The Segments seems like a good idea, but what happens if there are utility delays or electrical material delays which inevitably happen. The electrical materials are of particular concern. Will WisDOT provide additional contract time when critical delays occur as is provided for in the WisDOT Standard Specifications? |  |  | 13 | 2024-12-08 09:22
20241210 | 20241210012 | 12 | Proposal ID: 20241210012 Project: 2722-08-71 | Hello. I am working on getting a quote of this project, but I am missing the Inlets Median 1 grate. I can&#39;t find them in the plans to get information such as RIM elevation and inverts elevation so I can calculate the vertical feet for the structures. Could you please help me with this matter? Thank you. | Item 611.3901 Inlets Median 1 Grate was removed from the plans. Not required. | Mike Coleman | 1 | 2024-11-08 12:47 | 2024-11-15 07:20
20241210 | 20241210012 | 12 | Line Number 12 Item 204.0120 Removing Asphaltic Surface Milling | All of the asphaltic surface removal appears to be full depth. Should this item be removing asphaltic surface rather than removing asphaltic surface milling? | Since the areas currently listed as Removing Asphaltic Surface Milling are actually full depth pavement replacements, the areas should fall under the bid item Excavation Common. Excavation Common already includes these areas so there would be no changes needed for that bid item. The bid item Removing Asphaltic Surface Milling should be removed from the miscellaneous quantities sheet. An addendum will be issued to correct this. | Mike Coleman | 2 | 2024-11-14 13:19 | 2024-11-18 06:36
20241210 | 20241210012 | 12 | Line Item 452 - SPV.0090.05 Spot Repair Existing Storm Sewer | With the quantity of 345LF listed between manhole 100.52-104.00 is the intent to replace this pipe? | No, the intent is not to replace this pipe. There is one defect within this pipe that is proposed to be repaired. The bid item should be 1 EACH and not 345 LF. An addendum will be submitted to clarify. | Mike Coleman | 3 | 2024-11-26 11:33 | 2024-12-02 06:32
20241210 | 20241210012 | 12 | Design Files | We understand the PDF plans are the contract documents and any CAD files provided will be for information only and may not match the PDF plans, but can the contract data packet be provided with the following design files? Existing Conditions Survey Surface CAD files (Format&#58; LandXML, .Dwg or .DGN) Existing Condition Survey Mapping CAD files (Format&#58; LandXML, .Dwg or .DGN) Proposed Finish and Subgrade Surface CAD files (Format&#58; LandXML, .Dwg or .DGN) Proposed Alignments CAD files (Format&#58; LandXML, .Dwg or .DGN) Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format&#58; LandXML, .Dwg or .DGN) | This is a local program project. On local program projects, there is no requirement for contractor data packets. | Mike Coleman | 4 | 2024-12-03 09:58 | 2024-12-04 05:58
20241210 | 20241210012 | 12 | Interconnect Plan | I am looking at the conduit and fiber on the interconnect plan sheet 126-134 and it states that we are to install 48-ct fiber into existing 3&quot; conduit or new 3&quot; conduit. We do not have a fiber item on the items list; Is this fiber getting installed by others? | The fiber optic cable will be installed in a future project. | Mike Coleman | 5 | 2024-12-04 07:37 | 2024-12-04 09:07
20241210 | 20241210012 | 12 | Box Culvert Membrane | Does the existing box culvert V-67-045 have an existing membrane or membrane at the joints that will be required to be removed? Manufacture recommends shot blasting existing surface, will the vertial portion be allowed to be sand blasted? | Box Culvert V-67-045 does not have an existing sheet membrane, but it does have Polyvinyl Chloride Waterstop at the wingwall corners. This will need to be removed prior to manufacturer's surface preparation. Shot blasting the vertical portion will be allowed as long as the preparation does not damage the existing box and proper erosion control measures to protect Deer Creek are followed. See erosion control plans for details. | Mike Coleman | 6 | 2024-12-05 10:21 | 2024-12-06 15:38
20241210 | 20241210012 | 12 | Membrane Installation | Talking with the representative for the membrane, they are worried about placing backfill directly over the membrane and said that there is a protection course that should be placed inbetween. Is the Department going to add an item for this material or is it to be incidental to the bid item? Discussing with representative, they were thinking 2&quot; insulation. Will the representative be required for both days of installation given that the box is in halves? | According to the spec Sheet Membrane Waterproofing for Buried Structures, Item 516.0610.S, contractor should apply materials in strict accordance with the manufacturerâ€™s instructions. If this includes installing 2â€ insulation, this would be incidental to the bid item. According to the spec Sheet Membrane Waterproofing for Buried Structures, Item 516.0610.S: To provide quality assurance that the membrane has been properly installed, a manufacturerâ€™s representative familiar with membrane installation procedures shall be present during placement of the membrane. This would include both halves of the membrane. | Mike Coleman | 7 | 2024-12-06 07:53 | 2024-12-06 15:37
20241210 | 20241210012 | 12 | Concrete Pavement 10.5 and 10.5 HES - Quantities | The quantity for Concrete Pavement and Concrete Pavement 10.5 Inch appears to be overstated by the 4000+ SY. It appears that the quantity was double counted. Please clarify. |  |  | 8 | 2024-12-09 07:36
20241210 | 20241210013 | 13 | SPV 17 Structure Repainting General Clarificiation | Please clarify on the intent of SPV 17 (structure repainting general. If the structure is to be painted there is no item for this. Is this only included for the purpose of graffiti removal? | SPV 17 will be removed by addendum. | Mike Coleman | 1 | 2024-12-03 10:24 | 2024-12-05 13:23
20241210 | 20241210013 | 13 | Common Excavation | Please clarify that the common excavation item is only meant for removing the debris built up in the culvert. Does this need to be hauled off? | The common excavation item is meant for removing debris from inside the culvert and at culvert ends within the channel limits. It will need to be hauled off. | Mike Coleman | 2 | 2024-12-03 10:33 | 2024-12-05 13:19
20241210 | 20241210013 | 13 | Pavement Markings | There is a plan shown for permanent pavement markings but no bid items. | No pavement marking work will be done for this project. Please remove the Pavement Marking plan from the plan set. | Mike Coleman | 3 | 2024-12-03 10:38 | 2024-12-05 06:17
20241210 | 20241210014 | 14 | Pre-Bid Meeting Time | Per Special Provisions Non-Mandatory Prebid Meeting is set up for 10 am on November 12th, which is the morning of November DOT Letting as well. Can the meeting time be adjusted for a later date, so contractors have a better opportunity to get familiar with a job and attend the Pre-Bid Meeting? | An addendum has been issued to change the date from November 12 to November 19, at 2:00 PM. | Mike Coleman | 1 | 2024-11-05 14:37 | 2024-11-08 11:42
20241210 | 20241210014 | 14 | Pre-bid meeting | The non-mandatory pre-bid meeting scheduled for this project is not a convenient time for estimating staff of contractors since it is the morning of the November bid letting. Please consider revising the day/time. Thank you. | An addendum has been issued to change the date from November 12 to November 19, at 2:00 PM. | Mike Coleman | 2 | 2024-11-07 09:33 | 2024-11-08 11:42
20241210 | 20241210014 | 14 | Pre-Bid Meeting | Please move the meeting to a different day after November 12th. It is currently the same day as the November WIDOT letting and before the 11&#58;00AM deadline for the letting. | An addendum has been issued to change the date from November 12 to November 19, at 2:00 PM. | Mike Coleman | 3 | 2024-11-08 08:00 | 2024-11-08 11:42
20241210 | 20241210014 | 14 | Geotech report for the retaining wall | Please provide the link to the geotech reports for the retaining walls | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/bct5chcl3mtbvcm4w4shti6in819929o or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 4 | 2024-11-13 14:03 | 2024-11-25 08:44
20241210 | 20241210014 | 14 | Non-Mandatory Pre-Bid Meeting | Can a virtual Teams meeting option be added to the Non-Mandatory Pre-Bid Meeting? | No, a Teams meeting will not be provided for this meeting. | Mike Coleman | 5 | 2024-11-14 14:19 | 2024-11-18 12:14
20241210 | 20241210014 | 14 | Miscellaneous Quantities | Can the miscellaneous quantities for the storm sewer related items be provided in Excel format? | The drainage spreadsheets can be found at the following location: https://wisdot.box.com/s/bct5chcl3mtbvcm4w4shti6in819929o or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 6 | 2024-11-14 15:08 | 2024-11-18 12:29
20241210 | 20241210014 | 14 | Geotechical Reports | Please provide all geotechnical reports related to this proposal. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/bct5chcl3mtbvcm4w4shti6in819929o or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 7 | 2024-11-14 16:35 | 2024-11-18 12:30
20241210 | 20241210014 | 14 | Earthwork Summary | Is the MSE Wall backfill quantity excluded from the Embankment quantity? Is the 2&#39; undercut for the clay liner included in the Common quantity? | Yes, MSE Backfill is excluded from the Embankment quantity. It is paid for using the bid items: -Wall Concrete Panel Mechanically Stabilized Earth R-44-28 -Wall Concrete Panel Mechanically Stabilized Earth R-44-52 -Wall Concrete Panel Mechanically Stabilized Earth R-44-53 Revised earthwork for Pond APC that includes excavation common for the clay liner will be included in Addendum #2. | Mike Coleman | 8 | 2024-11-15 12:12 | 2024-11-25 08:38
20241210 | 20241210014 | 14 | Storm Sewer Backfill | Please confirm per construction details on sheets 85 &amp; 99 of the plan that all storm sewer pipe for the project, foundation backfill only needs to go 1 foot above top of pipe and that trench backfill can be onsite native material? Which defers from normal that storm sewer trench backfill typically has to meets spec for 209.2 or 520.2.5.2 and is to top of subgrade. | The detail on page 85 is only intended for the sanitary force main. The water main will use the same bedding but the backfill can be a native or other clean material. The special provisions reference the Grand Chute standard specifications for specific material type. The detail on page 99 is for storm sewer and will be updated in addendum #2 to reference the pertinent sections of the standard specifications. | Mike Coleman | 9 | 2024-11-18 11:18 | 2024-11-25 08:39
20241210 | 20241210014 | 14 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/bct5chcl3mtbvcm4w4shti6in819929o or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 10 | 2024-11-18 17:02 | 2024-11-25 09:47
20241210 | 20241210014 | 14 | B-44-340 Pier Details | On sheet 19 of the plans for structure B-44-340, the alignment is showing the girders running E-W instead of N-S. Can a corrected plan with the correct alignment be provided? | The plan sheet will be updated in an addendum. | Mike Coleman | 11 | 2024-11-19 10:09 | 2024-12-02 11:44
20241210 | 20241210014 | 14 | Rebar Weights | Please check the rebar weights for the B-44-339 specifically and the overall rebar weights for line items 158 and 160. They appear to be off. | The rebar weights for B-44-339 have been updated. The estimate of quantities will be updated in a future addendum. | Mike Coleman | 12 | 2024-11-19 14:50 | 2024-11-25 09:50
20241210 | 20241210014 | 14 | Concrete pavemnt 10-1/2" special | It is unclear to me if dowel bars will be required in the 4-0&quot; concrete pads below S-56 and S-42 concrete barriers adjacent to 10-1/2&quot; pavement along the mainline. | Dowel bars are not required for the 4â€™4â€ portion of the concrete payment under the concrete barrier. The construction detail will be updated in an addendum. | Mike Coleman | 13 | 2024-11-19 16:33 | 2024-12-02 11:45
20241210 | 20241210014 | 14 | Reconstructing Manholes | Please provide what type/size of manhole each reconstruction is for this item. Also where previous manholes constructed without a cover (top lid)? If so how is the new covers paid for? | The plan sheet will be updated in a future addendum. | Mike Coleman | 14 | 2024-11-20 08:44 | 2024-12-02 11:46
20241210 | 20241210014 | 14 | Storm Sewer Plug | Please provide size of each storm sewer plug needed of every location. | All pipe size information is provided within the storm sewer plan and profile sheets to influence the size of the temporary plug required. | Mike Coleman | 15 | 2024-11-20 09:02 | 2024-12-02 11:47
20241210 | 20241210014 | 14 | Rigid Inclusion Piles Size & Quantity | Please confirm the pile size for the rigid inclusion piles. Drawings &amp; schedule of prices don&#39;t appear to match. Quantity based on charts on sheet 77-80 appears to be different than bid quantity. | The pile size (Piling CIP Concrete 12 3/4 x 0.375-Inch) shown in the plan details and miscellaneous quantity tables is correct. The Estimate of Quantities (EOQ) will be updated to reflect the correct bid item, Piling CIP Concrete 12 3/4 x 0.375-Inch, in a future addendum. The quantity in the EOQ and miscellaneous quantities was checked against the table in the construction details. The total quantity in the EOQ and miscellaneous quantities matches the total length of CIP in the construction details table. When calculating the CIP length, note that not every station listed in the table includes CIP. Also, there are some stations where only 3 or 4 CIP shafts are required instead of 5. Additionally, the cutoff elevation for each CIP extends 0.5 feet into the rigid inclusion cap. The Rigid Inclusion-Driven Pile construction detail will be updated to show the location of the Rigid Inclusion Cutoff Elevation and will be included in a future addendum. | Mike Coleman | 16 | 2024-11-20 09:58 | 2024-12-02 11:48
20241210 | 20241210014 | 14 | Existing RR Substructure Units | Can the Department provide information regarding whether the substructure units from previous structures B-44-15 and B-44-464 were completely removed? Based on the assumed location of the previous substructure units, it is believed that they would be in conflict with the proposed shoring and construction of the new substructure units. The plan does not provide information regarding the status of these previous substructure units and this prevents the contractor from being able to design a shoring plan based on the in field conditions. | The department cannot be sure the entire substructure units were completely removed as standard spec 203.3 only requires them to be removed 2' below grade or such that they don't interfere with the new construction. The department will pay separately for removing unforeseen structures within the limits of the Excavation for Structures bid items as specified in standard spec 206.5.1(4). Any unforeseen structure removal paid separately under 206.5.1(4) could necessitate additional shoring and is covered in 206.5.2(2). | Mike Coleman | 17 | 2024-11-20 16:06 | 2024-12-04 05:59
20241210 | 20241210014 | 14 | STH 15 Interchange/Capitol Drive Project updated schedule | Can the updated schedule for Project 1130-64-76/81 be shared with prospective bidders, they could have an idea on the timing of available access to 41 from STH 15 and STH 15 Ramps when they are closed and/or restricted. | Please refer to the STH 15/Capitol Drive proposal (February 13, 2024 letting, Proposal 018) for dates relevant to this contract. To date, there have been no material changes to the project schedule for the STH 15/Capitol Drive project (1130-64-76/81). | Mike Coleman | 18 | 2024-11-22 14:13 | 2024-12-04 06:00
20241210 | 20241210014 | 14 | Storm Sewer Removals | Are the storm sewer removals to be backfilled the same as the new storm sewer trenches which the special provision call for using native materials excavated for the trench? | Storm sewer removals should be backfilled per the requirements of standard spec 204.3.2.2.1 (13). | Mike Coleman | 19 | 2024-11-22 15:11 | 2024-12-04 06:00
20241210 | 20241210014 | 14 | Construction Detail - Concrete Barrier Fixed Object Protection Type S56 Special | The fixed object protection type S56 special construction detail on sheet 67 of the plan appears to have the incorrect scale/dimensions. Please profice an updated detail. | The plan sheet will be updated in a future addendum. | Mike Coleman | 20 | 2024-11-26 08:58 | 2024-12-02 11:49
20241210 | 20241210014 | 14 | Lynndale Drive Typical Section and Plan Detail | Please provide clarrification on the lane width and barrier wall location for the NB Outside lanes on Lynndale drive. The typical section on sheet 36 does not coincide with the plan details on sheet 257 and 258 with respect to pavement widths and barrier wall location. Please provide clarrification on barrier wall locations, pavement width, and pay limits of approach slab and concrete pavement 9 1/2-inch shoulder. | The plan sheets will be updated in a future addendum. | Mike Coleman | 21 | 2024-11-26 09:27 | 2024-12-04 06:03
20241210 | 20241210014 | 14 | Removing Cover Plates | Line number 864 Removing Cover Plates does not appear in the miscellaneous quantity sheets so I cannot tell where they are or verify the quantities. It looks like it might tie out the note about in the strucutre tables that say &quot; Existing structure to be reconstructed, casting only&quot; but the quantities do not tie out with the other bid items. | The removing cover plates MQâ€™s can be found on page 907 of the advertised plans. | Mike Coleman | 23 | 2024-11-26 13:30 | 2024-12-04 06:02
20241210 | 20241210014 | 14 | Concrete Barrier S56A | Can you please provide additional information on the need for the 4 locations of Concrete Barrier S56A Wall. Per the plan cross sections it does not appear that an S56A wall is necessary as there is no opposing roadway adjacent to the wall since there is a median space between the NB and SB roadways. Should this wall be designated as C and not A? | The Concrete Barrier Type S56A is being utilized where median drains are in superelevated areas or one roadway is higher than the other. The purpose of the S56A barrier is to provide a flat area in the median for the median drain, ensuring water in the area between the median concrete barrier does not bypass the median drain. If the area between the median barrier is constructed on a slope, water will not drain into the median drain. | Mike Coleman | 24 | 2024-11-26 13:46 | 2024-12-04 06:03
20241210 | 20241210014 | 14 | Removing casting bolts | Plan sheet 101 shows &quot; Special Provision Article 13.11- Removing Casting Bolts Locations - Project 1130-64-72 There is no bid item for removing casting bolts and Article 13.11 is for Stone Ditch Checks Not sure what to do with this information. | The reference to the article number in the table will be removed. The plan sheets will be updated in a future addendum. | Mike Coleman | 25 | 2024-11-26 17:00 | 2024-12-04 06:09
20241210 | 20241210014 | 14 | Lynndale Ave Qtys | Is there quantities for the various stages of Lynndale Drive? Stage 1 work, stage 2 etc. | The sequence of work on Lynndale Drive is provided with the B-44-348 plans and on the traffic control sheets. The roadway quantities for Lynndale are broken out by direction which also corresponds with the staging approach for building the box culvert. Northbound Lynndale grading and paving is anticipated to be completed in Stage 1A and 1B. Southbound Lynndale grading and paving is anticipated to be completed in Stage 1C and 2A. | Mike Coleman | 26 | 2024-11-26 20:19 | 2024-12-04 06:09
20241210 | 20241210014 | 14 | Emergency Patching | As it pertains to the Emergency Patching Mobilization item, is the contractor responsible for Mobilizing during the Winter Shutdown period? | Yes, the emergency mobilizations may be needed for the full duration of the contract. | Mike Coleman | 27 | 2024-11-27 09:34 | 2024-12-05 06:04
20241210 | 20241210014 | 14 | Cross-over HMA Thickness | According to Sheet 3 Asphaltic Surface and Surface Temp has a cross section of 3.25â€ Binder and 1.75â€ Surface. Per Specification 460.3.2(1) the contractor is allowed a Max Single Layer thickness of 5â€ for 19mm mixes, will the 5â€ single layer be allowed specifically for use on cross-overs? | Two lifts will be required for the asphaltic surface items as noted on page 3. | Mike Coleman | 28 | 2024-11-27 09:35 | 2024-12-05 06:05
20241210 | 20241210014 | 14 | Earthwork Summary | On Plan Page 783, the Earthwork Summary includes Common Excavation and Embankment quantities for R-44-52 and R-44-53. It seems that these quantities may already be accounted for in other locations, such as the Mainline and Ramps. Please confirm if this assumption is correct. If not, please provide additional information to justify these required quantities. | The additional excavation and fill quantities for Structures R-44-52 and R-44-53 are included in the earthwork table based on the details shown in the structure plans on sheets 1506 and 1521. | Mike Coleman | 29 | 2024-11-27 10:06 | 2024-12-05 06:05
20241210 | 20241210014 | 14 | Slotted Vane Drains temporary and Permanent | The special provisions tell us to follow the Standard Detail drawing for vane drain construction. This appears to apply to both permanent and temporary. It does not appear that there is a SSD for Slotted van drain in this plan set. The only one I can find is SDD 8D 14 which is the pvc pipe and neenah castings. Other DOT project have been using the something other than this of the longer runs of slotted drains which this project has. Without a detail to reference and the special provisions lists nothing under materials I am at a loss. What are we supposed type of slotted drains are we to be bidding for this project? | The intent is to use SDD 8D14. The standard drawing will be added to the plan in a future addendum. | Mike Coleman | 30 | 2024-11-27 11:32 | 2024-12-04 06:10
20241210 | 20241210014 | 14 | Contractor Requests for Construction Access | Per Article 2.3 of the Special Provisions, the contractor is to submit proposed new ingress/egress access points to the Department for approval. Historically access has been difficult to obtain. Is it reasonable to assume that daytime access from IH41 to the work zone will be granted, or will offpeak lane closures be the only access from IH 41? | Daytime access will be granted if the design meets requirements as stated in section 4.5 â€œConstruction Accessâ€. All ingress/egress access points will be reviewed and approved by field staff. Each access point will be reviewed on its own basis. | Mike Coleman | 31 | 2024-11-27 12:56 | 2024-12-05 06:06
20241210 | 20241210014 | 14 | B-44-348 Temporary shoring | The geotech report for B-44-348 notes that temporary shoring install by vibratory hammer is not recommended. Will the use of a high frequency vibratory hammer be allowed for the installation of temporary shoring at B-44-348? | Based on the soil types and groundwater conditions, vibratory installation methods (regardless of frequency) are not recommended. | Mike Coleman | 32 | 2024-12-02 12:17 | 2024-12-05 06:06
20241210 | 20241210014 | 14 | N-44-11 , N-44-20 Posts | Will the noise barrier posts require touch up painting after installation? | See article 18.1, section C.1, paragraphs 3, 4 and 5 of the proposal for this contract for requirements at delivery and during construction. | Mike Coleman | 33 | 2024-12-02 12:21 | 2024-12-09 09:52
20241210 | 20241210014 | 14 | Maintain and Remove Concrete Barrier Temporary Left in Place Quantity | Has the department verified the SPV.0090 Special 0300 Maintain and Remove Concrete Barrier Temporary Left in Place quantity as discussed at the pre-bid meeting? | The quantity has been verified. Due to the overlap in schedules with projects 1130-64-71/72/87 and 1130-64-76/81 not all of the barrier has been delivered and installed with the 1130-64-76/81 contract at the time of this letting. Refer to Addendum No.2 for the anticipated station ranges and dates of transfer. | Mike Coleman | 34 | 2024-12-02 14:22 | 2024-12-05 06:09
20241210 | 20241210014 | 14 | R-44-28 Panel Sizes | Wall R-44-28 specifies that &quot;MSE Wall panels shall be 5&#39; x 5&#39; only&quot;. Can R-44-28 be constructed with 5&#39; x 10&#39; panels to match the other walls? | R-44-28 cannot be constructed with 5x10 panels. | Mike Coleman | 35 | 2024-12-02 15:51 | 2024-12-09 09:55
20241210 | 20241210014 | 14 | Plan Details | Sheet NUmber 9 Typical Section. Detail shows existing concrete pvmt 24 feet wide and on sheet number 24 it shows cutting off the pvmt at 22 ft for the grading work. Please clarify - will there be a saw cut required for this? | HMA shoulder widening begins at 24-foot offset from the reference line along the existing edge of travel. The two-foot dimension for the temporary concrete barrier is not labeled. Please refer to removal plan sheets for additional information related to locations where sawcuts are required along the existing edge of travel. | Mike Coleman | 36 | 2024-12-02 17:01 | 2024-12-05 06:11
20241210 | 20241210014 | 14 | sheets 1347 and 1387 - note B1 - abutment anchorage, lateral loads transferred to abutment | Are the loads given perpendicular to the backwall or parallel to the bridge beams? see sheets 1347 and 1387 - note B1 - abutment anchorage, lateral loads transferred to abutment | Loads have been updated. The updated loads are reported perpendicular to the abutment. TU = 0.55 k/ft BR = 0.57 k/ft WS = 0.14 k/ft WL = 0.08 k/ft Will be added to a future addendum | Mike Coleman | 37 | 2024-12-03 05:18 | 2024-12-05 06:11
20241210 | 20241210014 | 14 | structure B-44-339 and B-44-340, sheets 1347 and 1387 - note B1 - abutment anchorage, lateral loads | Are the loads given perpendicular to the backwall or parallel to the bridge beams? see sheets 1347 and 1387 - note B1 - abutment anchorage, lateral loads transferred to abutment for structure B-44-339 and B-44-340 | Loads have been updated. The updated loads are reported perpendicular to the abutment. TU = 0.55 k/ft BR = 0.57 k/ft WS = 0.14 k/ft WL = 0.08 k/ft Will be added to a future addendum | Mike Coleman | 38 | 2024-12-03 05:21 | 2024-12-05 06:12
20241210 | 20241210014 | 14 | South Abut. Diaph. | In structure B-44-339 There are 9 abutment diaph. are they made of steel or concrete? | An updated Steel Diaphragms B-44-339 quantity will be provided with a future addendum. There are no steel diaphragms at the abutments. All abutment diaphragms are to be concrete, as shown in the plans. | Mike Coleman | 39 | 2024-12-03 09:30 | 2024-12-05 06:13
20241210 | 20241210014 | 14 | Allowable MSE wall systems | On Sheet 1486, structure R-44-28, there is a note under design data that says &quot;Only wall concrete panel MSE systems that use strip soil type reinforcement that are hinged at the panel connection can be used for the project.&quot; Can welded wire soil reinforced systems that are on the approved products list be allowed? What is the justification for sole sourcing the MSE walls to one supplier on this project? | A welded wire soil reinforced system that is on the approved products list can be utilized for wall R-44-28 only. Plan sheet will be updated with a future addendum. | Mike Coleman | 40 | 2024-12-03 13:57 | 2024-12-06 07:35
20241210 | 20241210014 | 14 | Earthwork Data | Stage 3 Ditching - X sections start at sta 558+00 and Earthwork Summary says sta 569+00 and the data sheet starts at sta 575+50 can you clarify this information. New data sheet? | Earthwork summary and earthwork data sheets are updated in an addendum. | Mike Coleman | 41 | 2024-12-03 14:06 | 2024-12-09 09:59
20241210 | 20241210014 | 14 | Clarification for preboring - fill required and driving vs seating | There appears to be a conflict between the special provisions 11.4 Driven Piles and the prebore note on sheet 1347 of 2596 Struct B-44-339 &amp; sheet 1387 of 2596 Structure B-44-340. Plan note states..â€backfill pier pre-bored with cement grout to the bottom of the pier cap {I am assuming bottom of pier footing} . Special Provision says â€œbackfill within the rock or consolidated material with cement groutâ€¦{later} backfill the piles with sand or other engineered materialâ€ ALSO Plan note states to â€œdrive to required resistanceâ€ whereas the special provision states to â€œfirmly seat piles after preboringâ€. Please clarify. |  |  | 42 | 2024-12-03 16:08
20241210 | 20241210014 | 14 | Earthwork Data | Can you provide earthwork data for Stage 3 sta 537-569? | The earthwork data for Stage 3, Station 537 to 569, is provided in several different locations. Earthwork data for the median widening can be found on page 1592 (537 â€“ 551). Page 1594 contains earthwork data for the WND crossover (552 â€“ 555), page 1596 for the Stage 4B crossover (557 â€“ 567) and page 1597 for Stage 4A crossover (567 â€“ 569). | Mike Coleman | 43 | 2024-12-03 16:41 | 2024-12-06 07:41
20241210 | 20241210014 | 14 | Staging of Work | The narrative for Stage 4 A &amp; B says Ramp NLB is closed during this work. The staging in the plan shows as open. Can you clarify this. | All ramps from IH-41 to STH 15/CTH OO will remain open during Stage 4 during peak travel periods. | Mike Coleman | 44 | 2024-12-03 16:44 | 2024-12-05 06:14
20241210 | 20241210014 | 14 | Earthwork Qtys | Will there be an addendum for earthwork qtys for removals of temp cross overs? For example removing NLA temp connection; the median work in stage 5; stage 2 cross overs; etc? | An addendum for removing the temporary crossovers is not required as the removals are already accounted for in the earthwork quantities. For example, the removal of the median cross over south of STH 96 (STA 525 to 535) is included in the Earthwork Summary Table on page 783. The removal of the Stage 2B crossover between STH 96 and the railroad structures is included within the earthwork for 41 NB, 41 SB and WND. The removal of temporary crossovers in the -72 project limits is handled similarly in that it is included with the end areas of the various staged mainline or ramp quantities. | Mike Coleman | 45 | 2024-12-03 19:36 | 2024-12-06 07:43
20241210 | 20241210014 | 14 | R-44-28 Rigid Inclusion Cap Rebar | On sheet 76 there is a note that rebar reinforcement is incidental to the cap for the rigid inclusion at structure R-44-28. In the misc quantities on sheet 809, there are listed quantities for the bar steel reinforcement in the rigid inclusion caps. Is the rebar in the caps to be incidental to the concrete masonry bridges pay item or will this be paid under the bar steel reinforcement item? | The note indicating rebar reinforcement is incidental to the cap will be removed and a new sheet will be issued in a future addendum. | Mike Coleman | 46 | 2024-12-04 10:05 | 2024-12-06 07:44
20241210 | 20241210014 | 14 | slotted drains | Can you please provide construction details for, Special Drain slotted vane 1,207 lf permanent Special Drain slotted vane temporary 1,301 lf | Please see SDD 8D14 Slotted Vane Drain for details. The SDD will be included in a future addendum. | Mike Coleman | 47 | 2024-12-04 11:32 | 2024-12-06 07:45
20241210 | 20241210014 | 14 | Lynndale Qtys | Question 26- we are looking for the earthwork data sheets for Lynndale Ave. I do not see them in the plan data tables or the excel data sheet you provided(no tab on bottom of sheet) or the earthwork summary sheet. The plan staging we see and is good but the actual qtys we can not find. | The earthwork data sheets will be provided in a future addendum. | Mike Coleman | 48 | 2024-12-04 12:01 | 2024-12-06 07:46
20241210 | 20241210014 | 14 | Stageline temp shoring at structure B-44-339 & 340 | The total estimated quantities tables for each structure shows temporary shoring only at Piers 1 &amp; 2. The stage line shoring at the abutments for both structures does not appear to be quantified. Please clarify. | The temporary shoring at the abutments is included in the Temporary Shoring B-44-340 pay item (511.1200.0804). The quantities for Pier 1 and Pier 2 include shoring at the abutments. | Mike Coleman | 49 | 2024-12-04 14:40 | 2024-12-06 07:48
20241210 | 20241210014 | 14 | Rebar totals for 1130-64-72 error | The Estimate of Quantities shows 322,426 LB for item 158, Bar Steel Reinforcement Structures. Adding up the structures included in this, B-44-347/348 the total for this item is 224,510. The proposal totals also match up with the EOQ table. | The rebar totals for B-44-347/348 are correct in the structure plans. | Mike Coleman | 50 | 2024-12-04 15:22 | 2024-12-09 10:36
20241210 | 20241210014 | 14 | Lynndale Ave Earthwork | Regarding your response to the previously submitted Question 26, you are implying the earthwork quantities for the Lynndale Avenue work are included within the provided MQ in bid documents. They are not included. Please review and include them. |  |  | 51 | 2024-12-05 10:02
20241210 | 20241210014 | 14 | Ground Improvement | Per the construction detail on page 75 of the plan, Backfill Structure Type A is shown to be placed along the left and right side of the Load Transfer Platform. Please confirm the top extent of the pay limits for both sides. Would the limits be flush with the top of the Load Transfer Platform? |  |  | 52 | 2024-12-05 10:06
20241210 | 20241210014 | 14 | Structure Backfill | The details on page 1349 and 1389 of the plan for Structure B-44-339/340 show Backfill Structure Type A. A bid quantity is not included in the estimated quantities on page 1347 and 1387. Please review and add the missing quantities. |  |  | 53 | 2024-12-05 10:09
20241210 | 20241210014 | 14 | 10.2 QMP Ride for PCC Riding Surfaces Excessive Localized roughness | Based on E.2.2 Pay Adjustment â€“ Localized Roughness is it the Department&#39;s intent to assess disincentive even if areas are corrected with diamond grinding? In reviewing the specification should a paragraph be added to section E.2.2 similar to E.2.1 Pay Adjustment â€“ IRI (4) stating something to the effect that no disincentives will apply after corrective work? | Table 8 within the special provision article outlines the Localized Roughness as there are no incentives or disincentives for Localized Roughness. The corrective action is what is required to be conducted when localized roughness is above 200 inches/mile when posted vehicle speed is >45 mph and is to be corrected to <175 inches/mile. The requirement is to correct the work to the required performance specification. The goal of the SPV is receive the best possible ride, hence the requirement of corrective action. | Mike Coleman | 54 | 2024-12-05 10:31 | 2024-12-09 10:07
20241210 | 20241210014 | 14 | Pre-boring B-44-339/340 | Pre-boring is called out in the structure plans for B-44-339 &amp;B-44-340. It states, &quot;pre-bore to required elevation then drive to required capacity...&quot; What is the required elevation to pre-bore to at the abutments and piers for the bridge structures? |  |  | 55 | 2024-12-06 14:10
20241210 | 20241210015 | 15 | B-20-253 Proposal 15 & Proposal 19 | It appears the structure plan for proposal 15 and 19 the same, B-20-253, can this be reviewed. | An addendum will be issued by Central Office with the correct structure plans from BOS. | Mike Coleman | 1 | 2024-11-12 15:33 | 2024-11-15 07:30
20241210 | 20241210016 | 16 | Schedule | Contractor is requesting a copy of the DOT&#39;s estimated schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/4oh975wed5lzp6s1xzoz6eee8z4kj8k8 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-11-19 11:07 | 2024-11-20 07:07
20241210 | 20241210016 | 16 | Storm sewer and Culvert Patching | Sheet 8 of the plans show patching with 3 inches of asphalt in the storm sewer and culvert crossing patches. Does the DOT want to patch those areas with the minimum existing depth of 6.25 inches? | Sheet 8 of the plans shows patching with 8â€ of asphalt, not 3â€. As the existing pavement thickness varies throughout the project, 8â€ was chosen for consistency throughout the project to better define this quantity for the contractor. | Mike Coleman | 2 | 2024-11-19 11:27 | 2024-11-20 07:09
20241210 | 20241210016 | 16 | Soil Borings | The plan states that bedrock may be found during guardrail installation. It also shows at least 3 soil boring locations that were taken for this project. Can you explain where these boring logs are found? | Borings were taken at various locations within the project limits during preliminary design. Not all boring locations are noted in the plan. Only those locations with highest potential for encountering rock were shown in the plans. Information for all borings taken for this project can be found at the following location: https://wisdot.box.com/s/4oh975wed5lzp6s1xzoz6eee8z4kj8k8 The boring information is for information only and the draft plan sheets on which the boring information is provided is from preliminary design and not for bidding purposes. | Mike Coleman | 3 | 2024-12-06 10:48 | 2024-12-09 09:10
20241210 | 20241210017 | 17 | Geotechnical Report | Please provide a copy of geotechnical report. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/gvwa4eug2dgebxpsy3soa5i0sw2dyypx or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-11-30 20:08 | 2024-12-02 07:25
20241210 | 20241210017 | 17 | granular backfill | what is the intended use of the 1000 cy of granular backfill listed on sheet 107? |  |  | 3 | 2024-12-05 06:56
20241210 | 20241210017 | 17 | Bid Items | There is ped curb shown on sheet 21, but there is no bid item. There seems to be a sheet missing showing Sta 156 to 160 on CTH EE. | â€“ item added in addendum that was sent for question #3 â€“ I believe this is in reference to the intersection detail sheets, (sheets 9-21). These arenâ€™t intended to include the entire project, just intersections and locations where additional details are needed (beyond what is included in other sheets). For a full overview of the project, reference the plan and profile sheets included later in the plan set. | Mike Coleman | 4 | 2024-12-05 15:52 | 2024-12-06 15:35
20241210 | 20241210017 | 17 | Pulverizing Existing Asphalt | Will the department allow the contractor to pulverize existing asphalt and basecourse and reuse this material as basecourse without a sieve analysis or scaling of material? |  |  | 5 | 2024-12-06 12:58
20241210 | 20241210018 | 18 | Structure Plans Missing | Structure plans are not included. | An addendum will be issued to add the plans | Mike Coleman | 1 | 2024-11-06 15:15 | 2024-11-15 07:32
20241210 | 20241210018 | 18 | Department Construction Schedule | Can the department provide the design construction schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/4p6021yakswfbzu40079qy4s6ql9jlml or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-11-20 13:31 | 2024-11-25 11:06
20241210 | 20241210018 | 18 | excavation table | Will the excavation table be updated now the structures have been included? It is missing C-59-121 and seems to be incomplete in other areas. | This is a unique location, where both the existing and proposed box are basically right underneath the asphalt and the new structure will be almost the same length. All the earthwork required for the box and grading falls within the boundaries of Excavation of Structures and the Structural Backfill items. If a line for this structure was added to the earthwork table all it would show is a small amount of available material. This material would then be wasted, and none of this would end up in a bid item. Other structure locations were also checked and verified that they have the same issue to a lesser degree. | Mike Coleman | 3 | 2024-11-20 19:16 | 2024-11-26 06:30
20241210 | 20241210018 | 18 | Railing Pipe anchors on C-59-121 | Can the anchors for the rail on C-59-121 be epoxy anchors, which are typically an acceptable alternative to the cast in place anchors for this type of rail? | Epoxy anchors are not an acceptable alternative, donâ€™t meet minimum edge distance per ACI. | Mike Coleman | 4 | 2024-11-22 10:48 | 2024-11-25 13:20
20241210 | 20241210018 | 18 | Removing structure | structure @ Sta 189+62 has 2 removal items. Are there 2 structures there? | Yes, it is called out twice in error. An addendum will be issued to remove one. | Mike Coleman | 5 | 2024-11-22 13:06 | 2024-11-25 11:42
20241210 | 20241210018 | 18 | Anchor Post Assembly, Top Mounted | Page 33 has a note to see SDD Anchor Post Assembly, Top Mounted for installation onto the 2655 structure. It appears that the structure also flows under the 2 radii of the intersection. 1. Are these posts needed for these 2 radii also? 2. Where is the bid item for each of these top mounted posts? 3. Is the rail through these top mounted posts paid for as MGS 3K or is there a missing MGS 3HS bid item? | An addendum will be issued to clarify. | Mike Coleman | 6 | 2024-11-25 09:01 | 2024-12-02 11:52
20241210 | 20241210018 | 18 | Project Completion Date | With this project located in the southern zone and WisDOT Standard Specification 450 recommending asphalt placement between April 15th and November 1st, would the department consider moving the completion date for this project to October 31st to allow greater scheduling flexibility for the contractor? |  |  | 7 | 2024-12-05 12:25
20241210 | 20241210018 | 18 | Bid Items | 1. The plans show 8 and 9&quot; pavement, but there is only an 8&quot; Item, please advise. 2. The plans show a detail for the steps, but no bid item. | In taking a closer look at the plans we will be taking care of this questions in two different ways. First, we will change the couple of small areas of 9-Inch Concrete Pavement in the plans to 8-Inch pavement. They were quantified as such in the estimate and should have been changed on the plans but were not. Secondly, we will be using the item 602.1500 for Concrete Steps to take care of the other part of the question. An addendum will be issued | Mike Coleman | 8 | 2024-12-05 15:48 | 2024-12-06 15:34
20241210 | 20241210019 | 19 | Wrong Structure Plan | Plan set includes structure B-20-253 which is for proposal #15 in the December letting. No plans included for B-20-257. | An addendum will be issued by Central Office with the correct structure plans from BOS. | Mike Coleman | 1 | 2024-11-06 15:17 | 2024-11-15 07:27
20241210 | 20241210019 | 19 | Job 19 | The plan and special provisions do not match for the structure to be reconstructed. We believe it should be a different plan to match what the specials are describing. Please verify the bridge inserted into the plans. | An addendum will be issued by Central Office with the correct structure plans from BOS. | Mike Coleman | 2 | 2024-11-12 10:17 | 2024-11-15 07:29
20241210 | 20241210019 | 19 | Incorrect Structure plan | the bridge plan included in this planset is for B-20-253, the same structure as in proposal #15. | An addendum will be issued by Central Office with the correct structure plans from BOS. | Mike Coleman | 3 | 2024-11-12 13:52 | 2024-11-15 07:29
20241210 | 20241210019 | 19 | B-20-253 Proposal 15 and Proposal 19 | It appears the structure plan for proposal 15 and 19 are the same, B-20-253, can this be reviewed. | An addendum will be issued by Central Office with the correct structure plans from BOS. | Mike Coleman | 4 | 2024-11-12 15:36 | 2024-11-15 07:30
20241210 | 20241210024 | 24 | Geotechnical Report | Can the Geotechnical Report for this project be provided? | The project was scoped as an RSRF10, which is a mill and overlay perpetuation project. Therefore, no detail soils work was completed. We did do pavement cores on page of 11 of the plan. The core locations are also plotted on the plan and profile sheets starting on page 41 of the plan. | Mike Coleman | 1 | 2024-11-25 09:49 | 2024-11-25 13:10
20241210 | 20241210024 | 24 | HMA Test Strip | The job calls for 2 density test strips but in the HMA PWL table it shows the lower layer mainline desity being accepted by ordinary compaction, also the finished typical section show s the main road being only 11ft wide but the PWL table shows it being 12ft wide wich one is correct? | Hello, we have reviewed and there was an error in the table. An addendum will be submitted to correct and address the questions. | Mike Coleman | 2 | 2024-11-25 12:10 | 2024-11-26 11:51
20241210 | 20241210024 | 24 | C-71-029 Top Mount Posts | Plan sheet 12 shows (6) top mount posts required for the guardrail. Should item 614.8010 be added? | The existing culvert has a bridge railing system mounted on it. That existing system is going to remain in place. The new guardrail system will attach to the existing bridge railing system. The plan sheet will be revised to remove the anchor posts note and identify attaching to the existing bridge railing system. The location of the beam guard will also be adjusted to align with the bridge railing system. | Mike Coleman | 3 | 2024-12-03 09:07 | 2024-12-05 06:16
20241210 | 20241210024 | 24 | Removing Existing Guages | What exactly is this item? The special provision doesn&#39;t make it very clear. | Structure B-71-0127 had access grates and gauges installed that monitored structure backfill in a previous project and are no longer needed. This item is intended to call out the removal of those access grates, gauges with work conforming to standard spec 204. | Mike Coleman | 4 | 2024-12-04 12:48 | 2024-12-06 07:50
20241210 | 20241210024 | 24 | Pipe Culverts | The plans call out Class III-A Non-Metal pipe for the 42&quot;, 48&quot;, 72&quot; on pages 18 and 19. However, in the MQ&#39;s it calls out RCP and the bid items call for RCP. Can you please clarify what type of pipe is to be used? | RCP pipes are to be used for these. The plan sheets will be updated to reflect this. The MQ and bid items are correct. An addendum will be issued. | Mike Coleman | 5 | 2024-12-04 13:39 | 2024-12-06 07:49
20241210 | 20241210024 | 24 | time contraints | Specials state &quot;Work shall occur at one location at a time with no work occurring at other cross culvert locations unless approved by the engineer&quot;. Only allowing a single crew working at one time will consume much of the 35 working days; can &quot;no work&quot; be clarified? | This language will be edited to: Do not close STH 173 or divert water at more than one culvert locations at the same time, unless approved by the engineer. The goal is to ensure cranberry growers have access and can move water as required to maintain their beds. The Department will add 10 working days to the contract. An addendum will be issued. | Mike Coleman | 6 | 2024-12-04 13:47 | 2024-12-06 07:47
20241210 | 20241210024 | 24 | PWL | Taking a deeper look at the PWL table, THere is Approx. 2800 tons of surface 4MT that will be paved over the binder layer of asphalt and roughly 7000 tons paved over a milled surface. With the 2 different underlying materials that will be paved over and the &quot;small&quot; amount of total tons, this should be looked at to change to QMP for all Air Voids and density. | The Table has been revised based on this and a previous question. PWL will be completed by coring see table in upcoming addendum. The upper layer total tonnage is 10,559 and the lower layer tonnage is 4,166. An addendum will be issued | Mike Coleman | 7 | 2024-12-04 14:28 | 2024-12-06 07:41
20241210 | 20241210024 | 24 | Barrier System Grade Shape Finish Restoration | Is the intent to pay for restoration under applicable bid items rather then being incidental to the barrier system grade shape finish item? The MQS and overall bid quantities seem to show it this way. | Yes, restoration at guardrail locations was intended to be paid under applicable bid items rather than being incidental to item 614.0010 Barrier System Grading Shaping Finishing. These restoration items were separated because there was additional restoration areas for culvert replacement locations with no guardrail. Bid Item 614.0010 will cover excavation, borrow and staking for grading at these locations | Mike Coleman | 8 | 2024-12-04 15:38 | 2024-12-06 07:36
20241210 | 20241210024 | 24 | Time Frame | Will the department consider adding more working days to the contract. With the amount of dewatering and diversion work needed for these and only being able to work on 1 pipe at a time, the time frame will be difficult to obtain | Yes, the department will increase the number of working days for the contract from 35 to 45 working days. An addendum will be issued. | Mike Coleman | 9 | 2024-12-04 16:17 | 2024-12-06 07:34
20241210 | 20241210024 | 24 | Traffic Control Covering Signs Type 1 | Is this item supposed to be in the plan? There is no covering signs mentioned in the plan or proposal. | That is not the correct bid item. That bid item will be deleted from the contract The bid item for Type 2 sign covering is 643.0920 will be added. This will be addressed in an addendum. | Mike Coleman | 10 | 2024-12-05 12:59 | 2024-12-06 07:34
20241210 | 20241210025 | 25 | HMA | Would the Department consider changing the mixes to Asphaltic Surface? | The HMA mix called out in the plan was requested by and approved by the sponsor in the Pavement Design Report and should remain as is. | Mike Coleman | 1 | 2024-11-21 09:03 | 2024-11-25 13:23
20241210 | 20241210026 | 26 | Culvert Patch Paving | I am questioning the need for paving the culvert patches by the end of each week of installation when the Highway is a closed road? | The paved culvert patches are being required to limit the possibility for the base and subgrade for the culvert transitions to be saturated in the case of a rain event. | Mike Coleman | 1 | 2024-11-25 11:52 | 2024-12-02 11:21
20241210 | 20241210026 | 26 | Removing Structure Minimal Debris B-26-13 | The existing structure is a three-cell CIP concrete box culvert with a CIP concrete floor at the stream bed. How is minimal debris spec. to be obtained with the CIP floor underwater? Is it expected that a cofferdam is to surrounded the portions to be removed? In that case will a cofferdam item be added to the contract? | Cofferdam is anticipated and shown on the Erosion Control plan Sheet 12. As outlined in the note on that page, and section 206.5.2(2) of the General Spec the cost is included in that pay item for Excavation for Structures. | Mike Coleman | 2 | 2024-12-02 14:22 | 2024-12-03 12:57
20241210 | 20241210027 | 27 | Geotech Report | Please provide the full geotech report for this project. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/pc63pl06ergxq48ft0fdsoco669jn97s or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-11-18 10:44 | 2024-11-19 10:13
20241210 | 20241210028 | 28 | Pedestrian Staging and Curb Ramps | Sheets 75 &amp; 76 have pedestrian staging (shown) for 2nd St, but not for 1st St and 3rd St. Are we correct to assume that 1st and 3rd East curb ramps are to be done in Stage 1, and 1st and 3rd West curb ramps to be done in Stage 2? Plan shows the Proposed Pedestrian Route continuing through all quadrants of the 1st and 3rd intersections without a detour for both stages. The same goes for Division St. | Pedestrian staging can be accomplished multiple ways as long as it follows the Special Provisions and Notes indicated on those sheets. | Mike Coleman | 1 | 2024-11-14 16:14 | 2024-11-20 11:06
20241210 | 20241210028 | 28 | Item | Will the department consider adding a Finish Project Roadway item to the job? | This will be added via addendum. | Mike Coleman | 2 | 2024-12-04 14:32 | 2024-12-05 13:28
20241210 | 20241210031 | 31 | Modified Thrie Beam Transition | Sheet 40 of the plan shows MODIFIED THRIE BEAM TRANSITION at STA 2119+89. There doesn&#39;t seem to be any details given or quantities shown in the Misc Quantities. What is the expectation and how is it being paid? | The note referring to Modified Thrie Beam Transition on sheet 40 directs to the standard installation labeled as Modified MGS Thrie Beam Transition on Standard Detail Drawing 14B26-05b on sheet 194. This is the Steel Thrie Beam Bullnose Terminal detail. Per the SDD, this is to be paid as MGS Thrie Beam Transition. The quantity for this installation is not currently shown in the Miscellaneous Quantity table and will be added via addendum. | Mike Coleman | 1 | 2024-11-19 09:01 | 2024-11-20 10:55
20241210 | 20241210031 | 31 | HMA Table | In the HMA acceptance table is it correct that the SMA mix is being accepted by PWL for both Air Voids and Density as the special provisions do not indicate this. Also in the table it lists the 2&#39; &amp; 3&#39; shoulders as PWL Density. Is this correct? Lastly, it has the 4MT mixes on the ramps &amp; Cty M/Hwy73 listed as PWL Density. Questioning this as well. Thank you | PWL Density classifications will be updated in the MQ table via addendum. | Mike Coleman | 2 | 2024-11-22 11:41 | 2024-11-27 06:04
20241210 | 20241210031 | 31 | Safety Island | The typical section shows new asphaltic surface within the safety island at CTH T. How are the removals of the existing asphalt within the island being paid? Will the department require 1 1/4&quot; base as backfill behind the proposed curb within the island for a pavement structure? | Removals are incidental to the adjacent curb and gutter item per standard spec 601.5.1 (2). Additionally, the spec requires placing aggregate base as required in excavated areas. | Mike Coleman | 3 | 2024-11-22 13:19 | 2024-11-26 11:55
20241210 | 20241210031 | 31 | Removing Concrete Pavement | Should there be an item for Removing Concrete Pavement at the Approach Slab and 11-Inch Concrete Pavement replacements? | Removing Concrete Pavement will be included in the Miscellaneous Quantities by addendum. | Mike Coleman | 4 | 2024-11-25 15:11 | 2024-11-26 11:55
20241210 | 20241210031 | 31 | Curb and Gutter 36 Inch TBT | What are the expectations for prepping the areas at the end of the structures for Concrete Curb and Gutter 36 Inch TBT? Should there be some sawing/removals/excavation items associated with those areas? | Removals are incidental to the adjacent curb and gutter item per standard spec 601.5.1 (2). Additionally, the spec requires placing aggregate base as required in excavated areas. Sawing will be added via addendum as it may be needed. | Mike Coleman | 5 | 2024-11-26 07:12 | 2024-11-27 07:53
20241210 | 20241210031 | 31 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/9o24pfdfedpryha6olid58iojsl2845i or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2024-11-30 09:11 | 2024-12-02 11:41
20241210 | 20241210031 | 31 | Prep Foundation For Asphaltic Paving | On sheet 25, it notes removing crack fill patching to a minimum depth of 4&quot; below the pavement surface. Could this item be changed to a linear foot pay item? Reason being, there is no patch size minimum listed and an undetermined amount of area that could be viewed as requiring prep. | Prepare Foundation for Asphalt Paving (1050-00-62), Item 211.0101 provides payment for the prescribed work under the standard specifications as an EACH item. The detail on sheet 25 provides additional detail of the work required for Prepare Foundation for Asphalt Paving. The measurement and payment remain as EACH per standard specification. | Mike Coleman | 7 | 2024-12-02 15:21 | 2024-12-03 12:55
20241210 | 20241210031 | 31 | Special Provisions - Traffic - Lane Closure Restrictions | Hello, just a general question as to why lane closures are not permitted during Sundays in August of 2025. Thank you. | Traffic volumes for the anticipated duration of the project were analyzed using WisDOTâ€™s Work Zone Traffic Analysis Tool. The traffic volumes within the project are significant enough on Sundays in August to warrant no lane closures due to the backups that would occur. | Mike Coleman | 8 | 2024-12-02 16:39 | 2024-12-03 12:54
20241210 | 20241210031 | 31 | Concrete Masonry Deck Repair | There appears to be a bust in the Concrete Masonry Deck Repairs. Please confirm quantities for the concrete in the joint repair/parapet repairs for the two bridge structures. | There was a computational error in the concrete masonry quantity. An addendum will be prepared to reduce the quantity. | Mike Coleman | 9 | 2024-12-03 10:31 | 2024-12-04 06:11
20241210 | 20241210031 | 31 | Guardrail at Structures | The special provisions state that new guardrail shall be installed after binder. The TBT curb &amp; gutter and surface drain installation will require a portion of the existing guardrail to be removed. Chances are the existing post spacing will not align with the proposed surface drain. The new guardrail installation is MGS where the existing is the old &quot;Class A&quot; so height difference would also come into play. Please detail the expectations of the guardrail replacements at the structures in the area of the TBT curb/surface drain installation. | There are numerous opportunities for construction to progress based on individual contractor means and methods. Specific means and methods will not be prescribed. It is understood that the TBT curb and gutter and the finished MGS guardrail installations are based on final roadway grades and will be relatively higher than the lower layer of HMA than standards define. The Prosecution and Progress article defines the duration that traffic can run on the lower layer of HMA. | Mike Coleman | 10 | 2024-12-04 07:33 | 2024-12-04 11:44
20241210 | 20241210031 | 31 | Installing and Maintaining Bird Deterrent | B-10-19 &amp; B-10-170 consist of joint repairs. Is bird netting required at the joint repair only and not the entire bridge? | Per Article 31, C.3.1: Using concrete screws, anchor lumber to bridge or culvert along perimeter of intended netting. The deterrent system is intended to prevent nesting in the area of proposed work. Those areas impacted by construction should be netted per the specification. | Mike Coleman | 11 | 2024-12-05 09:46 | 2024-12-06 07:33
20241210 | 20241210031 | 31 | Temporary Shoring Popple River | Given the depth of cut required for the wingwall replacement at the Popple River box culvert and the fact that there is a hard layer which does not provide enough toe, is the Department planning on adding a tie back item or is it to be incidental to the shoring item? | Per standard spec 511.2 - Provide a shoring design for each location where the plan requires temporary shoring. Provide a design by a Wisconsin professional engineer addressing the site requirements. Per 511.5 (2) Payment for the Temporary Shoring bid items is full compensation for designing and providing shoring; for providing a signed and sealed copy of the design; for removal or additional work required to leave in place; and for excavating, and backfilling. This is intended to be the complete shoring system. | Mike Coleman | 12 | 2024-12-05 10:15 | 2024-12-06 07:50
20241210 | 20241210032 | 32 | Geotechnical Report | Can the Geotechnical Report for this project be provided? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/2xuaawl4r7tb4hqspzfozvdyrl8dx526 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-11-25 09:50 | 2024-11-26 11:50
20241210 | 20241210032 | 32 | Pavement Marking | The current permanent bid items of 6&quot; epoxy and 4&quot; epoxy are being used by alternating the two through the entire project. The current standard is to used 6&quot; Grooved Wet Reflective Epoxy. Will this be updated through addendum? | No, an addendum will not be submitted to update the pavement marking bid items to Grooved Wet Reflective Epoxy. The project is on a local road and the maintaining authority (Jackson County) has elected to use the standard epoxy pavement marking bid items. | Mike Coleman | 2 | 2024-11-30 13:03 | 2024-12-02 11:50
20241210 | 20241210032 | 32 | Earthwork Tables and Contractor Data Packet | Can you please provide the Earthwork Tables in excel format. Also, provide the Contractor Data Packet, if available. Thank you. | No Contractor Data Packet is available. The earthwork tables can be found at the following location: https://wisdot.box.com/s/2xuaawl4r7tb4hqspzfozvdyrl8dx526 or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-12-02 16:03 | 2024-12-04 06:07
20241210 | 20241210034 | 34 | Earthwork Summary | The earthwork summary shows the excavation from the pipe transitions to be available material or waste. Is that material being used to backfill the pipe or is granular needed? Also, in the guardrail grading areas, what is the salvaged/unusable pavement material? There isn&#39;t a sawcut and the slopes are being built out as shown on sheet 9. There won&#39;t be much common at all unless the backslope is moving. Driveway Replacements - Where is the 585 CY of Common Ex? | 1. See the construction detail for the culvert pipe transition for types of backfill. It is assumed the material removed around the pipes will meet the requirements of standard spec 520, but final approval is by the engineer in the field. 2. The earthwork is completed using end area methodology with the shapes shown on the cross section extending to the centerline. A portion of the cut is actually milling, and this area is subtracted to get the true earthwork to balance. While this calculation could have been hidden in the table by the designer, the table does reflect the correct earthwork necessary to construct the guardrail. The contractor is correct, there are no sawcut associated with this work and the excavation common is limited. 3. Follow the standard detail included for Driveway Without Curb And Gutter Resurfacing Projects Rural. We are proposing that the material to be removed (base and asphaltic pavement) is to be paid as excavation common per the summary table. | Mike Coleman | 1 | 2024-11-20 13:54 | 2024-11-25 13:22
20241210 | 20241210034 | 34 | Soil Borings | Are soil borings available? | There are no soil borings for the project. | Mike Coleman | 2 | 2024-12-02 09:09 | 2024-12-02 12:07
20241210 | 20241210034 | 34 | Roadside Clearing | Question on the roadside clearing Stations 401+00 - 411+00 AND Stations 413+00 - 432+00 Doesn&#39;t say how far out we&#39;re suppose to go. The other stations for the roadside clearing is planely stated 50ft or 60 ft typical. Also the ones labeled 50 and 60 ft typical, Is that from edge of the road or centerline? | â€¢ The offsets on Sheet 45 are 50-feet typical at all locations on that sheet. â€¢ All offsets are from the centerline. â€¢ The contractor needs to complete Roadside Clearing from the roadway to the right-of-way line, except for one station range from STA 328+04 to about STA 335+60, RT, where the clearing only needs to occur to 60-feet RT and does not extend all the way to the right-of-way line. | Mike Coleman | 3 | 2024-12-03 09:45 | 2024-12-04 06:01
20241210 | 20241210038 | 38 | 505.0600 BAR STEEL REINFORCEMENT HS COATED STRUCTURES | Plan quantity for epoxy coated reinforcement differs from what is shown in the bill of bars total. | The plans have incorrect epoxy coated reinforcement and will be corrected via an addendum. | Mike Coleman | 1 | 2024-11-21 14:33 | 2024-11-26 11:46
20241210 | 20241210040 | 40 | Missing item - not on plans or specs | Line 0276 SPV.0060 Special 06. Retangular Rapid Flashing Beacon (RRFB) System shows in Bid Express but the plans nor specs have this item listed. | 29. Rectangular Rapid Flashing Beacon (RRFB) System SPV.0060.06 , page 18 - special provisions Plan detail Sheet â€“ page 13 MQ Sheet â€“ page 128 | Mike Coleman | 1 | 2024-11-08 12:16 | 2024-11-15 07:27
20241210 | 20241210040 | 40 | Soil Borings | Are soil borings available for this project? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/0az8wcmxlglqmgzgy67vfpjoipmefgp4 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-12-02 09:09 | 2024-12-02 14:09
20241210 | 20241210040 | 40 | Anodes | Can you please address the following questions&#58; - Is there a spec on the 3# &amp; 32# Anodes? Are they required to be Zinc or Magnesium? Sounds like there is not a BABA compliant 32# available. - There is a 25# BABA Compliant Anode. Will this be an acceptable Alternate to the 32#? | Magnesium Anodes are preferred as they are the type being used on the existing system. Bid pricing shall reflect the materials as specified. Substitutions for anodes may be considered if the Contractor provides certification from multiple suppliers that BABA requirement cannot be met on this item. A 25# magnesium BABA Compliant Anode will be an acceptable Alternate to the 32#. | Mike Coleman | 3 | 2024-12-04 11:11 | 2024-12-06 15:39
20241210 | 20241210040 | 40 | Anodes | Please address the following questions&#58; - Can Zinc Anodes be used in lieu of Magnesium Anodes? Magnesium does not meet the BABA requirements, but Zinc will. - Also, there is a 30# Zinc anode that would be equivalent to the 32# and a 5# Zinc Anode bag equivalent to the 3#. Both met BABA Spec. Please confirm if these will be an acceptable alternate. |  |  | 4 | 2024-12-04 13:06
20241210 | 20241210040 | 40 | Storm Sewer | In the special provisions the watermain is called out to be bedded per the standard detail and then backfilled with native soils up to subgrade. Will the storm sewer be the same as the watermain trench and be backfilled with native materials or will the trench need to be replaced? | The storm sewer is to be placed and backfilled according to the WisDOT standard specifications for storm sewer. Bid pricing shall reflect the materials as specified. | Mike Coleman | 5 | 2024-12-06 10:31 | 2024-12-09 09:05