## qandasearchletting_results
Date | 2025-01-14
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250114 | 20250114001 | 1 | Design Schedule? | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/tv0ds2t0wtlu87t33ld820pziwlcudz0 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-12-14 10:17 | 2024-12-16 09:50
20250114 | 20250114001 | 1 | Polymer Overlay Removal | On the 2 structures to receive a polymer overlay, it looks as though there is an existing polymer overlay. Is that to be removed? If so there is no line item for it. | The existing polymer overlay will need to be removed. Item 509.9015.S â€“ Removing Polymer Overlay Structure for both B-13-52 and B-13-383 will be added via addendum. | Mike Coleman | 3 | 2024-12-20 15:32 | 2024-12-27 09:04
20250114 | 20250114001 | 1 | Geotech Report & Soil Borings | Was a geotechnical report prepared for this project (along with soil borings)? If so, can the department please share that information. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/tv0ds2t0wtlu87t33ld820pziwlcudz0 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 4 | 2024-12-23 08:21 | 2024-12-27 09:13
20250114 | 20250114001 | 1 | Peak & Off-Peak Hours | The provisions for this project are very clear on what hours are peak and off-peak, but there is no definition of what days-of-the-week these hours apply. Could the contract allow for peak &amp; off-peak hours to only apply during weekdays (Monday-thru-Friday) and not on weekends? | Peak restrictions will apply to Monday through Friday. Peak restrictions will not apply on weekends. | Mike Coleman | 5 | 2025-01-04 12:13 | 2025-01-06 14:55
20250114 | 20250114001 | 1 | Material Unavailability | Per the plans, line numbers 0244, 0246, 0248, &amp; 0250 (Truss Cantilever 4-chord Type I) requires a chord material size of 5&quot; od x .375&quot;w. This size is only available in Canadian material. Would the department allow the use of 5.563&quot;od x .375&quot;w (A500 Gr C)for the Type I cantilevers? | The designs for these structures (S-13-0613/0614/0615/0616) are â€œstandardizedâ€ and were originally based on the Steel Tube Institutes mill capability tool for availability. When they were completed, that resource said there were three mills that regularly roll the 5â€x0.375â€ shape. We have rechecked the designs and the requested ASTM A500 Grade C 5.563x0.375 would work (as would either ASTM A500 Grade C 5.5x0.313 or ASTM A500 Grade C 5.5x0.375 would work). | Mike Coleman | 6 | 2025-01-07 15:12 | 2025-01-08 12:54
20250114 | 20250114001 | 1 | Asphalt Qtys | It appears item 106 and item 114 will overrun by approximately 300% &amp; 170% respectively. Can the Department recheck these quantities so that we can verify that we are not missing anything? | Items 106 (460.5224) and 114 (460.7424) were rechecked. Quantities as shown are correct. | Mike Coleman | 7 | 2025-01-07 15:51 | 2025-01-08 12:55
20250114 | 20250114001 | 1 | Box Culvert Removals | The note on the plans for C-13-111 indicate that the concrete box culvert is to be partially removed. Please confirm that only part of the existing box culvert that will need to be removed as part of the project is the existing wingwall extension that is noted on sheet 667 of the plans. | The existing wings should be removed as the call out on the plan also shows. No portion of the existing box will need to be removed. | Mike Coleman | 8 | 2025-01-09 10:51 | 2025-01-10 09:12
20250114 | 20250114001 | 1 | B-13-383 Wing 3 Replacement | Does wing 3 at B-13-383 get replaced? There is a note for this on sheet 1 of the structure plans however there are no details or information for wing 3 in the abutment plans - just wings 2 and 4. |  |  | 9 | 2025-01-09 14:48
20250114 | 20250114002 | 2 | Geotech | Are Geotechnical reports available? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/3xemxz9cmx83wyzut4y4o52ijydf34pg or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-12-17 12:13 | 2024-12-18 11:04
20250114 | 20250114002 | 2 | Main Street Roundabout Staging Plans | Based on the Traffic Control Plans, it appears that the roundabout at Main St and STH 16 is to be built in stages. Are there Staging Plan sheet missing, or can the whole roundabout be built in one stage. | The roundabout can be built in one stage. The staging shown in the traffic control plans is due to the anticipated difference in construction timelines for the roundabout compared to the pavement replacement. The stages shown for details 1 and 2 are set up as follows: Stage 1 - Project 1370-00-73 (Pavement Replacement) Construction started; Project 1370-00-76 (Roundabout) Construction not started Stage 2 - Projects 1370-00-73 (Pavement Replacement) and 1370-00-76 (Roundabout) under construction Stage 3 - Project 1370-00-73 (Pavement Replacement) under construction; Project 1370-00-76 (Roundabout) Construction completed | Mike Coleman | 3 | 2024-12-18 16:44 | 2024-12-19 09:47
20250114 | 20250114002 | 2 | Pipe Underdrain 6" | Is there a construction detail that shows if fabric type DF sch. A is needed for installation? Per the miscellaneous quantities it only shows base agg open grade and the pipe underdrain. If fabric is needed can that quantity be increased since the fabric item already exists. | A construction detail is not currently shown in the project plans. An addendum will be submitted to add a construction detail and increase the quantity for the fabric. | Mike Coleman | 4 | 2024-12-19 08:36 | 2024-12-26 09:02
20250114 | 20250114002 | 2 | Existing Typical Sections | Are existing typical sections available for the STH 19 EB Ramp (Z) and STH 19 WB (Y) alignments? | An additional typical section will be included in addendum #1. | Mike Coleman | 5 | 2024-12-19 14:30 | 2024-12-26 09:03
20250114 | 20250114002 | 2 | Existing Concrete Pavement | Is the existing concrete pavement doweled or continually reinforced concrete pavement? | The as-builts did not indicate if the existing concrete pavement was doweled or continuously reinforced. See note on page 4 of the plans: "NOTE: EXISTING UNDERLYING CONCRETE PAVEMENT MAY CONTAIN REINFORCEMENT. ALL COSTS ASSOCIATED WITH REMOVAL AND DISPOSAL SHALL BE CONSIDERED INCIDENTAL TO THE REMOVING PAVEMENT ITEM. ALL EXISTING PAVEMENT THICKNESS ARE APPROXIMATE AND SHALL BE FIELD VERIFIED. ANY ADDITIONAL WORK DUE TO VARYING THICKNESS WILL BE CONSIDERED INCIDENTAL TO THE AFFECTED WORK ITEM(S)" | Mike Coleman | 6 | 2024-12-19 16:46 | 2024-12-24 09:22
20250114 | 20250114002 | 2 | Earthwork Table | Regarding MQ plan sheet 187, does the salvaged/unusable pavement column quantity include asphalt and concrete quantities? If &quot;YES&quot;, the quantity is greatly understated. If the quantity only represents the concrete quantity only, it is accurate. Need to know to determine how much excess excavation will be wasted. | The salvaged/unusable pavement column only represents the concrete quantity. | Mike Coleman | 7 | 2024-12-31 13:44 | 2025-01-03 14:43
20250114 | 20250114002 | 2 | B-28-12 deck rebar | The quantity listed for the S412 stirrups in the bill of bars for the deck on B-28-12 appears to be incorrect. A quantity of 8 S412 is listed which should be the number needed between each set of girders not for the entire deck. | Agree. The quantity for the Bar Steel Reinforcement HS Coated Structures is incorrect. An addendum will be submitted to correct. | Mike Coleman | 8 | 2025-01-02 08:14 | 2025-01-03 14:46
20250114 | 20250114002 | 2 | Mowing - Site maintenance | Please confirm the 6-8â€ mowing height. Can it be shorter or is this the constant height required? | The spec is to manage weeds so the permanent seed can grow. It isnâ€™t going to be required to keep the grass mowed consistently to 6â€-8â€. The grass will be mowed at the direction of the engineer when the vegetation is too high as to not allow sunlight for the grass to grow. | Mike Coleman | 9 | 2025-01-02 12:38 | 2025-01-08 12:43
20250114 | 20250114002 | 2 | Removing Small Pipe Culvert | For the existing pipe located at +/- station 325+00, what is expected for the removal? In the plan and miscellaneous quantities it seems to call out and shown to be removed under the removing small pipe culvert item but then there is also a note that existing pipe to be grouted? Typically if DOT would want a pipe backfilled with slurry backfill there would be an item for that. There is not an item for slurry backfilling a pipe. Please advise. | There are 2 separate pipes in this area being addressed. The first culvert pipe (Station 324+81) is an 18-inch culvert pipe which will be removed and replaced (removing small pipe culvert). The second culvert pipe (approximately Station 325+40) is an existing 48 CPCS with a 36-inch liner to be grouted (see the plan and profile on sheet 228 of the plans). The grouting of the existing 48-inch pipe with a 36-inch liner is paid for with item SPV.0035.01 Culvert Pipe Liner Grout. | Mike Coleman | 10 | 2025-01-07 14:21 | 2025-01-09 07:46
20250114 | 20250114002 | 2 | Removing Existing Concrete Pavement | The answer to question # 6 is insufficient. As you are aware the cost to process continually reinforced concrete pavement versus only doweled concrete pavement are two extremely different prices. Other WIDOT projects have stated if existing concrete pavement is continually reinforced in the plan at time of bid or if it is encountered while building the project compensation has been given to the contractor to deal with continually reinforced versus the typical doweled through a change order. Language must change in the plans / special provision to state that if continually reinforced concrete pavement is encountered that it is not typical and additional compensation will be given to contractor through the change order process. This is the only way to make it a equal for all prospective bidders. | An addendum will be submitted to remove the note shown on sheet 4 of the project plans. | Mike Coleman | 11 | 2025-01-07 16:51 | 2025-01-09 07:46
20250114 | 20250114002 | 2 | Line # 406 Culvert Pipe Liner Grout | Please confirm that this pipe is to be completely filled and abandoned or only filled between the existing metal pipe and liner? The specs seem to dictate only between the existing pipe &amp; liner but the bid item quantity seems to correlate to completely filling and abandoning the pipe. If abandoning is wanted this spec is not typical for pipe abandonment. | The existing 48-inch CPCS previously had a 36-inch liner pipe placed in it, but the grout was not installed. The item SPV.0035.01 Culvert Pipe Liner Grout is for installing the grout between the liner pipe and the existing CPCS pipe. The pipe is not being abandoned. | Mike Coleman | 12 | 2025-01-09 15:08 | 2025-01-10 09:13
20250114 | 20250114002 | 2 | EBS | Note 3 of the Earthwork Summary states EBS excavation to be backfilled with excavation common or Select Crushed. Please clarify which will be used. This will have an impact on the bid unit price of the Common Excavation if material is wasted off site or utilized as fill. The Earthwork Summary also appears to calculate the Expanded Fill and Mass Ordinate by utilizing cut to fill the EBS. If Select Crushed is utilized for EBS, has a quantity been included? | Either material will be acceptable as backfill for the EBS. We are anticipating the EBS will be backfilled with excavation common, however, the project engineer and/or regional soils engineer have the right to reject the excavation common for use as backfill for the EBS and direct the use of select crushed material. Excavation common being used to backfill EBS is reflected in the earthwork summary. | Mike Coleman | 13 | 2025-01-11 12:51 | 2025-01-14 06:20
20250114 | 20250114003 | 3 | Special Provision 10 "Adjusting Manhole Covers, Item 611.8110" | This Special Provision details that included under this pay item is necessary removals, temporary cover plating and temporary asphaltic pavement. It then goes on to state the following, â€œThe department will measure and pay for the items of asphaltic pavement mixture, temporary cover plate, milling, and paving separately.â€ This project does not include any line item for the removal of asphaltic pavement, asphaltic surface, temporary cover plates, or milling. My question is, can you please clarify if the necessary removals, temporary cover plating, temporary asphalt, and milling will be performed as part of the City of Portage project? To put it simply can you please clarify the state the manholes will be in prior to commencement of the WisDOT project? | The manholes will be set to the binder elevation by the city contractor. The WisDOT contractor will be responsible for setting the manholes to finished elevations. There are no longer removals required for the project as that is now being handled with the city project. | Mike Coleman | 1 | 2025-01-03 09:35 | 2025-01-08 06:14
20250114 | 20250114003 | 3 | Special Provision 10 " Adjusting Manhole Covers, Item 611.8110" | This Special Provision includes a supplemental specification indicating tolerances along the centerline of the manhole. Our questions is, will performing a â€œMr. Manholeâ€ or â€œCore and Pour Manhole Adjustmentâ€ be an acceptable form of adjusting the manholes to grade? | Yes, these are acceptable forms of adjusting the manhole covers to grade. | Mike Coleman | 2 | 2025-01-03 09:36 | 2025-01-08 06:13
20250114 | 20250114003 | 3 | Project Progress and Prosecution/Traffic and Phasing. | Special Provision article 3 states the contractor has 14 days from the start of the project to reopen USH 51/STH 33 back to traffic. The following work is to be completed before reopening, Base course, HMA, Concrete Pavement, Curb and Gutter, and Pavement Marking. Special Provision article 4 states that the USH 51/STH 33 curb ramp improvements are to be constructed under shoulder closures. Our question is, 1&#58; Is the intent for the project schedule to follow the pedestrian traffic control phasing meaning, working from west to east. To be specific this would mean that USH 51/STH 33 would be open to traffic until after the curb ramps are completed. Once they are a 14 day closure would start to complete the concrete pavement, HMA, and pavement marking. Or is the contractor expected to complete all the work starting west of the USH51/STH 33 intersection to the east end of the project within the 14 day closure which would start at the beginning of the project? | The intent of the pedestrian traffic control plans are to show the need to phase each intersection in order to maintain pedestrian access. The order of completing the curb ramp improvements at each intersection (and what order to do which intersection) is up to the contractor. The contractor will need to complete the work required in article 3 in the first 14 calendar days of the project. Concrete sidewalk (curb ramps) is not included in the required work to be completed in the 14-day closure. | Mike Coleman | 3 | 2025-01-08 10:52 | 2025-01-10 11:25
20250114 | 20250114003 | 3 | Project Progress and Prosecution/Traffic and Phasing Part 2 | See previous question in regards to Project Progress and Prosecution/Traffic and Phasing Our question is, 2&#58; Can the DOT provide a project schedule or project phasing plan that coincides with the DOT&#39;s response to the previous question? | The design schedule can be found at the following location: https://wisdot.box.com/s/tzkia5of59o3mkvhc2glnvyqtlmvkxu3 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2025-01-08 11:13 | 2025-01-10 11:24
20250114 | 20250114004 | 4 | Box Culverts | Will the Department allow C-53-2037 and C-53-3031 to be built as pre-cast structures in lieu of cast-in-place? | The Department will not allow C-53-2037 and C-53-3031 to be built as pre-cast structures because they do not meet the requirements of ASTM C1577. | Mike Coleman | 1 | 2024-12-13 09:10 | 2024-12-17 06:06
20250114 | 20250114004 | 4 | Roundabout Lighting | Per the Special provisions, the roundabout lighting is to be operational prior to August 4, 2025. Due to the long lead times for electrical equipment, this date is very unlikely to be met with permanent lighting. Would the Department entertain adding a LS item &quot;Special XX. Temporary Lighting STH 140/STH 67 Roundabout&quot; to eliminate arguments during the project? | WisDOT does not recognize a shortage of any electrical bid items at this time. WisDOT acknowledges extended material lead times for breakaway transformer bases. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. Any temporary or permanent contractor proposed solutions, due to material lead times, are the responsibility of the contractor. | Mike Coleman | 2 | 2024-12-13 10:17 | 2024-12-18 11:06
20250114 | 20250114004 | 4 | Select Borrow Pay Item | There is a quantity for select borrow in the earthwork table (EBS backfill per notes), but there is no pay item on the bid schedule for Select Borrow. Will this be added in an addendum? | The select borrow note will be removed from the earthwork tables, and the EBS will be backfilled with the selected crushed material. An addendum will be issued. | Mike Coleman | 3 | 2024-12-13 13:07 | 2024-12-19 06:58
20250114 | 20250114004 | 4 | Concrete removal and excavation | Is it the intent of the design that all concrete pavement be removed including pavement deeper than 2&#39; below the subgrade? In addition, How will excavation required to remove the concrete pavement below the subgrade be paid for? As Common Excavation? It doesn&#39;t seem that this quantity is included n the earthwork tables. Please advise. | The intent is to remove the concrete pavement within 2 feet of the subgrade, and the final locations will need to be in the field located during excavation. â€¢ Approximate locations are shown in, â€œConstruction Details â€“ Concrete Pavement Removalâ€ â€¢ The removal of the existing concrete pavement is to be paid as 204.0100 Removing Concrete Pavement, as shown in the miscellaneous quantities on page 131 of the plan. â€¢ Excavation associated with removing this existing pavement is to be paid as 205.0100 Common Excavation, as shown in the Earthwork Summary on page 133 of the plan. It is shown in the line â€œSTH 140 Concrete Pavement Removal. | Mike Coleman | 4 | 2024-12-13 13:11 | 2024-12-19 06:56
20250114 | 20250114004 | 4 | Box Culverts | it was asked if precast box culverts would be accepted and the answer given was that these sizes are outside of ASTM C1577. Actually ASTM C1577, Section 7.2 allows for special designs for special sizes just like these. Please reconsider allowing precast box culverts for this project. | Precast box culverts may be considered as an alternative upon shop drawing review after bid letting. | Mike Coleman | 5 | 2025-01-06 09:02 | 2025-01-08 12:47
20250114 | 20250114004 | 4 | Railraod Insurance and Coordination | Special Provision #9. states &quot;In addition to standard spec 107.26, provide railroad protective liability insurance coverage as specified in standard spec 107.17.3 Insurance is filed in the name of Wisconsin and Southern Railroad Company.&quot; The SP also implies that railroad flagging will be required for work on or near the rail road property. The closest railroad crossing seems to be the UPRR which is about 700 feet north of the northern limits of the project. Is there work for this project that will affect the UPRR, Wisconsin &amp; Southern, or any other railroad? | We donâ€™t expect any work with the railroad right-of-way for the project and the detour and as long as the contractor can guarantee they will not be working in the railroad r/w, Railroad Insurance and flagging will not be required. | Mike Coleman | 6 | 2025-01-07 09:47 | 2025-01-08 06:04
20250114 | 20250114004 | 4 | Box Culvert Temp Channels | During box culvert construction are alternate methods allowed to divert the creeks besides an open cut through the roadway e.g. bypass pumping or CMCP&#39;s? | Other alternatives can be used. Appropriate approvals would be needed for pumping. Project manager, dnr, etcâ€¦ CMCP could also be used. Sizing of the CMCP would need to be approved. | Mike Coleman | 7 | 2025-01-07 14:58 | 2025-01-08 12:48
20250114 | 20250114004 | 4 | Box Culvert Temp Channels | Within the roadway limits, what are the temporary channels to be backfilled with when the channels are no longer needed? The material that came out of the channel, structure backfill, CABC etc... | The contractor can backfill the temporary channel with the existing material if it is suitable; if the material is unsuitable, they will be able to utilize suitable excess material from other locations on the job. | Mike Coleman | 8 | 2025-01-07 15:04 | 2025-01-10 07:16
20250114 | 20250114005 | 5 | Clarification on Asphalt Apron and Pay Items 0002 Removing asphaltic surface, 0024 Asphaltic Surface | On Sheet 10- 14 Asphalt Apron is called out at all the curb ramps. Looking for clarification that removal of these areas are to be paid under ( Item 0002 Removing Asphaltic Surface) and The placement is to be paid under ( 0024 Asphaltic Surface). | The asphalt aprons will be new, as there are none existing, so the only thing to remove would be some aggregate to get the 2-inches of asphaltic surface placement. That removal and preparation is paid for under the Prepare Foundation For Asphaltic Shoulders bid item. The Removing Asphaltic Surface bid item is for the removal of the asphalt that is sawcut in front of each curb ramp. The Asphaltic Surface bid item covers both the Asphalt Aprons at all curb ramps and the lower 1.5-inches of removed asphalt. The upper 2-inches of the removed asphalt will be placed integrally with the mainline paving. | Mike Coleman | 1 | 2025-01-02 11:08 | 2025-01-03 08:18
20250114 | 20250114006 | 6 | Plan Note Clarification sheets 96 & 97 of 438 "Member Reinforcing, Typ" | On plan sheets 96 &amp; 97 of 438 there are ovals labeled as &quot;Member Reinforcing, Typ.&quot;. If this is a required repair. I cannot find any detail that labels or shows what this repair is. Please clarify. | Member reinforcing details will be added to the plans or additional clarity will be included. An addenda will be issued. | Mike Coleman | 1 | 2024-12-13 13:34 | 2024-12-23 08:14
20250114 | 20250114006 | 6 | Concrete Bases - SB11 | Should this be a Type 10-Special or a Type 1? | SB11 is a Concrete Bases Type 1. SB5 is a Concrete Bases Type 10-Speical. An addenda will be issued to correct the Miscellaneous Quantities table. | Mike Coleman | 2 | 2024-12-16 08:20 | 2024-12-23 08:15
20250114 | 20250114006 | 6 | Bid Item 80 Adhesive anchors No. 6 Bar | Please confirm Bid Item 80 Adhesive Anchors No. 6 Bars. Both bridges B-32-111 &amp; B-32-115 List 64 EA Adhesive Anchors No. 5 bars in the &quot;Total Estimated Quantity&quot; charts on the bridge plans. Looks like there are no #6 bars but the quantity for item 78 Adhesive Anchors #5 bars should be 128 ea . Please confirm. | The bridge plans are correct, all Adhesive Anchors should be #5 bar. Bid Item 80 should be removed and Bid Item 78 should be 128 EA. An addenda will be issued to correct the Bid Items. | Mike Coleman | 3 | 2024-12-16 16:00 | 2024-12-23 08:17
20250114 | 20250114006 | 6 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/uh7mklsu5khctizrmkm1wiv7k1iy2j8t or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2024-12-21 09:02 | 2024-12-24 09:20
20250114 | 20250114006 | 6 | PWL Pavement | With the specific staging on this project and the requirement of a ~750 ton HMA PWL test strip prior to production, how does the state intend to make this happen? The first stage, A-1, only allows enough space to pave roughly 100 tons per lane. Even if testing is waived for Stage A, Stage B-1 only leaves enough space for roughly 350 tons of HMA per lane. Would this project be better suited for QMP? Thank you. | PWL requirements should be removed and replaced with QMP items/provisions. An addenda will be issued. | Mike Coleman | 5 | 2025-01-02 13:53 | 2025-01-06 14:57
20250114 | 20250114006 | 6 | Item 677.0200 Install Camera Assembly | Where is the Camera being installed exactly? Is it a permanent or temp camera? | The bid item 677.0200 Install Camera Assembly will be removed. An addendum will be issued. | Mike Coleman | 6 | 2025-01-06 11:09 | 2025-01-07 13:17
20250114 | 20250114006 | 6 | SPV.0060 Special 33 Traffic Signal Interconnect | Is the City doing the fiber work? | The City will make the final connection to the cabinet, per SPV.0060.33. An addendum will be issued to clarify. | Mike Coleman | 7 | 2025-01-06 11:11 | 2025-01-07 13:18
20250114 | 20250114006 | 6 | Item 677.0200 Install Camera Assembly | Please provide what model camera is being installed | The bid item 677.0200 Install Camera Assembly will be removed. An addendum will be issued. | Mike Coleman | 8 | 2025-01-06 11:22 | 2025-01-07 13:19
20250114 | 20250114006 | 6 | Fixed/Expansion Bearing Procurement | Early conversations with suppliers indicate that there may be significant lead times for the bearings required on this contract which will likely affect final completion date. Will time extensions be allowed for completion of bearing replacement outside of current contract time stipulated in the proposal. | The Department is not aware of any material shortages for bearings. The contract completion date will remain as stated in the proposal. | Mike Coleman | 9 | 2025-01-09 10:45 | 2025-01-13 06:39
20250114 | 20250114006 | 6 | Concrete Bases | Will an addendum be issued to correct the quantity of Type 10-Special bases? | The project staff feels like this was addressed in addendum #1 which made a correction to the MQ table. There are 4 monotubes and 4 total bases. | Mike Coleman | 10 | 2025-01-10 10:22 | 2025-01-13 06:13
20250114 | 20250114006 | 6 | B-32-115 Deck Patching Qty | For structure B-33-115 the CONCRETE MASONRY DECK REPAIR qty seems to be significantly overstated for the work quantities provided for Deck Prep, Full Depth and Joint Repair. Please double check calcs and issue an addendum to correct if this is an error. | Any quantity discrepancies will be handled based on the Standard Specifications. | Mike Coleman | 11 | 2025-01-11 16:11 | 2025-01-14 06:21
20250114 | 20250114007 | 7 | Misc. Quantities items | In the miscellaneous Quantities sheet Page 111 of the plan set under Concrete Curb &amp; Gutter &amp; On Sheet 112 of the plan set under Concrete Sidewalk it lists the following items&#58; SPV.0090.02 Special (02. Grading Shaping and Finishing Concrete Curb &amp; Gutter) LF SPV.0060.09 Special (09. Grading Shaping and Finishing Curb Ramps) Each SPV.0090.03 Special (03. Grading Shaping and Finishing Concrete Sidewalk and Asphaltic Path) LF However, There are no line items associated with these SPV Items or any language in the Special provisions for the project. Are these items intended to be part of the contract or are these qtyâ€™s for information only? | Those SPV items were removed following central office review. However, they were missed on the miscellaneous quantity sheets. They are no longer associated/relevant to the project. An addendum will be issued to correct this. | Mike Coleman | 1 | 2024-12-13 13:21 | 2024-12-16 09:52
20250114 | 20250114007 | 7 | STA 200+00-217+00 | Per the Plan Details and Cross Sections from STA ~200+00-217+00 RT, how is the Department paying for the grading/shaping, clearing and grubbing, and finishing of the shared use path? | Additional excavation common quantity for the shared use path will be included in Addendum #2 to account for grading/shaping. Clearing and grubbing isnâ€™t required on the project as we are narrowing the road to install the new shared use path along St Albert. Finishing items were included in the miscellaneous quantities. | Mike Coleman | 2 | 2025-01-07 09:45 | 2025-01-08 13:03
20250114 | 20250114007 | 7 | Backfilling Curb/Common | 1. In many areas where the road is getting narrow, there is a large amount of backfill needed with no item. Will the Department be adding an item? 2. Is the Department paying common in the roadway since the RL is shifting? | 1. Topsoil is included in the project to account for backfill in these areas. Concrete sidewalk and concrete curb and gutter bid items also states in their specifications that payment is full compensation for foundation excavation, preparation, and backfill if there is no adjacent roadway excavation taking place. 2. The Department is not paying for excavation common in the roadway. The existing asphalt removal is being paid under â€œRemoving Asphaltic Surfaceâ€ bid item. Any removal of excess material and/or grading of material to the finished R/L is included in the bid item â€œPrepare Foundation for Asphaltic Pavingâ€, per the note on the finished typical sections. | Mike Coleman | 3 | 2025-01-08 16:11 | 2025-01-10 07:13
20250114 | 20250114008 | 8 | Asphalt Milling | Is the intent of the milling item on this project to mill the existing HMA full depth down to the underlying base course/pulverized base? If so, the depth of milling shown on the various typical sections does not represent the full depth of the existing asphalt as shown by the core log. Should this milling item be changed to Item 204.0125 and be paid by the Ton to compensate for the variable depth of removal? Outside of reconstruction areas, If the asphalt is removed full depth will CABC be required to raise the grade prior to placing the new HMA materials? | 1. Yes 2. The design team reviewed the as-builts in comparison to the plans and soil borings. Since the as-builts are fairly recent (Elder Ridge Road â€“ Spring Valley Road: 1998 and Spring Valley Road â€“ CTH K: 2005), we feel confident that the asphalt thickness is consistent and matches the milling thicknesses (4â€ â€“ 5.5â€) as shown on the typical finished sections as shown on the plans. The additional material shown on the boring log table of the plans is believed to include the pulverized and relayed material as part of the asphalt thickness. 3. The design team does not believe that it is necessary to include additional base since we have a uniform existing asphalt thickness that we will be milling (4â€-5.5â€) and the design proposes placing 5.5â€ HMA as shown on the typical finished section of the plans. | Mike Coleman | 1 | 2024-12-13 15:57 | 2024-12-18 07:15
20250114 | 20250114008 | 8 | MGS Thrie Beam Transition | Please review or explain the note on page 31 of the plan, detail A, that shows 25 feet of MGS Thrie Beam Transition that is paid for, according to note 1, as MGS Guardrail Short Radius? | The design team reviewed this question and verified the 25 foot dimension references â€œMGS Thrie Beam Transitionâ€ specifically referencing the height â€œtransitionâ€ from 27â€ to 31â€ per the SDD for Short Radius MGS. The pay limits for MGS Guardrail Short Radius are denoted by an asterisk on the plan and includes the radii limits plus the 25 foot height transition (ie. 50 feet which matches the Miscellaneous Quantities). | Mike Coleman | 2 | 2024-12-17 11:24 | 2024-12-23 08:44
20250114 | 20250114008 | 8 | STH 23 Design Schedule | Would DOT be willing to supply a design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/71h85iwck0mkzjlm2shu28d272iv0fxp or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2024-12-18 16:30 | 2024-12-23 08:42
20250114 | 20250114008 | 8 | Culvert Construction | Looking at the plan there is no quantity for any asphaltic surface for patching the culvert pipes that are being replaced on the project. The design schedule shows the culvert pipes being constructed early in the project which makes sense but is the intent for them to be left on gravel until milling starts? | No, the intent is not to leave the gravel. An addendum will be created to account for the Asphaltic Surface, saw cuts, and tack coat at the culvert pipe replacement locations to patch the pavement until the milling starts. Additional quantities will be added for saw cutting in the guardrail construction areas as well. | Mike Coleman | 4 | 2024-12-27 06:18 | 2025-01-03 06:13
20250114 | 20250114008 | 8 | Curb Ramp Construction | In the plan there is no quantity for any asphaltic surface patching around the curb and gutter ramps once finished but they are spelled out to be completed in stages. On previous projects the curb and gutter ramps need to be patched prior to switching stages is that the cases on this project as well? | Yes, patching will be required around curb ramps. An addendum will be created to account for the asphaltic surface, saw cuts, and tack coat at the curb ramp locations. Note- Asphaltic Surface bid item will be utilized instead of Asphaltic Surface Patching bid item because Asphaltic Surface will be utilized at the culvert pipe replacements as well due to the large area being patched. Since the asphalt will be patching in both locations, the same bid item will be utilized. | Mike Coleman | 5 | 2024-12-27 06:25 | 2025-01-03 06:16
20250114 | 20250114008 | 8 | 72 Hour Mill and Pave Requirement in Special Provisions | In the Special Provisions it states there is 72 hours between milling and paving the lower layer of asphalt, but on the design schedule shows 6 days from the time the mill starts and the paving needs to start. Wondering why the 72 hours between milling and paving if the design schedule shows 6 days between the operations? | The time chart has been revised to depict the 72 hours between milling and paving operations (see attached). Note that the length of each stage and the overall time remains unchanged however minor revisions have been made to the production rates and dates for tasks. No change was made to the completion date or overall construction duration. Please note that the time chart is a general overview of a guide to show that the project can be constructed within the allotted contractual time. It is not a detailed sequence of operations detailing the contractorâ€™s means and methods. The revised time chart can be found at the following location: https://wisdot.box.com/s/71h85iwck0mkzjlm2shu28d272iv0fxp or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2024-12-27 06:32 | 2025-01-03 06:20
20250114 | 20250114008 | 8 | Prepare Foundation for Asphalt Paving | On the Design schedule it shows are the 3/4-Inch and 1 1/4-Inch Base Aggregate being placed prior the removing asphaltic surface milling which is true due to the culvert construction on the project. What is the plan for installing base supplemental base to grade with after the mill goes through? | The purpose of the time chart is to show that enough time is provided to construct the project within the allotted time frame provided in the construction contract. It is not a detailed sequence of operations detailing the contractorâ€™s means and methods. It is not anticipated to add any supplemental base during the removing asphaltic surface milling operations. Per the plan, placement of Base Aggregate Dense ï¿½-inch is required for shouldering, concrete sidewalk, medians, and driveway construction activities. Placement of Base Aggregate Dense 1 ï¿½-inch is required for subgrade improvements, turn lanes, median, culvert replacement, curb and gutter replacements, and guardrail replacement construction activities. See Miscellaneous Quantities for additional information on locations of Base Aggregate Dense ï¿½-Inch and Base Aggregate Dense 1 ï¿½-Inch placement. | Mike Coleman | 7 | 2024-12-27 06:38 | 2025-01-03 06:22
20250114 | 20250114008 | 8 | Temporary Paint | There does not appear to be enough quantity to mark both the milled and lower layers of pavement. Does the Department intend to mark both layers? | The scope of the project requires removing the existing asphaltic surface milling (ie. pavement replacement) down to the existing base coarse material. The contractor will be required to pave the lower layer of HMA within 72 hours of removing the existing asphaltic surface (milling). We do not anticipate pavement marking on the existing base course material. The plans includes sufficient quantities for placing pavement marking on the lower layer and surface layer of HMA pavement. | Mike Coleman | 8 | 2024-12-31 15:07 | 2025-01-03 06:24
20250114 | 20250114008 | 8 | Survey Existing Slope Elevations | Who is â€œdevelopingâ€ bid items that are reliant on this new topo information? Why is this not completed already (clearing issues, grading, etc.)? What is the process for developing these other bid items? What is the ultimate goal of this bid item? | This bid item is only applicable within the Village of Loganville as noted within the station limits indicated on the SPV special provision. The intent of this project within the Village of Loganville (subgrade improvement) is to match finished grade elevations, cross slopes and drainage patterns to existing conditions. The survey information collected for design was limited to the curb ramp replacement areas. The survey existing slope elevations bid item is required to develop station, offset and elevation information for construction staking subgrade, construction staking base, and construction staking slope stake bid items. | Mike Coleman | 9 | 2025-01-02 14:03 | 2025-01-09 07:47
20250114 | 20250114008 | 8 | Reconstruction in Section 612+75 - 670+00 | On question #6 regarding the 72 hour requirement on milling and paving the design schedule was adjusted to match that requirement but I think there is are a few unaddressed concerns. In the reconstruction section from STA 612+75 - 670+00 to remove the asphaltic, do all the excavation, base placement, and paving will take more than the 72 hour requirement that is spelled out. How does DOT intent on handling that reconstruction section on the project? | An addendum will be prepared to revise the 72-hour restriction to 7 days. | Mike Coleman | 10 | 2025-01-03 15:22 | 2025-01-08 06:06
20250114 | 20250114008 | 8 | Boring Log for STA 655+36 - 979+36 | Would DOT be able to supply the boring log for the rest of the project? The boring log submitted covers the first 2.5 miles but the project is an almost 9 mile project, being that 2.5 miles of boring logs are shown that leaves a little uncertainty in the remaining 6.5 mile stretch of the project for overall asphalt thickness?. | The soil report can be found at the following location: https://wisdot.box.com/s/71h85iwck0mkzjlm2shu28d272iv0fxp or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 11 | 2025-01-03 15:27 | 2025-01-08 06:11
20250114 | 20250114008 | 8 | Existing Asphalt Thickness and PWL questions | Question #1 states that the design team is confident that there is 4.0&quot; - 5.5&quot; of asphalt existing and the borings are showing some pulverized and relayed material in the borings. If the existing asphalt is only 4.0&quot; is the intent to only mill 4.0&quot; of asphalt to base of asphalt and pave 4.0&quot; or 5.5&quot;? If the existing asphalt is greater than 5.5&quot; then is the intent to just mill 5.5&quot; and leave the milled surface or take it all the way to base aggregate? If you mill areas that are greater than 5.5&quot; of existing asphalt pavement how does the base to bring those sections back to grade get covered? What happens if the project has milled surface sections left and then gravel section being that there would be different underlying surface would coring the lower lift for PWL density be better versus nuclear density? | The intent is to mill (remove) the existing asphalt surface regardless of its thickness down to the top of the underlying base material with a maximum milling depth of 5.5â€. The design proposes paving a uniform 5.5â€ HMA Pavement layer overtop of the existing base material. Based on the information available, the majority of this project should need 4â€ milling to get down to the pulverized & relay surface. If during construction itâ€™s found to be otherwise, at that time there would be discussions with the Materials Engineer as to how to proceed with QMP. | Mike Coleman | 12 | 2025-01-03 15:40 | 2025-01-08 06:05
20250114 | 20250114008 | 8 | Work Operations between Milling, Prepare Foundation for Asphalt Paving, HMA Paving | Question #6 states that the 72 hour requirement holds per the spec but with the operations that has to happen between the milling, prepare foundation for asphalt paving, and paving, there isn&#39;t enough time between the 3 operations to safely have 3 different traffic control work zones with space in between so local traffic that will still be using the roadway while being worked on. The productivity on project will be limited as well do to having to mill for 2 days with an average production of .75 miles/day, shape for 1 day and then pave it in within 72 hours. This will also drive the cost of the project up at due to lack of production each week for all operations. Project 5060-00-77 the spec had 72 hours between milling and paving with shaping the roadway in between and the question was asked to change the restriction and the design team allowed 7 days to get the lower lift on the project. Would DOT be open to the 7 days to place the lower lift on this project? | An addendum will be prepared to revise the 72-hour restriction to 7 days. | Mike Coleman | 13 | 2025-01-03 16:18 | 2025-01-08 06:06
20250114 | 20250114008 | 8 | Shoulders- 3/4" DGB | The shoulders in the typical section show placing 5.5&quot; of 3/4&quot; DGB. There are no items to remove the existing gravel on the shoulders and typically projects of this scope are topping the existing gravel with new 3/4&quot; DGB. 1. Is the Department going to add an item to remove the existing shoulder gravel? 2. If the existing shoulder gravel is to remain and be shouldered over with new 3/4&quot; DGB, the quantity is overstated. Can the Department revise the 3/4&quot; DGB quantity to be more accurate? | 1. No. Typically, pavement replacement/resurfacing projects like this do not include a bid item for excavation common to remove existing shoulder material. 2. No change. Per Spec 305 of the WisDOT Standard Specs, payment is full compensation for preparing the foundation and placing, shaping and compacting the new base. It is our experience on previous projects that due to variable roadway foreslopes placement of Base Aggregate Dense ï¿½-Inch shouldering material runs heavy. The design team feels comfortable with the quantity of base aggregate dense ï¿½-inch on this project. | Mike Coleman | 14 | 2025-01-06 14:25 | 2025-01-09 07:49
20250114 | 20250114008 | 8 | Culvert Replacement Detail Sheet 19 | Based on culvert replacement detail on sheet 19, are we required to do the transition cut called out as a 1.5&#58;1; or would means and methods allow for trench box with vertical sides? Detail looks like a transition, however, it is not specified as one. | Excavation parameters for replacing culvert pipe shall follow WisDOT and OSHA standards, therefore the limits without vertical sides is required. The miscellaneous quantities (via upcoming addendum) are based off the detail as shown in the plan. | Mike Coleman | 15 | 2025-01-07 10:43 | 2025-01-09 07:44
20250114 | 20250114009 | 9 | Concrete curb & gutter 4" sloped 36" tbt | Is the intent of replacing this curb to be done under existing beam guard or will the beam guard be removed in these sections to allow for the use a slip machine? | : It was anticipated the curb and gutter would be installed while the guardrail was removed during the grading operations. However, coordination with the prime contractor should be completed to ensure this follows their intended means and methods. | Mike Coleman | 1 | 2024-12-13 12:26 | 2024-12-17 06:05
20250114 | 20250114009 | 9 | Guardrail Adjustment | The SPV&#39;s require all of the guardrail to be installed in 2025. That guardrail will be installed to the correct height based on the existing HMA surface. Will the road be paved to match the guardrail in 2026 or will the guardrail need to be adjusted? Will that adjustment be handled through a change order or will that be incidental to the project? | The existing asphalt surface will be milled 3.5-inches and 3.5-inches of HMA will be paved on the milled surface. The elevation of the asphalt surface is not being adjusted. No guardrail adjustments are anticipated. | Mike Coleman | 2 | 2024-12-18 06:08 | 2024-12-19 09:46
20250114 | 20250114009 | 9 | Culvert lengths | Page 75 of the plans shows most station locations RT/LT. Is that to mean that the culvert is being added on to both sides of the existing? If so how much pipe is adding to each side? Also is &quot;match into pipe prior to elbow&quot; mean that there is a length of CMP pipe existing that is the same size as is being proposed already in place that will be banded on to? | Question 1: The existing pipe under the road is being replaced, from the inlet side on the right side of the roadway to an approximate distance (5-10 ft) away from the existing elbow on the left side of the roadway. See the pipe cross sections for more information, beginning on page 252. Question 2: The existing elbow is remaining in place. Approximately 5-10 ft away from the existing elbow, the pipe will need to be cut. The existing length of pipe will remain connected to the existing elbow, so the existing elbow is not disturbed. The new pipe under STH 35 will then connect to the existing pipe with a concrete collar. | Mike Coleman | 3 | 2024-12-18 11:22 | 2024-12-23 08:43
20250114 | 20250114009 | 9 | Shot Rock | Is the stair-stepping prior to placing the shot rock incidental to the shot rock bid item since it is in a fill section or will the department pay common excavation for the work. | The benching for the shot rock is incidental to the shot rock item. | Mike Coleman | 4 | 2024-12-19 10:20 | 2024-12-23 08:43
20250114 | 20250114009 | 9 | Erosion Control Calculations | For the B-12-41, B-12-42, and B-12-43 structures that are to receive turbidity barrier, can you please provide the streambed elevations and Q2 data for calculating the required height of the turbidity barrier material? | Q2 information is not available for this project. Coordinating with WDNR the estimated high-water elevation will be used to calculate the height of the turbidity barrier. The elevations used to calculate the quantities are: â€¢ B-12-41: Stream Bed Elevation 617.30, High Water Elevation 629.9 â€¢ B-12-42: Stream Bed Elevation 611.00, High Water Elevation 621.3 â€¢ B-12-43: Stream Bed Elevation 617.00, High Water Elevation 627.6 | Mike Coleman | 5 | 2024-12-20 08:43 | 2025-01-08 12:41
20250114 | 20250114009 | 9 | Railroad Flagging | Is railroad flagging required when placing shot rock/slope fills above the BNSF Railway? If so, will there be any flagging reimbursement? | Railroad Flagging is not anticipated to be required for much of the shot rock placement. However, flagging requirements are decided by the railroad and may vary depending on the equipment and method of placement that will be used. Special Provisions Article 8. Railroad Insurance and Coordination â€“ BNSF Railway Company indicates the contractor is to comply with standard spec 107.17 which states â€œIf the railroad's chief engineering officer requires, arrange with the railroad to obtain the services of qualified railroad employees to protect railroad traffic through the work area. Bear the cost of these services and pay the railroad directly.â€ | Mike Coleman | 6 | 2025-01-02 10:49 | 2025-01-07 13:16
20250114 | 20250114009 | 9 | Site Mowing | Is the site inspection (for Blanchardâ€™s frogs) included in this mowing item? | Article 40. Site Mowing Project 5160-07-70, Item SPV.0060.1, Section C Construction, Subsection C.1 General indicates the â€Blanchardâ€™s Cricket Frog removals (as described in these special provisions under the prosecution and progress, Blanchardâ€™s Cricket Frog) must take place prior to any vegetation cutting.â€ Article 3. Prosecution and Progress, Section on Blanchardâ€™s Cricket Frog indicates â€œBlanchardâ€™s Cricket Frog removals will be conducted in the disturbance footprint by a qualified biologist approved by the WDNR ER Transportation Liaison prior to each work day/restoration activity. Coordinate with WisDOT Southwest Region Environmental Coordinator two weeks in advance of construction activities to schedule a qualified biologist to be on site during construction activities. The biologist will be contracted through a master contract with the department at the departmentâ€™s cost. Contact Anna Jahns, SWR REC, at annah.jahns@dot.wi.gov or (608) 785-9961.â€ Please see Article 3 for complete information. Per Article 3, the contractor is required to coordinate with the WisDOT Southwest Region Environmental Coordinator. However, the Department will contract with a biologist to complete the inspections. | Mike Coleman | 7 | 2025-01-02 12:41 | 2025-01-06 14:53
20250114 | 20250114009 | 9 | WIS MS Modified Inlet Details | The &quot;Inlet Covers, Type MS Modified&quot; (shown on page 16 of the plans) does not provide enough detail to confirm what iron castings are to be used for this special structure. Dimensions don&#39;t provide enough detail. | Additional detail for the MS Modified Inlet will be provided in an upcoming addendum. | Mike Coleman | 8 | 2025-01-06 10:44 | 2025-01-07 13:22
20250114 | 20250114011 | 11 | Cofferdam Bit Item is Missing | Cofferdam bid item is missing in the contract. | The cofferdam bid item is missing from the estimate. I will fill out an addendum form to add the bid item to the contract. No changes to the plans are necessary as the cofferdam bid item is shown on the structure sheets. | Mike Coleman | 1 | 2024-12-30 10:51 | 2025-01-02 05:30
20250114 | 20250114012 | 12 | Railroad Addendum | When will the Addendum come out for the Railroad as stated in article 8 &amp; 9 of the Special Provisions? | The addendum will be posted on Thursday 1/9/25. | Mike Coleman | 1 | 2025-01-08 15:45 | 2025-01-09 07:57
20250114 | 20250114013 | 13 | 6" Paint | Is the 6&quot; Paint supposed to be Temporary for the binder surface? | In this case, we opted to use the Marking Line Paint 6-inch bid item since the lines are being placed on the binder surface and do not require removal. | Mike Coleman | 1 | 2024-12-30 13:41 | 2025-01-03 06:03
20250114 | 20250114013 | 13 | landmark monuments | can someone look at what items were used at what notes are in the plan and fix it |  |  | 2 | 2025-01-02 08:53
20250114 | 20250114013 | 13 | Landmark Reference Monuments | Does setting these monuments require a licensed land surveyor? 621.xxx does not reference any license standards, but when shown on other projects as part of the Specials then all work is to be done under the direction of a WI licensed land surveyor. Please clarify. |  |  | 3 | 2025-01-02 13:24
20250114 | 20250114014 | 14 | Material Transfer Vehicle | The special provisions state that the 3 LT and 4 LT bid items shall be paved in echelon and serviced by a material transfer vehicle. The Material Transfer Vehicle item says the MTV will be paid for use during â€œupper layer paving operationsâ€. Is it the intent that payment will be made for the MTV for the 3 LT as well, if so, please update the MTV Specials or should it be considered incidental for the 3 LT item? | Dodge County requires the material transfer vehicle to be used for both the lower and upper layers of mainline paving. An addendum will be issued to update the Material Transfer Vehicle specification. | Mike Coleman | 1 | 2024-12-19 13:45 | 2024-12-24 09:14
20250114 | 20250114014 | 14 | Schedule | Could you please provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/jtfn51xmua900z239bi5gagnwtcb84lc or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-12-19 13:46 | 2024-12-23 09:56
20250114 | 20250114015 | 15 | Steel Plate Beam Guard Class A | Should this item be 614.0515 Guardrail Stiffened LHW? | Item 614.0515 Guardrail Stiffened LHW is not required as we have 2â€™ shoulder provided behind back of post. An Addendum will be prepared to update/remove note in Misc Quantities. | Mike Coleman | 1 | 2024-12-17 07:37 | 2024-12-23 08:45
20250114 | 20250114015 | 15 | Radius Guardrail Pay Limits | Detail 14B53-02b, note 107, shows beam guard to be paid to the end of the bell of the short radius terminal. Detail 14B53-02a show the 15&#39;7 1/2&quot; panel and the 12.5&#39; panel to be paid with the &quot;beam guard item&quot;. Which item is that to be paid under? The posts are CRT posts which would match the short radius guardrail item. On this project, the stretch of guardrail that transitions into radius is 3K. Which item is the approximately 30 ft of guardrail after the radius panels to be paid under? | The quantities for SRT and guardrail at this location are incorrect and an Addendum will be prepared to update the miscellaneous quantities, plan sheets and estimate. | Mike Coleman | 2 | 2024-12-17 07:45 | 2024-12-23 08:52
20250114 | 20250114015 | 15 | "Remove CL Pavement Markings" | In the traffic control plan during stages 2 &amp; 3 (pgs. 52-56) it says in the notes to &quot;remove CL markings&quot;. Should the marking removals have its own line? If not, what item should we include it in? | Removing Marking Line items and quantities will be added through an addendum. | Mike Coleman | 3 | 2024-12-30 11:41 | 2025-01-03 14:44
20250114 | 20250114017 | 17 | Concrete Surface Repair | What is the expectation for trying to match the existing architectural pattern for the concrete surface repair? Would the department consider allowing a flat formed surface instead? | General Notes on structure plans state â€œCONTRACTOR TO MATCH RANDOM WOOD LOOK ARCHITECTURAL SURFACE TREATMENT FOR CONCRETE SURFACE REPAIR AREASâ€ Contractor should match random wood look as best as possible. No flat formed surface will be allowed. | Mike Coleman | 1 | 2025-01-03 08:18 | 2025-01-03 14:45
20250114 | 20250114017 | 17 | Asphaltic Surface Items | How/what will the following items be paid under since there are no corresponding bid items? Will bid items be added for any of these? -Sheet 7. 6&quot; mill, repave 6&quot; asphaltic pavement. Will 2 lifts be required for this? -Sheet 9. Asphaltic surface temporary ramps and asphaltic surface driveways and field entrances. -Sheet 13. Asphaltic surface patching for manholes. -Sheet 24. Asphalt flume. -Sheets 25 &amp; 27. Asphaltic surface safety islands. | The additional quantities will be provided with Addendum No. 1 | Mike Coleman | 2 | 2025-01-07 11:15 | 2025-01-08 06:13
20250114 | 20250114017 | 17 | Concrete Surface Drains | On sheet 24 and Sheet 26 there is reference made R&amp;R Concrete Surface drain and to Add Concrete Surface Drains but there is no bid item for Concrete Surface drain. | Concrete Surface Drains have been removed and replaced with Asphaltic Flumes with additional quantities added in Addendum No. 1 | Mike Coleman | 3 | 2025-01-10 08:22 | 2025-01-13 07:07
20250114 | 20250114017 | 17 | Curb and Gutter Types | The only curb Bid item is 601.0411 Concrete curb &amp; Gutter 30-Inch Type D, however on sheet 25,26 &amp; 27 plans call out remove &amp; replace 6&quot; Sloped 36&quot; Type D Curb and on sheet 28 it calls out Remove &amp; Replace 31&quot; Type D Curb. | Additional quantities will be included with Addendum No. 1. | Mike Coleman | 4 | 2025-01-10 08:32 | 2025-01-13 07:07
20250114 | 20250114018 | 18 | Asphalt restoration at trenches | For watermain and sewer work, will trenches be temporarily filled flush with stone? Is it safe to assume no lifts of permanent pavement are expected once underground work is completed but prior to mainline milling and paving? | Base aggregate dense 1-1/4 inch may be used to temporarily restore trenches to the existing roadway surface as noted on the Construction Detail shown on Sheet 19. Prior to mainline paving, the contractor will need to regrade so trenches can be restored with HMA pavement per the thicknesses shown on the Construction Detail on Sheet 19. HMA pavement should be placed in multiple lifts per the General Notes on Sheet 2. | Mike Coleman | 1 | 2024-12-17 15:41 | 2024-12-19 06:55
20250114 | 20250114018 | 18 | Item 266 and restoration | Specs call for sod. Is seed an option for landscape restoration after the crossings are removed? Each location has a very small quantity and there are concerns about the feasibility and maintenance of using sod. | For Article #42, (Temporary Pedestrian Crossings, Item SPV.0060.01), seed and erosion mat can be used for restoration. | Mike Coleman | 2 | 2025-01-06 10:36 | 2025-01-07 08:12
20250114 | 20250114018 | 18 | water main testing | We are wondering if testing of the 12â€ water main is going to be required in sections where it calls out to remove and replace more than 20â€™ of 12&quot; pipe, like the area around Juniper Ln. where we are supposed to replace roughly 90â€™ of pipe in a timely manner. If testing will be required then it would be our understanding that we would have to offset the new water main, test, and then make connections on both sides using 45*bends? | The water main near Juniper Lane has been updated and included in Addendum #1 which offsets the new water main from the existing water main to allow for pressure testing. Pressure testing of new water main will be required where new water main is greater than 20-ft and includes a new gate valve, which includes: 1. 8-in and 12-in water main from School Road to Acacia Road; Sheets 146-147 2. 8-in and 12-in water main at Apple Tree Road; Revised Sheet 148 3. 8-in water main at Daphne Road; Sheet 148 4. 8-in water main at Holly Court; Sheet 149 5. 8-in water main at Belmont Lane; Sheet 150 6. 12-in water main near Juniper Lane; Revised Sheet 152 7. 8-in water main at Daisy Lane; Sheet 153 8. 8-in water main at Bridge Lane; Sheet 153 9. 8-in water main at Coleman Lane; Sheet 154 10. 8-in water main at Thorne Lane; Sheet 155 11. 12-in water main from Calumet Road to Beach Drive; Sheets 155-156 12. 8-in and 12-in water main from Links Circle to Club Circle; Sheets 157-159 13. 8-in water main at Links Circle; Sheet 159 14. 8-in water main at Goodrich Lane; Sheet 160 15. 8-in water main at Gray Log Lane; Sheet 161 16. 8-in and 12-in water main at Dean Road; Sheet 162 All other water main work is considered maintenance and will not be required to be pressure tested. | Mike Coleman | 4 | 2025-01-07 12:36 | 2025-01-09 07:50
20250114 | 20250114019 | 19 | Lines 432 and 434 Asphalt Repair and Joint Crack Repair quantities | Please confirm that these quantities are accurate. 5,313 tons of Joint and Crack repair cannot be correct. Is it possible that the Asphalt repair should be 5,313 TN and the Joint and Crack should be 732 TN? | Item Number SPV.0195.002 Asphalt Concrete Repair is correct at 732 TONS Item Number SPV.0195.003 Joint & Crack Repair is incorrect due to a late bid items change from LF to TON and should in fact be 65 TONS. An addendum will be issued. | Mike Coleman | 1 | 2025-01-03 08:56 | 2025-01-06 06:23
20250114 | 20250114020 | 20 | Bridge B-67-402 Geotech Report | Please provide the full geotechnical report for structure B-67-402. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ule3b28ibjrdq51tfay5263ai5f3vnst or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-12-30 12:23 | 2025-01-02 05:40
20250114 | 20250114021 | 21 | 104th Ave Pavement Replacement | Two questions Will The pavement replacement SHES at 104th and 158th have to be done at night. It would be alot to remove pavement, install loops and pour SHES in same night. | The pavement replacement SHES at 104th and 158th are not required to be completed in one night. Access and (1) way traffic in each direction shall be maintained during operations. Contractor to coordinate with construction engineer and businesses as needed. | Mike Coleman | 1 | 2025-01-07 16:18 | 2025-01-10 07:12
20250114 | 20250114021 | 21 | 104TH AVE PAVEMENT REPLACEMeNT | What is existing thickness on 104th Ave concrete pavement. | Per City of Kenosha, concrete pavement thickness on 104th Ave. is 8.5â€ | Mike Coleman | 2 | 2025-01-07 17:23 | 2025-01-10 07:13
20250114 | 20250114022 | 22 | In - Stream Restrictions | Plan Sheet 74 indicates the stream bed is a dry run. Why would the special provisions include no in stream disturbance of Dutch Gap Canal from March 1 to June 15 if this is a dry run or runs intermittently? | During times of drought the Br Dutch Gap Canal goes dry. The WDNR in-stream restrictions shall apply. In the event of drought conditions and there is no flow in the Br Dutch Gap Canal at the start of construction, the Contractor may contact the WDNR and request if work can proceed. | Mike Coleman | 1 | 2025-01-09 10:43 | 2025-01-10 09:12
20250114 | 20250114024 | 24 | EOQ 342 vs 348 | Please confirm the bid quantity for 503.0128 Proposal No 24. Quantities sum to 342 but 348 is listed in several places. |  |  | 1 | 2025-01-06 14:48
20250114 | 20250114026 | 26 | Asbestos Information | Can we get the asbestos removal and any other information about any hazardous materials for this project? | The Asbestos Reports can be found at the following location: https://wisdot.box.com/s/u5zp0dtwlfe2d27nuni7pkd7o7rdtol2 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-12-16 09:08 | 2024-12-17 07:00
20250114 | 20250114026 | 26 | Geotechnical Info | Can we get the geotechnical information for this project? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/u5zp0dtwlfe2d27nuni7pkd7o7rdtol2 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-12-16 09:09 | 2024-12-17 07:04
20250114 | 20250114026 | 26 | Geotech | Are soil borings available? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/u5zp0dtwlfe2d27nuni7pkd7o7rdtol2 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-12-16 14:20 | 2024-12-17 07:14
20250114 | 20250114026 | 26 | Doweled Concrete Pavement | The plan does not call out for doweled concrete pavement. However, it does include the SDD&#39;s for doweled pavement. If any of the pavement is to be doweled please update the typical sections and/or plan to denote which pavements are to be doweled. | The plan typical finished sections will be clarified through addendum that all concrete pavement is to be doweled. | Mike Coleman | 4 | 2024-12-16 16:51 | 2024-12-18 07:16
20250114 | 20250114026 | 26 | Sewer Ejector Pump and Controls | Is there GPM rate at a specific TDH that the pumps are supposed to handle? | Design information: Total Dynamic Head Htotal = Hlift+Hfriction+Hsafety Htotal = 2+5+9= 16 feet There are only 7 DSFUs (about 6 GPM max) coming from the Maintenance Building. We understand that the flow into S-2 is very low. A pump for this application is typically oversized to provide long-term durability. We do not specify a minimum GPM for this pump. The contractor sizes it based on the rest of the system (volume of the sump, etc.). | Mike Coleman | 5 | 2024-12-17 14:38 | 2024-12-19 07:01
20250114 | 20250114026 | 26 | Sewage Ejector Pump and Controls | IS this a duplex system with two pumps or just a single pump? | This is a single pump installation. | Mike Coleman | 6 | 2024-12-17 14:44 | 2024-12-19 07:00
20250114 | 20250114026 | 26 | Abandoning Wells | What is the diameter and depth of the wells to be abandoned? | Rest Area 51, I43 SB (Well Report IY166): The 8-inch well casing runs from the surface to 123 feet deep. Then, the diameter is 8-inches from 123 feet to 282 feet. Rest Area 52, I43 NB (Well Report IY177): The 8-inch well casing runs from the surface to 98 feet deep. Then, the diameter is 8-inches from 98 feet to 282 feet. Well construction reports can be found at the following location: https://wisdot.box.com/s/u5zp0dtwlfe2d27nuni7pkd7o7rdtol2 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 7 | 2024-12-23 08:38 | 2024-12-26 09:32
20250114 | 20250114026 | 26 | Bid Item 531.4500 | There is no detail in the plan for the Foundation High Mast 100 ft (Structure). Please provide one. | The high mast light foundation plan sheet will be added via addendum. The four foundations are identical and are cast in place reinforced concrete, 4â€™ in diameter with a 14â€™ shaft. | Mike Coleman | 8 | 2024-12-26 12:27 | 2024-12-30 08:32
20250114 | 20250114026 | 26 | Pond Liner Clay | Is the clay liner undercut material included in the common excavation or is the undercut incidental to the clay liner item? | Excavation required for the Pond Liner Clay is included in Common Excavation. See Miscellaneous Quantities. The basin on Rest Area 51 is listed in Division 1 with Ramp B, the basin on Rest Area 52 is listed in Division 2. | Mike Coleman | 9 | 2024-12-30 12:03 | 2025-01-02 05:37
20250114 | 20250114026 | 26 | 8" Sanitary sewer | Special provisions say to use granular material for bedding of pvc conforming to the requirements as per 2&quot; pvc forcemain. in C, Construction it says to &quot;prior to backfilling it says to test according to 607.3.5. ( there is no spec 607.3.5) and compact to the density of the surrounding undisturbed soils&quot;. Are we to interpret this that we are to use NATIVE SOILS for trench backfill for the 8&quot; Sanitary Sewer? | An addendum will be prepared to modify the backfill material requirement. Backfill with native soils is not acceptable. Article 67, Section C will be updated to: Make any changes in grade or direction at manholes or other structures. Placement and depth of bedding shall conform to the details shown on the plans. Bedding shall be compacted by hand or mechanically to 90% of the Standard Proctor density (ASTM D698) for the material used. Backfill trenches according to standard spec 608.3.5. | Mike Coleman | 10 | 2025-01-07 08:09 | 2025-01-07 13:22
20250114 | 20250114026 | 26 | Forcemain 2" PVC | The special provisions tells us all about what we are supposed to bed the pipe with but very little about the trench backfill. In C.1 Installation it does mention &quot; Use excavated material for backfill provided in the judgement of the engineer is suitable. Does one assume native soils for trench backfill and if unsuitable it would be padi as extra work? | Per special provision, excavated material may be used for backfill. It is assumed there is suitable material on site for backfill. | Mike Coleman | 11 | 2025-01-07 08:14 | 2025-01-07 13:21
20250114 | 20250114026 | 26 | Building Removal | Can the plans for the existing buildings be provided digitally? | The 1979 and 2013 as-builts can be found at the following location: https://wisdot.box.com/s/u5zp0dtwlfe2d27nuni7pkd7o7rdtol2 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 12 | 2025-01-07 08:25 | 2025-01-08 06:09
20250114 | 20250114026 | 26 | Concrete Rumble Strips, Transverse | The standard detail shows milling or tooling, the construction detail dictates milling. Would tooling of the rumble strips be allowed? | Milling or tooling of the rumble strips is acceptable. | Mike Coleman | 13 | 2025-01-08 13:25 | 2025-01-09 08:07
20250114 | 20250114027 | 27 | Water Elevations | Please review the Hydraulic Data for B-1-37. The Q2 is not matching the existing elevations. | After review of the plan elevations, below is the corrected elevations per sheet: Sheet 11 Q2 = 892.72 Observed Water = 889.06 Q100 = 897.00 Sheet 12 Q2 = 892.72 Observed Water = 889.06 Q100 = 897.00 Sheet 53 Q2 in the Hydraulic Data table = 892.72 Sheet 55 Q100 = 897.00 Sheet 62 Q2 = 892.72 Q100 = 897.00 | Mike Coleman | 1 | 2024-12-23 13:02 | 2025-01-14 05:54
20250114 | 20250114027 | 27 | Rubberized membrane quantity | Please double check the quantity listed for the rubberized membrane behind the abutments? | The correct quantity should be 11 SY per abutment for a total of 22 SY. | Mike Coleman | 2 | 2025-01-14 01:07 | 2025-01-14 09:25
20250114 | 20250114028 | 28 | HMA Pay Items | Would the department consider changing the Asphalt pay items to Asphaltic Surface with a Special Provision stating the lower layer needs to be 3MT 58-28S and the upper layer needs to be 4MT 58-28S? | An addendum will be issued to clarify. | Mike Coleman | 1 | 2024-12-20 15:20 | 2025-01-03 06:07
20250114 | 20250114029 | 29 | HMA Type | The Special Provision for Asphaltic Surface does not designate a specific mix type (LT or MT). Does the department wish to designate a specific mix type? | An addendum will be issued. | Mike Coleman | 1 | 2024-12-20 16:03 | 2025-01-03 06:04
20250114 | 20250114029 | 29 | Railing Tubular Type H | The aluminum version of this railing is becoming unattainable. Please consider an alternative for the steel version of Type H or a 3T or C railing, all of which are designed for mounting on top of parapet. |  |  | 2 | 2025-01-02 09:51
20250114 | 20250114030 | 30 | Special Provision Signage | Plan Sheet 10 has a special message requiring the Larger signs (ex. 48x48, 60x24, 21x21) to be affixed to Bouys. Is this provision practical, or would installing post mounted signs on both sides of the waterway be a better alternative? | The contractor will have an opportunity to propose different means/methods in their ECIP for the sign mounting. At this time, we cannot guarantee that alternate methods will be approved. This item should not have any significant impact on the project cost. | Mike Coleman | 1 | 2025-01-10 07:26 | 2025-01-13 09:56
20250114 | 20250114031 | 31 | HMA | Due to the quantity and phasing of the project the department may want to consider changing the HMA pavement to an Asphaltic Surface item. The mix type and asphalt cement type can be specified. Otherwise, the department may want to add the Incentive Density HMA Pavement item. | Incentive Density will be added to the project via addendum. | Mike Coleman | 1 | 2024-12-31 13:27 | 2025-01-06 15:00
20250114 | 20250114031 | 31 | Aggregate Shoulders | The department may consider adding the shaping shoulders item or clarify what the expectation is to account for constructing/finishing the aggregate shoulders after paving. | This will be part of the addendum as well. We will be adding quantity to the project in case there is a need for shoulder aggregate on this project. | Mike Coleman | 2 | 2024-12-31 13:28 | 2025-01-06 15:00
20250114 | 20250114031 | 31 | Temporary Marking Lines | The plan sheets show Temporary Marking Line Removable Tape to be used for the traffic control staging, but the Miscellaneous Quantities and the Bid items only show Temporary Marking Line Epoxy. Please advise which should be used for the traffic control staging, and if the temporary tape is to be used please issue an addendum for this item. Thanks | Painting items will be revised and submitted as part of the addendum. | Mike Coleman | 3 | 2025-01-02 09:56 | 2025-01-06 15:01
20250114 | 20250114033 | 33 | Temporary Structure | Can a midspan temporary support be utilized to erect the 105&#39; clear span temporary structure? | A midspan temporary support can be utilized to erect the 105â€™ clear span temporary structure. No instream disturbances apply for any midspan temporary support work, and no additional contract time will be added to the proposal. | Mike Coleman | 1 | 2024-12-23 10:31 | 2025-01-03 06:09
20250114 | 20250114033 | 33 | 661.0101 Temporary Traffic Signals for Bridges | Hello - the detail on plan page 13 shows the temporary signals to be mounted on Class 4 wood poles. Would trailer mounted signals be acceptable to use for this application as well? | Trailer mounted signals will not be acceptable to use for STH 54/Salvage Road/North Bend Drive due to the realignment on Salvage Road. An addendum to be issued to remove trailer mounted signals on east side of bridge structure and utilize Class 4 wood poles with mounted signal to provide consistency for the temporary signals. | Mike Coleman | 2 | 2024-12-27 15:25 | 2025-01-03 06:10
20250114 | 20250114033 | 33 | 643.0920 Covering Signs Type II | The plan sheets for the detour show several Type 2 signs that need to be covered, however there is not an item included for this. Can the item 643.0920 Traffic Control Covering Signs Type II be added to this project? Thanks | An addendum will be issued to add bid item 643.0920 Traffic Control Covering Signs Type II to the proposal. | Mike Coleman | 3 | 2024-12-27 15:30 | 2025-01-03 06:11
20250114 | 20250114033 | 33 | Temporary Structure information | The 25 ft minimum structure width (sheet 31/126) is that total width or roadway width? Deck thickness listed is 3&#39; (ft?) what is that referring to? | The 25 ft minimum structure width is referring to the total width (see structure plans B-27-235 page 169). The deck thickness listed in the plans should be removed, the deck thickness will be designed by the contractor with the temporary structure bid item. An addendum will be issued to remove the minimum deck thickness. | Mike Coleman | 4 | 2025-01-02 09:14 | 2025-01-08 12:44
20250114 | 20250114033 | 33 | Temporary Structure | Is temporary concrete barrier the required railing system for the structure? If a railing/barrier system is used other than concrete barrier, must the system be crash-tested? | Temporary concrete barrier is the required railing system for the structure. Engineer in field may review/approve alternative railing/barrier systems, but all bids should be prepared using the required temporary concrete barrier as shown. | Mike Coleman | 5 | 2025-01-06 17:29 | 2025-01-08 12:46
20250114 | 20250114033 | 33 | Geotech Report for B-27-235 | Please provide the geotechnical report for structure B-27-235. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/41ybe87ofoa8jxaoozwb2oxux0u671sy or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 6 | 2025-01-08 08:41 | 2025-01-10 06:42
20250114 | 20250114033 | 33 | Temporary Structure | To further clarify a previously answered question, will a midspan temporary support be allowed to be installed and left in place for the duration of the temporary structure if it is installed/removed outside of the instream disturbance period? | A midspan temporary support will be allowed to be installed and left in place for the duration of the temporary structure. | Mike Coleman | 7 | 2025-01-08 09:39 | 2025-01-10 07:11
20250114 | 20250114035 | 35 | Culvert Relay at STA 827+60 | It looks like the pipe was replaced this year at STA 827+60, could the department please verify that&#39;s correct and the work won&#39;t be needed? | The culvert at STA 827+60 was replaced this past year by County maintenance crews. An addendum will be issued to eliminate work associated with this culvert relay. | Mike Coleman | 1 | 2024-12-27 10:29 | 2025-01-03 06:23
20250114 | 20250114035 | 35 | Landmark Reference Monuments | Does setting these monuments require a licensed land surveyor? 621.xxx does not reference any license standards, but when shown on other projects as part of the Specials then all work is to be done under the direction of a WI licensed land surveyor. Please clarify. | The monuments will be tied out by the Taylor County surveyor and shall be contacted prior any potential disturbance. An addendum will be issued to eliminate the Landmark Reference Monuments bid item and language will be added to the Prosecution and Progress Article of the Special Provisions. For reference Section Corner Monuments and a NGS Monument are shown on the Alignment Detail sheet in the plan set. | Mike Coleman | 2 | 2025-01-02 13:28 | 2025-01-06 14:56
20250114 | 20250114035 | 35 | PWL Mix Use Table | Would the department please add to the table the mixture and density acceptance for side roads, driveways, and turn lanes? Thank you. | Mixture and Density acceptance for side roads and turn lanes will be added to the PWL table along with revised plan quantity for Incentive Density PWL HMA Pavement via Addendum. Private Asphalt Driveways are not included in PWL and the tonnage is paid for under the bid item 465.0120 Asphaltic Surface Driveways and Field Entrances which follows the Standard Specifications under 465 Asphaltic Surface. Note that article 16 Asphaltic Surface in the Special Provisions replaces 465.2 (1) but will not require conforming to the quality management program. | Mike Coleman | 3 | 2025-01-06 13:53 | 2025-01-07 13:15
20250114 | 20250114038 | 38 | Project Schedule | Please provide the design schedule showing the staged construction, painting, 21-day cure time for both stages prior to Methacrylate seal all completed in 50 working days. | The design schedule can be found at the following location: https://wisdot.box.com/s/ihwcz7mz2stfz6l2na6d9guy2fcqqr3d or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-01-02 15:18 | 2025-01-03 14:42
20250114 | 20250114038 | 38 | Construction Staking Structures | The plan does not have an item for Construction Staking Structures. The exposed girder will need to have elevations shot at the 1/10th points for calculating the deck grades. This work is covered by the structure staking item and should be added to the contract. | An addendum will be issued to add the bid item. | Mike Coleman | 2 | 2025-01-07 14:32 | 2025-01-08 12:59
20250114 | 20250114039 | 39 | Common Excavation | What is considered common excavation at the intersections? I don&#39;t see cross sections or a construction detail for those areas. There are curb ramp details but they don&#39;t necessarily show where the cuts would be. | The common excavation is for the curb ramps. Per Standard Spec 205.0100, it is to remove excess material under the existing curb ramp. | Mike Coleman | 1 | 2025-01-03 09:46 | 2025-01-06 06:13
20250114 | 20250114039 | 39 | Trench Patching | The 2 foot wide, 6.5â€ deep trench patch (STA 973+40 to 975+07) is calling for 5MT 58-34V on all three lifts on the plan cross section details. Can this be changed to the Asphaltic Surface Patching item? This is due to it needing to be patched flush to surface, prior to mainline milling and paving operations, along with all of the other curb patching. | The lower lifts will be changed to the Asphaltic Surface Patching item via addendum. | Mike Coleman | 2 | 2025-01-06 16:36 | 2025-01-08 12:50
20250114 | 20250114039 | 39 | Saw Cutting at Ped and Curbs | On all of the ped ramp and curb &amp; gutter replacements, the sawcut is shown being right on the curb pan line, where it meets the asphalt. There will need to be a 2 ft wide trench back into the blacktop at every replacement location, in order for the concrete forms to be put in place. Are the quantities needed for these trenches covered in the Asphaltic Surface Patching and Removing Asphaltic Surface items? | Removing Asphaltic Surface and Asphaltic Surface quantities were added for the areas in front of the curb via addendum. | Mike Coleman | 3 | 2025-01-06 16:37 | 2025-01-08 12:49
20250114 | 20250114039 | 39 | Gate Valve Adjustments | Can there be an item added for Gate Valve Adjustments? All of the gate valves will need to be adjusted throughout the project, due to their age and current deteriorating conditions. | Further coordination with the city is ongoing regarding adjusting the water valves. If there is a change to the contract needed as a result of coordination, a contract modification will be issued at that time. | Mike Coleman | 4 | 2025-01-06 16:37 | 2025-01-08 12:51
20250114 | 20250114039 | 39 | Plating Manholes | Can there be an item added for steel plating the manholes, after dropping them, prior to milling and paving? | Cover Plates Temporary, Item 611.8120.S was added via addendum. | Mike Coleman | 5 | 2025-01-06 16:38 | 2025-01-08 12:50
20250114 | 20250114039 | 39 | Timing at Roundabout | In Addendum No. 1, the staging plan for the roundabout shows construction happening in essentially four stages. Can this roundabout be detoured for 2 weeks, to complete all of the work at once? This will save on cost, minimize the time span needed to complete the work, and increase safety of roadworkers and the traveling public. It could be worked out to where it was back open on weekends, and shortly after milling and paving operations. | The roundabout will need to happen with flagging operations as addendum number 1 shows. Detour routes are not able to be provided. | Mike Coleman | 6 | 2025-01-06 16:39 | 2025-01-08 12:51
20250114 | 20250114039 | 39 | Construction Staking Curb Ramps | The plan quantity for staking curb ramps is 80 EACH. The curb ramp details in the plans show 116 ramps. Will the correct quantity be updated prior to the letting? | The quantity for Construction Staking Curb Ramps has been updated via addendum. | Mike Coleman | 7 | 2025-01-07 14:23 | 2025-01-08 12:52
20250114 | 20250114039 | 39 | Curb Ramps | Can a construction detail be provided for the proposed curb ramps? | Curb Ramp details begin on page 36 of the plan. Additional details can be found on the Standard Detail Drawings. | Mike Coleman | 8 | 2025-01-08 09:11 | 2025-01-09 06:31
20250114 | 20250114039 | 39 | Construction Staking Electrical | There is not a construction staking electrical item in the plan. Does this item need to be added? | Any staking needed for electrical installations will be incidental to the work. | Mike Coleman | 9 | 2025-01-10 11:17 | 2025-01-13 06:36
20250114 | 20250114039 | 39 | Temporary Pedestrian miscellaneous quantities | Hello - it appears that there is an incorrect calculation in the Temporary Pedestrian Accommodations table on sheet 188 of the plan, creating a significant increase in the overall quantity. I believe that each sub stage was counted and then the total was multiplied by the overall stage duration, essentially 4x the actual quantity. Otherwise, I&#39;m not sure where we can fit 147 drums and 55 signs at every intersection. This is also likely causing the Undistributed quantity to be significantly higher than it should be. Please review the Drums, Signs, and Temporary Curb Ramps in this table. | The quantities will be adjusted in construction. | Mike Coleman | 10 | 2025-01-11 15:06 | 2025-01-13 09:55
20250114 | 20250114040 | 40 | Soil Stabilizer A and Hydromulch | Are both of these products being applied in the boulevards? The Soil Stabilizer Type A is a reinforced fiber matrix while the hydromulch SPV is calling for a stabilized fiber matrix. I don&#39;t think both are necessary. | Soil Stabilizer A is the correct bid item and the Hydromulch should be removed. An addendum will be submitted next week. | Mike Coleman | 1 | 2024-12-18 16:17 | 2024-12-23 08:59
20250114 | 20250114040 | 40 | Trail Paving | The trail paving shows 3 inches of a 5LT 58-34S. The specification 460.3.2 Thickness allows one 3-inch layer of a No. 5 (9.5mm) mix for cross-overs and shoulders. Will the contractor be allowed to construct the 5LT 3-inch trail with one layer or will two be required? The department may want to consider changing the trail paving to an Asphaltic Surface item with the desired mix/asphalt cement type specified. | The single lift of 3â€ of 5LT 58-34S was selected by the Municipality during the pavement design report phase, as they have used this exact section on recently completed projects that connect to this project to ensure uniform trails across the City. | Mike Coleman | 2 | 2024-12-27 12:59 | 2025-01-03 06:13
20250114 | 20250114040 | 40 | Intersection Details | As current conditions and plans show; drainage is minimal and varies throughout the project. The city may want to consider adding concrete valley gutters at more intersections, specifically Green Street (sheet 14) and Girard Street (sheet 17). The area left (west) of centerline where 11th Street meets Wisconsin Street (sheet 21) is also a challenge. | The mainline profiles at both locations should provide adequate flow, so I donâ€™t think itâ€™s necessary to add valley gutters. The curb flowline profiles were designed with drainage in mind, and valley gutters were only preferred by the municipality at locations where they already exist (i.e., not at Green Street or Girard Street, but at Colonial Drive only). Additionally, the recent 2024 Green Street City Reconstruction project proposes increased storm sewer capacity and inlets to enhance drainage on Green Street, just west of the 11th Street project limits. | Mike Coleman | 3 | 2024-12-27 15:16 | 2024-12-31 08:40
20250114 | 20250114041 | 41 | Stabilized Base Reclamation | Can you please provide special provisions for Item SPV.0180 Stabilized Base Reclamation and Item SPV.0195 Asphalt Stabilizing Agent? Both appear to be missing from the proposal. Thanks | An addendum will be issued to add the special provisions. | Mike Coleman | 1 | 2024-12-10 16:21 | 2024-12-12 06:50
20250114 | 20250114041 | 41 | pavement report | Can please provide copies of core logs or geotech reports for the project? | The boring logs can be found at the following location: https://wisdot.box.com/s/hbwwlwlvq6v0ze7rcxywbqy0fqajy1jv or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-12-10 16:23 | 2024-12-12 06:49
20250114 | 20250114041 | 41 | Plan Sheets | Can you please provide the plan sheets for 0+28 to 32+00 | An addendum will be issued adding the missing plan sheets. | Mike Coleman | 3 | 2024-12-13 09:13 | 2024-12-18 10:40
20250114 | 20250114041 | 41 | Removing Railroad Crossing | Can you please provide the construction detail for Removing Railroad Crossing SPV.0060.01 | An addendum will be issued adding SDD 13B1 to the plans. | Mike Coleman | 4 | 2024-12-13 09:16 | 2024-12-18 10:42
20250114 | 20250114041 | 41 | Pulverize & Relay Item | Should Item 325.0100 Pulverize and Relay be added to the contract to pay for pulverizing the remaining asphalt after the milling operation is complete? | The operation refenced below is included in item SPV.0180, Special 01.Stablized Base Reclamation Layer | Mike Coleman | 5 | 2024-12-17 09:42 | 2024-12-19 10:14
20250114 | 20250114041 | 41 | Stabilized Base Reclamation/Pulverizing | Is it a requirement of this item to produce a layer of stabilized base reclamation with uniform layer thickness? If so, should the contractor be required to complete this operation is 2 passes of construction? Pass One - pulverizing the remaining asphalt, ensuring any localized areas of thick pavement are processed full depth, grading and balancing super elevations to meet slopes detailed on sheet 13 of the plans. Will bid item 374.1020.S QMP Pulverize and Relay Compaction be applied during this phase of the process? Pass Two- injection of emulsion into material pulverized, graded and compacted in pass one. If this work is attempted in a single pass the following will be sacrificed&#58; - Guarantee that all of the existing asphalt is pulverized. Localized thick sections cannot be addressed with a single pass of the pulverizer. - time to work the injected material is not sufficient to shape roadway to design cross section and achieve uniform layer thickness, especially in supers. | Stabilized Base Reclamation shall be completed per SPV.0180.01. Construction methods are addressed in section C.1. | Mike Coleman | 6 | 2024-12-19 12:33 | 2024-12-23 09:00
20250114 | 20250114041 | 41 | Super Elevation Corrections | I do not see any material included for super elevation corrections. Is it intended to utilize the material on the road and if it is short to wedge the remainder in with new HMA? | 400 tons of undistributed Asphaltic surface in the plan can be used for wedging. | Mike Coleman | 7 | 2024-12-19 15:08 | 2025-01-03 14:31
20250114 | 20250114042 | 42 | Geotech Reports | Please provide the geotech reports for this project. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/ytsddyh1k1y858opwo2j5mkmdk086b8t or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-02 09:48 | 2025-01-07 13:28
20250114 | 20250114042 | 42 | Full Closures | Per SPV#4 - Traffic And Restrictions to Work, Full closures will be required in both directions during bridge demolition (Pg. 15, Paragraph 5). This is contradicted in the staging narrative which states that NB and SB are not to be closed concurrently (Pg. 18, last paragraph NS Pg. 19, stage 5). Please clarify which is correct and how many total nights of closure are allowed for bridge demolition. | Pg. 15, Paragraph 5 specifies that full closures are required for bridge demolition and girder erection. Given these activities are planned over both directions of IH 41, full closures will be required for both directions of travel. The staging narrative on pages 18-20 dictate that full closures canâ€™t occur concurrently in both directions of travel along IH 41. The special provisions (pages 18-20) also provide that full closures are allow for a maximum of two nights per direction of travel for demolition (per bridge structure) and two nights per direction of travel for girder erection (per bridge structure). | Mike Coleman | 2 | 2025-01-03 13:39 | 2025-01-08 06:34
20250114 | 20250114042 | 42 | Further Clarification on Full Closures | While contractor is removing portions of the existing bridges (or setting girders) over either NB or SB, does the other direction of traffic need to remain open. | When one direction of IH 41 is fully closed and that direction detoured as shown in the plans, the other direction of travel along IH 41 shall remain open to through traffic with an inside lane closure to provide additional buffer between the work zone and live traffic as shown in the traffic control plans. | Mike Coleman | 3 | 2025-01-08 13:54 | 2025-01-10 07:16
20250114 | 20250114043 | 43 | Traffic Control | The following bridges are set up to use flagging operations to close one lane. B-17-847, B-10-158, B-47-0033, B-06-885, B-61-0014. Flagging will only allow for daytime operations. We need a continuous lane closure for staging, waste and paint storage, as well to maintain the containment. A temporary traffic signal set up would be best. Please add temporary traffic signals set up for these bridges to allow for continuous lane closures. |  |  | 1 | 2025-01-13 20:06
20250114 | 20250114043 | 43 | Completion Date | Starting work on September 1, 2025, for bridges B-09-0019, B-17-0130, B-61-0014, B-61-0118 after the nesting season of migratory birds and with a completion date of October 17,2025 is tough. Structure B-17-0130 will require almost all that time alone. Can the completion date be extended to at least 12/1/2025? We can heat and house to extend the paint season. If temperatures are a concern, we can get to a good stopping point in 2025 and return in 2026 to complete as well. |  |  | 2 | 2025-01-13 20:16
20250114 | 20250114044 | 44 | 3" Copper Water | One the previous attempt to clarify, 3&quot; Copper for direct bury is not a common item in the civil world and if available very expensive. The most cost effective thing would be to switch to 4&quot; C-900 PVC. Is it possible to allow 4&quot; C-900 in lieu of 3&quot; Copper? | The copper lines are specified for the project as that is the standard used at all other rest area facilities around the state. Changing the water line to 4-inch C-900 may require more well pump horsepower and different sizing of pipe from well pump, size of pitless adapter, and size of building piping. Bid as provided in proposal 44. | Mike Coleman | 1 | 2024-12-17 14:53 | 2024-12-19 07:02
20250114 | 20250114044 | 44 | Spec Section 26 05 19 Low Voltage Electrical Power Conductors and Cables Part 3.1 Installation B. | In spec section 26 05 19 Low Voltage Electrical Power Conductors and Cables Part 3.1 Installation B. It says to install no more than 3 phase conductors in one conduit. Can we figure our take offs to meet the NEC or do we need to follow this spec? | Follow specification paragraph 3.1 B for maximum number of phase conductors in one conduit. | Mike Coleman | 2 | 2024-12-19 15:03 | 2024-12-26 09:04
20250114 | 20250114044 | 44 | Spec Section 26 05 19 Low Voltage Electrical Power Conductors Part 2.2 | In spec section 26 05 19 Low Voltage Electrical Power Conductors Part 2.2 A3 is say for branch circuits served by GFCI circuit breakers to use XHHW. Due to these circuits being located in the same building as the panel can THHN be used instead? | THWN/THHN insulation may be used for circuits served by GFCI circuit breakers. | Mike Coleman | 3 | 2024-12-19 15:04 | 2024-12-26 09:05
20250114 | 20250114044 | 44 | Panel LP A.I.C Rating | Panel LP A.I.C rating is noted as 34KA. Note 1 says to provide GFCI Circuit Breakers for certain circuits in the panel. The specs call for a fully rated panel. They do not make a GFCI breaker with 34 AIC rating. How should we proceed with this? | A.I.C Ratings will be adjusted based on the final location of the transformers. Updated tables will be provided via addendum to the following values: Panel MDP: AIC 30 KA, Panel LP: AIC 22 KA, Panel LMP 10 KA. | Mike Coleman | 4 | 2024-12-19 15:05 | 2024-12-27 09:14
20250114 | 20250114044 | 44 | Electrical | Sheet 31 or Area 51 shows a septic tank with controls. Sheet 32 or Area 52 does not show these controls. Should we include controls for Area 52 in regards to septic? | Septic controls on Rest Area 52 are located behind the future truck lot and are not impacted by construction and therefore not shown on sheet 32. Septic controls on Rest Area 51 on sheet 31 are shown for the understanding that they will be relocated adjacent to the comfort building from the present location near the septic tank. The control panels, conduit and conductors will be provided and installed by others. | Mike Coleman | 5 | 2024-12-31 07:16 | 2025-01-02 05:31
20250114 | 20250114044 | 44 | Septic Controls | Do the septic controls get added into the comfort buildings electrical price? | The septic controls depicted on sheet 31 are to be removed and relocated by others. This work is not associated with this contract. See Question 5 also. | Mike Coleman | 6 | 2024-12-31 07:17 | 2025-01-02 05:32
20250114 | 20250114044 | 44 | Electrical Feeds | Where do the electrical feeds from the comfort buildings to the maintenance buildings get put? Into the main electrical for the comfort buildings? | The electrical between the comfort buildings and the maintenance buildings are associated with bid items SPV.0060.07 and SPV.0060.08 for the respective sites. | Mike Coleman | 7 | 2024-12-31 07:18 | 2025-01-02 05:36
20250114 | 20250114044 | 44 | Electrical Panel | Where does the electrical panel in the maintenance building get put for pricing? Comfort or maintenance building. | The electrical panel and associated work within each maintenance building should be included in the maintenance building bid item for each site. | Mike Coleman | 8 | 2024-12-31 07:18 | 2025-01-02 05:29
20250114 | 20250114044 | 44 | Exterior Conduits & Fiber | Where do the exterior conduits and fiber from the maintenance building to the comfort building get put for pricing? Comfort or maintenance building. | The exterior conduits and fiber connecting the comfort buildings and maintenance buildings are associated with the comfort building discipline bid items. | Mike Coleman | 9 | 2024-12-31 07:19 | 2025-01-02 05:35
20250114 | 20250114044 | 44 | Electrical | Sheet 35 has (2) 2â€ PVC and a spare out of the comfort building that is separate from the conduits between the comfort and maintenance building. Where do these go, and should I be including these in the electrical quote? | The two conduits exiting the Rest Area 52 comfort building to the north service the septic equipment beyond the truck lot. These will be installed by others and should not be included in the bid. | Mike Coleman | 10 | 2024-12-31 07:20 | 2025-01-02 05:35
20250114 | 20250114044 | 44 | Acceptable Manufacture | This request is not intended to seek prior approval but rather to confirm that HVAC manufacturers not specifically listed will be acceptable if the performance and size requirements outlined in the specifications are met are acceptable. I am seeking assurance that Division 23 equipment can be included in the bid based on compliance with these performance criteria and will not be excluded solely for not being a listed manufacturer in the Division 23 specifications. Specifically, we would like to propose Climatemaster for the heat pumps and Renewaire for the energy recovery units. | Alternative manufacturers and products are acceptable in accordance with Spec 01 25 13 and 01 61 00 and where it is demonstrated that the products meeting the requirements described in the specific section of the specifications. Substitution can be accepted when the appropriate product data is provided for review and conforms with product performance requirements in the contract. | Mike Coleman | 11 | 2025-01-02 12:43 | 2025-01-10 11:21
20250114 | 20250114044 | 44 | Furniture - B2 Flight Benches | The specified B2 Flight benches have an option for aluminum or Cumaru hardwood slats. What is the desired slat material? | The intended material is Cumaru hardwood. | Mike Coleman | 12 | 2025-01-03 11:14 | 2025-01-06 14:54
20250114 | 20250114044 | 44 | Trecnh backfill for sanitary and water lines | Special provisions for the 3&quot; and 1&quot; copper water lines specifically say in C. Contruction &quot;backfill the remainder of the trench with the excavated material&quot; Special provisions for the 6&quot; and the 8&quot; sanitary say in B.4 Trench backfill say to furnish trench backfill conforming to 209.2 or 509.2.5.2. I am asking the question since per because of the &quot;OR&quot; and can follow the 509.2.5.2 spec which only calls out a foundation backfill, which is not trench backfill. Lastly these sanitary and water lines are in the same general area, shouldn&#39;t they be all backfillled in a similar manner? | Per spec 520.2.5.2 as noted in the project special provisions (not 509.2.5.2), foundation backfill is acceptable for the sanitary sewer. This may differ from water line backfill. Other locations of sanitary sewer on the sites require backfill as defined in the special provisions. | Mike Coleman | 13 | 2025-01-06 18:12 | 2025-01-07 13:20
20250114 | 20250114044 | 44 | Acoustic Board Insulation | Acoustic board insulation is not shown in the drawings. Where is the board insulation per spec 09 81 13 scheduled to occur? | This spec section coordinates with 09 79 11, â€œWood Interior Wall and Ceiling Panels.â€ The intent is for the acoustic boards to be laid over the perforated ceiling tiles in both the restrooms and the lobby. | Mike Coleman | 14 | 2025-01-08 08:20 | 2025-01-09 08:08
20250114 | 20250114044 | 44 | Well Pump Electrical | Remark 1 on page 172 (sheet E654) is incomplete. Please advise. | Completion of the remark is: â€œPROVIDED BY A SEPARATE CONTRACT.â€ | Mike Coleman | 15 | 2025-01-08 08:20 | 2025-01-09 07:45
20250114 | 20250114045 | 45 | Spot Repair Existing Storm Sewer | Line item 444 consists of spot repair of existing storm sewer. What is the defect that needs to be repaired? Can you provide an existing televising report that shows the repair location? | The existing storm sewer rehabilitation report can be found at the following location: https://wisdot.box.com/s/agbpa7dhmxsgy7drkmvm8sy02zldveg4 or can be accessed on the HCCI January bid letting page under Supplemental Information. The location of the spot repair is within the section of pipe referenced within the report as P-166. The location of the spot repair is 129â€™ upstream of MH 165. There are 4 sections of circumferential cracks and some are leaking, a longitudinal crack on the bottom of the pipe, some debris in this stretch. | Mike Coleman | 1 | 2024-12-16 10:44 | 2024-12-18 07:10
20250114 | 20250114045 | 45 | Clean Existing Storm Sewer | Line item 446 consist of cleaning an existing storm sewer line. Can you provide an existing televising report that shows how dirty the storm sewer line is? | The existing storm sewer rehabilitation report can be found at the following location: https://wisdot.box.com/s/agbpa7dhmxsgy7drkmvm8sy02zldveg4 or can be accessed on the HCCI January bid letting page under Supplemental Information. See Table 3- Maintenance Recommendations for cleaning details. | Mike Coleman | 2 | 2024-12-16 10:47 | 2024-12-18 07:13
20250114 | 20250114045 | 45 | Select Crushed | Please review the EBS quantity in the MQ and verify the proposed quantity for select crushed is accurate. | An addendum will be issued to correct this. | Mike Coleman | 3 | 2024-12-16 15:40 | 2024-12-23 08:11
20250114 | 20250114045 | 45 | Project Schedule | Can the DOT make available their project schedule to Contractors | The design schedule can be found at the following location: https://wisdot.box.com/s/agbpa7dhmxsgy7drkmvm8sy02zldveg4 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2024-12-16 16:39 | 2024-12-17 07:52
20250114 | 20250114045 | 45 | Geotechnical Report | Is there a geotechnical report available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/agbpa7dhmxsgy7drkmvm8sy02zldveg4 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 5 | 2025-01-07 12:47 | 2025-01-08 06:03
20250114 | 20250114045 | 45 | Box Culvert Membrane | Is there an existing membrane on the Box Culvert that will need to be removed in order to place the new membrane? | No. There is not an existing membrane on the box culvert. | Mike Coleman | 6 | 2025-01-09 14:23 | 2025-01-10 09:11