## qandasearchletting_results
Date | 2025-02-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250211 | 20250211001 | 1 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/qeuydsjkm0e5wezvsjh6oesqw9pucdg5 or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-01-08 16:24 | 2025-01-21 06:29
20250211 | 20250211001 | 1 | Law Enforcement Usage | On previous projects and in meeting throughout the state they have spelled out that the local/state patrol law enforcement would be able to be used to patrol the work zone while crews are on site. To pull local/state patrol away from other parts of the state and counties just to patrol one area and would come at a cost. Would DOT be open to compensating the GC back for the use of the local/state patrol law enforcement for the duration of the project? | At this time we do not compensate the general contractor for use of law enforcement in work zones. Each year the department meets with the regions and division of state patrol to identify projects that require law enforcement (rolling closures) as well as identify other projects to add law enforcement to for speed enforcement, incident response, presence, etc. On average we have about 10-15 contracts per year with law enforcement mitigation added to them. Our work zone mitigation policy can be found in FDM 11-50-7. | Mike Coleman | 2 | 2025-01-22 08:26 | 2025-01-22 10:40
20250211 | 20250211001 | 1 | Work on Ramps | On last year's project there was discussion about adding ramps and it was understood the ramps would likely be added to this year's project. It appears there is no ramp on this year project. Will the ramp work be added to the bid documents? | A discussion was held last year regarding adding some additional ramp work to this project and the decision was made to not address them with this project. All ramps that will be treated as part of this project are noted in the plan set. No additional ramp work will be added at this time. | Mike Coleman | 3 | 2025-01-27 10:43 | 2025-02-04 08:23
20250211 | 20250211001 | 1 | Mixture Use Table | Looking through the plan set there is no mixture use table. Would DOT be able to provide a mixture use table for the project? | A PWL Mixture Use Table will be added to the contract through an addendum | Mike Coleman | 4 | 2025-01-28 11:16 | 2025-01-29 06:03
20250211 | 20250211001 | 1 | Traffic Control and and Paving Operations on STH 23 | Looking through the plans there is a Construction Detail for Traffic Control and Paving Operations for IH 90 but nothing for STH 23. Does DOT have a Construction Detail for Traffic Control and Paving Operations idea for STH 23 from STA 316+23 V - 402+93 V? | The department does not have a construction detail for traffic control and paving operations for STH 23 | Mike Coleman | 5 | 2025-01-28 11:20 | 2025-02-04 08:24
20250211 | 20250211001 | 1 | Paving Limits on CTH P off STH 23 | How far back does the DOT plan on going on CTH P North there are no limits shown on the plan set. | A plan note of â€œTo be determined by the engineer in the fieldâ€ is missing from the plan at this location. Quantities were developed using the back of the radius, but exact limits will be determined by the field engineer. | Mike Coleman | 6 | 2025-01-28 11:23 | 2025-02-04 08:25
20250211 | 20250211001 | 1 | Mixture Use Table for Project - PWL Incentive Air Voids for Ramps & Shoulders | Looking at the mixture use table it states that all the Ramps and Shoulders will be PWL Incentive Air Voids HMA Pavement. Is that suppose to be be QMP instead of PWL because you would need to do a volumetric test strip if the intent is suppose to be PWL tested. This is completely different then how other projects in the pass where the Ramps and Shoulders are all QMP. | The PWL Mixture Use Table provided in Addendum 01 is correct. Other projects may have been handled differently due to project staging and/or amount of shoulder/ramp work. | Mike Coleman | 7 | 2025-02-06 09:22 | 2025-02-10 06:31
20250211 | 20250211002 | 2 | Design Schedule | Could the Department please provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/281s7is7jp02g2go9f89ps2k9lwc2p1e or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-01-27 09:11 | 2025-01-28 08:03
20250211 | 20250211002 | 2 | Railroad Reconstruct | Per the construction details, contractors are to dig out on either side of the tracks, place SAS fabric, place DGB, and pave. How will the dig out for this area be paid? | We will be submitting an addendum to add the Excavation Common item to pay for the excavation needed to complete the work proposed at the railroad. | Mike Coleman | 2 | 2025-01-27 15:39 | 2025-01-30 06:25
20250211 | 20250211003 | 3 | temp struc | What is the low steel elevation for the temporary structure? | On the temporary bypass plan and profile, it is stated that the minimum opening must be 104.23 SF. The rest is up to the contractor so long as they meet the standard specifications in section 526. Based on our profile and highwater elevations given in the plan, there is sufficient headroom to accommodate their temporary structure depth. | Mike Coleman | 1 | 2025-02-06 15:47 | 2025-02-10 07:00
20250211 | 20250211004 | 4 | Bid item for pre-stressed girders... | Hi, please add a bid item for the girders. Thank you. | Item will be added via addendum. | Mike Coleman | 1 | 2025-01-17 08:01 | 2025-01-21 08:45
20250211 | 20250211004 | 4 | Crack & Damage, seismograph? Working hours? | Hello, Is the property on the SE quadrant occupied? At a glance from the site visit, the residents (if any) will certainly feel pile driving and other activities. Has a crack & damage, seismograph been considered to limit liability? Are there working hour restrictions so close to residential property? | Property near the SE quadrant is occupied. Crack & Damage Survey and Seismograph items will be added by addendum to the contract. Hours of operation restrictions are as included in Standard Specification section 107.8.6. | Mike Coleman | 2 | 2025-01-28 12:08 | 2025-02-03 06:24
20250211 | 20250211004 | 4 | Utility conduits attached to structure | There are conduits located on the east abutment. Are these abandoned utilities? There is no mention in the special provisions. | Yes, these conduits are abandoned. | Mike Coleman | 3 | 2025-01-28 12:09 | 2025-02-03 06:25
20250211 | 20250211004 | 4 | No bird deterrent present... | The specials indicate the County has installed bird netting. There is none present at the current time. We are assuming it will be installed, but wanted to menion it in case they had already installed something. | The County plans to install the bird netting. | Mike Coleman | 4 | 2025-01-28 12:11 | 2025-02-03 06:25
20250211 | 20250211005 | 5 | Pulverized Base Layer; Emulsified Asphalt Stabilizing Agent | What QC testing is required for the pulverized base layer? What type or grade of Emulsified Asphalt is required? The Pulverized Base Layer SPV references Section 455 of the spec book, which does not define a type/grade of emulsion to be used for Pulverized Base Layer. Performance of the Pulverized base layer will vary by the type or grade of emulsion selected. Should this specification be changed to the â€œStabilized Base Reclamationâ€ SPV that has been used on all WI DOT let projects starting in 2023? The January 2025 letting proposal numbers 14 & 41 both used this specification. The answers to all of the questions above are contained in the â€œStabilized Base Reclamationâ€ SPV. | An addendum will be issued removing Pulverized Base Layer and Emulsified Asphalt Stabilizing Agent items and substituting Stabilized Base Reclamation and Asphalt Stabilizing Agent. | Mike Coleman | 1 | 2025-01-23 13:57 | 2025-01-28 06:42
20250211 | 20250211005 | 5 | Asphalt Stabilizing Agent Quantity | The quantity for asphalt stabilizing agent of 575 Ton is roughly 2.13% by mass of the Stabilized Base Reclamation Material. Should the quantity be adjusted to reflect the Stabilized Base Reclamation SPV, which requires 5.5% Asphalt Stabilizing Agent by Mass (1,350 Tons)? | An addendum will be issued to adjust the quantity to match the SPV.0180.01 Stabilized Base Reclamation; SPV.0195.01 Asphalt Stabilizing Agent application rate. | Mike Coleman | 2 | 2025-02-03 07:55 | 2025-02-05 08:56
20250211 | 20250211006 | 6 | Geotechnical Reports | Can the geotechnical report be provided for this project? |  |  | 1 | 2025-02-06 08:26
20250211 | 20250211006 | 6 | EBS with SSR Geogrid and Guardrail | Based on the detail on page 7 of the plan showing the SSR Geogrid, it appears that the MGS 3K posts may have to go through as many as 2 layers of this SSR geogrid.The stations in the MQ's on page 30 state 127+30 to 139+20 and also 142+90 to 146+60, totaling approximately 450 guardrail posts. We aren't sure if posts can be driven through this material. If the posts can't be driven through this material, how will that issue be handled? |  |  | 2 | 2025-02-06 14:40
20250211 | 20250211007 | 7 | Fish Spawning | The contract states no in stream disturbance from Oct 1 to July 31 in order to avoid adverse impacts upon spawning trout. The limits are usually Oct 1 to May 15th for trout. Oct 1 to July 31 is getting a little carried away, the bridge construction season is already way too short. Are these dates correct? | The dates are correct, as outlined in the final DNR concurrence. There is a state endangered fish species identified downstream of the structure, which is driving the very restrictive dates. | Mike Coleman | 1 | 2025-02-03 15:05 | 2025-02-04 10:39
20250211 | 20250211007 | 7 | Temporary Structure | Will a 10' Wide, temporary steel bridge be sufficient with the correct signage and stop signs implemented or does the temporary structure have to be 12' wide? | On the temporary bypass plan and profile, it states that the temporary bypass must have a clear roadway width of 16 feet. | Mike Coleman | 2 | 2025-02-05 07:27 | 2025-02-05 14:06
20250211 | 20250211007 | 7 | temp struc- low steel | What is the low steel elevation for the temporary structure? |  |  | 3 | 2025-02-06 13:52
20250211 | 20250211008 | 8 | No Utility Conflicts Anticipated | The erosion control on page 7 of the plan shows turbidity barrier crossing both the gas and fiber optic on the west side and the turbidity barrier terminating over top of the fiber optic on the east side. In addition, the silt fence is shown to run directly over the top of the fiber optic through the majority of the east side of the project and crossing the fiber optic repeatedly on the west side. With the RW line preventing the silt fence from moving away from the utility, how was it determined that there are no conflicts anticipated with work on this project? Lastly, while the silt fence may be hand dug to avoid the utility, the staking can't be performed by hand as they are pounded into the ground. Can anything be done to alleviate the risk of damaging the utility with the required erosion control installations shown in the plan? | Based on further discussions with utility owners having buried facilities within the project limits, it is confirmed that no utility conflicts are anticipated. | Mike Coleman | 1 | 2025-01-23 09:08 | 2025-01-28 08:40
20250211 | 20250211009 | 9 | Geotech Report for Structure B-13-903 | Will the geotech report be made available for structure B-13-903? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/lo60143uodq2opp3krcpul44vzf8kewy or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 13:58 | 2025-01-16 06:47
20250211 | 20250211009 | 9 | Item 42 Railing type M quantity | There appears to be an error in the quantity listed in the proposal for the Type M railing. The structure plan lists 177 LF which seems correct but the proposal states 117 LF. | The structure plan quantity of 177 LF for Type M Railing is correct. An addendum will be provided. | Mike Coleman | 2 | 2025-01-22 13:29 | 2025-01-23 13:31
20250211 | 20250211011 | 11 | TRAFFIC SIGNAL CONTROLLER | Due to the recent changes with Siemen's distribution, would Onalaska/WisDOT consider the Econolite Cobalt controller as an equal alternative? | No. The City will require a McCain controller or approved equal. An addenda will be issued. | Mike Coleman | 1 | 2025-01-16 15:03 | 2025-01-24 06:30
20250211 | 20250211012 | 12 | Crack and Damage Surveys | Due to the varying nature and size of the structures requested, to what extent do the buildings have to be inspected? Many are multiple story; how many stories are required? In the apartment buildings, do we need to enter the apartments and inspect all interior walls? Basements are not listed, so what is the expected manner of visually inspecting footings and foundations? | The contractor shall follow the language provided in the bid item to determine the extent into which the surveys shall be completed. | Mike Coleman | 1 | 2025-01-21 13:01 | 2025-01-22 11:29
20250211 | 20250211012 | 12 | Brick Pavers | BRICK PAVER SYSTEM COMPLETE- Bricks should be from Interlock Concrete Products Inc or a city approved equal. Pavers shall be ASTM C 936 compliant. They shall be Holland Style 4â€x8â€x2 3/8â€ (6cm) in the normal or 5â€x10â€x3 1/8â€ (8cm) in the permeable paver. Which paver should we use? | The preferred brick is the Holland Style 4"x8"x2 3/8" (6cm) in the normal. | Mike Coleman | 2 | 2025-01-22 09:22 | 2025-01-23 09:00
20250211 | 20250211012 | 12 | Pipe Bedding | Regarding the storm and sanitary pipe bedding. The detail drawing of the pipe bedding in the plan set is from 2019 and the City of La Crosse has changed their drawings a couple times since then. Should we use what is in the plans or use what La Crosse has now? | The contractor shall use the current city of La Crosse standards referenced in article 8 of the Special Provisions. An addendum will be completed to update to the current city of La Crosse details. | Mike Coleman | 3 | 2025-02-05 13:07 | 2025-02-07 07:32
20250211 | 20250211012 | 12 | Outside Drops | I am only able to find 4 Outside Drops called out on the plans, which does not line up with the 7 Drops listed on the Sanitary Sewer Table. Please clarify the number of drops at each structure. |  |  | 4 | 2025-02-07 12:03
20250211 | 20250211012 | 12 | Sanitary Sewer HDPE | There is some 21" HDPE pipe shown in the Sanitary Sewer Profile Views, but no specs or bid form item for HDPE. Please clarify type of HDPE required (IPS, DIPS, DR etc) |  |  | 5 | 2025-02-07 12:05
20250211 | 20250211013 | 13 | Onsite Crushing | Will onsite Crushing be allowed on this project? | In coordination with the City of West Allis, onsite crushing will not be allowed. It would be too disruptive given the urban, residential, setting. | Mike Coleman | 1 | 2025-01-09 16:25 | 2025-01-21 06:18
20250211 | 20250211013 | 13 | APS PUSH BUTTON SYSTEM | Will Campbell/Ped Safety WiAAPS buttons, which are on the WisDOT contract #5105757, be accepted as an approved equal for this project? | APS push buttons on the WisDOT approved product list, including the Campbell/Ped Safety WiAAPS buttons will be allowed as approved equals. | Mike Coleman | 2 | 2025-01-17 12:54 | 2025-01-22 10:36
20250211 | 20250211013 | 13 | VEHICLE VIDEO DETECTION SYSTEM | Will the Econolite Vision 4 camera vehicle video detection system be accepted as approved equal for this project? | The Econolite Vision system will be accepted as an approved equal. Other vehicle video detection systems may be allowed, as well, with prior approval. | Mike Coleman | 3 | 2025-01-17 12:58 | 2025-01-22 11:17
20250211 | 20250211013 | 13 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/r74jpyrpetxx2hvtl0o5xugprqz69zoj or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2025-01-28 08:16 | 2025-01-28 09:32
20250211 | 20250211014 | 14 | Onsite Crushing | Will onsite Crushing be allowed on this project? | On-site crushing will not be allowed due to the residential nature of the project. | Mike Coleman | 1 | 2025-01-09 16:26 | 2025-01-16 06:44
20250211 | 20250211014 | 14 | Soils Report | Can the soils report be provided? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/7o7s5eeqrz8latba9f7vbca8yk7i8o5s or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-01-28 11:03 | 2025-01-29 06:07
20250211 | 20250211015 | 15 | Geotech Report for Structure B-40-1033 | Will the geotech report be made available for structure B-40-1033? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/gsluknx4bt558dxi2v8l7b2bpkyay105 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 14:02 | 2025-01-21 07:03
20250211 | 20250211015 | 15 | Existing As Built Plans | Can you provide the existing as built structure plans? They are not located on the HSI website. | The existing bridge details can be found at the following location: https://wisdot.box.com/s/gsluknx4bt558dxi2v8l7b2bpkyay105 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-01-20 15:20 | 2025-01-21 13:10
20250211 | 20250211015 | 15 | Schedule | Could the Department please provide the anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/gsluknx4bt558dxi2v8l7b2bpkyay105 or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2025-01-22 11:52 | 2025-01-24 07:02
20250211 | 20250211015 | 15 | Bridge Deck Construction Joints | Is the longitudinal Const. joint in the deck required or can it be optional? Can optional const joints be added flush with the top of the deck at the base of the terrace curbs as well as at the edge beam curbs? | Yes, the longitudinal joint in the slab is optional. Yes, an optional construction joint can be added flush with the slab just at the terrace curb. Edge beam is to be poured monolithically with the slab. | Mike Coleman | 4 | 2025-01-23 14:36 | 2025-01-24 10:39
20250211 | 20250211015 | 15 | Hauling restrictions on Glenview Ave & Honey Cr. Pkwy | Would the department consider relaxing the hauling restrictions to allow hauling on both roads from the south only to W. Wisconsin Ave? | Hauling will not be allowed on Honey Creek Parkway because it is a Milwaukee County Parks roadway. Hauling will be allowed on Glenview Avenue and 76th Street south of Wisconsin Avenue only. An addendum will be posted to provide this clarification. | Mike Coleman | 5 | 2025-01-27 10:35 | 2025-01-29 06:08
20250211 | 20250211015 | 15 | Spec Provisions article 80. Outlet Struct 55, Item SPV,0060.29; Outlet Struct 63, Item SPV.0060.30 | Special Provision article 80 references Outlet Structure 55. I cannot find any reference on the plans for "Outlet Structure 55" Please clarify. Outlet Structure 63 appears on plan sheets 28 & 29 | There is no Outlet Structure 55. An addendum will be posted to remove Outlet Structure 55 from Article 80, which is the only reference to it. | Mike Coleman | 6 | 2025-01-27 14:42 | 2025-01-29 06:09
20250211 | 20250211015 | 15 | Preboring Concrete Length | There is conflicting information presented with regard to the amount of concrete fill in the prebore. Standard specifications 550.3.9.3 article 3 states " Firmly seat piles after preboring and backfill within the rock or consolidated material with a cement grout. Remove the casing, backfill the piles with sand or other engineer-approved material, and dispose of excess material." This conflicts with the plan note on page 1 of B-40-1033 which states "THE ANNULAR SPACE BETWEEN THE WALL OF THE PREBORED HOLE AND THE PILING TO BE BACKFILLED WITH CONCRETE". There is no special provision for the preboring. Standard specs indicate the 3 ft rock socket to be poured in concrete, the remainder to be backfilled with sand or other engineered approval. Please provide direction for the amount of concrete to be placed in the prebored holes. | An article will be added via addendum to modify the standard spec to match the plans. | Mike Coleman | 7 | 2025-02-05 09:41 | 2025-02-05 14:49
20250211 | 20250211015 | 15 | Debris Capture Item for B-40-1033 | Please clarify why the debris capture item is required when the entire stream bed gets rehabilitated? Can the bridge demo be dropped into the stream prior to the stream being reshaped? | WDNR wanted slurry controlled and was not ok with the bid item allowing this slab to be dropped as it does not adequately address their concerns with slurry. The only alternative for this structure type per BOS direction was Debris Capture. | Mike Coleman | 8 | 2025-02-05 12:49 | 2025-02-05 14:48
20250211 | 20250211015 | 15 | Field Office over Winter Shutdown | Is the field office to be supplied in the bid post interim date Nov 2025 through end of job May or June of 2026? | The field office should be supplied throughout the duration of the project including winter shutdown. | Mike Coleman | 9 | 2025-02-05 15:19 | 2025-02-06 13:26
20250211 | 20250211015 | 15 | 30 inch Casing Pipe | The specs call out for the casing first to be seamless then to be spiral welded. Is straight seam pipe allowed? seamless is expensive and generally not BABA compliant. Spiral welded casing leaves one manufacturer. Industry standard for auger bores in a straight seam casing pipe conforming to ASTM A53 Grade B 35,000 psi | A straight seam pipe is acceptable. | Mike Coleman | 10 | 2025-02-06 07:46 | 2025-02-07 07:33
20250211 | 20250211015 | 15 | Roadway Shoring for the East Abutment & Wingwall | Can you please confirm there is NO shoring needed at the Honey Creek & Wisconsin Ave intersection to protect either the roadway, utilities, or any other infrastructures? Are any of these utilities going to be within the 1.5/1 slope excavation going back from the bottom of abutment/wing footing back to the roadway? Will roadway shoring be added if needed? (Not for supporting utilities) Acknowledged SPV Article 26 however seeking additional clarification from WisDOT. NE/SE Wings: multiple Fiber Optic lines, multiple TV lines, multiple SS lines, multiple utility manholes, multiple gas lines | Multiple existing utilities are planned to be discontinued. Please review Article #6 Utilities. Contractor will determine shoring needs based on their means and methods. | Mike Coleman | 11 | 2025-02-06 09:22 | 2025-02-07 07:34
20250211 | 20250211015 | 15 | Utility Roll Plot | Can a utility as built or existing utility roll plot be provided for this project? | The utilities roll plot can be found at the following location: https://wisdot.box.com/s/gsluknx4bt558dxi2v8l7b2bpkyay105 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 12 | 2025-02-06 14:29 | 2025-02-10 07:15
20250211 | 20250211015 | 15 | SPV.0035.01 to SPV.0035.02 Streambed Stone & Streambed Granular Gradation | The special provisions above note specific gradations for these two materials. In section B.5 it requires gradation tests at the place of production. Based on the size of the gradation this will not be possible. Similarly to select crushed will visual gradation at the source of material prior to delivery be acceptable? | Visual gradation at the source of material prior to delivery is acceptable for B.1 Streambed Stone and B.2 Streambed Granular Fill. | Mike Coleman | 13 | 2025-02-06 14:35 | 2025-02-10 07:16
20250211 | 20250211015 | 15 | SPV Article 125 - Cement Grout Specifications for Piles | Please clarify what technical requirements the cement grout needs to meet for the pre-bored pile back fill. There is no guidance on this in the 2025 Specs. | Cement Grout can either be a non-shrink grout from the current Approved Products List valid on the date of letting or a concrete mix meeting the requirements of section 501 of the standard specifications with the exception that the combined aggregate gradation does not need to meet table 501-4. Concrete minimum compressive strength to be 3500 psi per the structure plans. | Mike Coleman | 14 | 2025-02-07 12:56 | 2025-02-10 09:32
20250211 | 20250211015 | 15 | Contaminated Soils - Pre-Bore Drilling Spoils | Please clarify if pre-bore spoils are contaminated that they will be paid under the contaminated bid item? Typically, these spoils are incidental to the drilling item. |  |  | 15 | 2025-02-10 10:48
20250211 | 20250211016 | 16 | Typical Sections for 8" Pavement | In the typical Sections the 8" Pavement is saying that it is Non Doweled Concrete. Does this mean the DOT does not want any Dowel bars in the Pavement? | The City does not want dowel bars in the pavement except for the drilled dowel bars at matches to existing concrete. | Mike Coleman | 1 | 2025-01-21 11:00 | 2025-01-22 06:21
20250211 | 20250211016 | 16 | Geotechnical Data | Please provide any geotechnical data available for the project. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ljyl5z0p73hhsp18o07nfye63h86phde or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-01-27 08:22 | 2025-01-28 08:28
20250211 | 20250211016 | 16 | Onsite Crushing | The question has been asked if onsite crushing of existing pavement is allowed on other City of Milwaukee area projects being bid in the February 11, 2025 WisDOT Letting and WisDOT has denied crushing. Crushing would normally be allowed. Is crushing allowed on this project and if it is not will an addendum be issued? Please note, not allowing crushing onsite will add significant cost, result in a tremendous amount of fuel to be burned by the added trucking and adjoining roads will be more greatly impacted. | It has been re-confirmed that on site crushing for the Lisbon Avenue project will not be allowed, as indicated in the Notice to Contractor â€“ On Site Crushing spec. | Mike Coleman | 3 | 2025-01-28 13:35 | 2025-01-29 13:21
20250211 | 20250211016 | 16 | Is breaking of the existing concrete pavement allowed? | Are there any standards that would disallow normal breaking of existing concrete pavement? | Concrete pavement removal will be to WisDOT standard specifications. | Mike Coleman | 4 | 2025-01-30 10:40 | 2025-01-31 07:45
20250211 | 20250211016 | 16 | 1.) 678.0300 FIBER OPTIC SPLICE | Will the City be doing their own fiber as they have in the past? | The contractor is to do the fiber work as indicated in the special provisions. | Mike Coleman | 5 | 2025-02-05 14:43 | 2025-02-07 07:40
20250211 | 20250211016 | 16 | 2.) SPV.0060 SPECIAL 213 ETHERNET SWITCH | Will the City accept any Ethernet switch or just the Extreme Brand as in the past? | Bid the item in accordance with the special provision for the item. The Extreme brand is acceptable. | Mike Coleman | 6 | 2025-02-05 14:43 | 2025-02-07 07:41
20250211 | 20250211016 | 16 | 3.) SPV.0060 SPECIAL 212 FIBER OPTIC PATCH PANEL | What manufacturer will the city accept for the Fiber Patch Panel and what is the minimum lengths required? | Bid the item in accordance with the special provision for the item. The special provision for the item indicates to furnish the patch panel with cable length as specified in the plans. The cable length is per the interconnect plans, from splice enclosure to patch panel. One acceptable solution is the GatorPatch product by Fiber Connections Inc. | Mike Coleman | 7 | 2025-02-05 14:44 | 2025-02-07 08:47
20250211 | 20250211016 | 16 | 4.) 678.0200 FIBER OPTIC SPLICE ENCLOSURE | What manufacturer will the city accept for the Fiber Splice Enclosure? TYCO? | Bid the item in accordance with the standard specifications for the item. TYCO is an acceptable manufacturer. | Mike Coleman | 8 | 2025-02-05 14:45 | 2025-02-07 07:42
20250211 | 20250211016 | 16 | 5.) SPV.0060 SPECIAL 214 FIBER OPTIC PATCH CORDS | Specify the type of connectors need on each end of the 3â€™ patch cord. LCUPC, STUPC, SCUPC. | Per the special provisions, â€œFurnish single mode LC-ST duplex fiber cable with segmented boot.â€ This would be LC connectors on one end, ST on the other. | Mike Coleman | 9 | 2025-02-05 14:45 | 2025-02-07 07:42
20250211 | 20250211016 | 16 | Concrete Sidewalk and Detectable Edge Tiles | Which product should be used for the item on line 670 SPV.0165 Special 020.Detectable Edge Tiles 3,529 SF. Also is it shown on the WisDOT Approved Products List? | Products are to be per the special provisions article 120: â€œDetectable Edge Tiles, Item SPV.0165.020â€. Two potential manufacturers are listed, or approved equal. The two potential manufacturers listed are on the WisDOT approved products list under the detectable warning field category for natural grey iron products. | Mike Coleman | 10 | 2025-02-09 13:03 | 2025-02-10 09:26
20250211 | 20250211017 | 17 | Schedule | Could the Department please provide the anticipated schedule for this project? |  |  | 1 | 2025-01-21 11:05
20250211 | 20250211017 | 17 | Site visit request | Can a scheduled site visit to enter both of the machine room's be organized or can a phone # be provided to do so? | Yes, a site visit can be arranged. Please contact Karen Forlenza, City of Milwaukee Bridge Operator Supervisor, at 414-286-3450 at least 2 business days before requested site visit. Proper PPE is required for all individuals to enter the pier areas of the bridge. | Mike Coleman | 2 | 2025-01-24 07:51 | 2025-01-27 06:21
20250211 | 20250211017 | 17 | Start Date April 1st? | Would there be any reason that April 1st would be not allowed as a start date for the project? | There isnâ€™t any reference in the special provisions to work restrictions on April 1st. | Mike Coleman | 3 | 2025-01-24 07:54 | 2025-01-27 06:22
20250211 | 20250211017 | 17 | Rear Break Structural Steel Fabrication | Which fabrication designation will will be required for the rear break expansion joint materials. Will this be considered a fabricated bridge component or primary steel member. If primary steel member, which designation will be required (1,2,3 or 4)? | The rear break will be considered a Fabricated Bridge Component and can be fabricated by an approved supplier from the approved product list. | Mike Coleman | 4 | 2025-02-04 10:41 | 2025-02-06 13:25
20250211 | 20250211017 | 17 | Fiberglass Sidewalk Floor Plates | Can you confirm the SF quantity of the fiberglass plates? The layout on sheet 19 of 27 does not correlate with the approximate plan quantity. | The SF quantity of the fiberglass plates in the plan is not correct, the correct value is 1928 SF. | Mike Coleman | 5 | 2025-02-04 12:06 | 2025-02-05 08:55
20250211 | 20250211017 | 17 | Centerlock Repainting | Special Provision #38, section B.2 - Paint for CenterLocks indicates that existing centerlocks are to be cleaned and shop painted. Is the intent to remove these from the structure to have them shop painted or can they be cleaned and painted in place. |  |  | 6 | 2025-02-04 13:42
20250211 | 20250211017 | 17 | Weld details and Material Specs for Rear Break Assembly | Please provide callouts for weld details for new Rear Break Joint Assembly. All steel assumed to be ASTM A709, GR 36. How many field welds will be allowed at each joint assembly if they are required? |  |  | 7 | 2025-02-04 14:43
20250211 | 20250211017 | 17 | Epoxy Injection Crack Repair | Plan quantity for epoxy crack injection is 416 lf and indicates crack sealing on north and south piers and north and south pier walls in the cwt pits. Where are the anticipated repairs that are not shown on plan sheets #66 & #67? Are there any repairs anticipated at on near the water surface? | The anticipated epoxy injection crack repair 416 LF at south and north piers is shown correctly. Additional repairs not shown on sheet 66 and 67 are anticipated on other walls within the two piers. No epoxy injection is anticipated on the exterior face of the piers near the water surface. | Mike Coleman | 8 | 2025-02-04 16:22 | 2025-02-06 13:26
20250211 | 20250211017 | 17 | Drive machinery to be cleaned & coated | One of the subcontractor painting companies has asked this question; The general notes it indicates that machinery is included. Are we to blast/paint machinery? Our concern is the electric components, would be damaged by blast cleaning. | Sandblast and paint all steel machinery components is required. If there are sensitive components, power tool cleaning and brush painting will be required as shown in the notes on sheet 23 of 27. | Mike Coleman | 9 | 2025-02-06 13:13 | 2025-02-07 07:34
20250211 | 20250211017 | 17 | Structure Repainting | The special provisions state the approximate area of repainting is 54,000 SF. Does this estimated quantity account for the steel grating surfaces and if not is there an estimate on those surfaces? | The approximate estimated quantity 54,000 SF of repainting steel does not account for the steel grating surfaces. The estimated quantity on those surfaces is 2,736 SF. | Mike Coleman | 10 | 2025-02-07 10:09 | 2025-02-10 10:30
20250211 | 20250211019 | 19 | Approved Fabricators | What fabrication classification is required for the structural steel on this project? Will a WDOT approved fabricator for Primary Bridge Members be mandated? If different level classifications will acceptable, please identify which pieces can be fabricated by which classification. | For the fabrication work included in the advertised plan, the fabricator will need to be listed on the Steel Primary Bridge Members APL, approved product 1. In the event the scope of work changes subsequent to this response, the contractor should submit a RFI to the project team to ensure that this answer is still correct. | Mike Coleman | 1 | 2025-01-14 09:57 | 2025-01-21 06:14
20250211 | 20250211019 | 19 | Non Functional Architectural Fixtures | In the general notes it states, "Remove existing non functional architectural light fixtures, and corresponding conduits mounted at steel members between bents 5 thru 13." How is this to be paid? | This work is intended to be incidental to the bid item "Removing Structure Over Waterway Debris Capture P-40-875." | Mike Coleman | 2 | 2025-01-29 12:10 | 2025-01-30 13:11
20250211 | 20250211019 | 19 | Previous Phase's Touch Up Painting | Is there any touch up painting from the previous phases that is planned to be done under Phase 3? | Touch up painting on Phases 1 & 2 work is to be done by contractors from those phases. | Mike Coleman | 3 | 2025-01-29 12:16 | 2025-01-30 13:10
20250211 | 20250211019 | 19 | SPV 12 - Waterway Markers | Please confirm if SPV 12 is intended for the Holton St project. | Any water work including barges will require waterway markers. | Mike Coleman | 4 | 2025-01-29 12:19 | 2025-01-30 13:10
20250211 | 20250211019 | 19 | Addenda 001 | Will WISDOT consider extending completion date due to addenda 001 stating no work in spans 10, 11, and 12 before August 18, 2025. |  |  | 5 | 2025-02-07 14:31
20250211 | 20250211019 | 19 | Work Type Required for Bidding | Is there any chance to change the required work type to bid prime to just Type H? Currently the required work types to bid prime are Types AFH. The steel and concrete repairs are minor. The majority of the work is Bridge Painting. Were not going to be receiving fair quotes for the repairs while those contractors can bid this prime as well. Again, the majority of work is Bridge Painting anyways, it makes sense to have it as Type H Prime job. |  |  | 6 | 2025-02-10 15:38
20250211 | 20250211020 | 20 | Epoxy Crack Sealing - Bid Item | There is a note in the special provisions Article 2 Scope of work that mentions "Epoxy Crack Sealing" also on sheet 116 or 146 of the plans the general notes 15th paragraph also mentions "Epoxy Crack Sealing". I cannot find a bid item for "Epoxy Crack sealing" Please advise. | Epoxy Crack Sealing for substructures is not included in the project scope, no bid item is required. The notes referenced in the question should be ignored. All crack sealing is to be performed under bid item 502.0180.S â€œBridge Deck Crack Sealingâ€. This change will be included in an addendum. | Mike Coleman | 1 | 2025-01-27 16:19 | 2025-01-29 13:29
20250211 | 20250211020 | 20 | Schedule | The schedule to reopen Mason St. by May 23rd seems unrealistic. There isn't enough time to approve the shop drawings and manufacture the joint in that time frame. Typically there is a minimum of 12 week lead time for fabrication. Can that time frame be adjusted out farther? | The schedule for the project is being re-evaluated considering the required joint procurement time. A revised schedule will be provided via addendum. | Mike Coleman | 2 | 2025-01-28 07:48 | 2025-01-29 13:32
20250211 | 20250211020 | 20 | Please see question #2 | Please review the May 23, 2025 deadline. Shop drawings, approval and fabrication/delivery of the expansion joints will conflict with that deadline. 12 weeks may be optimistic. Plus the additional work required after the joint repairs have been completed. paving, pavement marking, ETC | Similar to the response for Question 2, the schedule for the project is being re-evaluated in light of the required joint procurement time. A revised schedule will be provided via addendum. | Mike Coleman | 3 | 2025-01-29 09:27 | 2025-01-29 13:32
20250211 | 20250211020 | 20 | High Friction Green Surfacing | Would a polymer Liquid binder from the approved products list be ok to use on the High Friction Green surfacing item? | Polymer Liquid Binder is not allowed for use with the High Friction Green Surfacing bid item. The product used should include an MMA based resin system that is intended for use with colored pavement markings and anti-skid surfacing. | Mike Coleman | 4 | 2025-02-05 07:54 | 2025-02-06 06:36
20250211 | 20250211024 | 24 | Item #144 Special 02. UV GRP CIPP 24-Inch | The special provisions indicate a UV cured GRP system for this item. Wondering if a Steam cured GRP system would also be allowed as equivalent to UV cured? | The County would like to stay with UV cured for the pipe liner. | Mike Coleman | 1 | 2025-01-20 11:06 | 2025-01-22 06:38
20250211 | 20250211024 | 24 | Asphaltic Surface Item | In the plans, it specifies that removal of loose asphaltic material on the flume (sta 315+80 - sta 318+30) is incidental to this item prior to paving. Given the rough shape that the flume is currently in, should it be assumed that a majority of the existing flume will be removed? Or are the removals expected to be minimal? | The intent with this item is for the Contractor to remove all broken and unattached loose pieces of existing asphalt, as agreed upon with the Construction Engineer, incidental to the Asphaltic Surface pay item. Full removal of the existing asphalt in the flume area is not anticipated but want to address continuing deterioration prior to construction and any loose asphalt/material. A thin 2" layer of asphalt is to be placed over the existing flume to continue to facilitate drainage and prevent erosion in this area. | Mike Coleman | 2 | 2025-02-04 13:11 | 2025-02-06 06:34
20250211 | 20250211025 | 25 | Geotech Reports | I am writing to request the Geotech reports. Specifically, OSS Non-Standard Foundations, August 1, 2024 and OSS Standard Foundations, August 1, 2024. | There are no OSS on this project. | Mike Coleman | 1 | 2025-01-27 15:45 | 2025-01-28 08:32
20250211 | 20250211026 | 26 | Geotech Report for Structure B-44-325 | Will the geotech report be made available for structure B-44-325? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/gsx1rn7jip9kzqcrhabyfcmsq696d1fv or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 14:05 | 2025-01-16 06:37
20250211 | 20250211026 | 26 | WisDOT Typical Section | Sheet 31 depicts the construction of a back-to-back MSE retaining wall. In the notes below it states "R-44-56 requires additional bid items for construction. Refer to wall plans and details for additional information." Wall 44-56 is not included in the contract plans, and neither of the proposed structures (R-44-40 & R-44-41) are in a back-to-back configurations. Please clarify this contradiction. Thank you. | Sheet 31 was inadvertently left in the plans. Sheet 31 should have been removed. This will be noted in upcoming addendum. | Mike Coleman | 2 | 2025-01-21 14:15 | 2025-01-24 06:38
20250211 | 20250211026 | 26 | MSE Retaining Wall Panels | Can the MSE walls constructed on this project use 5' x 10' panels to match the adjacent walls being constructed on the IH41 corridor? | On the wall plans, in the design data, note states â€œMSE WALL PANELS LIMITED TO 5â€™ X 5â€™ SQUARE SHAPEâ€. The proposed 5' x5' panels will not be changed to 5' x 10' panels. | Mike Coleman | 3 | 2025-01-21 14:17 | 2025-01-24 06:48
20250211 | 20250211026 | 26 | S-44-403 Footings | For this structure, page 924 of the plans state a drilling shaft item for 30-inch diameter by 13-foot depth caissons. However, an MF-II is typically a 36-inch diameter by 13-foot. Page 925 states that the foundation is an MF-II, and the chart on page 929 shows an MF-II is 36-inch by 13-foot. What footing size is required and will an addendum be issued to change the drilling shafts quantities for the 30-inch and 36-inch totals? | The 30-inch diameter will be updated to a 36-inch diameter in the upcoming addendum. Coordination with utilities has taken place. | Mike Coleman | 4 | 2025-01-24 10:11 | 2025-01-28 08:30
20250211 | 20250211026 | 26 | MGS Temporary EAT's | Page 63 and page 68 show the 2 locations for this bid item. I have the following questions: When do these temporary EAT's get removed? What is connected to the other end of the MGS 3 that leads into these EAT's? What happens to the end of the MGS 3 once the temporary EAT's are removed? | The two temporary EATS will be switched from the temporary bid item to the standard MGS Guardrail Terminal EAT bid item in the upcoming addendum. | Mike Coleman | 5 | 2025-01-24 10:25 | 2025-01-29 13:20
20250211 | 20250211026 | 26 | OSS Non-Standard Foundations, August 1, 2024 and OSS Standard Foundations, August 1, 2024. | I am writing to request the Geotech reports associated with the I-41 corridor. Specifically, project ID 1130-65-76 has 2 reports: OSS Non-Standard Foundations, August 1, 2024 and OSS Standard Foundations, August 1, 2024. Could you please post those reports. | The OSS included in 1130-65-76 are standard foundations. Geotechnical reports are not required for standard foundations. | Mike Coleman | 6 | 2025-01-28 06:47 | 2025-01-28 06:59
20250211 | 20250211026 | 26 | Geotech Report Follow-Up | First, thank you for moving the question to proposal 26. In regards to the previous answer, can you please clarify for me. Article 10.2 of the Proposal reads as though a geotechnical report is available for the OSS Standard Foundations and to 'Review the available information to determine if it is of use'. Does the response in question 6 mean that no investigation was performed since the foundations are standard or does it mean that the report will not be given to the contractor because the foundations are standard? | The special provision text is incorrect and will be removed in the addendum. Bullets 3 & 4 will be removed. No geotechnical investigation or reporting was completed because the soil encountered around the Ballard Road interchange was stronger than base design parameters in the WisDOT bridge manual used for the standard sign structure design. This allowed us to not complete any foundation analysis for the sign structures in this area and recommend the use of one WisDOT's outlined standard foundation designs for sign structure support. | Mike Coleman | 7 | 2025-01-28 07:49 | 2025-01-29 13:19
20250211 | 20250211026 | 26 | Park and Ride Driveway Thickness | On sheet 3 the typical asphalt thickness shows 2" of 3 LT. Should this be changed to 4 LT as the minimum thickness specified for 19mm mixes is 2.25"? | Change from 3 LT to 4 LT was included in addendum documents submitted on 1/29/25. | Mike Coleman | 8 | 2025-01-28 09:02 | 2025-01-30 13:12
20250211 | 20250211026 | 26 | Removing monotube structures and foundations | For removing the monotube structures(they have structure numbers) why isn't bid item 204.0246 Removing Ancillary Structure(Number) used? The removal of the Ancillary Structure Foundation, theses foundations should be called out different from the removing bases items, these are not bases they are Ancillary Structure foundation. |  |  | 9 | 2025-01-31 14:26
20250211 | 20250211026 | 26 | R-44-40/41 MSE Walls | In the general notes for each wall it says "excavation for installation of the 24" culvert pipe requires temporary shoring to support wall R-44-40". Same note repeats on -41 wall. It does not say that the temporary shoring is incidental and there is no bid item for temporary shoring. |  |  | 10 | 2025-02-10 13:16
20250211 | 20250211027 | 27 | Geotechnical Report | Can the geotechnical report be posted? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/h2bpgn6cxphsh05vmd330vr0gegxry64 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-28 06:48 | 2025-01-28 06:57
20250211 | 20250211027 | 27 | Schedule | Can we get the designers schedule please. | The design schedule can be found at the following location: https://wisdot.box.com/s/h2bpgn6cxphsh05vmd330vr0gegxry64 or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-02-03 13:14 | 2025-02-04 13:34
20250211 | 20250211027 | 27 | access | Is there a construction access plan for the project? If so please advise where to find it. If not can we get the designers plan for ingress and egress to the stage 2 median work. | Access to the median is provided to/from I 41 through the north and south crossovers. Additionally, approved access to the I 41 median is provided from CTH JJ or Wrightstown Road between the existing structures, as shown in the construction details. | Mike Coleman | 3 | 2025-02-03 13:23 | 2025-02-04 13:36
20250211 | 20250211028 | 28 | Guardrail | Will the department allow steel I-beams to be used versus the wood posts? The rub rail would be mounted to the steel I-beams with an approved carriage bolt. | It is the desire of DOT to require wood posts in this area vs steel posts. Steel posts will not be considered as a replacement to wood posts. | Mike Coleman | 1 | 2025-01-20 09:33 | 2025-01-23 09:01
20250211 | 20250211028 | 28 | Department Construction Schedule | Can the Department's design construction schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/jtvcj45jtifzjugmpar2md38xy3u9fas or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-01-21 08:30 | 2025-01-22 08:28
20250211 | 20250211028 | 28 | HMA Mix For Multi Use Patch and Curb Patches | Would the Department consider adding an Asphaltic Surface item for the multi use path/curb patching and remove it from the 4 MT 58-28 S item in order to allow the contractor to complete the patching outside of the PWL requirements. | An addendum will be issued | Mike Coleman | 3 | 2025-01-28 14:00 | 2025-02-04 08:27
20250211 | 20250211028 | 28 | Traffic Control During Detour | How does the Department expect local traffic to be handled during the detour? There does not appear to be any traffic barrels or signs figured for lane closures during this time. With the bridge being hard closed on the far north end of the project and the number of businesses and housing located along this stretch, it seems like there could be a lot of traffic still utilizing the roadway during the detour? Will traffic control devices be paid to handle this traffic during the detour? | Traffic Control Cones 42-Inch and additional traffic control items will be added into the contract as part of Addendum 2. | Mike Coleman | 4 | 2025-01-31 08:33 | 2025-02-05 08:58
20250211 | 20250211028 | 28 | 11â€™ Lane Restriction. | The specials require an 11â€™ minimum lane while milling and paving with a lane closure or flagging. WisDOT flagging does not allow for flagging on a 4-lane highway without traffic closed to one lane. The inside lanes of this project are only 12â€™ to the face of curb. When paving the outside lane, at a minimum the drums will need to be moved over the center line narrowing the inside lane to less than 11â€™. It does not seem possible to maintain an 11â€™ lane? Will the Department allow the contractor to push traffic bidirectional with flagging operations? If so, will the traffic signals be disabled? Could the Department provide a traffic plan? | The minimum lane width requirement was reduced to 10-foot. Traffic Control Cones 42-Inch and additional traffic control devices were added into the plan quantities. In addition, a lane width restriction signing plan sheet was added as part of Addendum 2. Bi-directional traffic is not anticipated. | Mike Coleman | 5 | 2025-01-31 08:35 | 2025-02-05 09:02
20250211 | 20250211028 | 28 | Pipe work | Special provision article 24. Pipe Culverts The last sentence says "provide joint ties at all joints of circular or horizontal elliptical concrete culvert pipes greater than 60 inches, including endwalls" The 66 inch is bid as storm sewer 608, does this requirement for joint ties apply to storm sewer also? | Yes, the joint tie requirement applies to the 66â€ storm sewer. | Mike Coleman | 6 | 2025-02-04 08:50 | 2025-02-05 08:59
20250211 | 20250211028 | 28 | Culvert Backfill | Special provision article 25. Culvert Pipe Backfill. I am confused were all the pipe meant to be culverts per 520 or culverts per 608? If all the pipes were meant to be per 608 storm sewer (which requires granular backfill) why is this article even in the contract? | Article 25 Culvert Pipe Backfill will be removed as part of Addendum 2. | Mike Coleman | 7 | 2025-02-04 08:56 | 2025-02-05 09:00
20250211 | 20250211030 | 30 | On-Site Access to the inside of the bascule bridge | We are requesting access inside the bascule bridge to the counterweight pit to complete an on-site inspection since they donâ€™t believe the plans provide a complete picture for bidding purposes. | An addendum will be issued to address upcoming site access times. They are as follows: â€¢ Thursday, January 23, 2025; 8:00 am â€“ 9:00 am (Jim will provide access) â€¢ Tuesday, January 28, 2025; 8:00 am â€“ 9:00 am (Winnebago County will provide access) These opportunities will allow the contractors to review the bridge, but they are not Q/A sessions. Please submit any questions through the standard BidX process after your field review. | Mike Coleman | 1 | 2025-01-21 12:04 | 2025-01-21 12:08
20250211 | 20250211030 | 30 | HPU BOM | Regarding sheet 104 Hydraulic Schematic, please provide the bill of materials for the existing HPUs. | Note 7 on Sheet 104 Hydraulic Schematic (drawing M-04) indicates that the Bill of Materials can be found on the Price Engineering shop drawings from the rehabilitation project in 2000. The drawings can be found at the following location: https://wisdot.box.com/s/cdkhiiecwd6jmra3phspje9b2qj8hrkc or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-01-30 08:21 | 2025-01-30 13:16
20250211 | 20250211030 | 30 | Additional Bridge Access Date | Requesting another date for access to bridge to allow contractors to review work with potential subcontractors. | WisDOT is unavailable and unable to provide additional bridge access times. However, much of the work area is visible from the waterway, which could be accessed with a private boat. Under no circumstances will unauthorized access onto or within the bridge be allowed. | Mike Coleman | 3 | 2025-02-03 21:08 | 2025-02-05 08:59
20250211 | 20250211030 | 30 | Steel Fabricators | What fabrication classification is required for the structural steel on this project? Will a WDOT approved fabricator for Primary Bridge Members be mandated? If different level classifications will acceptable, please identify which pieces can be fabricated by which classification. | Subsection 506.3 of the Standard Specification applies. Rolled beam stringers, their connections and bascule span lateral bracing are considered Primary Members. Railings, expansion devices, and access platforms are considered Fabricated Bridge Components. | Mike Coleman | 4 | 2025-02-04 06:35 | 2025-02-05 08:57
20250211 | 20250211030 | 30 | Fox River Closure | There are no navigation closure restrictions shown in the special provisions for the Fox River between 9/2/2025 and 4/17/2026, please confirm that the Fox River may be completely closed to navigation during this time frame. If clearance restrictions will be added please provide the minimum allowable elevation. | The Fox River may not be completely closed between 9/2/2025 and 4/17/2026. Movable bridge operations are governed by Code of Federal Regulation 33 CFR Part 117. Operating regulations for this portion of the Fox River are located at 33 C.F.R. 117.1087(b). During the normal navigation season from April 27 through October 7, the draws shall open on signal, except between the hours of midnight and 8 a.m., the draws shall open if at least 2-hours advance notice is given. From October 8 through April 26, the draws shall open if at least 12-hours advance notice is given. The Contractor may make written requests to the USCG for temporary deviations from operating regulations. The USCG will review, consult with mariner stakeholders, and make a determination. The USCGâ€™s willingness to receive a request should not be construed in any manner as a willingness to approve a submitted request. The horizontal and vertical clearance restrictions are those of the current bridge geometry. Similar to operating regulations the Contractor may make advanced written requests to the USCG for temporary alterations to navigation clearances. Upon receipt, the USCG would engage with local mariners and issue a determination. This willingness to receive a request should not be construed in any manner as a willingness to approve any request submitted. | Mike Coleman | 5 | 2025-02-04 07:15 | 2025-02-07 07:35
20250211 | 20250211030 | 30 | Buy America Requirement for Cylinders | Will the cylinders have to meet Buy America requirements for all components that are incorporated into the final product? | See the â€œBuy America Provisionâ€ in the contract for the requirements of Iron and Steel Materials, Manufactured Products, and Construction Materials. | Mike Coleman | 6 | 2025-02-04 11:35 | 2025-02-05 14:03
20250211 | 20250211031 | 31 | Stage 1A & 2A Friday Hours | Stage 1A and 2A show hours for nighttime lane closures. The Friday AM hours appear to be missing in the closure times. | Article 6 (Traffic) does include the Friday AM hours for Stages 1A and 2A. For STH 441/USH 10 eastbound (page 8 of 30), the first bullet under Stage 1A hours to maintain a minimum of 1-12â€™ lane and 2â€™ minimum shoulder shows Monday â€“ Thursday 8:00 PM â€“ 6:00 AM. This would include the Thursday 8:00 PM â€“ Friday 6:00 AM timeframe. The same logic can be applied to the respective timeframes shown for STH 441/USH 10 westbound during Stage 1A and to all timeframes shown for STH 441/USH 10 during Stage 2A. | Mike Coleman | 1 | 2025-01-20 09:40 | 2025-01-21 13:07
20250211 | 20250211031 | 31 | Existing Structural Approach Slabs | Is the removal of the existing structural approach slabs to be included in the Removing Pavement, Excavation for Structures Bridges, or Removing Structure bid items? | The removal of the existing Structural Concrete Approach Slabs is included in the removing structure item. The removal of the concrete approach slabs is part of the removing concrete pavement. Also, this response applies to the 7 structures that have bridge plans. For the other 6 structures where regular approach slabs are being constructed, the removal of the existing would be under the removing concrete pavement bid item. | Mike Coleman | 2 | 2025-01-22 13:36 | 2025-01-24 10:38
20250211 | 20250211031 | 31 | Work Zone Access | Once temporary barrier wall is installed, will access to and from the work zones be permitted during daytime hours without an additional lane closure? | Yes, this would be allowed during daytime hours. | Mike Coleman | 3 | 2025-01-22 13:44 | 2025-01-27 06:21
20250211 | 20250211031 | 31 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/16y9s232yi0jzg19ox27icnl93062uhb or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2025-01-30 15:14 | 2025-01-31 10:26
20250211 | 20250211032 | 32 | HMA items | Could the HMA items be changed to Asphaltic Surface, as the 4LT is less than1 full load and density should be waved by specification as the segment lengths are less than 50 lineal feet. | An addendum will be issued. | Mike Coleman | 1 | 2025-01-21 09:39 | 2025-01-22 08:36
20250211 | 20250211033 | 33 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/cmvvlt1r9tpz5svvyybt7o0i24tsgpv3 or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-01-08 15:54 | 2025-01-16 06:25
20250211 | 20250211033 | 33 | Project Schedule | Please provide the project schedule developed as part of the design process. | The design schedule can be found at the following location: https://wisdot.box.com/s/cmvvlt1r9tpz5svvyybt7o0i24tsgpv3 or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-01-14 09:39 | 2025-01-16 06:27
20250211 | 20250211033 | 33 | Geotechnical Data | Please provide the geotechnical data available for the project limits. | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/cmvvlt1r9tpz5svvyybt7o0i24tsgpv3 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-01-14 09:40 | 2025-01-16 06:32
20250211 | 20250211033 | 33 | Foam Sealant Joint Repair | The special provisions for the Foam Sealant Joint Repair provide minimum standards the material must meet in order to be used on the project. Can you please provide the manufacturer(s) considered at the time the special was developed. Having trouble finding a material that meets all the requirements. | We cannot provide a list of manufacturer (s); however, this same special provision article has been used in past WisDOT projects. | Mike Coleman | 4 | 2025-01-29 15:19 | 2025-02-03 05:57
20250211 | 20250211033 | 33 | Pavement Marking | There does not appear to be enough quantity for Grooved Wet Reflective Epoxy 6-inch (specifically the white). Please advise | Agree, quantity updates will be addressed by addendum. | Mike Coleman | 5 | 2025-01-30 08:25 | 2025-01-31 07:49
20250211 | 20250211033 | 33 | Proposal 33 | Should Line Item 324 Covering Type I Signs be Covering Type II Signs instead? | Yes, they should be Covering Type II signs. Updates will be addressed by addendum. | Mike Coleman | 6 | 2025-02-02 13:47 | 2025-02-03 14:18
20250211 | 20250211033 | 33 | Asphaltic Surface at Culvert Replacements | Per sheet 23 (ID# 1590-18-71/81), the culvert replacements call for 6 ï¿½" of Asphaltic Surface HMA. Per the miscellaneous quantities on sheet 99 in the plan (IDâ€™s 1590-18-71/81), the full depth 6.25â€ HMA at the culvert crossings is to be paid as Asphaltic Surface Temporary. Will the HMA be paid as asphaltic surface or asphaltic surface temporary? Quantity appears to only account for 4â€ of HMA. How will the remaining 2 ï¿½â€ be paid? | Agree, an addendum will be issued to address the differences. | Mike Coleman | 7 | 2025-02-03 12:07 | 2025-02-04 08:28
20250211 | 20250211033 | 33 | Traffic on Milled Surface | Can the department clarify what its intention is with special provision 3 stating, traffic is not allowed on a milled surface during mainline milling operations following the conclusion of the working day. This can be interpreted that after mainline milling operations are done each day, that traffic can then run on the milled surface while milling operations arenâ€™t occurring. | The intent is to pave the areas that are milled each day. The sentence states, "Traffic shall not be allowed to run on a milled surface during mainline removing asphaltic surface milling operations following the conclusion of the working day." | Mike Coleman | 8 | 2025-02-03 12:09 | 2025-02-04 08:22
20250211 | 20250211033 | 33 | 3MT Binder Thickness from STA 553+50 to STA 605+26 | Will the department consider increasing the binder thickness in the above station range to 4.5â€ to allow the contractor to pave the 3MT in two 2.25â€ lifts rather than one 4â€ lift? This will allow the contractor to have better control of even compaction and cross slope across this section. | No, please bid according to the plans. | Mike Coleman | 9 | 2025-02-03 12:09 | 2025-02-04 08:20
20250211 | 20250211033 | 33 | 3LT and 4LT | Based on the type of paving that the 3LT and 4LT HMA is called out to be used for per sheet 50 of ID 1590-18-83 plan set, will the department consider eliminating these items and instead using the Asphaltic Surface Patching item for this work? This would eliminate the need for HMA testing and be a more cost effective way to patch the utility trenches. If the department doesnâ€™t want to eliminate the items, can they waive HMA mix and density testing for the 3LT and 4LT bid items? | Agree, items will be changed to Asphaltic Surface item, and it will be addressed by addendum. | Mike Coleman | 10 | 2025-02-04 13:23 | 2025-02-05 09:08
20250211 | 20250211034 | 34 | Geotech Report for Structure B-37-474 | Will the geotech report be made available for structure B-37-474? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/gsv2h0188l9adbaedvtzyhifw69nb9rw or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 14:07 | 2025-01-16 05:51
20250211 | 20250211034 | 34 | Cofferdam in drawings, but no bid item | Hi, The erosion control sheet (pg 6) shows no erosion control around the existing pier, which will need to be removed. Sheet 1 of the bridge plan shows and labels a cofferdam around the new pier installation. There is no bid item for the cofferdam. Will one be added? Will any erosion control be needed during existing pier removal? | The cofferdam item was never intended to be used for the project due to the shallow water at the site. However, this item will be added to the structure plan through an addendum as the prebored holes at the pier will need to be dry for setting the piles. Due to the shallow water at this site, an undistributed quantity of silt fence could be used for temporary erosion control purposes during removal operations of the existing pier. The contractorâ€™s proposed method for controlling erosion during the pier removal will need to be detailed in the ECIP. | Mike Coleman | 2 | 2025-01-17 14:44 | 2025-01-23 13:28
20250211 | 20250211034 | 34 | Cofferdam Bid Item Missing | A cofferdam is called for in the plans, however there is not bid item in the contract. | The cofferdam item was never intended to be used for the project due to the shallow water at the site. However, this item will be added to the structure plan through an addendum as the prebored holes at the pier will need to be dry for setting the piles. | Mike Coleman | 3 | 2025-01-21 12:29 | 2025-01-23 13:30
20250211 | 20250211035 | 35 | Tack Coat Item | Proposal Line Number 0024 Tack Coat has the unit measurement in Tons. Will the department issue an addendum to change this to Gallons? | The proposal has the incorrect bid item. It should use bid item number 455.0605, Tack Coat, GAL. An addendum will be created to resolve the discrepancy with the miscellaneous quantities in the plan. | Mike Coleman | 1 | 2025-01-29 11:23 | 2025-01-30 06:31
20250211 | 20250211036 | 36 | R-39-14 Permanent Sheet Piling Minimum Section Modulus | What is the minimum section modulus for the R-39-14 permanent steel sheet piling? | The minimum section modulus is 57.17 in^3/ft, which is the standard plastic section modulus for the PZ-35 shape specified on sheet 2 of the structures plan set. | Mike Coleman | 1 | 2025-02-04 14:03 | 2025-02-10 07:18
20250211 | 20250211037 | 37 | HMA Pay Items | Would the department consider changing the Asphalt pay items to Asphaltic Surface with a Special Provision stating the lower and upper layer mix requirements? Also, the typical sections on Sheet 4 of the plans is showing 2" 3LT Upper Lift and 2.25" 4LT Lower Lift. this appears to be switched. | An addendum will be issued to remove HMA Pavement bid items and will be replaced with the Asphaltic Surface bid item and an associated special provision. Mix type and pavement section will be modified on plan and in special provisions as follows; 2.25â€ 3 MT 58-28 S (Lower) 2â€ 4 MT 58-28 S (Upper) | Mike Coleman | 1 | 2025-01-15 15:58 | 2025-01-22 06:18
20250211 | 20250211038 | 38 | Traffic Control Sheets | The plan appears to be missing the Traffic Control - Detour Detail Pages for Details #5 and #6. | An addendum will be issued to add detour detail sheets #5 & #6. | Mike Coleman | 1 | 2025-01-24 15:02 | 2025-01-28 06:31
20250211 | 20250211038 | 38 | 520.2.5.3 Trench Backfill (Culvert Pipe) | According to spec 520.2.5.3 excavated material can be used for the trench backfill, if the engineer feels it is unsuitable, then the contractor will need to use an engineer-approved material. If the material is rejected by the engineer at the time of construction, will a change order be issued for the contractor to supply an approved material? | It is not anticipated that excavated material will be deemed unsuitable for use as trench backfill. If it were deemed unsuitable, Base Aggregate Dense, 1 ï¿½-inch would be used and paid for under the contract item. | Mike Coleman | 2 | 2025-02-05 09:34 | 2025-02-06 06:35
20250211 | 20250211039 | 39 | Geotech Report for Structure B-71-205 | Will the geotech report be made available for structure B-71-205? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/fa8vdo1lmioj2d9yufvyyzlfypo46mbx or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 14:09 | 2025-01-16 06:22
20250211 | 20250211039 | 39 | Utility conflict, wing piling, B-71-206 | There are overhead lines directly above the proposed east side wing pile, but the overhead lines are noted as remining in place. These power lines will need to be moved prior to construction- de-energizing or pole tipping will not be sufficient. Sheeting may be required to remove the existing concrete footings as well, further complicating the utilities. Please clarify how this conflict is to be addressed. | An addendum will be issued to clarify. | Mike Coleman | 2 | 2025-01-24 10:42 | 2025-01-30 06:38
20250211 | 20250211039 | 39 | Traffic Control | There is a section for Type II Covering signs listed in the Special Provision section, but is not a bid item or reference in the plan. We would just like to make sure that it isn't missing from the plan. | An addendum will be issued | Mike Coleman | 3 | 2025-02-03 13:22 | 2025-02-05 09:04
20250211 | 20250211041 | 41 | Geotech Report for Structure B-50-95 | Will the geotech report be made available for structure B-50-95? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/mb8whhdch8fit2jkyff1nyn3rqkn3kgd or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 14:11 | 2025-01-16 06:43
20250211 | 20250211041 | 41 | Borrow | The earthwork summary on sheet 12 shows 370 CY of waste generated from the west side of the bridge. The table then shows a expanded fill of 511 CY and 425 CY of borrow on the east side. Is the intent to dispose of the waste generated from the west side of the bridge offsite and bring in borrow for the east side? | Yes, that was the intent regarding the earthwork. | Mike Coleman | 2 | 2025-01-31 09:47 | 2025-02-03 14:18
20250211 | 20250211041 | 41 | Traffic Control | Will a Portage route be provided for the waterway? | Yes, a portage route is to be provided. It is shown on the plan & profile sheet. The portage route signage is included in the Traffic Control item per special provision article 14. | Mike Coleman | 3 | 2025-02-03 12:06 | 2025-02-04 08:21
20250211 | 20250211043 | 43 | Geotech Report for Structure B-37-478 | Will the geotech report be made available for structure B-37-478? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/38s31ei7dvzkqn5gygd7wdrlxf7yxchd or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 14:12 | 2025-01-21 06:47
20250211 | 20250211046 | 46 | Geotech Report for Structure B-37-480 | Will the geotech report be made available for structure B-37-480? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/x6degx2am47j9b7olfl22h8d0qvzl6a6 or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-01-14 14:14 | 2025-01-16 06:19
20250211 | 20250211046 | 46 | Contract Time | Would the Department consider extending the number of working days to accommodate the pre-boring requirements in all substructure units? The current contract timeframe appears unattainable without extraordinary forces. | The contract completion time will be updated to 55 working days to accommodate the effort due to pile pre-boring. | Mike Coleman | 2 | 2025-01-22 13:06 | 2025-01-24 10:40
20250211 | 20250211047 | 47 | Concrete Pavement | We are requesting for hand placement methods be approved for the pavement on this project. | The project will follow Spec 415.6 for the placement of concrete and any location/areas where the contractor deems hand methods are warranted need to be approved by the construction engineer. | Mike Coleman | 1 | 2025-01-20 08:41 | 2025-01-21 13:06
20250211 | 20250211047 | 47 | Geotechnical Data | Please provide any geotechnical data available for this project. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/rds0gxvf10f1809m4zr02ww8l5ht2cyc or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-01-21 11:57 | 2025-01-22 07:47
20250211 | 20250211047 | 47 | Pipe Bollards | Would a red, high density, polyethylene sleeve be allowed to cover the galvanized pipe bollards? Having to use the paint system specified in 517.2.4 will make each bollard more expensive than the hydrant they are protecting. Thanks | City would like it bid as indicated in the plan. | Mike Coleman | 3 | 2025-01-22 10:46 | 2025-01-23 08:57
20250211 | 20250211047 | 47 | Design Schedule | Can the Design Schedule be provided for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/rds0gxvf10f1809m4zr02ww8l5ht2cyc or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2025-02-05 07:51 | 2025-02-05 13:59
20250211 | 20250211048 | 48 | Culvert Pipe | The culvert pipe at STA 376+83 is listed in the misc quantities under 520.3630 Class III-B NON-METAL 30-INCH. The plan details show the same pipe as RCP REQ'D. Please clarify. | An addendum will be issued to clarify. | Mike Coleman | 1 | 2025-01-28 11:15 | 2025-01-29 13:18
20250211 | 20250211048 | 48 | Concrete pavement in road | According to the Lane repair detail, there is 9" of concrete pavement in the road. How is the removal of the concrete pavement paid for in the culvert transition areas? | The removal of the concrete pavement in the culvert transition areas will be paid for with an added item, 204.0100 Removing Concrete Pavement. An addendum will follow. | Mike Coleman | 2 | 2025-02-03 14:58 | 2025-02-04 10:40
20250211 | 20250211048 | 48 | Culvert work at sta. 238 + 56 | On sheet 60 of the plan, for the 48" it references extending the pipe 30' to the new slope intercept. In the cross sections it shows 21' of CL 3 B non-metal 48" in this area. There is not an item for this in the misc. quantities. Please clarify what we are constructing. Additionally, there are not any quantities for constructing a transition at the salvage culvert work at Sta. 76+00 pipe. Is the intention to construct a transition at this location? | 1. We are extending 21-ft of Culvert Pipe Reinforced Concrete Class III 48-Inch per pipe. An addendum was submitted to add this item. 2. The intention is to construct a transition at this location. | Mike Coleman | 3 | 2025-02-05 10:07 | 2025-02-07 07:30
20250211 | 20250211048 | 48 | Backfill Controlled Low Strength | Where does the Backfill Controlled Low Strength go? | Backfill Controlled Low Strength was replaced by Foam Void Filling B-10-72, Item SPV.0060.02. Backfill Controlled Low Strength item should be removed. | Mike Coleman | 4 | 2025-02-05 10:36 | 2025-02-07 07:30
20250211 | 20250211048 | 48 | Traffic Control: Structure C-10-1092 | Would the department consider adding temporary traffic signals/ Temporary Barrier with one lane traffic to construct C-10-1092? It appears the guardrail will need to be removed to install the temporary shoring which will leave an unprotected excavation/ working area. | At this time, the department feels temporary traffic signals are not necessary for the construction of box culvert C-10-1092 extension. However, temporary barrier wall could be considered for C-10-1092. | Mike Coleman | 5 | 2025-02-05 12:32 | 2025-02-07 07:30
20250211 | 20250211048 | 48 | C-10-1092 - Temporary Water Diversion | C-10-1092: Can the department provide details for the temporary water diversion noted on sheet 2 of the structure plans? | The intent is to pump the water through the pipe during culvert extension and will be paid for with a temporary water diversion bid item. | Mike Coleman | 6 | 2025-02-05 12:34 | 2025-02-07 07:31
20250211 | 20250211050 | 50 | HMA Mix Type | The plans show a 4MT 58-28H for the mix type in the typical sections and miscellaneous quantities, however the pay item is 4LT 58-34S. | An addendum will be issued. | Mike Coleman | 1 | 2025-01-27 16:36 | 2025-01-31 10:40
20250211 | 20250211050 | 50 | Paved Shoulder | Is there a detail or cross-section somewhere for the paved shoulder (for stage 3 traffic) from 63+50 to 66+00 or what is the desired pavement thickness for this shoulder? | The desired pavement thickness for the shoulder widening is 5â€ Asphaltic Surface (i.e., match existing adjacent asphalt thickness) | Mike Coleman | 2 | 2025-01-27 16:50 | 2025-01-31 10:41
20250211 | 20250211050 | 50 | Curb Patching | Want to confirm there are quantities/plans for sawing, removals and HMA patching along the curb replacement locations? | There are quantities for sawing asphalt, removing asphalt surface, and asphaltic surface where there is existing asphalt behind the back of the spot curb & gutter replacement. It is assumed the existing asphalt on the flag side of the spot curb & gutter replacement will be used to form the new curb & gutter. Any sawing, removals, or patching on the flag side necessary for contractor operations would be considered incidental to Concrete Curb & Gutter, 30-Inch, Type D. | Mike Coleman | 3 | 2025-01-27 16:59 | 2025-01-31 10:42
20250211 | 20250211051 | 51 | Construction Staking | I do not see an construction staking items on this proposal. Will the staking be performed by the contractor or engineering staff? | The items will be added via addendum. | Mike Coleman | 1 | 2025-01-29 10:02 | 2025-01-31 07:44
20250211 | 20250211051 | 51 | Storm Sewer Removals | there are no items currently listed for storm sewer removals. can/will these be added? | The project will need to remove the existing structures in order to install the new structures as they will be at same locations, so we feel that removal is not a separate item in these cases. Contractor can include their removal costs in the cost of the new structures or part of the excavation common item. | Mike Coleman | 2 | 2025-01-30 09:10 | 2025-01-31 07:42
20250211 | 20250211051 | 51 | Construction Staking Slope Stakes | I believe an item for Construction Staking Slope Stakes needs to be added to the contract. | We looked at that as an item but felt it was not warranted in the urban segment as for the most part it is pretty cut and dry what the excavation limits are. The county is doing all the grading work outside the shoulder points in the rural segment so there is none required there. | Mike Coleman | 3 | 2025-02-04 16:50 | 2025-02-05 14:02
20250211 | 20250211053 | 53 | Mussel Relocation | In the past the state has procured malacological personnel. Can the Department provide a list of recommended malacologists? | The Department does not maintain a publicly available list of qualified individuals or firms for these services. However, the Wisconsin DNR maintains a list of those qualified for this type of work at the following link: MusselContacts.pdf (wiatri.net). | Mike Coleman | 1 | 2025-02-04 09:45 | 2025-02-05 08:53
20250211 | 20250211053 | 53 | Structure Removal | An industry standard, to safely and efficiently remove the truss is to lighten the truss, drop it, and remove in sections. Will dropping the truss be allowed? | Bridge removal is to follow standard specification item 203.0250 (Removing Structure Over Waterway Remove Debris) as included in the contract documents. This item allows for the dropping of the truss into the waterway. The DNR is aware of the potential need to drop the truss into the waterway. | Mike Coleman | 2 | 2025-02-04 09:52 | 2025-02-05 08:54
20250211 | 20250211053 | 53 | Design Schedule | Can the department provide the design construction schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/l1eg1jvod1vkhxdppe5xl5ttg6x23djl or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2025-02-05 08:12 | 2025-02-05 14:05
20250211 | 20250211053 | 53 | Project Schedule | The project calls out a notice to proceed no later than 4/1/25, with a road closure on CTH G that cannot happen until 6/1/25. The nature of this project is dictated heavily on the closure of G and the structure removal. The project also has an instream restriction form 4/1-6/1. What is the reason for the 4/1/25 notice to proceed? | The 4/1/25 notice to proceed is so that the Bird Deterrent system can be installed prior to 4/15/25. | Mike Coleman | 4 | 2025-02-05 08:19 | 2025-02-05 14:01