## qandasearchletting_results
Date | 2025-05-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250513 | 20250513001 | 1 | EBS / Select Crushed | The MQ include undistributed quantities of EBS and select crushed for cable barrier anchors. Please provide a construction detail on how these quantities will be utilized. | Refer to the General Notes for Cable Barrier Type 1 Layout (SDD 14B52-03a). â€œProvide Wisconsin Professional Engineer signed and approved footing design and construction sequence when over excavation is required near a footing.â€ | Mike Coleman | 1 | 2025-04-23 07:49 | 2025-04-23 11:10
20250513 | 20250513001 | 1 | soils report | Do the DOT have and can they make available to the contractors any boring in the areas that new cable barrier will be installed? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/g6mclnccbkp640gvw487hu2o9z94p79t or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-05-01 12:54 | 2025-05-02 09:28
20250513 | 20250513003 | 3 | Design Schedule | Will the Department please share the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/nvymknp4mtyc4ognw179qai1mp3kc02i or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-04-15 09:39 | 2025-04-15 13:40
20250513 | 20250513003 | 3 | Salvaged Asphaltic Pavement Base | Would the Department consider changing the salvaged asphaltic pavement base special to match the pulverizing specification as follows: Pulverize the existing asphaltic pavement until 97 percent or more will pass the 2-inch sieve per spec 325.3(1) |  |  | 2 | 2025-05-01 09:18
20250513 | 20250513003 | 3 | Working days | Contractor is requesting a change in working days from 45 to 57 based on the following: There are 10 pipes and 10 pipe transitions and one removing structure. Though the road is closed to through traffic, it is open to local and emergency vehicles. As such, the pipe work and structure removal is expected to take 23-25 days. Following this work will be the remainder of the schedule including the milling, paving, shouldering, guard rail, striping and rumble strips. |  |  | 3 | 2025-05-01 09:41
20250513 | 20250513003 | 3 | sawing | will a sawing item be added for culvert pipes, driveways and removing the structure? |  |  | 4 | 2025-05-01 10:48
20250513 | 20250513004 | 4 | Temporary Pavement Marking | Does the Department intend to use the Temporary Pavement Marking item on the Upper Layer of pavement without using The Grooved Wet Reflective Epoxy item for the permanent marking? | Temporary Pavement Marking will be used on upper layer of pavement prior to centerline rumble strips. After centerline rumble strips are installed, use Marking Line Epoxy. Grooved wet reflective epoxy is not proposed. | Mike Coleman | 1 | 2025-04-28 12:42 | 2025-04-30 07:06
20250513 | 20250513005 | 5 | Geotech Report for B-62-266 | Will the geotech report for structure B-62-266 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/gh1ufko0822yke22wy77ddcn4liaj2ew or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-04-16 15:04 | 2025-04-18 07:18
20250513 | 20250513009 | 9 | TPO closures | For the Howard Ave thin polymer overlay the daytime off-peak closure, "contractor is allowed one full roadway closure" is that one day per direction? Would the department allow 2 stages to do this? | The department will allow one roadway closure for each direction for TPO work at Howard Avenue so that it can be completed in two stages. An addendum will be issued to revise the special provisions to allow one full roadway closure for each direction for this work. | Mike Coleman | 1 | 2025-04-24 16:34 | 2025-04-28 06:52
20250513 | 20250513009 | 9 | Design Schedule | Can the Department provide a design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/iv2gim1cumu9p9wq05m737p1ni8kwn4d or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-04-25 12:58 | 2025-04-28 08:57
20250513 | 20250513009 | 9 | Removing Concrete Surface Partial Depth | It appears in the typical sections, the milling contractor is to remove the existing HMA and variable depths of concrete. How is the removing concrete surface partial depth paid? | The work will be paid under item 204.0109.S Removing Concrete Surface Partial Depth. An addendum will be issued to add the pay item, quantity, and SPV. | Mike Coleman | 3 | 2025-04-29 09:07 | 2025-04-29 12:55
20250513 | 20250513010 | 10 | Geotech Report for Bridge B-40-1102 | Will the geotech report for structure B-40-1102 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/v57682f2yl62g5h6yj0lsxfm6w6fnvhu or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-04-16 15:05 | 2025-04-17 09:53
20250513 | 20250513010 | 10 | 17'x5' manhole | can you provide a detail fro the structure | Sheet 9 of the plans has a Construction Detail for the 17â€™x5â€™ manhole. | Mike Coleman | 2 | 2025-04-24 12:42 | 2025-04-25 07:22
20250513 | 20250513011 | 11 | Design Schedule | Can the Department provide a project design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/gvep0c52bmhsz77lz5fuypn0pgmk53ba or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-04-25 13:00 | 2025-04-29 07:54
20250513 | 20250513011 | 11 | Award/Execution | Can the Department expedite the contract award and execution? | we will follow our typical award process. The award is not solely contingent upon the department, rather the contractorâ€™s timely and complete submittal of all necessary documentation directly impacts the timeline to award. | Mike Coleman | 2 | 2025-04-25 13:03 | 2025-04-29 08:43
20250513 | 20250513011 | 11 | Concrete Staging | Based on planned new concrete pavement, all concrete pavement repairs/replacements should be done ahead of new pavement placement to assure jointing aligns properly and to assist in crack mitigation between old and new pavements. It doesnâ€™t appear the planned staging accounts for SHES Concrete Repair/Replacement work. Can SHES concrete pavement repairs/replacements be performed ahead of the July 7th date, independently of plan scheduled lane closures if performed during nights hours and reopen daily during peak and off-peak hours? At minimum concrete patching operations of the WB lanes, West of National will need to be completed prior to stage 1 traffic control setup which the plans do not indicate. | The project start date of July 7th as shown in the Special Provisionâ€™s Prosecution and Progress article will remain unchanged. | Mike Coleman | 3 | 2025-04-30 10:07 | 2025-05-05 11:10
20250513 | 20250513011 | 11 | Temporary Signal Schedule | Can temporary signal work be performed prior to July 7th, if work is performed in guidance with SPV off-peak, nighttime work, holiday restriction, and special event lane closure hours? | The project start date of July 7th as shown in the Special Provisionâ€™s Prosecution and Progress article will remain unchanged. | Mike Coleman | 4 | 2025-04-30 10:09 | 2025-05-05 11:05
20250513 | 20250513011 | 11 | Utility Coordination | Can electrical meter pedestal bases be installed prior to July 7th to allow for WE Energies electrical supply order lead time? | The project start date of July 7th as shown in the Special Provisionâ€™s Prosecution and Progress article will remain unchanged. | Mike Coleman | 5 | 2025-04-30 10:10 | 2025-05-05 11:06
20250513 | 20250513013 | 13 | Approved Fabricators | What fabrication classification is required for the structural steel on this project? Will a WDOT approved fabricator for Primary Bridge Members be mandated? If different level classifications will acceptable, please identify which pieces can be fabricated by which classification. | There are several steel bid items for this project: - For SPV.0085.510 BRIDGE STRUCTURAL STEEL and SPV.0085.513 STRUCTURAL STEEL REPAIR, a WisDOT-approved fabricator for Primary Bridge Members is required. Subsection 506.3 of the Standard Specification applies, and only fabricators meeting category 3 for â€œbascule bridgesâ€ will be acceptable. - For SPV.0085.550 NON-STRUCTURAL STEEL BALLAST, no approved fabricator is needed. | Mike Coleman | 1 | 2025-04-09 14:33 | 2025-04-14 06:53
20250513 | 20250513013 | 13 | Site Visit | We would like to visit the site and get access to all parts of the bridge. Who do we coordinate with to setup this site visit? | The City of Milwaukee can provide access to the bridge. Please contact Siba Rahman at 414-286-0468 to discuss availability for access. Note that due to poor condition some areas of the bridge are not accessible without access vehicles (man lift etc.). Access to these areas will not be provided by the City of Milwaukee at this time. Any person entering the area under the bridge will be required to wear proper PPE (hard hat, safety vest, steel toed boots, etc.). | Mike Coleman | 2 | 2025-04-09 16:32 | 2025-04-14 06:50
20250513 | 20250513013 | 13 | Pre-approved Steel fabricators | For the Bridge Structural Steel and Structural Steel Repair items, does the approved primary member fabricator need to be approved for category 3 (bascule bridges) or do they just have to be approved for category 1 or 2. | For SPV.0085.510 BRIDGE STRUCTURAL STEEL and SPV.0085.513 STRUCTURAL STEEL REPAIR, a WisDOT-approved fabricator for Primary Bridge Members is required. Subsection 506.3 of the Standard Specification applies, and only fabricators meeting category 3 for â€œbascule bridgesâ€ will be acceptable. | Mike Coleman | 3 | 2025-04-11 10:38 | 2025-04-14 09:32
20250513 | 20250513013 | 13 | Non-structural ballast steel grade | Will the department consider alternative steel grades for non-structural ballast? If so, what would the acceptance criteria be? Current spec requires A709 gr 36 or 50. | A709 Grade 36 or 50 is preferred, but alternative steel grades that will be considered for non-structural ballast are A36, A572, A992, or A588. All material substitutions will be subject to review and approval by the engineer. Acceptance criteria will include weight per cubic foot, corrosion resistance, paintability, durability, and weldability. | Mike Coleman | 4 | 2025-04-15 09:51 | 2025-04-16 09:06
20250513 | 20250513013 | 13 | Structure Repainting Recycled Abrasive B-40-550-14, Item 517.1801.S | The subject item states that all metal surfaces Structure B-40-550-14 are to be blasted and painted. Please confirm. If yes, then the estimated area of 82,000 seems largely underestimated. | The estimated area of 82,000 is approximate and given for informational purposes only, and it is intended to cover all existing steel that is to remain. The steel is to be cleaned and painted under bid items "Structure Repainting Recycled Abrasive B-40-550-14" and "Negative Pressure Containment and Collection of Waste Materials B-40-550-14." Existing top flanges of steel to remain which will be embedded in new deck concrete are to be repainted under bid item "Preparation and Coating of Top Flanges B-40-550-14.â€ This is not included in the estimated area to be blasted and painted. All new steel is to be painted under bid item "Painting Epoxy System B-40-550-14." This work is not included in the estimated area to be blasted and painted. | Mike Coleman | 5 | 2025-04-17 10:56 | 2025-04-24 08:15
20250513 | 20250513013 | 13 | Schedule | Can the Department provide the anticipated schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/smnln4hz6ekuvhkterojscugxxmlmsyd or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2025-04-17 15:58 | 2025-04-22 07:58
20250513 | 20250513013 | 13 | Clarification plan sheet 70 of 218 - AG2 Girders Remove & Replace or Repair only | Notes in the middle of the page state, "Anchor Girder AG2 to be repaired", note at top of the page states "Portion of anchor girder AG1 to be replaced" Note towards bottom states "anchor girder AG1 to be repaired". Notes are confusing with sheet 71 which shows 24'-10" of all anchor girders AG1 & AG2 as being replaced. Please clarify | The 24â€™-10â€ portions of all anchor girders will be replaced as shown on Sheet 71. The portions of the anchor girders to the left of the splice are to be repaired as noted and shown on sheet 72. | Mike Coleman | 7 | 2025-04-18 11:43 | 2025-04-22 08:03
20250513 | 20250513013 | 13 | Most Recent Balance Calculations - availability. | Can the department provide the most recent balance calculations? | The balance calculations from the 1985 rehabilitation project is available can be found at the following location: https://wisdot.box.com/s/smnln4hz6ekuvhkterojscugxxmlmsyd or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 8 | 2025-04-18 11:54 | 2025-04-22 09:50
20250513 | 20250513013 | 13 | Rack Removal Required | Please clarify the required rack removals? | Items SPV.0060.571 and SPV.0060.572 include the complete demolition of the existing bridge operating machinery, including racks, unless otherwise requested by the City. Item SPV.0060.522 designates the removal of the rack and pinion at the southwest interior bascule girder (SW G2) as the gear set to be used as part of the interpretive exhibit. In short, all eight racks are to be removed but the one rack located at SW G2 is to be repurposed as part of the interpretive exhibit. | Mike Coleman | 9 | 2025-04-18 11:56 | 2025-04-22 08:03
20250513 | 20250513013 | 13 | Faying Surface Painting | Please advise if the existing faying surfaces will require painting prior to new structural steel members being installed. If required, please advise what painting spec and bid item this is supposed to follow. | All existing steel that is to remain is to be cleaned and painted under bid items "Structure Repainting Recycled Abrasive B-40-550-14" and "Negative Pressure Containment and Collection of Waste Materials B-40-550-14." The surfaces of existing steel, which will become faying surfaces for new steel connections, would be included in those items. All existing steel surfaces where new steel will be bolted must be cleaned and receive one coat of primer according to Standard Spec 517.3.1.3 and 506.3.12. Those faying surfaces are to be painted with zinc-rich primer and masked for intermediate and protective coats as described in Standard Spec 517 if painting is performed prior to steel installation being completed. | Mike Coleman | 10 | 2025-04-21 09:43 | 2025-04-29 07:56
20250513 | 20250513013 | 13 | Plan Sheet Note 62/218 Btm middle "Temp Bracket to Support Shoring No Disturbance to River Allowed | The note in the middle bottom of the sheet states. "Temporary Bracket to Support Shoring - No Disturbance to the River Bottom Allowed" (TYP). The special provisions allow for instream disturbance outside the fish window 3-1 to 6-15. The special provisions pages 4 & 5 of 75 United States Coast Guard - list guidelines for spudding barges outside the fish window. SPV 50 Removing timber Fender System & Dolphins lists ways to "minimize" disturbance but disturbance will be required. Does the note on sheet 62 or 218 refer to within the fish window or is it for the job duration? | The note on plan sheet 62/218 refers to the job duration. The temporary bracket system is not to disturb the river bottom at any time. | Mike Coleman | 11 | 2025-04-21 10:30 | 2025-04-23 06:39
20250513 | 20250513013 | 13 | Asbestos Inspection Report | Can the department please supply a copy of the asbestos inspection report referenced in SPV 22 sheet 29/215 | The Asbestos Inspection Report can be found at the following location: https://wisdot.box.com/s/smnln4hz6ekuvhkterojscugxxmlmsyd or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 12 | 2025-04-22 08:38 | 2025-04-23 06:36
20250513 | 20250513013 | 13 | Asbestos Report B-40-0550-14 | Can the Department provide the asbestos report for the structure? | The Asbestos Inspection Report can be found at the following location: https://wisdot.box.com/s/smnln4hz6ekuvhkterojscugxxmlmsyd or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 13 | 2025-04-22 13:04 | 2025-04-23 07:04
20250513 | 20250513013 | 13 | Bearing Replacement | Can the Department clarify whether the quantities for the Fixed and Expansion bearing replacement are correct? If they are correct, can a revised "Sheet A-02 of A-21" be provided to identify all (36) fixed bearing replacement locations? | Thank you for the question. The quantities for the Fixed and Expansion bearing replacement were not correct. An Addendum will soon be released to provide the following updates: â€¢ The quantity for bid item 505.6000 Bearing Assemblies Expansion will be revised to 20. â€¢ The bid item 505.5000 Bearing Assemblies Fixed is eliminated. â€¢ All other â€œbearingsâ€ not paid as â€œBearing Assemblies Expansionâ€ are paid as â€œBridge Structural Steelâ€. â€¢ Some clarifying notes are added. | Mike Coleman | 14 | 2025-04-22 13:12 | 2025-04-29 07:57
20250513 | 20250513013 | 13 | Asbestos Abatement Report Clarification | The asbestos abatement report identifies a small amount of mastic and caulk as ACM requiring abatement. The report also mentions that observed electrical wiring/components and internal components of bridge equipment were assumed to contain regulated ACM, but testing could not be completed on those materials. Does the Department plan to have an environmental consultant onsite during demolition to test the rest of the materials that were previously assumed to be containing regulated ACM? | An environmental consultant will not be on-site during planned demolition to test observed but inaccessible materials assumed to contain regulated ACM. | Mike Coleman | 15 | 2025-04-23 10:26 | 2025-05-01 06:38
20250513 | 20250513013 | 13 | City of Milwaukee Bureau of Electrical Services Property | The SPVs mention a TLE for the City of Milwaukee Bureau of Electrical Services property and that access to the material storage bins be maintained at all times during the construction project. The SPV doesn't mention anything regarding other materials stored near/underneath the bridge inside of TLE. Can those materials stored underneath the bridge on that property be moved prior to/for the construction project? | The material stored under the bridge between Bent 59 and the Menomonee River from the West right-of-way Line to the East edge of the TLE will be removed prior to the allowable start date of July 6, 2025 for the project. Material storage by the City of Milwaukee will continue within other areas of the TLE. | Mike Coleman | 16 | 2025-04-23 10:57 | 2025-04-25 07:27
20250513 | 20250513013 | 13 | Followup to questions 15 - Asbestos Abatement - Payment for additional abatement | The report also mentions that observed electrical wiring/components and internal components of bridge equipment were assumed to contain regulated ACM, but testing could not be completed on those materials. Does the Department plan to have an environmental consultant onsite during demolition to test the rest of the materials that were previously assumed to be containing regulated ACM? If these "assumed" inaccessible areas are later identified as containing regulated ACM. How will the additional abatement work be paid for? | An environmental consultant will not be on-site during planned demolition to test observed but inaccessible materials assumed to contain regulated ACM. Testing of these materials will need to be performed by the Contractor. Should the materials assumed to contain regulated ACM be confirmed then proper abatement will need to be carried out by the Contractor. For the materials assumed to contain regulated ACM only, abatement will be handled as a revision to the contract. | Mike Coleman | 17 | 2025-04-23 13:30 | 2025-05-01 06:39
20250513 | 20250513013 | 13 | Steel Repair Removals | There are notes on the structure plans at repair details that â€œcost for removing structural steel for repairs is included in the bid item - removing structure over waterway minimal debris B-40-550-14.â€ See notes at the bottom of S-18 and S-19, or notes at the bottom right of S-56 â€“ S-60, S-70-S-74, S-93, S-95, S-98, S-99 and A-03. However under SPV 54. Structural Steel Repair it states that it includes removing sections of existing steel members, or payment is for removal of existing steel required to accommodate repairs. Please confirm that steel to be removed for repairs is to be included under the structural steel repair item. | All permanent steel removal is included in the bid item â€œRemoving Structure over Waterway Minimal Debris B-40-550-14.â€ References to removal in SPV 54. Structural Steel Repair are related to existing steel that is to remain but needs to be temporarily removed to accommodate the steel repair. One possible example of this situation would be if removal of member H22A on Sheet S-56 (page 117) is needed to accommodate the Structural steel repair #2 on that sheet, then the removal and reinstallation of the H22A member is incidental to the Structural Steel Repair item and will not be measured for payment. | Mike Coleman | 18 | 2025-04-28 16:54 | 2025-05-05 07:13
20250513 | 20250513013 | 13 | Question 10 - Follow-up Faying Surface Painting | Can the cleaning as required by this question be done using a power tool method or does it need to be a full abrasive blast before receiving the primer coat? | Acceptable preparation methods for the faying surfaces of existing members to be primed are either blast cleaning to near-white metal (in accordance with item 517.1801.S and SSPC SP-10) or power tool cleaning to bare metal with no stains from mill scale, rust, or paint (in accordance with Standard Spec Section 517.3.1.3.2 and SSPC SP-11). | Mike Coleman | 19 | 2025-04-29 08:31 | 2025-05-02 06:40
20250513 | 20250513013 | 13 | Clarification SPV 18 Notice to Contractor - Creosote Timber and SPV 50 Remove Timber Fender System | Page 26 of 215 SPV 18 "Notice to Contractor - Creosote Lumber" states that Disposal shall be incidental to "Excavation, Hauling, and Disposal of Creosote Contaminated Soil" Page 76 thru 78 of 215 also references Bid Item 10 205.0506S Excavation, Hauling, and Disposal of Creosote Contaminated Soil. Please clarify payment of disposal of creosote timbers | Payment for disposal of creosote timbers is to be included as part of Items SPV.0060.587, Remove Timber Fender Systems B-40-550-14 and SPV.0060.588, Remove Timber Dolphins B-40-550-14. | Mike Coleman | 20 | 2025-05-01 08:59 | 2025-05-05 07:14
20250513 | 20250513013 | 13 | Turbidity Barrier for Timber Removals | Turbidity barrier is a standard bid item, please provide a contract bid item for turbidity barrier instead of making it incidental to the timber removal item. | We respectfully disagree with adding a bid item for turbidity barrier for the following reasons. The use of turbidity barrier as one of several methods or options to control sediment during timber removals has been extensively coordinated with the WisDNR during the design phase of this project. Based on this extensive coordination, the WisDNR is OK with the Special Provisions as written and with the pay items as listed in the Project, based on their multiple reviews during the design phase of the Project. The contractor can use methods other than turbidity barriers for controlling sediment if he so desires, as noted in the special provisions. The Special Provisions as written have been closely coordinated with the WisDNR and should not be edited without knowledge of the WisDNR. A pay item for Turbidity Barrier is not needed because such means of controlling sediment is already spelled out in the Special Provisions and included in the basis of payment and bid items for removing the timber fender systems and timber dolphins and handling creosote contaminated soil. | Mike Coleman | 21 | 2025-05-01 09:10 | 2025-05-05 07:15
20250513 | 20250513013 | 13 | Clarification on "Remove, rehabilitate and reinstall" | Please provide clarification on expectations for pieces with notes to "remove, rehabilitate and reinstall". An example is on sheet 75/218 regarding the A18 strut. | For the pieces with notes to â€œremove, rehabilitate and reinstallâ€, â€œremoveâ€ refers to the assumed need to temporarily remove the piece because the members that support it are being replaced, â€œrehabilitateâ€ refers to blast cleaning, re-painting, and any preparation required to make the new connection, and â€œreinstallâ€ refers to reconnecting it to the replaced members. If the contractor prefers to temporarily support these pieces in their current locations during replacement of the supporting members, that would be acceptable instead of removing and reinstalling, but this was assumed to be less desirable. | Mike Coleman | 22 | 2025-05-01 15:16 | 2025-05-05 07:14
20250513 | 20250513013 | 13 | Center Shear Transfer Device Installation | There is only a 4" gap between the bascule girders and between the floor beam flanges to access the area between the north and south bascule spans to install the center shear transfer devices once the deck is poured. Please advise how the Department intended for this area to be accessed to install bolts for the shear device. | The intent is that most of the work be done from the other side, not between the floorbeams. For all times that the bearings are not installed, work can be done through the hole in the north floorbeam. When the bearings are installed, we acknowledge that access to the last bolts will be difficult. Modifications could be made to accommodate the specific means and methods preferred by the contractor. We will be open to discussions during shop drawing development to incorporate such modifications. | Mike Coleman | 23 | 2025-05-02 13:13 | 2025-05-06 10:17
20250513 | 20250513013 | 13 | 643.5000 Traffic Control | Hello, item 643.5000 Traffic Control is not included in the bid items. Can this item be added on? Thanks | Item 643.5000 Traffic Control will be added to the bid items. | Mike Coleman | 24 | 2025-05-05 15:03 | 2025-05-06 10:24
20250513 | 20250513013 | 13 | Bascule girder alignment | Is any straightening anticipated as part of SPV.0085.510 Bridge Structural Steel or just re-aligning the bascule girders as noted in sections C.3 and C.4? | No heat-straightening is anticipated. Re-alignment of the bascule girders is anticipated to require equipment to pull and hold the girder ends in position while steel is erected, but heating should not be necessary to accomplish this | Mike Coleman | 25 | 2025-05-06 13:12 | 2025-05-07 05:35
20250513 | 20250513013 | 13 | Anchor Span Deck | The underside of the concrete deck on the approach spans between the loading and anchor girders will not be accessible to strip formwork over the bascule girders after the deck is cast (see sheets S-43/S-44). Will the department allow stay-in-place decking in these areas? |  |  | 26 | 2025-05-07 09:24
20250513 | 20250513014 | 14 | Geotechnical Report | Please provide a copy of the Geotechnical Report. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/8nwovo4oo2ohtelo82fe6y4iltu5sc8x or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-05-01 08:43 | 2025-05-05 07:02
20250513 | 20250513014 | 14 | EBS | The Earthwork table indicates EBS is to be backfilled with 3" dense but Note 2 of the General Notes on plan page 2 states EBS areas are depicted by the 16" select crushed material shown in the plans. Please review and clarify. | Due to the extensive amount of moisture in the soil borings, the project team decided to include the subgrade improvement into the overall pavement structure, which is the select crushed material as shown in the typical sections. Any EBS encountered beyond that should be backfilled with the 3â€ dense. | Mike Coleman | 2 | 2025-05-01 08:55 | 2025-05-05 07:12
20250513 | 20250513018 | 18 | Inquiry about Plan holder List | Could you please provide a list of plan holders for this bid letting as we would be working with the prime contractors as a WIM supplier. | In Bid Express, where you went into the lettings tab, there is a link at the top of the lettings page that allows you to click on the Plan holders link. It will open to show you all plan holders per proposal. | Mike Coleman | 1 | 2025-04-09 10:23 | 2025-04-14 07:03
20250513 | 20250513018 | 18 | Geotech Reports | Can you send out the soil borings and geotech reports for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/64e9bfnpvsxfiu423p2udh7led64vzz3 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-04-18 09:14 | 2025-04-21 09:12
20250513 | 20250513018 | 18 | Schedule | Can we get the estimated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/64e9bfnpvsxfiu423p2udh7led64vzz3 or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2025-04-18 09:14 | 2025-04-21 09:14
20250513 | 20250513018 | 18 | site clearance | Could there be some information be provided for the item site clearance. It is listed as undistributed and I have not found any information in the specification or plan. | The item was included for the removal of site items that may have been left from the previous project and for erosion control items left in place. The current construction oversight staff said that the building site clearance will be completed prior to this contract being initiated. The site clearance item will be limited to removal of erosion control items, such as silt fence, left in place at the completion of the 1130-44-74 grading. | Mike Coleman | 4 | 2025-05-05 21:19 | 2025-05-06 11:18
20250513 | 20250513020 | 20 | Schedule | Can you send out the DOT estimated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/a2bx42raffeyfuc12e3tk2wusv5yg33v or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-04-18 09:11 | 2025-04-21 08:54
20250513 | 20250513020 | 20 | Geotech Reports | Can you send out the geotech and soil borings for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/a2bx42raffeyfuc12e3tk2wusv5yg33v or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-04-18 09:12 | 2025-04-22 08:02
20250513 | 20250513020 | 20 | C-05-0800 | Can Hemlock Creek be bypass pumped and the box culvert extension be built in one piece instead of the staged construction shown on the structure plans? | The intent is to utilize staged construction with water diversion; however, alternative methods of handling water will be reviewed if proposed as part of the ECIP submittal process | Mike Coleman | 3 | 2025-04-21 11:43 | 2025-04-22 12:01
20250513 | 20250513020 | 20 | Earthwork Cross Sections | Can we get cross sections for the bridge abuttment stations? there is nothing close on the east side for us to calculate the structure excavation. for this side. The west side has a cross section at 117+50 but it would help to have one at 117 +80. To calculate the structure excavation we actually need the crossection right thru to I-41. | The cross sections will be added via addendum. | Mike Coleman | 4 | 2025-04-29 11:10 | 2025-05-02 09:31
20250513 | 20250513020 | 20 | Schedule | The Department provided schedule indicates structure B-05-0696 beginning in April 2026. Can the structure work begin in September 2025 or once the 1130-68-81 project is complete? | Work can begin on the median pier of structure B-05-0696 in 2025 once the widening and temporary concrete barrier is completed on I-41. Work on the abutments cannot begin until early fill settlement is complete which is expected in the spring of 2026. | Mike Coleman | 5 | 2025-05-01 08:06 | 2025-05-05 06:48
20250513 | 20250513020 | 20 | Freeway Full Closures | For full closures, would the Department allow BOTH directions to be closed for certain operations such as beam setting, falsework stripping, and equipment movements? | As per special provisions, full freeway closures will be limited to one direction of travel at a time. Lane closures would still be allowed in the opposite direction during permitted times. | Mike Coleman | 6 | 2025-05-02 15:42 | 2025-05-06 11:19
20250513 | 20250513020 | 20 | Anchoring to C-08-0800 | Will any anchoring to the existing box culvert we allowed for shoring or water diversion purposes? | Anchoring temporary supports or shoring to any portion of the existing box culvert to remain in place will not be permitted. | Mike Coleman | 7 | 2025-05-02 15:44 | 2025-05-06 10:16
20250513 | 20250513020 | 20 | C-05-0800 Undercut/Temporary Shoring | 1. Please confirm that the undercut beneath the new culvert extension and apron is to be 10ft. 2. Please confirm that a temporary shoring line shall be placed along the west end of apron removal limits to protect the existing culvert under slab fill. 3. Some of the temporary shoring will not be able to be removed. Please confirm that this is acceptable. | 1) Yes, the undercut is 10 feet below the floor of the box culvert extension and extends 5 feet beyond the footprint. Area is backfilled with breaker run. 2) Yes, the temporary shoring between stage 1 and stage 2 removals would be needed as the two halves are constructed. Once stage 2 breaker run is placed the expectation would be that the temporary shoring would be removed prior to pouring the slab. 3) We are not anticipating any temporary shoring to remain in place. | Mike Coleman | 8 | 2025-05-02 16:35 | 2025-05-06 13:16
20250513 | 20250513020 | 20 | Innovation Court | Does the plan include any excavation quantities for the temporary pavement work on Innovation Court? | The removal quantities for the temporary pavement on the north end of Innovation Court were not included. These quantities will be added via addendum. | Mike Coleman | 9 | 2025-05-05 10:49 | 2025-05-07 12:44
20250513 | 20250513020 | 20 | Misc Qtys | Would there be some qtys for Aggs for the following; Sta NB 648+88 - 652+00 Sta NB 590+66 - 600+00 Sta C Ramp 600+00 - 608+00 C Sta SB 583+75 - 606+13 B Ramp/Parallel Ramp And anything else that might be missing. | Aggregate quantities were included within those locations, but the MQ table incorrectly labeled those station ranges. This will be corrected via addendum. | Mike Coleman | 10 | 2025-05-06 10:29 | 2025-05-07 12:44
20250513 | 20250513020 | 20 | Aggs Conversions | Could you tell us what conversions were used for: Select Crushed CABC 1.25 Inch CABC 3/4 Inch | Select Crushed: 2.0 Tons/CY CABC 1.25 Inch: 2.0 Tons/CY CABC ï¿½ Inch: 2.1 Tons/CY | Mike Coleman | 11 | 2025-05-06 10:57 | 2025-05-07 05:34
20250513 | 20250513020 | 20 | Right of Way | Will the department allow placing the excess excavation from the project within the ROW? In particular, the areas that would be available would be the following: * Area bound by Mid Valley Dr/Ramp C/Southbridge Rd EB * Area bound by Southbridge Rd Ramp B Pond/Southbridge Rd EB It looks like both of these locations are being used on the current project to place excess earthwork materials. |  |  | 12 | 2025-05-07 09:57
20250513 | 20250513021 | 21 | Schedule | Would the Department provide their construction schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/u4urz1ptwuz9mbcxgkf4rutiuaftkm5d or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-04-17 07:35 | 2025-04-18 07:12
20250513 | 20250513022 | 22 | Geotech Report for Bridge B-20-263 | Will the geotech report for structure B-20-263 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/rk9rx5zdr2f9zonxndw3yhvrq0l63jfr or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-04-16 15:06 | 2025-04-17 09:57
20250513 | 20250513023 | 23 | geotechnical Data | Can you supply geotechnical data for this project? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/b7wj0hbaabuk2ay0s3iuctj36e08sb21 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-04-22 09:19 | 2025-04-23 06:43
20250513 | 20250513024 | 24 | Geotechnical Report | Please provide a copy of the geotechnical report. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/bu6lf6nc56gzs1cfkvkxd2lmfb69ifgu or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-04-23 13:15 | 2025-04-24 09:39
20250513 | 20250513024 | 24 | Geotechnical Report | Regarding the provided geotechnical report, were there any borings completed? | There were no soil borings completed as part of the overall design effort. | Mike Coleman | 2 | 2025-05-01 08:36 | 2025-05-02 09:29
20250513 | 20250513025 | 25 | Excavation Fills | Based on water elevation shown in the plan, and from a site visit today, project fills will be occurring in water with depths up to or over 2 feet, and horizontally out 8 to 10 feet into the water. The cofferdam is shown to only satisfy the bridge itself in the dry. Was there any thought how the excavation fills should be satisfied in the water? | An addendum will be issued to address the fill in the water. | Mike Coleman | 1 | 2025-04-28 14:49 | 2025-04-29 12:59
20250513 | 20250513025 | 25 | 643.5000 Traffic Control | Item 643.5000 Traffic Control is missing from this project. Can this item be added on? Thanks | Bid Item 643.5000 Traffic Control will be added to this project. An addendum will be issued to add this bid item. | Mike Coleman | 2 | 2025-04-28 14:55 | 2025-04-29 12:57
20250513 | 20250513026 | 26 | Proposal Line Items | Proposal Line Items in the plans and in the Special Provisions do not appear to line up, and some items appear to be missing in the Special Provisions that are included in the EOQ in the plans. Example: Item 34m in the plans is Prep of Foundation and is not in the Specials. Item 34 in the specials is Finishing Roadway. | Please bid the Schedule of Items in the back of the proposal as these are showing the correct items and quantities. The EOQ line numbers in each plan set will not line up with the schedule of items in the back of the proposal. The item Prepare Foundation for Asphaltic Paving (project) 01. 6508-01-71 is not needed and a bid item for this is not included in this proposal. | Mike Coleman | 1 | 2025-04-23 11:57 | 2025-04-23 12:21
20250513 | 20250513026 | 26 | 53-INCH X 83-INCH ENDWALLS | The 53-INCH X 83-INCH CL HE-III Culverts at STA. 40+28 call for concrete masonry endwalls which is item 0072 Concrete Masonry Endwalls. There is also item 0104 Apron Endwalls for Culvert Pipe Reinforced Concrete Horizontal Elliptical 53x83-Inch - 4 each, but this quantity is not listed on the Miscellaneous Quantities table for culvert pipe items on page 108 of the planset. Could the department please clarify Item 0104 and if it is needed? | Bid Item 522.2653 Apron Endwalls for Culvert Pipe Reinforced Concrete Horizontal Elliptical 53X83-Inch will not be used in this project. The quantity for Item 504.0900 Concrete Masonry Endwalls is for the 53X83-Inch culverts as shown in the plan. An addendum will be issued to remove bid item 522.2653 from the proposal. | Mike Coleman | 2 | 2025-04-24 12:29 | 2025-04-28 06:52
20250513 | 20250513026 | 26 | MISSING CROSS SECTIONS | Could The department please provide the Cross Sections For stations 58+00 - 62+56.89 not included in the proposed plan set? | An addendum will be issued to add the cross sections to the plan set. | Mike Coleman | 3 | 2025-04-28 15:37 | 2025-04-30 06:52
20250513 | 20250513027 | 27 | Geotech Report for Bridge B-38-152 | Will the geotech report for structure B-38-152 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/x4u5o5xdaksy84ncfrvh309ccheuiob3 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-04-16 15:07 | 2025-04-18 07:21
20250513 | 20250513027 | 27 | 643.5000 Traffic Control | Item 643.5000 is missing from this project. Can this item be added on? Thanks | We will prepare an amendment to add this item. | Mike Coleman | 2 | 2025-04-28 15:00 | 2025-04-29 12:58
20250513 | 20250513028 | 28 | Temporary Mask Out Tape | The Miscellaneous Quantities call for 1,345 LF of Temporary Mask Out Tape on this project but I do not see a Bid Item for it. | Bid item should be 1345 LF of Item 643.3960 "Temporary Marking Removable Mask Out Tape 6-Inch". Quantity for bid item 643.3180 "Temporary Marking Line Removable Tape 6-Inch" will be revised to 4920 LF. An addendum will be prepared. | Mike Coleman | 1 | 2025-04-21 10:37 | 2025-04-22 12:01
20250513 | 20250513028 | 28 | Topsoil | There appears to be an error with the topsoil "unit" in the proposal. Can it be switched from CY to SY? | This was incorrectly entered as CY into AWP. It is shown correctly as SY on the plans. We will issue an addendum for this to correct | Mike Coleman | 2 | 2025-05-05 13:37 | 2025-05-06 10:18
20250513 | 20250513029 | 29 | Concrete Pavement 10-Inch and asphalt shoulders | The item of Concrete Pavement 10-Inch is greater than 300' in length requiring the use of a slipform paver. Please advise on the plan intent for this area ss it does not appear that the plan accounts for removing and replacing the asphalt shoulders in the concrete pavement area. | The plan originally included 2 longer pavement replacement sections and in the end those two sections were combined that created the longer than 300â€™ section and the concrete pavement item. The shoulders will need to be removed and replaced in this concrete pavement section and this was missed on the plans. We will prepare an addendum to incorporate this change. | Mike Coleman | 1 | 2025-05-02 08:49 | 2025-05-05 06:51
20250513 | 20250513030 | 30 | Design Schedule for Construction | Please provide the construction schedule that was proposed during the design phase. | The design schedule can be found at the following location: https://wisdot.box.com/s/kilbnlhfneowd5nchu6syuedvpbgdtdni or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-04-22 15:15 | 2025-04-23 08:37
20250513 | 20250513031 | 31 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/yb9sy46vqvysrznoeeh4xsq2fxns17kp or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-04-17 11:29 | 2025-04-18 07:09
20250513 | 20250513032 | 32 | Forest County Potawatomi Community Contact | Could the Department check the contact information for the tribal labor office and confirm the details provided? | An addendum has been issued to correct the contact information. The contact is as follows: Katheryn Tupper, Tribal Labor Officer 5414 Everybodyâ€™s Road, Crandon, WI 54520 Office: (715) 478-4896 Cell: (715) 889-3402 Email: Katheryn.tupper@fcp-nsn.gov | Mike Coleman | 1 | 2025-04-14 13:25 | 2025-04-14 13:30
20250513 | 20250513032 | 32 | 643.5000 Traffic Control | The item 643.5000 is missing from this project. Can this item be added on? Thanks. | Addendum 02 will be issued to add item 643.5000 to the project. | Mike Coleman | 2 | 2025-04-28 15:43 | 2025-05-01 14:44
20250513 | 20250513034 | 34 | Cold Weather Paving | Would the Department consider adding cold weather asphalt paving items to allow for paving later in the season? | The bid item will be added via addendum | Mike Coleman | 1 | 2025-04-16 16:24 | 2025-04-29 07:38
20250513 | 20250513036 | 36 | Working Days | Bridges this size will typically have 40 working days. Most of those bridges do not have poured parapets and approach slabs which require additional days for the work and cure times. Was that accounted for in the schedule? Thanks | Appropriate concrete cure times were accounted for related to all concrete elements. | Mike Coleman | 1 | 2025-04-15 07:33 | 2025-04-22 12:04
20250513 | 20250513036 | 36 | Cold Weather Paving | Would the Department consider adding cold weather asphalt paving items to allow for paving later in the season? | No accommodation for cold weather asphalt paving items will be allowed for late season paving. | Mike Coleman | 2 | 2025-04-16 16:24 | 2025-04-22 12:02
20250513 | 20250513038 | 38 | Cold Weather Paving | Would the Department consider adding cold weather asphalt paving items to allow for paving later in the season? |  |  | 1 | 2025-04-16 16:25