## qandasearchletting_results
Date | 2025-06-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250610 | 20250610001 | 1 | Design Schedule. | Can the Design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/g6mclnccbkp640gvw487hu2o9z94p79t or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-05-08 12:13 | 2025-05-08 13:25
20250610 | 20250610001 | 1 | Design Schedule. | Was the correct link to the correct schedule provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/tr5269fm7lw1perurkevrq7asc29zyq1 or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-05-09 22:48 | 2025-05-20 06:43
20250610 | 20250610001 | 1 | 1.25" Base on STH 11 | No Base is called out for the ramps or mainline work on STH 11. After the pavement is removed, we expect some 1.25-base will be needed. Will WisDOT pay for the 1.25-inch base in this area or will it be incidental? | The project does not anticipate additional 1.25-BAD to be required in these areas. In the event that there is loss and additional 1.25-BAD is required for preparing the foundation, that additional material will be considered incidental. | Mike Coleman | 3 | 2025-05-17 09:53 | 2025-05-20 06:45
20250610 | 20250610001 | 1 | MIll and Relay | Mill and Relay requires 100% of the milled material to pass a 1.5" sieve. Milling the existing shoulders in-place without further processing (most likely hauling off site and crushing) will not produce a gradation with 100% passing a 1.5" screen. Would the department consider replacing the Mill and Relay bid item with the Pulverize and Relay bid item? | An addendum will be issued. | Mike Coleman | 4 | 2025-05-22 10:23 | 2025-05-28 06:38
20250610 | 20250610001 | 1 | Sawing | Will the department pay for sawing per 690.4(2) in association with item 204.0100 Removing Concrete Pavement? Breaking and removal of the existing concrete pavement in a traditional manner would greatly disturb the subbase. Considering the department is seeking minimal disturbance of subbase during the removal process in the planned existing concrete pavement removal and replacement scenario, use of 690.4(2) would help minimize subbase disruption by allowing pavement to be removed similar to pavement patching. |  |  | 5 | 2025-06-03 10:43
20250610 | 20250610001 | 1 | Staging. | Can there be overlapping of the stages or does each stage have to be complete prior to the next stage. For example, can STH 11 start at the same time at Stage one on USH 151/61? | The example posed in the question would be acceptable. | Mike Coleman | 6 | 2025-06-05 14:23 | 2025-06-06 07:00
20250610 | 20250610001 | 1 | Barrier Wall Removal. | Is there a footing under the existing barrier wall and if yes can dimension be provided? Was an old standard used for the footing if a footing exists? | Yes there is a footing 2â€™ wide, 9â€ High and 10â€™ Long. | Mike Coleman | 7 | 2025-06-06 10:16 | 2025-06-09 11:30
20250610 | 20250610001 | 1 | Length of Barrier Wall Transition. | Can the length of the Concrete Barrier Transition Type NJ32 DF to S 36 be provided? Can you confirm it is 10' unless it is some other length? | Yes there is a footing 2â€™ wide, 9â€ High and 10â€™ Long. | Mike Coleman | 8 | 2025-06-06 12:20 | 2025-06-09 11:31
20250610 | 20250610001 | 1 | Barrier Wall Pad | Please confirm the S 42 Barrier Pad (101) is new asphalt pavement. | No it is a concrete footer following the SDD 14B37 footer. | Mike Coleman | 9 | 2025-06-07 18:39 | 2025-06-09 11:32
20250610 | 20250610001 | 1 | Staging | Can Stage 4 be constructed with Stage 2 as long STH 11 to the NB 151/61 Ramp traffic is maintained? Some concrete work in stage two will need to be completed prior to switching into the Stage 4 configuration. Time is going to be very tight in this area of the project. | As long as the ramp traffic is maintained then yes. | Mike Coleman | 10 | 2025-06-08 10:56 | 2025-06-09 11:33
20250610 | 20250610001 | 1 | 8 Inch Pavement | Can it be confirmed that only the through lanes of STH 11 are being removed and paved at Badger Road. There is no paving plan or removal plan that shows the concrete. The miscellaneous concrete only includes quantity for the through lanes. Please clarify or we can figure the miscellaneous quantities shown for the 8 Inch Concrete Pavement represent the work to be done in this area and bid accordingly. | The miscellaneous quantities for concrete pavement replacement have the pavement sections on the outside next to the mainline under 38+01V to 41+60V and 37+96W to 41+51W. These sections are in front of Badger Rd and STH 35. | Mike Coleman | 11 | 2025-06-09 06:25 | 2025-06-09 12:19
20250610 | 20250610001 | 1 | Stage 6 | Can some of the advance work be performed in Stage 6 this year as long as the roadway is left in the current condition or better prior to the November 10, 2025 completion date for Stages 1 through 5? |  |  | 12 | 2025-06-09 12:21
20250610 | 20250610003 | 3 | Pre Walk Meeting | Are we having a prebid walk? | Due the scope of this project a pre walk meeting is not scheduled. The department is willing to entertain specific questions that a contractor may have. | Mike Coleman | 1 | 2025-05-20 14:27 | 2025-05-27 11:17
20250610 | 20250610003 | 3 | Construction Time | Can you clarify the construction time for the job? It does mention Oct 15 for some items but nothing for the building. | The completion date for the entire project is 12/9/25. The October 15, 2025 date was for sitework and to get erosion control and restoration completed in time to have the grass start to grow. | Mike Coleman | 2 | 2025-05-28 17:58 | 2025-06-03 13:04
20250610 | 20250610003 | 3 | Removing Exisiting Bldg | SOW indicates to remove an existing building. Drawings does not show demolitions drawings for the building to be removed. | 1. The specifications call out item Removing Building STA 5+75, Item 204.0231.01 and the spec provides a description for the demolition of the structure under that item. The existing structure is a garage with the intent to be cleaned out by the County prior to the start of project work. There is no full demolish plan provided because the is no demolition phasing, no salvaging of materials, etc. | Mike Coleman | 3 | 2025-05-28 18:42 | 2025-06-03 13:05
20250610 | 20250610003 | 3 | Plan Holder List | Not really sure if this is the right area to ask. We submitted all the required information and we are not listed as a plan holder. Would you be so kind as to clarify if we are good to submit our cost in bid day? | Please submit the DT1633 to be an eligible plan holder. We have not seen one submitted by you for this proposal. The link to the DT1633 is https://trust.dot.state.wi.us/bprs/dt1633Submittal.do | Mike Coleman | 4 | 2025-06-03 13:35 | 2025-06-04 07:58
20250610 | 20250610004 | 4 | Special Provision 4. Traffic | Under Flagging heading is the contractor require to keep delays under 5 or 15 minutes? | The contractor will be required to keep delays under 5 minutes | Mike Coleman | 1 | 2025-05-20 10:18 | 2025-05-22 06:08
20250610 | 20250610004 | 4 | Seed Water | Can you please verify your calculations for the seed water quantity? The water quantity for each area seems excessive. | There is a calculation error for both the seed water and seeding rate. An addendum will be issued to update quantities. | Mike Coleman | 2 | 2025-05-21 14:11 | 2025-05-27 11:16
20250610 | 20250610006 | 6 | Signal Loops | At STH 50/Townhall Rd and STH 50/67 the plans show loops to be installed. The item for patching back in the loops depicts Asphalt Repair for the removal and replacement. Since the Asphalt Repair Item will be done after milling this item doesn't work in this application since the Asphalt Repair item is only 2" of removal and the loops need to be in prior to milling and paving. Please add items for either Base Patching Asphaltic and the associated removal item or Removing Asphaltic Surface with an associated patching item. | A full depth Asphalt Repair can be used. The special provisions will be revised to allow signal loop replacement any time prior to the paving operations. | Mike Coleman | 1 | 2025-05-20 09:21 | 2025-05-28 12:18
20250610 | 20250610006 | 6 | Curb Replacement | Per the detail on sheet 16, can the Department change the HMA patching in front of the curb to either an Asphaltic Surface or a concrete curb front fill item? This would eliminate testing/density requirements. | The Department wants an HMA mixture at the curb repairs. | Mike Coleman | 2 | 2025-05-20 12:33 | 2025-05-28 12:18
20250610 | 20250610006 | 6 | Curb and Gutter Detail | On page 24 of the plan, is this detail depicting guardrail posts being installed in the pan of the curb and gutter or is this simply a graphic problem? | The guard rail should be installed behind the curb and gutter per the plan details. The plan detail and construction detail will be revised by addendum. | Mike Coleman | 3 | 2025-05-21 14:36 | 2025-05-28 12:18
20250610 | 20250610006 | 6 | Gravity Retaining Wall Pay Limits | The pay limits shown on the lower left detail of page 15 show the pay limits for this wall will be from the finished grade at front face of wall up to the top of wall. This is non-standard for calculating modular block walls. Is this how the project intends to pay for this wall or using the bottom of wall elevation for the lower limit of the pay limits? | The Wall Modular Block Gravity Landscape construction detail will be revise to show the correct pay limits by addendum. | Mike Coleman | 4 | 2025-05-21 14:44 | 2025-05-28 12:19
20250610 | 20250610006 | 6 | SIGNALS | Should these signal housings be black face with yellow housings as per usual to match the yellow signal mounting hardware or should they be all black as in the specifications on page 24 of 42? Also are the backplates to have 2-inch yellow reflective tape? | The back plates are not called out as reflective on the plan, and the housing can be yellow. The special provisions will be revised to reflect this. | Mike Coleman | 5 | 2025-05-28 08:16 | 2025-06-03 07:52
20250610 | 20250610006 | 6 | Contaminated Soil | Is there a report that shows what was found in the contaminated areas? | The Phase 2.5 hazmat report can be found at the following location: https://wisdot.box.com/s/iuv8c1hy8znh1cb61of01ncmrtrne6mh or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 7 | 2025-05-30 12:04 | 2025-06-03 13:21
20250610 | 20250610006 | 6 | Hazardous Waste Manifest | Is there already a hazardous waste manifest that can be supplied? | Manifest tickets for hazardous material/contaminated soil will be provided during construction when the material is hauled to a landfill. HAZWOPER training is required for both excavation and dewatering and removal of contaminated water. This is included in article 20: Site workers taking part in activities that will result in the reasonable probability of exposure to safety and health hazards associated with hazardous materials shall have completed health and safety training that meets the Occupational Safety and Health Administration (OSHA) requirements for Hazardous Waste Operations and Emergency Response (HAZWOPER), as provided in 29 CFR 1910.120. | Mike Coleman | 8 | 2025-06-04 06:10 | 2025-06-04 11:47
20250610 | 20250610006 | 6 | 677.0200 Install Camera Assembly Qty 2 | 1.) Are the cameras temporary? 2.) Where will they be located? 3.) What is the Cat 5 or 6 distance from camera top of pole to cabinet? 4.) Contact name and number of who is supplying the IP and network connections? | 1. The cameras are supplied by the Department. The install item is in the temporary signal quantities. 2. ? It is up to the contractor to determine, but the max length of Cat 5 without a repeater is 100 meters. So, it is generally placed on the wood pole closest to the cabinet. 3. Depends on which wood pole the camera is mounted on. Generally, the closest wood pole, but within 333 feet. 4. The camera and cell modem will be programmed by the Department. | Mike Coleman | 9 | 2025-06-04 09:25 | 2025-06-05 06:12
20250610 | 20250610006 | 6 | Contaminated Soil Dewatering | In the special provisions, it states that dewatering is incidental to contaminated soil excavation item. Does WisDOT have soil boring information indicating if ground water will be encountered? If so, what is the WisDOT/WisDNR approved remediation of the contaminated ground water? How is the contractor to price the possible dewatering incidental work? | The Phase 2.5 hazmat report provides information on the soil and groundwater sampling and evaluation and can be found at the following location: https://wisdot.box.com/s/iuv8c1hy8znh1cb61of01ncmrtrne6mh or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 10 | 2025-06-05 09:58 | 2025-06-06 07:34
20250610 | 20250610006 | 6 | Dewatering Contaminated Soil - 2nd Question | The question about how to handle water from contaminated soil dewatering was not answered in WisDOTâ€™s response from the original question. Can the water be pumped into sanitary sewer? Does it have to be hauled off site with tanker trucks? Etc? These are all vastly different prices. WisDOT needs to provide scope/expectations so contractors can price out the incidental work. This has been provided before, specifically on ID #3831-08-71. Stating that dewatering of contaminated soil can be pumped into sanitary sewer with engineerâ€™s approval. |  |  | 11 | 2025-06-06 12:01
20250610 | 20250610007 | 7 | AC Requirements | Bid item 38 call out 5MT 58-28 S asphalt. Plan sheet #2 call out 5MT 58-28 V. Please verify which is correct. | The pavement is intended to be 5MT 58-28 V. An addendum will be issued to clarify. | Mike Coleman | 1 | 2025-05-19 09:02 | 2025-05-21 07:01
20250610 | 20250610007 | 7 | Barrier System Finishing | The MQ's don't have any anticipated items list for these grade shapes. Should we anticipate using No. 30 seed, fertilizer, and mulch as stated for other areas of the project or will the grade shape areas be using something different? |  |  | 2 | 2025-05-21 15:12
20250610 | 20250610007 | 7 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/opfl33rtiua4a7j6545yhp21pdt4pxpy or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2025-06-02 14:15 | 2025-06-03 13:15
20250610 | 20250610007 | 7 | AT&T Utility Relocation | When does AT&T expect to be complete with relocation and removal of the existing conduit package from the current structure? | Per the latest correspondence with AT&T Wisconsin, relocations are still on schedule. The full response from AT&Tâ€™s contact is â€œWe are still on schedule; theyâ€™ve been working on the copper splicing and I believe will be done either this week or early next which just leaves the fiber splicing. I planned on checking in with them mid next week to get a better estimate on timing.â€ | Mike Coleman | 4 | 2025-06-03 16:48 | 2025-06-04 13:03
20250610 | 20250610007 | 7 | Cold Weather Items | With the project finishing late in the construction season, will the department be adding cold weather pay items? (Asphalt, Pavement Marking, etcâ€¦) | There is sufficient time for the paving and marking to be completed, with the exception for marking on the bridge. Per the schedule that was shared, curing should be finished in late September or early October. We will include a cold weather marking quantity for the bridge only, the rest of the work should be completed prior to October 1. We will also update the P&P article to indicate this. One of the designers is updating the MQ sheet to add this quantity as well. | Mike Coleman | 5 | 2025-06-03 16:50 | 2025-06-04 13:03
20250610 | 20250610007 | 7 | SPV.0060.01 Fisheries Consultant | Where can the Broad Incidental Take Authorization be found? | The Broad Incidental Take Authorization for fish can be found at the following location: https://wisdot.box.com/s/opfl33rtiua4a7j6545yhp21pdt4pxpy or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 6 | 2025-06-04 17:46 | 2025-06-05 10:30
20250610 | 20250610009 | 9 | Paving Requirements | The prosecution and progress section of the special provisions indicate mill surfaces must be paved with 96 hours or by the end of each week. Does this paving schedule requirement apply the common excavation areas at each pipe location also? | The 96 hour requirement does not apply to areas excavated for culvert replacement while through traffic is detoured. Emergency services and local traffic will be allowed on the aggregate patches. | Mike Coleman | 1 | 2025-06-09 10:51 | 2025-06-09 12:28
20250610 | 20250610010 | 10 | Geotechnical Report | Please provide a copy of the geotechnical report. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/v4gghd339crily09rum6y94yp7pkuinw or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-05-19 14:57 | 2025-05-21 07:27
20250610 | 20250610010 | 10 | Project Access | What is going to be the route into the project area for building materials, base, drainage blanket and common excavation? Assuming through Outagamie county highway departments yard? | Yes, the route into the project area will be through the Outagamie County Highway Department yard via the entrance off Holland Road. A picture representing this can be found at the following location: https://wisdot.box.com/s/v4gghd339crily09rum6y94yp7pkuinw or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-05-28 15:21 | 2025-06-04 07:27
20250610 | 20250610010 | 10 | Salt Building Design | Are we able to bid an alternate structure that will hold the same capacity as the plan provided? | The salt storage building type has been coordinated and agreed upon with Outagamie County. An alternate structure type that holds the same capacity will not be acceptable. | Mike Coleman | 3 | 2025-05-30 14:44 | 2025-06-04 07:31
20250610 | 20250610010 | 10 | Salt Shed Coiling Door | Are we able to use a coiling door from Cornell Cookson (Cloplay) in lieu of the spec'd door for the salt shed? Can provide a BABA letter if necessary. | Door suppliers that can meet the requirements as presented in the specifications will be acceptable. Door submittals will be required during construction prior to approval of the overhead doors. | Mike Coleman | 4 | 2025-06-03 10:16 | 2025-06-05 06:22
20250610 | 20250610010 | 10 | Common Excavation | Are you paying common excavation for the grading required to make the pad for the bottom of the drainage layer? | Yes, the Stage 1 Common Excavation quantity includes the grading necessary to get to the bottom of the drainage layer. | Mike Coleman | 5 | 2025-06-03 11:07 | 2025-06-04 07:32
20250610 | 20250610010 | 10 | CAD Files | Can we get the CAD Files for this project? | The Contractor Data Packet can be found at the following location: https://wisdot.box.com/s/v4gghd339crily09rum6y94yp7pkuinw or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 6 | 2025-06-03 11:31 | 2025-06-04 07:43
20250610 | 20250610010 | 10 | Rebar for Building | Does the rebar need to be epoxy coated for the building? | No, rebar does not need to be epoxy coated. | Mike Coleman | 7 | 2025-06-04 08:55 | 2025-06-05 06:15
20250610 | 20250610010 | 10 | Schedule | Can you send out your anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/v4gghd339crily09rum6y94yp7pkuinw or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 8 | 2025-06-05 10:59 | 2025-06-05 14:03