## qandasearchletting_results
Date | 2026-05-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260512 | 20260512002 | 2 | Design Schedule | Can the Department provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/i2jnquxh6xrgi2qrferzrejbu7qc6ppz or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-04-20 09:30 | 2026-04-20 11:42
20260512 | 20260512002 | 2 | Geotechnical Report | Can the Department provide the Geotechnical Report for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/i2jnquxh6xrgi2qrferzrejbu7qc6ppz or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-04-20 09:35 | 2026-04-23 09:18
20260512 | 20260512002 | 2 | HFST | Would the Department consider having the HFST be completed in spring of 2027? The reason for the question is the HFST requires 30 day cure time after placement of the new HMA pavement and the HFST is centered on STH 59 (where traffic is detoured at stage lines). There is not enough time to get the pavement placed in Stage 1, maintain the detour, and meet the manufacturer's temperature requirements. | No, we would not extend time into 2027. The application of HFST would need to be applied using flagging during Stage 2 or paving the area of the treatment earlier in stage 1 to have the 30 days of cure time. | Mike Coleman | 3 | 2026-04-21 08:01 | 2026-04-27 07:00
20260512 | 20260512002 | 2 | Water Item | Can the water bid quantity be revised to not include the quantity of select crushed? | An addendum will be issued. | Mike Coleman | 4 | 2026-05-01 13:56 | 2026-05-05 07:41
20260512 | 20260512002 | 2 | Aggregate Conversion Rates | What is the conversion rate used for Base Aggregate Dense 1 1/4", Base Aggregate Dense 3", and Select Crushed? | Base Aggregate Dense 1 1/4": 2.0 TON/CY Base Aggregate Dense 3â€: 2.0 TON/CY Select Crushed: 1.8 TON/CY | Mike Coleman | 5 | 2026-05-07 09:10 | 2026-05-07 12:14
20260512 | 20260512002 | 2 | Fixed Message Sign Quantity | Can the Square Footage for the Fixed Message Sign item (643.1000) be updated? It's currently at 1 SF, which is incorrect according to the signs shown on the plan (p. 60, 63, etc.) |  |  | 6 | 2026-05-07 11:36
20260512 | 20260512002 | 2 | Traffic control/staging clarification | If excavation at Butts Corner is to start after excavation at Holt Rd is complete per pg 3 of the specials, is it the intent of the plans to have Butts Corner closed simultaneously during stage 1 closure? Please clarify the intent and what will be permitted in terms of closures. |  |  | 7 | 2026-05-08 10:48
20260512 | 20260512003 | 3 | Asbestos Inspection Reports for B-53-135 & B-53-154 | Can you please post the asbestos inspection reports for B-53-135 & B-53-154? | The asbestos reports can be found at the following location: https://wisdot.box.com/s/p6wsig3r2k3qxc6k2v2dgwwse17eq3zv or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-05-06 07:04 | 2026-05-06 07:36
20260512 | 20260512005 | 5 | Geotechnical Data | Please provide the geotechnical report for this project including bedrock core samples and compressive strengths. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-09 10:24 | 2026-04-14 12:46
20260512 | 20260512005 | 5 | Geotech | Can you please provide a geotechnical report with boring logs? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-04-10 11:58 | 2026-04-14 13:02
20260512 | 20260512005 | 5 | Geotech2 | Can you please provide a geotechnical baseline report for the tunnel work? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-04-10 11:58 | 2026-04-14 13:04
20260512 | 20260512005 | 5 | Microtunneling | Can you please provide your definition of Microtunneling? | Microtunneling is a trenchless construction method used to install underground pipelines with a remote controlled microtunnel boring machine (MTBM) that excavates the tunnel while pipes are simultaneously placed. The process can be operated entirely from the surface and does not require personnel to enter the tunnel, allowing for high precision and improved safety | Mike Coleman | 4 | 2026-04-10 11:59 | 2026-04-24 06:32
20260512 | 20260512005 | 5 | Microtunneling2 | Can you please clarify the intent of the Microtunneling 108â€ bid item? The bid item calls it microtunneling and the work throughout the documents describes it as microtunneling, but the spec is adversely written. It says that an EPB TBM shall be used. The spec then says things like â€œIf a slurry system is usedâ€¦â€, â€œIf a microtunneling system is to be usedâ€¦â€, and â€œIf a slurry TBM system is usedâ€¦â€ If your intent is for this to be microtunneled, your spec certainly does not read this way. | The intent of the bid item is for the pipe to be microtunneled or a similar trenchless method that is able to meet the specifications. | Mike Coleman | 5 | 2026-04-10 11:59 | 2026-04-23 07:23
20260512 | 20260512005 | 5 | Construction Data Pack | This contained 1 blank text file. Was another attachment intended? | This is a local program project. Construction Data Packets are not required for local program projects. | Mike Coleman | 6 | 2026-04-10 12:00 | 2026-04-14 13:09
20260512 | 20260512005 | 5 | Experience Requirements | The proposal document includes minimum experience requirements for the Project Superintendent (5 installations of 1,500â€™ at least 60â€) and TBM Operator (7 installations of 1,500â€™ at least 60â€). These qualifications are not part of the bid submittal we would like to know how the DOT plans to administer post-award. Will these requirements be strictly enforced as a condition of award or NTP? If the low bidder or its tunnel subcontractor does not meet these requirements exactly as written, will the DOT allow substitutions with comparable experience or require strict compliance? Will the DOT consider equivalent experience like similar diameter with shorter lengths or similar lengths with slightly smaller diameters subject to Engineer approval? The intent of the questions is to understand how the language will be applied because as written, they may significantly limit the pool of contractors. | An addendum will be issued to revise the bid item language to update the minimum experience requirements. The Wisconsin Department of Transportation will review and approve of these requirements as part of the NTP process and not condition of award. | Mike Coleman | 7 | 2026-04-10 13:37 | 2026-04-28 08:32
20260512 | 20260512005 | 5 | Precast Concrete Tunnel Segements | Would fiber reinforced precast tunnel segments built per the guidelines of ACI 533.5R-20 Guide for Precast Concrete Tunnel Segments and ACI 544.7R-16 Design and Construction of Fiber Reinforced Precast Concrete Tunnel Segments be considered an acceptable alternative to concrete pipe for the tunneled portion of this project? Concrete Tunnel Segments are a typical industry accepted final tunnel lining for larger diameter tunnels and can be a more cost effective approach than large diameter RCP. | An addendum will be issued to update the specification language to allow for Fiber Reinforced precast tunnel segments. | Mike Coleman | 8 | 2026-04-15 07:34 | 2026-04-28 08:34
20260512 | 20260512005 | 5 | Work Plans | Can you post the utility work plans? | The Work Plans can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 9 | 2026-04-15 07:54 | 2026-04-15 07:58
20260512 | 20260512005 | 5 | Rock Cores | Can photos of the rock cores provided in the geotechnical report be made available? | The rock core photos can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 10 | 2026-04-15 09:30 | 2026-04-16 10:51
20260512 | 20260512005 | 5 | Shoring | In addition to the contractor requesting to leaving shoring in place on S. High Point Road, will requests to leave shoring in other areas be accepted by the engineer? Will the engineer accept shoring to be left in place if removed five feet below grade? | An addendum will be issued to clarify the specification language regarding what shoring may remain in place. | Mike Coleman | 11 | 2026-04-20 15:46 | 2026-04-27 07:02
20260512 | 20260512005 | 5 | WISDOT Red Square | Wondering where the WISDOT red Squares are accounted for? They are not included in the 9.5 inch concrete pavement squares. | The details of the location of the red concrete are found within the plan details and Miscellaneous quantities portion of the plan set. | Mike Coleman | 12 | 2026-04-21 10:48 | 2026-04-28 08:27
20260512 | 20260512005 | 5 | RFI â€“ 110" Hobas FRPM Jacking Pipe Approval | Regarding Project No. 20260512005 (Mineral Point Road; USH 12 to High Point Road), the specifications require a minimum 108" ID for jacking pipe. Hobas's 110" FRPM jacking pipe has an ID of 106.9", slightly below the minimum; however, due to its smoother interior surface, it provides superior hydraulic performance to 108" RCP. RCP is designed with a Manning's n of 0.013, while Hobas FRPM pipe has a Manning's n of 0.009. At equivalent slope and flow conditions, a 108" RCP conveys approximately the same flow as a 94" FRPM pipe â€” meaning the 106.9" Hobas pipe far exceeds the hydraulic performance of 108" RCP. We believe this hydraulic equivalency justifies approval of the 110" Hobas FRPM jacking pipe and are happy to provide full supporting calculations for your review. | All material including pipe specified within the special provisions will be reviewed and approved by the engineer. | Mike Coleman | 13 | 2026-04-22 10:40 | 2026-05-04 06:44
20260512 | 20260512005 | 5 | Design Schedule | Can the Design Schedule be provided for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 14 | 2026-05-01 08:38 | 2026-05-05 07:34
20260512 | 20260512005 | 5 | Design Schedule | Can the WISDOT design Schedule be provided for this project? |  |  | 15 | 2026-05-01 12:08
20260512 | 20260512005 | 5 | Sign Post Materials | It doesn't appear that the precast sign post bases, the sign post bases for concrete installation, or the reflective sign posts are available as specified from any manufacturers. Would the project consider using square tube posts and v-loc bases for the signing on this project? |  |  | 16 | 2026-05-06 10:21
20260512 | 20260512007 | 7 | Formliner for parapets on Retaining Walls | We would like you to give us clarification of what you are looking for regarding the 2" Rectangular Cut Stone you have recommended for the parapet formliners. This would not be your official design choice. We will not hold anyone accountable. We just would like to give you and the community what they are expecting. Do you have any pictures of existing stone structures that might have the "look" you are trying to achieve? | The Village of Lake Delton would like to match the existing parapets for the US 12 bridge over Dell Creek (between N Delavan St and Hines Terrace) and the parapet along the NE side of US 12 adjacent to Fieldâ€™s at the Wilderness which is ~850-ft NE of the intersection with Hillman Rd. A photo showing the parapet can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-09 10:01 | 2026-04-17 09:25
20260512 | 20260512007 | 7 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-04-09 12:46 | 2026-04-17 09:15
20260512 | 20260512007 | 7 | Geotechnical Report | Can the Geotechnical Report be supplied? | The Geotech Reports can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-04-09 12:46 | 2026-04-20 07:41
20260512 | 20260512007 | 7 | design schedule | can WIDOT please provide the design schedule for this project | The design schedule can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2026-04-14 12:12 | 2026-04-17 09:16
20260512 | 20260512007 | 7 | Structure plans missing | Are there some structure plans missing? The quantities for the railing for each wall shown do not match proposal totals. | In addition to the R-numbered retaining walls in the structure plans section, there are landscape wall, concrete stair and concrete parapet details located within the Construction Details section that contain railings. | Mike Coleman | 5 | 2026-04-20 13:18 | 2026-04-23 09:19
20260512 | 20260512007 | 7 | Rebar quantity | The proposal quantity for coated rebar, Item 166 is 91,990 LB's. Adding up the walls that have an estimated quantity for rebar totals up to 77,400 LB's. Are quantities for the landscape walls included in the proposal total? It looks like this is incidental to the concrete slabs similar to coping. | The rebar quantities for all structures was quantified correctly. The additional rebar aside from the retaining walls is for the driveways as shown in the Construction Details on Pages 23 and 24 in the plans. | Mike Coleman | 6 | 2026-04-27 09:31 | 2026-04-29 07:28
20260512 | 20260512007 | 7 | VLD/CWD Imported Granular Backfill | The two SPV's for VLD/CWD imported granular backfill will follow Village of Lake Delton and City of Wisconsin Dell specifications. Can you provide the gradations of the backfill that will be required. | The Village of Lake Delton and City of Wisconsin Dells Specifications can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 7 | 2026-04-30 08:42 | 2026-05-06 07:11
20260512 | 20260512007 | 7 | sewer / watermain spec clarifications | VLD- Hydrants- are alpha ends required and what is the bury depth of each hydrant? Valves- are alpha ends required? T-Bolts- What is the spec? SS, Cor-blu or Black? Valve boxes- Which manufacturer? Tyler or B&T? MJ gaskets- Armor tipped or plain rubber? Sanitary connections- Are the Ferncos regular or strongback, or hard plastic couplings required? Brass- Which manufacturer? Mueller or AY McDonald? CWD- Hydrants- What is the bury depth? T-Bolts- What is the spec? SS, Cor-blu or Black? MJ gaskets- Armor tipped or plain rubber? Sanitary pipe- Please specify where SDR26 should be used- especially in deep bury. Brass- Which manufacturer? Mueller or AY McDonald? | The Village of Lake Delton and City of Wisconsin Dells Specifications can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 8 | 2026-05-01 11:57 | 2026-05-06 07:12
20260512 | 20260512007 | 7 | Storm Sewer Addendum Request | Several of the bidding contractors have asked if CL IIIB Storm Sewer per WisDOT Section 608 would be allowed in lieu of CL III RCP. Upon reviewing the plans there appears enough cover on a good percentage of the CL III Specified, to request consideration of an addendum for CL IIIB. |  |  | 9 | 2026-05-02 06:48
20260512 | 20260512007 | 7 | Geotech Info for R-56-37 | Can you post the geotechnical information for added retaining wall R-56-37? |  |  | 10 | 2026-05-06 07:01
20260512 | 20260512007 | 7 | Aggregate Conversion Rate | What is the conversion rate used for Base Aggregate Dense 1 1/4"? | The conversion rate for Base Aggregate Dense 1 ï¿½â€ is 2.0. | Mike Coleman | 11 | 2026-05-06 11:16 | 2026-05-07 14:09
20260512 | 20260512007 | 7 | 513.2001 Railing Pipe | Are there some details for the Railing Pipe, Item 0170 | Details for railing pipe can be found on page 29 of the 6145-01-72/73/74 plans. | Mike Coleman | 12 | 2026-05-06 15:54 | 2026-05-07 14:09
20260512 | 20260512007 | 7 | Storm Sewer Video | Please advise if a video link is available for the storm sewer segments scheduled for CIPP. |  |  | 13 | 2026-05-08 10:57
20260512 | 20260512009 | 9 | Geotechnical Report | Can the Department provide the Geotechnical Report for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/etwufbo6oconxg4q5q8823nr76rn8mty or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-21 11:21 | 2026-04-22 06:21
20260512 | 20260512009 | 9 | Clearing Item | What is the reason for item # 2 Clearing of 6.8 acres? It looks like all the trees have been cut down? Are all the felled trees going to be removed prior to construction? If all the felled trees are to be cleaned up and removed under this contract that should be stated in the bid documents. | Trees will not be removed prior to construction. All trees are to be removed or buried a minimum of 1 foot below finished grade. This is stated in Note #4 of the General Notes and is the intent of the clearing bid item. | Mike Coleman | 2 | 2026-04-22 14:48 | 2026-04-24 06:33
20260512 | 20260512009 | 9 | Geo Technical Report | Can the full geotechnical report be provided showing each of the boring logs information? | The remaining geotechnical information can be found at the following location: https://wisdot.box.com/s/etwufbo6oconxg4q5q8823nr76rn8mty or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-04-28 11:10 | 2026-04-29 12:35
20260512 | 20260512009 | 9 | Kressin Branch | This question would be mainly for the east site. Will contractors be allowed to install a temp culvert to cross Kressin Branch to get fill materials from south cut area to the north fill area? (lateral 3 & 2) | Contractors will not be allowed to install a temporary culvert to cross Kressin Branch. Access to the north side of Kressin Branch, east of Division Rd, will be provided through the TLE on the south side of Pioneer Rd. | Mike Coleman | 4 | 2026-04-28 14:36 | 2026-05-01 07:30
20260512 | 20260512009 | 9 | 2026 Vegetation Management Plan | Will the site be treated with herbicides in 2026 prior to construction? If so, how many applications, timing, and what type of herbicide will be used? |  |  | 5 | 2026-05-07 14:24
20260512 | 20260512009 | 9 | Past Vegetation Management | What types of herbicides were used in 2025 and when were they last applied? |  |  | 6 | 2026-05-07 14:25
20260512 | 20260512009 | 9 | Seeding Timing vs Contract Sunset | The RFB states that all work must be completed by Oct. 20 and the seeding window doesn't start until Oct. 15. Will the contract be extended to allow seeding to occur after Oct. 20, assuming conditions for seeding may be best in winter months? |  |  | 7 | 2026-05-07 14:26
20260512 | 20260512009 | 9 | Terminating Cover Crop | Depending on the timing for completion of grading and temporary seeding activities, would it be acceptable to conduct an herbicide application in the graded areas at the end of the growing season, as needed, to terminate the cover crop and weedy vegetation expressed from seed bank? In general, can herbicides be used for site preparation if not already planned to be conducted by WisDOT in 2026, prior to the acceptable seeding window. |  |  | 8 | 2026-05-07 14:29
20260512 | 20260512011 | 11 | Prosecution and Progress Specs | Special Provisions 3. Prosecution and Progress states, "Do not begin work on IH 41 and US 45 before May 22, 2027.". Is this just referring to structure B-70-269? The next line in Prosecution and Progress references several structure ramps leading to/from IH 41 that need to be completed between July 6, 2026 and September 30, 2026. Are these dates accurate, or is the 2026 intended to say 2027? | Correct, "Do not begin work on IH 41 and US 45 before May 22, 2027." only refers to structure B-70-0269. The next line is accurate as well, requiring structures B-05-0679, B-05-0678, B-05-0671 and B-06-660 to be completed between July 6, 2026 and September 30, 2026. Only structures B-05-0658 and B-05-0661 do not have requirements to construct specifically in 2026 or 2027. | Mike Coleman | 1 | 2026-04-15 12:30 | 2026-04-16 10:53
20260512 | 20260512011 | 11 | 646.9000 Marking Removal Line 4-Inch | Please review the pavement marking removals. Removals shown on plan sheets 6-8 are 8-In Grooved Contrast Tape. Sheet 9 is 4-In Grooved Contrast Tape. Sheets 14 and 17 are a combination of 4 and 8-IN GCWR Tape. Please provide updated quantities and bid items (646.9055 and 646.9155) | An addendum will be issued to address the question. | Mike Coleman | 2 | 2026-05-05 15:15 | 2026-05-07 06:48
20260512 | 20260512011 | 11 | Cleaning Decks/Removing Polymer Overlay Bid Items | Please clarify the difference between the two bid items. Under cleaning decks it states to remove 3/4" and under Removing Polymer Overlay Bid Item it states to remove the existing overlay and do not remove more than 1/4" of the existing concrete surface. Is one bid item to remove any excess that might remain? |  |  | 3 | 2026-05-08 13:18
20260512 | 20260512012 | 12 | Line 0038 644.1810 Temporary Pedestrian Barricade Quantity Clarification | Line 0038 644.1810 Temporary Pedestrian Barricade shows 2,238 LF. Misc quantities shows that is 2,238 DY. Based on the quantities it should be 204 LF. Which unit of measurement should this Item be? | An addendum will be issued to revise the quantity and clarify the unit of measurement for item 644.1810 Temporary Pedestrian Barricade. | Mike Coleman | 1 | 2026-05-04 10:54 | 2026-05-06 07:13
20260512 | 20260512012 | 12 | Bascule Leaves Balancing | Will Span 4 (Bascule Span) require preliminary/post balance testing? | An addendum will be issued to require balancing bascule bridge leaves. | Mike Coleman | 2 | 2026-05-06 19:58 | 2026-05-08 11:37
20260512 | 20260512012 | 12 | Existing Bridge Plans | Are the existing bridge plans available for this structure? They are not on the HSIS site. |  |  | 3 | 2026-05-08 15:05
20260512 | 20260512013 | 13 | Soil borings | Are the soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/qnikt99ddz78hm6emgjwro64fdhdzrg6 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-27 09:37 | 2026-04-29 07:26
20260512 | 20260512015 | 15 | Lower Layer Mix Type | The plan typical sections show the lower layer as 1.75 inches of 5MT. Would the department consider changing the lower layer mix type to a 4MT? This would match the typical section of the previously bid section of Hwy 63 1550-04-77 | An addendum will be issued. | Mike Coleman | 1 | 2026-04-21 08:10 | 2026-04-28 08:31
20260512 | 20260512015 | 15 | Design Schedule | Can you provide the design project schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/12utb51rk9zl9s3nunc9bauf61xug8ye or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-04-21 08:55 | 2026-04-22 06:19
20260512 | 20260512015 | 15 | Bird Deterrent System | Can you confirm that the bird deterrent system installed by the county is functional, and the if the intent of this project scope is to only maintain the system? | I can confirm that the county did the netting and it is installed pretty well per discussion with Nick Schaff. | Mike Coleman | 3 | 2026-04-21 08:58 | 2026-04-22 06:11
20260512 | 20260512015 | 15 | Clearing and Grubbing | Looking like the clearing and grubbing near STA 92 might require some trees to be removed. With clearing exclusion dates of April 15th though October 31st, and this project bidding in the May letting. This project may require special consideration on clearing, if the trees have not already been removed by the county. Would that be possible on this project? | November 1 is the start of the clearing and subsequent work in that area in order to avoid the bat dates. We were anticipating the contractor doing everything they could in the area except the final bit of grading in the ditch near the driveway/culvert where the clearing needs to take place. We anticipated the contractor clearing the two large trees Nov 1, then performing the remaining work in the area prior to Nov 13 completion date. | Mike Coleman | 4 | 2026-04-21 09:22 | 2026-04-23 08:52
20260512 | 20260512015 | 15 | Culvert pipe - liners | Are the culvert sizes listed in the SOI / misc quantities the existing culvert pipe i.d. or the required new liner size? Also, what is the existing culvert material for each pipe? | Culvert sizes listed in the miscellaneous quantities are the existing culvert pipe inside diameters. All existing culvert pipes that require liners are reinforced concrete. This can be verified, as all existing culvert pipes lengths and material types are shown on the plan sheets. | Mike Coleman | 5 | 2026-04-23 07:34 | 2026-04-23 10:40
20260512 | 20260512015 | 15 | Culvert Liners | When using a Manning's coefficient of 0.013 for concrete pipe none of the culvert liner products on the departments APL meet the flow capacity given in the SPV. Can either the coefficient or flow capacity requirements be changed? |  |  | 6 | 2026-05-07 05:29
20260512 | 20260512016 | 16 | Diversion Pipe breakdown | Do you have a breakdown of the 36" diversion pipe? Looks like an elbow is needed and there is a manhole as well. Need to know these locations in the run to provide proper lengths and band qty's. Thank you!! | On page 13 of the plan (Construction Phasing and Dewatering â€“ Phase 1 & 2 â€“ Drawing C02) the detail shows the angle of the 3 bends required in the 36â€ pipe. One is a 45 degree and the other two are 22.5 degree. There are also N & E coordinates given at each angle point as well as the manhole to be able to locate these horizontally. There are also individual pipe lengths shown on the detail between angle points or between structures. | Mike Coleman | 1 | 2026-04-29 13:42 | 2026-05-01 07:31
20260512 | 20260512016 | 16 | Elbow Degree | Could i get the elbow degree on the 36" diversion as well as the location of it and the manhole in the run. Thank you! | On page 13 of the plan (Construction Phasing and Dewatering â€“ Phase 1 & 2 â€“ Drawing C02) the detail shows the angle of the 3 bends required in the 36â€ pipe. One is a 45 degree and the other two are 22.5 degree. There are also N & E coordinates given at each angle point as well as the manhole to be able to locate these horizontally. | Mike Coleman | 2 | 2026-04-29 14:22 | 2026-05-01 07:31
20260512 | 20260512016 | 16 | Driveway Assistance Device Bid Item | The Traffic Control Plan calls for a Driveway Assistance Device but I do not see a bid item shown for it. Would you please check on this | The Driveway Assistance Device is shown in the plans on page 29 (Estimate of Quantities), item â€œSPV.0060 Special 10. Driveway Assistance Deviceâ€. It also is called out on the Miscellaneous Quantity sheets page 33. In the Special Provisions, it is shown on page 16 of 19, special #27. | Mike Coleman | 3 | 2026-05-03 12:32 | 2026-05-05 07:35
20260512 | 20260512016 | 16 | Lower Cofferdam | Due to the size and location of the lower cofferdam shown in the plans, may the contractor construct a temporary rock causeway to facilitate installation of the cofferdam and access for construction operations? | We do not see any issue with what you are proposing. This would be a contractor means and methods issue. As long as the causeway stays within the permitted impact area this should be fine. | Mike Coleman | 4 | 2026-05-07 16:01 | 2026-05-08 11:36
20260512 | 20260512016 | 16 | Contractor-Furnished Permits | The special provisions state that the contractor is responsible for obtaining DNR permits for both the cofferdams and dewatering. Given this job bids in May, a potential contract award would not be received until June. With the stream realignment interim completion date being 10/1/26, it seems unrealistic that permits will be in hand for the cofferdam installation to take place in June/July. Special provisions indicate a review period of 30-90 days for DNR permits. With the restricted drawdown rate (4" per day) along with the review period for DNR permitting, it seems highly unlikely that the stream realignment work can be completed by 10/1/26. Please confirm this is constructable with all of these things considered. |  |  | 5 | 2026-05-07 16:15
20260512 | 20260512016 | 16 | Access - Cofferdam Installation | Will temporary access (causeway) be permitted to facilitate the installation of the upper and lower cofferdams? Cofferdams as shown in the plans are too far to reach with excavators/ cranes. Additionally, USH 63 can only be shutdown for 7 calendar days which is insufficient time to complete the installation of cofferdams and supporting work. |  |  | 6 | 2026-05-08 14:48
20260512 | 20260512017 | 17 | Geotech Report for B-27-183 | Could the getoech report for bridge B-27-183 please be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/evxzdtcm1it83p0qs6izt5dvxm4ganv4 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-24 14:57 | 2026-05-06 07:38
20260512 | 20260512021 | 21 | Project Timeline | Does all of the Armor Stone and associated work below OHWM need to be complete by September 15, 2026? | Yes, there is no instream disturbance of Lake Superior from Sep. 15 to July 1. All work in the water will need to be completed by Sep. 15, unless a waiver is granted by the Wisconsin DNR. | Mike Coleman | 1 | 2026-04-30 09:05 | 2026-05-05 07:37
20260512 | 20260512023 | 23 | 506.0105 Structural Steel Carbon | The plans and structure quantity table show an item for 506.0105 Structural Steel Carbon, however no such item is included in the contract bid items. Please clarify. | Bid item 506.0105 Structural Carbon Steel will be added to the contract by addendum. | Mike Coleman | 1 | 2026-04-29 11:00 | 2026-04-30 07:22
20260512 | 20260512024 | 24 | Marking Removal Line Water Blasting | Where will the three marking removal line water blasting items be used. The removal items match the permanent marking quantities for Project 2290-24-71, but I do not understand what needs to be removed. | Two of the three water blasting removal items will be removed from the project via an addendum. An item for temporary centerline pavement marking paint will be added to the project with the same addendum. | Mike Coleman | 1 | 2026-04-28 10:18 | 2026-05-05 07:41
20260512 | 20260512024 | 24 | Design Schedule | Please provide the design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/gilysyc9z6hzbe9g0ri9lpndyyymzip2 or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-05-01 18:04 | 2026-05-05 07:40
20260512 | 20260512024 | 24 | Soils Report. | Please provide the soils report | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/gilysyc9z6hzbe9g0ri9lpndyyymzip2 or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-05-06 05:42 | 2026-05-07 06:45