## qandasearchletting_results
Date | 2026-06-26
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260714 | 20260714002 | 2 | Geotechnical Report | Can the geotechnical information be provided for this project? | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/cc2sfsb132vxh7mxzujvpk68pp1syi4e or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-06-12 10:16 | 2026-06-16 07:07
20260714 | 20260714002 | 2 | Design Schedule | Can the design schedule for this project be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/cc2sfsb132vxh7mxzujvpk68pp1syi4e or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-06-12 10:16 | 2026-06-16 07:15
20260714 | 20260714002 | 2 | Design Schedule | Please provide the design schedule. |  |  | 5 | 2026-06-15 06:30
20260714 | 20260714002 | 2 | Existing Dam Structure Plans | Can existing structure plans for the adjacent dam please be provided? | The existing structure plans can be found at the following location: https://wisdot.box.com/s/cc2sfsb132vxh7mxzujvpk68pp1syi4e or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 6 | 2026-06-16 08:24 | 2026-06-17 06:25
20260714 | 20260714002 | 2 | B-13-907 Pile Driving and Dunn Sanitary Sewer Cofferdams and Pile Pipe Supports | How are these operations to be completed when contract documents require hydraulic press installation for the Cofferdam on B-13-907 and Permanent Steel Sheet Piling? | The methodology for driving piles for B-13-907 is specified as requiring hydraulic press installation for the cofferdam and sheet pile walls. The H-piles can be driven using traditional installation methods. The method for installing the Dunn Sanitary Sewer Cofferdams and pile pipe supports can be done by traditional pile driving methods as required in the standard specifications but with a slight modification on the equipment that can be used. We will work on an addendum to clarify. | Mike Coleman | 7 | 2026-06-17 12:34 | 2026-06-24 08:36
20260714 | 20260714002 | 2 | Permanent Steel Sheet Piling Delivered Bid Quantity | Some hydraulic presses require a certain amount of steel sheet piling to be embedded in the ground for stability and use for force to apply to the next sheet being driven. Since the use of hydraulic press is being dictated by the department, does the quantity in the delivered SF bid quantity account for footage needed for the actual sheeting installation process or just final design required? Will the department pay for the extra sheeting necessary as the department is dictating the installation procedure to be utilized? | The quantity is for the final design required. Any additional sheeting needed for hydraulic press-in system process should be included or incidental to the item Piling Steel Sheet Permanent Installed. | Mike Coleman | 8 | 2026-06-17 12:46 | 2026-06-24 08:35
20260714 | 20260714002 | 2 | Sheeting and Cofferdam Pile Press Obstructions | How will obstructions and downtime be compensated for if obstructions are encountered during pile press installation operations? Borings show cobles and boulders present. |  |  | 9 | 2026-06-22 10:46
20260714 | 20260714002 | 2 | Dunn Sanitary Sewer Cofferdam | The cofferdam plan provided does not appear to allow for excavating and dewatering given the cut and soil conditions. If the intent is for the cofferdam to allow dewatering, please provide calculations for the designed cofferdam in the plans. |  |  | 10 | 2026-06-22 10:56
20260714 | 20260714002 | 2 | Form liner for MSE walls - R-13-379 and R-13-9382 | Sheet 945 of the contract drawings show a liner with 9" coursing. For MSE walls with staggered panels joints and standard panel height of 60" as approved by Wisconsin DOT, 9" courses will not work. Courses needs to be 7.5", 15" or 30" so that the panel joints will match with courses. Otherwise, you will end with one unique liner for each panel. Please change coursing of the liner to 7.5" or 15" |  |  | 11 | 2026-06-23 11:53
20260714 | 20260714002 | 2 | Quantities Polymer Overlay | The proposal has a total of 2101 sy of Polymer Overlays, but I'm only finding the one bridge B-13-907 with a quantity of 731 sy. Are there other bridges not added to the plan or is the proposal quantity incorrect? |  |  | 12 | 2026-06-25 16:27
20260714 | 20260714003 | 3 | Existing Asphalt Pavement | Consider changing note 2 in excavation summary stating "pavement material is expected to be used as fill" to salvaged / unusable pavement material, which is more typically seen. Explanation for changing this as stated below. 1. This is be the most economical option to reuse the existing pavement for recycled 1 1/4" base aggregate. The borrow quantity would increase to offset the pavement quantity but still be cheapest option for the taxpayer. 2. Per the cross section takeoff there are very little to no areas that could even take any of the existing asphalt chunks and be below 2' of finished grade or subgrade per the standard spec. | After discussion, WisDOT has been decided that an addendum will be issued to address this. | Mike Coleman | 1 | 2026-06-12 09:36 | 2026-06-24 08:38
20260714 | 20260714003 | 3 | Geotechnical Report | Can the geotechnical information for this project be provided? | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/9dzyalorrzygr29qhwvvchhdpvnum6jl or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-06-12 10:17 | 2026-06-17 08:59
20260714 | 20260714003 | 3 | Design Schedule | Can the design schedule for this project be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/9dzyalorrzygr29qhwvvchhdpvnum6jl or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2026-06-12 10:18 | 2026-06-17 09:02
20260714 | 20260714003 | 3 | Railroad | What are the rates to be used if railroad flagging is needed or is DOT going to add a railroad flagging reimbursement item? | Flagging for this project should be minimal and will be considered incidental and will not be reimbursed. Current flagging rates as provided by Union Pacific railroad are as followsâ€¦ $1,200 daily rate for an eight-hour day (including wages, labor surcharges, lodging, vehicle and mileage expenses), - $1,550 "Rest Time" or nightly rate for weekday overnight work for an eight-hour day (including wages, labor surcharges, lodging, vehicle and mileage expenses) - $1,500 daily rate for an eight-hour day on Saturdays, Sundays, or holidays (including wages, labor surcharges, lodging, vehicle and mileage expenses) - $1,550 "Rest Time" or nightly rate for weekend overnight work for an eight-hour day (including wages, labor surcharges, lodging, vehicle and mileage expenses) - $175 per hour overtime rate for all time worked before or after the regular assigned eight hours on any day, or for a minimum three hour call on Saturdays, Sundays, or Holidays. The railroad or its third-party flagging contractor www.up.com/flagging will require pre-payment and a minimum 40-day notice. The flagger is required to set flags each day in advance of the contractor commencing work that will require flagging. The flagger must also remove the flags each day after the completion of work that required flagging. Any time worked before or after the minimum eight-hour flagging day to set or remove flags will be billed at the overtime rate. The contractor is responsible for knowing the requirements of the railroad for arranging and terminating flagging services and for the associated costs of those services. For a more accurate flagging rate, contractor should contact Union Pacific RR. | Mike Coleman | 4 | 2026-06-12 15:38 | 2026-06-16 10:45
20260714 | 20260714003 | 3 | Tree Clearing | Please confirm that there are NO specific dates for tree clearing and that tree clearing can occur anytime. | Correct, there are no specific dates when trees can be cleared. They can be cleared at any time. | Mike Coleman | 5 | 2026-06-15 17:23 | 2026-06-17 06:30
20260714 | 20260714003 | 3 | Start Date | Please confirm that DOT expects this project to be constructed in the 2027 construction season. | Correct, we expect construction to occur in the 2027 construction season. | Mike Coleman | 6 | 2026-06-15 17:26 | 2026-06-17 06:31
20260714 | 20260714004 | 4 | Design Schedule. | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/iv46n8q2vngdd0pg28y1rs9qpxg8x6p4 or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-06-10 20:30 | 2026-06-15 08:00
20260714 | 20260714004 | 4 | Geotechnical Report | Can the geotechnical report for the bridge and the 4 retaining walls be provided? | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/iv46n8q2vngdd0pg28y1rs9qpxg8x6p4 or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-06-11 15:22 | 2026-06-15 11:39
20260714 | 20260714004 | 4 | Existing Embankment Removal | Both MSE walls include the note: "Removal of substandard existing embankment as directed by the engineer. Payment shall be included in the bid item "Wall Concrete..."". What constitutes substandard embankment? Is there a maximum depth that the Engineer would remove? Please clarify what material shall be placed back after removal, and to what elevation. | Removal of existing embankment is required for installation of proposed load transfer pad. Expected removal of the undocumented existing fill/possible fill, layers of possible buried topsoil and lower strength soils, which extends to approximate depths from 7.6 feet bgs (RW-1and RW-2) to 10 bgs (RW-3). See Geotechnical Exploration and Engineering Report STH 100/N. Mayfair Road Bridges over Menomonee River Structures R-40-729 & R-40-730 Wauwatosa, Milwaukee County, Wisconsin WisDOT Project ID 2030-10-71,Section 4.1 | Mike Coleman | 3 | 2026-06-11 15:43 | 2026-06-15 12:42
20260714 | 20260714004 | 4 | Extent of Ground Improvement | Please clarify the horizontal extent of ground improvement. Plans seem to indicate only under the MSE walls and backfill, the special provision requires to limit settlement "under the wall and embankment". | R-40-729 and R-40-730 indicate â€œGROUND IMPROVEMENT SYSTEM CONSISTING OF RAMMED AGGREGATE PIERS OR STONE COLUMNS REQUIRED AS DETAILED IN SPECIAL PROVISIONS. PIERS/COLUMNS TO EXTEND A MINIMUM OF 1 PIER/COLUMN DIAMETER IN FRONT OF THE WALL. WORK TO BE INCLUDED IN THE BID ITEM "GROUND IMPROVEMENT SYSTEM R-40-7XX". â€“ this provides guidance for the minimum horizontal limit in front of the wall. Per the Special Provision language, the bid item GROUND IMPROVEMENT SYSTEM â€œdescribes designing, installing and testing ground improvement using either stone columns or rammed aggregate piers (RAP) to the lines and grades designated on the project drawingsâ€. | Mike Coleman | 4 | 2026-06-11 15:46 | 2026-06-15 12:43
20260714 | 20260714004 | 4 | Bid Item 0166 Structural Steel HS - Soldier Piles for Retaining Walls R-40-731 & 732 Fabricators | Do the fabricators for the soldier piles need to be from the approved products list for steel? If so, which category? Fabricated bridge components or Primary steel members? | The R-40-731 & 732 Structural Steel HS soldier pile posts are considered primary members. The welding requirements are covered by standard specification 506. If any welding or fabrication is required for the soldier pile posts, work must be performed by an approved fabricator selected from the APL for Steel Bridge Primary Members (Approved Product 1) or the APL lists for Fabricated Bridge Components. | Mike Coleman | 5 | 2026-06-15 10:11 | 2026-06-24 09:23
20260714 | 20260714004 | 4 | Follow-Up to Question 4 - Extent of Ground Improvement | Should the improvement area include underneath the roadway embankment behind and between the soil reinforcement area of each MSE wall? There will be roughly 100 feet of retained soil between the 2 MSE walls, does this area require ground improvement or is it just underneath the two walls? | SPV.0060 Ground Improvement System is not required between the MSE reinforcement area of the walls. | Mike Coleman | 6 | 2026-06-15 16:30 | 2026-06-24 08:33
20260714 | 20260714004 | 4 | Follow-Up to Question 3 - Existing Embankment Removal | Section 4.1 of the geotech report outlines removal and replacement of existing fill/possible fill/buried topsoil as one option, the other option being ground improvement. If ground improvement is the method chosen, removal of 7.6-10 feet of embankment should not be required. Please clarify the response to Question #3 and include details if the department will be directing removal, what to be backfilled with, and to what elevation. | The design intent is to include the ground improvement system below the proposed MSE walls. The plan note on R-40-729/730 sheet 3 stating â€œRemoval of substandard existing embankment as directed by the engineer. Payment shall be included in the bid item â€œwall concrete mechanically stabilized earth R-40-7XXâ€ does not apply to the design intent using the ground improvement system. | Mike Coleman | 7 | 2026-06-15 16:39 | 2026-06-24 08:33
20260714 | 20260714004 | 4 | Geotech Report - Sign Structures | Is there a geotechnical report that can be made available for the sign structure bases? Signs 3106 and 3107 |  |  | 8 | 2026-06-19 14:12
20260714 | 20260714004 | 4 | Sawing Quanity | Based on the cubic yards of Base Patching, it seems like either the sawing is understated or the Base Patching is overstated. Can this be reviewed and corrected? |  |  | 9 | 2026-06-22 07:49
20260714 | 20260714004 | 4 | SHES and stardard Base Patching. | Will the patches be performed through the existing asphalt? If they are to be performed both through the existing asphalt and after milling, can the locations for the different approaches be clarified? |  |  | 10 | 2026-06-22 07:51
20260714 | 20260714004 | 4 | Soils Reports. | Can the soils report for the locations other than the structures also be provided? |  |  | 11 | 2026-06-22 07:51
20260714 | 20260714004 | 4 | Milwaukee County Parks Right-of-Entry Permit | Is the department able to provide/post the draft Milwaukee County Parks Right-of-Entry permit, discussed in special provision #17, within the supplemental QA documents? |  |  | 12 | 2026-06-25 13:28
20260714 | 20260714004 | 4 | Structure Removal | Will existing structures not in conflict with the proposed structure be allowed to remain if they are at or below stream bed within water or a minimum of 2ft below finished grade not in water? |  |  | 13 | 2026-06-25 13:42
20260714 | 20260714005 | 5 | Schedule | Please provide the designer's construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/v/20260714005folder or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-06-10 17:39 | 2026-06-15 12:16
20260714 | 20260714005 | 5 | Geotech Reports | Please provide geotech reports for this proposal. | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/v/20260714005folder or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-06-10 17:41 | 2026-06-15 11:41
20260714 | 20260714005 | 5 | Temporary Ingress/Egress Access Costs | SPV article 3.3 states work zone access request is to include the cost of proposed temporary access including grading, traffic control, erosion control, and all other items and incidentals to implement and remove the access. The general notes on sheet 3 of the plan state temporary contractor access road costs are incidental to the project. Please clarify. | Access points (ingress/egress), shown in the plan, have quantities including in the plan to implement. In Article 3.3, access points, not shown in the plan, require approval and costs are incidental to the project. The General Note on page 3 of the plan refers to the proposed permanent access roads, which are future maintenance roads for the flyover ramps. The permanent access roads cannot be built until the final stages because they are not designed for construction traffic. Also, any temporary access roads within the project site are incidental to the project. | Mike Coleman | 3 | 2026-06-10 17:47 | 2026-06-17 14:23
20260714 | 20260714005 | 5 | Temporary Ingress/Egress Access Ramp Requirements | Provided the scope of this project is an interchange, several temporary construction access ingress/egress locations will be in the vicinity of ramps. On previous IH-41 corridor projects, approval of temporary construction access ingress/egress locations in the vicinity of ramps has been limited. Several stages of the traffic control plans include trucks leaving/entering signage anticipating temporary construction access ingress/egress locations. Are there time of day restrictions on when these ingress/egress locations can be used? What are the limitations on new temporary construction access ingress/egress locations in the vicinity of ramps? | Several anticipated construction access points are shown in the plan set. Each access point not shown in the plan will be evaluated and approved as a case-by-case basis per the special provisions. Access points anticipated on the two high-speed ramps (WS, SE) are ingress points, except for a couple stages. The slower speeds on the loop ramps as well as a closed lanes were utilized for both ingress & egress points in several stages. If additional access points are needed, the contractor must follow the access request process as stated in the special provisions. Access restrictions are described in the special provisions. | Mike Coleman | 4 | 2026-06-10 17:57 | 2026-06-17 12:08
20260714 | 20260714005 | 5 | Geotechical Reprt | Please provide a copy of the complete geotechnical report. | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/v/20260714005folder or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 5 | 2026-06-11 06:17 | 2026-06-15 12:40
20260714 | 20260714005 | 5 | Design Schedule | Please provide a copy of the design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/v/20260714005folder or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2026-06-11 06:18 | 2026-06-15 12:30
20260714 | 20260714005 | 5 | Earthwork | Please confirm the volumes of Excavation, Hauling, and Reuse of Low-Level Contaminated Material, LFCF, and MSE backfill have been deducted from the Excavation Common and Roadway Embankment quantities. | The Low-Level Contaminated Material has not been deducted from the Excavation Common and Roadway Embankment quantities. The LFCF and MSE back fill have been deducted from the Excavation Common and Roadway Embankment quantities. The Low-Level Contaminated Material will be deducted from the Excavation Common and Roadway Embankment quantities in an upcoming addendum. | Mike Coleman | 7 | 2026-06-11 08:18 | 2026-06-17 12:07
20260714 | 20260714005 | 5 | Temporary Shoring | 1,050 SF for item 511.1100-Temporary Shoring is included in the miscellaneous quantities and is noted for B-44-326. The B-44-326 structure plan does not detail temporary shoring or include quantity for it. What/where is the 1,050 SF of temporary shoring for? | Temporary Shoring quantity will be removed in upcoming addendum | Mike Coleman | 8 | 2026-06-11 10:38 | 2026-06-16 07:18
20260714 | 20260714005 | 5 | Excavation, Hauling, and Reuse of Low-Level Contaminated Material, | Section A.1 states "excavating, hauling, and reusing fly ash within the project limits or at a WDNR approved off site location" Section A.3 states "shall be reused as fill at the following locations meeting placement criteria of NR 538.12, and as shown on plans" then proceeds to state "that cannot be reused in the specified reuse locations must be hauled off-site and disposed of according to Section C below". The provided fill volumes in Section A.3 match the proposed bid quantity. Section A.4 states "designed to minimize the off-site disposal of impacted material" Section C states "If the environmental consultant determines the material can be beneficially re-used on-site" The overall SPV indicates using material onsite and disposing of it offsite. Will it all remain onsite or will it need to hauled offsite? If material is will need to be hauled offsite, a separate bid item should be added for this portion. Will the clay liner excavation be paid as Common or under this item? | Based on the estimated quantity of fly ash present it is anticipated all material will remain on site. Clay liner excavation will be paid with the Excavation Common bid item. | Mike Coleman | 9 | 2026-06-12 06:49 | 2026-06-17 14:24
20260714 | 20260714005 | 5 | Concrete for Concrete Masonry Bridges Special & Piling CIP Concrete 14x0.50-Inch Special | The special provision articles for these items requires Portland cement to be limited to Type IP, Type IS or Type IT to provide moderate sulfate resistance. Supplying these cements for concrete will be costly. Please consider allowing type IL cement that is blended with supplementary cementitious material(s) to meet the requirements for Moderate Sulfate resistance (MS) under ASTM C1012 performance tests. | The possible use of Type IL Cement is under review. If Type IL Cement is allowed, contractors will be notified through an addendum. | Mike Coleman | 10 | 2026-06-12 15:07 | 2026-06-17 14:26
20260714 | 20260714005 | 5 | Conversion Rates | Please clarify the conversions rates utilized for base aggregate and select crushed. | The conversion rate used for aggregates and select crushed are as follows. BAD ï¿½â€: 2.1 Ton/CY BAD 1 ï¿½â€: 2.0 Ton/CY Select Crushed: 1.9 Ton/CY These values are based on Table 10.4 of FDM 14-15. | Mike Coleman | 11 | 2026-06-15 08:34 | 2026-06-16 10:52
20260714 | 20260714005 | 5 | EBS | Please clarify the location and stage for the anticipated EBS. A lump sum total only is provided for each earthwork table. In addition, the earthwork tables provided in the construction data packets provide calculations for EBS that are not shown in the cross sections. How are these being calculated if they are not shown in the cross sections? Please review the EBS in the median of IH 41NB/SB. The quantities appear to be doubled up with the temporary widening EBS. | Individual tables showing EBS quantities are included in the plans on the earthwork data sheets. The EBS quantities shown on the earthwork data sheets total up to the lump sums shown on the summary tables. A document is provided detailing where the EBS is shown in the cross sections. Median EBS is shown in both the temporary and permeant cross sections, but it was verified that quantities were not doubled. The document titled Proposal 005 Question 12 EBS XS.pdf can be found at the following location: https://wisdot.box.com/v/20260714005folder or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 12 | 2026-06-15 08:40 | 2026-06-24 08:51
20260714 | 20260714005 | 5 | Storm/Culvert Miscellaneous Quantities | Can the miscellaneous quantities for storm sewer related items be provided in Excel format? | The Storm Sewer and Culvert quantities in Excel can be found at the following location: https://wisdot.box.com/v/20260714005folder or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 13 | 2026-06-15 09:43 | 2026-06-16 10:51
20260714 | 20260714005 | 5 | Grooved Wet Ref Pavement Markings | For the bid items 646.2040 and 646.4040, the 6" and 10" black grooved wet ref is not separated into its own bid item. I would assume that this is an error and the black should be separated into their own bid items 646.2025 and 646.4025? Please advise. |  |  | 14 | 2026-06-15 13:59
20260714 | 20260714005 | 5 | Earthwork Summary | The earthwork summary in the Data Package does not match the earthwork summary in the Miscellaneous Quantities. Which summary and supporting information should be used to analyze the the hauls for the project? | Updated data package files, that match the earthwork summary, will be provided in upcoming addendum. The addendum will also include an updated earthwork summary in the miscellaneous quantities that will be adjusted to account for the low-level contaminated material (question 7). | Mike Coleman | 15 | 2026-06-16 08:41 | 2026-06-24 08:44
20260714 | 20260714005 | 5 | Relief Trenches | Will the excavation for the relief trenches shown on page 83 of the plan be paid as Common Excavation? | yes; it will be paid as excavation common. | Mike Coleman | 16 | 2026-06-16 11:10 | 2026-06-17 12:06
20260714 | 20260714005 | 5 | Full Depth LFCF | Will the excavation for the full depth LFCF be paid as common excavation? Is the quantity included as EBS or Common Excavation? The SPV states "the department will measure Lightweight Foamed Concrete Fill Grade 1 and Lightweight Foamed Concrete Fill Grade 2, by the cubic yard of LFCF material acceptably placed within the limits" and payment is full compensation for "temporary shoring". Is this temporary shoring for excavation? If temporary shoring is required for the excavation, will it be paid under the Temporary Shoring bid item since some excavations appear to be 10' deep? | Excavation below the existing ground line for the LFCF volume is paid as excavation common and is included in the miscellaneous quantities. The use of temporary shoring is not required to place the LFCF to the limits shown in the plans based on the proposed work-zone areas. If the contractor elects to use temporary shoring to reduce the excavation required to place the LFCF to limits shown in the plan, the temporary shoring is incidental to the LFCF bid item and will not be paid under the temporary shoring item. | Mike Coleman | 17 | 2026-06-16 12:11 | 2026-06-24 09:22
20260714 | 20260714005 | 5 | R-44-70/71 Excavations | At structure R-44-70 and R-44-71, the excavation under the existing structure is called to be a 1:1. Per OSHA requirements this needs to be a 1.5:1 at a minimum. Temporary shoring is likely required to retain the existing slope and structure. | Subsurface exploration has been conducted at the retaining wall sites. The soil type encountered is predominately cohesive (clays) with some localized silty sand (north abutment). OSHA Part 1926 Subpart P categorizes this material as Type B where a 1H:1V temporary excavation is allowable. If other soil with a greater granular content (ie. Clean sands) is encountered, the temporary slope may need to be flattened and/or other slope stabilization methods may be required. | Mike Coleman | 18 | 2026-06-16 16:42 | 2026-06-17 14:25
20260714 | 20260714005 | 5 | Excavation, Hauling, and Reuse of Low-Level Contaminated Material | Regarding question #9, will the Department consider the export of this material as change order work if directed by the onsite environmental consultant? | Yes | Mike Coleman | 19 | 2026-06-17 16:28 | 2026-06-24 09:09
20260714 | 20260714005 | 5 | Railroad Flagging | The proposal includes $50,000.00 in railroad flagging reimbursement. The contract work in the vicinity of railroad right of way is traffic control installation on highway structures above railroad lines or adjacent to overhead rail line (S-01-0001). This work typically does not require railroad flagging as the work remains within the limits of the highway structure parapet or within 25' of overhead track centerline. Why did the department include the railroad flagging reimbursement item? |  |  | 20 | 2026-06-18 10:18
20260714 | 20260714005 | 5 | Railroad Insurance & Coordination | The proposal identifies railroad insurance and coordination requirements for CN line (crossing ID 693817C). Please confirm this is the crossing of STH 441 over CN Fox River subdivision at approximately STA 1107'441N'+50. SPV article 1.4 lists the route name as IH 41. The proposal does not identify railroad insurance and coordination requirements for the WATCO (Foxy) line that goes over STH 441 in the vicinity of proposed S-01-0001 work. Please confirm there are no insurance or coordination requirements at this location. | Crossing ID 693817c is located on WIS 441, route will be addressed via addendum. FOXY crossing 693816v railroad insurance and coordination special provision will be added via addendum. | Mike Coleman | 21 | 2026-06-18 10:28 | 2026-06-24 09:24
20260714 | 20260714005 | 5 | SB 41 to SB 441 Interim Completion Date | According to SPV article 3 the SB 41 to SB 441 Ramp may be closed for 120 consecutive calendar days during Stage 4A. The traffic control plans show this ramp is closed through the completion of stage 4B. Please clarify. |  |  | 22 | 2026-06-18 13:02
20260714 | 20260714005 | 5 | Excavation, Hauling, and Reuse of Low-Level Contaminated Material | Section C of the SPV states the material will need to be covered with a "2-foot thick low permeable clay soil cover". What are the specifications for this material and how will the Department pay for the placement of this material? Please provide cross sections and an overview map for the proposed placement locations. |  |  | 23 | 2026-06-19 07:38
20260714 | 20260714005 | 5 | B-44-326 & B-44-327 Pier Height | Due to the height of the piers will construction joints be allowed in the stems? |  |  | 24 | 2026-06-19 12:26
20260714 | 20260714005 | 5 | B-44-327 Pier 1-8 Construction | The designer's construction schedule and the traffic control plan sheets indicate construction of B-44-327 piers 1-8 will occur in stage W1. On several of these substructure units the structure excavation limits are in conflict with traffic staging. Please consider including temporary shoring at necessary pier locations in the B-44-327 plan. |  |  | 25 | 2026-06-20 14:42
20260714 | 20260714005 | 5 | Backfill Structure Type A | Item 94 Backfill Structure Type A is listed as a paid by the cubic yard, however the plan does not included any quantities that are paid by the cubic yard. The listed quantity appears to be the total of the tons listed for R-44-70/71. Please review and correct or remove this item. |  |  | 26 | 2026-06-22 11:28
20260714 | 20260714005 | 5 | Low-Level Contaminated Material Dewatering | It is likely that water generated from dewatering activities within the fly ash contaminated locations will exceed the surface water discharge limits for compounds specified in WPDES Permit WI-0046566-5. Several of the substructure units for the B-44-326 and 327 structures are within the fly ash contamination limits. Dewatering will likely be required for construction of these substructure units and the LCFC at the approaches. Containment (holding tanks) and disposal of the contaminated water is incidental to the Excavation, Hauling, and Reuse of Low-Level Contaminated Material item. Would the department considering including a separate item for the containment and disposal of contaminated water instead of having it be incidental to the excavation item? |  |  | 27 | 2026-06-22 14:27
20260714 | 20260714005 | 5 | Longitudinal Bridge Deck Grooving Limits | Most longitudinal grooving contractors can only get within 24" of a vertical face. SPV article 11.17 requires getting with 18". Requesting the department consider 24" instead. |  |  | 28 | 2026-06-22 15:42
20260714 | 20260714005 | 5 | Design Schedule | Is WisDOT aware that the Preliminary Construction Schedule is missing most of the storm sewer and culvert work? There is one single line item for storm sewer listed in Stage 1. I understand the schedule shown is for information only; however, it was used to determine the completion date. |  |  | 29 | 2026-06-23 07:50
20260714 | 20260714005 | 5 | Precast box culverts | There is only 1 bid item #1002 for a 9'x5' box culvert. Plan sheet 542 refers to C44-146 as 8'x5'. Structure C44-146; plan sheet 1990 shows a 9'x5' box culvert. Plan sheet 566 refers to C44-147 as 8'x4'. Structure C44-147; plan sheet 2071 shows a 8'x4' box culvert. |  |  | 30 | 2026-06-23 08:03
20260714 | 20260714005 | 5 | Excavation Common | Please confirm the excavation for clay liner at the ponds has been included in the bid quantity for Excavation Common. |  |  | 31 | 2026-06-23 09:09
20260714 | 20260714005 | 5 | Earthwork Qty | Can you provide earthwork qtys for the temp ditching and CTH OO work in Stage 1? |  |  | 32 | 2026-06-23 12:00
20260714 | 20260714005 | 5 | Excavation, Hauling, and Reuse of Low-Level Contaminated Material | Has the Department included the quantity for material that will be encountered during pier excavation? Will the the excavated material be paid under this bid item? Has the Department considered the traffic control staging when providing the proposed placement locations? |  |  | 34 | 2026-06-24 08:39
20260714 | 20260714005 | 5 | Earthwork | Stage 1 441 NB widening Cross section sheets 3612-3615 appear to show a substantial EBS on the right slope, is there a data table listing this EBS qty? or where would we find the information for this? |  |  | 35 | 2026-06-24 12:10
20260714 | 20260714005 | 5 | Question #17 - Full Depth LFCF | Regarding the Departments answer to Question #17, please review Station 320+00 ES on page 2928 of the plan. The cross sections are showing a vertical excavation that is 8' depth. For safety purposes this excavation will likely need to be back sloped or benched. The Department should consider increasing the excavation volume and the full depth LFCF quantities to reflect safe excavations. |  |  | 36 | 2026-06-24 12:29
20260714 | 20260714005 | 5 | Temp Access | Can you list the temp access locations for each stage of the project? |  |  | 37 | 2026-06-24 14:26
20260714 | 20260714005 | 5 | R-44-70/71 Excavations | The borings for these wall areas do not show cohesive soils. The borings Silty Sand/ Fine medium Sand etc. This would not be Type B soils it would be Type C. The slope can not be "flattened" because the excavation is already at a 1:1 slope and any flatter would undermine the abuttment. This excavation will require shoring. Will temp shoring be paid to safely perform this work? |  |  | 38 | 2026-06-24 16:32
20260714 | 20260714005 | 5 | Fuel Cost Adjustment | ASP 5 currently indicates the base fuel index for this project is $4.70 per gallon. With the recent decrease in fuel cost, please consider adjusting the base fuel index the week prior to bid submittal to more accurately reflect the current fuel market. |  |  | 39 | 2026-06-26 06:07
20260714 | 20260714005 | 5 | Pipe Underdrain 6-Inch Special | The estimate of quantities on page 1384 list 16,520' for project 1130-65-71 but a table is not provided in the miscellaneous quantities. Please provide a table. |  |  | 40 | 2026-06-26 11:13
20260714 | 20260714005 | 5 | Storm Sewer & Culvert work CAD file | Could you post a .dwg file for the proposed storm sewer and culvert work? |  |  | 41 | 2026-06-26 11:55
20260714 | 20260714005 | 5 | Road Closures | Are there any scheduled closures of the CTH N & IH 41 interchange within the duration of this project? |  |  | 42 | 2026-06-26 14:40
20260714 | 20260714008 | 8 | Design Schedule | Please provide the design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/7tgjupl103hyi4n0jawm0q36k8672lo7 or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-06-15 06:34 | 2026-06-16 07:22
20260714 | 20260714009 | 9 | Geotechnical Report | Can the geotechnical information for this project be provided? | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/oqepmjivof38ixe3b7gcxnyahqfpdlvm or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-06-12 10:19 | 2026-06-16 07:01
20260714 | 20260714009 | 9 | Design Schedule | Can the design schedule for this project be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/oqepmjivof38ixe3b7gcxnyahqfpdlvm or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-06-12 10:19 | 2026-06-16 07:11
20260714 | 20260714009 | 9 | Climbing Turtle Exclusion Fence | Will the climbing turtle exclusion fence be installed prior to construction by others or will the installation of exclusion fence be allowed outside of the specified time of September 19th to May 19th? Without a variation from the allowable time frame of installation the work within 1,000â€™ of Barnes Creek cannot happen in 2026. However, it is included in the 2026 work under the â€œConstruction Phasingâ€ section of the special provisions. | The exclusion window for turtle fencing is from May 20th, 2026 to Sept 18th, 2026. Our intent is that the contractor will simply gap any area around Barnes Creek requiring climbing turtle exclusion fence until the exclusion window has expired. Please note that the current bridge project at Barnes Creek does have some turtle fence in place already. That fence is scheduled to remain in place at the completion of their project. At that time, responsibility for maintenance, removal, and restoration needed due to the 82 turtle exclusion fence will be transferred to the 72 paving project. | Mike Coleman | 3 | 2026-06-16 19:03 | 2026-06-17 12:09
20260714 | 20260714009 | 9 | Utilities | Per section 6 of the special provisions, there are utility adjustments to be made by Spectrum and WPS before the 2027 construction season, however many of the station ranges where adjustments are to be made fall into the station ranges specified to be constructed in 2026. Does the department anticipate the existing utilities to be in conflict with the 2026 construction work? If they are deemed to be in conflict, will the adjustments be made prior to work beginning in 2026? |  |  | 4 | 2026-06-16 19:07
20260714 | 20260714009 | 9 | Barnes Creek Bridge Project #9030-07-82 | Will the above project be completed before work on 9030-07-72 begins? | At this time, the current Barnes Creek bridge project is on schedule to be completed prior to the paving project starting. | Mike Coleman | 5 | 2026-06-16 19:08 | 2026-06-17 12:10
20260714 | 20260714009 | 9 | Incentive/Disincentive for Interim Completion of Work | The bid items at the end of the proposal includes item 208 â€œIncentive/Disincentive for interim completion of workâ€ but that item is not found in the miscellaneous quantities or on BidX. Should the description for item 210 in the proposal be moved to item 208 and the existing item 208 in the proposal be eliminated to match the MQâ€™s and BidX? |  |  | 6 | 2026-06-24 20:53