## qandasearchletting_results
Date | 2026-08-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260811 | 20260811002 | 2 | Polyethylene Sheeting | Where is the poly sheeting used on this project? | Polyethylene sheeting shall be utilized if ground disturbing activities and re-establishing vegetation cannot be completed by October 15th, the contractor shall be responsible for keeping the ground disturbed. Disturbance shall be classified by removal of the topsoil and placement of a Polyethylene on top of the exposed soil surface. This is stated in article 3 under the Blanchard Cricket Frog and also an asterisk in the miscellaneous quantity table. | Mike Coleman | 1 | 2026-07-23 14:45 | 2026-07-27 09:45
20260811 | 20260811002 | 2 | Cofferdam Elevations | The plans for the bridge shows the top of the cofferdam to be at a minimum elevation of 808.11. That is significantly higher than the observed water elevation and only about 2' below the top of the pier. Please confirm the cofferdam can be installed to approx elevation of 800 which is similar to what is shown in the section view on sheet 1 of the bridge plans. | Cofferdams must be installed to a minimum elevation of 808.11 as stated in the plans. This is to satisfy the incidental take authorization for Blanchard Cricket Frogs; this is also stated in the special provisions Article 11 subsection 4. | Mike Coleman | 2 | 2026-07-23 15:15 | 2026-07-29 10:35
20260811 | 20260811002 | 2 | Dockwall Explaination | Section 11 of the special provisions states that barges are anticipated for pier access and that dock wall installation is prohibited. Can you please explain the intent of this language, and what the Department is defining as a dock wall? | A dockwall is defined as a temporary structure extending into the Baraboo River for the purposes of transferring equipment and/or personnel onto barges. A dockwall does not fall under the current permitting for the project, any changes to this would need to be re-coordinated with the DNR. | Mike Coleman | 3 | 2026-07-24 10:26 | 2026-07-28 06:32
20260811 | 20260811004 | 4 | Geotechnical Report | Can the Geotechnical Report be provided for this project? | The revised soils report and addendum(01) can be found at the following location: https://wisdot.box.com/s/5bgl07qilc9kic960w4p2ecjz571ztz1 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-07-21 12:04 | 2026-07-23 07:26
20260811 | 20260811004 | 4 | Earthwork Table: Expanded Fill Factor | The MQ table for earthwork calculates expanded fill with a factor of 1.5. This value seems rather high, 1.2 or 1.3 seem more appropriate. Although this is for information only, it would be good to realize (in the EW table) that the waste factor on the job is actually higher than what is currently shown. |  |  | 2 | 2026-08-06 17:05
20260811 | 20260811005 | 5 | Engineer's Prebid Project Schedule | Please provide the Engineer's pre-bid project schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/siijc5n9cdyv7xi31tcrget6n8i98rr8 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-07-20 15:34 | 2026-07-21 08:52
20260811 | 20260811005 | 5 | Geotechnical Data | Please provide any geotechnical data available for the project area. | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/v/20260714005folder or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-07-20 15:34 | 2026-07-21 08:54
20260811 | 20260811005 | 5 | MSE Wall | The wall requires small block and shows the back side of the block exposed to the sidewalk. The backside of these block is not typically continuous and is filled with drain rock. Also, there is a high potential that the top block and cap could be pushed off the top of the wall. Given the minimal wall height, is there a different option for this slope? | An addendum will be issued to update the project plans and contract documents. The changes will result in the MSE wall being eliminated from the project. | Mike Coleman | 3 | 2026-07-31 09:39 | 2026-08-05 08:38
20260811 | 20260811005 | 5 | watermain items | Please provide the spec for the T-bolts required; cor-blu, cor-black or stainless steel. There is a tapping sleeve in the plans. Please provide a spec for that item and connection. | After further communication, the Village has no preference on the T-Bolts required. An addendum is being issued to correct a quantity error. | Mike Coleman | 4 | 2026-08-04 11:31 | 2026-08-06 06:16
20260811 | 20260811007 | 7 | 38. Furnish & Install APS System | Will the Campbell/PedSafety Guardian Duo APS system which is on the WisDOT contract & QPL/APL be accepted as an approved equal for this project? |  |  | 1 | 2026-07-10 14:19
20260811 | 20260811007 | 7 | 40. Non-Intrusive Vehicle Detection System | Will the Econolite Vision Video Detection System be accepted as an approved equal for this project? |  |  | 2 | 2026-07-10 14:22
20260811 | 20260811009 | 9 | Bid Item 645.0220 Geogrid SR | We have downloaded the 20260811009 proposal PDF from the Wisconsin DOT website and we did not see a special provision for bid item Geogrid SR. Can a special provision be provided regarding the material properties for this bid item? | This bid item is a standard item and can be found in the State of Wisconsin Standard Specifications for Highway and Structure Construction, Section 645 - Geosynthetics. The material properties are listed in Section 645.2.3.2 Geogrid, Type SR (Subgrade Reinforcement). | Mike Coleman | 1 | 2026-07-09 15:51 | 2026-07-22 10:30
20260811 | 20260811009 | 9 | Earthwork Miscellaneous Quantities | Can the earthwork breakdown tables be provided in excel format? | The earthwork quantities breakdowns are provided in excel format in the Construction Data Packets. Note there are separate packets for the two Project IDs included in this proposal. https://wisdot.app.box.com/v/Supplemental-Info-20260811/folder/397429750873 Spreadsheets can be found at these paths; there are multiple spreadsheets for each Project ID: look in CD-X-Section | Mike Coleman | 2 | 2026-07-14 10:09 | 2026-07-22 11:08
20260811 | 20260811009 | 9 | Datat Packs | The data pack for 1090-09-75 is missing the earthwork info for Stage 2 I43 SB and STH 20 Ramp B; Stage 3 permanent I43 NB and STH 20 Ramp A; Stage 3 Temp SB Entr Rampfrom STH 83 X-over removal; and Stage 4 NB Entr Ramp from STH 20 X-over removal. There is no earthwork info regarding project 1090-09-77. | The earthwork quantities breakdowns are provided in excel format in the Construction Data Packets. Some stages for 1090-09-75 are included in the 10900975-Erwk-Ult. Note there are separate packets for the two Project IDs included in this proposal. https://wisdot.app.box.com/v/Supplemental-Info-20260811/folder/397429750873 Spreadsheets can be found at these paths. | Mike Coleman | 3 | 2026-07-18 13:46 | 2026-07-22 11:12
20260811 | 20260811009 | 9 | Geotechnical Report | Can the Geotechnical Report be provided for this project? | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/ya3v8uk0szo9wbca2bn9u2ygj8gen4e6 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 4 | 2026-07-21 12:06 | 2026-07-22 10:27
20260811 | 20260811009 | 9 | As-Builts | Can the Department provide the as-builts for the reinforcement in the existing concrete pavement? | The as-builts can be found at the following location: https://wisdot.box.com/s/ya3v8uk0szo9wbca2bn9u2ygj8gen4e6 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 5 | 2026-07-21 15:45 | 2026-07-22 10:59
20260811 | 20260811009 | 9 | Structure B-67-129 | For Structure B-67-129, the estimated quantities indicate 22 each â€“ Adhesive Anchors 7/8 - Inch at each abutment. Where are the adhesive anchors to be used? | The adhesive anchors are used for the bearing replacements. The adhesive anchor bid item should be â€œAdhesive Anchors 1 ï¿½-Inchâ€ to match the anchor bolt size shown on the bearing sheet. These revisions will be made via addendum. | Mike Coleman | 6 | 2026-07-27 12:06 | 2026-07-29 12:03
20260811 | 20260811009 | 9 | Structure B-67-130 | For Structure B-67-130, are the 7/8â€ diameter anchors for the elastomeric bearings included with Bearing Pads Elastomeric Laminated item for payment? | Payment for the new anchor bolts is included with payment for the Bearing Pads Elastomeric Laminated bid item as stated in the 3rd note on Sheet 6 of 7 on the structure plans. | Mike Coleman | 7 | 2026-07-27 12:06 | 2026-07-29 12:02
20260811 | 20260811009 | 9 | Subcontractor List | When and how are Subcontractor Lists submitted? | A list of eligible bidders and plan holders can be found on the HCCI site for the August letting. The lists can be found at the following location: Eligible Bidders https://wisconsindot.gov/hccidocs/bid-let/2026/20260811/eligiblebidders.pdf Plan Holders https://wisconsindot.gov/hccidocs/bid-let/2026/20260811/planholders.pdf | Mike Coleman | 8 | 2026-07-27 12:08 | 2026-07-27 12:31
20260811 | 20260811009 | 9 | Asphaltic Surface Patching | The misc quantities under both ID's show a table for asphaltic surface patching. It shows asphaltic surface milling (SY) and asphaltic surface patching (TN) for prep stage and stage 1 with stationing covering the entire length of the job. Does WisDOT have locations and sizes for the patching or is all the work undistributed? If undistributed, what are minimal sizes (width/length) and depth? Can WisDOT provide a detail? Is all the work under daytime lane closure? | These quantities are undistributed and calculated using 15% of the joint length for joint repair and 8% of the pavement area for patching. HMA longitudinal joint repair dimensions are shown on sheet 23 of the plan set. Work is to be completed in accordance with the special provision requirements, off peak work hours are anticipated. | Mike Coleman | 9 | 2026-07-29 12:26 | 2026-08-03 07:11
20260811 | 20260811009 | 9 | Asphalt Quantities | On page pdf page 2301 of the plan, there is 8,930 tons of "Shoulder Replacement" asphalt in the Misc Qtys. This qty seems high as it should only be the areas where the crossovers meet the existing pavement or new pavement. Are we looking at this correctly and does the qtys need to be revised? | Revised plans and quantities are provided in Addendum #2. | Mike Coleman | 10 | 2026-07-31 10:45 | 2026-08-06 06:38
20260811 | 20260811009 | 9 | Common Excavation | Will the Department grant the contractor permission to dispose of excess cut material in medians within the project limits if DNR approves? | The plans do not include locations to dispose of surplus excavated material and there are not any pre-approved locations identified. The department will review and evaluate surplus excavated material disposal locations proposed by the contractor per Standard Specification 205.3.12. The proposed locations must be identified within the Erosion Control Implementation Plan (ECIP) and will be evaluated through the ECIP review process. | Mike Coleman | 11 | 2026-07-31 13:48 | 2026-08-04 09:27
20260811 | 20260811009 | 9 | Asphaltic Surface Temporary | Under project 1090-09-77 the misc quantities table "HMA Pavement" show 17,284 tons of asphaltic surface tempoary under stage 1 with comment that is for inside NB rumble strips. Is all the quantity for rumble strip removal/paving or is it for other areas? | The quantity is for rumble strip paving and the quantity has been updated. Revised plans and quantities are provided in Addendum #2. | Mike Coleman | 12 | 2026-08-01 10:56 | 2026-08-06 06:38
20260811 | 20260811009 | 9 | Design Schedule | Please provide the design schedule | The design schedule can be found at the following location: https://wisdot.box.com/s/ya3v8uk0szo9wbca2bn9u2ygj8gen4e6 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 13 | 2026-08-02 11:39 | 2026-08-05 10:09
20260811 | 20260811009 | 9 | Cad Files | Would it be possible to provide a surface for the top of the base aggregate dense 1 1/4"? | A top of base aggregate dense 1 ï¿½â€ CAD surface will not be provided for the project. | Mike Coleman | 14 | 2026-08-03 10:55 | 2026-08-06 05:58
20260811 | 20260811009 | 9 | Milling | What thickness of milling is required for the NB Rumble Strip Milling? | The depth of milling at this location is 2 inches. | Mike Coleman | 15 | 2026-08-03 12:59 | 2026-08-04 09:29
20260811 | 20260811009 | 9 | B-64-92 Surface Repair | Notes on page 2 of plans for B-64-92 state that girder surface repair shall be included in the concrete surface repair bid item. Typically this is broken out in a separate item - "prestressed girder surface repair". Not blended with surface repair on the rest of the structure. Can a new item be added for the surface repair at the prestressed girders? | Revised plans, bid items, and quantities are provided in Addendum #2. | Mike Coleman | 16 | 2026-08-03 16:11 | 2026-08-06 06:37
20260811 | 20260811009 | 9 | Selected Subcontract List | As outlined in the project manual, Contractor is required to submit a list of selected Subcontractors with the proposal including Name, Class of Work and Estimated Value. Where does the contractor attach or submit this information at bid time? We do not see a location in Bid Express to attach. | The subcontractor list is to be submitted within 10 business days after the date of notice of the award of the contract. | Mike Coleman | 17 | 2026-08-04 15:48 | 2026-08-06 06:04
20260811 | 20260811009 | 9 | Excess Materials | The project has a significant quantity of excess material. Would the Department consider raising the roadway profile to create a balanced site and mitigate scope and cost for offsite haul off of the excess excavated materials? | The design profile will not be adjusted. Bid the project as shown in the plans and special provisions. | Mike Coleman | 18 | 2026-08-04 15:49 | 2026-08-06 05:58
20260811 | 20260811009 | 9 | Excess Materials | The project has a significant quantity of excess material. Would the Department allow the contractor to waste excess excavated materials outside of the mainline between the shoulders and right of way? | The plans do not include locations to dispose of surplus excavated material and there are not any pre-approved locations identified. The department will review and evaluate surplus excavated material disposal locations proposed by the contractor per Standard Specification 205.3.12. The proposed locations must be identified within the Erosion Control Implementation Plan (ECIP) and will be evaluated through the ECIP review process. | Mike Coleman | 19 | 2026-08-04 15:50 | 2026-08-06 05:53
20260811 | 20260811009 | 9 | Earthwork Quantity Errors | In the 1090-09-75 plan, sheet 685, the EBS Excavation quantity is not incorporated into the Excavation Common quantity, as notes 4 details. Please correct. In the 1090-09-77 plan, sheet 958, it seems there wasnâ€™t any cut/fill quantified between station 684+00 and 693+00 on SB, even though the cross sections show excavation in this area. Please correct. | Revised plans and quantities are provided in Addendum #2. | Mike Coleman | 20 | 2026-08-04 19:04 | 2026-08-06 06:36
20260811 | 20260811009 | 9 | Asbestos Surveys | Can you please provide a copy of the Asbestos Inspection Report for the following structures, B-64-0092, B-64-0093, and B-64-0094. | The asbestos inspection reports can be found at the following location: https://wisdot.box.com/s/ya3v8uk0szo9wbca2bn9u2ygj8gen4e6 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 21 | 2026-08-05 10:26 | 2026-08-06 11:15
20260811 | 20260811009 | 9 | Bridge Inspection Report | Please provide the most recent bridge inspection report for structure # B-64-92. | The inspection report can be found at the following location: https://wisdot.box.com/s/ya3v8uk0szo9wbca2bn9u2ygj8gen4e6or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 22 | 2026-08-05 15:46 | 2026-08-06 11:19
20260811 | 20260811009 | 9 | Clearing & Grubbing STA Quantity | The plans only show 9 STA for Clearing & Grubbing but the proposal sheets on bid form on BidX show 29 STA. Can you please clarify? | Project ID 1090-09-75 includes 9 Stations and Project ID 1090-09-77 includes 20 Stations for an overall total of 29 Stations. | Mike Coleman | 23 | 2026-08-06 06:10 | 2026-08-06 11:11
20260811 | 20260811009 | 9 | High Performance Drilled Dowel Bars. | Can it be confirmed that standard dowel bars shall be used for the Concrete Repairs and Replacements on STH 83 and the Ramps and not high-performance dowel bars? | Confirmed. Use standard dowel bars in these locations as shown on Sheet 680. | Mike Coleman | 24 | 2026-08-06 06:34 | 2026-08-06 11:24
20260811 | 20260811010 | 10 | Design Schedule | Can the construction design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/ahxgoatpfi7ii77f01l9lcmkqb1biiej or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-08-05 11:00 | 2026-08-06 11:23
20260811 | 20260811010 | 10 | Concrete Staining | Per the specification, concrete staining can not take place until a minimum of 28 days after concrete placement. This would likely cause concrete staining to occur after the roadway is open to traffic. Will the Department waive any LD's or project disincentives if concrete staining is not completed but the roadway is open to traffic as specified in the project specs? |  |  | 2 | 2026-08-05 14:06
20260811 | 20260811010 | 10 | Access | What is the Department's anticipated plan for access for stages 2 and 3? Will ingress and egress be allowed during all times from either end of the project to and from IH-41 and STH 29? Additionally, what was the Department's plan for access between Parkview Road and Oneida Street during construction? There is not any access indicated in the plans for between these structures. Once the approach work begins there will not be a way in or out as currently shown. |  |  | 3 | 2026-08-05 14:28
20260811 | 20260811010 | 10 | Closures | Will full freeway closures be allowed for the nights of traffic switches between stages and initial setup? Having to maintain live traffic while switching traffic configurations is unsafe to the travelling public as well as those performing the work. Can the Department include language to allow full closures for certain operations and include the allowable hours of these closures. | The special provisions article 4, Traffic, specify â€œone lane must remain open at all times along northbound and southbound IH 41â€ and allow for up to double lane closures along I-41 during allowed times specified. For any further traffic control considerations, the special provisions discuss the process for submitting any changes to the proposed traffic control detail as the plans show for approval by the engineer. Any proposed changes and if they would be allowable would be discussed at that time. | Mike Coleman | 4 | 2026-08-05 14:45 | 2026-08-10 09:43
20260811 | 20260811010 | 10 | Concrete Barrier Wall S42 Barrier Pad | Is the Concrete Barrier Pad under the S42 wall paid as pavement or is it incidental to the wall? |  |  | 5 | 2026-08-10 11:35
20260811 | 20260811010 | 10 | Removing Electrical Median Bases Type 1 & 2 | There does not appear to be a removal item for removing Concrete Base Median Barrier Type 1 & 2. How are the removals of these bases being paid? |  |  | 6 | 2026-08-10 12:10
20260811 | 20260811011 | 11 | Designer's Construction Schedule | Can the department provide the designer's construction schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/dweiu2u31qsjofeeybmdfetlgfyn0gt1 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-07-20 13:38 | 2026-07-21 08:47
20260811 | 20260811011 | 11 | Spring 2027 Continuous Closures | Would the department consider allowing continuous lane closures on both ends of the project during Spring 2027 to allow paving and concrete work to happen simultaneously? This is the only time frame that both ends are allowed continuous closures, and it may not be possible to get all the paving done on the north end during continuous closures if it cannot overlap the work on the south end. | Continuous Closures may happen in both the North and South segments provided that the closure is only in one direction NB or SB in one segment and is in opposite direction in the other segment. | Mike Coleman | 2 | 2026-07-22 15:03 | 2026-07-27 06:10
20260811 | 20260811011 | 11 | Local Road Work Restrictions | The Local Road Work Restrictions in the special provisions due not allow for work on the local roads when the corresponding ramps are closed. In some cases, especially on Manitowoc Road/ CTH JJ, if the road is closed to work on it, the ramps will also need to be closed. Can the department remove this requirement from the specials? | The local road can be closed during the allowable ramp closure windows, local roads that are 2 lanes in each direction will still have single lane closures for work. | Mike Coleman | 3 | 2026-07-22 15:03 | 2026-07-27 06:23
20260811 | 20260811011 | 11 | Day Time Ramp Closures | Would the department consider allowing temporary daytime closures of ramps to allow milling and paving to happen in the outside lanes through the ramp areas during the allowed continuous closures? To safely complete this work the ramps should be closed. | Only ramps that would have daytime ramp closure ability would be at Webster Ave on-ramp to 43 SB, 54/57 EB to 43 SB and 54/57 WB to 43 NB. Otherwise every other service or system ramp in this project doesnâ€™t have any daytime ability for fully closing with the AADTâ€™s at or above 4000. | Mike Coleman | 4 | 2026-07-22 15:06 | 2026-07-27 06:25
20260811 | 20260811011 | 11 | Ramp Nightly Closure Times | For constructability of setting and opening the nighttime closures, would the department considered allowing the ramp closure times to match the allowed IH 43 lane closure times? If ramps needed to be closed this would allow them to be closed and opened with the lane closures rather than having to set temporary merges for an hour or two or open ramps an hour before the lane closures are removed. | Ramp closures will not be adjusted to match I-43 closure times. | Mike Coleman | 5 | 2026-07-22 15:07 | 2026-07-27 06:29
20260811 | 20260811011 | 11 | SB Atkinson ON Ramp | The SB on-ramp from Atkinson Drive is allowed to be closed 7 PM â€“ 5 AM nightly but is required to be closed when there is a long-term continuous lane closure on IH 43 SB. Will the department also allow continuous closures of this ramp during these allowable lane closures? Also, depending on where the SB lane closure can be started, it may be impossible to keep the SB Atkinson ON ramp and SB Webster ON ramp open at the same time when work is required on the Webster ramp. Unless the lane closure is allowed to start south of Atkinson on the bridge, the Atkinson Ramp needs to be closed. Will both ramps be allowed to be closed in this situation? . | Consecutive on-ramps in this case canâ€™t be closed continuously, especially with the alt route for the SB Atkinson on-ramp needing to go through the City of GB and use this signed alt route to hop back on via Webster Ave on-ramp for SB traffic. Any mainline SB lane closure for work on the east side of the bridge will need to start at the top of the bridge or to the east of there, to avoid needing to close the SB on-ramp from Atkinson. The concern is with the large vehicles being able to enter the single lane of traffic from the Atkinson on-ramp to SB with the vertical profile at safe speed and ability to climb the bridge without major queuing. | Mike Coleman | 6 | 2026-07-22 15:09 | 2026-07-27 06:29
20260811 | 20260811011 | 11 | 6â€™ Inside Shoulder NB/SB IH 43 | Could the department change the slope of the inside shoulder to 2% or match the existing inside lane on NB/SB IH 43 mainline? | Maintain the typical section in plans. No Change. | Mike Coleman | 7 | 2026-07-22 15:12 | 2026-07-27 06:30
20260811 | 20260811011 | 11 | Ramp Shoulder Slope | Could the department change the slope of the shoulders on the ramps to match the lane. This would allow the ramps to be paved in echelon as has been approved in previous IH 43 corridor contracts. | The shoulder slopes will be allowed to be changed on ramps provided that the ramp is paved in echelon. | Mike Coleman | 8 | 2026-07-22 15:14 | 2026-07-27 06:31
20260811 | 20260811011 | 11 | System Ramp Shoulder Mix Type/Slope | For the system ramps at STH 54, would the department consider changing the mix and slope of the shoulders to match the mainline to allow them to be paved in echelon in one pass as has been approved in previous IH 43 corridor contracts. | The department would like to keep mix and slope as stated in plans for the system ramps at STH 54. | Mike Coleman | 9 | 2026-07-22 15:15 | 2026-08-05 10:11
20260811 | 20260811011 | 11 | Maintenance X-Overâ€™s | Would the department consider changing the item for the maintenance x-overs to one asphaltic surface item rather than 3 LT and 4 LT? Also, would the department consider overlaying the existing pavement on the x-overs and not milling them since the roadway profile is being raised? | The maintenance crossover will be considered to changed to asphaltic surface item and crossovers will be built as shown in plan- milling and placing 2 layers of asphaltic material. | Mike Coleman | 10 | 2026-07-22 15:17 | 2026-08-05 10:11
20260811 | 20260811011 | 11 | Even Cross-Sectional Profile | Paragraph 7 of the Prosecution and Progress requires an even cross-sectional profile of the roadway within 72 hrs. of paving the adjacent lane. Will this be required if the contractor utilizes a notched wedge per the standard specifications. | This question will be addressed in forthcoming addenda | Mike Coleman | 11 | 2026-07-22 15:18 | 2026-07-29 10:22
20260811 | 20260811011 | 11 | CTH V/Mason Street Ramps Allowable Closure Times | What are the allowable closure times for the CTH V/Mason Street ramps. The specials did not include those. | The times will be added via upcoming addenda | Mike Coleman | 12 | 2026-07-23 09:13 | 2026-07-27 06:44
20260811 | 20260811011 | 11 | Extended Weekend Echelon Paving Requirement | The special provisions require that HMA needs to be paved in echelon for all lanes during the extended weekend closure. In some cases this may not be possible if some of the work is completed under lane closures ahead of the weekend closure or where there are different mix types. Could the department remove this requirement? | Echelon paving will be required for centerline joint during the extended weekend closures; the department recognizes that some of the areas maybe done ahead of full weekend closure and that echelon paving the centerline joint will not be possible. Echelon paving will not be required at joints that change mix types. | Mike Coleman | 13 | 2026-07-23 11:32 | 2026-08-05 10:12
20260811 | 20260811011 | 11 | S-5-447 Geotech Report | Is there a geotechnical report for structure S-5-447 that can be made available? | There is no boring at the exact location of S-5-447, but Boring #7 on page 256 of the plans is close by. | Mike Coleman | 14 | 2026-07-27 08:25 | 2026-07-28 10:31
20260811 | 20260811011 | 11 | Full Depth Pavement Removal Under B-5-198 | With the amount of work required to get the roadway back open to traffic at the full depth pavement replacement location under B-5-198 (Concrete Removal, Excavation, Select Crushed placement, 1-1/4" placement, and 4 lifts of HMA), would the department allow an additional extended closure of the CTH JJ NW Loop Ramp to complete this work ahead of the full weekend closure? The inside lane can be completed with the extended lane closure but to complete the outside and ramp lane the ramp would need to be closed. Even during the weekend full closure it does not seem possible to complete all this work, allow the pavement to cool, and get all the mainline paving done as described in the specials. With the thickness of this patch the contractor feels it would be best to complete this work ahead of time to allow it to be opened to traffic prior to paving mainline over it. | The Department will not allow any extended closure of the ramp ahead of the scheduled extended weekend full closure. You may complete the median lane of IH 43 before the extended weekend full closure by using a continuous 24-hour single lane closure. You may also complete the outside lane of IH 43 before the extended weekend full closure by using a continuous 24-hour single lane closure. However, the CTH JJ NW Loop Ramp must be completed during the extended weekend full closure period. | Mike Coleman | 15 | 2026-08-03 12:36 | 2026-08-05 10:10
20260811 | 20260811011 | 11 | Str C-05-114 Size Discrepancy | The plans list this as a 60" round CIPP liner to install. We have inspected this pipe and found the size to be a 71" span x 55" rise ARCH Structural Steel Segmental Pipe (SSSP). This is equivalent to a 66" Arch based on circumference. Please clarify or address this size discrepancy. | An emergency addendum will be sent out to address this. | Mike Coleman | 16 | 2026-08-05 11:39 | 2026-08-07 07:47
20260811 | 20260811013 | 13 | Select Borrow | SPV 17 Select Borrow indicates the contractor may substitute Select Crushed Material if the engineer approves. Please directly state if Select Crushed will be approved as a substitute. | Select crushed will be allowed as a substitute for select borrow. | Mike Coleman | 1 | 2026-07-30 09:09 | 2026-08-03 07:50
20260811 | 20260811013 | 13 | Geotechnical Report | Please provide a copy of the Geotechnical Report if available. | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/xne65i9h0mb1r92boxmhkokb9y608wuj or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-07-30 09:38 | 2026-08-03 08:08
20260811 | 20260811013 | 13 | Select Borrow | Could the EBS be backfilled with excess cut from common excavation? After reviewing the cross sections it appears fill will be placed over the select borrow in several areas. | Per the soils report recommendation, EBS should be filled with select borrow due to a high water table identified during the soil investigation. | Mike Coleman | 3 | 2026-07-30 09:42 | 2026-08-03 08:09
20260811 | 20260811014 | 14 | Geotechnical Report | Can the Geotechnical Report be provided for this project? | The soil borings can be found at the following location: https://wisdot.box.com/s/302xhryn4368haie6qhri8pxxs77uukw or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-07-21 12:07 | 2026-07-24 06:55
20260811 | 20260811014 | 14 | Grading & Shaping Ditch | The work proposed for these areas appears to be included in the cross sections and the earthwork and the plan appears to include a topsoil quantity. Is this item necessary? | The SPV item for Grading & Shaping Ditch will be modified with an upcoming addendum and quantities updated as well. | Mike Coleman | 2 | 2026-07-23 13:42 | 2026-07-30 06:16
20260811 | 20260811015 | 15 | Engineer's prebid project schedule | Please provide the Engineer's pre-bid project schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/t6krgryqqcw6cugy2oguji55jlbf4tba or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-07-20 15:35 | 2026-07-23 08:55
20260811 | 20260811015 | 15 | Geotechnical Data | Please provide any geotechnical data available for the project area. | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/t6krgryqqcw6cugy2oguji55jlbf4tba or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-07-20 15:36 | 2026-07-23 08:55
20260811 | 20260811015 | 15 | 2" Rigid Insulation | The Lincoln Ave Culvert Detail refers to SPV.0060.04 Rigid Insulation Board 2-Inch Thick. This SPV is not in the special provisions. There is not a bid item for 2" rigid insulation. Is 2" rigid insulation required for the Lincoln Ave. culvert installation? | The construction detail note is incorrect. Intent is to utilize 612.0902.S.01 Insulation Board Polystyrene (Inch)(01.2-inch) as detailed in the miscellaneous quantities, special provisions and AWP. | Mike Coleman | 3 | 2026-07-30 14:49 | 2026-08-03 08:10
20260811 | 20260811015 | 15 | Mortared Riprap | On sheet 12 of the plan there is a note indicating that there is "mortared riprap". Is there going to be a bid item added for grouted riprap? | There will not be an item added for grouted riprap. The note on page 12 is pointing to the existing mortared riprap, it is grey scaled. The detail on page 32 shows the limits of the new riprap. | Mike Coleman | 4 | 2026-08-05 16:55 | 2026-08-10 06:29
20260811 | 20260811016 | 16 | Design Construction Schedule | Can the department provide the designer's construction schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/fyekq4u2qcfm9ugqwgb8a23nl7etnzwa or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-07-24 14:02 | 2026-07-27 09:50
20260811 | 20260811016 | 16 | Culvert Pipe | Per detail on page 5 of the plan under the culvert replacement detail it states grade 2 granular backfill for culvert pipe backfill to 1' over the top of pipe. Must the backfill be grade 2 material or can it also be base aggregate per 520 of standard specs? | We want granular backfill grade 2 per the detail in the plan. | Mike Coleman | 2 | 2026-08-07 08:34 | 2026-08-10 07:28
20260811 | 20260811017 | 17 | Geotechnical Report | Can the Geotechnical Report be provided for this project? | The Geotechnical Report(s) can be found at the following location: https://wisdot.box.com/s/hrg1iupkon0dru4ng8ses57kxnw56mdg or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-07-21 12:08 | 2026-07-27 09:43
20260811 | 20260811017 | 17 | Railroad insurance, flagging costs | Due to the proximity of the railroad tracks to the wing repair on Structure B-37-187, (it appears to be less than 50' from CL of tracks) will a right of entry permit be required from the railroad? Will permitting costs be reimbursed by the Department? Will flagging costs be reimbursed? |  |  | 2 | 2026-08-07 12:44
20260811 | 20260811017 | 17 | ROW locations at bridge repair site | Can the Department please clarify where the DOT right of way ends and the railroad right of way begins at STA 436+27? |  |  | 3 | 2026-08-07 14:03
20260811 | 20260811018 | 18 | Design Schedule. | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/ct3aqc3mxgfyu9rxdbx30s4pcyoqpdkk or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-07-20 08:22 | 2026-07-23 07:06
20260811 | 20260811018 | 18 | Expedited Contract. | Given the time frame for this project Will WisDOT expedite turning around the contract and ECIP for this project in order to get a timely start? | Standard Spec 103.6 will be followed to execute the contract within 10 days of award. In regards to the ECIP, the project staff is committed to prioritizing the ECIP review and routing through WDNR as quickly as possible. If desired a coordination meeting can be arranged with WDNR to go over any questions the contractor may have regarding the development of the ECIP. | Mike Coleman | 2 | 2026-07-21 05:35 | 2026-07-27 09:40
20260811 | 20260811018 | 18 | Earthwork | Why does the South & North Crossover Install have such a large quantity for Salvaged Pavement? The quantities appear to be incorrect unless this quantity includes topsoil in the cut. Why is the South Crossover Removal missing quantities? Is this going to remain in place? | The earthwork table was reviewed and a discrepancy was identified. There will be an addendum developed to correct the discrepancy and adjust the quantities appropriately. The south crossover will remain in place after the project which is why it is not included in the quantities table. | Mike Coleman | 3 | 2026-07-22 10:26 | 2026-07-28 06:33
20260811 | 20260811018 | 18 | Earthwork | Common Excavation includes 1619 cy for Median Crossovers and Sideroads. Every location in the plan is shown as Removing Asphaltic Surface Milling for these locations. Why is this quantity included in Common? Please clarify this scope of work. | The work was mistakenly doubled up and included in both Removing Asphaltic Surface Milling and Common Excavation bid items. An addendum will be issued to clarify the work and adjust quantities as needed. | Mike Coleman | 4 | 2026-07-22 10:50 | 2026-07-28 06:34