## qandasearchletting_results
Date | 2026-09-11
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260915 | 20260915001 | 1 | Conflict with overhead power lines... | On Structure B-56-257, the power lines on the north side of the project cross Rott Road are closer than they appear in the plan- roughly 80' from the end of the existing bridge. . Since the road is a dead end, all pile driving will need to be conducted from the north side, and after performing excavation for the north abutment, the crane will have less than 40' to pick up and lay down a pile driver (80' long). De-energizing would not adequate in this situation. There needs to be more room to properly pick up and lay down a hammer. Can this power line be shifted further north, or taken down during construction? | The Contractor shall review the Special Provisions, (Section 5: Utilities): VERNON ELECTRIC COOPERATIVE â€œExisting pole structures will remain in place and are not in conflict. The utility will de-energize and remove the line (two spans) from Station 1+00, 20â€™ LT to Station 6+00, 38â€™ RT temporarily to allow for the structure construction. The line will be replaced after construction. | Mike Coleman | 1 | 2026-08-28 13:51 | 2026-08-31 08:50
20260915 | 20260915001 | 1 | Geotech Report | Can the WODT provide the geotechnical report for this project? | The geotechnical report(s) can be found at the following location: https://wisdot.box.com/s/rebp7sbx7fjqzbhmiqhr8j6odh7oervl or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-09-04 08:23 | 2026-09-08 12:38
20260915 | 20260915001 | 1 | Design Schedule | Can the design schedule be posted, in particular for project 5738-00-74? The 60 C.D. work restriction seems difficult to meet with the project requiring a temp bypass and pre-bored piling and any lost weather/flooding days. | The design schedule can be found at the following location: https://wisdot.box.com/s/rebp7sbx7fjqzbhmiqhr8j6odh7oervl or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2026-09-08 11:37 | 2026-09-08 13:04
20260915 | 20260915002 | 2 | Concrete Masonry Qty | Please review the quantity of Concrete Masonry for the project, in particular the superstructure quantity. Plan quantity appears to be inaccurate. | An addendum will be issued to correct this. | Mike Coleman | 1 | 2026-08-13 13:50 | 2026-08-19 08:37
20260915 | 20260915002 | 2 | Geotechnical Report | We are requesting the geotechnical report for this project | The geotechnical report(s) can be found at the following location: https://wisdot.box.com/s/6thcyh8z45eheyrfs02s2y2ea65ppnwn or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-09-04 08:24 | 2026-09-08 12:33
20260915 | 20260915002 | 2 | Preboring and Piling Quantity | Please verify these quantities as the prebore quantity and piling quantity for the west abutment and pier should not theoretically be the same footage. |  |  | 3 | 2026-09-11 13:07
20260915 | 20260915003 | 3 | Sign Post Bases | Will the project allow a substitution of the appropriate style of V-LOC bases in lieu of the SPV for precast bases and bases for concrete installation? | V-LOC bases will not be accepted. Sign posts will need to use the Precast Sign Post Base item. | Mike Coleman | 1 | 2026-08-27 11:00 | 2026-08-28 06:23
20260915 | 20260915003 | 3 | Geotechnical Exploration Report | Can the geotechnical report (including soil boring information) be made available? | The geotechnical report(s) can be found at the following location: https://wisdot.box.com/s/m8zkl8fnpkubxx4tciiom7ja286p8v80 or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-09-09 15:16 | 2026-09-10 11:27
20260915 | 20260915007 | 7 | Plans and Specifications | On both sets of plan sheets there is a note stating to "Place HMA pavement when the adjacent, previously placed pavement, is 200 degrees Fahrenheit or greater by paving in echelon lanes 2 and 3/ shoulder." This is not stated anywhere inside the project specification though. Will echelon paving of lanes 2/3 and the outside shoulder be required for both plan sets? | Yes, echelon paving of Lanes 2 and 3/shoulder is required. The requirement does not need to be repeated in the special provisions or specifications per 105.4 of the standard spec and guidance in the FDM. | Mike Coleman | 1 | 2026-09-01 14:06 | 2026-09-04 05:47
20260915 | 20260915007 | 7 | Special 03. Reseal Crushed Aggregate Slope Paving Special | The current proposal specifications under Sections B.1 and B.2 appear to be based on the previously specified non-UV-resistant epoxy coating. Specifically, the listed minimum requirements, including the ASTM C881/AASHTO M235 requirements, water absorption values, and viscosity requirement of 2,500 cps, appear to correspond to the former non-UV epoxy product. Section B.1 now states that the epoxy resin binder shall be UV-resistant (aliphatic or cycloaliphatic curing system) and suitable for exterior exposure without a topcoat. However, the remaining specifications and minimum requirements do not appear to have been revised to correspond with a UV-resistant epoxy system. Since the DOT intends to allow/use the new UV-resistant coating, please confirm whether the project specifications will be revised to remove or modify the requirements that apply specifically to the former non-UV epoxy coating and establish appropriate requirements for the UV-resistant epoxy system. Please clarify how bidders should proceed, as the current specifications appear to conflict with the stated requirement for a UV-resistant coating. | An addendum revising the special provision will be submitted to address the contradicting information. | Mike Coleman | 2 | 2026-09-04 08:44 | 2026-09-10 15:00
20260915 | 20260915007 | 7 | Design Schedule | Please provide the design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/bgic22tziob90b5hj0lfi5kr7k6oxm1w or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2026-09-09 17:54 | 2026-09-11 06:57
20260915 | 20260915007 | 7 | 531.5310 Foundation Single-Shaft Type TC-I (structure) 05 S-40-3124 | Can you tell me where to find the SDD for this type of sign structure base? I have looked in SDD, the bridge manual and the plans and cannot find anything with this designation. |  |  | 4 | 2026-09-10 17:24
20260915 | 20260915007 | 7 | Asphalt Paving | Would the Department consider placing a 5 MT 58-28 S in the binder to significantly reduce project costs? |  |  | 5 | 2026-09-11 09:31
20260915 | 20260915008 | 8 | Special Provisions | The Specials provided in the proposal seem to be for a different project. Can the department please verify? | Please clear the cache in your browser and re-download. The special provisions in the proposal are for the correct project. | Mike Coleman | 1 | 2026-08-12 12:07 | 2026-08-13 13:33
20260915 | 20260915008 | 8 | Geotechnical Data | Please provide any geotechnical data available for this project area. | The geotechnical report(s) can be found at the following location: https://wisdot.box.com/s/5mtlhe9tuxqa9uox9j0v6dm37o8b2cqf or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-08-25 08:43 | 2026-08-25 10:23
20260915 | 20260915008 | 8 | Project Schedule | Please provide the engineer's project schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/5mtlhe9tuxqa9uox9j0v6dm37o8b2cqf or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2026-08-25 08:44 | 2026-08-25 12:33
20260915 | 20260915008 | 8 | Bid Item 374 - Temporary Pedestrian Surface Asphalt Locations | The drawings do not show a specific location for temporary pedestrian surface asphalt. The miscellaneous quantities sheets show 1,297 SF to be installed in Stage 1A. The traffic control plan for Stage 1A (sheet 295) shows "ASPHALTIC SURFACE TEMPORARY CONSTRUCTED THIS STAGE". Is the temporary asphalt shown on this sheet the temporary pedestrian surface asphalt shown in the miscellaneous quantities? Will this temporary asphalt be paid by SF installed under bid item 374? Or will this be paid by TN installed under bid item 94? | The Asphaltic Surface Temporary callouts at the path for Stage 1A on page 295 should be Temporary Pedestrian Surface Asphalt. Additionally, there is a revision in the quantity of Temporary Pedestrian Surface Asphalt. These changes will be included in an addendum. | Mike Coleman | 4 | 2026-09-02 11:01 | 2026-09-04 05:42
20260915 | 20260915008 | 8 | SPECIAL 104-106 FURNISH & INSTALL VIDEO DETECTION SYSTEMS | We see that Autoscope is spec'd specifically for this work, but we know that the county has recently purchased NoTraffic equipment. We are asking if NoTraffic would be accepted as an acceptable alternative detection system for this bid? | Please bid the project with the specified Autoscope video detection system. | Mike Coleman | 5 | 2026-09-04 16:08 | 2026-09-10 05:59
20260915 | 20260915008 | 8 | SPECIAL 107-109 TRAFFIC SIGNAL CONTROLLER AND CABINETS | We see that within this provision that an Econolite Cobalt controller is specifically listed as the controller to use with this cabinet. We know that the county has a handful of McCain traffic controllers. We are asking if a McCain traffic controller would be an acceptable alternative controller for this bid? | Please bid the project with the specified Econolite Cobalt controller. | Mike Coleman | 6 | 2026-09-04 16:09 | 2026-09-10 06:00
20260915 | 20260915008 | 8 | SPECIAL 503 FURNISH & INSTALL EVP SYSTEM WITH CONFIRMATION LIGHTS CTH O & RIDGE RD | We see that GTT equipment is specifically listed for this intersection's EVP equipment, which requires additional hardware to provide confirmation beacons. We know that the county has a handful of sites with Tomar EVP equipment installed and has an integrated confirmation beacon and only requires a single cable pulled to each detector for full operation. We are asking if Tomar would be an acceptable alternative EVP system for this bid? | Please bid the project with the specified GTT equipment for the EVP system. | Mike Coleman | 7 | 2026-09-04 16:10 | 2026-09-10 06:01
20260915 | 20260915008 | 8 | Temp Traffic Signals | Will the Department permit the contractor to begin installation of temp signals prior to April 1st 2027? | Installation of temporary signals prior to April 1,, 2027 is permitted. See the first paragraph under Work Restrictions in the Prosecution and Progress article on page 4 of 86 of the special provisions. | Mike Coleman | 8 | 2026-09-08 13:48 | 2026-09-09 08:26
20260915 | 20260915008 | 8 | Article 17 of The special provisions - Pavement Breaking Equipment | Per Article 17 of the SPV's it States " do not use guillotine, drop hammer, Falling weight, gravity impact breakers or equivalent equipment within 300 feet of any structure." Can the Department please define "Structure" and the intent of this specification to the contract. |  |  | 9 | 2026-09-10 15:35
20260915 | 20260915008 | 8 | Utility Relocations and Anticipated Construction Start Date | Can WisDOT confirm that that of all the utility relocations listed in the special provisions that are to be relocated prior to construction, will physically be relocated so the contractor can plan operations for this project to begin on 4/1/27 (weather pending of course). |  |  | 10 | 2026-09-11 13:21
20260915 | 20260915009 | 9 | GFRP Rebar Size | Plan calls out a #6 GFRP rebar size at some locations. The manufacturer is telling us they only produce #3-4-5 rods. Can this #6 size be changed to #5? According to them a fiberglass #5 is equal to a #6 rebar. | The availability of #6 GFRP rebar was confirmed through a search of manufacturers and suppliers. #6 GFRP substitutions will not be allowed.The availability of #6 GFRP rebar was confirmed through a search of manufacturers and suppliers. #6 GFRP substitutions will not be allowed. | Mike Coleman | 1 | 2026-09-08 15:19 | 2026-09-10 06:13
20260915 | 20260915010 | 10 | Solar Flashing Beacon | Q1. Wisconsin DOT doesn't publish a minimum solar panel or battery size for these beacons, but neighboring Minnesota DOT requires at least a 50 watt panel and a 95 amp-hour battery for the same equipment. What minimum panel and battery size will this project require? Q2. Is this beacon supposed to flash 24/7, or only on a schedule? If it's on a schedule, what hours? Q3. How many days does the solar system need to keep running if the panel gets no sun, like when it's covered in snow for a stretch? Florida DOT requires 10 days for solar beacons, so we want to know what this project requires. Q4. Will each bidder have to put in writing what size solar panel and battery they are quoting, and what winter conditions they sized it for? Q5. Does the beacon run at full brightness during daylight hours? And is it ever allowed to dim itself to save battery, day or night? |  |  | 1 | 2026-09-10 13:01
20260915 | 20260915011 | 11 | Tree Clearing Clarification | The Clearing & Grubbing general specification does not clearly define what is clearing vs grubbing. For the purpose of this project will the contractor be required to remove and dispose of vegetation under 3" DBH? |  |  | 1 | 2026-09-09 15:48
20260915 | 20260915012 | 12 | Designers Construction Schedule | Can the department provided the designers construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/n5k5uyb86rd5x2nh9uq8ckovz0w5gh7r or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-08-28 07:47 | 2026-09-01 07:35
20260915 | 20260915012 | 12 | 3 MT/ 4 MT HMA Quantity | The typical section for the SB lanes of STH 57 show 2 lifts of 4 MT 58-28 S but the bid quantities and miscellaneous quantities figure 3 MT 58-28 S for the lower lift. Can the department clarify which is correct? | The typical sections are correct. The bid quantities and miscellaneous quantities will be updated via addendum. | Mike Coleman | 2 | 2026-09-01 14:46 | 2026-09-04 05:40
20260915 | 20260915012 | 12 | Intersections & Median Intersections Paving Details | There does not appear to be a detail for what is to be paved on the intersections or median x-overs. Can the department clarify what they are expecting and how the lower lift or wedge lift would be paid? 4 MT or 3 MT? | A table clarifying milling depths, pavement thicknesses and HMA types at sideroad intersections and medians will be added to plans via addendum. | Mike Coleman | 3 | 2026-09-01 15:05 | 2026-09-04 05:43
20260915 | 20260915012 | 12 | Excavation at beam guard replacement areas | Is the intention at the beam guard replacement sections to excavate the shoulder fully, as shown in the cross sections? The detail on page 11 shows base agg dense 1.25 below the shoulder. If the shoulder is fully excavated, is the base agg paid under the base agg dense 1.25 line item? MQs do not show any base agg dense quantitity for these areas? |  |  | 4 | 2026-09-11 12:28
20260915 | 20260915013 | 13 | Turtle fence | In the turtle exclusion fence does the drain tile need to be DOT certified? | No, there are no material requirements listed for the item in the specials. This is a temporary item. It does not need to be a draintile but fulfill the same function to what is shown in the standard detail. | Mike Coleman | 1 | 2026-08-29 16:02 | 2026-08-31 10:19
20260915 | 20260915013 | 13 | Interi Completion - SItes 12 & 13 | The section for the interim completion for Sites 12 & 14 lists March 4 in the header but mentions March 14 in the body. Please advise |  |  | 2 | 2026-09-09 15:27
20260915 | 20260915013 | 13 | Tree Clearing Requirements | The Clearing & Grubbing general specification does not clearly define what is clearing vs grubbing. For the purpose of this project will the contractor be required to remove and dispose of vegetation under 3" DBH? |  |  | 3 | 2026-09-09 15:48
20260915 | 20260915014 | 14 | Traffic Control | Can the Department provide a detour for culvert replacement work for a reasonable duration? This would significantly reduce the cost of several items as well as protect the travelling public/construction staff. | A detour route will not be provided for this project and should be bid accordingly. | Mike Coleman | 1 | 2026-09-01 14:22 | 2026-09-04 05:44
20260915 | 20260915014 | 14 | Construction Schedule | Can the Department provide their construction schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/vzafacagnbwyz8qe2bm1el2mbevvdekb or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-09-02 11:56 | 2026-09-04 05:52
20260915 | 20260915014 | 14 | Asphaltic Surface Quantity | Miscellaneous Quantities shows removing and replacing 627 LF of Curb & Gutter as well as removing the asphalt surface in those areas. On sheet 19 of the construction details it shows asphaltic surface being placed to match existing. The asphaltic surface in the miscellaneous quantities for asphaltic surface does not account for this tonnage. Can the Department add that tonnage? | The quantities for Asphaltic Surface, common excavation and Curb and Gutter Removal have been reviewed. The quantities will be updated to match plan needs. These updates will be included with the upcoming addendum that will address adding the removing concrete pavement item. | Mike Coleman | 3 | 2026-09-02 12:04 | 2026-09-04 05:46
20260915 | 20260915014 | 14 | Geotechnical Data | Please provide any geotechnical data available for this project area. | There was no geotechnical data gathered during the design of this project. | Mike Coleman | 4 | 2026-09-02 12:36 | 2026-09-04 05:41
20260915 | 20260915014 | 14 | Removing Concrete Pavement | Concrete pavement is located at most of the culvert replacement locations according to the existing typical sections. Is a removing concrete pavement bid item going to be added as part of an addendum? | The design team has reviewed this question and will generate an addendum to add the removing concrete bid item. | Mike Coleman | 5 | 2026-09-02 13:27 | 2026-09-04 05:40
20260915 | 20260915014 | 14 | Preparing Foundation for Asphaltic Paving | With the culvert patches and curb patching on this project, would the Department add a Prepare Foundation for Asphaltic Paving item? | The design team has reviewed this question and determined that with sideroad culverts being installed by others outside of our contract and left as a base aggregate surface, we should include the Prep Foundation for Asphaltic Paving bid item. This inclusion will be part of the upcoming addendum. | Mike Coleman | 6 | 2026-09-03 16:39 | 2026-09-08 08:35
20260915 | 20260915014 | 14 | Schedule - Working Days | The contractor has reviewed the plans and quantities. The contractor is asking for 9 additional working days to be added to the contract for pipes, shoulder widening, distressed milling, PWL HMA paving, ï¿½â€ shoulder and the grooved striping. | The design team has reviewed the request and time chart. It has been determined that an additional 5 working days is warranted for the contract. This additional time and new time chart will be part of Addendum #1 that will be sent in for distribution today. | Mike Coleman | 7 | 2026-09-09 04:24 | 2026-09-10 06:02
20260915 | 20260915015 | 15 | Climbing Turtle Exclusion Fence | This fence is not sediment control fence. The General Note on page 15 states it is being used for both silt fence and climbing turtle exclusion fence and dictating means and methods for installation. Both silt fence and climbing turtle exclusion fence are allowed to be installed separately per article 22 of the specials. If the contractor elects to install both on the same posts, that is an optional alternative. However, both items should be quantified in the plan to allow for separate installations of these items. Will DOT include a separate item for silt fence for sediment control to allow the bid items to be installed and measured separately? | Silt fence and silt fence maintenance items will be added via Addendum #1. | Mike Coleman | 1 | 2026-08-28 09:28 | 2026-09-01 07:27
20260915 | 20260915015 | 15 | Water | Please consider adding a bid item for Water. | Water item will be added via Addendum #1. | Mike Coleman | 2 | 2026-08-31 09:48 | 2026-09-01 07:28
20260915 | 20260915015 | 15 | 12" items | Could you please review all of the 12" Culvert items on this job. The quantities page 83 shows poly coated steel, and the plan pages 33 and 37 show polyethylene pipe? Also is item 80 supposed to be 18" RCP? I only see two 12" ends needed and four listed and no item for 18" RCP? | Page 83 should indicate Item 530.0112 Culvert Pipe Corrugated Polyethylene 12-Inch NOT item 521.5112 Culvert Pipe Corrugated Steel Polymer Coated 12-inch. Callout on sheets 33 and 37 of the plans is correct. Item 80 is not needed, item 82 Apron Endwalls for Culvert Pipe Steel 12-inch is the required item at structures on sheets 33 and 37. All 18-inch RCP apron endwalls and pipe are under their respective salvaged bid items. The necessary bid item changes noted above will be revised via Addendum #1. | Mike Coleman | 3 | 2026-09-01 15:32 | 2026-09-02 10:37
20260915 | 20260915015 | 15 | Borrow | Please review and clarify the Borrow Item. The remarks on page 86 seem to imply salvaging and reusing aggregate shoulder material. Shouldn't this be considered Excavation Common? | Note Clarification: â€œPlace borrow from aggregate shoulder â€œpointâ€ to match existing median at 6:1 or flatter slopeâ€ Intent: Borrow item used to grade from final condition aggregate shoulder edge to existing ground (6:1 or flatter) where existing and temporary shoulder is being removed and replaced. | Mike Coleman | 4 | 2026-09-02 13:15 | 2026-09-04 05:46
20260915 | 20260915016 | 16 | Design Schedule | Can the department please provide the design schedule for the project | The design schedule can be found at the following location: https://wisdot.box.com/s/a2kmjkl9bmlfryx68stne86buojxulge or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-08-25 07:08 | 2026-08-25 10:19
20260915 | 20260915016 | 16 | Schedule | Putting a schedule together with a start date of the middle of April, as the DOT's schedule shows, we are going 1 week beyond the completion date. We don't feel the DOT schedule is representative for operations starting with the SMA paving til the end of the job, as it shows too many work items going on at one time for the entire month of August with being able to satisfy the Special Provisions of 6 mile max length closures and a 2 mile gap inbetween. Would the department consider breaking the closures to halves instead of thirds once the milling and paving starts? or when the job is in the last segment of milling and paving being able to combine one other section to be able to get the finishing work of shoulders, paint, rumbles done and then take that additional section down? | The design team has reviewed the subject question and feel some additional time should be added to the contract. We are preparing an addendum for processing this change. It will be sent in for processing as soon as possible. | Mike Coleman | 2 | 2026-09-09 15:53 | 2026-09-10 11:32
20260915 | 20260915017 | 17 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/m3xd3wxe18plvbt4dtmggkyansf65kho or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-08-19 12:29 | 2026-08-20 13:36
20260915 | 20260915018 | 18 | Two foot asphalt widening | The asphalt in the shoulder widening in the mill and overlay sections shows as 4MT mix. With only 518 tons that might have to be done on multiple days, and not being able to be density tested, could this mix be classified as asphaltic surface? | Yes, the shoulder widening mix will changed to asphaltic surface. An addendum will be issued. | Mike Coleman | 1 | 2026-08-21 12:30 | 2026-08-25 10:20
20260915 | 20260915018 | 18 | Geotechnical Report | Can the Geotech report be provided for this project? | The geotechnical report(s) can be found at the following location: https://wisdot.box.com/s/i35ze8aurjjhhqj59mvkv9xumabt06o0 or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-08-27 10:37 | 2026-08-31 07:29
20260915 | 20260915019 | 19 | Special 29 | The construction staking special talks about determining existing curb grades but there isn't any curb staking item for this project? | The Department does not typically provide separate payment for curb & gutter staking on projects with less than 50 feet of proposed curb & gutter. For this project, the effort required to stake the curb & gutter is considered incidental to Construction Staking Supplemental Control, Item 650.9911. | Mike Coleman | 1 | 2026-08-18 14:10 | 2026-08-21 06:02
20260915 | 20260915019 | 19 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/3b34fzvcbgv253xfhl161vb69n2f62qo or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-08-19 12:31 | 2026-08-20 13:40
20260915 | 20260915019 | 19 | Special Provision #21 | Can the department please clarify what special provision #21 QMP Pavement Nuclear Density is being used for? It is not shown in the mixture use table. | QMP HMA Pavement Nuclear Density and the associated incentive is not needed for this project. The article will be removed via addendum. | Mike Coleman | 3 | 2026-08-28 07:47 | 2026-09-02 05:59
20260915 | 20260915019 | 19 | Guardrail Widening HMA | Can the department change the guardrail paving from station 190+95 to 192+12 LT to asphaltic surface? | The lower layer of the guardrail widening will be changed to Asphaltic Surface. The upper layer will remain HMA pavement. An addendum will be issued to reflect this change. | Mike Coleman | 4 | 2026-08-31 18:17 | 2026-09-09 07:27
20260915 | 20260915019 | 19 | Additional Working Days | Based on the depth and length of the culvert pipe replacements and the requirement to pave them in before the weekend, thus allowing the pipe contractor only 3 to 3.5 days a week to work so fine grading and paving can happen by weeks end (Per the Specials), can the department add 10 working days to the contract? | The Department believes the number of working days is adequate. No additional working days will be added. | Mike Coleman | 5 | 2026-09-04 16:34 | 2026-09-08 13:01
20260915 | 20260915021 | 21 | Design Schedule | Can the construction design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/jeadf0ji46cr58oigkt5phdu8f375gwl or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-08-30 06:18 | 2026-09-01 07:30
20260915 | 20260915021 | 21 | Paving | #1 The existing asphalt is 4" - 5" thick according to the typical sections. The contractor is scheduled to take off 1" for 90% of the project. Could the specials be changed to allow the 96hour rule for the milled surfaces? #2 Per sheet #11, the item for distressed milling does not have a quantity for the Asphalt Patching to correspond with the milling. |  |  | 2 | 2026-09-10 14:10
20260915 | 20260915022 | 22 | RR Xing Work | Can the department define the extent of the work that the Railroad will self-perform at the two crossings? Also, will the railroad be closing these crossings, and if they are, for how long? Lastly, is there a proposed timeframe for the railroad to perform their work on these crossings? | The extent of the work by the railroad is to place the crossing surface material between and adjacent the railroad tracks in the 2 locations. No closures are expected to complete this work. The railroad is scheduled to complete their work at these 2 crossings this fall although no date has been provided by the railroad. | Mike Coleman | 1 | 2026-08-24 13:51 | 2026-08-26 07:12
20260915 | 20260915023 | 23 | Staging | Can stages 1-3 and 4-5 be worked on at the same time. Work on both STH 13 and STH 80 concurrently if desired? | We have reviewed the question below and determined that stages 1-3 and 4-5 can be worked on at the same time if desired. | Mike Coleman | 1 | 2026-09-09 16:20 | 2026-09-10 11:34
20260915 | 20260915024 | 24 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/96pstpihj1lil0tgjl5t6s7olwg4hzsv or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-08-19 12:27 | 2026-08-20 13:47
20260915 | 20260915024 | 24 | Pavement Curing Time | Is it the intention of the department to stop charging working days while the new pavement is curing prior to installing the HFST? | Working days will continue to be charged during new pavement curing time. Refer to Contract Time for Completion that was published as Supplemental Information as part of the Question and Answer process. | Mike Coleman | 2 | 2026-08-31 18:32 | 2026-09-02 06:17
20260915 | 20260915025 | 25 | Pier construction joint | Could consideration be made to change the location of the designed construction joint in the pier? Currently the pier has a vertical construction joint directly inline with the construction joint of the deck. This will be problematic in installing/extracting steel sheets for the cofferdam in stage 2 as the sheets will need to tie into the newly constructed pier in stage 1. By moving the pier construction joint to outside of the edge of deck (stage 1), we would be able to install and extract these sheets without conflict from the stage 1 superstructure. Moving the construction joint would result in changes to the rebar design, so it would need to be addressed pre-bid/construction. | The pier construction joint shall remain as shown in the plans. The joint location was established as part of the pier design and staging considerations, and it is not uncommon for the pier and deck construction joints to be located along the same stage line. The piles are efficiently utilized under the current configuration, and shifting the joint would increase the Stage 1 loading and require the pier and foundation design to be reevaluated. | Mike Coleman | 1 | 2026-08-19 11:08 | 2026-08-20 13:49
20260915 | 20260915025 | 25 | Geotechnical Report | Can the geotechnical report be provided for this project? | The geotechnical report(s) can be found at the following location: https://wisdot.box.com/s/opirvxap88yd3cc7oo74z79glv9in9bl or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-08-25 11:42 | 2026-08-26 07:11
20260915 | 20260915025 | 25 | Structure Construction Joints | Would the Department consider adding rebar couplers to structure B-34-61 at the locations of the stage 1 and stage 2 construction joint? The current details indicate that the rebar is to extend through the stage line. There will be limited space at the stage line due to the location of the existing structure and shoring that will be required. | Yes. If the Contractor elects to use bar couplers, the Contractor shall adjust the reinforcing bar lengths shown on the plans as necessary and provide the couplers in accordance with the applicable WisDOT Standard Specifications. | Mike Coleman | 3 | 2026-08-28 07:11 | 2026-08-31 07:30
20260915 | 20260915025 | 25 | Structure Staged Joint | At structure B-34-61, will the Department be adding a pay item for any temporary support of the overhang from the stage one construction? | No. Falsework and forming needs are covered in section 502 of the WisDOT Standard Specifications. | Mike Coleman | 4 | 2026-08-28 07:11 | 2026-08-31 07:31
20260915 | 20260915025 | 25 | Temporary Barrier Wall | In the traffic control section for the temporary bypass temporary barrier wall is shown to be installed and anchored on shoulder gravel. Per the standard detail, this is not allowable. Temporary barrier must be placed on a paved surface. | Yes. Temporary pavement is to be installed to anchor the temporary barrier on the shoulder. The temporary pavement should be removed in Stage 3 and replaced with the gravel shoulder. An addendum will be issued to address the revision. | Mike Coleman | 5 | 2026-08-28 07:12 | 2026-09-02 06:28
20260915 | 20260915025 | 25 | Schedule | Can the Department please provide the design schedule that they used to determine the timeframe for completion of this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/opirvxap88yd3cc7oo74z79glv9in9bl or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2026-08-28 07:12 | 2026-08-31 07:26
20260915 | 20260915025 | 25 | Tree Clearing and Bird Netting | Since tree clearing and bird netting will need to take place prior to 4/15, and no instream disturbances are allowed prior to 6/15, will the Department allow the bird netting and tree clearing to take place without charging working days against the contract? | Yes. This effort could be completed with a conditional start with no working days charged. | Mike Coleman | 7 | 2026-08-28 07:39 | 2026-08-31 07:32
20260915 | 20260915025 | 25 | Polymer Overlay | Will construction be allowed to switch to stage 2 without the application of the polymer overlay on the stage one portion of structure B-34-61? There is a minimum 28-day period after concrete placement that the polymer overlay can not be applied. | Yes. Construction can switch to Stage 2 without the polymer overlay. | Mike Coleman | 8 | 2026-08-28 08:43 | 2026-08-31 07:33
20260915 | 20260915025 | 25 | Structure B-34-024 Staging | Please clarify the traffic control requirements for structure B-34-024. Section 3 of the special provisions states to close STH 64 to thru traffic for 35 working days to complete the work. However, Section 5 of the special provisions states to complete the B-34-024 work under staged construction utilizing single lane closures. | Section 3 of the special provisions to be revised to state that work is to have staged construction utilizing single lane closures. | Mike Coleman | 9 | 2026-08-31 15:20 | 2026-09-03 07:21
20260915 | 20260915025 | 25 | Contract Schedule | The contract completion timeline of 75 working days is not adequate. The design construction schedule is missing several major items such as cofferdams, structure backfill & riprap, temporary barrier block and crash cushions, as well as non-paid items that will consume considerable amounts of contract time such as construction access and traffic control switches. Please reconsider the amount of contract time allocated to this project. At a minimum this looks like a 95 working day project given the scope of work, staging, working alongside live traffic, and challenging construction access limitations. This is not a high efficiency project. | After review of critical tasks and operations, the contract completion timeframe is revised to have a start date of June 1, 2027, with 90 working days. | Mike Coleman | 10 | 2026-08-31 15:43 | 2026-09-03 07:45
20260915 | 20260915025 | 25 | Timber Rub Rail | The fastener called out is A325 anchored into concrete for the timber rub rail. F1554 are more typical can and F1554 bolt be substituted for the A325 bolt? | Yes. The ASTM F1554 anchor can be substituted for the A325 in the timber rail anchorage to the concrete parapets. | Mike Coleman | 11 | 2026-09-09 17:48 | 2026-09-10 15:03
20260915 | 20260915028 | 28 | Asbestos Report | Can you please provide the asbestos report for structure B-27-0026 | The asbestos report can be found at the following location: https://wisdot.box.com/s/8j661cy707tjm16fhee74mog2hgd50df or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-08-31 10:41 | 2026-09-01 07:23
20260915 | 20260915029 | 29 | Asbestos Report | Can you please provide the asbestos report Structure B-27-53 | The asbestos report can be found at the following location: https://wisdot.box.com/s/b99ktu46qh6ea51xbrbt38b7xu6oq9u2 or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-08-31 10:40 | 2026-09-01 07:25
20260915 | 20260915029 | 29 | Off-Peak Lane Closure Temp Tape | The specs say "No lane closures shall remain in place outside the allowable closure periods", though the plans for the lane closure show temporary markings and removals. Will the tape need to be removed and re-applied during peak and off-peak hours? Additionally, how many set/removals are anticipated for the lane closure? |  |  | 2 | 2026-09-10 15:59
20260915 | 20260915030 | 30 | Asbestos Report | Can you please provide the asbestos report for Structure B-9-32? | The asbestos report can be found at the following location: https://wisdot.box.com/s/tqsn9bl0ghlk5nvq98q68tt4v85njy85 or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-09-09 11:56 | 2026-09-10 06:55
20260915 | 20260915030 | 30 | Prosecution and Progress | Please provide the anticipated design schedule for the project. Based on our review, there does not appear to be sufficient time to complete the work within the timeframe outlined in the Special Provisions when accounting for the restrictions associated with the school release period, music festivals, and holidays. Would the Department consider allowing the Contractor to perform work during the school year and/or during the scheduled music festivals? |  |  | 2 | 2026-09-10 12:17
20260915 | 20260915030 | 30 | Traffic Control | Will the Department consider allowing full closures of STH 29 EB and/or WB to accommodate bridge deck removal operations? Performing bridge deck removal directly over live traffic presents a significant safety risk to the traveling public. |  |  | 3 | 2026-09-10 12:24
20260915 | 20260915030 | 30 | Traffic Control Devices | Workers performing operations from manlifts and other equipment adjacent to live traffic should be provided positive protection from the traveling public. Please consider adding temporary precast concrete barrier and/or crash attenuator vehicles to provide protection for workers and equipment during these operations. Alternatively, please consider allowing full closures and detours of STH 29 EB and/or WB during bridge deck removal and formwork stripping operations to provide a safer work environment for both workers and the traveling public. |  |  | 4 | 2026-09-10 12:27
20260915 | 20260915030 | 30 | Debris Containment | Working over live traffic poses many risks. Is it assumed that a debris containment system will be needed and installed over the live lanes? If so, please add the item to the contract. |  |  | 5 | 2026-09-11 13:13
20260915 | 20260915031 | 31 | Prosecution and Progress - Project ID 1180-01-72 Paving Operations | Can the profile milling areas (Station 5318+40 to Station 5440+50) be changed to "do not place live traffic on a milled surface for longer than 96 hours"? | We have discussed this with the Region pavement designer and will change this to be the same requirement as the standard milling areas with 96 hours. We will be issuing an addendum. | Mike Coleman | 1 | 2026-09-01 11:14 | 2026-09-02 07:19
20260915 | 20260915031 | 31 | Soil Borings | Are there any soil borings for this project? | While there were not current borings completed, the Region assembled some soils information for each culvert to demonstrate suitability of materials. There are no soil borings for the resurfacing project. The soils information can be found at the following location: https://wisdot.box.com/s/mn92v10s2immqcudfzarcj62naxxbvtl or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-09-10 13:44 | 2026-09-11 08:42